## Sheet1
NCSX FY05 Contingency/Management Reserve Candidates
Risks
| 13. TF coil fabrication procurement | Procurement | 200 | 40% risk applied to planned FY05 expenditures
| 14. MC Winding Parts Fab. (at 40% of FY05 plan) | PPPL Labor | 166.8
| 14.TRC increase in fab time incl overtime (50% as long as budgeted) | PPPL Labor | 28.6
| 18. Field Period Assy MCturning fixture plus 100% risk | PPPL Labor | 322
| 12. 14. VVSA & MCWF contract changes (10%) incl preproduction casting | Procurement | 500
| 12.VV Final FDR (40%) | ORNL LABOR | 63.6
| 14.MC Winding TYPE C FDR and documentation (40%) | ORNL LABOR | 190.92
|  | Subtotal Risks = | 1471.92
Opportunities
| 12. VV insulation | Procurement | 109.26 | Can start on VV field period assy earlier
| 12 VV heating/cooling | Procurement | 318 | Can start on VV field period assy earlier
| 18. Vac Vsl Prep (pre-assy) supports & platforms plus 100% increase risk | Procurement | 52 | Can start on VV field period assy earlier
| 31. Magnetic sensors material procurement | Procurement | 39.29 | Can start on VV field period assy earlier
| 31. Magnetic sensors fab. | PPPL Labor | 65.6 | Can start on VV field period assy earlier
|  | sub-total = | 584.15
| 13. PF 1-3 Design acceleration | PPPL Labor | 88 | Provides flexibility for assigning staff and increases schedule margin
| 13. CPF1-3 wind at PPPL | Procurement | 600 | Provides flexibility for assigning staff and increases schedule margin
|  | sub-total = | 688
| 14. MC Winding Parts Fab. Accelerate | PPPL Labor | 205 | increases schedule margin by 3 mos.
| 15. Coil support structure | Procurement | 250
| 16. LN2 manifolds and leads design (ORNL) | Procurement | 418.053
| 17. Machine base procurement | Procurement | 283
| 4. Control & Protection procurements | Procurement | 168.99
| 17. Cryostat Design | PPPL Labor | 228.53
| 4. Electrical interlocks design | PPPL Labor | 213.547
| 4. Coil protection systems design | PPPL Labor | 258.649
|  | subtotal opportunities = | 3297.919
Descretionary Funds
|  | Project contingency= | 1200
|  | PPPL Management Reserve = | 1700
2900
Variable
| Schedule Variance for planned work (@ spi=.95) |  | -934