## Ordered by Divi (hidden)
| Impact | Probability | Likelihood | Technical | Schedule | 1,1 | 1,2 | 1,3 | 2,1 | 2,2 | 2,3 | 3,1 | 3,2 | 3,3 | Overall Grade |  | mm
Target
Additional A-E Design | 100 | 100% | V | M | S | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Additional A-E Design/Process Engr | 275 | 100% | V | M | S | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Additional Field Survey Cost | 270 | 100% | V | M | M | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Target | 2
Be Cost Increase | 250 | 75% | V | M | S | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Circulator Cost Inc | 80 | 75% | V | M | S | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Core Vessel Design Complexity | 400 | 100% | V | M | S | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Increased Hg Tgt Dsn & Fab | 1000 | 65% | V | M | S | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Integrated Mdrtr/Plug Config | 450 | 75% | V | M | S | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Integrated Mdrtr/Plug Config | 150 | 75% | V | M | S | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
N&S Analysis Support - ES&H | 255 | 50% | V | M | M | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Target | 2
Plug Design Complexity | 450 | 100% | V | M | S | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
Remaining Equipment Instln | 3800 | 50% | L | C | S | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | H | Target | 1
Remaining Steel Procurement | 2250 | 50% | L | C | S | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | H | Target | 1
Specialty Shield Blocks | 135 | 75% | L | C | S | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | H | Target | 1
Utility Handling Cart Proc. | 235 | 100% | V | M | S | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | Target | 1
3
3
Instruments | [16 empty] | 3
Installation cost | 219.857 | 20% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 219.857 | 0 | 0 | L | Instruments | 3
Addl. ES&H/engineering coverage | 595.2 | 75% | L | M | M | 0 | 0 | 0 | 595.2 | 0 | 0 | 0 | 0 | 0 | L | Instruments | 3
Cost increase for inserts | 381.782 | 75% | L | M | M | 0 | 0 | 0 | 381.782 | 0 | 0 | 0 | 0 | 0 | L | Instruments | 3
Installation cost | 182.485 | 20% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 182.485 | 0 | 0 | L | Instruments | 3
Installation cost | 209.205 | 20% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 209.205 | 0 | 0 | L | Instruments | 3
Instrument design | 70.164 | 10% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 70.164 | 0 | 0 | L | Instruments | 3
Instrument design | 22.517 | 10% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 22.517 | 0 | 0 | L | Instruments | 3
Instrument design | 15.218 | 10% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 15.218 | 0 | 0 | L | Instruments | 3
Instrument design | 57.5 | 0% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 57.5 | 0 | 0 | L | Instruments | 3
Instrument design | 59.74 | 10% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 59.74 | 0 | 0 | L | Instruments | 3
Labor for testing inserts | 126.636 | 75% | L | M | M | 0 | 0 | 0 | 126.636 | 0 | 0 | 0 | 0 | 0 | L | Instruments | 3
PCR IS02006 (explained in detail in August EAC Report) | 511.8 | 100% | L | M | M | 0 | 0 | 0 | 511.8 | 0 | 0 | 0 | 0 | 0 | L | Instruments | 3
PCR IS02006 (explained in detail in August EAC Report) | -511.834 | 100% | L | M | M | 0 | 0 | 0 | -511.834 | 0 | 0 | 0 | 0 | 0 | L | Instruments | 3
Reassignment of unallocated budget to cover additional costs | -751.178 | 75% | L | M | M | 0 | 0 | 0 | -751.178 | 0 | 0 | 0 | 0 | 0 | L | Instruments | 3
Shared component design | 252.996 | 10% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 252.996 | 0 | 0 | L | Instruments | 3
Value of admin. effort transferred to IDTs | -352.47 | 75% | L | M | M | 0 | 0 | 0 | -352.47 | 0 | 0 | 0 | 0 | 0 | L | Instruments | 3
3
Ring | [16 empty] | 3
2nd Magnet Measurement Station | 60 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | L | Ring | 3
ASAC Recommendations | 120 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | L | Ring | 3
Beam Tube extensions + flanges | 48 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | L | Ring | 3
Customs, special freight to ORNL | 72 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | L | Ring | 3
Diagnostics - magnet and video ASAC recommendation | 144 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | L | Ring | 3
Dipole Shimming | 144 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | L | Ring | 3
ECN's, Change Orders, Inspection and Repair of Components | 66.0433 | 75% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 66.0433 | 0 | 0 | L | Ring | 3
higher vendor cost 26S26 | 69.6457 | 75% | L | M | M | 0 | 0 | 0 | 69.6457 | 0 | 0 | 0 | 0 | 0 | L | Ring | 3
higher vendor cost 27CD30 | 43.2283 | 75% | L | M | M | 0 | 0 | 0 | 43.2283 | 0 | 0 | 0 | 0 | 0 | L | Ring | 3
higher vendor costs | 144 | 75% | L | M | M | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | L | Ring | 3
higher vendor costs for DC magnet | 36 | 50% | L | M | M | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | L | Ring | 3
higher vendor costs pulsed magnets | 72 | 50% | L | M | M | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | L | Ring | 3
Inner Box Shielding | 72 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | L | Ring | 3
Lo Mu Ferrite for Extraction Kicker testing | 30 | 100% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | L | Ring | 3
lower vender cost extraction power supply | -220 | 100% | L | M | M | 0 | 0 | 0 | -220 | 0 | 0 | 0 | 0 | 0 | L | Ring | 3
Quadrupole Shimming | 144 | 50% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | L | Ring | 3
vendor increase in Primary collimator cost | 72 | 75% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | L | Ring | 3
3
LANL | [16 empty] | 3
HVCM Delivery Schedule does not support the current IPS | 0 | 100% | L | S | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | LANL | 3
NC LLRF Delivery does not support the current IPS | 0 | 100% | L | S | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | LANL | 3
DTL Delivery Schedule does not support the current IPS | 0 | 100% | L | S | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | LANL | 3
3
3
JLAB | [16 empty] | 3
Vacuum failure | 350 | 3%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | L | JLAB | 3
FPC arc over, etc | 0 | 2%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | JLAB | 3
Low Gradient | 0 | 5%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | JLAB | 3
Low Q0 | 0 | 5%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | JLAB | 3
Vacuum failure | 400 | 3%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | L | JLAB | 3
FPC arc over, etc | 0 | 2%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | JLAB | 3
Low Gradient | 0 | 5%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | JLAB | 3
Low Q0 | 0 | 5%perCM | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | JLAB | 3
Rotating equipment failure | 0 | 75% | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | L | JLAB | 3
Maintaince & repair 1MW RF system | 150 | 100% | V | M | M | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | JLAB | 2
Cryomodule Procedure Upgrade | 300 | 100% | V | M | M | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | JLAB | 2
LLRF test support | 100 | 75% | U | M | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | L | JLAB | 3
3
3
3
Controls | [16 empty] | 3
PLC interface to FE for MPS | 100 | 100% | V | M | M | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Controls | 2
Fund former 1.10 Controls personnel (16 - 34 FTEs) | 3000 | 40% | U | C | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | M | Controls | 2
Additional stack monitoring | 50 | 100% | V | M | M | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Controls | 2
Additional PPS equip. to support DTL3 | 35 | 100% | V | M | M | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Controls | 2
PPS equip. missed during last ETC | 135 | 100% | V | M | M | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Controls | 2
New ODH estimate | 100 | 100% | V | M | M | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Controls | 2
3
ASD | [16 empty] | 3
HVCM technical issues | 200 | 25% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | L | ASD | 3
DTL recovery | 300 | 50% | U | M | M | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | L | ASD | 3
Insufficient operators as identified in ASAC mtg. | 2091 | 50% | L | C | S | 0 | 0 | 0 | 0 | 0 | 2091 | 0 | 0 | 0 | H | ASD | 1
3
PS | [16 empty] | 3
small lease | 380.281 | 100% | V | M | M | 380.281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | PS | 2
furniture | 1000 | 25% | U | S | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | L | PS | 3
Human Resources-Staff reductions postponed | 260 | 75% | L | M | M | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | L | PS | 3
Procurement-Staff reductions postponed | 1310.811 | 75% | L | S | M | 0 | 0 | 0 | 0 | 1310.811 | 0 | 0 | 0 | 0 | M | PS | 2
Project Controls / MIS- Staff reductions postponed / additional staff required | 1372.728 | 75% | L | S | M | 0 | 0 | 0 | 0 | 1372.728 | 0 | 0 | 0 | 0 | M | PS | 2
Information Technology- Potential to underrun $83,500 with CNMS charge out | -83.5 | 75% | L | M | M | 0 | 0 | 0 | -83.5 | 0 | 0 | 0 | 0 | 0 | L | PS | 3
Document Control System-Staff reductions postponed | 407.03 | 75% | L | M | M | 0 | 0 | 0 | 407.03 | 0 | 0 | 0 | 0 | 0 | L | PS | 3
ES&H- Revised Estimate/Potential reduction of 102,185 for CNMS chargeout | 1458.529 | 100% | V | S | S | 0 | 1458.529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H | PS | 1
3
Conventional Facilities | [16 empty] | 3
Un-awarded contracts are awarded higher than budget | 3400 | 0% | L | C | M | 0 | 0 | 0 | 0 | 0 | 3400 | 0 | 0 | 0 | H | Conventional Facilities | 1
5% change orders on un-awarded procurements | 170 | 0% | V | M | M | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | M | Conventional Facilities | 2
[6 empty] | 1945.281 | 4848.529 | 0 | 728.34 | 2683.539 | 11676 | 2561.7253 | 1850 | 3000 | 29293.4143
| Dollars by Classification | [13 empty] | 29293.4143
| Marginal | Significant | Critical
Very Likely | 1945.281 | 4848.529 | 0
Likely | 728.34 | 2683.539 | 11676
Unlikely | 2561.7253 | 1850 | 3000
Percentage by Classification
| Marginal | Significant | Critical
Very Likely | 6.641% | 16.55% | 0%
Likely | 2.486% | 9.161% | 39.86%
Unlikely | 8.745% | 6.315% | 10.24%
| High | Moderate | Low
Risks against contingency by category | 16524.529 | 7628.82 | 5140.0653
Available Contingency: Sep02 | 75511
5% on commitments and phase funded | 12353.35
Remaining Work (less commitments and phase funded) | 306713.35
10% on remaining work | 29310
Available Contingency | 33847.65
EAC Items | 7135
High Risk | 16524.529
Moderate Risk | 7628.82
Low Risk | 5140.0653
Forecasted Contingency balance after all risks considered | -2580.7643

## Ordered by grade (hidden)
Descrition | Cost Impact | STL Probability | Management Likelihood | Cost Impact | Technical Consequence | Schedule Consequence | Overall Risk | Subproject | sort
Un-awarded contracts are awarded higher than budget | 3400 | 0% | L | 3400 | C | M | H | Conventional Facilities | 1
Instrument design | 57.5 | 0% | U | 57.5 | M | M | L | Instruments | 3
5% change orders on un-awarded procurements | 170 | 0% | V | 170 | M | M | M | Conventional Facilities | 2
Instrument design | 70.164 | 10% | U | 70.164 | M | M | L | Instruments | 3
Instrument design | 22.517 | 10% | U | 22.517 | M | M | L | Instruments | 3
Instrument design | 15.218 | 10% | U | 15.218 | M | M | L | Instruments | 3
Instrument design | 59.74 | 10% | U | 59.74 | M | M | L | Instruments | 3
Shared component design | 252.996 | 10% | U | 252.996 | M | M | L | Instruments | 3
Installation cost | 219.857 | 20% | U | 219.857 | M | M | L | Instruments | 3
Installation cost | 182.485 | 20% | U | 182.485 | M | M | L | Instruments | 3
Installation cost | 209.205 | 20% | U | 209.205 | M | M | L | Instruments | 3
HVCM technical issues | 200 | 25% | U | 200 | M | M | L | ASD | 3
furniture | 1000 | 25% | U | 1000 | S | M | L | PS | 3
Fund former 1.10 Controls personnel (16 - 34 FTEs) | 3000 | 40% | U | 3000 | C | M | M | Controls | 2
Insufficient operators as identified in ASAC mtg. | 2091 | 50% | L | 2091 | C | S | H | ASD | 1
Remaining Equipment Instln | 3800 | 50% | L | 3800 | C | S | H | Target | 1
Remaining Steel Procurement | 2250 | 50% | L | 2250 | C | S | H | Target | 1
higher vendor costs for DC magnet | 36 | 50% | L | 36 | M | M | L | Ring | 3
higher vendor costs pulsed magnets | 72 | 50% | L | 72 | M | M | L | Ring | 3
DTL recovery | 300 | 50% | U | 300 | M | M | L | ASD | 3
Quadrupole Shimming | 144 | 50% | U | 144 | M | M | L | Ring | 3
N&S Analysis Support - ES&H | 255 | 50% | V | 255 | M | M | M | Target | 2
Increased Hg Tgt Dsn & Fab | 1000 | 65% | V | 1000 | M | S | H | Target | 1
Specialty Shield Blocks | 135 | 75% | L | 135 | C | S | H | Target | 1
Procurement-Staff reductions postponed | 1310.811 | 75% | L | 1310.811 | S | M | M | PS | 2
Project Controls / MIS- Staff reductions postponed / additional staff required | 1372.728 | 75% | L | 1372.728 | S | M | M | PS | 2
Addl. ES&H/engineering coverage | 595.2 | 75% | L | 595.2 | M | M | L | Instruments | 3
Cost increase for inserts | 381.782 | 75% | L | 381.782 | M | M | L | Instruments | 3
Labor for testing inserts | 126.636 | 75% | L | 126.636 | M | M | L | Instruments | 3
Reassignment of unallocated budget to cover additional costs | -751.178 | 75% | L | -751.178 | M | M | L | Instruments | 3
Value of admin. effort transferred to IDTs | -352.47 | 75% | L | -352.47 | M | M | L | Instruments | 3
Human Resources-Staff reductions postponed | 260 | 75% | L | 260 | M | M | L | PS | 3
Information Technology- Potential to underrun $83,500 with CNMS charge out | -83.5 | 75% | L | -83.5 | M | M | L | PS | 3
Document Control System-Staff reductions postponed | 407.03 | 75% | L | 407.03 | M | M | L | PS | 3
higher vendor cost 26S26 | 69.6457 | 75% | L | 69.6457 | M | M | L | Ring | 3
higher vendor cost 27CD30 | 43.2283 | 75% | L | 43.2283 | M | M | L | Ring | 3
higher vendor costs | 144 | 75% | L | 144 | M | M | L | Ring | 3
Rotating equipment failure | 0 | 75% | U | 0 | M | S | L | JLAB | 3
LLRF test support | 100 | 75% | U | 100 | M | S | L | JLAB | 3
ECN's, Change Orders, Inspection and Repair of Components | 66.0433 | 75% | U | 66.0433 | M | M | L | Ring | 3
vendor increase in Primary collimator cost | 72 | 75% | U | 72 | M | M | L | Ring | 3
Be Cost Increase | 250 | 75% | V | 250 | M | S | H | Target | 1
Circulator Cost Inc | 80 | 75% | V | 80 | M | S | H | Target | 1
Integrated Mdrtr/Plug Config | 450 | 75% | V | 450 | M | S | H | Target | 1
Integrated Mdrtr/Plug Config | 150 | 75% | V | 150 | M | S | H | Target | 1
PCR IS02006 (explained in detail in August EAC Report) | 511.8 | 100% | L | 511.8 | M | M | L | Instruments | 3
PCR IS02006 (explained in detail in August EAC Report) | -511.834 | 100% | L | -511.834 | M | M | L | Instruments | 3
HVCM Delivery Schedule does not support the current IPS | 0 | 100% | L | 0 | S | S | L | LANL | 3
NC LLRF Delivery does not support the current IPS | 0 | 100% | L | 0 | S | S | L | LANL | 3
DTL Delivery Schedule does not support the current IPS | 0 | 100% | L | 0 | S | S | L | LANL | 3
lower vender cost extraction power supply | -220 | 100% | L | -220 | M | M | L | Ring | 3
2nd Magnet Measurement Station | 60 | 100% | U | 60 | M | M | L | Ring | 3
ASAC Recommendations | 120 | 100% | U | 120 | M | M | L | Ring | 3
Beam Tube extensions + flanges | 48 | 100% | U | 48 | M | M | L | Ring | 3
Customs, special freight to ORNL | 72 | 100% | U | 72 | M | M | L | Ring | 3
Diagnostics - magnet and video ASAC recommendation | 144 | 100% | U | 144 | M | M | L | Ring | 3
Dipole Shimming | 144 | 100% | U | 144 | M | M | L | Ring | 3
Inner Box Shielding | 72 | 100% | U | 72 | M | M | L | Ring | 3
Lo Mu Ferrite for Extraction Kicker testing | 30 | 100% | U | 30 | M | M | L | Ring | 3
Utility Handling Cart Proc. | 235 | 100% | V | 235 | M | S | H | Target | 1
ES&H- Revised Estimate/Potential reduction of 102,185 for CNMS chargeout | 1458.529 | 100% | V | 1458.529 | S | S | H | PS | 1
Additional A-E Design | 100 | 100% | V | 100 | M | S | H | Target | 1
Additional A-E Design/Process Engr | 275 | 100% | V | 275 | M | S | H | Target | 1
Core Vessel Design Complexity | 400 | 100% | V | 400 | M | S | H | Target | 1
Plug Design Complexity | 450 | 100% | V | 450 | M | S | H | Target | 1
PLC interface to FE for MPS | 100 | 100% | V | 100 | M | M | M | Controls | 2
Additional stack monitoring | 50 | 100% | V | 50 | M | M | M | Controls | 2
Additional PPS equip. to support DTL3 | 35 | 100% | V | 35 | M | M | M | Controls | 2
PPS equip. missed during last ETC | 135 | 100% | V | 135 | M | M | M | Controls | 2
New ODH estimate | 100 | 100% | V | 100 | M | M | M | Controls | 2
Maintaince & repair 1MW RF system | 150 | 100% | V | 150 | M | M | M | JLAB | 2
Cryomodule Procedure Upgrade | 300 | 100% | V | 300 | M | M | M | JLAB | 2
small lease | 380.281 | 100% | V | 380.281 | M | M | M | PS | 2
Additional Field Survey Cost | 270 | 100% | V | 270 | M | M | M | Target | 2
FPC arc over, etc | 0 | 2%perCM | U | 0 | M | S | L | JLAB | 3
FPC arc over, etc | 0 | 2%perCM | U | 0 | M | S | L | JLAB | 3
Vacuum failure | 350 | 3%perCM | U | 350 | M | S | L | JLAB | 3
Vacuum failure | 400 | 3%perCM | U | 400 | M | S | L | JLAB | 3
Low Gradient | 0 | 5%perCM | U | 0 | M | S | L | JLAB | 3
Low Q0 | 0 | 5%perCM | U | 0 | M | S | L | JLAB | 3
Low Gradient | 0 | 5%perCM | U | 0 | M | S | L | JLAB | 3
Low Q0 | 0 | 5%perCM | U | 0 | M | S | L | JLAB | 3

## Instruments
SNS Risk Summary (as of 1/09/03)
| WBS | Description | STL Likelihood | Management Likelihood | Technical Consequence | Schedule Consequence | Early Finish Schedule Impact (#days if risk materializes) | Cost Impact ($K) | Overall Risk | Cost Consequence | Type Risk | Risk Expiration | Mitigation Plan
High Risk |  | none
| Instruments Total | [6 empty] | 0
Moderate Risk |  | none
| Instruments Total | [6 empty] | 0
| WBS | Description | STL Likelihood | Management Likelihood | Technical Consequence | Schedule Consequence | Early Finish Schedule Impact (#days if risk materializes) | Cost Impact ($K) | Overall Risk | Cost Consequences | Type Risk | Risk Expiration | Mitigation Plan
Low Risk | Instruments | Addl. ES&H/engineering coverage |  | L | M | M |  | 595.2 | Low | M | Cost | 2003-09-01 | Offset w/ other Savings
|  | Cost increase for inserts |  | L | M | M |  | 381.782 | Low | M | Cost | 2003-10-01 | Offset w/ other Savings
|  | Increased Design costs |  | U | M | M |  | 478 | Low | M | Cost |  | Offset w/ other Savings
|  | Installation |  | U | M | M |  | 612 | Low | M | Cost/Schedule |  | Offset w/ other Savings; Integrated installation/construction schedule
|  | Labor for testing inserts |  | L | M | M |  | 126.636 | Low | M | Cost | 2003-04-01 | Offset w/ other Savings
|  | admin. effort can not be transferred to IDTs |  | L | M | M |  | 352.47 | Low | M | Cost |  | Reduce staff as required
| Instruments Total | [6 empty] | 2546.088

## Target
SNS Risk Summary (as of 1/9/03)
| WBS | Description | STL Likelihood | Management Likelihood | Technical Consequence | Schedule Consequence | Early Finish Schedule Impact (#days if risk materializes) | Cost Impact ($K) | Overall Risk | Cost Consequence | Type Risk | Risk Expiration | Mitigation Plan
High Risk | Target
| Target Total | [6 empty] | 0
Moderate Risk | Target | Remaining Equipment Instln | L | L | S | M |  | 2000 | High | S | Cost | 2003-03-03 | Evaluting possibilites to reduce tolerances;integrated installation/construction schedule
| Target Total | [6 empty] | 2000
| WBS | Description | STL Likelihood | Management Likelihood | Technical Consequence | Schedule Consequence | Early Finish Schedule Impact (#days if risk materializes) | Cost Impact ($K) | Overall Risk | Cost Consequence | Type Risk | Risk Expiration | Mitigation Plan
Low Risk | Target | Additional Field Survey Cost | L | L | M | M |  | 270 | Low | M | Cost |  | Offset w/ other Savings
|  | N&S Analysis Support - ES&H | L | L | M | M |  | 255 | Low | M | Cost |  | Offset w/ other Savings
|  | Additional A-E Design - Controls | V | V | M | M |  | 100 | High | M | Cost |  | Offset w/ other Savings
|  | Additional A-E Design/Process - Utility System | V | V | M | M |  | 275 | High | M | Cost |  | Offset w/ other Savings
|  | Be Cost Increase | V | V | M | M |  | 250 | High | M | Cost | 2002-11-02 | Offset w/ other Savings
|  | Circulator Cost Increase | V | V | M | M |  | 80 | High | M | Cost | 2002-10-02 | Offset w/ other Savings
|  | Core Vessel Design Complexity - OFFSET BY OTHER ACTIONS | [6 empty] | High
|  | Integrated Mdrtr/Plug Config - Moderator systems - REMOVE, PCR APPROVED |  | V |  |  |  |  | High
|  | Plug Design Complexity - Reflector assemblies | V | V | M | M |  | 450 | High | M | Cost | 2002-10-02 | Offset w/ other Savings
|  | Remaining Steel Procurement | V | V | M | M |  | 800 | High | M | Cost | 2003-02-03 | Offset w/ other Savings
|  | Utility Handling Cart Procurement | V | V | M | M |  | 235 | High | M | Cost |  | Offset w/ other Savings
|  | Specialty Shield Blocks | L | L | M | M |  | 135 | Low | M | Cost | 2002-12-02 | Offset w/ other Savings
| Target Total | [6 empty] | 2850