## Summary by Name
ECP5 Baseline Plan
|  | NOV FY04 | DEC FY04 | JAN FY04 | FEB FY04 | MAR FY04 | APR FY04 | MAY FY04 | JUN FY04 | JUL FY04 | AUG FY04 | SEP FY04
EA//EM - PPPL Analysis engineer
| ANALYST | 0.5 | 0.1 | 0.2 | 0.1 | 0.1 | 0.5
| Brooks | 0.6 | 0.6 | 0.6 | 1 | 1 | 0.9 | 0.9 | 1 | 1 | 1 | 0.9
| Brown | 0.6 | 0.7 | 0.6 | 0.9 | 0.9 | 0.7 | 0.6 | 0.7 | 0.7 | 0.7 | 0.7
| Chrzanowski | 0.7 | 0.7 | 0.8 | 0.8 | 1 | 1.2 | 1.1 | 1.1 | 0.5 | 0.6 | 0.5
| Dahlgren | 0.3 | 0.3 | 0.3 | 1.7 | 0.5 | 0.4 | 0.1 |  | 0.2 | 0.3 | 0.2
| Fan | 0.8 | 0.9 | 0.8 | 1.4 | 1.6 | 1.8 | 0
| Heitzenroeder | 0.7 | 0.3 | 0.2 | 0.4 | 1 | 2.1 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3
| JUN |  |  |  | 0.5 | 0.6 | 0.6 | 0.5
| KALISH | 0.2 | 0.3 | 0.5 | 0.7 | 0.6 | 1 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Long-Poe Ku |  |  |  | 0.2 | 0.3 | 0.2
| Raftopoulos | 0.3 | 0.2 | 0.5 | 0.6 | 1.7 | 0.7 | 0.8 | 1.2 | 0.7 | 0.3 | 0.7
| Reiersen | 0.7 | 0.8 | 0.7 | 0.7 | 0.8 | 0.8 | 0.7 | 0.8 | 0.8 | 0.8 | 0.8
| ZATZ |  |  |  |  | 0.4 | 0.1
| TOTAL = | 5.4 | 4.9 | 5.2 | 9 | 10.5 | 11 | 5.5 | 5.6 | 4.6 | 4.4 | 4.5
EA//SM - PPPL Designer
| ELECT DESIG |  |  |  |  | 0.3 | 0.3 | 0.2 | 0.2
| JONES | 0.4 | 0.4 | 0.5
| Mech Designer TBD | 1.1 | 1.1 | 1.1 | 1.1 | 1.3 | 1.2 | 1.7 | 1.9 | 2.4 | 2.5 | 2.2
| RUSHINSKI | 1.2 | 1.4 | 0.8 | 0.4 | 1.5 | 0.7 | 0.6 | 0.6 | 0.4 | 0.6 | 0.4
| vanKirk | 0.2 |  |  | 0.3 | 0.5 | 1.2 | 1.2 | 1.1 | 0.9 | 0.4 | 0.3
| TOTAL = | 2.9 | 2.9 | 2.4 | 1.8 | 3.6 | 3.4 | 3.7 | 3.8 | 3.7 | 3.5 | 2.9
EE//EM - PPPL Electrical engineer
| ELECT ENGR |  |  |  | 0.1 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1
| HATCHER | [7 empty] | 0.3
Neumeyer
| Raki | 0.2 |  |  | 0.4 | 1 | 1.5 | 1.4 | 1.1 | 0.9 | 0.6 | 0.3
| Stevenson | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL = | 0.2 | 0 | 0 | 0.5 | 1.3 | 1.8 | 1.7 | 1.6 | 1 | 0.7 | 0.4
EE//SM - PPPL Electrical Senior Tech
| Carson |  |  | 0.8 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1
| EDWARDS | [8 empty] | 0 | 0.1
| Electrical Senior L& |  |  |  | 0 | 0.1 | 0.4 | 0.5 | 0.3 | 0.2 | 0 | 0.1
| Electrical Techs TB | [5 empty] | 0.3 | 0.5 | 0.6 | 0.1
| Gernhardt | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0 |  | 0.3
| Gibilisco |  |  | 0.2 | 0 | 0 | 0 | 0
| Marsala |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| MCBRIDE | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0
| Rossi |  |  | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| TOTAL = | 0.3 | 0.3 | 1.7 | 0.9 | 1.3 | 1.4 | 1.7 | 1.9 | 0.5 | 0.3 | 0.2
EE//TB - PPPL Electrical Technician
| Electrical Techs TB |  |  |  | 0 | 0.2 | 0.6 | 0.6 | 2.2 | 1.3 | 0.1 | 0.2
| HALVORSEN |  |  | 0.1 | 0 | 0 | 0 | 0
| TOTAL = | 0 | 0 | 0.1 | 0 | 0.2 | 0.6 | 0.6 | 2.2 | 1.3 | 0.1 | 0.2
EM//EM - PPPL FO&M Engineer
Blanchard
| Dudek | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| GETTLEFINGE | 0.4 | 0.3 | 0.4 | 0.4 | 0.5 | 0.1 | 0.9 | 1.3 | 1 | 1 | 0.7
| KEILBACH |  |  |  | 0.1 | 0.1
| KOZUB | 0.2 | 0.2 | 0.2 | 0.9 | 1.1
| Perry | 0.4 | 0.5 | 0.4 | 0.7 | 0.5 | 0.5 | 0.4 | 0.5 | 0.7 | 0.8 | 0.7
| VIOLA | 0.5 | 0.5 | 0.4 | 0.3 | 0.4 | 0.4 | 0.8 | 0.9 | 0.6 | 0.1 | 0.1
| TOTAL = | 1.8 | 1.8 | 1.7 | 2.7 | 2.9 | 1.3 | 2.4 | 3 | 2.6 | 2.2 | 1.8
EM//SM - PPPL FO&M Senior Tech
| DELANY |  |  |  | 0.3 | 0.2
| FOM TECHS S | 1 |  |  | 0.5 | 0.5 | 0.5 |  | 0.4 | 0.2 |  | 0.2
| JURZYNSKI | 0.2 | 0.2 | 0.2 | 0.9 | 1.1
| Machinist | 0.7 | 1.2 | 1.4 | 1.2 | 1.4 | 3.1 | 2.7 | 2.2 | 0.3 | 1.1 | 2.3
| Meighan | 0.6 | 0.6 | 0.7 | 0.7 | 1 | 1.2 | 1.1 | 1.1 | 0.4 | 0.4 | 0.4
| WELDER | 0.2 | 0.2 | 0.2 |  |  |  | 0.3 | 0.7
| TOTAL = | 2.7 | 2.2 | 2.5 | 3.3 | 4 | 4.8 | 4.1 | 4.4 | 0.9 | 1.5 | 2.9
EM//TB - PPPL FO&M Technician
| FOM TECHS T | 3 | 3.7 | 5.4 | 7.5 | 8.9 | 12.1 | 11.8 | 13.5 | 7.9 | 11.6 | 11.1
ORNLEM - ORNL Engineer
| COLE | 0.8 | 0.7 | 0.9 | 2.2 | 2.8 | 1.8 | 2.2 | 1.8 | 1.4 | 1.5 | 1.8
| FREUDENBERG | 0.6 | 0.1 | 0.1 | 0.2 | 0.2
| GORANSON | 1.2 | 1.6 | 0.9 | 3.3 | 1.5 | 0.9 | 0.7 | 1.2 | 1.6 | 1.6 | 1.4
| HARGROVE | 0.2 | 0.2 | 0.7 | 1.1 | 1.5 | 1.1 | 0.4 | 0.2 | 0.9 | 0.9 | 0.5
| HIRSHMAN |  |  |  | 0.5 | 0.4 | 0.2 |  |  | 0.3 | 0.4 | 0.4
| JONES | 0.5 | 0.1 | 0.1 | 0.3 | 0.9 | 0.7 | 0.5 | 0.3 | 0.7 | 1 | 0.5
| LOVETT | 0.9 | 0.7 | 1.2 | 1.4 | 1.7 | 1.1 | 0.4 | 0.2 | 0.9 | 0.9 | 0.5
| MYATT | 0 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2
| NELSON | 0.7 | 0.8 | 0.9 | 0.9 | 0.9 | 0.8 | 0.7 | 0.6 | 0.6 | 0.6 | 0.6
| ORNL DESIGN | 0 | 0.8 | 0.7 | 2.3 | 2.7 | 2.2 | 1 | 1.1 | 1 | 1.1 | 1
| ORNL ENGR | 0.2 | 0.2 | 0.2 | 0.5 | 0.1 | 0.2 | 0.6 | 0.7 | 0.3 | 0.1 | 0.1
| STRICKLER |  |  |  | 0.5 | 0.6 | 0.6 | 0.5 | 0.3 | 0.4 | 0.7 | 0.6
| WILLIAMSON | 1.2 | 0.6 | 0.3 | 2.7 | 5 | 4.3 | 1.6 | 0.9 | 1.1 | 1 | 1.5
| TOTAL = | 6.3 | 5.8 | 6 | 16.5 | 18.9 | 14.5 | 8.8 | 7.3 | 9.2 | 9.8 | 8.9

## DETAIL BY JOB and NAME
DETAIL BY JOB and NAME
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Job: 1202 - Vacuum Vessel R&D
| FOM TECHS S | Jun: 0.4; Jul: 0.2
| KEILBACH | Feb: 0.1; Mar: 0.1
| MACHINIST | Apr: 0.3; May: 0.7
| RAFTOPOULOS | Mar: 1; Apr: 0.1; May: 0.2; Jun: 0.6; Jul: 0.3
| VIOLA | 0.5 | 0.5 | 0.4 | 0.3 | 0.4 | 0.4 | 0.8 | 0.8 | 0.4
| WELDER | May: 0.3; Jun: 0.7
Job: 1203 - Vacuum Vessel Final Dsn-GORANSON
| BROOKS | Nov: 0; Dec: 0; Jan: 0; Feb: 0.1; Mar: 0
| DAHLGREN | 0.3 | 0.3 | 0.3 | 1.2 | 0.5 | 0.4 | 0.1 |  | 0.2 | 0.3 | 0.2
| GORANSON | 1.2 | 1.6 | 0.9 | 3.3 | 1.5 | 0.9 | 0.7 | 0 | 0.4 | 0.4 | 0.4
| ORNL DESIGN | Nov: 0; Dec: 0.8; Jan: 0.7; Feb: 1.4; Mar: 1.6; Apr: 1.2
| VIOLA | Jun: 0; Jul: 0.1; Aug: 0
Job: 1250 - Vacuum Vessel Fabrication
| GORANSON | May: 0.1; Jun: 0.2; Jul: 0.2; Aug: 0.2; Sep: 0.2
| VIOLA | May: 0; Jun: 0.1; Jul: 0.1; Aug: 0.1; Sep: 0.1
Job: 1301 - Convential Coils
| ANALYST | Nov: 0.5; Dec: 0.1; Jan: 0.2; Feb: 0.1; Mar: 0.1; Apr: 0.5
HEITZENROED
| KALISH | Nov: 0.1; Dec: 0.2; Jan: 0.4; Feb: 0.7; Mar: 0.6; Apr: 0.9
| RUSHINSKI | Nov: 0.6; Dec: 1.4; Jan: 0.8; Feb: 0.3; Mar: 0.3; Apr: 0.3
Job: 1303 - TF Final Design & Fabrication
| KALISH | May: 0.3; Jun: 0.4; Jul: 0.3; Aug: 0.4; Sep: 0.3
| ORNL ENGR | May: 0.1; Jun: 0.1; Jul: 0.1; Aug: 0.1; Sep: 0.1
| RUSHINSKI | May: 0.3; Jun: 0.4; Jul: 0.4; Aug: 0.4; Sep: 0.4
Job: 1403 - Mod. Coil Final Design-WILLIAMSON
| COLE | May: 0.4; Jun: 0.2; Sep: 0.3
| DAHLGREN | Dec: 0; Jan: 0; Feb: 0.2
| FAN | 0.8 | 0.9 | 0.8 | 1.4 | 1.6 | 1.8 | 0
| FREUDENBERG | Nov: 0.1; Dec: 0.1; Jan: 0.1; Feb: 0.2; Mar: 0.2
| HARGROVE | 0.2 | 0.2 | 0.7 | 1.1 | 1.5 | 1.1 | 0.4 | 0.2 | 0.9 | 0.9 | 0.5
| JONES |  |  |  | 0.2 | 0.6 | 0.6 | 0.4 | 0.2 | 0.6 | 0.9 | 0.5
| KU | Feb: 0.2; Mar: 0.3; Apr: 0.2
| LOVETT | 0.4 | 0.5 | 0.9 | 1.4 | 1.5 | 1.1 | 0.4 | 0.2 | 0.9 | 0.9 | 0.5
| MYATT | 0 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2
| ORNL ENGR | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.3
| WILLIAMSON | 0.8 | 0.6 | 0.3 | 2.7 | 4.8 | 4.3 | 1.6 | 0.7 | 0.9 | 0.8 | 1.3
Job: 1406 - Mod. Coil Winding
| CHRZANOWSKI | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2
| COLE | Nov: 0.2; Mar: 0.2
| ELECT TB | Jun: 0.6
| FOM TECHS T |  | 0.1 | 1 | 3.6 | 1.1 | 0.9 | 2 | 2.4
| FREUDENBERG | Nov: 0.5
| GERNHARDT | Jun: 0.3
| GETTLEFINGE | Jun: 0.3
| HATCHER | Jun: 0.3
| JONES | Nov: 0.4; Mar: 0.2
| JURZYNSKI | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.9; Mar: 1.1
| KOZUB | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.9; Mar: 1.1
| LOVETT | Nov: 0.4; Dec: 0.2; Jan: 0.3; Mar: 0.2
| MACHINIST | Nov: 0.5; Dec: 0.6; Jan: 0.7; Feb: 0.8; Mar: 0.4; Apr: 0.6
| MEIGHAN | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3
| NELSON | Nov: 0; Dec: 0.1; Jan: 0.1; Feb: 0.2
| WELDER | Nov: 0.2; Dec: 0.2; Jan: 0.2
| WILLIAMSON | Nov: 0.4; Mar: 0.2
| ZATZ | Mar: 0.4; Apr: 0.1
Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI
| CHRZANOWSKI | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| ELECT TB | Apr: 0.3; May: 0.5; Jun: 0.6; Jul: 0.1
| FOM TECHS T | 3 | 3.6 | 4.4 | 3.4 | 7.4 | 10.5 | 9.8 | 10.7 | 6.6 | 6.6 | 6.3
| MACHINIST | 0.2 | 0.6 | 0.7 | 0.5 | 1 | 1.8 | 1.5 | 1.7 | 0.3 | 0.3 | 0.3
| MECH DESIGN | 0.6 | 0.5 | 0.7 | 0.6 | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.7 | 0.7
| MEIGHAN | 0.3 | 0.3 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0.4
| RAFTOPOULOS | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Job: 1409 - Mod. Coil Test Stand-GETTELFINGER
| DELANY | Feb: 0.3; Mar: 0.2
| FOM TECHS T | Feb: 0.5; Mar: 0.4
| GERNHARDT | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.2; Mar: 0.3; Apr: 0
| GETTLEFINGE | Nov: 0.3; Dec: 0.3; Jan: 0.4; Feb: 0.4; Mar: 0.4; Apr: 0
| JONES | Nov: 0.4; Dec: 0.4; Jan: 0.5
| MCBRIDE | Nov: 0.1; Dec: 0.1; Jan: 0.1; Feb: 0.1; Mar: 0.2; Apr: 0
Job: 1410 Mod Coil Prototype Winding-CHRZANOWSKI
| CHRZANOWSKI |  |  |  |  | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| FOM TECHS T | Jul: 0.5; Aug: 3.7; Sep: 3.6
| MEIGHAN |  |  |  |  | 0.2 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4
Job: 1411 - Modular Coil Casting Fabrication
| HEITZENROED | May: 0; Jun: 0.1; Jul: 0.1; Aug: 0.1; Sep: 0.1
| WILLIAMSON | May: 0.1; Jun: 0.2; Jul: 0.2; Aug: 0.2; Sep: 0.2
Job: 1501 - Structures Design- Heitzenroeder
| HEITZENROED | 0.5 | 0.1 | 0.1 | 0.3 | 0.8 | 2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2
| RUSHINSKI | 0.6 |  |  | 0.1 | 1.2 | 0.4 | 0.2 | 0.3 | 0 | 0.2
Job: 1802 - FP Assy Oversight&Support-VIOLA
| CHRZANOWSKI | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| ELECT ENGR |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Job: 1803- FP Assy Tooling/Constructability-COLE
| COLE |  | 0.1 | 0.1 | 1.5 | 1.7 | 1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
| FOM TECHS S | Sep: 0.2
| FOM TECHS T | Sep: 0.4
| ORNL DESIGN |  |  |  | 1 | 1.1 | 1.1 | 1 | 1.1 | 1 | 1.1 | 1
| RAFTOPOULOS | Sep: 0.4
Job: 1804-FP Assy Measurement
| RAFTOPOULOS |  |  | 0.1 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Job: 1901 - Stellarator Core Mngtt&Integr-NELSON
| BROOKS | 0.1 | 0.1 | 0.1 | 0.7 | 0.9 | 0.7 | 0.7 | 0.2 | 0.1 | 0.2 | 0.1
| BROWN | 0.1 | 0.1 | 0.1 | 0.4 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| COLE | 0.7 | 0.6 | 0.8 | 0.7 | 0.8 | 0.8 | 1 | 0.8 | 0.6 | 0.7 | 0.6
| DAHLGREN | Feb: 0.3
| HIRSHMAN | Feb: 0.5; Mar: 0.4; Apr: 0.2; Jul: 0.3; Aug: 0.4; Sep: 0.4
| JONES | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
| NELSON | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.6 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6
| ORNL ENGR | Feb: 0.2; Mar: 0.1; Apr: 0.2; May: 0.5; Jun: 0.6; Jul: 0.2
| STRICKLER |  |  |  | 0.5 | 0.6 | 0.6 | 0.5 | 0.3 | 0.4 | 0.7 | 0.6
ZATZ
Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD
BLANCHARD
Job: 2501 - Neutral Beam Refurbishment-STEVENSON
| CARSON |  |  | 0.8 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1
| GIBILISCO | Jan: 0.2; Feb: 0; Mar: 0; Apr: 0; May: 0
| HALVORSEN | Jan: 0.1; Feb: 0; Mar: 0; Apr: 0; May: 0
| ROSSI | Jan: 0.4; Feb: 0.3; Mar: 0.3; Apr: 0.3; May: 0.3; Jun: 0.3
| STEVENSON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job: 3901 - Diagnostics sys Integration-JOHNSON
| JOHNSON | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| STRATTON | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Job: 4101 - AC Power-RAMAKRISHNAN
| ELECT SM |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ELECT TB |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RAKI |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| VANKIRK |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job: 4301 - DC Systems-RAMAKRISHNAN
| ELECT DESIG | Mar: 0.3; Apr: 0.3; May: 0.2; Jun: 0.2
| ELECT ENGR | Mar: 0.1; Apr: 0.1; May: 0.1; Jun: 0.1
| ELECT SM | Mar: 0.1; Apr: 0.3; May: 0.4; Jun: 0.3; Jul: 0.2; Sep: 0.1
| ELECT TB | Mar: 0; Apr: 0.3; May: 0.2; Jun: 0.3; Jul: 0.3; Sep: 0.1
| RAKI | 0.2 |  |  |  | 0.1 | 0.5 | 0.5 | 0.4 | 0.3 |  | 0.1
| VANKIRK | Nov: 0.2; Mar: 0; Apr: 0.3; May: 0.5; Jun: 0.5; Jul: 0.5
Job: 4401 - Control & Protection-RAMAKRISHNAN
| ELECT TB |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| MARSALA |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| RAKI |  |  |  |  | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0
| VANKIRK |  |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0
Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN
| RAKI |  |  |  | 0.4 | 0.5 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2
| VANKIRK |  |  |  | 0.3 | 0.3 | 0.5 | 0.5 | 0.3 | 0.2 | 0.3 | 0.2
Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN
| ELECT SM | Apr: 0; May: 0; Jun: 0
| ELECT TB | Apr: 0.2; May: 0.2; Jun: 0.2
| RAKI | Apr: 0.1; May: 0.1; Jun: 0.1
| VANKIRK | Apr: 0.1; May: 0.1; Jun: 0.1
Job: 5801 -Central I&C Integr
| OLIARO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job: 6163 - Facility Systems Support FY04
| GETTLEFINGE | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| KALISH | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Job: 7201 - Control Room Walls&Floors-PERRY
| EDWARDS | Jul: 0; Aug: 0.1
| ELECT TB | Jun: 1.1; Jul: 0.9
| FOM TECHS T | Jul: 0; Aug: 0.4
Job: 7301 - Platform Design &
| FOM TECHS T | Jul: 0.7; Aug: 0.8; Sep: 0.8
| MECH DESIGN | Jul: 0.6; Aug: 0.6; Sep: 0.6
| PERRY | Feb: 0.3; Jul: 0.3; Aug: 0.3; Sep: 0.3
Job: 7401 - TC Prep & Mach Assy Planning-PERRY
| FOM TECHS S | Nov: 1; Feb: 0.5; Mar: 0.5; Apr: 0.5
| FOM TECHS T | Mar: 0.1; Apr: 0.7; May: 0
| MECH DESIGN | 0 | 0.1 | 0 | 0 | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1
| PERRY | 0.4 | 0.5 | 0.4 | 0.4 | 0.5 | 0.5 | 0.4 | 0.5 | 0.4 | 0.5 | 0.4
Job: 8101 - Project Management & Control-NEILSON
NEUMEYER
Job: 8102 - NCSX MIE Management ORNL-LYON
| BENSON/AKER | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| LYON | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN
| DUDEK | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| REIERSEN | 0.7 | 0.8 | 0.7 | 0.7 | 0.8 | 0.8 | 0.7 | 0.8 | 0.8 | 0.8 | 0.8
Job: 8203 - Design Integration-REIERSEN
| BROWN | 0.5 | 0.6 | 0.5 | 0.5 | 0.6 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5
| MECH DESIGN | 0.4 | 0.5 | 0.4 | 0.4 | 0.5 | 0.5 | 0.4 | 0.5 | 0.4 | 0.5 | 0.4
Job: 8204 - Systems Analysis-REIERSEN
| BROOKS | 0.5 | 0.5 | 0.5 | 0.2 | 0.1 | 0.2 | 0.2 | 0.8 | 0.9 | 0.8 | 0.8 | 5.5
| JUN | Feb: 0.5; Mar: 0.6; Apr: 0.6; May: 0.5
Job: 8402 - Project Physics MIE ORNL-LYON
| LAZARUS | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Job:1204 - VV Insulation H&C Supports-GORANSON
| GORANSON | Jun: 1; Jul: 1; Aug: 1; Sep: 0.8
| VIOLA | Jun: 0; Jul: 0; Aug: 0; Sep: 0
Job:1404-Mod Coil Winding Form R&D-HEITZENROEDER
| HEITZENROED | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| NELSON | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.2 | 0.2
Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI
| FOM TECHS T | Jun: 0.4
| MACHINIST | Apr: 0.5; May: 0.4; Jun: 0.5; Jul: 0; Aug: 0.8; Sep: 2.1
Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER
| GETTLEFINGE | May: 0.9; Jun: 0.9; Jul: 0.9; Aug: 0.9; Sep: 0.6
| MECH DESIGN | May: 0.6; Jun: 0.6; Jul: 0.6; Aug: 0.6; Sep: 0.4
| ORNL ENGR | Sep: 0
| RUSHINSKI | Sep: 0

## Detail by Name and Job
ECP5 Baseline detail by name and job
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
ANALYST
| Job: 1301 - Convential Coils | Nov: 0.5; Dec: 0.1; Jan: 0.2; Feb: 0.1; Mar: 0.1; Apr: 0.5
BENSON/AKER
| Job: 8102 - NCSX MIE Management ORNL-LYON | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
BLANCHARD
Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD
BROOKS
| Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | Nov: 0; Dec: 0; Jan: 0; Feb: 0.1; Mar: 0
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 0.1 | 0.1 | 0.1 | 0.7 | 0.9 | 0.7 | 0.7 | 0.2 | 0.1 | 0.2 | 0.1
| Job: 8204 - Systems Analysis-REIERSEN | 0.5 | 0.5 | 0.5 | 0.2 | 0.1 | 0.2 | 0.2 | 0.8 | 0.9 | 0.8 | 0.8 | 5.5
BROWN
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 0.1 | 0.1 | 0.1 | 0.4 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Job: 8203 - Design Integration-REIERSEN | 0.5 | 0.6 | 0.5 | 0.5 | 0.6 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5
CARSON
| Job: 2501 - Neutral Beam Refurbishment-STEVENSON |  |  | 0.8 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1
CHRZANOWSKI
| Job: 1406 - Mod. Coil Winding | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2
| Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Job: 1410 Mod Coil Prototype Winding-CHRZANOWSKI |  |  |  |  | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Job: 1802 - FP Assy Oversight&Support-VIOLA | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
COLE
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | May: 0.4; Jun: 0.2; Sep: 0.3
| Job: 1406 - Mod. Coil Winding | Nov: 0.2; Mar: 0.2
| Job: 1803- FP Assy Tooling/Constructability-COLE |  | 0.1 | 0.1 | 1.5 | 1.7 | 1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 0.7 | 0.6 | 0.8 | 0.7 | 0.8 | 0.8 | 1 | 0.8 | 0.6 | 0.7 | 0.6
DAHLGREN
| Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | 0.3 | 0.3 | 0.3 | 1.2 | 0.5 | 0.4 | 0.1 |  | 0.2 | 0.3 | 0.2
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | Dec: 0; Jan: 0; Feb: 0.2
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | Feb: 0.3
DELANY
| Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | Feb: 0.3; Mar: 0.2
DUDEK
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
EDWARDS
| Job: 7201 - Control Room Walls&Floors-PERRY | Jul: 0; Aug: 0.1
ELECT DESIG
| Job: 4301 - DC Systems-RAMAKRISHNAN | Mar: 0.3; Apr: 0.3; May: 0.2; Jun: 0.2
ELECT ENGR
| Job: 1802 - FP Assy Oversight&Support-VIOLA |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Job: 4301 - DC Systems-RAMAKRISHNAN | Mar: 0.1; Apr: 0.1; May: 0.1; Jun: 0.1
ELECT SM
| Job: 4101 - AC Power-RAMAKRISHNAN |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 4301 - DC Systems-RAMAKRISHNAN | Mar: 0.1; Apr: 0.3; May: 0.4; Jun: 0.3; Jul: 0.2; Sep: 0.1
| Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | Apr: 0; May: 0; Jun: 0
ELECT TB
| Job: 1406 - Mod. Coil Winding | Jun: 0.6
| Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | Apr: 0.3; May: 0.5; Jun: 0.6; Jul: 0.1
| Job: 4101 - AC Power-RAMAKRISHNAN |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 4301 - DC Systems-RAMAKRISHNAN | Mar: 0; Apr: 0.3; May: 0.2; Jun: 0.3; Jul: 0.3; Sep: 0.1
| Job: 4401 - Control & Protection-RAMAKRISHNAN |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | Apr: 0.2; May: 0.2; Jun: 0.2
| Job: 7201 - Control Room Walls&Floors-PERRY | Jun: 1.1; Jul: 0.9
FAN
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | 0.8 | 0.9 | 0.8 | 1.4 | 1.6 | 1.8 | 0
FOM TECHS S
| Job: 1202 - Vacuum Vessel R&D | Jun: 0.4; Jul: 0.2
| Job: 1803- FP Assy Tooling/Constructability-COLE | Sep: 0.2
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | Nov: 1; Feb: 0.5; Mar: 0.5; Apr: 0.5
FOM TECHS T
| Job: 1406 - Mod. Coil Winding |  | 0.1 | 1 | 3.6 | 1.1 | 0.9 | 2 | 2.4
| Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | 3 | 3.6 | 4.4 | 3.4 | 7.4 | 10.5 | 9.8 | 10.7 | 6.6 | 6.6 | 6.3
| Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | Jun: 0.4
| Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | Feb: 0.5; Mar: 0.4
| Job: 1410 Mod Coil Prototype Winding-CHRZANOWSKI | Jul: 0.5; Aug: 3.7; Sep: 3.6
| Job: 1803- FP Assy Tooling/Constructability-COLE | Sep: 0.4
| Job: 7201 - Control Room Walls&Floors-PERRY | Jul: 0; Aug: 0.4
| Job: 7301 - Platform Design & | Jul: 0.7; Aug: 0.8; Sep: 0.8
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | Mar: 0.1; Apr: 0.7; May: 0
FREUDENBERG
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | Nov: 0.1; Dec: 0.1; Jan: 0.1; Feb: 0.2; Mar: 0.2
| Job: 1406 - Mod. Coil Winding | Nov: 0.5
GERNHARDT
| Job: 1406 - Mod. Coil Winding | Jun: 0.3
| Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.2; Mar: 0.3; Apr: 0
GETTLEFINGE
0
| Job: 1406 - Mod. Coil Winding | Jun: 0.3
| Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | Nov: 0.3; Dec: 0.3; Jan: 0.4; Feb: 0.4; Mar: 0.4; Apr: 0
| Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | May: 0.9; Jun: 0.9; Jul: 0.9; Aug: 0.9; Sep: 0.6
| Job: 6163 - Facility Systems Support FY04 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
GIBILISCO
| Job: 2501 - Neutral Beam Refurbishment-STEVENSON | Jan: 0.2; Feb: 0; Mar: 0; Apr: 0; May: 0
GORANSON
| Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | 1.2 | 1.6 | 0.9 | 3.3 | 1.5 | 0.9 | 0.7 | 0 | 0.4 | 0.4 | 0.4
| Job:1204 - VV Insulation H&C Supports-GORANSON | Jun: 1; Jul: 1; Aug: 1; Sep: 0.8
| Job: 1250 - Vacuum Vessel Fabrication | May: 0.1; Jun: 0.2; Jul: 0.2; Aug: 0.2; Sep: 0.2
HALVORSEN
| Job: 2501 - Neutral Beam Refurbishment-STEVENSON | Jan: 0.1; Feb: 0; Mar: 0; Apr: 0; May: 0
HARGROVE
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | 0.2 | 0.2 | 0.7 | 1.1 | 1.5 | 1.1 | 0.4 | 0.2 | 0.9 | 0.9 | 0.5
HATCHER
| Job: 1406 - Mod. Coil Winding | Jun: 0.3
HEITZENROED
Job: 1301 - Convential Coils
| Job:1404-Mod Coil Winding Form R&D-HEITZENROEDER | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| Job: 1411 - Modular Coil Casting Fabrication | May: 0; Jun: 0.1; Jul: 0.1; Aug: 0.1; Sep: 0.1
| Job: 1501 - Structures Design- Heitzenroeder | 0.5 | 0.1 | 0.1 | 0.3 | 0.8 | 2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2
HIRSHMAN
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | Feb: 0.5; Mar: 0.4; Apr: 0.2; Jul: 0.3; Aug: 0.4; Sep: 0.4
JOHNSON
| Job: 3901 - Diagnostics sys Integration-JOHNSON | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
JONES
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON |  |  |  | 0.2 | 0.6 | 0.6 | 0.4 | 0.2 | 0.6 | 0.9 | 0.5
| Job: 1406 - Mod. Coil Winding | Nov: 0.4; Mar: 0.2
| Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | Nov: 0.4; Dec: 0.4; Jan: 0.5
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
JUN
| Job: 8204 - Systems Analysis-REIERSEN | Feb: 0.5; Mar: 0.6; Apr: 0.6; May: 0.5
JURZYNSKI
| Job: 1406 - Mod. Coil Winding | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.9; Mar: 1.1
KALISH
| Job: 1301 - Convential Coils | Nov: 0.1; Dec: 0.2; Jan: 0.4; Feb: 0.7; Mar: 0.6; Apr: 0.9
| Job: 1303 - TF Final Design & Fabrication | May: 0.3; Jun: 0.4; Jul: 0.3; Aug: 0.4; Sep: 0.3
| Job: 6163 - Facility Systems Support FY04 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
KEILBACH
| Job: 1202 - Vacuum Vessel R&D | Feb: 0.1; Mar: 0.1
KOZUB
| Job: 1406 - Mod. Coil Winding | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.9; Mar: 1.1
KU
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | Feb: 0.2; Mar: 0.3; Apr: 0.2
LAZARUS
| Job: 8402 - Project Physics MIE ORNL-LYON | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
LOVETT
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | 0.4 | 0.5 | 0.9 | 1.4 | 1.5 | 1.1 | 0.4 | 0.2 | 0.9 | 0.9 | 0.5
| Job: 1406 - Mod. Coil Winding | Nov: 0.4; Dec: 0.2; Jan: 0.3; Mar: 0.2
LYON
| Job: 8102 - NCSX MIE Management ORNL-LYON | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
MACHINIST
| Job: 1202 - Vacuum Vessel R&D | Apr: 0.3; May: 0.7
| Job: 1406 - Mod. Coil Winding | Nov: 0.5; Dec: 0.6; Jan: 0.7; Feb: 0.8; Mar: 0.4; Apr: 0.6
| Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | 0.2 | 0.6 | 0.7 | 0.5 | 1 | 1.8 | 1.5 | 1.7 | 0.3 | 0.3 | 0.3
| Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | Apr: 0.5; May: 0.4; Jun: 0.5; Jul: 0; Aug: 0.8; Sep: 2.1
MARSALA
| Job: 4401 - Control & Protection-RAMAKRISHNAN |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
MCBRIDE
| Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | Nov: 0.1; Dec: 0.1; Jan: 0.1; Feb: 0.1; Mar: 0.2; Apr: 0
MECH DESIGN
| Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | 0.6 | 0.5 | 0.7 | 0.6 | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.7 | 0.7
| Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | May: 0.6; Jun: 0.6; Jul: 0.6; Aug: 0.6; Sep: 0.4
| Job: 7301 - Platform Design & | Jul: 0.6; Aug: 0.6; Sep: 0.6
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 0 | 0.1 | 0 | 0 | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1
| Job: 8203 - Design Integration-REIERSEN | 0.4 | 0.5 | 0.4 | 0.4 | 0.5 | 0.5 | 0.4 | 0.5 | 0.4 | 0.5 | 0.4
MEIGHAN
| Job: 1406 - Mod. Coil Winding | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3
| Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | 0.3 | 0.3 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0.4
| Job: 1410 Mod Coil Prototype Winding-CHRZANOWSKI |  |  |  |  | 0.2 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4
MYATT
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | 0 | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.2
NELSON
| Job:1404-Mod Coil Winding Form R&D-HEITZENROEDER | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.2 | 0.2
| Job: 1406 - Mod. Coil Winding | Nov: 0; Dec: 0.1; Jan: 0.1; Feb: 0.2
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.6 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6
NEUMEYER
Job: 8101 - Project Management & Control-NEILSON
OLIARO
| Job: 5801 -Central I&C Integr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNL DESIGN
| Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | Nov: 0; Dec: 0.8; Jan: 0.7; Feb: 1.4; Mar: 1.6; Apr: 1.2
| Job: 1803- FP Assy Tooling/Constructability-COLE |  |  |  | 1 | 1.1 | 1.1 | 1 | 1.1 | 1 | 1.1 | 1
ORNL ENGR
0
| Job: 1303 - TF Final Design & Fabrication | May: 0.1; Jun: 0.1; Jul: 0.1; Aug: 0.1; Sep: 0.1
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | Nov: 0.2; Dec: 0.2; Jan: 0.2; Feb: 0.3
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | Feb: 0.2; Mar: 0.1; Apr: 0.2; May: 0.5; Jun: 0.6; Jul: 0.2
PERRY
| Job: 7301 - Platform Design & | Feb: 0.3; Jul: 0.3; Aug: 0.3; Sep: 0.3
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 0.4 | 0.5 | 0.4 | 0.4 | 0.5 | 0.5 | 0.4 | 0.5 | 0.4 | 0.5 | 0.4
RAFTOPOULOS
| Job: 1202 - Vacuum Vessel R&D | Mar: 1; Apr: 0.1; May: 0.2; Jun: 0.6; Jul: 0.3
| Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Job: 1803- FP Assy Tooling/Constructability-COLE | Sep: 0.4
| Job: 1804-FP Assy Measurement |  |  | 0.1 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
RAKI
| Job: 4101 - AC Power-RAMAKRISHNAN |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 4301 - DC Systems-RAMAKRISHNAN | 0.2 |  |  |  | 0.1 | 0.5 | 0.5 | 0.4 | 0.3 |  | 0.1
| Job: 4401 - Control & Protection-RAMAKRISHNAN |  |  |  |  | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN |  |  |  | 0.4 | 0.5 | 0.4 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2
| Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | Apr: 0.1; May: 0.1; Jun: 0.1
REIERSEN
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 0.7 | 0.8 | 0.7 | 0.7 | 0.8 | 0.8 | 0.7 | 0.8 | 0.8 | 0.8 | 0.8
ROSSI
| Job: 2501 - Neutral Beam Refurbishment-STEVENSON | Jan: 0.4; Feb: 0.3; Mar: 0.3; Apr: 0.3; May: 0.3; Jun: 0.3
RUSHINSKI
0
| Job: 1301 - Convential Coils | Nov: 0.6; Dec: 1.4; Jan: 0.8; Feb: 0.3; Mar: 0.3; Apr: 0.3
| Job: 1303 - TF Final Design & Fabrication | May: 0.3; Jun: 0.4; Jul: 0.4; Aug: 0.4; Sep: 0.4
| Job: 1501 - Structures Design- Heitzenroeder | 0.6 |  |  | 0.1 | 1.2 | 0.4 | 0.2 | 0.3 | 0 | 0.2
STEVENSON
| Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STRATTON
| Job: 3901 - Diagnostics sys Integration-JOHNSON | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
STRICKLER
| Job: 1901 - Stellarator Core Mngtt&Integr-NELSON |  |  |  | 0.5 | 0.6 | 0.6 | 0.5 | 0.3 | 0.4 | 0.7 | 0.6
VANKIRK
| Job: 4101 - AC Power-RAMAKRISHNAN |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 4301 - DC Systems-RAMAKRISHNAN | Nov: 0.2; Mar: 0; Apr: 0.3; May: 0.5; Jun: 0.5; Jul: 0.5
| Job: 4401 - Control & Protection-RAMAKRISHNAN |  |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN |  |  |  | 0.3 | 0.3 | 0.5 | 0.5 | 0.3 | 0.2 | 0.3 | 0.2
| Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | Apr: 0.1; May: 0.1; Jun: 0.1
VIOLA
| Job: 1202 - Vacuum Vessel R&D | 0.5 | 0.5 | 0.4 | 0.3 | 0.4 | 0.4 | 0.8 | 0.8 | 0.4
| Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | Jun: 0; Jul: 0.1; Aug: 0
| Job:1204 - VV Insulation H&C Supports-GORANSON | Jun: 0; Jul: 0; Aug: 0; Sep: 0
| Job: 1250 - Vacuum Vessel Fabrication | May: 0; Jun: 0.1; Jul: 0.1; Aug: 0.1; Sep: 0.1
WELDER
| Job: 1202 - Vacuum Vessel R&D | May: 0.3; Jun: 0.7
| Job: 1406 - Mod. Coil Winding | Nov: 0.2; Dec: 0.2; Jan: 0.2
WILLIAMSON
| Job: 1403 - Mod. Coil Final Design-WILLIAMSON | 0.8 | 0.6 | 0.3 | 2.7 | 4.8 | 4.3 | 1.6 | 0.7 | 0.9 | 0.8 | 1.3
| Job: 1406 - Mod. Coil Winding | Nov: 0.4; Mar: 0.2
| Job: 1411 - Modular Coil Casting Fabrication | May: 0.1; Jun: 0.2; Jul: 0.2; Aug: 0.2; Sep: 0.2
ZATZ
| Job: 1406 - Mod. Coil Winding | Mar: 0.4; Apr: 0.1
Job: 1901 - Stellarator Core Mngtt&Integr-NELSON