## NAME and WBS
|  | FEB FY04 | MAR FY04 | APR FY04 | MAY FY04 | JUN FY04 | JUL FY04 | AUG FY04 | SEP FY04 | OCT FY05 | NOV FY05 | DEC FY05 | JAN FY05 | FEB FY05 | MAR FY05 | APR FY05 | MAY FY05 | JUN FY05 | JUL FY05 | AUG FY05 | SEP FY05 | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08
BLANCHARD | 21 - Fueling Systems | [20 empty] | 0.16 | 0.15 | 0.16 | 0.02 | [8 empty] | 0.08 | 0.08 | 0.08 | 0.01
BLANCHARD | 22 - Torus Vacuum Pumping Systems | [20 empty] | 0.2 | 0.19 | 0.2 | 0.03 |  |  | 0.14 | 0.19 | 0.19 | 0.04 | [5 empty] | 0.11 | 0.11 | 0.03
BLANCHARD | 61 - Water Systems | [8 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
BLANCHARD | 63 - Utility Systems | [8 empty] | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02
BROOKS | 12 - Vacuum Vessel Systems
BROOKS | 19 - Stellarator Core Management and Integration | 0.75 | 0.86 | 0.69 | 0.66 | 0.15 | 0.14 | 0.15 | 0.14 | 0.51 | 0.48 | 0.41 | 0.48 | 0.48 | 0.56 | 0.51 | 0.51 | 0.53 | 0.48 | 0.56 | 0.51
BROOKS | 82 - Project Engineering |  |  |  |  | 0.75 | 0.72 | 0.75 | 0.72
BROWN | 19 - Stellarator Core Management and Integration | 0.36 | 0.27 | 0.13 | 0.12 | 0.13 | 0.13 | 0.13 | 0.13
BROWN | 82 - Project Engineering | 0.51 | 0.58 | 0.56 | 0.51 | 0.56 | 0.53 | 0.56 | 0.53
CARSON | 25 - Neutral Beam Injection System | 0.26 | 0.3 | 0.29 | 0.26 | 0.26 | 0.09 | 0.09 | 0.09
CHRZANOWSKI | 14 - Modular Coils | 0.56 | 0.69 | 0.97 | 0.88 | 0.88 | 0.33 | 0.35 | 0.33 | 0.33 | 0.32 | 0.65 | 0.65 | 0.65 | 0.75 | 0.68 | 0.68 | 0.72 | 0.65 | 0.75 | 0.68 | 0.68 | 0.65 | 0.55 | 0.68 | 0.65 | 0.75 | 0.65 | 0.72 | 0.72 | 0.65 | 0.75 | 0.29
COLE | 14 - Modular Coils |  | 0.15 | 0.36 | 0.16 | 0.12 | 0.02 | 0.15 |  |  | 0.17 |  |  |  |  | 0.1 | 0.07
COLE | 18 - Field Period Assembly | 1.51 | 1.73 | 0.96 | 0.77 | 0.85 | 0.81 | 0.85 | 0.81 | 0.45 | 0.43 | 0.36 | 0.43 | 0.46 | 0.86 | 0.79 | 0.79 | 0.82 | 0.75 | 0.86 | 0.79 | 0.78 | 0.75 | 0.63 | 0.78 | 0.75 | 0.86 | 0.75 | 0.82 | 0.82 | 0.75 | 0.86 | 0.75 | 0.04
COLE | 19 - Stellarator Core Management and Integration | 0.73 | 0.84 | 0.8 | 0.98 | 0.8 | 0.62 | 0.65 | 0.62 | 1.09 | 1.03 | 0.88 | 1.03 | 1.03 | 1.19 | 1.09 | 1.09 | 1.14 | 1.03 | 1.19 | 1.09 | 0.42 | 0.4 | 0.34 | 0.42 | 0.4 | 0.46 | 0.4 | 0.44 | 0.44 | 0.4 | 0.46 | 0.4 | 0.35 | 0.31 | 0.25 | 0.34 | 0.31 | 0.34 | 0.33 | 0.34 | 0.33 | 0.33 | 0.36 | 0.2 | 0.65 | 0.57 | 0.43 | 0.65 | 0.6 | 0.6 | 0.64 | 0.63 | 0.24
COMPUTER SM | 52 - Central Instrumentation & Control | [31 empty] | 0.33 | 0.48 | 0.43 | 0.35 | 0.48 | 0.43 | 0.48 | 0.46 | 0.33
COMPUTER SM | 54 - Facility Timing & Synchronization | [33 empty] | 0.55 | 0.52 | 0.71 | 0.65 | 0.71 | 0.68 | 0.55
COMPUTER SM | 55 - Real Time Plasma & Power | [33 empty] | 0.81 | 1 | 1.38 | 1.25 | 1.38 | 1.31 | 0.38
COMPUTER SM | 57 - Control Room Facility | [34 empty] | 0.28 | 0.47 | 0.43 | 0.47 | 0.22
DAHLGREN | 12 - Vacuum Vessel Systems | 1.04 | 1.19 | 1.02 |  |  | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09
DAHLGREN | 14 - Modular Coils | 0.23
DAHLGREN | 19 - Stellarator Core Management and Integration | 0.25
DELANY | 14 - Modular Coils | 0.25 | 0.19
DUDEK | 82 - Project Engineering | 0.29 | 0.34 | 0.32 | 0.29 | 0.32 | 0.31 | 0.32 | 0.31
EA ENGR TBD | 16 - Coil Services | [22 empty] | 0.13 | 0.16 | 0.15 | 0.32 | 0.33 | 0.37 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EA ENGR TBD | 64 - PFC/VV Heating & Cooling | [27 empty] | 0.06 | 0.44 | 0.4 | 0.38 | 0.31 | 0.34 | 0.23 | 0.16 | 0.22 | 0.2 | 0.22 | 0.21 | 0.14
EA ENGR TBD | 82 - Project Engineering | [8 empty] | 1.6 | 1.52 | 1.68 | 1.52 | 1.52 | 1.75 | 1.6 | 1.6 | 1.68 | 1.52 | 1.75 | 1.68 | 1.43 | 1.36 | 1.43 | 1.43 | 1.36 | 1.56 | 1.36 | 1.5 | 1.5 | 1.36 | 1.56 | 1.43 | 1.46 | 1.33 | 1.33 | 1.46 | 1.33 | 1.46 | 1.39 | 1.46 | 1.39 | 1.46 | 1.53 | 1.24 | 0.86 | 0.74 | 0.74 | 0.82 | 0.78 | 0.78 | 0.82 | 0.82
EDWARDS | 72 - Control Room Refurbishment | [5 empty] | 0.02 | 0.14
ELEC TECH S | 43 - DC Systems | [20 empty] | 0.05 | 0.04 | 0.04 | 0.05 | 0.04 | 0.05 | 0.04
ELEC TECH T | 43 - DC Systems | [20 empty] | 0.07 | 0.06 | 0.05 | 0.07 | 0.06 | 0.07 | 0.06
ELECT DESIG | 41 - AC Power | [25 empty] | 0.18 | 0.15 | 0.17
ELECT DESIG | 43 - DC Systems | [20 empty] | 0.34 | 0.52 | 0.44 | 0.54 | 0.52 | 0.6 | 0.52 | 0.43
ELECT DESIG | 44 - Control and protection Systems | [19 empty] | 0.03 | 1.41 | 1.46 | 0.93 | 0.87 | 0.42 | 0.15 | 0.09 | 0.06 | 0.06 | 0.01 |  |  | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.02
ELECT DESIG | 45 - Power System Design and Integration | [18 empty] | 0.27 | 0.37 | 0.57 | 0.58 | 0.49 | 0.37 | 0.16
ELECT DESIG | 51 - TCP/IP Infrastructure Systems | [33 empty] | 0.05 | 0.13 | 0.18 | 0.17 | 0.18 | 0.18 | 0.11
ELECT DESIG | 64 - PFC/VV Heating & Cooling | [30 empty] | 0.55 | 0.62 | 0.68 | 0.15
ELECT ENGR | 14 - Modular Coils | [10 empty] | 0.1
ELECT ENGR | 18 - Field Period Assembly | 0.13 | 0.14 | 0.14 | 0.13 | 0.14 | 0.13 | 0.14 | 0.13
ELECT ENGR | 31 - Magnetic Diagnostics | [17 empty] | 0.21 | 0.98 | 0.9 | 1.14 | 0.91 | 0.32 | 0.39 | 0.31 | 0.3 | 0.35 | 0.27 | 0.27 | 0.25 | 0.16
ELECT ENGR | 38 - Electron Beam (EB) Mapping | [32 empty] | 0.07 | 0.07 | 0.06 | 0.08 | 0.07 | 0.02
ELECT ENGR | 43 - DC Systems | [20 empty] | 0.11 | 0.11 | 0.09 | 0.11 | 0.11 | 0.12 | 0.1
ELECT ENGR | 85 - Integrated Systems Testing | [40 empty] | 0.44 | 0.49 | 0.54 | 0.46 | 0.34 |  | 0.22
ELECT SM | 14 - Modular Coils | [10 empty] | 0.13 |  |  | 0.08 | 0.13 | 0.13 | 0.14 | 0.13 | 0.15 | 0.13 | 0.13 | 0.13 | 0.11 | 0.13 | 0.13 | 0.15 | 0.13 | 0.14 | 0.14 | 0.13 | 0.04
ELECT SM | 21 - Fueling Systems | [23 empty] | 0.28 | 0.31 | 0.35 | 0.06 | [5 empty] | 0.17 | 0.15 | 0.15 | 0.08 | 0.06 | 0.02
ELECT SM | 22 - Torus Vacuum Pumping Systems | [23 empty] | 0.55 | 0.62 | 0.71 | 0.12 |  |  |  | 0.15 | 0.21 | 0.22 | 0.2 | 0.2 | 0.13 | 0.11 | 0.03
ELECT SM | 25 - Neutral Beam Injection System | [8 empty] | 0.03 | 0.03 | 0.04 | 0.03 | 0.03 | 0.04 | 0.03 | 0.03 | 0.04 | 0.03 | 0.04 | 0.04 | 0.18 | 0.17 | 0.18 | 0.18 | 0.17 | 0.2 | 0.17 | 0.19 | 0.19 | 0.17 | 0.2 | 0.18 | 1.23 | 1.13 | 1.13 | 1.25 | 1.13 | 0.87 | 0.81 | 0.85 | 0.58 | 0.08
ELECT SM | 31 - Magnetic Diagnostics | [21 empty] | 0.04 | 0.14 | 0.18 | 0.17 | 0.66 | 0.91 | 0.92 | 0.92 | 0.84 | 0.55
ELECT SM | 38 - Electron Beam (EB) Mapping | [32 empty] | 0.09 | 0.1 | 0.08 | 0.11 | 0.1 | 0.03
ELECT SM | 41 - AC Power | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [12 empty] | 0.18 | 0.22 | 0.19 | 0.24 | 0.22 | 0.26 | 0.22 | 0.31 | 0.29 | 0.18 | 0.21 | 0.21 | 0.44 | 0.38 | 0.3 | 0.42 | 0.38 | 0.04 | 0.15 | 0.25 | 0.24 | 0.1
ELECT SM | 42 - AC/DC Converters | [32 empty] | 0.06 | 0.05 | 0.04 | 0.06 | 0.05
ELECT SM | 43 - DC Systems |  | 0.09 | 0.12 | 0.41 | 0.26 | 0.3 | 0.1 | 0.14 | 0.26 | 0.1 | [9 empty] | 0 | 0.06 | 0.06 | 0.05 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.05 | 0.01 | 0.17 | 0.18 | 0.28 | 0.26 | 0.21 | 0.14 | 0.12 | 0.05 | 0.03 | 0.03 | 0.01
ELECT SM | 44 - Control and protection Systems | [20 empty] | 0.02 | 0.02 | 0.02 | 0.08 | 0.19 | 0.57 | 0.55 | 0.64 | 0.66 | 0.65 | 0.94 | 0.85 | 1.3 | 1.09 | 0.71 | 0.64 | 0.27 | 0.25 | 0.09
ELECT SM | 45 - Power System Design and Integration | [23 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.04 | 0.04 | 0.05 | 0.04 | 0.15 | 0.2 | 0.13 | 0.18 | 0.1 | 0.03
ELECT SM | 46 - FCPC Building Modifications |  |  | 0.03 | 0.03 | 0.03 | [9 empty] | 0.02 | 0.03 | 0.03 | 0.02 |  |  | 0.03 | 0.03 | 0.03 | 0.01
ELECT SM | 51 - TCP/IP Infrastructure Systems | [33 empty] | 0.42 | 1.12 | 1.54 | 1.4 | 1.54 | 1.47 | 0.91
ELECT SM | 56 - Central Safety Interlock | [33 empty] | 0.49 | 1.11 | 1.53 | 1.39 | 1.53 | 1.46
ELECT SM | 57 - Control Room Facility | [34 empty] | 0.19 | 0.32 | 0.29 | 0.32 | 0.14
ELECT SM | 64 - PFC/VV Heating & Cooling | [27 empty] | 0.02 | 0.11 | 0.1 | 0.16 | 0.15 | 0.17 | 0.15 | 0.12 | 0.17 | 0.15 | 0.17 | 0.16 | 0.11
ELECT SM | 85 - Integrated Systems Testing | [40 empty] | 1.14 | 1.26 | 1.41 | 1.2 | 0.89 |  | 0.59
ELECT TB | 14 - Modular Coils |  |  | 0.28 | 0.52 | 0.57 | 0.05 | 0.55 |  |  |  | 0.45 |  |  | 0.3 | 0.48 | 0.48 | 0.5 | 0.46 | 0.53 | 0.48 | 0.48 | 0.46 | 0.39 | 0.48 | 0.46 | 0.53 | 0.46 | 0.5 | 0.5 | 0.46 | 0.14
ELECT TB | 31 - Magnetic Diagnostics | [21 empty] | 0.01 | 0.03 | 0.03 | 0.03 | 0.04 | 0.01
ELECT TB | 41 - AC Power | 0.02 | 0.03 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | [12 empty] | 0.3 | 0.38 | 0.32 | 0.4 | 0.38 | 0.44 | 0.38 | 0.69 | 0.71 | 0.48 | 0.55 | 0.56 | 0.86 | 0.76 | 0.6 | 0.83 | 0.76 | 0.14 | 0.35 | 0.59 | 0.57 | 0.24
ELECT TB | 42 - AC/DC Converters | [32 empty] | 0.14 | 0.13 | 0.1 | 0.14 | 0.13
ELECT TB | 43 - DC Systems |  |  |  | 0.24 | 0.26 | 0.4 | 0.15 | 0.14 | 0.26 | 0.1 | [18 empty] | 0.01 | 0.03 | 0.19 | 0.19 | 0.3 | 0.27 | 0.22 | 0.13 | 0.09 | 0.02
ELECT TB | 44 - Control and protection Systems |  | 0.12 | 0.12 | 0.11 | 0.12 | 0.11 | 0.12 | 0.01 | [12 empty] | 0.06 | 0.07 | 0.06 | 0.14 | 0.4 | 1.59 | 1.65 | 2.08 | 2.32 | 2.37 | 3.45 | 3.01 | 3.83 | 2.85 | 1.67 | 1.31 | 0.38 | 0.27 | 0.1
ELECT TB | 45 - Power System Design and Integration | [23 empty] | 0.03 | 0.07 | 0.08 | 0.07 | 0.1 | 0.25 | 0.23 | 0.26 | 0.23 | 0.68 | 0.81 | 0.48 | 0.65 | 0.48 | 0.12
ELECT TB | 46 - FCPC Building Modifications |  |  | 0.21 | 0.19 | 0.21 | [6 empty] | 0.2 | 0.31 | 0.35 | 0.27 | 0.23 | 0.24 | 0.11 |  |  | 0.09 | 0.09 | 0.08 | 0.04
ELECT TB | 72 - Control Room Refurbishment |  |  |  |  | 1.07 | 0.93
FAN | 14 - Modular Coils | 1.38 | 1.6 | 1.76 | 0.03
FIELDTECHSM | 18 - Field Period Assembly | [25 empty] | 0.05 | 0.9 | 0.75 | 0.8 | 0.65 | 0.6
FOM ENGR | 14 - Modular Coils | [10 empty] | 0.18
FOM ENGR | 25 - Neutral Beam Injection System | [8 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.11 | 0.19 | 0.17 | 0.17 | 0.19 | 0.17 | 0.11 | 0.1 | 0.11 | 0.1 | 0.1 | 0.09
FOM ENGR | 36 - Edge and Divertor Diagnostics | [20 empty] | 0.04 | 0.04 | 0.03 | 0.04 | 0.04 | 0.04 | 0.02 |  |  |  | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01
FOM ENGR | 38 - Electron Beam (EB) Mapping | [20 empty] | 0.18 | 0.17 | 0.14 | 0.18 | 0.08 | [7 empty] | 0.18 | 0.2 | 0.16 | 0.22 | 0.2 | 0.06
FOM ENGR | 39 - Diagnostics Integration | [8 empty] | 0.22 | 0.21 | 0.18 | 0.21 | 0.21 | 0.24 | 0.22 | 0.22 | 0.23 | 0.21 | 0.24 | 0.22 | 0.22 | 0.21 | 0.18 | 0.22 | 0.21 | 0.24 | 0.21 | 0.23 | 0.23 | 0.21 | 0.24 | 0.21 | 0.23 | 0.21 | 0.17 | 0.23 | 0.21 | 0.23 | 0.22 | 0.23 | 0.23 | 0.23 | 0.25 | 0.21 | 0.25 | 0.22
FOM ENGR | 61 - Water Systems | [20 empty] | 0.05 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  | 0.03 | 0.37 | 0.5 | 0.58 | 0.31 | 0.28 | 0.21 | 0.18 | 0.36 | 0.53 | 0.48 | 0.56 | 0.35
FOM ENGR | 62 - Cryogenic Systems | [26 empty] | 0.11 | 0.36 | 0.56 | 0.51 | 0.59 | 0.51 | 0.46 | 0.22 | 0.03 | 0.21 | 0.36 | 0.44 | 0.42 | 0.22
FOM ENGR | 63 - Utility Systems | [27 empty] | 0.01 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.03 | 0.03 | 0.17 | 0.11
FOM ENGR | 74 - Machine Assembly Planning and Oversight | [20 empty] | 0.46 | 0.43 | 0.37 | 0.46 | 0.43 | 0.5 | 0.63 | 0.7 | 0.7 | 0.63 | 0.73 | 0.63 | 0.7 | 0.63 | 0.51 | 0.7 | 0.63 | 0.7 | 0.66 | 0.7 | 0.66 | 0.66 | 0.73 | 0.74 | 0.75 | 0.65 | 0.49 | 0.75 | 0.68 | 0.68 | 0.71 | 0.68
FOM ENGR | 75 - Test Cell and Basement Assembly Operations | [31 empty] | 0.06 | 0.1 | 0.09 | 0.04 | 0.06 | 0.05 | 0.3 | 0.05 | 0.06 | 0.05 | 0.04 |  |  | 0.95 | 1 | 0.05
FOM ENGR | 82 - Project Engineering | [8 empty] | 0.31 | 0.3 | 0.33 | 0.3 | 0.3 | 0.34 | 0.31 | 0.31 | 0.33 | 0.3 | 0.34 | 0.33 | 0.31 | 0.3 | 0.31 | 0.31 | 0.3 | 0.34 | 0.3 | 0.33 | 0.33 | 0.3 | 0.34 | 0.31 | 0.32 | 0.29 | 0.29 | 0.32 | 0.29 | 0.32 | 0.3 | 0.32 | 0.3 | 0.32 | 0.33 | 0.29 | 0.37 | 0.32 | 0.32 | 0.35 | 0.34 | 0.34 | 0.35 | 0.35
FOM ENGR | 85 - Integrated Systems Testing | [26 empty] | 0.77 | 0.85 | 0.85 | 0.77 | 0.88 | 0.77 | 0.85 | 0.77 | 0.61 | 0.85 | 0.77 | 0.85 | 0.31 |  | 1.32 | 1.46 | 1.63 | 1.39 | 1.02 |  | 0.69
FOM TECHS SM | 12 - Vacuum Vessel Systems |  |  |  |  | 0.4 | 0.15 | [17 empty] | 0.1 | 0.11 | 0.05
FOM TECHS SM | 13 - Conventional Coils | [28 empty] | 0.12 | 0.12 | 0.14 | 0.12 | 0.13 | 0.12 | 0.03
FOM TECHS SM | 14 - Modular Coils | [23 empty] | 0.02 | 0.03 | 0.03 | 0.02 | [8 empty] | 0.7 | 0.38
FOM TECHS SM | 15 - Structures | [20 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
FOM TECHS SM | 16 - Coil Services | [34 empty] | 0.1 | 0.22 | 0.2 | 0.12
FOM TECHS SM | 18 - Field Period Assembly | [7 empty] | 0.18 | 0.19 | 0.08 |  |  | 0.02 | 0.18 | 0.16 | 0.16 | 0.17 | 0.15 | 0.18 | 0.16 | 0.81 | 0.77 | 0.65 | 0.81 | 0.99 | 2.76 | 1.85 | 3.58 | 3.61 | 4.56 | 4.97 | 3.61 | 2.83 | 1.29 | 1.03 | 0.13
FOM TECHS SM | 21 - Fueling Systems | [23 empty] | 0.1 | 0.12 | 0.13 | 0.02 | [5 empty] | 0.44 | 0.4 | 0.4 | 0.06
FOM TECHS SM | 22 - Torus Vacuum Pumping Systems | [20 empty] | 0.16 | 0.15 | 0.16 | 0.02 |  |  | 0.12 | 0.17 | 0.17 | 0.04 | 0.5 | 0.7 | 0.73 | 0.66 | 0.66 | 0.07
FOM TECHS SM | 31 - Magnetic Diagnostics | [21 empty] | 0.14 | 0.48 | 0.59 | 0.56 | 0.65 | 0.53
FOM TECHS SM | 36 - Edge and Divertor Diagnostics | [30 empty] | 0.02 | 0.09 | 0.1 | 0.09 | 0.07 | 0.1 | 0.09 | 0.03
FOM TECHS SM | 38 - Electron Beam (EB) Mapping | [32 empty] | 0.19 | 0.21 | 0.17 | 0.23 | 0.21 | 0.06
FOM TECHS SM | 62 - Cryogenic Systems | [34 empty] | 0.02 | 0.09 | 0.28 | 0.38 | 0.37 | 0.17
FOM TECHS SM | 64 - PFC/VV Heating & Cooling | [33 empty] | 0.17 | 0.18 | 0.25 | 0.23 | 0.25 | 0.24 | 0.16
FOM TECHS SM | 73 - Platform Design & Fabrication | [20 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.01
FOM TECHS SM | 74 - Machine Assembly Planning and Oversight | 0.46 | 0.53 | 0.51 | [5 empty] | 0.45 | 0.43 | 0.37 | 0.43 | 0.43 | 0.5 | 0.45 | 0.45 | 0.48 | 0.43 | 0.5 | 0.45 | 0.46 | 0.43 | 0.37 | 0.46 | 0.43 | 0.5 | 0.63 | 0.7 | 0.7 | 0.63 | 0.73 | 0.63 | 0.7 | 0.63 | 0.51 | 0.7 | 0.63 | 0.7 | 0.66 | 0.7 | 0.66 | 0.66 | 0.73 | 0.74 | 0.75 | 0.65 | 0.49 | 0.75 | 0.68 | 0.68 | 0.71 | 0.68
FOM TECHS SM | 75 - Test Cell and Basement Assembly Operations | [8 empty] | 0.48 | 0.48 | 0.32 | 0.36 | 0.28 | 0.27 | 0.07 | [8 empty] | 0.82 | 0.87 | 1 | 0.87 | 0.95 | 0.95 | 1.2 | 1.7 | 1.86 | 3.13 | 2.85 | 1.09 | 1.97 | 1.86 | 2.54 | 1.43 | 1.3 | 0.18 | 0.05 |  |  | 1.77 | 1.87 | 0.09
FOM TECHS SM | 76 - Tooling Design & Fabrication | [8 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
FOM TECHS SM | 85 - Integrated Systems Testing | [26 empty] | 0.77 | 0.85 | 0.85 | 0.77 | 0.88 | 0.77 | 0.85 | 0.77 | 0.61 | 0.85 | 0.77 | 0.85 | 0.31 |  | 0.66 | 0.73 | 0.81 | 0.7 | 0.51 |  | 0.34
FOM TECHS TB | 12 - Vacuum Vessel Systems | [23 empty] | 0.39 | 0.43 | 0.04
FOM TECHS TB | 13 - Conventional Coils | [28 empty] | 0.47 | 0.47 | 0.54 | 0.47 | 0.52 | 0.47 | 0.12
FOM TECHS TB | 14 - Modular Coils | 7.48 | 8.67 | 10.95 | 10.93 | 11.72 | 7.77 | 11.82 | 9.91 | 3.76 | 3.58 | 2.44 | 4.66 | 11.52 | 13.85 | 13.06 | 13.06 | 13.68 | 12.44 | 14.31 | 13.06 | 13.06 | 12.44 | 10.57 | 13.06 | 12.44 | 14.31 | 12.44 | 13.68 | 13.68 | 12.44 | 3.73 |  |  |  |  | 2.34 | 1.26
FOM TECHS TB | 15 - Structures | [20 empty] | 0.03 | 0.02 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.02 | 0.03 | 0.02
FOM TECHS TB | 16 - Coil Services | [34 empty] | 0.4 | 0.79 | 0.72 | 0.43
FOM TECHS TB | 18 - Field Period Assembly | [7 empty] | 0.42 | 0.44 | 0.19 |  |  | 0.04 | 0.48 | 0.44 | 0.44 | 0.46 | 0.42 | 0.48 | 0.44 | 3.06 | 2.92 | 2.48 | 3.06 | 3.57 | 7.92 | 6.78 | 10.96 | 10.68 | 13.22 | 13.88 | 9.84 | 7.14 | 3.26 | 2.6 | 0.33
FOM TECHS TB | 21 - Fueling Systems | [32 empty] | 0.42 | 0.38 | 0.38 | 0.06
FOM TECHS TB | 22 - Torus Vacuum Pumping Systems | [30 empty] | 0.36 | 0.5 | 0.52 | 0.48 | 0.48 | 0.05
FOM TECHS TB | 25 - Neutral Beam Injection System | [8 empty] | 0.03 | 0.03 | 0.04 | 0.03 | 0.03 | 0.04 | 0.03 | 0.03 | 0.04 | 0.03 | 0.04 | 0.04 | 0.18 | 0.17 | 0.18 | 0.18 | 0.17 | 0.2 | 0.17 | 0.19 | 0.19 | 0.17 | 0.2 | 0.18 | 1.23 | 1.13 | 1.13 | 1.25 | 1.13 | 0.87 | 0.81 | 0.85 | 0.58 | 0.08
FOM TECHS TB | 61 - Water Systems | [32 empty] | 0.37 | 0.42 | 0.69 | 1.41 | 1.42 | 1.1 | 1.16 | 0.72
FOM TECHS TB | 62 - Cryogenic Systems | [34 empty] | 0.29 | 1.99 | 2.94 | 3.55 | 3.38 | 2.03
FOM TECHS TB | 63 - Utility Systems | [34 empty] | 0.29 | 1.57 | 1
FOM TECHS TB | 64 - PFC/VV Heating & Cooling | [33 empty] | 1.67 | 1.78 | 2.45 | 2.23 | 2.45 | 2.34 | 1.56
FOM TECHS TB | 72 - Control Room Refurbishment | [5 empty] | 0.04 | 0.4
FOM TECHS TB | 73 - Platform Design & Fabrication | [5 empty] | 0.71 | 0.79 | 0.75 | [12 empty] | 0.25 | 0.24 | 0.25 | 0.25 | 0.24 | 0.27 | 0.07
FOM TECHS TB | 74 - Machine Assembly Planning and Oversight |  |  |  | 0.6 | 0.15
FOM TECHS TB | 75 - Test Cell and Basement Assembly Operations | [23 empty] | 2.06 | 2.17 | 2.49 | 2.17 | 2.38 | 2.38 | 3.5 | 5.32 | 6.16 | 11.1 | 10.09 | 3.43 | 6.6 | 6.26 | 6.37 | 4.47 | 3.9 | 0.71 | 0.3 | 1.33 | 3.15 | 10.08 | 8.17 | 0.41
FOM TECHS TB | 76 - Tooling Design & Fabrication | [8 empty] | 0.02 | 0.02 | 0.03 | 0.02 | 0.02 | 0.03 | 0.02 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.02
FOM TECHS TB | 85 - Integrated Systems Testing | [40 empty] | 0.57 | 0.63 | 0.71 | 0.6 | 0.44 |  | 0.51
FREUDENBERG | 12 - Vacuum Vessel Systems | 1.35 | 0.8 | 0.45
FREUDENBERG | 14 - Modular Coils | 0.16 | 0.19
GERNHARDT | 14 - Modular Coils | 0.23 | 0.26 | 0.02 |  |  |  | 0.28
GETTLEFINGE | 14 - Modular Coils | 0.36 | 0.41 | 0.04 |  |  |  | 0.25 | [6 empty] | 0.05 | 0.08 | 0.08 | 0.08 | 0.08 | 0.09 | 0.08 | 0.08 | 0.08 | 0.07 | 0.08 | 0.08 | 0.09 | 0.08 | 0.08 | 0.08 | 0.08 | 0.02
GETTLEFINGE | 17 - Cryostat and Base Support Structure |  |  |  | 0.86 | 0.95 | 0.91 | 0.95 | 0.68 | 0.63 | 0.6 | 0.51 | 0.6 | 0.6 | 0.69 | 0.63 | 0.63 | 0.66 | 0.6 | 0.69 | 0.45 |  |  | 0.05 | 0.07 | 0.06 | 0.07 | 0.06 | 0.07 | 0.07 | 0.03 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
GETTLEFINGE | 65 - Facility Systems Integration | 0.05 | 0.06 | 0.06 | 0.05 | 0.06 | 0.05 | 0.06 | 0.05
GIBILISCO | 25 - Neutral Beam Injection System | 0.01 | 0.02 | 0.02 | 0.01
GORANSON | 12 - Vacuum Vessel Systems | 2.69 | 1.07 | 1.79 | 1.13 | 0.2 | 0.93 | 0.93 | 0.89 | 0.89 | 0.85 | 0.91 | 0.85 | 0.85 | 0.14 | 0.13 | 0.13 | 0.17 | 0.29 | 0.35 | 0.33 | 0.36 | 0.34 | 0.36 | 0.28 | 0.26 | 0.16 | 0.13 | 0.14 | 0.14 | 0.13 | 0.14 | 0.13 | 0.14 | 0.1
HALVORSEN | 25 - Neutral Beam Injection System | 0.01 | 0.01 | 0.01 | 0.01
HARGROVE | 14 - Modular Coils | 0.77 | 1.23 | 1.38 | 0.16 | 0.12 | 0.32 | 0.94 | 0.43 | 0.43 | 0.53 | 0.1 | 0.41 | 0.41 | 0.47 | 0.53 | 0.19
HATCHER | 14 - Modular Coils | [6 empty] | 0.25
HEITZENROED | 13 - Conventional Coils
HEITZENROED | 14 - Modular Coils | 0.17 | 0.2 | 0.19 | 0.17 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.07 | 0.06 | 0.07 | 0.07 | 0.08 | 0.08 | 0.08 | 0.08 | 0.07 | 0.08 | 0.08 | 0.08 | 0.07 | 0.06 | 0.08 | 0.07 | 0.08 | 0.07 | 0.08 | 0.08 | 0.07 | 0.08 | 0.07
HEITZENROED | 15 - Structures | 0.25 | 0.77 | 1.96 | 0.27 | 0.3 | 0.17 | 0.24 | 0.25 | 0.53 | 0.39 | [8 empty] | 0.33 | 0.38 | 0.38 | 0.36 | 0.31 | 0.38 | 0.36 | 0.42 | 0.36 | 0.4 | 0.4 | 0.36 | 0.07
HIRSHMAN | 19 - Stellarator Core Management and Integration | 0.48 | 0.43 | 0.22 |  |  | 0.25 | 0.39 | 0.38 | 0.11
JONES | 14 - Modular Coils | 0.16 | 0.75 | 0.93 | 0.16 | 0.12 | 0.02 | 0.15 |  |  | 0.17 |  |  |  |  | 0.1 | 0.07
JONES | 19 - Stellarator Core Management and Integration | 0.1 | 0.11 | 0.11 | 0.1 | 0.11 | 0.04 | 0.05 | 0.04
JUN | 82 - Project Engineering | 0.54 | 0.62 | 0.58 | 0.52
JURZYNSKI | 14 - Modular Coils | 0.94 | 1.06
KALISH | 12 - Vacuum Vessel Systems |  | 0.08 | 0.43
KALISH | 13 - Conventional Coils | 0.85 | 1.15 | 1.53 | 0.32 | 0.36 | 0.34 | 0.36 | 0.34 | 0.34 | 0.33 | 0.28 | 0.45 | 0.52 | 0.6 | 0.75 | 0.79 | 0.83 | 0.75 | 1.09 | 1 | 0.41 | 0.39 | 0.35 | 0.55 | 0.82 | 0.76 | 0.63 | 0.69 | 0.69 | 0.63 | 0.72 | 0.63 | 0.48 | 0.44 | 0.35 | 0.48 | 0.37
KALISH | 18 - Field Period Assembly | [20 empty] | 0.06 | 0.06 | 0.05 | 0.06 | 0.02
KALISH | 65 - Facility Systems Integration | 0.05 | 0.06 | 0.06 | 0.05 | 0.06 | 0.05 | 0.06 | 0.05
KEILBACH | 12 - Vacuum Vessel Systems | 0.1 | 0.1
KOZUB | 14 - Modular Coils | 0.94 | 1.06
KU | 14 - Modular Coils | 0.23 | 0.33 | 0.2
LAZARUS | 84 - Project Physics | 0.09 | 0.1 | 0.1 | 0.09 | 0.1 | 0.09 | 0.1 | 0.09
LOVETT | 14 - Modular Coils | 1.07 | 1.38 | 1.41 | 0.16 | 0.12 | 0.32 | 0.94 | 0.43 | 0.43 | 0.53 | 0.1 | 0.41 | 0.41 | 0.47 | 0.53 | 0.19
LYON | 81 - Project Management and Control | 0.17 | 0.2 | 0.19 | 0.17 | 0.19 | 0.18 | 0.19 | 0.18 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09 | 0.1 | 0.1 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.09 | 0.1 | 0.1 | 0.09 | 0.1 | 0.09 | 0.1 | 0.09 | 0.09 | 0.12 | 0.12 | 0.13 | 0.12 | 0.13 | 0.12 | 0.13 | 0.13 | 0.12 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09
MACHINIST | 12 - Vacuum Vessel Systems |  |  | 0.3 | 0.7
MACHINIST | 14 - Modular Coils | 1.21 | 1.01 | 2.45 | 2.26 | 2.17 | 0.73 | 0.38 | 0.28 | 2.23 | 2.74 | 3.78 | 2.66 | 1.28 | 1.6 | 1.66 | 2.29 | 2.58 | 0.83 | 1.33 | 1.74 | 1.66 | 1.58 | 0.55
MACHINIST | 18 - Field Period Assembly | [25 empty] | 0.02 | 0.38 | 0.38 | 0.4 | 0.33 | 0.3
MARSALA | 14 - Modular Coils | [13 empty] | 0.07 | 0.11 | 0.11 | 0.11 | 0.1 | 0.12 | 0.11 | 0.11 | 0.1 | 0.09 | 0.11 | 0.1 | 0.12 | 0.1 | 0.11 | 0.11 | 0.1 | 0.03
MARSALA | 44 - Control and protection Systems |  | 0.1 | 0.09 | 0.08 | 0.09 | 0.09 | 0.09 | 0
MCBRIDE | 14 - Modular Coils | 0.14 | 0.16 | 0.01
MECH DESIGN | 14 - Modular Coils | 0.65 | 0.74 | 0.71 | 0.65 | 0.71 | 0.68 | 0.71 | 0.68
MECH DESIGN | 15 - Structures | [18 empty] | 0.1 | 0.11 | 0.11 | 0.11 | 0.09 | 0.11 | 0.11 | 0.13 | 0.11 | 0.12 | 0.12 | 0.11 | 0.02
MECH DESIGN | 17 - Cryostat and Base Support Structure |  |  |  | 0.58 | 0.64 | 0.61 | 0.64 | 0.44 | 0.32 | 0.31 | 0.26 | 0.31 | 0.31 | 0.35 | 0.32 | 0.32 | 0.34 | 0.31 | 0.35 | 0.23 |  |  | 0.03 | 0.09 | 0.09 | 0.1 | 0.09 | 0.1 | 0.1 | 0.09 | 0.1 | 0.09 | 0.1 | 0.09 | 0.07 | 0.1 | 0.09 | 0.09
MECH DESIGN | 18 - Field Period Assembly | [20 empty] | 0.12 | 0.12 | 0.1 | 0.12 | 0.04
MECH DESIGN | 21 - Fueling Systems | [23 empty] | 0.35 | 0.38 | 0.44 | 0.08
MECH DESIGN | 22 - Torus Vacuum Pumping Systems | [23 empty] | 0.64 | 0.71 | 0.82 | 0.14
MECH DESIGN | 25 - Neutral Beam Injection System | [8 empty] | 0.18 | 0.17 | 0.19 | 0.17 | 0.17 | 0.2 | 0.18 | 0.18 | 0.19 | 0.17 | 0.2 | 0.19 | 0.18 | 0.17 | 0.18 | 0.18 | 0.17 | 0.2 | 0.38 | 0.41 | 0.41 | 0.38 | 0.43 | 0.39 | 0.41 | 0.38 | 0.38 | 0.41 | 0.38 | 0.41 | 0.39 | 0.41 | 0.16
MECH DESIGN | 31 - Magnetic Diagnostics | [17 empty] | 0.21 | 0.95 | 0.86 | 0.86 | 0.62
MECH DESIGN | 38 - Electron Beam (EB) Mapping | [20 empty] | 0.15 | 0.14 | 0.12 | 0.15 | 0.06
MECH DESIGN | 39 - Diagnostics Integration | [8 empty] | 0.18 | 0.17 | 0.15 | 0.17 | 0.17 | 0.2 | 0.18 | 0.18 | 0.19 | 0.17 | 0.2 | 0.18 | 0.18 | 0.17 | 0.15 | 0.18 | 0.17 | 0.2 | 0.17 | 0.19 | 0.19 | 0.17 | 0.2 | 0.17 | 0.19 | 0.17 | 0.14 | 0.19 | 0.17 | 0.19 | 0.18 | 0.19 | 0.19 | 0.19 | 0.21 | 0.18 | 0.21 | 0.18
MECH DESIGN | 61 - Water Systems | [20 empty] | 0.18 | 0.17 | 0.15 | 0.17 | 0.16 | 0.17 |  | 0.01 | 0.23 | 0.21 | 0.24 | 0.23 | 0.28 | 0.21 | 0.08
MECH DESIGN | 62 - Cryogenic Systems | [29 empty] | 0.09 | 0.45 | 0.72 | 0.7 | 0.38
MECH DESIGN | 63 - Utility Systems | [27 empty] | 0.03 | 0.19 | 0.17 | 0.2 | 0.17 | 0.19 | 0.06
MECH DESIGN | 64 - PFC/VV Heating & Cooling | [27 empty] | 0.03 | 0.22 | 0.2 | 0.74 | 0.77 | 0.85 | 0.19
MECH DESIGN | 73 - Platform Design & Fabrication | [5 empty] | 0.62 | 0.64 | 0.62
MECH DESIGN | 74 - Machine Assembly Planning and Oversight | 0.05 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
MECH DESIGN | 82 - Project Engineering | 0.42 | 0.48 | 0.46 | 0.42 | 0.46 | 0.44 | 0.46 | 0.44 | 0.44 | 0.42 | 0.47 | 0.42 | 0.42 | 0.49 | 0.44 | 0.44 | 0.47 | 0.42 | 0.49 | 0.47 | 0.45 | 0.42 | 0.45 | 0.45 | 0.42 | 0.49 | 0.42 | 0.47 | 0.47 | 0.42 | 0.49 | 0.45 | 0.45 | 0.41 | 0.41 | 0.46 | 0.41 | 0.46 | 0.43 | 0.46 | 0.43 | 0.46 | 0.48 | 0.35
MEIGHAN | 14 - Modular Coils | 0.71 | 0.87 | 1.16 | 1.06 | 1.05 | 0.37 | 0.38 | 0.37 | 0.37 | 0.35 | 0.67 | 0.65 | 0.65 | 0.75 | 0.68 | 0.68 | 0.72 | 0.65 | 0.75 | 0.68 | 0.68 | 0.65 | 0.55 | 0.68 | 0.65 | 0.75 | 0.65 | 0.72 | 0.72 | 0.65 | 0.75 | 0.29
MYATT | 13 - Conventional Coils | 0.12 | 0.14 | 0.54
MYATT | 14 - Modular Coils | 0.56 | 0.64 | 0.62 | 0.18
NELSON | 14 - Modular Coils | 0.4 | 0.26 | 0.25 | 0.2
NELSON | 19 - Stellarator Core Management and Integration | 0.53 | 0.61 | 0.59 | 0.53 | 0.59 | 0.56 | 0.59 | 0.56 | 0.66 | 0.63 | 0.54 | 0.63 | 0.63 | 0.73 | 0.66 | 0.66 | 0.69 | 0.63 | 0.73 | 0.66 | 0.66 | 0.63 | 0.53 | 0.66 | 0.63 | 0.72 | 0.63 | 0.69 | 0.69 | 0.63 | 0.72 | 0.63 | 0.72 | 0.66 | 0.53 | 0.72 | 0.66 | 0.72 | 0.69 | 0.72 | 0.69 | 0.69 | 0.76 | 0.16 | 0.82 | 0.74 | 0.78 | 0.82 | 0.75 | 0.75 | 0.82 | 0.78
NEUMEYER | 81 - Project Management and Control
OLIARO | 51 - TCP/IP Infrastructure Systems | 0.04 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.04 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | [10 empty] | 0.05 | 0.11 | 0.16 | 0.34 | 0.43 | 0.6 | 0.54 | 0.6 | 0.57 | 0.35
OLIARO | 52 - Central Instrumentation & Control | [25 empty] | 0.44 | 0.44 | 0.89 | 1.01 | 0.92 | 1.06 | 1.07 | 1.23 | 1.12 | 0.9 | 1.23 | 1.12 | 1.23 | 1.18 | 0.84
OLIARO | 53 - Data Acquisition & Facility Computing | [25 empty] | 0.8 | 0.89 | 0.83 | 0.76 | 0.69 | 0.79 | 0.84 | 1.02 | 0.92 | 0.74 | 1.02 | 0.92 | 1.02 | 0.97 | 0.79
OLIARO | 54 - Facility Timing & Synchronization | [28 empty] | 0.73 | 0.67 | 0.79 | 0.69 | 0.76 | 0.86 | 0.71 | 0.98 | 0.89 | 0.98 | 0.93 | 0.76
OLIARO | 55 - Real Time Plasma & Power | [30 empty] | 0.26 | 0.22 | 0.52 | 0.33 | 0.4 | 0.55 | 0.5 | 0.55 | 0.53 | 0.15
OLIARO | 56 - Central Safety Interlock | [27 empty] | 0.14 | 0.25 | 0.23 | 0.26 | 0.34 | 0.49 | 0.6 | 0.72 | 0.99 | 0.9 | 0.99 | 0.95
OLIARO | 57 - Control Room Facility | [31 empty] | 0.22 | 0.24 | 0.46 | 0.22 | 0.25 | 0.23 | 0.25 | 0.11
OLIARO | 85 - Integrated Systems Testing | [40 empty] | 0.57 | 0.63 | 0.71 | 0.6 | 0.44 |  | 0.29
ORNL DESIGN | 12 - Vacuum Vessel Systems | 1.36 | 1.56 | 1.16
ORNL DESIGN | 18 - Field Period Assembly | 0.96 | 1.1 | 1.05 | 0.96 | 1.05 | 1.01 | 1.05 | 1.01
ORNL ENGR | 13 - Conventional Coils | 0.04 | 0.05 | 0.04 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.08 | 0.07 | 0.06 | 0.08 | 0.09 | 0.1 | 0.12 | 0.13 | 0.13 | 0.12 | 0.17 | 0.15 | 0.05 | 0.04 | 0.04 | 0.06 | 0.09 | 0.07 | 0.06 | 0.07 | 0.08 | 0.08 | 0.09 | 0.08 | 0.07 | 0.06 | 0.04 | 0.05 | 0.04
ORNL ENGR | 14 - Modular Coils | 0.3
ORNL ENGR | 15 - Structures | [18 empty] | 0.03 | 0.03 | 0.05 | 0.04 | 0.04 | 0.05 | 0.04 | 0.05 | 0.04 | 0.05 | 0.05 | 0.04 | 0.02 | 0.01
ORNL ENGR | 16 - Coil Services | [22 empty] | 0.41 | 0.51 | 0.48 | 1.01 | 1.05 | 1.15 | 0.14 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.09 | 0.27 | 0.24 | 0.16 | 0.04 | 0.04 | 0.04 | 0.02
ORNL ENGR | 17 - Cryostat and Base Support Structure | [7 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 |  |  | 0.18 | 0.22 | 0.21 | 0.24 | 0.21 | 0.23 | 0.23 | 0.05
ORNL ENGR | 19 - Stellarator Core Management and Integration | 0.16 | 0.09 | 0.23 | 0.52 | 0.57 | 0.18
PERRY | 73 - Platform Design & Fabrication | 0.25 |  |  |  |  | 0.29 | 0.3 | 0.29 | [12 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0
PERRY | 74 - Machine Assembly Planning and Oversight | 0.42 | 0.48 | 0.46 | 0.42 | 0.46 | 0.44 | 0.46 | 0.44 | 0.45 | 0.43 | 0.37 | 0.43 | 0.43 | 0.5 | 0.45 | 0.45 | 0.48 | 0.43 | 0.5 | 0.45
PERRY | 76 - Tooling Design & Fabrication | [8 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01
RAFTOPOULOS | 12 - Vacuum Vessel Systems |  | 1 | 0.05 | 0.18 | 0.55 | 0.34
RAFTOPOULOS | 14 - Modular Coils | 0.29 | 0.33 | 0.32 | 0.29 | 0.32 | [6 empty] | 0.17 | 0.42 | 0.48 | 0.44 | 0.44 | 0.46 | 0.42 | 0.48 | 0.44 | 0.44 | 0.42 | 0.35 | 0.44 | 0.42 | 0.48 | 0.42 | 0.46 | 0.46 | 0.42 | 0.13
RAFTOPOULOS | 18 - Field Period Assembly | 0.3 | 0.34 | 0.33 | 0.3 | 0.33 | 0.31 | 0.33 | 0.71 | 0.42 | 0.18 |  |  | 0 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0
RAKI | 41 - AC Power | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.24 | 0.23 | 0.2 | 0.23 | 0.21 | 0.18 | 0.16 | 0.16 | 0.17 | 0.16 | 0.13 | 0.02 | 0.11 | 0.13 | 0.11 | 0.14 | 0.13 | 0.24 | 0.21 | 0.29 | 0.2 | 0.14 | 0.17 | 0.15 | 0.29 | 0.25 | 0.2 | 0.27 | 0.25 | 0.03 | 0.1 | 0.17 | 0.16 | 0.07
RAKI | 42 - AC/DC Converters | [32 empty] | 0.06 | 0.05 | 0.04 | 0.06 | 0.05
RAKI | 43 - DC Systems |  | 0.24 | 0.26 | 0.66 | 0.5 | 0.56 | 0.23 | 0.07 | 0.32 | 0.23 | 0.15 | 0.18 | 0.18 | 0.21 | 0.19 | 0.19 | 0.07 | 0.05 | 0.06 | 0.04 | 0.13 | 0.18 | 0.15 | 0.19 | 0.18 | 0.21 | 0.18 | 0.15 | 0.02 | 0.01 | 0.17 | 0.18 | 0.28 | 0.26 | 0.21 | 0.16 | 0.14 | 0.07 | 0.05 | 0.05 | 0.01
RAKI | 44 - Control and protection Systems |  | 0.36 | 0.34 | 0.31 | 0.34 | 0.33 | 0.34 | 0.02 | 0.38 | 0.37 | 0.31 | 0.37 | 0.37 | 0.42 | 0.34 | 0.27 | 0.28 | 0.26 | 0.29 | 0.37 | 1.53 | 1.51 | 0.97 | 1.14 | 0.84 | 0.56 | 0.56 | 0.79 | 0.83 | 0.72 | 0.97 | 0.93 | 1.51 | 1.19 | 0.75 | 0.59 | 0.2 | 0.18 | 0.06
RAKI | 45 - Power System Design and Integration | 0.41 | 0.47 | 0.44 | 0.43 | 0.19 | 0.18 | 0.19 | 0.18 | 0.79 | 0.75 | 0.35 | 0.26 | 0.23 | 0.27 | 0.24 | 0.24 | 0.26 | 0.23 | 0.32 | 0.32 | 0.83 | 0.86 | 0.66 | 0.73 | 0.55 | 0.28 | 0.24 | 0.27 | 0.29 | 0.26 | 0.3 | 0.26 | 0.54 | 0.59 | 0.45 | 0.62 | 0.53 | 0.28 | 0.18 | 0.19 | 0.18 | 0.18 | 0.2 | 0.16 | 0.08
RAKI | 46 - FCPC Building Modifications |  |  | 0.1 | 0.09 | 0.1 |  |  |  | 0.02 | 0.02 | 0.01 | 0.01 |  |  | 0.04 | 0.05 | 0.05 | 0.01 |  |  | 0.01 | 0.02 | 0.01 | 0.01
REIERSEN | 82 - Project Engineering | 0.72 | 0.82 | 0.79 | 0.72 | 0.79 | 0.75 | 0.79 | 0.75
ROSSI | 25 - Neutral Beam Injection System | 0.3 | 0.34 | 0.33 | 0.3 | 0.33
RUSHINSKI | 13 - Conventional Coils | 0.42 | 0.49 | 0.41 | 0.34 | 0.38 | 0.36 | 0.38 | 0.36 | 0.45 | 0.43 | 0.37 | 0.45 | 0.46 | 0.53 | 0.58 | 0.6 | 0.63 | 0.57 | 0.72 | 0.66 | 0.09 | 0.08 | 0.08 | 0.13 | 0.16 | 0.13 | 0.11 | 0.12 | 0.12 | 0.11 | 0.13 | 0.11 | 0.09 | 0.09 | 0.07 | 0.09 | 0.07
RUSHINSKI | 15 - Structures | 0.15 | 1.2 | 0.41 | 0.24 | 0.26 | 0.03 | 0.22
RUSHINSKI | 17 - Cryostat and Base Support Structure | [7 empty] | 0.03 | 0.09 | 0.09 | 0.07 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.06
STEVENSON | 25 - Neutral Beam Injection System | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | 0.08 | 0.09 | 0.08 | 0.08 | 0.09 | 0.08 | 0.08 | 0.18 | 0.18 | 0.2 | 0.19 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.2 | 0.18 | 0.19 | 0.19 | 0.18 | 0.2 | 0.18 | 0.19 | 0.18 | 0.18 | 0.19 | 0.18 | 0.19 | 0.18 | 0.19 | 0.14
STRICKLER | 19 - Stellarator Core Management and Integration | 0.48 | 0.57 | 0.55 | 0.53 | 0.25 | 0.42 | 0.65 | 0.63 | 0.18
TITUS | 12 - Vacuum Vessel Systems |  | 1.15 | 0.35 | 0.5
VANKIRK | 41 - AC Power | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.5 | 0.48 | 0.41 | 0.48 | 0.44 | 0.39 | 0.35 | 0.35 | 0.37 | 0.34 | 0.26 | 0.02 | 0
VANKIRK | 43 - DC Systems |  | 0.27 | 0.26 | 0.71 | 0.7 | 0.68 | 0.18 |  | 0.45 | 0.42 | 0.36 | 0.42 | 0.42 | 0.49 | 0.45 | 0.45 | 0.16 | 0.1 | 0.11 | 0.07
VANKIRK | 44 - Control and protection Systems |  | 0.18 | 0.17 | 0.15 | 0.17 | 0.16 | 0.17 | 0.01 | 0.43 | 0.41 | 0.35 | 0.41 | 0.41 | 0.47 | 0.35 | 0.27 | 0.28 | 0.26 | 0.29 | 0.27 | 0.27 | 0.26 | 0.22 | 0.27 | 0.22
VANKIRK | 45 - Power System Design and Integration | 0.26 | 0.3 | 0.51 | 0.48 | 0.26 | 0.25 | 0.26 | 0.25 | 0.71 | 0.68 | 0.29 | 0.19 | 0.16 | 0.18 | 0.17 | 0.17 | 0.17 | 0.16 | 0.18 | 0.17 | 0.28 | 0.27 | 0.16 | 0.17 | 0.16 | 0.18 | 0.16 | 0.17 | 0.17 | 0.16 | 0.18 | 0.16 | 0.17 | 0.16 | 0.13 | 0.17 | 0.16 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.18 | 0.15 | 0.07
VANKIRK | 46 - FCPC Building Modifications |  |  | 0.14 | 0.13 | 0.14 |  |  |  | 0.03 | 0.03 | 0.03 | 0.01 |  |  | 0.03 | 0.03 | 0.03 | 0
VIOLA | 12 - Vacuum Vessel Systems | 0.44 | 0.63 | 0.53 | 0.83 | 1.1 | 0.73 | 0.26 | 0.25 | 0.25 | 0.23 | 0.26 | 0.23 | 0.23 | 0.25 | 0.23 | 0.23 | 0.25 | 0.24 | 0.28 | 0.27 | 0.26 | 0.02 | 0.03 | 0.02 | 0.02 | 0
VIOLA | 14 - Modular Coils | [11 empty] | 0.04 | 0.09 | 0.11 | 0.1 | 0.1 | 0.1 | 0.09 | 0.11 | 0.1 | 0.1 | 0.09 | 0.08 | 0.1 | 0.09 | 0.11 | 0.09 | 0.1 | 0.1 | 0.09 | 0.03
VIOLA | 18 - Field Period Assembly | 0.21 | 0.24 | 0.23 | 0.21 | 0.23 | 0.22 | 0.23 | 0.22 | 0.42 | 0.4 | 0.34 | 0.4 | 0.4 | 0.46 | 0.42 | 0.42 | 0.44 | 0.4 | 0.46 | 0.42 | 1.36 | 1.29 | 1.1 | 1.36 | 1.29 | 1.49 | 1.29 | 1.42 | 1.42 | 1.29 | 1.49 | 1.29 | 0.06
WELDER | 12 - Vacuum Vessel Systems |  |  |  | 0.3 | 0.7
WELDER | 14 - Modular Coils
WILLIAMSON | 14 - Modular Coils | 2.71 | 4.63 | 4.22 | 1.51 | 1.32 | 0.73 | 1.3 | 0.24 | 0.9 | 1.07 | 0.82 | 0.86 | 0.86 | 0.99 | 1 | 1.09 | 0.95 | 0.86 | 0.99 | 0.9 | 1.41 | 1.31 | 1.07 | 0.98 | 0.9 | 1.04 | 0.9 | 0.95 | 0.95 | 0.86 | 0.99 | 0.86
WILLIAMSON | 16 - Coil Services | [20 empty] | 0.17 | 0.16 | 0.85 | 1.12 | 1.1 | 1.05 | 0.84 | 0.93 | 0.93 | 0.84 | 0.97 | 0.84 | 0.93 | 0.84 | 0.42 | 0.01 | 0.01 | 0.01
ZATZ | 14 - Modular Coils |  | 0.37 | 0.13
ZATZ | 19 - Stellarator Core Management and Integration

## SUMMARY BY NAME
| ACT ID | FEB FY04 | MAR FY04 | APR FY04 | MAY FY04 | JUN FY04 | JUL FY04 | AUG FY04 | SEP FY04 | OCT FY05 | NOV FY05 | DEC FY05 | JAN FY05 | FEB FY05 | MAR FY05 | APR FY05 | MAY FY05 | JUN FY05 | JUL FY05 | AUG FY05 | SEP FY05 | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08
EA//EM - PPPL Analysis engineer
| BROOKS | 0.75 | 0.86 | 0.69 | 0.66 | 0.9 | 0.86 | 0.9 | 0.86 | 0.51 | 0.48 | 0.41 | 0.48 | 0.48 | 0.56 | 0.51 | 0.51 | 0.53 | 0.48 | 0.56 | 0.51
| BROWN | 0.87 | 0.85 | 0.69 | 0.63 | 0.69 | 0.66 | 0.69 | 0.66
| CHRZANOWSK | 0.56 | 0.69 | 0.97 | 0.88 | 0.88 | 0.33 | 0.35 | 0.33 | 0.33 | 0.32 | 0.65 | 0.65 | 0.65 | 0.75 | 0.68 | 0.68 | 0.72 | 0.65 | 0.75 | 0.68 | 0.68 | 0.65 | 0.55 | 0.68 | 0.65 | 0.75 | 0.65 | 0.72 | 0.72 | 0.65 | 0.75 | 0.29
| DAHLGREN | 1.51 | 1.19 | 1.02 |  |  | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09
| EA ENGR TB | [8 empty] | 1.6 | 1.52 | 1.68 | 1.52 | 1.52 | 1.75 | 1.6 | 1.6 | 1.68 | 1.52 | 1.75 | 1.68 | 1.43 | 1.36 | 1.56 | 1.59 | 1.51 | 1.88 | 1.69 | 1.92 | 1.97 | 1.76 | 1.94 | 1.74 | 1.8 | 1.56 | 1.49 | 1.69 | 1.53 | 1.69 | 1.61 | 1.61 | 1.4 | 1.46 | 1.53 | 1.24 | 0.86 | 0.74 | 0.74 | 0.82 | 0.78 | 0.78 | 0.82 | 0.82
| FAN | 1.38 | 1.6 | 1.76 | 0.03
| HEITZENROE | 0.42 | 0.96 | 2.14 | 0.44 | 0.38 | 0.25 | 0.32 | 0.33 | 0.61 | 0.46 | 0.06 | 0.07 | 0.07 | 0.08 | 0.08 | 0.08 | 0.08 | 0.07 | 0.41 | 0.46 | 0.46 | 0.43 | 0.37 | 0.46 | 0.43 | 0.5 | 0.43 | 0.48 | 0.48 | 0.43 | 0.16 | 0.07
| JUN | 0.54 | 0.62 | 0.58 | 0.52
| KALISH | 0.9 | 1.28 | 2.01 | 0.37 | 0.41 | 0.39 | 0.41 | 0.39 | 0.34 | 0.33 | 0.28 | 0.45 | 0.52 | 0.6 | 0.75 | 0.79 | 0.83 | 0.75 | 1.09 | 1 | 0.47 | 0.45 | 0.4 | 0.62 | 0.84 | 0.76 | 0.63 | 0.69 | 0.69 | 0.63 | 0.72 | 0.63 | 0.48 | 0.44 | 0.35 | 0.48 | 0.37
| KU | 0.23 | 0.33 | 0.2
| MYATT | 0.68 | 0.79 | 1.15 | 0.18
| RAFTOPOULO | 0.59 | 1.68 | 0.7 | 0.77 | 1.2 | 0.65 | 0.33 | 0.71 | 0.42 | 0.18 |  | 0.17 | 0.42 | 0.52 | 0.48 | 0.48 | 0.5 | 0.46 | 0.52 | 0.48 | 0.48 | 0.46 | 0.39 | 0.48 | 0.46 | 0.52 | 0.46 | 0.5 | 0.5 | 0.46 | 0.17 | 0.04 | 0
| REIERSEN | 0.72 | 0.82 | 0.79 | 0.72 | 0.79 | 0.75 | 0.79 | 0.75
| RUSHINSKI | 0.57 | 1.68 | 0.82 | 0.58 | 0.64 | 0.39 | 0.59 | 0.36
| TITUS |  | 1.15 | 0.35 | 0.5
| ZATZ |  | 0.37 | 0.13
|  | 9.72 | 14.87 | 14 | 6.28 | 5.89 | 4.37 | 4.48 | 4.48 | 3.9 | 3.38 | 3.18 | 3.43 | 3.75 | 4.26 | 4.1 | 4.14 | 4.34 | 3.93 | 5.08 | 4.81 | 3.52 | 3.35 | 3.27 | 3.83 | 3.89 | 4.41 | 3.86 | 4.31 | 4.36 | 3.93 | 3.74 | 2.77 | 2.28 | 2 | 1.84 | 2.17 | 1.9 | 1.69 | 1.61 | 1.61 | 1.4 | 1.46 | 1.53 | 1.24 | 0.86 | 0.74 | 0.74 | 0.82 | 0.78 | 0.78 | 0.82 | 0.82 | 0 | 0 | 0 | 0
EA//SM - PPPL Designer
| ELECT DESI | [18 empty] | 0.27 | 0.4 | 2.32 | 2.55 | 1.86 | 1.78 | 1.1 | 0.93 | 0.76 | 0.66 | 0.06 | 0.01 | 0.55 | 0.62 | 0.73 | 0.25 | 0.17 | 0.23 | 0.21 | 0.23 | 0.19 | 0.11
JONES
| MECH DESIG | 1.12 | 1.28 | 1.23 | 1.7 | 1.87 | 2.4 | 2.52 | 2.23 | 1.13 | 1.08 | 1.06 | 1.08 | 1.08 | 1.24 | 1.13 | 1.13 | 1.18 | 1.28 | 2.28 | 2.05 | 2.24 | 1.93 | 1.27 | 2.44 | 2.32 | 2.54 | 1.39 | 1.35 | 1.93 | 1.84 | 2.87 | 2.99 | 3.17 | 1.9 | 1.08 | 1.15 | 1.05 | 1.15 | 1.01 | 1.06 | 0.79 | 0.65 | 0.69 | 0.53 | 0.21 | 0.18
| RUSHINSKI | [7 empty] | 0.03 | 0.54 | 0.52 | 0.44 | 0.53 | 0.54 | 0.62 | 0.67 | 0.69 | 0.72 | 0.66 | 0.82 | 0.72 | 0.09 | 0.08 | 0.08 | 0.13 | 0.16 | 0.13 | 0.11 | 0.12 | 0.12 | 0.11 | 0.12 | 0.11 | 0.09 | 0.08 | 0.06 | 0.09 | 0.07
| VANKIRK | 0.27 | 0.76 | 1.09 | 1.49 | 1.28 | 1.09 | 0.61 | 0.27 | 2.12 | 2.02 | 1.43 | 1.51 | 1.43 | 1.53 | 1.35 | 1.27 | 1.02 | 0.85 | 0.85 | 0.52 | 0.56 | 0.52 | 0.37 | 0.43 | 0.38 | 0.18 | 0.16 | 0.17 | 0.17 | 0.16 | 0.18 | 0.16 | 0.17 | 0.16 | 0.13 | 0.17 | 0.16 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.18 | 0.15 | 0.07
|  | 1.39 | 2.04 | 2.32 | 3.19 | 3.15 | 3.49 | 3.13 | 2.53 | 3.79 | 3.62 | 2.93 | 3.12 | 3.05 | 3.39 | 3.15 | 3.09 | 2.92 | 2.79 | 4.22 | 3.69 | 5.21 | 5.08 | 3.58 | 4.78 | 3.96 | 3.78 | 2.42 | 2.3 | 2.28 | 2.12 | 3.72 | 3.88 | 4.16 | 2.39 | 1.44 | 1.64 | 1.49 | 1.55 | 1.37 | 1.34 | 0.96 | 0.82 | 0.87 | 0.68 | 0.28 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EC//EM - PPPL Comuter Engineer
| OLIARO | 0.04 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.04 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | [5 empty] | 1.24 | 1.33 | 1.86 | 2.76 | 2.51 | 3.21 | 3.5 | 4.43 | 4.63 | 4.13 | 5.62 | 5.11 | 5.62 | 5.24 | 2.88 | 0.57 | 0.63 | 0.71 | 0.6 | 0.44 |  | 0.29
EC//SM - PPPL Computer Senior Tech
| COMPUTER S | [31 empty] | 0.33 | 0.48 | 1.8 | 2.15 | 3.04 | 2.76 | 3.04 | 2.66 | 1.25
EE//EM - PPPL Electrical engineer
| ELECT ENGR | 0.13 | 0.14 | 0.14 | 0.13 | 0.14 | 0.13 | 0.14 | 0.13 |  |  | 0.1 | [6 empty] | 0.21 | 0.98 | 0.9 | 1.25 | 1.02 | 0.41 | 0.5 | 0.42 | 0.42 | 0.45 | 0.27 | 0.27 | 0.25 | 0.16 |  | 0.07 | 0.07 | 0.06 | 0.08 | 0.07 | 0.02 |  |  | 0.44 | 0.49 | 0.54 | 0.46 | 0.34 |  | 0.22
| HATCHER | [6 empty] | 0.25
| MARSALA | [13 empty] | 0.07 | 0.11 | 0.11 | 0.11 | 0.1 | 0.12 | 0.11 | 0.11 | 0.1 | 0.09 | 0.11 | 0.1 | 0.12 | 0.1 | 0.11 | 0.11 | 0.1 | 0.03
NEUMEYER
| RAKI | 0.43 | 1.09 | 1.17 | 1.51 | 1.16 | 1.09 | 0.78 | 0.29 | 1.76 | 1.6 | 1.03 | 1.04 | 0.99 | 1.08 | 0.98 | 0.92 | 0.83 | 0.7 | 0.8 | 0.75 | 2.62 | 2.69 | 1.9 | 2.21 | 1.7 | 1.28 | 1.19 | 1.5 | 1.35 | 1.14 | 1.61 | 1.52 | 2.68 | 2.34 | 1.65 | 1.7 | 1.17 | 0.56 | 0.39 | 0.41 | 0.35 | 0.25 | 0.2 | 0.16 | 0.08
| STEVENSON | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | 0.08 | 0.09 | 0.08 | 0.08 | 0.09 | 0.08 | 0.08 | 0.18 | 0.18 | 0.2 | 0.19 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.2 | 0.18 | 0.19 | 0.19 | 0.18 | 0.2 | 0.18 | 0.19 | 0.18 | 0.18 | 0.19 | 0.18 | 0.19 | 0.18 | 0.19 | 0.14
|  | 0.57 | 1.25 | 1.32 | 1.65 | 1.31 | 1.23 | 1.18 | 0.43 | 1.84 | 1.68 | 1.22 | 1.12 | 1.07 | 1.24 | 1.17 | 1.11 | 1.12 | 1.19 | 2.1 | 1.95 | 4.16 | 3.99 | 2.58 | 3 | 2.4 | 2.02 | 1.92 | 2.07 | 1.92 | 1.67 | 2 | 1.7 | 2.94 | 2.59 | 1.89 | 1.97 | 1.42 | 0.77 | 0.57 | 0.6 | 0.93 | 0.74 | 0.74 | 0.62 | 0.42 | 0 | 0.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EE//SM - PPPL Electrical Senior Tech
| CARSON | 0.26 | 0.3 | 0.29 | 0.26 | 0.26 | 0.09 | 0.09 | 0.09
| EDWARDS | [5 empty] | 0.02 | 0.14
| ELEC TECH | [20 empty] | 0.05 | 0.04 | 0.04 | 0.05 | 0.04 | 0.05 | 0.04
| ELECT SM | 0.01 | 0.11 | 0.17 | 0.45 | 0.31 | 0.31 | 0.11 | 0.15 | 0.3 | 0.13 | 0.16 | 0.03 | 0.03 | 0.12 | 0.19 | 0.2 | 0.21 | 0.17 | 0.18 | 0.17 | 0.6 | 0.67 | 0.71 | 1.72 | 1.87 | 2.97 | 2.24 | 2.29 | 2.4 | 2.13 | 2.47 | 1.83 | 4.1 | 4.62 | 5.5 | 6.55 | 5.55 | 4.86 | 4.31 | 2.15 | 1.97 | 1.44 | 1.41 | 1.2 | 0.89 |  | 0.59
| ELECT TB |  |  | 0.28 | 0.52 | 0.57 | 0.05
| GERNHARDT | 0.23 | 0.26 | 0.02 |  |  |  | 0.28
| GIBILISCO | 0.01 | 0.02 | 0.02 | 0.01
| MARSALA |  | 0.1 | 0.09 | 0.08 | 0.09 | 0.09 | 0.09 | 0
| MCBRIDE | 0.14 | 0.16 | 0.01
| ROSSI | 0.3 | 0.34 | 0.33 | 0.3 | 0.33
|  | 0.95 | 1.29 | 1.21 | 1.62 | 1.56 | 0.56 | 0.71 | 0.24 | 0.3 | 0.13 | 0.16 | 0.03 | 0.03 | 0.12 | 0.19 | 0.2 | 0.21 | 0.17 | 0.18 | 0.17 | 0.65 | 0.71 | 0.75 | 1.77 | 1.91 | 3.02 | 2.28 | 2.29 | 2.4 | 2.13 | 2.47 | 1.83 | 4.1 | 4.62 | 5.5 | 6.55 | 5.55 | 4.86 | 4.31 | 2.15 | 1.97 | 1.44 | 1.41 | 1.2 | 0.89 | 0 | 0.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EE//TB - PPPL Electrical Technician
| ELEC TECH | [20 empty] | 0.07 | 0.06 | 0.05 | 0.07 | 0.06 | 0.07 | 0.06
| ELECT TB | 0.02 | 0.15 | 0.35 | 0.56 | 1.68 | 1.46 | 0.84 | 0.17 | 0.26 | 0.1 | 0.45 | 0.2 | 0.31 | 0.65 | 0.75 | 0.71 | 0.74 | 0.57 | 0.53 | 0.48 | 0.93 | 1.01 | 0.88 | 1.12 | 1.34 | 2.68 | 2.57 | 3.37 | 3.8 | 3.57 | 4.59 | 3.99 | 5.81 | 4.82 | 3.08 | 3.06 | 1.83 | 0.55 | 0.45 | 0.59 | 0.57 | 0.24
| HALVORSEN | 0.01 | 0.01 | 0.01 | 0.01
|  | 0.03 | 0.16 | 0.36 | 0.57 | 1.68 | 1.46 | 0.84 | 0.17 | 0.26 | 0.1 | 0.45 | 0.2 | 0.31 | 0.65 | 0.75 | 0.71 | 0.74 | 0.57 | 0.53 | 0.48 | 1 | 1.07 | 0.93 | 1.19 | 1.4 | 2.75 | 2.63 | 3.37 | 3.8 | 3.57 | 4.59 | 3.99 | 5.81 | 4.82 | 3.08 | 3.06 | 1.83 | 0.55 | 0.45 | 0.59 | 0.57 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EM//EM - PPPL FO&M Engineer
| BLANCHARD | [8 empty] | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.41 | 0.39 | 0.4 | 0.1 | 0.04 | 0.05 | 0.18 | 0.24 | 0.22 | 0.07 | 0.03 | 0.02 | 0.08 | 0.08 | 0.08 | 0.12 | 0.11 | 0.03
| DUDEK | 0.29 | 0.34 | 0.32 | 0.29 | 0.32 | 0.31 | 0.32 | 0.31
| FOM ENGR | [8 empty] | 0.54 | 0.51 | 0.69 | 0.51 | 0.51 | 0.59 | 0.54 | 0.54 | 0.57 | 0.51 | 0.59 | 0.56 | 1.28 | 1.22 | 1.1 | 1.28 | 1.13 | 1.2 | 2.06 | 2.53 | 3.16 | 3.04 | 3.5 | 3.02 | 3.41 | 2.84 | 2.2 | 3.29 | 3.33 | 3.48 | 2.63 | 1.98 | 2.67 | 2.8 | 3.03 | 2.63 | 3.35 | 2.19 | 1.55 | 1.1 | 1.02 | 1.02 | 1.07 | 1.04
| GETTLEFING | 0.41 | 0.47 | 0.09 | 0.91 | 1 | 0.96 | 1.25 | 0.73 | 0.63 | 0.6 | 0.51 | 0.6 | 0.6 | 0.74 | 0.71 | 0.71 | 0.75 | 0.68 | 0.78 | 0.53 | 0.08 | 0.08 | 0.11 | 0.15 | 0.14 | 0.16 | 0.14 | 0.15 | 0.15 | 0.1 | 0.04 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
| KEILBACH | 0.1 | 0.1
| KOZUB | 0.94 | 1.06
| PERRY | 0.67 | 0.48 | 0.46 | 0.42 | 0.46 | 0.73 | 0.76 | 0.73 | 0.47 | 0.45 | 0.38 | 0.45 | 0.45 | 0.51 | 0.47 | 0.47 | 0.49 | 0.45 | 0.51 | 0.47 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.02 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.01
| VIOLA | 0.65 | 0.86 | 0.76 | 1.03 | 1.32 | 0.95 | 0.48 | 0.46 | 0.67 | 0.63 | 0.6 | 0.67 | 0.73 | 0.82 | 0.75 | 0.75 | 0.79 | 0.74 | 0.85 | 0.79 | 1.71 | 1.41 | 1.2 | 1.48 | 1.4 | 1.6 | 1.39 | 1.53 | 1.53 | 1.39 | 1.52 | 1.29 | 0.06
|  | 3.06 | 3.31 | 1.63 | 2.65 | 3.1 | 2.95 | 2.81 | 2.23 | 2.35 | 2.23 | 2.22 | 2.27 | 2.33 | 2.71 | 2.52 | 2.52 | 2.65 | 2.42 | 2.78 | 2.4 | 3.5 | 3.12 | 2.83 | 3.03 | 2.73 | 3.04 | 3.79 | 4.46 | 5.07 | 4.61 | 5.11 | 4.35 | 3.57 | 2.94 | 2.3 | 3.43 | 3.46 | 3.53 | 2.64 | 1.99 | 2.68 | 2.81 | 3.05 | 2.64 | 3.35 | 2.19 | 1.55 | 1.1 | 1.02 | 1.02 | 1.07 | 1.04 | 0 | 0 | 0 | 0
EM//SM - PPPL FO&M Senior Tech
| DELANY | 0.25 | 0.19
| FIELDTECHS | [25 empty] | 0.05 | 0.9 | 0.75 | 0.8 | 0.65 | 0.6
| FOM TECHS | 0.46 | 0.53 | 0.51 |  | 0.4 | 0.15 |  | 0.18 | 1.13 | 1 | 0.69 | 0.8 | 0.74 | 0.96 | 0.69 | 0.62 | 0.65 | 0.59 | 0.68 | 0.62 | 1.46 | 1.53 | 1.7 | 2.96 | 3.14 | 5.16 | 4.84 | 6.26 | 6.41 | 7.34 | 8.96 | 7.79 | 9.1 | 7.2 | 4.9 | 5.36 | 4.65 | 4.94 | 3.01 | 2.33 | 1.51 | 1.45 | 1.55 | 1.44 | 3.03 | 2.52 | 0.92 | 0.75 | 0.68 | 0.68 | 0.71 | 0.68
| JURZYNSKI | 0.94 | 1.06
| MACHINIST | 1.21 | 1.01 | 2.75 | 2.96 | 2.17 | 0.73 | 0.38 | 0.28 | 2.23 | 2.74 | 3.78 | 2.66 | 1.28 | 1.6 | 1.66 | 2.29 | 2.58 | 0.83 | 1.33 | 1.74 | 1.66 | 1.58 | 0.55 |  |  | 0.02 | 0.38 | 0.38 | 0.4 | 0.33 | 0.3
| MEIGHAN | 0.71 | 0.87 | 1.16 | 1.06 | 1.05 | 0.37 | 0.38 | 0.37 | 0.37 | 0.35 | 0.67 | 0.65 | 0.65 | 0.75 | 0.68 | 0.68 | 0.72 | 0.65 | 0.75 | 0.68 | 0.68 | 0.65 | 0.55 | 0.68 | 0.65 | 0.75 | 0.65 | 0.72 | 0.72 | 0.65 | 0.75 | 0.29
| RUSHINSKI | [28 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0
| WELDER |  |  |  | 0.3 | 0.7
|  | 3.57 | 3.66 | 4.42 | 4.32 | 4.32 | 1.25 | 0.76 | 0.83 | 3.73 | 4.09 | 5.14 | 4.11 | 2.67 | 3.31 | 3.03 | 3.59 | 3.95 | 2.07 | 2.76 | 3.04 | 3.8 | 3.76 | 2.8 | 3.64 | 3.79 | 5.98 | 6.77 | 8.11 | 8.34 | 8.98 | 10.62 | 8.09 | 9.11 | 7.21 | 4.9 | 5.36 | 4.65 | 4.94 | 3.01 | 2.33 | 1.51 | 1.45 | 1.55 | 1.44 | 3.03 | 2.52 | 0.92 | 0.75 | 0.68 | 0.68 | 0.71 | 0.68 | 0 | 0 | 0 | 0
EM//TB - PPPL FO&M Technician
| FOM TECHS TB | 7.48 | 8.67 | 10.95 | 11.53 | 11.87 | 8.53 | 13.01 | 11.08 | 4.26 | 3.82 | 2.5 | 4.72 | 11.62 | 14.39 | 13.56 | 13.56 | 14.2 | 12.91 | 14.85 | 13.56 | 16.6 | 15.82 | 13.53 | 19.05 | 19.06 | 25.29 | 21.68 | 27.27 | 27.46 | 29.85 | 24.08 | 17.2 | 21.34 | 17.92 | 11.62 | 18.86 | 16.99 | 14.79 | 12.19 | 9.09 | 1.89 | 1.03 | 2.06 | 3.77 | 10.52 | 8.17 | 0.92
ORNLEM - ORNL Engineer
| COLE | 2.23 | 2.72 | 2.11 | 1.9 | 1.77 | 1.45 | 1.65 | 1.43 | 1.53 | 1.63 | 1.24 | 1.46 | 1.49 | 2.05 | 1.97 | 1.94 | 1.96 | 1.78 | 2.05 | 1.87 | 1.2 | 1.15 | 0.97 | 1.2 | 1.15 | 1.32 | 1.15 | 1.26 | 1.26 | 1.15 | 1.32 | 1.15 | 0.38 | 0.31 | 0.25 | 0.34 | 0.31 | 0.34 | 0.33 | 0.34 | 0.33 | 0.33 | 0.36 | 0.2 | 0.65 | 0.57 | 0.43 | 0.65 | 0.6 | 0.6 | 0.64 | 0.63 | 0.24
| FREUDENBER | 1.52 | 0.99 | 0.45
| GORANSON | 2.69 | 1.07 | 1.79 | 1.13 | 0.2 | 0.93 | 0.93 | 0.89 | 0.89 | 0.85 | 0.91 | 0.85 | 0.85 | 0.14 | 0.13 | 0.13 | 0.17 | 0.29 | 0.35 | 0.33 | 0.36 | 0.34 | 0.36 | 0.28 | 0.26 | 0.16 | 0.13 | 0.14 | 0.14 | 0.13 | 0.14 | 0.13 | 0.14 | 0.1
| HARGROVE | 0.77 | 1.23 | 1.38 | 0.16 | 0.12 | 0.32 | 0.94 | 0.43 | 0.43 | 0.53 | 0.1 | 0.41 | 0.41 | 0.47 | 0.53 | 0.19
| HIRSHMAN | 0.48 | 0.43 | 0.22 |  |  | 0.25 | 0.39 | 0.38 | 0.11
| JONES | 0.26 | 0.86 | 1.04 | 0.26 | 0.23 | 0.06 | 0.2 | 0.04 |  | 0.17 |  |  |  |  | 0.1 | 0.07
| LOVETT | 1.07 | 1.38 | 1.41 | 0.16 | 0.12 | 0.32 | 0.94 | 0.43 | 0.43 | 0.53 | 0.1 | 0.41 | 0.41 | 0.47 | 0.53 | 0.19
| NELSON | 0.93 | 0.87 | 0.83 | 0.73 | 0.59 | 0.56 | 0.59 | 0.56 | 0.66 | 0.63 | 0.54 | 0.63 | 0.63 | 0.73 | 0.66 | 0.66 | 0.69 | 0.63 | 0.73 | 0.66 | 0.66 | 0.63 | 0.53 | 0.66 | 0.63 | 0.72 | 0.63 | 0.69 | 0.69 | 0.63 | 0.72 | 0.63 | 0.72 | 0.66 | 0.53 | 0.72 | 0.66 | 0.72 | 0.69 | 0.72 | 0.69 | 0.69 | 0.76 | 0.16 | 0.82 | 0.74 | 0.78 | 0.82 | 0.75 | 0.75 | 0.82 | 0.78
| ORNL DESIG | 2.32 | 2.67 | 2.21 | 0.96 | 1.05 | 1.01 | 1.05 | 1.01
| ORNL ENGR | 0.5 | 0.14 | 0.27 | 0.6 | 0.66 | 0.27 | 0.09 | 0.09 | 0.09 | 0.08 | 0.07 | 0.09 | 0.1 | 0.11 | 0.13 | 0.14 | 0.14 | 0.13 | 0.21 | 0.19 | 0.09 | 0.09 | 0.67 | 0.84 | 0.82 | 1.37 | 1.36 | 1.5 | 0.51 | 0.21 | 0.15 | 0.13 | 0.11 | 0.1 | 0.13 | 0.31 | 0.28 | 0.16 | 0.04 | 0.04 | 0.04 | 0.02
| STRICKLER | 0.48 | 0.57 | 0.55 | 0.53 | 0.25 | 0.42 | 0.65 | 0.63 | 0.18
| WILLIAMSON | 2.71 | 4.63 | 4.22 | 1.51 | 1.32 | 0.73 | 1.3 | 0.24 | 0.9 | 1.07 | 0.82 | 0.86 | 0.86 | 0.99 | 1 | 1.09 | 0.95 | 0.86 | 0.99 | 0.9 | 1.57 | 1.46 | 1.92 | 2.1 | 2 | 2.08 | 1.74 | 1.87 | 1.87 | 1.7 | 1.96 | 1.7 | 0.93 | 0.84 | 0.42 | 0.01 | 0.01 | 0.01
|  | 15.96 | 17.56 | 16.48 | 7.94 | 6.31 | 6.32 | 8.73 | 6.13 | 5.22 | 5.49 | 3.78 | 4.71 | 4.75 | 4.96 | 5.05 | 4.41 | 3.91 | 3.69 | 4.33 | 3.95 | 3.88 | 3.67 | 4.45 | 5.08 | 4.86 | 5.65 | 5.01 | 5.46 | 4.47 | 3.82 | 4.29 | 3.74 | 2.28 | 2.01 | 1.33 | 1.38 | 1.26 | 1.23 | 1.06 | 1.1 | 1.06 | 1.04 | 1.12 | 0.36 | 1.47 | 1.31 | 1.21 | 1.47 | 1.35 | 1.35 | 1.46 | 1.41 | 0.24 | 0 | 0 | 0