## Cost Spread Sheet FY 01
ORNL COMPACT STELLARATOR SUPPORT NCSX - MONTHLY COST - FY 2003
ADVANCED CONCEPTUAL DESIGN - 35600300
AT501502
OPERATING FUNDS
PROPOSED
[15 empty] | Adjusted |  | ORNL/ENGR
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Total | Budget | % Used | Account | Remarks
| Work Package | [16 empty] | TOTAL FY 2003 BA + Carry over
Limiter Design | WBS 1101 | [15 empty] | 3560030A
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0%
Vacuum Vessel Design | WBS 1201 | [15 empty] | 3560030B
(Goranson) | Labor | 6028 | 12677 | 12354 | 20325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51384 |  |  | PEX00263
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 6028 | 12677 | 12354 | 20325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51384 | 96000 | 53.52% |  | 47500
Vacuum Vessel R & D | WBS 1202 | [15 empty] | 3560030C
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0%
Modular Coils Design | WBS 1401 | [15 empty] | 3560030D | 127389
(Williamson) | Labor | 14329 | 18677 | 20619 | 19611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73236 |  |  | PEX00264
| Material | 0 | 0 | 8960 | 4027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12987
| Sub | 14329 | 18677 | 29579 | 23638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86223 | 176000 | 48.99%
Modular Coil Analysis | WBS 1402 | [15 empty] | 3560030E | 0
(Williamson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0%
Modular Coil Winding Forms | WBS 1404 | [15 empty] | 3560030F | 32000
(Williamson) | Labor | 12558 | 6056 | 3045 | 7431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29090
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 12558 | 6056 | 3045 | 7431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29090 | 80000 | 36.36%
Stellarator Core Management | WBS 1901 | [15 empty] | 3560030G | 85999
and Integration | Labor | 19432 | 7118 | 16366 | 16728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59644 |  |  | PEX00265
| Material | 0 | 0 | 10533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10533
| Sub | 19432 | 7118 | 26899 | 16728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70177 | 176000 | 39.87%
Project Management and | WBS 8102 | [15 empty] | 3560030H | 51800
Control | Labor | 5911 | 15293 | 13670 | 7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42259
(Lyon, Benson, Akers) | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 5911 | 15293 | 13670 | 7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42259 | 32000 | 132.1%
Project Physics (Off-Site) | WBS 8402 | [15 empty] | 3560030I | 10000
(Lazarus) | Labor | 1175 | -118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 1175 | -118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1057 | 55000 | 1.922%
Program |  | 848 | 1573 | 1808 | 1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5744 | 15000 | 38.29% | 33440940 | 7335
Administration
GRAND | TOTAL | 60281 | 61276 | 87355 | 77022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285934 | 750000 | 38.12% |  | 362023
[15 empty] | Actual % used to Actual BA |  |  | 78.98%