## Cost Spread Sheet FY 01
ORNL COMPACT STELLARATOR SUPPORT NCSX - MONTHLY COST - FY 2004
FINAL DESIGN - K6872 | CAPITAL FUNDS (MIE)
AT5506000
PROPOSED
[15 empty] | Adjusted |  | ORNL/ENGR
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | TOTAL | Budget | % Used | Account | Remarks
| Work Package | [13 empty] | w/ Carryover
Limiter Design | WBS 1101 | [15 empty] | K6872LDD
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.41
ORNL | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.41 | 0%
Vacuum Vessel R & D | WBS 1202 | [15 empty] | K6872VVR
(Goranson) | Labor | 0 | 129 | 0 | 0 | 0 | 0 | 363.75 | 12727.06 | 2071.86 | 0 | 6984.55 | 3604.93 | 25881.15 | 542.41
ORNL | Material | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137
| Sub | 0 | 129 | 137 | 0 | 0 | 0 | 363.75 | 12727.06 | 2071.86 | 0 | 6984.55 | 3604.93 | 26018.15 | 542.41 | 4797%
Vacuum Vessel R & D | WBS 1202
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BWXT- MOU | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Vacuum Vessel Final Design | WBS 1203 | [15 empty] | K6872VVD
(Goranson) | Labor | 5535 | 1431 | 897 | 7173.32 | 2392.5 | 7007.49 | 36931.29 | 19759.58 | 52989.12 | 28391.76 | 20354.72 | 22137.4 | 205000.18 | 92461.4
ORNL | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 5535 | 1431 | 897 | 7173.32 | 2392.5 | 7007.49 | 36931.29 | 19759.58 | 52989.12 | 28391.76 | 20354.72 | 22137.4 | 205000.18 | 92461.4 | 221.7%
Vacuum Vessel Final Design | WBS 1203 | [15 empty] | K6872YVD
(Goranson) | Labor | 20782 | 24620 | 14898 | 20201.03 | 51271 | 59617.18 | 41161.35 | -4025.25 | 14710.16 | 6667.28 | 6746.05 | 0 | 256648.8 | 90000
BWXT - MOU | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 20782 | 24620 | 14898 | 20201.03 | 51271 | 59617.18 | 41161.35 | -4025.25 | 14710.16 | 6667.28 | 6746.05 | 0 | 256648.8 | 90000 | 285.2%
Vacuum Vessel Insulation H&C | WBS 1204
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNL | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Vacuum Vessel Insulation H&C | WBS 1204
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BWXT - MOU | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Modular Coil Analysis | WBS 1402 | [15 empty] | K6872MCA
(Williamson) | Labor | -1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1298 | 1537.3
ORNL | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | -1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1298 | 1537.3 | -84.43%
Modular Coil Analysis | WBS 1402 | [15 empty] | K6872YMA
(Williamson) | Labor | 27257 | 31670 | 26834 | 33512.48 | 4191.27 | 9289.06 | 13319.25 | 5545.75 | 24912.48 | 13382.71 | 21364.08 | 25478.44 | 236756.52 | 259500
BWXT-MOU | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 27257 | 31670 | 26834 | 33512.48 | 4191.27 | 9289.06 | 13319.25 | 5545.75 | 24912.48 | 13382.71 | 21364.08 | 25478.44 | 236756.52 | 259500 | 91.24%
Modular Coil Final Design | WBS 1403 | [15 empty] | K6872MCD
(Williamson) | Labor | 75259 | 59557 | 82117 | 102119.48 | 80224.22 | 105392.93 | 113539.13 | 115009.95 | 127971.3 | 99070 | 86838.33 | 123908.23 | 1171006.57 | 499957.69
ORNL | Material | 22801 | 0 | 0 | 2494 | 0 | 0 | 0 | 0 | 0 | 3796.65 | 0 | 1791.93 | 30883.58
| Sub | 98060 | 59557 | 82117 | 104613.48 | 80224.22 | 105392.93 | 113539.13 | 115009.95 | 127971.3 | 102866.65 | 86838.33 | 125700.16 | 1201890.15 | 499957.69 | 240.4%
Modular Coil Final Design | WBS 1403 | [15 empty] | K6872MCO
(Williamson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
BWXT - MOU | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0%
Modular Coil R&D | WBS 1404 | [15 empty] | K6872YMR
(Williamson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000
BWXT - MOU R&D CRAFT SUPPORT | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91000 | 0%
Modular Coil R&D | WBS 1404 | [15 empty] | K6872MCR
(Williamson) | Labor | 29483 | 36557 | 8501 | 0 | 0 | 1520.57 | 21911.1 | 9784.13 | 18809.87 | 6637.11 | 16247.5 | 19494.65 | 168945.93 | 102294.57
ORNL | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058.48 | 3552.31 | 255.78 | 4431.7 | 10298.27
| Sub | 29483 | 36557 | 8501 | 0 | 0 | 1520.57 | 21911.1 | 9784.13 | 20868.35 | 10189.42 | 16503.28 | 23926.35 | 179244.2 | 102294.57 | 175.2%
Field Period Assy, Tooling & Met. | WBS 1803 | [15 empty] | K6872FPA
(Cole) | Labor | 0 | 0 | 1495 | 0 | 1495.3 | 1495.3 | 3588.72 | 0 | 0 | 0 | 0 | 0 | 8074.32 | 57966.83
ORNL | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 1495 | 0 | 1495.3 | 1495.3 | 3588.72 | 0 | 0 | 0 | 0 | 0 | 8074.32 | 57966.83 | 13.93%
Field Period Assy, Tooling & Met. | WBS 1803 | [15 empty] | K6872FPO
(Cole) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
BWXT - MOU | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0%
Stellarator Core Management and | WBS 1901 | [15 empty] | K6872SCI
Integration | Labor | 36686 | 47368 | 36863 | 27916.45 | 45577.52 | 46313.49 | 37146.92 | 42975.59 | 56356.36 | 24137.64 | 47103.2 | 63602.61 | 512046.78 | 139938.45
(Cole) | Material | 8001 | 0 | 0 | 822 | 0 | 751.07 | 0 | 157.78 | 0 | 62.75 | 335 | 14607.74 | 24737.34
ORNL | Sub | 44687 | 47368 | 36863 | 28738.45 | 45577.52 | 47064.56 | 37146.92 | 43133.37 | 56356.36 | 24200.39 | 47438.2 | 78210.35 | 536784.12 | 139938.45 | 383.6%
Stellarator Core Management and | WBS 1901 | [15 empty] | K6872SCO
Integration | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
(Cole) | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BWXT - MOU | Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0%
Project Management and | WBS 8102 | [15 empty] | K6872PMC
Control | Labor | 10339 | 11425 | 8894 | 5938.66 | 10500.38 | 10844.61 | 9415.28 | 10500.38 | 13629.7 | 344.24 | 0 | 989.29 | 92820.54 | 110010.11
(Lyon, Benson/Martin, Akers) | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 10339 | 11425 | 8894 | 5938.66 | 10500.38 | 10844.61 | 9415.28 | 10500.38 | 13629.7 | 344.24 | 0 | 989.29 | 92820.54 | 110010.11 | 84.37%
Project Physics (Off-Site) | WBS 8402 | [15 empty] | K6872PPO
(Lazarus) | Labor | 7386 | 9232 | 10463 | 3077.36 | 3692.84 | 22156.99 | 12309.45 | 12309.45 | 9232.09 | 13162.63 | 2461.89 | 0 | 105483.7 | 31417.17
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 7386 | 9232 | 10463 | 3077.36 | 3692.84 | 22156.99 | 12309.45 | 12309.45 | 9232.09 | 13162.63 | 2461.89 | 0 | 105483.7 | 31417.17 | 335.8%
| TOTAL | 242231 | 221989 | 191099 | 203254.78 | 199345.03 | 264388.69 | 289686.24 | 224744.42 | 322741.42 | 199205.08 | 208691.1 | 280046.92 | 2847422.68 | 2422668.34 | 117.5%
spent
| 2744020.52 | includes $173,631 carryover + $600k +$311k +$317k + $75k, excludes 8% (reduced) GSO carryover requirement
|  |  | --> to date spent | 103.8% |  | business days to date | 100%