## Cost Spread Sheet FY 01
ORNL COMPACT STELLARATOR SUPPORT NCSX - MONTHLY COST - FY 2004
RESEARCH PREPARATION | OPERATING FUNDS
AT5015060
PROPOSED
[15 empty] | Adjusted |  | FY 2004
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Total | Budget | % Used | Account | Remarks
Work Package
Project Management and | WBS 8101
Control | Labor | 3965 | 4140 | 3828 | 2297 | 4593.71 | 4785.12 | 3253.87 | 4210.9 | 4593.71 | 12625.37 | 12555.17 | 28043.73 | 88891.58 |  |  | 35600332 | Was FY 03 Account 356003ZA
(Lyon, Benson/Martin, Akers) | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1363.65 | 0 | 1363.65
| Sub | 3965 | 4140 | 3828 | 2297 | 4593.71 | 4785.12 | 3253.87 | 4210.9 | 4593.71 | 12625.37 | 13918.82 | 28043.73 | 90255.23 | 49927 | 180.8%
Project Physics (On-Site) | WBS 8401
(Mioduszewski, Owen) | Labor | 11701 | 10546 | 6534 | 990 | 0 | 792.04 | 990.05 | 0 | 6336.32 | 15444.78 | 3960.2 | 792.04 | 58086.43 |  |  | 35600337 | Was FY 03 Account 356003ZB
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 11701 | 10546 | 6534 | 990 | 0 | 792.04 | 990.05 | 0 | 6336.32 | 15444.78 | 3960.2 | 792.04 | 58086.43 | 65000 | 89.36%
Project Physics (Off-Site) | WBS 8401
(Lazarus) | Labor | 0 | 0 | 0 | 2481 | 17308.56 | -620.02 | 3721.24 | 0 | 0 | 0 | 620.2 | 171.19 | 23682.17 |  |  | 35600356 | Was FY 03 Account 356003ZC
| Material | 413 | -680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -267
| Sub | 413 | -680 | 0 | 2481 | 17308.56 | -620.02 | 3721.24 | 0 | 0 | 0 | 620.2 | 171.19 | 23415.17 | 58000 | 40.37%
Project Physics (On-Site) | WBS 8401
(Spong and Berry) | Labor | 17445 | 5949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272.07 | 26666.07 |  |  | 35600357 | Was FY 03 Account 356003ZD
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 17445 | 5949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272.07 | 26666.07 | 31000 | 86.02%
University Support | WBS 8401
UCSD | S/C | 2113 | 0 | 2018 | 240 | 6165.76 | 0 | 6878.68 | 0 | 3420.8 | 0 | 8833.4 | 13419.09 | 43088.73 | 38248 |  | 35600358 | Was FY 03 Account 356003ZE
| S/C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 2113 | 0 | 2018 | 240 | 6165.76 | 0 | 6878.68 | 0 | 3420.8 | 0 | 8833.4 | 13419.09 | 43088.73 | 38248 | 112.7%
Program Administration | Fusion Program | 0 | 531 | 345 | 231 | 345.4 | 521.94 | 253.2 | 262.51 | 210.78 | 121.7 | 48.05 | 0 | 2870.58 | 4940.37 | 58.1% | 33440956
Administration
Correction from FY 2003 |  | -3622
| TOTAL | 32015 | 20486 | 12725 | 6239 | 28413.43 | 5479.08 | 15097.04 | 4473.41 | 14561.61 | 28191.85 | 27380.67 | 45698.12 | 240760.21 | 247115.37 | 97.43%
spent
| 242172.48 | includes $56,196 carryover, excludes 12% GSO carryover requirement
|  | --> to date spent | 99.42% | versus | 100% | business days to date