## Sheet1
NEPA | WP | Cog | RLM | Status | Job Number | Job Description | Job Mgr | Status | Remarks
| 1074 | Viola | Reiersen | Approved for installation. | 1202 | VV Supplier R&D (PVVS fabrication and VVSA proposal preparation activities) | Viola | Comments provided, awaiting response
| 1105 | Viola | Reiersen | Submitted 11/05 Awaiting approval | 1202 | VV Supplier R&D (Vessel weld joint R&D activities)
| 1103 | Goranson | Reiersen | Approved | 1203 | VV Final Design | Goranson | Comments provided, awaiting response
[5 empty] | 1250 | VVSA Fabrication | Goranson |  | Post-FDR. PPPL:ORNL resource split is an issue.
| 1098 | Kalish | Reiersen | Approved | 1301 | Conventional Coils Preliminary Design | Kalish | Awaiting submission
[5 empty] | 1303 | TF/PF Coil Final Design | Viola |  | Post-PDR
|  |  |  | WP not required | 1402 | Modular Coil Analysis | Williamson |  | Accrue Myatt charges for PDR here - no WP required
| 1096 | Williamson | Reiersen | Approved | 1403 | Modular Coil Final Design | Williamson | Comments provided, awaiting response
| 1404 | Heitzenroeder | Reiersen | Approved | 1404 | Modular Coil Winding Form R&D | Heitzenroeder | OK
| ??? | Chrzanowski | Reiersen | Awaiting submission | 1406 | Modular Coil Winding R&D | Chrzanowski | Comments provided, awaiting response
| 1018 | Chrzanowski | Reiersen | Approved for initial work planning, revision requested | 1407 | Modular Coil Winding Facilities | Chrzanowski | Comments provided, awaiting response
| ??? | Chrzanowski | Reiersen | Awaiting submission | 1408 | MC Supplies | Chrzanowski | OK
| 1100 | Gettlefinger | Reiersen | Awaiting submission | 1409 | Modular Coil Test Stand | Gettelfinger | OK
| 1019 | Chrzanowski | Reiersen | Approved for initial work planning, revision requested | 1410 | MC Prototype Winding | Chrzanowski | Split out of original 1408, awaiting response
[5 empty] | 1411 | Modular Coil Winding Form Fabrication | Williamson |  | Post-FDR
[5 empty] | 1501 | Structures Preliminary Design | Kalish
[5 empty] | 1802 | FP Assy Oversight and Support | Chrzanowski
[5 empty] | 1803 | FP Assy Tooling Design and Constructability | Cole
[5 empty] | 1804 | FP Assy Measurement Systems | Raftopoulos
[5 empty] | 1901 | Stellarator Core Management and Integration | Nelson
[5 empty] | 2501 | Neutral Beam Refurbishment | Stevenson
| ??? | Johnson | Reiersen | Awaiting submission | 3901 | Diagnostic Systems Integration | Johnson |  | Needs to identify what interfaces need to be devloped by when
[5 empty] | 4101 | AC Power | Ramakrishnan
[5 empty] | 4301 | DC Systems | Ramakrishnan
[5 empty] | 4401 | Control and Protection | Ramakrishnan
[5 empty] | 4501 | Power Systems Design and Integration | Ramakrishnan
[5 empty] | 4601 | PFCPC Building Modifications | Ramakrishnan
[5 empty] | 5801 | Central I&C Integration and Oversight | Oliaro
| 1102 | Dudek | Reiersen | Approved | 6163 | Facility Systems FY03 Support | Dudek | Ready
[5 empty] | 7201 | Control Room Walls/Floors | Perry
[5 empty] | 7301 | Platform Design and Fabrication | Perry
[5 empty] | 7401 | Test Cell Prep and Machine Assembly Planning | Perry
[5 empty] | 8101 | Project Management and Control | Neilson
[5 empty] | 8102 | NCSX MIE Management ORNL | Lyon
[5 empty] | 8202 | Engineering Management and Systems Engineering Support | Reiersen
[5 empty] | 8203 | Design Integration | Brown
[5 empty] | 8204 | Systems Analysis | Brooks
[5 empty] | 8401 | Project Physics | Zarnstorff
[5 empty] | 8401 | Proejct Physics MIE ORNL | Lyon
Existing jobs
New FY04 job
Not ready to begin
Delete job