## Task 191-4
NCSX Planning Package
WBS No: | 191 | WBS title | Stellarator Core Management
Task number: | 191-4
Task Title: | WBS-1 management activities
Prepared by: | B. Nelson |  |  |  | Date prepared: |  | 2003-10-29
Brief description of work:
Purpose: | Provide management and oversight of WBS-1. Activities will include planning, review, documentation, presentations, cost estimates, scheduling, etc.
Method: | This task is a level of effort activity.
Deliverables:
Subtask 1
Subtask 2
Subtask 3
Subtask 4
Subtask 5
Sub-task list, resources and schedule
Subtask | start date | finish date | Resources (hours) |  |  |  |  | hours per subtask
Nelson
ORNLEM
1 | 2003-10-01 | 2004-09-30 | 1065 |  |  |  |  | 1065
0
0
0
0
Total hours/person |  |  | 1065 | 0 | 0 | 0 | 0
Grand total hours | [7 empty] | 1065

## Task 192-4
NCSX Planning Package
WBS No: | 192 | WBS title | Stellarator Core Design Integration
Task number: | 192-4
Task Title: | WBS-1 Design integration activities
Prepared by: | B. Nelson |  |  |  | Date prepared: |  | 2003-10-29
Brief description of work:
Purpose: | Provide design integration and support for WBS-1, Stellarator Core. Activities will include verification of all design models, interfaces, drawings, and coordination of Pro-E and Pro-Intralink at ORNL.
Method: | This task is a level of effort activity.
Deliverables:
Subtask 1 | Self consistent models and drawings for Modular Coil / VV FDR
Subtask 2 | Self consistent models and drawings for Conventional Coils / support structure
Subtask 3 | Day to day coordination of Pro-E and Pro-Intralink models at ORNL
Subtask 4 | Prepare Stellarator Core Assembly drawings and assembly sequence
Subtask 5 | Coordinate VV Ports with diagnostics
Sub-task list, resources and schedule
Subtask | start date | finish date | Resources (hours) |  |  |  |  | hours per subtask
|  |  | Cole | Jones | Brown
|  |  | ORNLEM | Y12DM | EA/EM
1 | 2003-10-01 | 2004-04-14 | 240 | 60 |  |  |  | 300
2 | 2004-01-01 | 2004-06-01 | 160 | 40 |  |  |  | 200
3 | 2003-10-01 | 2004-09-30 | 400 |  |  |  |  | 400
4 | 2003-10-01 | 2004-09-30 | 96 | 360 |  |  |  | 456
5 | 2003-10-01 | 2004-04-01 | 288 | 196 | 240 |  |  | 724
Total hours/person |  |  | 1184 | 656 | 240 | 0 | 0
Grand total hours | [7 empty] | 2080

## Task 192-5
NCSX Planning Package
WBS No: | 192 | WBS title | Stellarator Core Design Integration
Task number: | 192-5
Task Title: | WBS-1 Vacuum vessel and coil services integration
Prepared by: | B. Nelson |  |  |  | Date prepared: |  | 2003-10-29
Brief description of work:
Purpose: | Provide layouts and stay-out zones for vacuum vessel and coil services, including He piping, N2 piping, and electrical leads.
Method: | Pro-E envelope models will be created for each of the various service lines.
Deliverables:
Subtask 1 | VV helium line models
Subtask 2 | Mod coil LN2 lines
Subtask 3 | Mod coil leads
Subtask 4 | PF coil leads and services
Subtask 5 | TF coil leads and services
Subtask 6 | External trim coil leads and services
Sub-task list, resources and schedule
Subtask | start date | finish date | Resources (hours) |  |  |  |  | hours per subtask
|  |  | Cole | Jones | Brown
|  |  | ORNLEM | Y12DM | EA/EM
1 | 2003-11-01 | 2004-04-01 | 40 | 40 |  |  |  | 80
2 | 2003-11-01 | 2004-04-01 | 40 | 80 |  |  |  | 120
3 | 2003-11-01 | 2004-04-01 | 40 | 80 |  |  |  | 120
4 | 2004-02-01 | 2004-06-15 | 40 | 60 | 20 |  |  | 120
5 | 2004-02-01 | 2004-06-15 | 40 | 40 | 20 |  |  | 100
6 | 2004-02-01 | 2004-06-15 | 40 | 60 | 20 |  |  | 120
Total hours/person |  |  | 240 | 360 | 60 | 0 | 0
Grand total hours | [7 empty] | 660

## Task 192-6
NCSX Planning Package
WBS No: | 192 | WBS title | Stellarator Core Design Integration
Task number: | 192-6
Task Title: | WBS-1 Integrated analysis activities
Prepared by: | B. Nelson |  |  |  | Date prepared: |  | 2003-10-29
Brief description of work:
Purpose: | Provide integrated analyses for WBS-1, including coil tolerance, coil assembly and fit trajectories, error field studies, development of design criteria documents and allowable material properties.
Method: | 1.Analyze final coil geometry with multi-filament winding models including leads and complete documentation for coil tolerance requirements 2.Develop software and models to finalize coil geometry tolerance requirements and best fit algorithms as well as assembly trajectories for the modular coils over vacuum vessel. 3.Analyze material property test data and develop material property database as well as any necessary modifications to structural design criteria document.
Deliverables:
Subtask 1 | Provide final analysis of coil geometry with respect to tolerance and field errors.
Subtask 2 | Provide final mod coil trajectories
Subtask 3 | Develop best fit method for assembling mod coils based on winding measurements
Subtask 4 | Perform global analyses for WBS-1 as required
Subtask 5 | Prepare Stellarator Core Assembly Design Criteria
Subtask 6 | Prepare Stellarator Core materials database
Sub-task list, resources and schedule
Subtask | start date | finish date | Resources (hours) |  |  |  |  | hours per subtask
|  |  | Brooks | Zatz
|  |  | EA/EM | EA/EM
1 | 2003-10-01 | 2004-02-01 | 160 |  |  |  |  | 160
2 | 2003-10-01 | 2004-03-01 | 80 |  |  |  |  | 80
3 | 2004-03-01 | 2004-09-30 | 320 |  |  |  |  | 320
4 | 2003-10-01 | 2004-09-30 | 360 |  |  |  |  | 360
5 | 2003-10-01 | 2004-02-01 |  | 80 |  |  |  | 80
6 | 2003-10-01 | 2004-03-01 |  | 160 |  |  |  | 160
Total hours/person |  |  | 920 | 240 | 0 | 0 | 0
Grand total hours | [7 empty] | 1160