## Sheet2
WP# | Name of Work Activity | Cog Engr | RLM | WP Status a | WP Risk Type | Job# b | Job Title | Job Manager | Comments | Next Action Needed By
1074 | PVVS Fabrication | Viola | Heitzenroeder | Closed | Standard | 1202, | VV R&D | Viola
1103 | Vacuum Vessel Final Design | Goranson | Nelson | Pending Installation Approval | Serious | 1203, | VV Final Design | Goranson
1191 | Ex-VVSA Procurements | Goranson | Nelson | Pending Installation Approval | Standard | 1204, | VV System Procurements (non VVSA) | Goranson
1225 | Vessel Weld Joint R&D | Dudek | Reiersen | Pending Installation Approval | Standard | 1206, | VV Weld Joint R&D | Dudek
1181 | VVSA Fabrication | Viola | Nelson | Pending Installation Approval | Major | 1250, | VVSA Fabrication | Viola
1190 | TF Coils | Kalish | Nelson | Pending Installation Approval | Major | 1301 | TF Design | Kalish
1250 | PF Coils | Kalish | Nelson | Pending Installation Approval | Major | 1301 | TF Design | Kalish
1231 | TF Coil Fabrication Preparation | Chrzanowski | Dudek | Pending Installation Approval |  | 1350, | TF Coil Fabrication Preparation | Chrzanowski
1227 | TF Coil Fabrication | Kalish | Dudek | Pending Installation Approval | Major | 1351, | TF Coil Fabrication | Kalish
1096 | Modular Coil Final Design and Analysis (FY2004-2005) | Williamson | Nelson | Pending Installation Approval | Serious | 1403, 1413 | Modular Coil Final Design | Williamson
1088 | Prototype Modular Coil Winding Form | Heitzenroeder | Reiersen | Closed | Standard | 1404 | Modular Coil Winding Form R&D | Heitzenroeder
1125 | Modular Coil Winding R&D plus Procurement of Coil Winding Supplies | Chrzanowski | Dudek | Pending Final Approval | Serious | 1406 1408 | Modular Coil Winding R&D Modular Coil Winding Supplies | Chrzanowski
1018 | Winding Equipment & Tooling | Chrzanowski | Dudek | Pending Installation Approval | Standard | 1407 1412 | Modular Coil Winding Facilities | Chrzanowski
1138 | Manufacturing of Modular Coils-Production Activities | Chrzanowski | Dudek | Pending Installation Approval | Serious | 1408 & 1451 | Modular Coil Winding | Chrzanowski
1100 | Coil Power Test Area | Gettelfinger | Von Halle | Closed | Standard | 1409, | Modular Coil Test Stand | Gettelfinger
1188 | Manufacturing Twisted Racetrack Coil (TRC) | Chrzanowski | Dudek | Pending Installation Approval | Serious | 1410, | MC Twisted Racetrack Fabrication | Chrzanowski
1256 | MCWF Fabrication | Heitzenroeder | Nelson | Pending Installation Approval | Serious | 1411, | MCWF Fabrication | Heitzenroeder
1237 | Operate NCSX Coil Test Facility | Gettelfinger | von Halle | Pending Installation Approval | Serious | 1414 | Modular Coil Testing | Gettelfinger
1019 | Winding Prototype Modular Coil | Chrzanowski | Dudek | Closed | Standard | 14XX
1101 | Structural Support Castings | Kalish | Nelson | Pending Installation Approval | Serious | 1501, | Structures Design | Kalish
1254 | Cryostat and Base Support Structure Design | Gettelfinger | Nelson | Pending Installation Approval | Standard | 1701, | Cryostat and Base Support Structure Design | Gettelfinger
1224 | FP Assembly Oversight and Support | Viola | Dudek | Pending Installation Approval | Serious | 1802, | FP Assembly Oversight and Support | Viola
1249 | FPA Tooling and Constructability | Brown | Nelson | Pending Installation Approval | Serious | 1803, | FPA Tooling and Constructability | Brown
[6 empty] | 1804, | FPA Measurement Systems | Raftopoulos | No WP required per RLM.
[6 empty] | 1901, | Stellarator Core Management and Integration | Nelson | No WP required per RLM.
1126 | C Site NCSX NBI Testing and Development | Stevenson | von Halle | Pending Final Approval | Standard | 2501, | Neutral Beam Refurbishment | Stevenson | Cog is keeping WP open in the event more work can be done.
1212 | NCSX External Magnetics | Stratton | Johnson | Pending Installation Approval | Standard | 3101, | Magnetic Diagnostics | Stratton
1091 | Diagnostic Systems Integration (FY2004) | Johnson | Johnson | Closed | Standard | 3901, | Diagnostic Systems Integration | Johnson
1116 | Power Systems Engineering and Design | Ramakrishnan | von Halle | Closed | Standard | 4101 4401 D 4501 | AC Power Control & Protection Power Systems Design & Integration | Ramakrishnan
1118 | DC Transmission Structure & Trays from D to C site | Ramakrishnan | von Halle | Closed | Standard | 4301, | DC Systems | Ramakrishnan
1216 | NCSX WBS4 C-Site DC System Design and Installation | Ramakrishnan | von Halle | Pending Installation Approval | Major | 4301, | DC Systems | Ramakrishnan
TBD | Control Room Walls and Floor | TBD | Perry |  | TBD | 7201, | Control Room Walls and Floor | Perry | Work will most likely be GPP - will not be done this FY. WP will be prepared when work scheduled.May be assigned to GPP. | Perry
1247 | Platform Design and Fabrication | Perry | Reiersen | Pending Installation Approval | Standard | 7301, 7501 | Platform Design and Fabrication | Perry
1146 | NCSX Test Cell Copper Ground Plane Cuts | Perry | Reiersen | Approved for Installation | Standard | 7401 (613.030) | TC Prep and Machine Assy Planning (Test cell copper ground plane cuts) | Perry
1137 | Shielding in CS Building High Bay | Priniski | Perry | Pending Installation Approval | Standard | 7401, | Test Cell Facility Preparations | Perry | This is now GPP work.
1093 | Project Management and Control (FY2004) | Strykowsky | Neilson | Closed | Standard | 8101 8102 | Project Management & Control NCSX MIE Management at ORNL | Neilson
1094 | Systems Engineering Support (FY2004) | Reiersen | Neilson | Closed | Standard | 8202 8203 8204 8205 | Engineering Management & Systems Engineering Support Design Integration Systems Analysis Dimensional Control | Reiersen Brown Brooks Stratton | WP not required on future work per the RLM
1095 | Project Physics Support (FY2004) | Zarnstorff | Neilson | Closed | Standard | 8401 8402 | Project Physics | Zarnstorff