## Sheet2
WP# | Name of Work Activity | Cog Engr | RLM | WP Status a | WP Risk Type | Job# b | Job Title | Job Manager | Comments | Next Action Needed By
1105 | Vessel Weld Joint Design | Viola | Dudek | Closed | Standard | 1201 | VV Prelim Dsn | Viola
1074 | PVVS Fabrication | Viola | Heitzenroeder | Closed | Standard | 1202 | VV R&D | Viola
1103 | Vacuum Vessel Final Design | Goranson | Nelson | Closed | Serious | 1203 | VV Final Design | Goranson
1191 | VVProcurements - Non-VVSA | Dudek | Reiersen | Pending Installation Approval | Standard | 1204 | VV System Procurements (non VVSA) | Dudek
1225 | Vessel Weld Joint R&D | Dudek | Reiersen | Closed | Standard | 1206 | VV Weld Joint R&D | Dudek
1181 | VVSA Fabrication | Viola | Nelson | Closed | Major | 1250 | VVSA Fabrication | Viola
1190 | TF Coils | Kalish | Nelson | Closed | Major | 1301 | TF Design | Kalish
1250 | PF Coils | Kalish | Nelson | Closed | Major | 1301 | TF Design | Kalish
| PF Coils Design | Kalish | Reiersen |  |  | 1302 | PF Coil Design | Kalish | Prepare WP prior to start of work | Prepare WP prior to start of work
1361 | CS Support Structure Design & Analysis | Dahlgren | Reiersen | Pending Initial Approval | Standard | 1303 | CS Support Structure Design & Analysis | Dahlgren
1231 | TF Coil Fabrication Preparation | Chrzanowski | Dudek | Closed | Standard | 1350 | TF Coil Fabrication Preparation | Chrzanowski
1295 | Procurement of NCSX TF Coils | Kalish | Reiersen | Pending Initial Approval | Major | 1351, 1361 | TF Coil Supplies TF Coil Fabriaction | Kalish | THIS WORK IS CURRENT => SHOULD BE BEYOND INITIAL APPROVAL STAGE! | KALISH & REIERSEN REVIEW AND UPDATE WP
| PF Coil Procurement | Kalish | Reiersen |  |  | 1352 | PF Coil Procurement | Kalish | Prepare WP prior to start of work
| CS Structure Procurement | Dahlgren | Reiersen |  |  | 1353 | CS Structure Procurement | Dahlgren | Prepare WP prior to start of work
| Trim Coil Design & Fab | Kalish | Reiersen |  |  | 1354 | Trim Coil Design & Fab | Kalish | Prepare WP prior to start of work
| Conventional Coils I&C Design and Fab | Kalish | Reiersen |  |  | 1355 | Conventional Coils I&C Design & Fab | Kalish | Prepare WP prior to start of work
1088 | Prototype Modular Coil Winding Form | Heitzenroeder | Reiersen | Closed | Standard | 1404 | Modular Coil Winding Form R&D | Heitzenroeder
1125 | Modular Coil Winding R&D plus Procurement of Coil Winding Supplies | Chrzanowski | Dudek | Pending Installation Approval | Serious | 1406, 1408 | Modular Coil Winding R&D Modular Coil Winding Supplies | Chrzanowski
1018 | Winding Equipment & Tooling | Chrzanowski | Dudek | Closed | Standard | 1407 1412 | Modular Coil Winding Facilities | Chrzanowski
1138 | Manufacturing of Modular Coils-Production Activities | Chrzanowski | Dudek | Pending Installation Approval | Serious | 1408, 1451, 1459, 1460 | Modular Coil Winding | Chrzanowski
1100 | Coil Power Test Area | Gettelfinger | Von Halle | Closed | Standard | 1409 | Modular Coil Test Stand | Gettelfinger
1188 | Manufacturing Twisted Racetrack Coil (TRC) | Chrzanowski | Dudek | Closed | Serious | 1410 | MC Twisted Racetrack Fabrication | Chrzanowski
1256 | MCWF Fabrication | Heitzenroeder | Nelson | Pending Installation Approval | Serious | 1411 | MCWF Fabrication | Heitzenroeder
1237 | Operate NCSX Coil Test Facility | Gettelfinger | von Halle | Closed | Serious | 1414 | Modular Coil Testing | Gettelfinger
1308 | Prep C1 Coil for Power Testing | Gettelfinger | Reiersen | Closed | Standard | 1414 | Prepare C1 for Power Test | Gettelfinger
1096 | Modular Coil Final Design and Analysis (FY2004-2005) | Williamson | Nelson | Closed | Serious | 1416, 1421 | Modular Coil Final Design | Williamson
1357 | Modular Coil Shim Friction Testing | Gettelfinger | Dudek | Pending Initial Approval | Standard | 1429 | Friction Testing of MC Shims | Gettelfinger
1355 | Prototype of NCSX Modular Coil Inflatable Shim | Dudek | Reiersen | Pending Initial Approval | Standard | 1431 | MC Interface Hardware | Dudek
|  | Dudek | Reiersen |  |  | 1431 | MC Interface Hardware Fab | Dudek | Prepare new WP or expend scope of WP1355 prior to starting additional work
1019 | Winding Prototype Modular Coil | Chrzanowski | Dudek | Closed | Standard | 14XX
1360 | TF & PF Support Structure Design & Analysis | Dahlgren | Reiersen | Pending Final Approval | Serious | 1501 | TF & PF Support Structure Design & Analysis | Dahlgren
1101 | Structural Support Castings | Kalish | Nelson | Closed | Serious | 1501, | Structures Design | Kalish
| Coil Structures Procurements | Dahlgren | Reiersen |  |  | 1550 | Coil Structures Procurements | Dahlgren | Prepare WP prior to start of work
| Coil Services Design | Williamson | Nelson |  |  | 1601 | Coil Services Design | Nelson | Prepare WP prior to start of work
1254 | Cryostat and Base Support Structure Design | Gettelfinger | Reiersen | Pending Installation Approval | Standard | 1701 | Cryostat and Base Support Structure Design | Gettelfinger
| Cryostat Procurement | Gettelfinger | Reiersen |  |  | 1751 | Cryostat Procurement | Gettelfinger | Prepare WP prior to start of work
| Base Supporet Structure Procurement | Gettelfinger | Reiersen |  |  | 1752 | Base Supporet Structure Procurement | Gettelfinger | Prepare WP prior to start of work
1224 | FP Assembly Oversight and Support | Viola | Dudek | Pending Installation Approval | Serious | 1802 | FP Assembly Oversight and Support | Viola
1249 | FPA Tooling and Constructability | Brown | Dudek | Pending Initial Approval | Serious | 1803, | FPA Tooling and Constructability | Brown
N/A | Metrology Hardware | Raftopoulos | Dudek |  |  | 1804 | FPA Measurement Systems | Raftopoulos | No WP required per RLM.
|  | Cole | Nelson |  |  | 1806 | FPA Specs and Drawings | Cole | THIS WORK IS CURRENT => NEED WP NOW! | PREPARE WP BY 1/26/2007
1350 | Perform C-C Coil prototype fitup | Viola | Dudek | Pending Final Approval | Standard | 1810 | Field Period Assembly | Viola
N/A | Stellartore Core Mgmt & Integration | Nelson | Reiersen |  |  | 1901 | Stellarator Core Management and Integration | Nelson | No WP required per RLM.
| Fueling System | Blanchard | Dudek |  |  | 2101 | Fueling System | Blanchard | Prepare WP prior to start of work
| Vacuum Pumping System | Blanchard | Dudek |  |  | 2201 | Vacuum Pumping System | Blanchard | Prepare WP prior to start of work
1126 | C Site NCSX NBI Testing and Development | Stevenson | von Halle | Pending Final Approval | Standard | 2501, | Neutral Beam Refurbishment | Stevenson | Cog is keeping WP open in the event more work can be done.
1212 | NCSX External Magnetics | Stratton | Dudek | Pending Final Approval | Standard | 3101 | Magnetic Diagnostics | Labik
| Edge & Divertor Diagnostics | Stratton | Dudek |  |  | 3601 | Edge & Divertor Diagnostics | Stratton | Prepare WP prior to start of work
1091 | Diagnostic Systems Integration (FY2004) | Johnson | Johnson | Closed | Standard | 3901, | Diagnostic Systems Integration | Johnson
1116 | Power Systems Engineering and Design | Ramakrishnan | von Halle | Closed | Standard | 4101 4401 4501 | AC Power Control & Protection Power Systems Design & Integration | Ramakrishnan
| Power Systems Engineering and Design | Ramakrishnan | von Halle |  |  | 4101 4401 4501 | AC Power Control & Protection Power Systems Design & Integration | Ramakrishnan | Prepare WP prior to start of work
1118 | DC Transmission Structure & Trays from D to C site | Ramakrishnan | von Halle | Closed | Standard | 4301 | DC Systems | Ramakrishnan
1216 | NCSX WBS4 C-Site DC System Design and Installation | Ramakrishnan | von Halle | Pending Installation Approval | Major | 4301 | DC Systems | Ramakrishnan
N/A | Control Room Walls and Floor |  | Perry |  |  | 7201 | Control Room Walls and Floor | Perry | Work will most likely be GPP - will not be done this FY. WP will be prepared when work scheduled.May be assigned to GPP. Close? | Perry
1247 | Platform Design and Fabrication | Perry | Reiersen | Pending Installation Approval | Standard | 7301, 7501 | Platform Design and Fabrication | Perry
1146 | NCSX Test Cell Copper Ground Plane Cuts | Perry | Reiersen | Approved for Installation | Standard | 7401 (613.030) | TC Prep and Machine Assy Planning (Test cell copper ground plane cuts) | Perry | IS THIS DONE YET? | UPDATE BY 1/26/2007 IF NEEDED.
1137 | Shielding in CS Building High Bay | Priniski | Perry | Pending Installation Approval | Standard | 7401, 7101 | Test Cell Facility Preparations | Perry | This was done under GPP. SHOULDN'T WE CLOSE? | UPDATE BY 1/26/2007
1241 | Prep for NCSX Installation | Perry | Reiersen | Pending Final Approval | Standard | '7401, '7501 | Test Cell Facility Preparations | Perry
| Machine Assembly Tooling Design & Fab |  | Perry |  |  | 7601 | Machine Assembly Tooling Design & Fab | Brown | No work scheduled until 10/07
1093 | Project Management and Control (FY2004) | Strykowsky | Neilson | Closed | Standard | 8101 8102 | Project Management & Control NCSX MIE Management at ORNL | Neilson
1094 | Systems Engineering Support (FY2004) | Reiersen | Neilson | Closed | Standard | 8202 8203 8204 8205 | Engineering Management & Systems Engineering Support Design Integration Systems Analysis Dimensional Control | Reiersen Brown Brooks Stratton | WP not required on future work per the RLM
1095 | Project Physics Support (FY2004) | Zarnstorff | Neilson | Closed | Standard | 8401 8402 | Project Physics | Zarnstorff
1045 | Re-install Chiller for C-Site Rectifier Cooling System | Dudek | Reiersen | Closed | Standard
1046 | Checkout of the NCSX NB Rectifier Cooling Water System | Dudek | Reiersen | Closed | Standard
1048 | NCSX NBI Development Activities | Stevenson | Von Halle | Closed | Standard
1061 | C site NBI Modulator Repair | Stevenson | Von Halle | Closed | Standard
1082 | Neutral Beam Box Exhaust Monitoring System | Carnavelle | Von Halle | Closed | Standard
1090 | Stellarator Core Management and Integration (FY2004) | Nelson | Reiersen | Closed | Standard
1098 | NCSX Conventional coils Preliminary Design | Kalish | Reieren | Closed | Standard
1102 | NCSX WBS 6 -Facility systems FY04 Support | Dudek | Reiersen | Closed | Standard