## Summary
BCWS Monthly
|  | ACWP | BTC | BCWS May 1,2007 - Sep 30,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12
11056.504 | Jim Anderson | 5262.504 | 5794 | 755 | 104 | 95 | 95 | 103 | 86 | 145 | 127 | 95 | 139 | 132 | 132 | 139 | 132 | 132 | 139 | 132 | 131 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45121.891 | Larry Dudek | 20428.331 | 24693.56 | 4659.28 | 196.57 | 494.19 | 847.97 | 726.4 | 547.77 | 1204.61 | 641.77 | 490.99 | 733.18 | 615.01 | 599.26 | 565.74 | 520.27 | 441.47 | 567.25 | 382.9 | 368.82 | 467.28 | 499.05 | 700.13 | 870.14 | 709.69 | 742.23 | 653.24 | 657.74 | 669.4 | 589.32 | 545.17 | 610.17 | 830.32 | 573.51 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58190.153 | Phil Heitzeroeder | 40659.653 | 17530.5 | 3601.4 | 423.8 | 618 | 608 | 497 | 433 | 608 | 413.6 | 344.9 | 505.2 | 417.8 | 461.8 | 418.7 | 375.5 | 644.8 | 856.7 | 999.1 | 943.7 | 810.4 | 517 | 369.6 | 442.4 | 422.3 | 412.7 | 404.6 | 301.5 | 362.7 | 283.7 | 192 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5082.85 | Al vonHalle | 752.65 | 4330.2 | -90.8 | -102.8 | 1.2 | 1.3 | 2 | 1.3 | 3.1 | 3.1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total BCWS | 67103.138 | 52348.26 | 8924.88 | 621.57 | 1208.39 | 1552.27 | 1328.4 | 1068.07 | 1960.71
|  |  | 119451.398 | 7739.41
|  | Jim Anderson |  | BCWS | 104 | 199 | 294 | 397 | 483 | 628 | 755 | 850 | 989 | 1121 | 1253 | 1392 | 1524 | 1656 | 1795 | 1927 | 2058 | 2217 | 2343 | 2461 | 2607 | 2746 | 2898 | 3050 | 3189 | 3341 | 3493 | 3639 | 3781 | 3923 | 4046 | 4150 | 4280 | 4410 | 4559 | 4701 | 4831 | 4973 | 5109 | 5251 | 5387 | 5495 | 5598 | 5685 | 5793 | 5794
|  |  |  | BCWP | 102 | 199 | 294 | 396.9789 | 482.56 | 627.698 | 754.927
|  |  |  | ACWP | 111.7184 | 218.6445 | 309.5976 | 416.8916 | 597.4836 | 693.7456 | 836.8386
|  |  |  | CPI | 0.91301 | 0.91015 | 0.94962 | 0.95224 | 0.80765 | 0.9048 | 0.90212
|  |  |  | SPI | 0.98077 | 1 | 1 | 0.99995 | 0.99909 | 0.99952 | 0.9999
|  | Larry Dudek |  | BCWS | 196.57 | 690.76 | 1538.73 | 2265.13 | 2812.9 | 4017.51 | 4659.28 | 5150.27 | 5883.45 | 6498.46 | 7097.72 | 7663.46 | 8183.73 | 8625.2 | 9192.45 | 9575.35 | 9944.17 | 10411.45 | 10910.5 | 11610.63 | 12480.77 | 13190.46 | 13932.69 | 14585.93 | 15243.67 | 15913.07 | 16502.39 | 17047.56 | 17657.73 | 18488.05 | 19061.56 | 19478.56 | 20022.56 | 20411.56 | 20973.56 | 21592.56 | 22074.56 | 22502.56 | 22860.56 | 23235.56 | 23559.56 | 23969.56 | 24344.56 | 24662.56 | 24693.56
|  |  |  | BCWP | 122 | 778 | 1447 | 2191.7652 | 2900.1205 | 3794.506 | 4333.6991
|  |  |  | ACWP | 305.793 | 823.5043 | 1302.9008 | 2004.9938 | 2727.8868 | 3154.7718 | 3726.6878
|  |  |  | CPI | 0.39896 | 0.94474 | 1.1106 | 1.0932 | 1.0631 | 1.2028 | 1.1629
|  |  |  | SPI | 0.62064 | 1.1263 | 0.94039 | 0.96761 | 1.031 | 0.94449 | 0.93012
|  | Phil Heitzeroeder |  | BCWS | 423.8 | 1041.8 | 1649.8 | 2146.8 | 2579.8 | 3187.8 | 3601.4 | 3946.3 | 4451.5 | 4869.3 | 5331.1 | 5749.8 | 6125.3 | 6770.1 | 7626.8 | 8625.9 | 9569.6 | 10380 | 10897 | 11266.6 | 11709 | 12131.3 | 12544 | 12948.6 | 13250.1 | 13612.8 | 13896.5 | 14088.5 | 14297.5 | 14635.5 | 14930.5 | 15181.5 | 15464.5 | 15702.5 | 15950.5 | 16143.5 | 16293.5 | 16458.5 | 16616.5 | 16781.5 | 16939.5 | 17096.5 | 17246.5 | 17373.5 | 17526.5 | 17530.5
|  |  |  | BCWP | 300 | 817 | 1546 | 1938.6461 | 2268.7 | 2722.1431 | 3091.3718
|  |  |  | ACWP | 317.203 | 705.0554 | 1005.8607 | 1659.2607 | 2055.8407 | 2404.7427 | 2776.3457
|  |  |  | CPI | 0.94577 | 1.1588 | 1.537 | 1.1684 | 1.1035 | 1.132 | 1.1135
|  |  |  | SPI | 0.70788 | 0.78422 | 0.93708 | 0.90304 | 0.87941 | 0.85393 | 0.85838
|  | Al vonHalle |  | BCWS | -102.8 | -101.6 | -100.3 | -98.3 | -97 | -93.9 | -90.8 | -88.8 | -85.8 | -82.8 | -79.8 | -76.8 | -73.8 | -70.8 | -67.8 | -64.8 | -61.8 | -0.8 | 76.2 | 170.2 | 284.2 | 366.2 | 472.2 | 576.2 | 672.2 | 792.2 | 965.2 | 1228.2 | 1415.2 | 1657.2 | 1918.2 | 2144.2 | 2394.2 | 2666.2 | 3014.2 | 3267.2 | 3464.2 | 3632.2 | 3744.2 | 3799.2 | 3858.2 | 4027.2 | 4137.2 | 4231.2 | 4330.2
|  |  |  | BCWP | -103 | -102 | -101 | -98.3768 | -97.12 | -94.8 | -91.0243
|  |  |  | ACWP | -104.2596 | -104.2596 | -104.3015 | -104.3015 | -104.6585 | -104.6585 | -104.6585
|  |  |  | CPI | 0.98792 | 0.97833 | 0.96835 | 0.9432 | 0.92797 | 0.9058 | 0.86973
|  |  |  | SPI | 1.0019 | 1.0039 | 1.007 | 1.0008 | 1.0012 | 1.0096 | 1.0025
|  | TOTAL PROJECT |  | BCWS | 621.57 | 1829.96 | 3382.23 | 4710.63 | 5778.7 | 7739.41 | 8924.88 | 9857.77 | 11238.15 | 12405.96 | 13602.02 | 14728.46 | 15759.23 | 16980.5 | 18546.45 | 20063.45 | 21509.97 | 23007.65 | 24226.7 | 25508.43 | 27080.97 | 28433.96 | 29846.89 | 31160.73 | 32354.97 | 33659.07 | 34857.09 | 36003.26 | 37151.43 | 38703.75 | 39956.26 | 40954.26 | 42161.26 | 43190.26 | 44497.26 | 45704.26 | 46663.26 | 47566.26 | 48330.26 | 49067.26 | 49744.26 | 50588.26 | 51326.26 | 51952.26 | 52343.26 | 23324.5 | 0
|  |  |  | BCWP | 421 | 1692 | 3186 | 4429.0134 | 5554.2605 | 7049.5471 | 8088.9736
|  |  |  | ACWP | 630.4547 | 1642.9445 | 2514.0576 | 3976.8446 | 5276.5526 | 6148.6016 | 7235.2136
|  |  |  | CPI | 0.66777 | 1.0299 | 1.2673 | 1.1137 | 1.0526 | 1.1465 | 1.118
|  |  |  | SPI | 0.67732 | 0.92461 | 0.94198 | 0.94022 | 0.96116 | 0.91086 | 0.90634
|  | Mod Coil Design |  | BCWS | 219 | 518 | 827 | 1070 | 1184 | 1418 | 1500 | 1538 | 1580 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606
|  | 1416/1421/1429 |  | BCWP | 96 | 292 | 797 | 897.5716 | 918.5 | 1122.391 | 1224.7874
|  |  |  | ACWP | 123.9413 | 257.935 | 406.7498 | 700.8288 | 828.5818 | 943.1298 | 1073.1128
|  |  |  | CPI | 0.77456 | 1.1321 | 1.9594 | 1.2807 | 1.1085 | 1.1901 | 1.1413
|  |  |  | SPI | 0.43836 | 0.56371 | 0.96372 | 0.83885 | 0.77576 | 0.79153 | 0.81652
|  | Field Period Assy |  | BCWS | 254.37 | 497.46 | 838.33 | 1170.53 | 1417.1 | 1754.71 | 1998.28 | 2223.27 | 2531.45 | 2783.46 | 3079.72 | 3346.46 | 3596.73 | 3831.2 | 4258.45 | 4570.35 | 4851.17 | 5164.45 | 5448.5 | 5663.63 | 5966.77 | 6353.46 | 6781.69 | 7133.93 | 7480.67 | 7795.07 | 8142.39 | 8432.56 | 8725.73 | 8964.05 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56
|  | 1802/1810/1815 |  | BCWP | 254 | 494 | 808 | 1064.6539 | 1359.15 | 1600.257 | 1777.2997
|  |  |  | ACWP | 191.2809 | 363.5801 | 571.3968 | 851.3268 | 1075.1188 | 1226.7268 | 1443.2528
|  |  |  | CPI | 1.3279 | 1.3587 | 1.4141 | 1.2506 | 1.2642 | 1.3045 | 1.2315
|  |  |  | SPI | 0.99855 | 0.99304 | 0.96382 | 0.90955 | 0.95911 | 0.91198 | 0.88941
|  | Mod Coil Winding Ops |  | BCWS | 237 | 408 | 639 | 821 | 957 | 1170 | 1358 | 1491 | 1713 | 1924 | 2107 | 2316 | 2509 | 2665 | 2752 | 2768 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769
|  | 1451 |  | BCWP | 236 | 412 | 711 | 946.222 | 1184 | 1439.27 | 1546.0835
|  |  |  | ACWP | 283.7075 | 502.5031 | 659.7907 | 900.0867 | 1090.4237 | 1245.0187 | 1436.4037
|  |  |  | CPI | 0.83184 | 0.8199 | 1.0776 | 1.0513 | 1.0858 | 1.156 | 1.0764
|  |  |  | SPI | 0.99578 | 1.0098 | 1.1127 | 1.1525 | 1.2372 | 1.2301 | 1.1385
|  | Mod Coil Winding Ops Punch list |  | BCWS | 0 | 4 | 23 | 43 | 90 | 147 | 190 | 216 | 258 | 301 | 343 | 369 | 393 | 418 | 444 | 477 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501
|  | 1459 |  | BCWP | 0 | 18 | 32 | 44.1632 | 135.3 | 168.318 | 282.9757
|  |  |  | ACWP | 42.2044 | 97.4829 | 149.185 | 213.991 | 289.453 | 339.23 | 370.053
|  |  |  | CPI | 0 | 0.18465 | 0.2145 | 0.20638 | 0.46743 | 0.49618 | 0.76469
|  |  |  | SPI |  | 4.5 | 1.3913 | 1.0271 | 1.5033 | 1.145 | 1.4893
|  | Engr Mgmt & Sys Eng Sup |  | BCWS | 82 | 158 | 221 | 290 | 343 | 404 | 457 | 497 | 556 | 612 | 668 | 727 | 783 | 839 | 898 | 954 | 1010 | 1071 | 1119 | 1164 | 1220 | 1273 | 1332 | 1391 | 1444 | 1503 | 1562 | 1618 | 1674 | 1733 | 1784 | 1827 | 1880 | 1933 | 1994 | 2053 | 2106 | 2165 | 2221 | 2280 | 2336 | 2384 | 2430 | 2469 | 2517 | 2519
|  | 8202 |  | BCWP | 108 | 208 | 295 | 289.203 | 342.46 | 403.1 | 456.8854
|  |  |  | ACWP | 59.5964 | 118.2282 | 176.8311 | 264.2051 | 318.4291 | 373.1311 | 428.2571
|  |  |  | CPI | 1.8122 | 1.7593 | 1.6683 | 1.0946 | 1.0755 | 1.0803 | 1.0668
|  |  |  | SPI | 1.3171 | 1.3165 | 1.3348 | 0.99725 | 0.99843 | 0.99777 | 0.99975
|  | Design Integration |  | BCWS | 33 | 65 | 97 | 132 | 161 | 196 | 226 | 249 | 282 | 314 | 346 | 379 | 411 | 443 | 476 | 508 | 540 | 575 | 602 | 628 | 660 | 690 | 723 | 756 | 786 | 819 | 852 | 884 | 916 | 949 | 978 | 1002 | 1032 | 1062 | 1097 | 1130 | 1160 | 1193 | 1225 | 1258 | 1290 | 1322 | 1352 | 1378 | 1410 | 1412
|  | 8203 |  | BCWP | 31 | 60 | 89 | 130.9084 | 160.47 | 194.2511 | 225.2187
|  |  |  | ACWP | 5.0798 | 10.3179 | 11.959 | 22.052 | 36.561 | 55.866 | 75.916
|  |  |  | CPI | 6.1027 | 5.8151 | 7.4421 | 5.9363 | 4.3891 | 3.4771 | 2.9667
|  |  |  | SPI | 0.93939 | 0.92308 | 0.91753 | 0.99173 | 0.99671 | 0.99108 | 0.99654
|  | Systems Analysis |  | BCWS | 37 | 73 | 109 | 148 | 180 | 207 | 231 | 249 | 275 | 300 | 325 | 351 | 376 | 401 | 427 | 452 | 477 | 504 | 525 | 545 | 570 | 594 | 620 | 646 | 670 | 696 | 722 | 747 | 772 | 798 | 820 | 839 | 863 | 887 | 914 | 940 | 964 | 990 | 1015 | 1041 | 1066 | 1091 | 1115 | 1135 | 1160
|  | 8204 |  | BCWP | 35 | 69 | 103 | 147.9102 | 180.95 | 207.311 | 231.4724
|  |  |  | ACWP | 42.5836 | 95.7359 | 142.8443 | 193.3133 | 225.4093 | 272.0633 | 319.3953
|  |  |  | CPI | 0.82191 | 0.72073 | 0.72106 | 0.76513 | 0.80276 | 0.762 | 0.72472
|  |  |  | SPI | 0.94595 | 0.94521 | 0.94495 | 0.99939 | 1.0053 | 1.0015 | 1.002
|  | Dimensional Cont Coordin |  | BCWS | 0 | 27 | 54 | 84 | 102 | 123 | 143 | 158 | 180 | 205 | 240 | 277 | 312 | 330 | 342 | 354 | 366 | 379 | 393 | 407 | 425 | 443 | 459 | 475 | 489 | 500 | 509 | 518 | 527 | 536 | 542 | 545 | 549 | 553 | 557 | 561 | 565 | 569 | 573 | 577 | 581 | 585 | 589 | 592
|  | 8205 |  | BCWP | 0 | 21 | 42 | 75.2674 | 76 | 87.581 | 100.769
|  |  |  | ACWP | 17.5068 | 37.5899 | 60.0821 | 81.5541 | 92.0961 | 96.1341 | 113.3171
|  |  |  | CPI | 0 | 0.55866 | 0.69904 | 0.92291 | 0.82522 | 0.91103 | 0.88927
|  |  |  | SPI |  | 0.77778 | 0.77778 | 0.89604 | 0.7451 | 0.71204 | 0.70468
|  | Diagnostic |  | BCWS | 14.2 | 31.3 | 55.4 | 153.6 | 192.8 | 252.8 | 279 | 298 | 310 | 313 | 315 | 318 | 320 | 322 | 325 | 327 | 329 | 332 | 334 | 336 | 339 | 341 | 369 | 396 | 426 | 453 | 456 | 459 | 461 | 499 | 532 | 554 | 587 | 623 | 669 | 691 | 696 | 702 | 707 | 713 | 718
|  | 3101;3601;3801;3901 |  | BCWP | 14 | 58 | 114 | 148.2661 | 155.7805 | 160.581 | 209.0172
|  |  |  | ACWP | 29.6873 | 49.7738 | 94.6838 | 129.3728 | 141.1718 | 145.5328 | 151.1708
|  |  |  | CPI | 0.47158 | 1.1653 | 1.204 | 1.146 | 1.1035 | 1.1034 | 1.3827
|  |  |  | SPI | 0.98592 | 1.853 | 2.0578 | 0.96527 | 0.80799 | 0.63521 | 0.74917
|  | PF Coil Des/Procurement |  | BCWS | 5 | 5 | 5 | 14 | 44 | 79 | 104 | 134 | 182 | 214 | 251 | 282 | 322 | 458 | 631 | 956 | 1226 | 1409 | 1510 | 1566 | 1629 | 1694 | 1758 | 1827 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1861 | 1873 | 1887
|  | 1302;1352 |  | BCWP | 5 | 5 | 5 | 47.3325 | 60.35 | 61.085 | 61.5946
|  |  |  | ACWP | 4.26 | 5.8007 | 7.206 | 13.784 | 44.385 | 47.602 | 55.349
|  |  |  | CPI | 1.1737 | 0.86197 | 0.69387 | 3.4339 | 1.3597 | 1.2832 | 1.1128
|  |  |  | SPI | 1 | 1 | 1 | 3.3809 | 1.3716 | 0.77323 | 0.59226
|  | TF Fabrication |  | BCWS | 8 | 73 | 133 | 168 | 228 | 289 | 348 | 404 | 463 | 521 | 625 | 682 | 739 | 795 | 898 | 952 | 1004 | 1004
|  | 1361 |  | BCWP | 4 | 49 | 108 | 199.4121 | 267.65 | 331.282 | 363.6
|  |  |  | ACWP | -6.0157 | 34.3792 | 88.8075 | 185.3505 | 271.3235 | 340.5435 | 385.1965
|  |  |  | CPI | -0.66492 | 1.4253 | 1.2161 | 1.0759 | 0.98646 | 0.9728 | 0.94393
|  |  |  | SPI |  | 0.67123 | 0.81203 | 1.187 | 1.1739 | 1.1463 | 1.0448
|  | Mod Coil Type AB Fnl Dsn |  | BCWS | 219 | 518 | 827 | 1070 | 1184 | 1418 | 1500 | 1538 | 1580 | 1606
|  | 1416;1421;1429 |  | BCWP | 96 | 292 | 797 | 897.5716 | 918.5 | 1122.391 | 1224.7874
|  |  |  | ACWP | 123.9413 | 257.935 | 406.7498 | 700.8288 | 828.5818 | 943.1298 | 1073.1128
|  |  |  | CPI | 0.77456 | 1.1321 | 1.9594 | 1.2807 | 1.1085 | 1.1901 | 1.1413
|  |  |  | SPI | 0.43836 | 0.56371 | 0.96372 | 0.83885 | 0.77576 | 0.79153 | 0.81652
|  | Coil Structure Dsn/Proc |  | BCWS | 7 | 38 | 70 | 128 | 164 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 218 | 327 | 458 | 589 | 732 | 825 | 876 | 939 | 999 | 1065 | 1131 | 1191 | 1257 | 1260
|  | 1501;1550 |  | BCWP | 2 | 45 | 75 | 81.9424 | 136.7 | 145.001 | 145.1989
|  |  |  | ACWP | 54.1006 | 101.4754 | 138.5961 | 174.6521 | 176.9141 | 160.0001 | 183.0811
|  |  |  | CPI | 0.036968 | 0.44346 | 0.54114 | 0.46917 | 0.77269 | 0.90626 | 0.79309
|  |  |  | SPI | 0.28571 | 1.1842 | 1.0714 | 0.64017 | 0.83354 | 0.77958 | 0.78064
|  | Coil Service Design |  | BCWS | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 34 | 61 | 88 | 116 | 143 | 191 | 222 | 269 | 327 | 404 | 465 | 518 | 544 | 564 | 587 | 610 | 630 | 653 | 676 | 697 | 701 | 743 | 785 | 824 | 858 | 861
|  | 1601 |  | BCWP | 0 | 6 | 6 | 6.2288 | 14.6 | 14.598 | 22.9678
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | 1 | 1 | 1.0381 | 2.4333 | 2.433 | 3.828
|  |  | Stellarator Core Mngtt&Integr | BCWS | 34 | 66 | 98 | 133 | 162 | 200 | 233 | 258 | 294 | 328 | 362 | 398 | 432 | 466 | 502 | 536 | 569 | 609 | 640 | 670 | 707 | 742 | 780 | 818 | 853 | 891 | 929 | 966 | 999 | 1039 | 1073 | 1102 | 1138 | 1174 | 1216 | 1256 | 1292 | 1332 | 1370 | 1410 | 1448 | 1493 | 1536 | 1573 | 1618
|  |  | 1901 | BCWP | 34 | 66 | 98 | 132.6417 | 161.56 | 199.131 | 232.2105
|  |  |  | ACWP | 36.462 | 53.934 | 64.981 | 96.648 | 109.709 | 119.964 | 130.754
|  |  |  | CPI | 0.93248 | 1.2237 | 1.5081 | 1.3724 | 1.4726 | 1.6599 | 1.7759
|  |  |  | SPI | 1 | 1 | 1 | 0.99731 | 0.99728 | 0.99565 | 0.99661
|  |  | CS Structure Procurement | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 28 | 30 | 32 | 79 | 131 | 176 | 214 | 261 | 308 | 339
|  |  | 1353 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Trim Coil Design/Procurement | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 29.6 | 74.5 | 145.7 | 191.5 | 259.3 | 327 | 355.5 | 519.3 | 733 | 958.1 | 1172.8 | 1341.2 | 1431.2 | 1488.8 | 1584.2 | 1671.5 | 1713.2 | 1736.8 | 1738.3 | 1803 | 1867.7 | 1867.7
|  |  | 1354 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 9.652
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | I&C Proc & Coil Assy | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 12 | 17 | 20 | 27 | 31 | 31 | 46 | 58 | 61 | 67 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 73
|  |  | 1355 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Cryostat Dsn/Proc | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 14 | 24 | 46 | 89 | 133 | 154 | 177 | 200 | 207 | 207 | 281 | 345 | 399 | 451 | 487 | 518 | 532
|  |  | 1701;1751 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | -0.23265 | 2.8487 | 4.3022 | 4.3022 | 5.2332 | 5.2332
|  |  |  | CPI | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | SPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Base support Structure Dsn/Proc | BCWS | 0 | 0 | 0 | 0 | 0 | 43 | 79 | 107 | 148 | 163 | 165 | 166 | 167 | 173 | 191 | 208 | 226 | 246 | 252 | 253 | 254 | 255
|  |  | 1702;1752 | BCWP | 0 | 0 | 0 | 0 | 10.83 | 11.09 | 11.0679
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 32.6 | 31.743
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.34018 | 0.34867
|  |  |  | SPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.25791 | 0.1401
|  |  | FP Assembly | BCWS | 9 | 24 | 41 | 67 | 92 | 120 | 139 | 164 | 201 | 236 | 271 | 307 | 339 | 371 | 404 | 438 | 477 | 496 | 503 | 510 | 517
|  |  | 1806 | BCWP | 0 | 3 | 25 | 27.7447 | 36.15 | 39.838 | 106.1322
|  |  |  | ACWP | 0 | 0 | -0.128 | 2.007 | 2.007 | 2.007 | 2.89
|  |  |  | CPI | #DIV/0! | #DIV/0! | -195.3125 | 13.824 | 18.012 | 19.8495 | 36.7239
|  |  |  | SPI | 0 | 0.125 | 0.60976 | 0.4141 | 0.39293 | 0.33198 | 0.76354

## BCWS by JOB
[5 empty] | BCWS Monthly |  |  |  |  | BCWS Monthly | [11 empty] | BCWS Monthly | [11 empty] | FY 2010 BCWS Monthly | [11 empty] | FY 2011 BCWS Monthly
RLM | JOB | notes | BTC | BCWS May 1,2007 - Nov 30,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 |  | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON |  | 3844 | 455 | 61 | 54 | 54 | 59 | 49 | 95 | 83 | 62 | 91 | 87 | 87 | 91 | 87 | 87 | 91 | 87 | 87 | 107 | 84 | 79 | 98 | 93 | 102 | 102 | 93 | 102 | 102 | 98 | 98 | 95 | 82 | 69 | 87 | 87 | 100 | 95 | 87 | 95 | 91 | 95 | 91 | 80 | 76 | 64 | 80
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON |  | 497 | 88 | 13 | 12 | 12 | 13 | 11 | 14 | 13 | 10 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 12 | 11 | 13 | 13 | 14 | 14 | 13 | 14 | 14 | 13 | 13 | 9 | 8 | 7 | 8 | 8 | 9 | 9 | 8 | 9 | 9 | 9 | 9 | 5 | 5 | 4 | 5
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY |  | 1453 | 212 | 30 | 29 | 29 | 31 | 26 | 36 | 31 | 23 | 34 | 32 | 32 | 34 | 32 | 32 | 34 | 32 | 31 | 38 | 30 | 28 | 35 | 33 | 36 | 36 | 33 | 36 | 36 | 35 | 31 | 38 | 33 | 28 | 35 | 35 | 40 | 38 | 35 | 38 | 36 | 38 | 36 | 23 | 22 | 19 | 23 | 1
| Total Jim Anderson |  | 5794 | 755 | 104 | 95 | 95 | 103 | 86 | 145 | 127 | 95 | 139 | 132 | 132 | 139 | 132 | 132 | 139 | 132 | 131 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK |  | 409 | 102 |  | 17 | 25 | 4 |  | 27 | 29 | 2 |  |  |  | 30 | 27 | 12 | 12 | 12 | 12 | 1 | [11 empty] | 60 | 88 | 34 | 17
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** |  | -252 | -252 | -162 |  |  | -90
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI |  | 348 | 225 | 17 | 24 | 51 | 56 | 29 | 26 | 22 | 28 | 41 | 35 | 11 | 5 | 3
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK |  | 1039 | 879 | 144 | 7 | 103 | 82 | 27 | 452 | 64 | 22 | 25 | 23 | 20 | 11 | 10 | 10 | 10 | 6 | 6 | [12 empty] | 12 | 4 | 1
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI |  | 2769 | 1358 | 237 | 171 | 231 | 182 | 136 | 213 | 188 | 133 | 222 | 211 | 183 | 209 | 193 | 156 | 87 | 16 | 1
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  | 501 | 190 |  | 4 | 19 | 20 | 47 | 57 | 43 | 26 | 42 | 43 | 42 | 26 | 24 | 25 | 26 | 33 | 24
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA |  | 1987 | 390 | 64 | 47 | 47 | 52 | 43 | 79 | 58 | 43 | 63 | 60 | 86 | 71 | 67 | 66 | 68 | 64 | 63 | 89 | 65 | 60 | 74 | 81 | 84 | 83 | 74 | 68 | 62 | 59 | 59 | 61 | 27
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK |  | 522 | 184 |  | 11 | 54 | 42 | 23 | 30 | 24 | 35 | 81 | 46 | 43 | 13 | 9 |  |  |  | 36 | 39 | 31 | 5
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA |  | 5751.56 | 1608.28 | 190.37 | 196.09 | 293.87 | 280.2 | 203.57 | 258.61 | 185.57 | 181.99 | 245.18 | 192.01 | 210.26 | 195.74 | 183.27 | 168.47 | 204.25 | 192.9 | 204.82 | 221.28 | 189.05 | 115.13 | 171.14 | 256.69 | 252.23 | 167.24 | 160.74 | 136.4 | 113.32 | 108.17 | 108.17 | 113.32 | 51.51
D - Larry Dudek | Job: 1815 - Field Period Assy |  | 1335 | 0 | [14 empty] | 155 | 55 | 13 | 3 | 30 | 40 | 58 | 49 | 92 | 102 | 112 | 110 | 172 | 123 | 126 | 64 | 31
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD |  | 69 | 0 | [28 empty] | 13 | 21 | 3 | 2 | 3 | 2 | 0 | 2 | 12 | 11
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD |  | 170 | 0 | [20 empty] | 22 | 20 | 25 | 3 | [5 empty] | 0 | 7 | 15 | 19 | 19 | 22 | 16 | 2
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON |  | 290 | 263 | 12 | 15 | 22 | 96 | 37 | 57 | 24 | 17 | 9 | 1
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON |  | 31 | 0 | [29 empty] | 9 | 8 | 1 | 2 | 2 | 7 | 2
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON |  | 263 | 0 | [22 empty] | 25 | 24 | 28 | 24 |  |  |  | 23 | 20 | 17 | 26 | 29 | 33 | 14
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON |  | 134 | 16 | 2.2 | 2.1 | 2.1 | 2.2 | 2.2 | 3 | 2.2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 6 | 5 | 4 | 5 | 5 | 6 | 6 | 5 | 6 | 5 | 6 | 5
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK |  | 46 | 0 | [17 empty] | 13 | 1 | 1 | 2 | 2 | 1 | 5 | 11 | 8 | 2
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER |  | 654 | 0 | [17 empty] | 23 | 18 |  | 59 | 35 | 21 | 23 | 17 |  |  | 30 | 44 | 61 | 57 | 49 | 55 | 42 | 32 | 29 | 26 | 30 | 2 | 1
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK |  | 105 | 0 | [17 empty] | 18 | 18 | 11 | 13 | 10 |  |  | 15 | 16 | 4
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH |  | 573 | 0 | [23 empty] | 7 | 8 | 23 | 24 | 21 | 23 | 25 | 57 | 58 | 73 | 68 | 60 | 57 | 45 | 24
D - Larry Dudek | Job: 7301 - Platform Design & |  | 202 | 0 | [16 empty] | 5 | 43 | 74 | 68 | 12
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY |  | 1416 | -304 | -308 |  |  |  |  | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | 12 | 5 | 71 | 63 | 68 | 66 | 60 | 66 | 66 | 62 | 61 | 64 | 54 | 45 | 56 | 55 | 86 | 85 | 79 | 85 | 83 | 84 | 81 | 79 | 77 | 70 | 4
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY |  | 1406 | 0 | [20 empty] | 10 | 38 | 42 | 42 | 38 | 42 | 42 | 40 | 42 | 42 | 40 | 44 | 40 | 38 | 83 | 87 | 83 | 87 | 87 | 87 | 87 | 83 | 87 | 91 | 4
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY |  | 4511 | 0 | [18 empty] | 59 | 393 | 369 | 129 | 103 | 102 | 108 | 147 | 75 | 74 | 107 | 243 | 98 | 128 | 224 | 105 | 206 | 295 | 206 | 172 | 181 | 197 | 151 | 248 | 211 | 157 | 23
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY |  | 414 | 0 | [20 empty] | 6 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 23 | 19 | 24 | 24 | 27 | 26 | 24 | 13
| Total Larry Dudek |  | 24693.56 | 4659.28 | 196.57 | 494.19 | 847.97 | 726.4 | 547.77 | 1204.61 | 641.77 | 490.99 | 733.18 | 615.01 | 599.26 | 565.74 | 520.27 | 441.47 | 567.25 | 382.9 | 368.82 | 467.28 | 499.05 | 700.13 | 870.14 | 709.69 | 742.23 | 653.24 | 657.74 | 669.4 | 589.32 | 545.17 | 610.17 | 830.32 | 573.51 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH |  | 258 | 104 | 5 |  |  | 9 | 30 | 35 | 25 | 30 | 48 | 32 | 33 | 11
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH |  | 1629 | 0 | [10 empty] | 4 | 20 | 40 | 136 | 173 | 325 | 270 | 183 | 101 | 56 | 63 | 65 | 64 | 69 | 32 | [8 empty] | 2 | 12 | 14
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN |  | 339 | 0 | [23 empty] | 4 | 8 | 16 | 2 | 2 | 47 | 52 | 45 | 38 | 47 | 47 | 31
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | updated baseline to include trim coil 36 coil set | 1867.7 | 29.6 | [6 empty] | 29.6 | 44.9 | 71.2 | 45.8 | 67.8 | 67.7 | 28.5 | 163.8 | 213.7 | 225.1 | 214.7 | 168.4 | 90 | 57.6 | 95.4 | 87.3 | 41.7 | 23.6 | 1.5 | 64.7 | 64.7
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  | 73 | 0 | [9 empty] | 4 | 4 | 4 | 5 | 3 | 7 | 4 |  | 15 | 12 | 3 | 6 | 4 | [12 empty] | 2
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH |  | 1004 | 348 | 8 | 65 | 60 | 35 | 60 | 61 | 59 | 56 | 59 | 58 | 104 | 57 | 57 | 56 | 103 | 54 | 52
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod |  | -36 | -36 | -36
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER |  | -84 | -84 | 5 | 1 |  | -90
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON |  | 280 | 242 | 12 | 23 | 8 | 15 | 12 | 116 | 56 | 19 | 17 | 2
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON |  | 1208 | 1140 | 177 | 276 | 250 | 191 | 102 | 118 | 26 | 19 | 25 | 24
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER |  | 118 | 118 | 30 |  | 51 | 37
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN |  | 186 | 186 | 7 | 31 | 32 | 58 | 36 | 22 | 0
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN |  | 1074 | 0 | [13 empty] | 32 | 109 | 131 | 131 | 143 | 93 | 51 | 63 | 60 | 66 | 66 | 60 | 66 | 3
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON |  | 861 | 6 | 6 | [7 empty] | 28 | 27 | 27 | 28 | 27 | 48 | 31 | 47 | 58 | 77 | 61 | 53 | 26 | 20 | 23 | 23 | 20 | 23 | 23 | 21 | 4 | 42 | 42 | 39 | 34 | 3
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER |  | 207 | 0 | [17 empty] | 6 | 4 | 4 | 10 | 22 | 43 | 44 | 21 | 23 | 23 | 7
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN |  | 164 | 79 | [5 empty] | 43 | 36 | 28 | 41 | 15 | 1
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER |  | 325 | 0 | [29 empty] | 74 | 64 | 54 | 52 | 36 | 31 | 14
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN |  | 91 | 0 | [10 empty] | 1 | 1 | 1 | 6 | 18 | 17 | 18 | 20 | 6 | 1 | 1 | 1 | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs |  | 517 | 139 | 9 | 15 | 17 | 26 | 25 | 28 | 19 | 25 | 37 | 35 | 35 | 36 | 32 | 32 | 33 | 34 | 39 | 19 | 7 | 7 | 7
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE |  | 1618 | 233 | 34 | 32 | 32 | 35 | 29 | 38 | 33 | 25 | 36 | 34 | 34 | 36 | 34 | 34 | 36 | 34 | 33 | 40 | 31 | 30 | 37 | 35 | 38 | 38 | 35 | 38 | 38 | 37 | 33 | 40 | 34 | 29 | 36 | 36 | 42 | 40 | 36 | 40 | 38 | 40 | 38 | 45 | 43 | 37 | 45
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN |  | 2519 | 457 | 82 | 76 | 63 | 69 | 53 | 61 | 53 | 40 | 59 | 56 | 56 | 59 | 56 | 56 | 59 | 56 | 56 | 61 | 48 | 45 | 56 | 53 | 59 | 59 | 53 | 59 | 59 | 56 | 56 | 59 | 51 | 43 | 53 | 53 | 61 | 59 | 53 | 59 | 56 | 59 | 56 | 48 | 46 | 39 | 48 | 2
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN |  | 1412 | 226 | 33 | 32 | 32 | 35 | 29 | 35 | 30 | 23 | 33 | 32 | 32 | 33 | 32 | 32 | 33 | 32 | 32 | 35 | 27 | 26 | 32 | 30 | 33 | 33 | 30 | 33 | 33 | 32 | 32 | 33 | 29 | 24 | 30 | 30 | 35 | 33 | 30 | 33 | 32 | 33 | 32 | 32 | 30 | 26 | 32 | 2
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS |  | 1160 | 231 | 37 | 36 | 36 | 39 | 32 | 27 | 24 | 18 | 26 | 25 | 25 | 26 | 25 | 25 | 26 | 25 | 25 | 27 | 21 | 20 | 25 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 22 | 19 | 24 | 24 | 27 | 26 | 24 | 26 | 25 | 26 | 25 | 25 | 24 | 20 | 25
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS |  | 592 | 143 |  | 27 | 27 | 30 | 18 | 21 | 20 | 15 | 22 | 25 | 35 | 37 | 35 | 18 | 12 | 12 | 12 | 13 | 14 | 14 | 18 | 18 | 16 | 16 | 14 | 11 | 9 | 9 | 9 | 9 | 6 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks |  | 18.8 | 18.8 | 14.8 | 4
H - Phil Heitzenroeder | Job: 8215 Plant Design |  | 129 | 21 |  |  |  | 8 | 7 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3
| Total Phil Heitzenroeder |  | 17530.5 | 3601.4 | 423.8 | 618 | 608 | 497 | 433 | 608 | 413.6 | 344.9 | 505.2 | 417.8 | 461.8 | 418.7 | 375.5 | 644.8 | 856.7 | 999.1 | 943.7 | 810.4 | 517 | 369.6 | 442.4 | 422.3 | 412.7 | 404.6 | 301.5 | 362.7 | 283.7 | 192 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN |  | 52 | -104 | -104 | [16 empty] | 0 | 0 | 0 | 12 | 11 | 14 | 4 | 3 | 1 | 1 | 3 | 6 | 6 | 4 | 3 | 8 | 27 | 29 | 15 | 6 | 3
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN |  | 604 | 2 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 38 | 31 | 41 | 53 | 18 | 1 | 1 | 1 | 1 | 14 | 74 | 1 | 0 | 62 | 52 | 66 | 66 | 72
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN |  | 1084 | 0 | [21 empty] | 11 | 26 | 33 | 32 | 41 | 42 | 60 | 69 | 103 | 73 | 55 | 67 | 75 | 111 | 97 | 91 | 56 | 31 | 10 | 1
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN |  | 682 | 0 | [17 empty] | 21 | 23 | 20 | 18 | 17 | 37 | 34 | 29 | 37 | 43 | 40 | 37 | 39 | 22 | 18 | 19 | 13 |  |  | 3 | 35 | 33 | 35 | 56 | 53
V - Al vonHalle | Job: 5101 - Network and Fiber |  | 151 | 0 | [26 empty] | 3 | 2 | 2 | 2 | 14 | 14 | 18 | 23 | 32 | 31 | 10
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA |  | 197 | 0 | [22 empty] | 5 | 3 | 2 | 2 | 21 | 25 | 24 | 15 | 6 | 5 | 7 | 9 | 5 | 14 | 20 | 22 | 12
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA |  | 165 | 0 | [24 empty] | 4 | 7 | 11 | 21 | 7 | 7 | 12 | 10 | 12 | 9 | 10 | 13 | 17 | 15 | 10
V - Al vonHalle | Job: 5401 - Facility Timing & |  | 204 | 0 | [26 empty] | 5 | 4 | 3 | 16 | 25 | 24 | 15 | 16 | 32 | 24 | 10 | 15 | 12 | 3
V - Al vonHalle | Job: 5501 - Real Time Control |  | 131 | 0 | [26 empty] | 5 | 7 | 6 | 6 | 8 | 7 | 9 | 14 | 21 | 25 | 9 | 13 | 1
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA |  | 221 | 0 | [25 empty] | 2 | 2 | 3 | 4 | 19 | 20 | 17 | 18 | 18 | 34 | 32 | 29 | 7 | 11 | 5
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA |  | 72.2 | 11.2 | 1.2 | 1.2 | 1.3 | 2 | 1.3 | 2.1 | 2.1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE |  | 767 | 0 | [18 empty] | 22 | 32 | 29 | 24 | 21 | 27 | 24 | 27 | 24 | 22 | 26 | 27 | 14 | 20 | 9 | [8 empty] | 116 | 110 | 94 | 99
| Total Al vonHalle |  | 4330.2 | -90.8 | -102.8 | 1.2 | 1.3 | 2 | 1.3 | 3.1 | 3.1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 52348.26 | 8924.88 | 621.57 | 1208.39 | 1552.27 | 1328.4 | 1068.07 | 1960.71 | 1185.47 | 932.89 | 1380.38 | 1167.81 | 1196.06 | 1126.44 | 1030.77 | 1221.27 | 1565.95 | 1517 | 1446.52 | 1497.68 | 1219.05 | 1281.73 | 1572.54 | 1352.99 | 1412.93 | 1313.84 | 1194.24 | 1304.1 | 1198.02 | 1146.17 | 1148.17 | 1552.32 | 1252.51 | 998 | 1207 | 1029 | 1307 | 1207 | 959 | 903 | 764 | 737 | 677 | 844 | 738 | 626 | 391
23007.65
9857.77
corrected

## FY08 MR worksheet
NCSX FY08 Alternate Plan
FY08 Budget |  |  | FY08 Plan (base plus ETC's) |  |  | Acceleration Candidates
| 15.9 | BA |  | 1.96 | spent oct & nov |  | Design accelerations- Priority 1 Scope
| 1.777 | fy07 c/o |  | 13.515 | current plan BCWR (dec-sept) |  |  | 0.069 | NBI port exte dsn | Resource Requirements Priority 1 scope (manmonmths)
| 17.677 | fyg08 budget | [5 empty] | 0.028 | CS structure bus dsn/analysis | 7 | EA Engrs
| 3 | additional funding | [5 empty] | 0.352 | coil service leads (ornl) | 21.4 | Mech Designers
| 20.677 | total planning budget for alternate plan |  | 15.475 |  |  |  | 0.207 | cryostat | 6.2 | Electrical Engrs
[8 empty] | 0.198 | cryogenic sys design | 10.5 | FO&M Engrs
|  |  | APPARENT FREE BALANCE = | 5.202 |  |  |  | 0.109 | fueling (3 injectors) | 3 | I&C engr
[8 empty] | 0.213 | VPS | 17.1 | ORNL Engrs
|  |  | ETC's (estimated) |  |  |  |  | 0.025 | water systems
|  |  |  | -0.4 | rate reductions ~-5 points |  |  | 0.138 | bakeout sys
|  |  |  | 0.2 | wbs 82 simmons/phil +.65 fte |  |  | 0.065 | WBS 5 I&C Adv Concep design
|  |  |  | 0.1 | plant design +.5 fte designer |  |  | 0.215 | power systems design wbs 4
|  |  |  | 0.137 | Project mgr |  |  | 1.619
|  |  |  | 0.037 | allocations
|  |  |  | -0.2 | wbs 19 stell core mgt (ornl) |  | Procurement commitments carried over into fy09 (M&S loaded)
|  |  |  | 0.15 | make FPA schedule slip |  |  | 0.342 | PF
|  |  | ADJUSTED FREE BALANCE = | 5.226 |  |  |  | 0.472 | Trim Coils
[8 empty] | 0.55 | Coil Support Struct
[8 empty] | 0.055 | Station 6 Fixtures
1.419
[7 empty] | Other accelerations- Priority 2 Scope |  |  | Resource Requirements Priority 2 scope(manmonmths or $K)
[8 empty] | 0.1 | e-beam mapping | 1 | Mech Designers
[8 empty] | 0.1 | coil protection wbs4 | 2.3 | Electrical Engrs
[8 empty] | 0.2 | ISTP documentation (~50% ) | 4.7 | FO&M Engrs
[8 empty] | 0.444 | Award/Commit Lead HW | 4 | FO&M Tech
[8 empty] | 0.168 | Award/Commit LN2 distr sys HW | 2.2 | Reserach
[8 empty] | 1.012 |  | $342k | M&S
[7 empty] | Remaining unplanned free balance = | 1.176
Other candidates
NON MIE Scope-Long Lead Upgrade Scope
NB Armor Design (ornl)
[8 empty] | 1600 | 1 fte analysis engr
3.8 fte designer
2.1 fte engr
[8 empty] | 1206 | NB #1&#2 refurbishment

## ACWP by JOB
|  |  |  | ACWP Monthly |  |  |  |  | ACWP Monthly
RLM | JOB | ACWP May 1,2007 - Nov 30,2007 |  | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 392.3228 | 8101 | 55.8777 | 58.9419 | 48.7333 | 48.726 | 80 | 47.586 | 52.458
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON | 137.118 | 8102 | 30.964 | 22.991 | 13.862 | 23.695 | 17.316 | 15.755 | 12.535
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY | 307.3978 | 8998 | 24.8767 | 24.9933 | 28.3578 | 34.873 | 83.276 | 32.921 | 78.1
| Total Jim Anderson | 836.8386 |  | 111.7184 | 106.9261 | 90.9531 | 107.294 | 180.592 | 96.262 | 143.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 185.3709 | 1204 | 16.0209 | 1.3261 | 5.4769 | 16.8 | 100.76 | 25.926 | 19.061
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -251.7703 | 1250 | -161.88 | 0 | -92.5573 |  | 2.667
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 116.8304 | 1408 | 23.8679 | 11.6976 | 31.1989 | 21.389 | 8.337 | 8.641 | 11.699
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 370.9819 | 1431 | 144.2801 | 0 | 47.0428 |  | 96.358 | 16.395 | 66.906
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1436.4037 | 1451 | 283.7075 | 218.7955 | 157.2876 | 240.296 | 190.337 | 154.595 | 191.385
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 370.053 | 1459 | 42.2044 | 55.2785 | 51.7021 | 64.806 | 75.462 | 49.777 | 30.823
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA | 432.1947 | 1802 | 84.3784 | 51.4086 | 66.9277 | 81.881 | 56.68 | 34.76 | 56.159
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 179.8729 | 1803 | 34.185 | 34.0075 | 22.4994 | 37.434 | 13.088 | 15.582 | 23.077
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 1011.0581 | 1810 | 106.9026 | 120.8905 | 140.889 | 198.049 | 167.112 | 116.848 | 160.367
D - Larry Dudek | Job: 1815 - Field Period Assy | 0
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON | 123.9386 | 3101 | 27.0665 | 15.8846 | 38.1895 | 30.572 | 9.403 | 1.477 | 1.346
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON | 0
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON | 27.2322 | 3901 | 2.6208 | 4.2019 | 6.7205 | 4.117 | 2.396 | 2.884 | 4.292
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 0
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER | 0
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0
D - Larry Dudek | Job: 7301 - Platform Design & | 0
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -275.4783 | 7401 | -297.561 | 4.2205 | 4.0193 | 6.749 | 0.293 | 0 | 6.801
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY | 0
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY | 0
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY | 0
| Total larry Dudek | 3726.6878 |  | 305.793 | 517.7113 | 479.3966 | 702.093 | 722.893 | 426.885 | 571.916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 55.349 | 1302 | 4.26 | 1.5406 | 1.4053 | 6.578 | 30.601 | 3.217 | 7.747
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH | 0
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | 18.074 | 1354 | [5 empty] | 9.652 | 8.422
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH | 385.1965 | 1361 | -6.0157 | 40.395 | 54.4283 | 96.543 | 85.973 | 69.22 | 44.653
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod | -34.9474 | 1404 | -35.9384 | 0 | 0 | 0.835 | 0.156 | 0
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -65.1126 | 1411 | 7.495 | 2.0635 | -92.7721 |  | 18.101
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 122.0559 | 1416 | 12.3179 | 9.522 | 18.891 | 27.345 | -0.069 | 19.257 | 34.792
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 864.1527 | 1421 | 81.6509 | 107.2854 | 109.3563 | 253.823 | 122.667 | 94.85 | 94.52
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER | 86.9042 | 1429 | 29.9725 | 17.1863 | 20.5674 | 12.911 | 5.155 | 0.441 | 0.671
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN | 183.0811 | 1501 | 54.1006 | 47.3749 | 37.1207 | 36.056 | 2.262 | -16.914 | 23.081
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 1550 | [5 empty] | 0
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON | 0
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER | 5.2332 | 1701 | -0.23265 | 3.0813 | 1.4536 |  | 0.931
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN | 31.743 | 1702 | [5 empty] | 32.6 | -0.857
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs | 2.89 |  |  |  | -0.128 | 2.135 |  |  | 0.883
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 130.754 | 1901 | 36.462 | 17.472 | 11.047 | 31.667 | 13.061 | 10.255 | 10.79
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 428.2571 | 8202 | 59.5964 | 58.6317 | 58.6029 | 87.374 | 54.224 | 54.702 | 55.126
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN | 75.916 | 8203 | 5.0798 | 5.2382 | 1.641 | 10.093 | 14.509 | 19.305 | 20.05
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS | 319.3953 | 8204 | 42.5836 | 53.1523 | 47.1084 | 50.469 | 32.096 | 46.654 | 47.332
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS | 113.3171 | 8205 | 17.5068 | 20.0831 | 22.4922 | 21.472 | 10.542 | 4.038 | 17.183
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks | 54.0865 | 8210 | 8.3642 | 4.8261 | 9.5912 | 16.099 | 6.371 | 1.625 | 7.21
H - Phil Heitzenroeder | Job: 8215 Plant Design | 0
| Total Phil Heitzenroeder | 2776.3457 |  | 317.203 | 387.8524 | 300.8052 | 653.4 | 396.58 | 348.902 | 371.603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104.1027 | 4101 | -104.1027 | 0 | 0
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | -0.55581 | 4501 | -0.15696 | 0 | -0.041849 |  | -0.357
V - Al vonHalle | Job: 5101 - Network and Fiber | 0
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA | 0
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA | 0
V - Al vonHalle | Job: 5401 - Facility Timing & | 0
V - Al vonHalle | Job: 5501 - Real Time Control | 0
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 0
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE | 0
| Total Al vonHalle | -104.6585 |  | -104.2596 | 0 | -0.041849 | 0 | -0.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total project | 7235.2136 |  | 630.4547 | 1012.4898 | 871.113 | 1462.787 | 1299.708 | 872.049 | 1086.612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1958.661
corrected

## BCWP by JOB
|  |  | BCWP Monthly |  |  |  |  | BCWP Monthly | [59 empty] | BCWP Cum |  |  | BCWP Cum | [11 empty] | FY 2009 BCWP Cum | [11 empty] | FY 2010 BCWP Cum | [17 empty] | oct | oct | oct | nov | nov | nov
RLM | JOB | BCWP May 1,2007 - Nov 30,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | Sum of EVC |  |  | RLMS | JJJJ | Total
A - Jjm Anderson | Job: 8101 - Project Management &Control-ANDERSON | 455 | 59 | 56 | 54 | 60.1165 | 48.9835 | 95.146 | 81.754 | [58 empty] | 169 | 229.1165 | 278.1 | 373.246 | 455 | [40 empty] | A | 8101 | 373.2469 | A | 8101 | 455.98
A - Jjm Anderson | Job: 8102 - NCSX MjE Management ORNL-LYON | 87.927 | 13 | 12 | 12 | 12.6048 | 10.8152 | 14.628 | 12.879 | [58 empty] | 37 | 49.6048 | 60.42 | 75.048 | 87.927 | [41 empty] | 8102 | 75.048 |  | 8102 | 87.927
A - Jjm Anderson | Job: 8998 - Allocatjons-STRYKOWSKY | 212 | 30 | 29 | 29 | 30.2576 | 25.7824 | 35.364 | 32.596 | [58 empty] | 88 | 118.2576 | 144.04 | 179.404 | 212 | [41 empty] | 8998 | 179.4042 |  | 8998 | 210.5393
| Total Jjm Anderson | 754.927 | 102 | 97 | 95 | 102.9789 | 85.5811 | 145.138 | 127.229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 294 | 396.9789 | 482.56 | 627.698 | 754.927 | [40 empty] | A Total |  | 627.6991
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 140.9945 |  | 55 | 9 | 4.4894 | 14.5406 | 36.153 | 21.8115 | [58 empty] | 64 | 68.4894 | 83.03 | 119.183 | 140.9945 | [40 empty] | D | 1204 | 119.1836 | D | 1204 | 140.9945
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrjcatjon**CLOSED** | -251.6947 | -162 |  | -90 | 0.30528 | 0.00472 | -0.005 | 0.00028 | [58 empty] | -252 | -251.6947 | -251.69 | -251.695 | -251.6947 | [41 empty] | 1250 | -251.6947 |  | 1250 | -251.6947
D - Larry Dudek | Job: 1408 - MC Wjndjng Suppljes-CHRZANOWSKj | 226.4223 | 7 | 33 | 23 | 93.4268 | 5.9732 | 41.568 | 22.4543 | [58 empty] | 63 | 156.4268 | 162.4 | 203.968 | 226.4223 | [41 empty] | 1408 | 203.9684 |  | 1408 | 226.4223
D - Larry Dudek | Job: 1431 - Mod. Cojl jnterface Hardware-DUDEK | 635.6104 | 81 | 77 |  | 98.8971 | 52.7029 | 280.1 | 45.9104 | [58 empty] | 158 | 256.8971 | 309.6 | 589.7 | 635.6104 | [41 empty] | 1431 | 589.746 |  | 1431 | 635.6104
D - Larry Dudek | Job: 1451 - Mod Cojl Wjndjng-CHRZANOWSKj | 1546.0835 | 236 | 176 | 299 | 235.222 | 237.778 | 255.27 | 106.8135 | [58 empty] | 711 | 946.222 | 1184 | 1439.27 | 1546.0835 | [41 empty] | 1451 | 1439.2702 |  | 1451 | 1546.0835
D - Larry Dudek | Job: 1459 - Mod Cojl Fabr.Punch Ljst-CHRZANOWSKj | 282.9757 |  | 18 | 14 | 12.1632 | 91.1368 | 33.018 | 114.6577 | [58 empty] | 32 | 44.1632 | 135.3 | 168.318 | 282.9757 | [41 empty] | 1459 | 168.3665 |  | 1459 | 282.9757
D - Larry Dudek | Job: 1802 - FP Assy Oversjght&Support-VjOLA | 353.7331 | 64 | 47 | 47 | 52.1107 | 42.5393 | 54.06 | 47.0231 | [58 empty] | 158 | 210.1107 | 252.65 | 306.71 | 353.7331 | [41 empty] | 1802 | 306.7178 |  | 1802 | 353.7331
D - Larry Dudek | Job: 1803/1805- FPA Tooljng/Constr-BROWN/DUDEK | 68.7378 |  | 12 | 42 | 10.0883 | 4.2117 | 0.21 | 0.22777 | [58 empty] | 54 | 64.0883 | 68.3 | 68.51 | 68.7378 | [41 empty] | 1803 | 68.5159 |  | 1803 | 68.7378
D - Larry Dudek | Job:1810-Fjeld Perjod Assy -Statjon 1 2 3 VjOLA | 1423.5666 | 190 | 193 | 267 | 204.5431 | 251.9569 | 187.047 | 130.0196 | [58 empty] | 650 | 854.5431 | 1106.5 | 1293.547 | 1423.5666 | [41 empty] | 1810 | 1293.58 |  | 1810 | 1423.5666
D - Larry Dudek | Job: 1815 - Fjeld Perjod Assy | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1815 | 0 |  | 1815 | 0
D - Larry Dudek | Job: 2101 - Fueljng Systems-BLANCHARD | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 2101 | 0 |  | 2101 | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumpjng Systems-BLANCHARD | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 2201 | 0 |  | 2201 | 0
D - Larry Dudek | Job: 3101 - Magnetjc Djagnostjcs-STRATTON | 192.6012 | 12 | 42 | 54 | 30.94 | 5.4811 | 2.1119 | 46.0682 | [58 empty] | 108 | 138.94 | 144.4211 | 146.533 | 192.6012 | [41 empty] | 3101 | 146.5334 |  | 3101 | 192.6012
D - Larry Dudek | Job: 3601 - Edge Djvertor Djagnostjcs-STRATTON | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 3601 | 0 |  | 3601 | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mappjng-STRATTON | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 3801 | 0 |  | 3801 | 0
D - Larry Dudek | Job: 3901 - Djagnostjcs sys jntegratjon-STRATTON | 16.4159 | 2 | 2 | 2 | 3.3261 | 2.0333 | 2.6886 | 2.3679 | [58 empty] | 6 | 9.3261 | 11.3594 | 14.048 | 16.4159 | [41 empty] | 3901 | 14.0484 |  | 3901 | 16.4159
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 6101 | 0 |  | 6101 | 0
D - Larry Dudek | Job: 6201 - Cryogenjc Syst-GETTELFjNGER | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 6201 | 0 |  | 6201 | 0
D - Larry Dudek | Job: 6301 - Utjljty Systems-DUDEK | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 6301 | 0 |  | 6301 | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooljng(bakeout)- KALjSH | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 6401 | 0 |  | 6401 | 0
D - Larry Dudek | Job: 7301 - Platform Desjgn & | 2.6336 |  | 1 | 2 | -0.44672 | -0.003282 | 0.064 | 0.019634 | [58 empty] | 3 | 2.5533 | 2.55 | 2.614 | 2.6336 | [41 empty] | 7301 | 2.6149 |  | 7301 | 2.6336
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Plannjng-PERRY | -304.3808 | -308 |  |  | -0.3 | 0 | 2.1 | 1.8192 | [58 empty] | -308 | -308.3 | -308.3 | -306.2 | -304.3808 | [41 empty] | 7401 | -306.1947 |  | 7401 | -304.3808
D - Larry Dudek | Job: 7501 - Constructjon Support Crew-PERRY | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 7501 | 0 |  | 7501 | 0
D - Larry Dudek | Job: 7503 - Machjne Assembly (statjon 6)-PERRY | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 7503 | 0 |  | 7503 | 0
D - Larry Dudek | Job: 7601 - Tooljng Desjgn & Fabrjcatjon-PERRY | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 7601 | 0 |  | 7601 | 0
| Total larry Dudek | 4333.6991 | 122 | 656 | 669 | 744.7652 | 708.3553 | 894.3855 | 539.1931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1447 | 2191.7652 | 2900.1205 | 3794.506 | 4333.6991 | [40 empty] | D Total |  | 3794.6557
H - Phjl Hejtzenroeder | Job: 1302 - PF Desjgn -KALjSH | 61.5946 | 5 |  |  | 42.3325 | 13.0175 | 0.735 | 0.50959 | [58 empty] | 5 | 47.3325 | 60.35 | 61.085 | 61.5946 | [40 empty] | H | 1302 | 61.2847 | H | 1302 | 61.5946
H - Phjl Hejtzenroeder | Job: 1352 - PF Cojl Procurement-KALjSH | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1352 | 0 |  | 1352 | 0
H - Phjl Hejtzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1353 | 0 |  | 1353 | 0
H - Phjl Hejtzenroeder | Job: 1354 - Trjm Cojl Desjgn &Procurement-KALjSH | 1.4861 |  |  |  | 0 | 0 | 0 | 1.4861 | [58 empty] | 0 | 0 | 0 |  | 1.4861 | [41 empty] | 1354 | 0 |  | 1354 | 1.4861
H - Phjl Hejtzenroeder | Job: 1355 - WBS 13 j&C Proc and Cojl Assy-KALjSH | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1355 | 0 |  | 1355 | 0
H - Phjl Hejtzenroeder | Job: 1361 - TF Fabrjcatjon-KALjSH | 363.6 | 4 | 45 | 59 | 91.4121 | 68.2379 | 63.632 | 32.318 | [58 empty] | 108 | 199.4121 | 267.65 | 331.282 | 363.6 | [41 empty] | 1361 | 331.2825 |  | 1361 | 363.6
H - Phjl Hejtzenroeder | Job: 1404 - MCWF R&D 1st Prod | -35.94 | -36 |  |  | 0.06 | 0 | 0 | 0 | [58 empty] | -36 | -35.94 | -35.94 | -35.94 | -35.94 | [41 empty] | 1404 | -35.94 |  | 1404 | -35.94
H - Phjl Hejtzenroeder | Job: 1411 - MCWF Fabr. S005242-HEjTZENROEDER | -80.3908 | 6 | 4 | -90 | -0.3908 | 0.0008 | 0 | -0.0008 | [58 empty] | -80 | -80.3908 | -80.39 | -80.39 | -80.3908 | [41 empty] | 1411 | -80.3908 |  | 1411 | -80.3908
H - Phjl Hejtzenroeder | Job: 1416 - Mod Cojl Type AB Fnl Dsn-WjLLjAMSON | 112.6397 | 4 | 29 | 55 | 15.1533 | 0.046734 | 0.632 | 8.8077 | [58 empty] | 88 | 103.1533 | 103.2 | 103.832 | 112.6397 | [41 empty] | 1416 | 103.5594 |  | 1416 | 112.6397
H - Phjl Hejtzenroeder | Job: 1421 - Mod Cojl jnterface Desjgn-WjLLjAMSON | 1033.8228 | 62 | 167 | 406 | 76.1819 | 30.1181 | 199.194 | 93.3288 | [58 empty] | 635 | 711.1819 | 741.3 | 940.494 | 1033.8228 | [41 empty] | 1421 | 940.2338 |  | 1421 | 1033.8228
H - Phjl Hejtzenroeder | Job: 1429 - MC jnterface R&D-GETTELFjNGER | 78.3249 | 30 |  | 44 | 9.2365 | -9.2365 | 4.065 | 0.25992 | [58 empty] | 74 | 83.2365 | 74 | 78.065 | 78.3249 | [41 empty] | 1429 | 78.0654 |  | 1429 | 78.3249
H - Phjl Hejtzenroeder | Job: 1501 - Cojl Structures Desjgn-DAHLGREN | 145.1989 | 2 | 43 | 30 | 6.9424 | 54.7576 | 8.301 | 0.19791 | [58 empty] | 75 | 81.9424 | 136.7 | 145.001 | 145.1989 | [41 empty] | 1501 | 145.0015 |  | 1501 | 145.1989
H - Phjl Hejtzenroeder | Job: 1550 - Cojl Struct. Procurement -DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1550 | 0 |  | 1550 | 0
H - Phjl Hejtzenroeder | Job: 1601 - Cojl Servjces Desjgn-GORANSON | 22.9678 |  | 6 |  | 0.2288 | 8.3712 | -0.002 | 8.3698 | [58 empty] | 6 | 6.2288 | 14.6 | 14.598 | 22.9678 | [41 empty] | 1601 | 14.5983 |  | 1601 | 22.9678
H - Phjl Hejtzenroeder | Job: 1701 - Cryostat Desjgn-GETTLEFjNGER | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1701 | 0 |  | 1701 | 0
H - Phjl Hejtzenroeder | Job: 1702 - Base Support Struct Desjgn-DAHLGREN | 11.0679 |  |  |  | 0 | 10.83 | 0.26 | -0.022104 | [58 empty] | 0 | 0 | 10.83 | 11.09 | 11.0679 | [41 empty] | 1702 | 11.0903 |  | 1702 | 11.0679
H - Phjl Hejtzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFjNGER | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1751 | 0 |  | 1751 | 0
H - Phjl Hejtzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 1752 | 0 |  | 1752 | 0
H - Phjl Hejtzenroeder | Job: 1806 - FP Assembly specs | 106.1322 |  | 3 | 22 | 2.7447 | 8.4053 | 3.688 | 66.2942 | [58 empty] | 25 | 27.7447 | 36.15 | 39.838 | 106.1322 | [41 empty] | 1806 | 39.8389 |  | 1806 | 106.1322
H - Phjl Hejtzenroeder | Job: 1901 - Stellarator Core Mngtt&jntegr-COLE | 232.2105 | 34 | 32 | 32 | 34.6417 | 28.9183 | 37.571 | 33.0795 | [58 empty] | 98 | 132.6417 | 161.56 | 199.131 | 232.2105 | [41 empty] | 1901 | 199.1319 |  | 1901 | 232.2105
H - Phjl Hejtzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REjERSEN | 456.8854 | 108 | 100 | 87 | -5.797 | 53.257 | 60.64 | 53.7854 | [58 empty] | 295 | 289.203 | 342.46 | 403.1 | 456.8854 | [41 empty] | 8202 | 403.1012 |  | 8202 | 456.8854
H - Phjl Hejtzenroeder | Job: 8203 - Desjgn jntegratjon-BROWN | 225.2187 | 31 | 29 | 29 | 41.9084 | 29.5616 | 33.7811 | 30.9676 | [58 empty] | 89 | 130.9084 | 160.47 | 194.2511 | 225.2187 | [41 empty] | 8203 | 194.2511 |  | 8203 | 225.2187
H - Phjl Hejtzenroeder | Job: 8204 - Systems Analysjs-BROOKS | 231.4724 | 35 | 34 | 34 | 44.9102 | 33.0398 | 26.361 | 24.1614 | [58 empty] | 103 | 147.9102 | 180.95 | 207.311 | 231.4724 | [41 empty] | 8204 | 207.311 |  | 8204 | 231.4724
H - Phjl Hejtzenroeder | Job: 8205 - Djmensjonal Control Coordjn-ELLjS | 100.769 |  | 21 | 21 | 33.2674 | 0.73264 | 11.581 | 13.188 | [58 empty] | 42 | 75.2674 | 76 | 87.581 | 100.769 | [41 empty] | 8205 | 87.9122 |  | 8205 | 100.769
H - Phjl Hejtzenroeder | Job: 8210 - FY07 Rebaseljng tasks | 18.8142 | 15 | 4 |  | -0.1858 | -0.0042 | 0.004 | 0.0002 | [58 empty] | 19 | 18.8142 | 18.81 | 18.814 | 18.8142 | [41 empty] | 8210 | 18.8142 |  | 8210 | 18.8142
H - Phjl Hejtzenroeder | Job: 8215 Plant Desjgn | 5.4974 |  |  |  | 0 | 0 | 3 | 2.4974 | [58 empty] | 0 | 0 | 0 | 3 | 5.4974 | [41 empty] | 8215 | 2.9601 |  | 8215 | 5.4974
| Total Phjl Hejtzenroeder | 3091.3718 | 300 | 517 | 729 | 392.6461 | 330.0539 | 453.4431 | 369.2287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1546 | 1938.6461 | 2268.7 | 2722.1431 | 3091.3718 | [40 empty] | H Total |  | 2722.1059
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRjSHNAN | -104.1 | -104 |  |  | -0.1 | 0 | 0 | 0 | [58 empty] | -104 | -104.1 | -104.1 | -104.1 | -104.1 | [40 empty] | V | 4101 | -104.1 | V | 4101 | -104.1
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRjSHNAN | 1.8943 |  |  |  | 0 | 0 | 0 | 1.8943 | [58 empty] | 0 | 0 | 0 |  | 1.8943 | [41 empty] | 4301 | 1.0132 |  | 4301 | 1.8943
V - Al vonHalle | Job: 4401 - Control & Protectjon-RAMAKRjSHNAN | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 4401 | 0 |  | 4401 | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & jntegr-RAMAKRjSHNAN | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 4501 | 0 |  | 4501 | 0
V - Al vonHalle | Job: 5101 - Network and Fjber | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 5101 | 0 |  | 5101 | 0
V - Al vonHalle | Job: 5201 - j&C Systems-SjCHTA | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 5201 | 0 |  | 5201 | 0
V - Al vonHalle | Job: 5301 - Data Acqujsjtjon-SjCHTA | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 5301 | 0 |  | 5301 | 0
V - Al vonHalle | Job: 5401 - Facjljty Tjmjng & | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 5401 | 0 |  | 5401 | 0
V - Al vonHalle | Job: 5501 - Real Tjme Control | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 5501 | 0 |  | 5501 | 0
V - Al vonHalle | Job: 5601 - Central Safety &jnterlock Sys-SjCHTA | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 5601 | 0 |  | 5601 | 0
V - Al vonHalle | Job: 5801 - Central j&C jntegr& Oversjght-SjCHTA | 11.1814 | 1 | 1 | 1 | 2.7232 | 1.2568 | 2.32 | 1.8814 | [58 empty] | 3 | 5.7232 | 6.98 | 9.3 | 11.1814 | [41 empty] | 5801 | 9.2529 |  | 5801 | 11.1814
V - Al vonHalle | Job: 8501 - jntegrated Systems Testjng-GENTjLE | 0 |  |  |  | 0 | 0 | 0 | 0 | [58 empty] | 0 | 0 | 0 |  | 0 | [41 empty] | 8501 | 0 |  | 8501 | 0
| Total Al vonHalle | -91.0243 | -103 | 1 | 1 | 2.6232 | 1.2568 | 2.32 | 3.7757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | -101 | -98.3768 | -97.12 | -94.8 | -91.0243 | [40 empty] | V Total |  | -93.8339 | Grand Total |  | 8027.3488
|  | 8088.9736 | 421 | 1271 | 1494 | 1243.0134 | 1125.2471 | 1495.2866 | 1039.4265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3186 | 4429.0134 | 5554.2605 | 7049.5471 | 8088.9736 | [40 empty] | Grand Total |  | 7050.6268
corrected
corrected

## critical path watch list
Total Float Trend (float in days/monthly status period)
(schedule slippage trends)
Schedule Total Float (work days)
FDR Forecast Date = |  |  |  | July | Aug | Sept | Oct | Nov
2/5/2008 | FDR Forecast Date =2/5/2008 |  | Job: 1302 - PF Design -KALISH | 87 | 75 | 72 | 49 | 54
4/17/2008 | FDR Forecast Date =4/17/2008 |  | Job: 1354 - Trim Coil Design &Procurement-KALISH | 13 | 13 | 13 | 15 | -11
5/23/2008 | FDR Forecast Date =5/23/2008 |  | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 86 | 86 | 86 | 83 | 83
3/6/2008 | FDR Forecast Date =3/6/2008 |  | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 65 | 56 | 37 | -2 | 24
11/27/2007 | FDR Forecast Date =11/27/2007 |  | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 0 | -23 | -57 | -38 | -37
|  |  | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 16 | 15 | -24 | -39 | -39
|  |  | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 14 | 13 | -10 | -18
12/7/2007 | FDR Forecast Date =12/7/2007 |  | Job: 1501 - Coil Structures Design-DAHLGREN | 56 | 17 | 110 | 110 | 106
Job: 1601 - Coil Services Design-GORANSON
8/10/2009 | FDR Forecast Date =8/10/2009 |  | Job: 1701 - Cryostat Design-GETTLEFINGER | 49 | 49 | 49 | 49 | 49
4/28/2008 | FDR Forecast Date =4/28/2008 |  | Job: 1702 - Base Support Struct Design-DAHLGREN | 38 | 22 | 0 | 0 | 32
Job: 1803/1805- FPA Tooling/Constr-BROWN -
|  |  | Job: 1803/1805- FPA Tooling/Constr-BROWN -Station 3 | 39 | 17 | 56 | 23 | -34
2/19/2008 | FDR Forecast Date =2/19/2008 |  | Job: 1803/1805- FPA Tooling/Constr-BROWN -Station 5 | 122 | 144 | 44 | 69 | 69
6/4/2008 | FDR Forecast Date =6/4/2008 |  | Job: 1803/1805- FPA Tooling/Constr-BROWN -Station 6 | 69 | 69 | 69 | 69 | 69
Job: 1806 - FP Assembly specs-COLE-
|  |  | Job: 1806 - FP Assembly specs-COLE-Station 2 | 0 | -23 | -35 | -28 | -23
|  |  | Job: 1806 - FP Assembly specs-COLE-Station 3 | 28 | 28 | 28 | 10 | -8
|  |  | Job: 1806 - FP Assembly specs-COLE-Station 5 | 92 | 97 | 97 | 80 | 57
|  |  | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 0 | -23 | -57 | -39 | -39
Total Float Trend (float in days/monthly status period)

## COST PERFORMANCE BY RLM & JOB
NCSX Cost Performance Report
Period May 1, 2007 through November 30, 2007
(Measured against unofficial proposed baseline)
|  | CUMULATIVE | [6 empty] | MONTHLY
RLM | JOB | BCWS | BCWP | ACWP | SPI | CPI | schedule variance | cost variance | BCWS | BCWP | ACWP | SPI | CPI | sched variance | cost variance | BUDGET to COMPLETE (from May 1,2007) | % plan | % work completed | % spent | EAC | C=calculated JM=Job Mgr estimate | increase/ (decrease)
Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 455 | 455 | 392.3228 | 1 | 1.1598 | 0 | 62.6772 | 83 | 81.754 | 52.458 | 0.98499 | 1.5585 | -1.246 | 29.296 | 3843 | 11.84% | 11.84% | 10.21% | 4158 | Strykowsky | 315
| Job: 8102 - NCSX MIE Management ORNL-LYON | 88 | 87.927 | 137.118 | 0.99917 | 0.64125 | -0.073 | -49.191 | 13 | 12.879 | 12.535 | 0.99069 | 1.0274 | -0.121 | 0.344 | 499 | 17.64% | 17.62% | 27.48% | 499 | Lyon | 0
| Job: 8998 - Allocations-STRYKOWSKY | 212 | 212 | 307.3978 | 1 | 0.68966 | 0 | -95.3978 | 31 | 32.596 | 78.1 | 1.0515 | 0.41736 | 1.596 | -45.504 | 1453 | 14.59% | 14.59% | 21.16% | 1536 | Strykowsky | 83 | -52 overrun in FY07 & 31k projection for fy08
| Total Jim Anderson | 755 | 754.927 | 836.8386 | 0.9999 | 0.90212 | -0.073 | -81.9116 | 127 | 127.229 | 143.093 | 1.0018 | 0.88914 | 0.229 | -15.864 | 5795 | 13.03% | 13.03% | 14.44% | 6193 |  | 398
[8 empty] | #REF! | [6 empty] | 0
Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 102 | 140.9945 | 185.3709 | 1.3823 | 0.76061 | 38.9945 | -44.3764 | 29 | 21.8115 | 19.061 | 0.75212 | 1.1443 | -7.1885 | 2.7505 | 408 | 25% | 34.56% | 45.43% | 916 | goranson | 508 | scope add-back | 203.2
| Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -252 | -251.6947 | -251.7703 | 0.99879 | 0.9997 | 0.30528 | 0.07558 | 0 | 0.00028 | 0 | #DIV/0! | #DIV/0! | 0.00028 | 0.00028 | -252 | 100% | 99.88% | 99.91% | -252 | JM | 0
| Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 225 | 226.4223 | 116.8304 | 1.0063 | 1.938 | 1.4223 | 109.5919 | 22 | 22.4543 | 11.699 | 1.0207 | 1.9193 | 0.45431 | 10.7553 | 350 | 64.29% | 64.69% | 33.38% | 350 | JM | 0
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 879 | 635.6104 | 370.9819 | 0.72311 | 1.7133 | -243.3896 | 264.6285 | 64 | 45.9104 | 66.906 | 0.71735 | 0.68619 | -18.0896 | -20.9956 | 1039 | 84.6% | 61.18% | 35.71% | 1039 | JM | 0 |  |  |  |  | 92449
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1358 | 1546.0835 | 1436.4037 | 1.1385 | 1.0764 | 188.0835 | 109.6798 | 188 | 106.8135 | 191.385 | 0.56816 | 0.55811 | -81.1865 | -84.5715 | 2867 | 47.37% | 53.93% | 50.1% | 2867 | JM | 0 |  |  |  |  | 115418
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 190 | 282.9757 | 370.053 | 1.4893 | 0.76469 | 92.9757 | -87.0773 | 43 | 114.6577 | 30.823 | 2.6665 | 3.7199 | 71.6577 | 83.8347 | 501 | 37.92% | 56.48% | 73.86% | 746 | Dudek | 245 | Lifts, transportation, add'l re-work |  |  |  | 92448
| Job: 1802 - FP Assy Oversight&Support-VIOLA | 390 | 353.7331 | 432.1947 | 0.90701 | 0.81846 | -36.2669 | -78.4616 | 58 | 47.0231 | 56.159 | 0.81074 | 0.83732 | -10.9769 | -9.1359 | 1989 | 19.61% | 17.78% | 21.73% | 1989 | JM | 0
| Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 184 | 68.7378 | 179.8729 | 0.37357 | 0.38215 | -115.2622 | -111.1351 | 24 | 0.22777 | 23.077 | 0.0094903 | 0.0098698 | -23.7722 | -22.8492 | 522 | 35.25% | 13.17% | 34.46% | 522 | JM | 0 |  |  |  |  | 92447 | 115417
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 1608.28 | 1423.5666 | 1011.0581 | 0.88515 | 1.408 | -184.7134 | 412.5085 | 185.57 | 130.0196 | 160.367 | 0.70065 | 0.81076 | -55.5504 | -30.3474 | 5745 | 27.99% | 24.78% | 17.6% | 5845 | strykowsky | 100 | re-estimate
| Job: 1815 - Field Period Assy | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1334 | 0% | 0% | 0% | 1334 | C | 0
| Job: 2101 - Fueling Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 69 | 0% | 0% | 0% | 258 | blanchard | 189 | scope add-back | 75.6
| Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 172 | 0% | 0% | 0% | 575 | blanchard | 403 | scope add-back | 161.2
| Job: 3101 - Magnetic Diagnostics-STRATTON | 263 | 192.6012 | 123.9386 | 0.73232 | 1.554 | -70.3988 | 68.6626 | 24 | 46.0682 | 1.346 | 1.9195 | 34.226 | 22.0682 | 44.7222 | 291 | 90.38% | 66.19% | 42.59% | 326 | stratton | 35 | scope add-back | 14
| Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 31 | 0% | 0% | 0% | 31 | C | 0
| Job: 3801 - Electron Beam Mapping-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 263 | 0% | 0% | 0% | 263 | C | 0
| Job: 3901 - Diagnostics sys Integration-STRATTON | 16 | 16.4159 | 27.2322 | 1.026 | 0.60281 | 0.41594 | -10.8163 | 2.2 | 2.3679 | 4.292 | 1.0763 | 0.55171 | 0.16794 | -1.9241 | 132 | 12.12% | 12.44% | 20.63% | 218.9732 | C | 86.9732
| Job: 6101 - Water Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 46 | 0% | 0% | 0% | 95 | C | 49 | scope add-back | 19.6
| Job: 6201 - Cryogenic Syst-GETTELFINGER | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 655 | 0% | 0% | 0% | 655 | C | 0
| Job: 6301 - Utility Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 105 | 0% | 0% | 0% | 105 | C | 0
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 573 | 0% | 0% | 0% | 573 | C | 0
| Job: 7301 - Platform Design & | 0 | 2.6336 | 0 | #DIV/0! | #DIV/0! | 2.6336 | 2.6336 | 0 | 0.019634 | 0 | #DIV/0! | #DIV/0! | 0.019634 | 0.019634 | 204 | 0% | 1.291% | 0% | 204 | C | 0
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -304 | -304.3808 | -275.4783 | 1.0013 | 1.1049 | -0.38082 | -28.9026 | 2 | 1.8192 | 6.801 | 0.90959 | 0.26749 | -0.18082 | -4.9818 | 1417 | -21.45% | -21.48% | -19.44% | 1417 | RLS | 0
| Job: 7501 - Construction Support Crew-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1407 | 0% | 0% | 0% | 1407 | C | 0
| Job: 7503 - Machine Assembly (station 6)-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 4511 | 0% | 0% | 0% | 4603 | strykowsky | 92 | scope add-back | 36.8
| Job: 7601 - Tooling Design & Fabrication-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 412 | 0% | 0% | 0% | 412 | C | 0
| Total Larry Dudek | 4659.28 | 4333.6991 | 3726.6878 | 0.93012 | 1.1629 | -325.5809 | 607.0113 | 641.77 | 539.1931 | 571.916 | 0.84017 | 0.94278 | -102.5769 | -32.7229 | 24791 | 18.79% | 17.48% | 15.03% | 26498.9732 |  | 1707.9732
0
Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 104 | 61.5946 | 55.349 | 0.59226 | 1.1128 | -42.4054 | 6.2456 | 25 | 0.50959 | 7.747 | 0.020384 | 0.065779 | -24.4904 | -7.2374 | 257 | 40.47% | 23.97% | 21.54% | 257 | JM | 0
| Job: 1352 - PF Coil Procurement-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1630 | 0% | 0% | 0% | 1630 | C | 0
| Job: 1353 - CS Structure Procurement-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 337 | 0% | 0% | 0% | 337 | C | 0
| Job: 1354 - Trim Coil Design &Procurement-KALISH | 29.6 | 1.4861 | 18.074 | 0.050205 | 0.082222 | -28.1139 | -16.5879 | 29.6 | 1.4861 | 8.422 | 19.9182 | 0.17645 | -28.1139 | -6.9359 | 162 | 18.27% | 0.9173% | 11.16% | 1516 | kalish/strykowsky | 1354 | scope add-back | 541.6
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 73 | 0% | 0% | 0% | 73 | C | 0
| Job: 1361 - TF Fabrication-KALISH | 348 | 363.6 | 385.1965 | 1.0448 | 0.94393 | 15.6 | -21.5965 | 59 | 32.318 | 44.653 | 0.54776 | 0.72376 | -26.682 | -12.335 | 1003 | 34.7% | 36.25% | 38.4% | 1003 | JM | 0
| Job: 1404 - MCWF R&D 1st Prod | -36 | -35.94 | -34.9474 | 0.99833 | 1.0284 | 0.06 | -0.99262 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | -36 | 100% | 99.83% | 97.08% | -36 | JM | 0
| Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -84 | -80.3908 | -65.1126 | 0.95703 | 1.2346 | 3.6092 | -15.2782 | 0 | -0.0008 | 0 | 0 | #DIV/0! | -0.0008 | -0.0008 | -80 | 105% | 100.5% | 81.39% | -80 | JM | 0
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 242 | 112.6397 | 122.0559 | 0.46545 | 0.92285 | -129.3603 | -9.4161 | 56 | 8.8077 | 34.792 | 0.15728 | 0.25315 | -47.1923 | -25.9843 | 280 | 86.43% | 40.23% | 43.59% | 280 | JM | 0
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1140 | 1033.8228 | 864.1527 | 0.90686 | 1.1963 | -106.1772 | 169.6701 | 26 | 93.3288 | 94.52 | 3.5896 | 0.9874 | 67.3288 | -1.1912 | 1207 | 94.45% | 85.65% | 71.6% | 1207 | JM | 0
| Job: 1429 - MC Interface R&D-GETTELFINGER | 118 | 78.3249 | 86.9042 | 0.66377 | 0.90128 | -39.6751 | -8.5793 | 0 | 0.25992 | 0.671 | 0 | 0.38737 | 0.25992 | -0.41108 | 118 | 100% | 66.38% | 73.65% | 118 | JM | 0
| Job: 1501 - Coil Structures Design-DAHLGREN | 186 | 145.1989 | 183.0811 | 0.78064 | 0.79309 | -40.8011 | -37.8822 | 0 | 0.19791 | 23.081 | #DIV/0! | 0.0085744 | 0.19791 | -22.8831 | 186 | 100% | 78.06% | 98.43% | 186 | JM | 0
| Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1076 | 0% | 0% | 0% | 1076 | C | 0
| Job: 1601 - Coil Services Design-GORANSON | 6 | 22.9678 | 0 | 3.828 | #DIV/0! | 16.9678 | 22.9678 | 0 | 8.3698 | 0 | 0 | #DIV/0! | 8.3698 | 8.3698 | 861 | 0.6969% | 2.668% | 0% | 1141 | goranson/strykowsky | 280 | scope add-back | 112
| Job: 1701 - Cryostat Design-GETTLEFINGER | 0 | 0 | 5.2332 | #DIV/0! | 0 | 0 | -5.2332 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 207 | 0% | 0% | 2.528% | 207 | JM | 0
| Job: 1702 - Base Support Struct Design-DAHLGREN | 79 | 11.0679 | 31.743 | 0.1401 | 0.34867 | -67.9321 | -20.6751 | 36 | -0.022104 | -0.857 | -0.00061401 | 0.025793 | -36.0221 | 0.8349 | 163 | 48.47% | 6.79% | 19.47% | 163 | JM | 0
| Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 325 | 0% | 0% | 0% | 325 | C | 0
| Job: 1752 - Base Support Proc-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 89 | 0% | 0% | 0% | 89 | C | 0
| Job: 1806 - FP Assembly specs | 139 | 106.1322 | 2.89 | 0.76354 | 36.7239 | -32.8678 | 103.2422 | 19 | 66.2942 | 0.883 | 3.4892 | 0.013319 | 47.2942 | 65.4112 | 514 | 27.04% | 20.65% | 0.5623% | 514 | JM | 0
| Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 233 | 232.2105 | 130.754 | 0.99661 | 1.7759 | -0.78946 | 101.4565 | 33 | 33.0795 | 10.79 | 1.0024 | 3.0658 | 0.079538 | 22.2895 | 1620 | 14.38% | 14.33% | 8.071% | 912.1958 | C | -707.8042
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 457 | 456.8854 | 428.2571 | 0.99975 | 1.0668 | -0.11455 | 28.6284 | 53 | 53.7854 | 55.126 | 1.0148 | 0.97568 | 0.78545 | -1.3406 | 2649 | 17.25% | 17.25% | 16.17% | 3149 | simmons | 500 | re-estimate
| Job: 8203 - Design Integration-BROWN | 226 | 225.2187 | 75.916 | 0.99654 | 2.9667 | -0.78128 | 149.3027 | 30 | 30.9676 | 20.05 | 1.0323 | 1.5445 | 0.96762 | 10.9176 | 1408 | 16.05% | 16% | 5.392% | 1408 | JM | 0
| Job: 8204 - Systems Analysis-BROOKS | 231 | 231.4724 | 319.3953 | 1.002 | 0.72472 | 0.47238 | -87.9229 | 24 | 24.1614 | 47.332 | 1.0067 | 0.51047 | 0.16138 | -23.1706 | 1154 | 20.02% | 20.06% | 27.68% | 1592.3376 | C | 438.3376
| Job: 8205 - Dimensional Control Coordin-ELLIS | 143 | 100.769 | 113.3171 | 0.70468 | 0.88927 | -42.231 | -12.5481 | 20 | 13.188 | 17.183 | 0.6594 | 0.76751 | -6.812 | -3.995 | 598 | 23.91% | 16.85% | 18.95% | 672.4648 | C | 74.4648
| Job: 8210 - FY07 Rebaseling tasks | 18.8 | 18.8142 | 54.0865 | 1.0008 | 0.34785 | 0.0142 | -35.2723 | 0 | 0.0002 | 7.21 | 0 | 2.7739e-05 | 0.0002 | -7.2098 | 19 | 98.95% | 99.02% | 284.7% | 54.6206 | C | 35.6206
| Job: 8215 Plant Design | 21 | 5.4974 | 0 | 0.26178 | #DIV/0! | -15.5026 | 5.4974 | 3 | 2.4974 | 0 | 1.2013 | #DIV/0! | -0.50261 | 2.4974 | 121 | 17.36% | 4.543% | 0% | 227 | strykowsky/brown | 106 | re-estimate
| Total Phil Heitzenroeder | 3601.4 | 3091.3718 | 2776.3457 | 0.85838 | 1.1135 | -510.0282 | 315.0262 | 413.6 | 369.2287 | 371.603 | 0.89272 | 0.99361 | -44.3713 | -2.3743 | 15941 | 22.59% | 19.39% | 17.42% | 18021.6188 |  | 2080.6188
#DIV/0!
Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104 | -104.1 | -104.1027 | 1.001 | 0.99997 | -0.1 | 0.00269 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 55 | -189.1% | -189.3% | -189.3% | 55.0014 |  | 0.0014212
| Job: 4301 - DC Systems-RAMAKRISHNAN | 2 | 1.8943 | 0 | 0.94713 | #DIV/0! | -0.10573 | 1.8943 | 1 | 1.8943 | 0 | 0.52791 | #DIV/0! | 0.89427 | 1.8943 | 603 | 0.3317% | 0.3141% | 0% | 603 |  | 0
| Job: 4401 - Control & Protection-RAMAKRISHNAN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1084 | 0% | 0% | 0% | 1084 |  | 0
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 0 | 0 | -0.55581 | #DIV/0! | 0 | 0 | 0.55581 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 683 | 0% | 0% | -0.08138% | 683 |  | 0
| Job: 5101 - Network and Fiber | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 150 | 0% | 0% | 0% | 226 | sichta | 76 | scope add-back | 30.4
| Job: 5201 - I&C Systems-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 196 | 0% | 0% | 0% | 432 | sichta | 236 | scope add-back | 94.4
| Job: 5301 - Data Acquisition-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 165 | 0% | 0% | 0% | 179 | sichta | 14 | scope add-back | 5.6
| Job: 5401 - Facility Timing & | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 205 | 0% | 0% | 0% | 376 | sichta | 171 | scope add-back | 68.4
| Job: 5501 - Real Time Control | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 129 | 0% | 0% | 0% | 349 | sichta | 220 | scope add-back | 88
| Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 222 | 0% | 0% | 0% | 387 | sichta | 165 | scope add-back | 66
| Job: 5801 - Central I&C Integr& Oversight-SICHTA | 11.2 | 11.1814 | 0 | 0.99834 | #DIV/0! | -0.018562 | 11.1814 | 2.1 | 1.8814 | 0 | 1.1162 | #DIV/0! | -0.21856 | 1.8814 | 69 | 16.23% | 16.2% | 0% | 69 | sichta | 0 | scope add-back | 0 |  | 882
| Job: 8501 - Integrated Systems Testing-GENTILE | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 765 | 0% | 0% | 0% | 765 |  | 0
| Total Al vonHalle | -90.8 | -91.0243 | -104.6585 | 1.0025 | 0.86973 | -0.22429 | 13.6342 | 3.1 | 3.7757 | 0 | 1.218 | #DIV/0! | 0.67571 | 3.7757 | 4326 | -2.099% | -2.104% | -2.419% | 5208.0014 |  | 882.0014
[16 empty] | Project stretch-out cost (@$202k /mo.) = |  |  |  | 505 |  | 505
| Total project (May 1 through completion) | 8924.88 | 8088.9736 | 7235.2136 | 0.90634 | 1.118 | -835.9064 | 853.76 | 1185.47 | 1039.4265 | 1086.612 | 0.87681 | 0.95658 | -146.0435 | -47.1855 | 50853 | 17.55% | 15.91% | 14.23% |  |  |  |  | -50853 |  | 1516.8
[15 empty] | Contingency = | 14380 | [7 empty] | -14380
[15 empty] | Cost through April 30,2007= | 67178.138 | 0 | 6264 | 16688
[15 empty] | TOTAL TEC = | 132411.138 | [7 empty] | -132411.138
[15 empty] | EAC Growth = | 1781.592 | [7 empty] | 5308.8 | scope add-back and 40% contingency
[15 empty] | Scope Add backs= | 3792 | [7 empty] | 1276.592 | re-estimate
[15 empty] | Contingency on scope add-backs= | 1516.8 | [7 empty] | 505 | strecthout cost
[15 empty] | Projected new baseline = | 139501.53 | [7 empty] | 1781.592
| ornl jobs | 1848 | 1595.7 | 1256.9706 | 0.86347 | 1.2695 |  | 338.7294 | 147 | 222.759 | 153.52 | 1.5154 | 1.451 |  | 69.239 | [8 empty] | 3058.1841
| pppl jobs | 7076.88 | 6493.2736 | 5978.243 | 0.91753 | 1.0862 |  | 515.0306 | 1038.47 | 816.6675 | 933.092 | 0.78641 | 0.87523 |  | -116.4245
|  | 8924.88 | 8088.9736 | 7235.2136
|  | 410 | 293.9565 | 255.7889 | 0.71697 | 1.1492 | -116.0435 | 38.1676
Phil's jobs
| ornl jobs | 1621 | 1401.6408 | 1116.9626 | 0.86468 | 1.2549 | -219.3592 | 284.6782
| pppl jobs | 1980.4 | 1689.731 | 1659.3831 | 0.85323 | 1.0183 | -290.669 | 30.3479
|  | 3601.4 | 3091.3718 | 2776.3457 | 0.85838 | 1.1135 | -510.0282 | 315.0262
corrected
corrected

## TOTAL PROJECT REPORT
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
TOTAL PROJECT |  |  |  | Jim Anderson |  | 2007-11-30
Highlights and Progress:
[13 empty] | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 2007-10-31 | 2007-12-01 | 2
[13 empty] | INTRF-055 | AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07* | 2007-11-01 | 2
Issues (not currently impacting technical, cost, or schedule but being watched): | [12 empty] | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2
Problems and work around plans :
Schedule | [8 empty] | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float | Group 1
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Float (work days) |  | task- | INTRF-055 | AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07A | 2007-11-01 | 2 |  | X |  |  | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish | Variance target 1 early finish
AB/BC/AA inboard interface - FDR task- INTRF-055 | 1421 | DW | 2007-09-04 | 27NOV07A | 2007-11-01 |  |  | task- | 1302-225 | PF Coils - PDR | 1302 | MK | 2007-12-11 | 2007-12-14 |  | 3 | 57 | X |  |  | 8205 | BE | 01JUN07* | 2007-08-31 | 01JUN07A | 2007-09-21 | -14 | -14
PF Coils - PDR task- 1302-225 | 1302 | MK | 2007-12-11 | 2007-12-14 |  | 57 |  | task- | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-14 |  | 3 | 106 | X |  |  | 1806 | MC | 11JUN07* | 2007-09-11 | 11JUN07A | 2007-10-03 | -16 | -16
Coil Support Structures - FDR task- 1501-541 | 1501 | FD | 2007-09-21 | 2007-12-14 |  | 106 |  | task- | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2 | -39 | X |  |  | 1421 | DW | 2007-07-05 | 2007-07-18 | 25JUN07A | 29JUN07A | 12 | 12
Shims required for 1st 3 pack MC assy task- S21-5.04X | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | -39 |  | task- | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-01-29 |  | 3 | 54 | X |  |  | 1806 | MC | 11JUN07* | 2007-09-11 | 01JUL07A | 2007-10-12 | -23 | -23
PF Coils - FDR task- 1302-270 | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 54 |  | task- | 1416-605 | Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-01-30 |  | 3 | 24 | X |  |  | 1416 | DW | 2007-08-01 | 2007-11-21 | 01JUL07A | 2007-11-21 | 0 | 0
Prepare Type-ABC closeout FDR task- 1416-605 | 1416 | DW | 2008-01-14 | 2008-01-30 |  | 24 |  | task- | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-02-04 |  | 3 | 429 | X |  |  | 1803 | TB | 13JUL07* | 2007-07-13 | 02JUL07A | 17JUL07A | -2 | -2
Mod Coil C-C Joint - FDR task- 1421-3144 | 1421 | DW | 2008-01-07 | 2008-02-04 |  | 429 |  | task- | 1702-515 | Base support - PDR | 1702 | FD | 2007-11-26 | 2008-02-07 |  | 3 | 32 | X |  |  | 1501 | FD | 20JUL07* | 2007-07-20 | 20JUL07A | 20JUL07A | 0 | 0
Base support - PDR task- 1702-515 | 1702 | FD | 2007-11-26 | 2008-02-07 |  | 32 |  | task- | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 69 | X |  |  | 3101 | BS |  | 2007-09-06 |  | 09AUG07A | 19 | 19
Station 5 FDR task- 1803-5.6 | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 69 |  | task- | 1702-525M | Base Support Structure FDR | 1702 | FD | 2008-02-04 | 2008-03-13 | 2008-05-01 | 2 | 32 | X |  |  | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2 | -2
Base Support Structure FDR task- 1702-525M | 1702 | FD | 2008-02-04 | 2008-03-13 | 2008-05-01 | 32 |  | task- | 141-036 | PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-04-01 | 2008-09-01 | 2 | 54 | X |  |  | 8205 | BE | 2007-09-04 | 2007-10-15 | 2007-09-24 | 2007-11-02 | -14 | -14
PF Coils Awarded task- 141-036 | 1352 | MK | 2008-05-27 | 2007-04-18 | 2008-09-01 | 54 |  | task- | 191-002 | LN2 manifolds&piping- PDR | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 3 | 96 | X |  |  | 1416 | DW | 01OCT07* | 2007-11-06 | 01OCT07* | 2007-11-06 | 0 | 0
LN2 manifolds&piping- PDR task- 191-002 | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 96 |  | task- | TRIM-101 | ** Trim Coil PDR ** | 1354 | MK |  | 2008-04-16 |  | 3 | 0 | X |  |  | 1421 | DW |  | 2007-09-04 |  | 05OCT07* | -23 | -23
** Trim Coil PDR ** task- TRIM-101 | 1354 | MK |  | 2008-04-16 |  | 0 |  | task- | 162-036.9 | Award Coil Support Structure | 1550 | FD | 16JUN08* | 28APR08* | 2008-10-01 | 2 | 62 | X |  |  | 1302 | MK |  | 2007-12-11 |  | 2007-10-19 | 1900-02-03 | 35
Award Coil Support Structure task- 162-036.9 | 1550 | FD | 16JUN08* | 28APR08* | 2008-10-01 | 62 |  | task- | S21-11.07M | Complete 1st MCHP Assy (Sta 2) | 1810 | MV | 2008-05-09 | 2008-05-23 | 2008-09-01 | 2 | -39 | X |  |  | 1361 | MK |  | 2007-09-28 |  | 2007-10-19 | -15 | -15
Complete 1st MCHP Assy (Sta 2) task- S21-11.07M | 1810 | MV | 2008-05-09 | 2008-05-23 | 2008-09-01 | -39 |  | task- | TRIM-221 | ** Trim Coil + Structure FDR ** | 1354 | MK |  | 2008-06-03 |  | 3 | 0 | X |  |  | 1803 | TB |  | 2007-11-21 |  | 2007-10-29 | 1900-01-16 | 17
** Trim Coil + Structure FDR ** task- TRIM-221 | 1354 | MK |  | 2008-06-03 |  | 0 |  | task- | 1803-6.6 | Station 6 FDR | 1803 | TB | 2008-06-04 | 2008-06-04 |  | 3 | 69 | X |  |  | 8205 | BE | 2007-10-16 | 2008-02-15 | 2007-11-05 | 2008-03-06 | -14 | -14
Station 6 FDR task- 1803-6.6 | 1803 | TB | 2008-06-04 | 2008-06-04 |  | 69 |  | task- | P3-171VM | COMPLETE VPI OF 18th MOD COIL | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 2 | 44 | X |  |  | 1361 | MK | 23NOV07* | 2007-11-23 | 23NOV07* | 2007-11-23 | 0 | 0
COMPLETE VPI OF 18th MOD COIL task- P3-171VM | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 2 | 44 | [13 empty] | 1302 | MK | 2008-03-21 | 2008-03-24 | 2007-12-19 | 2007-12-20 | 1900-02-28 | 60
[21 empty] | 1421 | DW |  | 2008-01-07 |  | 2008-02-07 | -23 | -23
|  |  | Cost and schedule Performance | [17 empty] | 1501 | FD | 2007-09-21 | 2007-09-21 | 2008-02-21 | 2008-02-21 | -100 | -100
[5 empty] | From May 1,2007 | Current Month | [14 empty] | 1352 | MK |  | 2008-05-27 |  | 2008-03-03 | 1900-02-28 | 60
|  |  |  | BCWS = | 8924.88 | 1185.47 | [14 empty] | 1810 | MV | 2008-02-01 | 2008-02-06 | 2008-03-04 | 2008-03-07 | -22 | -22
|  |  |  | BCWP = | 8088.9736 | 1039.4265 | [14 empty] | 8205 | BE | 2008-02-18 | 2008-06-09 | 2008-03-07 | 2008-06-27 | -14 | -14
|  |  |  | ACWP = | 7235.2136 | 1086.612 | [14 empty] | 1702 | FD |  | 2008-02-04 |  | 2008-03-27 | -38 | -38
|  |  |  | CV = | 853.76
|  |  |  | SV = | -835.9064
|  |  |  | CPI = | 1.118 | 0.95658
|  |  |  | SPI = | 0.90634 | 0.87681
|  |  |  | BAC = | 118031.138
|  |  |  | EAC = | 67178.138
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact

## Monthly Report-JIM
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Project Management |  |  |  | Jim Anderson |  | 2007-11-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
PPPL Project Management Job 8101 | JA
ORNL Project Management Job 8102 | JL
Allocations Job 8998 | RLS
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 755 | 127
|  |  |  | BCWP = | 754.927 | 127.229
|  |  |  | ACWP = | 836.8386 | 143.093
|  |  |  | CV = | -81.9116
|  |  |  | SV = | -0.073
|  |  |  | CPI = | 0.90212 | 0.88914
|  |  |  | SPI = | 0.9999 | 1.0018
|  |  |  | BAC = | 11057.504
|  |  |  | EAC = | 11455.504
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
N/A

## Monthly Report-LARRY
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
NCSX Construction |  |  |  | Larry Dudek |  | 2007-11-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Mod Coil Fab Jobs 1408/1451/1459 | JC |  | Fueling & Vacuum WBS 21 & 22 |  | BB
Cryo Systems WBS 62 | GG |  | Diagnostics WBS 3 |  | BS
Assy Tooling design/fab Job 1803 | TB |  | Water/Utilities WBS 61/63 |  | LD
Field Period Assy Jobs 1802/1810/1815 | MV |  | Bakeout Systems WBS 64 |  | MK
Final Machine Assy WBS 75 | EP
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Float (work days) |  | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float | Group 1
Shims required for 1st 3 pack MC assy -(task S21-5.04X | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | -39 | -(task | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2 | -39 | X | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish
Final Scan of VVSA #3 Station 1 complete -(task R1810-1329 | 1810 | MV | 2008-02-06 | 2008-01-21 |  | 302 | -(task | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-21 |  | 3 | 302 |  | 3 | 1803 | TB | 13JUL07* | 39276 | 02JUL07A | 17JUL07A | -2
Station 5 FDR -(task 1803-5.6 | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 69 | -(task | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 69 | X | 3 | 3101 | BS |  | 39331 |  | 09AUG07A | 19
Complete 1st MCHP Assy (Sta 2) -(task S21-11.07M | 1810 | MV | 2008-05-09 | 2008-05-23 | 2008-09-01 | -39 | -(task | S21-11.07M | Complete 1st MCHP Assy (Sta 2) | 1810 | MV | 2008-05-09 | 2008-05-23 | 2008-09-01 | 2 | -39 | X | 2 | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2
Remove from stand Move A2-B2-C2 to holding area -(task S22-11.06 | 1810 | MV | 2008-06-19 | 2008-05-23 |  | -29 | -(task | S22-11.06 | Remove from stand Move A2-B2-C2 to holding area | 1810 | MV | 2008-06-19 | 2008-05-23 |  | 3 | -29 | 2110 | 3 | 1803 | TB |  | 39407 |  | 2007-10-29 | 17
Station 6 FDR -(task 1803-6.6 | 1803 | TB | 2008-06-04 | 2008-06-04 |  | 69 | -(task | 1803-6.6 | Station 6 FDR | 1803 | TB | 2008-06-04 | 2008-06-04 |  | 3 | 69 | X | 3 | 1810 | MV | 2008-02-01 | 39484 | 2008-03-04 | 2008-03-07 | -22
COMPLETE VPI OF 18th MOD COIL -(task P3-171VM | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 44 | -(task | P3-171VM | COMPLETE VPI OF 18th MOD COIL | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 2 | 44 | X
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 4659.28 | 641.77
|  |  |  | BCWP = | 4333.6991 | 539.1931
|  |  |  | ACWP = | 3726.6878 | 571.916
|  |  |  | CV = | 607.0113
|  |  |  | SV = | -325.5809
|  |  |  | CPI = | 1.1629 | 0.94278
|  |  |  | SPI = | 0.93012 | 0.84017
|  |  |  | BAC = | 45219.331
|  |  |  | EAC = | 46927.3042
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
NCSX
COST and SCHEDULE
PERFORMANCE REPORTS
NOVEMBER 2007

## Monthly Report- PHIL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Stellarator CoreDesign and Procurement |  |  |  | Phil Heitzenroeder |  | 2007-11-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Conventional Coils WBS 13 | Mike Kalish |  | Modular Coils Jobs 1416/1421/1429/1431 |  | Dave Williamson
Coil Services WBS 16 | Paul Goranson |  | Coil Structures & Base Support Structure WBS 15 |  | Fred Dahlgren
Cryostat Job 1701/1751 | Geoff Gettelfinger |  | Assembly Specs & Dwgs Job 1806 |  | Mike Cole
Assy tooling & constructability Job 1803 | Tom Brown |  | Systems Analysis Job 8204 |  | Art Brooks
Dimensional Control Job 8205 | Bob Ellis |  | Systems Engineering & Support Job 8202 |  | Wayne Reiersen
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Float (work days) |  | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Milestones | Total float | Group 1
AB/BC/AA inboard interface - FDR -(task INTRF-055 | 1421 | DW | 2007-09-04 | 27NOV07A | 2007-11-01 |  | -(task | INTRF-055 | AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07A | 2007-11-01 | 2 |  | X
Station 2 Assembly Drawings -(task 1803-205 | 1806 | MC | 2007-09-11 | 2007-12-07 |  | -21 | -(task | 1803-205 | Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2007-12-07 |  | 3 | -21
Station 2 Assembly Specification -(task 1803-201 | 1806 | MC | 2007-09-11 | 2007-12-11 |  | -23 | -(task | 1803-201 | Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2007-12-11 |  | 1900-01-02 | -23
PF Coils - PDR -(task 1302-225 | 1302 | MK | 2007-12-11 | 2007-12-14 |  | 57 | -(task | 1302-225 | PF Coils - PDR | 1302 | MK | 2007-12-11 | 2007-12-14 |  | 3 | 57 | X
Fab, Test & Deliver Coil #6 -(task 1361C-106 | 1361 | MK | 2007-11-23 | 2007-12-14 |  | 389 | -(task | 1361C-106 | Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 | 2007-12-14 |  | 3 | 389
Coil Support Structures - FDR -(task 1501-541 | 1501 | FD | 2007-09-21 | 2007-12-14 |  | 106 | -(task | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-14 |  | 3 | 106 | X
Dimensional control plans for station 2 -(task METFY07R1 | 8205 | BE | 2007-08-31 | 2007-12-21 |  | -31 | -(task | METFY07R1 | Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 | 2007-12-21 |  | 1900-01-02 | -31
Check and promote top-level models/drawings -(task 1416-506 | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 26 | -(task | 1416-506 | Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 3 | 26
Dimensional control plans for station 3 -(task METDCP-3 | 8205 | BE | 2007-10-15 | 2008-01-11 |  | 6 | -(task | METDCP-3 | Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2008-01-11 |  | 3 | 6
PF Coils - FDR -(task 1302-270 | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 54 | -(task | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-01-29 |  | 3 | 54 | X
Prepare Type-ABC closeout FDR -(task 1416-605 | 1416 | DW | 2008-01-14 | 2008-01-30 |  | 24 | -(task | 1416-605 | Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-01-30 |  | 3 | 24 | X
Prepare EM and structural analysis of leads -(task 1416-601 | 1416 | DW | 2007-11-06 | 2008-01-31 |  | 1169 | -(task | 1416-601 | Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-01-31 |  | 3 | 1169
Mod Coil C-C Joint - FDR -(task 1421-3144 | 1421 | DW | 2008-01-07 | 2008-02-04 |  | 429 | -(task | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-02-04 |  | 3 | 429 | X
Base support - PDR -(task 1702-515 | 1702 | FD | 2007-11-26 | 2008-02-07 |  | 32 | -(task | 1702-515 | Base support - PDR | 1702 | FD | 2007-11-26 | 2008-02-07 |  | 3 | 32 | X
Base Support Structure FDR -(task 1702-525M | 1702 | FD | 2008-02-04 | 2008-03-13 | 2008-05-01 | 32 | -(task | 1702-525M | Base Support Structure FDR | 1702 | FD | 2008-02-04 | 2008-03-13 | 2008-05-01 | 2 | 32 | X
PF Coils Awarded -(task 141-036 | 1352 | MK | 2008-05-27 | 2008-04-25 | 2008-09-01 | 54 | -(task | 141-036 | PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-04-01 | 2008-09-01 | 2 | 54 | X
LN2 manifolds&piping- PDR -(task 191-002 | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 96 | -(task | 191-002 | LN2 manifolds&piping- PDR | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 1900-01-02 | 96 | X
** Trim Coil PDR ** -(task TRIM-101 | 1354 | MK |  | 2008-04-16 |  | 0 | -(task | TRIM-101 | ** Trim Coil PDR ** | 1354 | MK |  | 2008-04-16 |  | 3 | 0 | X
** Trim Coil + Structure FDR ** -(task TRIM-221 | 1354 | MK |  | 2008-06-03 |  | 0 | -(task | TRIM-221 | ** Trim Coil + Structure FDR ** | 1354 | MK |  | 2008-06-03 |  | 3 | 0 | X
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 3601.4 | 413.6
|  |  |  | BCWP = | 3091.3718 | 369.2287
|  |  |  | ACWP = | 2776.3457 | 371.603
|  |  |  | CV = | 315.0262
|  |  |  | SV = | -510.0282
|  |  |  | CPI = | 1.1135 | 0.99361
|  |  |  | SPI = | 0.85838 | 0.89272
|  |  |  | BAC = | 56600.653
|  |  |  | EAC = | 58681.2718
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact

## Monthly Report-AL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Electrical, I&C and Startup |  |  |  | Al vonHalle |  | 2007-07-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Electrical Powers Systems WBS 4 | RR
Instrumentation and Controls | PS
Startup | CG
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
[10 empty] | Activity ID | Activity description | Early start | Early finish | Milestones | Job Number | Job Manager
[10 empty] | 1803-3.4 | Stage 3 support FDR | 13JUL07* | 2007-07-13 | 3 | 1803 | TB
[10 empty] | 3101-326 | FDR - ROWGOSKI COIL |  | 2007-09-06 | 3 | 3101 | BS
[10 empty] | S21-5.04X | Shims required for 1st 3 pack MC assy |  | 2007-09-20 | 2 | 1431 | LD
[10 empty] | 1803-5.6 | Station 5 FDR |  | 2007-11-21 | 3 | 1803 | TB
[10 empty] | R1810-1329 | Final Scan | 2008-02-01 | 2008-02-06 | 3 | 1810 | MV
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | -90.8 | 1.3
BCWP =
ACWP =
CV =
SV =
CPI =
SPI =
|  |  |  | BAC = | 5082.85
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 |  |  | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 |  |  | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 |  |  | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
No Milestones during the period

## Contingency
| period ending | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12
Cost
| Baseline | 14380 | 14380 | 14380 | 14380 | 14380 | 14380 | 14380
| ECP drawdown | 0 | 0 | 0 | 0
| (ECP Number) | none | none | none | none | none | none | none
| EAC (overrun)/underrun | 0 | 0 | 0 | 0 | -531 | -43 | -1277
| Cost Variance (overrun)/underrun | -209.4547 | 49.0555 | 671.9424 | 452.1688 | 278 | 901 | 854
| Schedule Slip (@$202k/mo.) | 0 | 0 | 0 | -221.2381 | -548.2857 | -375.114 | -505
| FREE BALANCE ($K) | 14170.5453 | 14429.0554 | 15051.9424 | 14610.9308 | 13578.7143 | 14862.886 | 13452
| BCWR | 50433 | 49162 | 47668 | 46424 | 45299 | 43803 | 42764
| FREE BALANCE (% of ETC) | 28.1% | 29.35% | 31.58% | 31.47% | 29.98% | 33.93% | 31.46%
| Target Drawdown Rate (%) | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3%
| BCWR | 50004 | 48796 | 47244 | 45880 | 44747 | 42784 | 41635 | 40752 | 39450 | 38335 | 37213 | 36161 | 35165 | 34114 | 32769 | 31484 | 30259 | 28922 | 27784 | 26546 | 25056 | 23790 | 22420 | 21112 | 19903 | 18646 | 17495 | 16340 | 15192 | 13640 | 12387 | 11389 | 10182 | 9153 | 7846 | 6639 | 5680 | 4777 | 4013 | 3276 | 2599 | 1755 | 1017 | 391 | 0
| BCWS | 621 | 1208 | 1552 | 1364 | 1133 | 1963 | 1149 | 883 | 1302 | 1115 | 1122 | 1052 | 996 | 1051 | 1345 | 1285 | 1225 | 1337 | 1138 | 1238 | 1490 | 1266 | 1370 | 1308 | 1209 | 1257 | 1151 | 1155 | 1148 | 1552 | 1253 | 998 | 1207 | 1029 | 1307 | 1207 | 959 | 903 | 764 | 737 | 677 | 844 | 738 | 626 | 391 |  | 50625
| Target Contingency Freebalance ($K) | 14151.132 | 13809.268 | 13370.052 | 12984.04 | 12663.401 | 12107.872 | 11782.705 | 11532.816 | 11164.35 | 10848.805 | 10531.279 | 10233.563 | 9951.695 | 9654.262 | 9273.627 | 8909.972 | 8563.297 | 8184.926 | 7862.872 | 7512.518 | 7090.848 | 6732.57 | 6344.86 | 5974.696 | 5632.549 | 5276.818 | 4951.085 | 4624.22 | 4299.336 | 3860.12 | 3505.521 | 3223.087 | 2881.506 | 2590.299 | 2220.418 | 1878.837 | 1607.44 | 1351.891 | 1135.679 | 927.108 | 735.517 | 496.665 | 287.811 | 110.653 | 0
Schedule
| Baseline | 11 | 11 | 11 | 11 | 11 | 11 | 11
| ECP Schedule Drawdown | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Critical path Schedule Slip (months) | 0 | 0 | 0 | -1.0952 | -2.7143 | -1.857 | -2.5
| FREE BALANCE (months) | 11 | 11 | 11 | 9.9048 | 8.2857 | 9.143 | 8.5
| Target (months) | 10.8036 | 10.6071 | 10.4107 | 10.2143 | 10.0179 | 9.8214 | 9.625 | 9.4286 | 9.2321 | 9.0357 | 8.8393 | 8.6429 | 8.4464 | 8.25 | 8.0536 | 7.8571 | 7.6607 | 7.4643 | 7.2679 | 7.0714 | 6.875 | 6.6786 | 6.4821 | 6.2857 | 6.0893 | 5.8929 | 5.6964 | 5.5 | 5.3036 | 5.1071 | 4.9107 | 4.7143 | 4.5179 | 4.3214 | 4.125 | 3.9286 | 3.7321 | 3.5357 | 3.3393 | 3.1429 | 2.9464 | 2.75 | 2.5536 | 2.3571 | 2.1607 | 1.9643 | 1.7679 | 1.5714 | 1.375 | 1.1786 | 0.98214 | 0.78571 | 0.58929 | 0.39286 | 0.19643 | 7.272e-15

## EAC calculation
Project start | current date | Baseline Finish | current total float (work days from primavera) | available 2 shift operation remaining on CP (mo.) | Projected Finish | Projected slip (mo.)
2007-05-01 | 2007-09-30 | 2011-01-11 | -57 | 18 | 2014-05-14 14:39 | 40.1188
[6 empty] | 8103.991 | = Stretchout cost impact @( $202k/mo.)
[6 empty] | 576 | = second shift supervision cost @ $64k/mo.
|  |  | BAC | EAC (from cpr)
|  |  | 50853 | #REF! | ETC increase = | #REF!
[5 empty] | Total Increase = | #REF!
[5 empty] | Projected EAC = | #REF!
[5 empty] | TEC = | 132412
[5 empty] | (under)/over = | #REF!
Formulas:
Projected Finish = ((([Baseline Finish]-[Project start])/(([current date]-[Project start]+(F6*7/5))/([current date]-[Project start]))+([Project start])))-(G6/2*30.4)

## Summary analysis
NCSX Summary Overview
NOVEMBER 2007
Cost Performance |  |  |  | BCWS | BCWP | ACWP
| Cumulative from May 1st, 2007 = |  |  | 8924.88 | 8088.9736 | 7235.2136
| Cost Through April 2007 = |  |  |  |  | 67178
| Cost to date = |  |  |  |  | 74413.2136
| BCWR (work to go) = |  |  |  | 42764.0264
| Contingency = |  |  |  | 14380
| Total TEC = |  |  |  | 132411
CPI = | 1.118 | 1.15 last month |  | Cost Variance = |  | 853.76 | Major Cost Variances
SPI = | 0.90634 | .91 last month |  | Schedule Variance = |  | -835.9064 | Mod Coil Punch List |  | CPI = .76 | -87 | (.5 last month)
[7 empty] | FP Assy tooling (job 1803) |  | CPI = .38 | -111 | (.44 last month)
[7 empty] | Systems Analysis (job 8204) |  | CPI =.72 | -88 | (.76 last month)
[7 empty] | Allocations (job 8998) |  | CPI=.69 | -95 | (.78 last month)
EAC= | 1782 |  |  |  |  | Scope Add-backs = |  | 5308.8
| 1277 | re-estimate
|  | 500 | WBS 82 project engineering management |  |  |  |  | scope add-back and 40% contingency
|  | 106 | Plant Design |  |  |  |  | 1701 | Trim coils incl coil services & install
|  | 100 | Field Period Assembly |  |  |  |  | 985 | VPS (incl NB ducts, pumps,instl, water systems
|  | 438 | Systems analysis |  |  |  |  | 189 | Injectors
|  | 398 | Project management |  |  |  |  | 35 | Diagnostics
|  | -708 | Stellarator core mgt |  |  |  |  | 882 | I&C
|  | 245 | mc punch list |  |  |  |  | 1516.8 | Contingency @40%
|  | 198 | other
| 505 | stretch-out cost
Cost/Schedule Uncertainties and Opportunities
| Uncertainties | [5 empty] | Opportunities
|  | Field period assy | [5 empty] | G&A/Burden rates ~$1M
Trim coil and PF coil fabrication schedule from vendors
MCI hardware (cost variance, ETC cost, and schedule delivery)
Critical path assessment
| #1 | Issue MC shim and puck drawings, fab shims and pucks by 1/10/08, start station 2 assy
Current critical path = -53 days (-2.5 months) as measured against preliminary assembly schedule (undergoing revision-action Viola/Strykowsky)
The schedule impact has increased from -1.9 mos last month to -2.5 mo. due to recent revision in station 2 task durations.
| #2 | Trim coil design, fabrication required for assembly in station 5.
First trim coils req'd end January 2009
zero float
Level II milestone status (near term) | [11 empty] | Activity ID | Activity description | Job Number | Job Manager | Baseline | Forecast | WBS | Milestones | Total float
| Design Reviews | [5 empty] | Baseline | Forecast | DOE Commitment | Float (mos.)
|  | PF Coils - PDR |  |  |  |  | 2007-12-11 | 2007-12-14 |  | 2.0952 |  | Design Reviews | [7 empty] | Float (mos.)
|  | Coil Support Structures - FDR |  |  |  |  | 2007-09-21 | 2007-12-14 |  | 4.5714 |  | 1302-225 | PF Coils - PDR | 1302 | MK | 2007-12-11 | 2007-12-14 |  | 3 | 2.0952
|  | Prepare Type-ABC closeout FDR |  |  |  |  | 2008-01-14 | 2008-01-30 |  | 1.2381 |  | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2007-12-14 |  | 3 | 4.5714
|  | PF Coils - FDR |  |  |  |  | 2008-03-24 | 2008-02-05 |  | 1.7143 |  | 1416-605 | Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-01-30 |  | 3 | 1.2381
|  | Base support - PDR |  |  |  |  | 2007-11-26 | 2008-02-07 |  | 1.5238 |  | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-05 |  | 3 | 1.7143
|  | Station 5 FDR |  |  |  |  | 2007-11-21 | 2008-02-19 |  | 3 |  | 1702-515 | Base support - PDR | 1702 | FD | 2007-11-26 | 2008-02-07 |  | 3 | 1.5238
|  | Base Support Structure FDR |  |  |  |  | 2008-02-04 | 2008-03-13 | 2008-05-01 | 1.5238 |  | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 3 | 3
|  | LN2 manifolds&piping- PDR |  |  |  |  | 2008-04-02 | 2008-04-02 |  | 4.2857 |  | 1702-525M | Base Support Structure FDR | 1702 | FD | 2008-02-04 | 2008-03-13 | 2008-05-01 | 2 | 1.5238
|  | ** Trim Coil PDR ** | [5 empty] | 2008-04-16 |  | -0.14286 |  | 191-002 | LN2 manifolds&piping- PDR | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 3 | 4.2857
|  | ** Trim Coil + Structure FDR ** | [5 empty] | 2008-06-03 |  | -0.14286 |  | TRIM-101 | ** Trim Coil PDR ** | 1354 | MK |  | 2008-04-16 |  | 3 | -0.14286
| Fabrication/Assembly | [10 empty] | TRIM-221 | ** Trim Coil + Structure FDR ** | 1354 | MK |  | 2008-06-03 |  | 3 | -0.14286
|  | Shims required for 1st 3 pack MC assy |  |  |  |  | 2007-09-20 | 2008-01-11 | 2007-12-01 | -2.0476 |  | Fabrication/Assembly
|  | PF Coils Awarded |  |  |  |  | 2008-05-27 | 2008-04-25 | 2008-09-01 | 1.7143 |  | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2 | -2.0476
|  | Complete 1st MCHP Assy (Sta 2) |  |  |  |  | 2008-05-09 | 2008-06-03 | 2008-09-01 | -2.0476 |  | 141-036 | PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-04-25 | 2008-09-01 | 2 | 1.7143
|  | Remove from stand Move A2-B2-C2 to holding area |  |  |  |  | 2008-06-19 | 2008-07-01 |  | -2.5238 |  | S21-11.07M | Complete 1st MCHP Assy (Sta 2) | 1810 | MV | 2008-05-09 | 2008-06-03 | 2008-09-01 | 2 | -2.0476
|  | COMPLETE VPI OF 18th MOD COIL |  |  |  |  | 2008-07-15 | 2008-06-30 | 2008-11-01 | 1.619 |  | S22-11.06 | Remove from stand Move A2-B2-C2 to holding area | 1810 | MV | 2008-06-19 | 2008-07-01 |  | 3 | -2.5238
Contingency | [6 empty] | BCWR
|  | Planned = |  |  | 14380 |  | 50853 | 28.28%
|  | Drawdown to date = |  |  | 0
|  | EAC (overrun)/underrun = |  |  | -1277
|  | Cost Variance (overrun)/underrun = |  |  | 854
|  | Schedule Slip (@$202k/mo.) = |  |  | -505
[5 empty] | 13452 |  | 42764 | 31.46%
|  | Current free balance contingency on remaining scope = |  |  |  |  | 31%
Risks (from updated risk registry)
2 risk retired; #4 MC interface design and #19 Viola/Perry cross utilization
ISSUES
1) Uncertainty in the component fabrication schedules requires urgency in meeting
upcoming design review dates for the Trim Coils, PF coils, Base support structure, and Coil support structure
2) The coil services lead design and fabrication schedule should be accelerated into FY08 to
ensure supporting the field period assembly schedule. (requires add'l $231k in FY08)
Additional candidates for acceleration include the cryogenic systems and cryostat design. (Requires add'l $405k in FY08)
Contents
Page
[19 empty] | Summary |  | 3
[19 empty] | Cost Performance Report (CPR) |  | 4-5
[19 empty] | Performance Curves |  | 6-9
[19 empty] | Milestones |  | 10-11
[19 empty] | Contingency Analysis |  | 12
[19 empty] | Critical Path |  | 13
[19 empty] | Responsible Line Manager Analysis Reports |  | Issued under separate cover
[19 empty] | Schedule Barcharts |  | Issued under separate cover

## Baseline Reconciliation
NCSX EAC - Reconciliation Detail
|  | WBS II |  | JOB | COST TO DATE 4/1/03 - 4/30/07 |  | ETC 5/1/07 THROUGH COMPLETION |  |  |  |  | TOTAL |  | ecp31 | deltas
[7 empty] | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | ETC | TOTAL EAC
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18
|  | 12 - Vacuum Vessel Systems | Phil | 1201 - Vacuum Vessel Prelim Dsn | 424 | [6 empty] | 0 | 424 | 424 | 0 | 0% | 1201
|  |  | Phil | 1202 - Vacuum Vessel R&D | 1770.9 | [6 empty] | 0 | 1770.9 | 1791 | -20.1 | -1.122% | 1202
|  |  | Phil | 1203 - Vacuum Vessel Final Dsn | 1217 | [6 empty] | 0 | 1217 | 944 | 273 | 28.92% | 1203
1204-VV Sys Procurements (non VVSA) |  |  | Larry | 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 535.9 |  | 47 | 162 | 1 | 198 | 0 | 408 | 943.9 | 557 | 386.9 | 69.46% | 1204
|  |  | Phil | 1206 - VV Field Weld Joint R&D | 15.954 | [6 empty] | 0 | 15.954 | 74 | -58.046 | -78.44% | 1206
|  |  | Larry | 1250 - Vacuum Vessel Fabrication | 5788.9 |  | -252 | 0 | 0 | 0 | 0 | -252 | 5536.9 | 5741 | -204.1 | -3.555% | 1250
|  |  |  | Subtotal | 9752.654 |  | -205 | 162 | 1 | 198 | 0 | 156 | 9908.654 | 9531 | 377.654 | 3.962%
[15 empty] | 0 | #DIV/0!
|  | 13 - Conventional Coils | Phil | 1301 - TF Design | 970.1 | [6 empty] | 0 | 970.1 | 837 | 133.1 | 15.9% | 1301
1302 - PF Design |  |  | Phil | 1302 - PF Design -KALISH | 19.338 |  | 44 | 213 | 0 | 0 | 0 | 257 | 276.338 | 253 | 23.338 | 9.225% | 1302
|  |  | Phil | 1303 - Central Solenoid Support Design | 154.9 | [6 empty] | 0 | 154.9 |  | 154.9 | #DIV/0!
|  |  | Phil | 1350 - TF Coil Fabr Prep | 535.99 | [6 empty] | 0 | 535.99 | 400 | 135.99 | 34% | 1350
|  |  | Phil | 1351 - TF Coil Fabr Supplies | 482.959 | [6 empty] | 0 | 482.959 | 1318 | -835.041 | -63.36% | 1351
|  |  | Phil | 1352 - PF Coil Procurement-KALISH |  |  | 0 | 968 | 634 | 28 | 0 | 1630 | 1630 | 1362 | 268 | 19.68% | 1352
|  |  | Phil | 1353 - CS Structure Procurement-DAHLGREN |  |  | 0 | 0 | 78 | 259 | 0 | 337 | 337 | 270 | 67 | 24.81% | 1353
|  |  | Phil | 1354 - Trim Coil Design &Procurement-KALISH |  |  | 0 | 0 | 162 | 0 | 0 | 162 | 162 | 258 | -96 | -37.21% | 1354
|  |  | Phil | 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  |  | 0 | 32 | 39 | 2 | 0 | 73 | 73 | 92 | -19 | -20.65% | 1355
|  |  | Phil | 1361 - TF Fabrication-KALISH | 1062.999 | (1) | 228 | 775 | 0 | 0 | 0 | 1003 | 2065.999 |  | 2065.999 | #DIV/0!
|  |  |  | Subtotal | 3226.286 |  | 272 | 1988 | 913 | 289 | 0 | 3462 | 6688.286 | 4790 | 1898.286 | 39.63%
[15 empty] | 0 | #DIV/0!
|  | 14 - Modular Coils | Phil | 1401 - Mod Coil Prel.Dsn | 304.5 | [6 empty] | 0 | 304.5 | 303 | 1.5 | 0.495% | 1401
|  |  | Phil | 1402 - Mod.Coil Analyses | 239.14 | [6 empty] | 0 | 239.14 | 239 | 0.14 | 0.05858% | 1402
|  |  | Phil | 1403 modular coil winding form design | 3310.9 | [6 empty] | 0 | 3310.9 | 3149 | 161.9 | 5.141% | 1403
|  |  | Phil | 1404-MCWF R&D & 1st Prod Casting | 2554.9 |  | -36 | 0 | 0 | 0 | 0 | -36 | 2518.9 | 2534 | -15.1 | -0.5959% | 1404
|  |  | Phil | 1405-Mod Coil Winding R&D Prep | 168 | [6 empty] | 0 | 168 | 168 | 0 | 0% | 1405
|  |  | Phil | 1406 - Mod. Coil Winding Facility | 2263 | [6 empty] | 0 | 2263 | 2214 | 49 | 2.213% | 1406
|  |  | Phil | 1407 -Mod Coil Winding Facility | 2569 | [6 empty] | 0 | 2569 | 2523 | 46 | 1.823% | 1407
1408-Mod Coil Winding Supplies |  |  | Larry | 1408 - MC Winding Supplies-CHRZANOWSKI | 2353 |  | 178 | 172 | 0 | 0 | 0 | 350 | 2703 | 1836 | 867 | 47.22% | 1408
|  |  | Phil | 1409 - Mod. Coil Test Stand | 832.9 | [6 empty] | 0 | 832.9 | 488 | 344.9 | 70.68% | 1409
|  |  | Phil | 1410 MC Twisted Racetrack Fabr | 1049.908 | [6 empty] | 0 | 1049.908 | 799 | 250.908 | 31.4% | 1410
1411-MCWF Fabrication S005242 |  |  | Phil | 1411 - MCWF Fabr. S005242-HEITZENROEDER | 9965 |  | -80 | 0 | 0 | 0 | 0 | -80 | 9885 | 8329 | 1556 | 18.68% | 1411
|  |  | Phil | 1412 - Complete Winding Facilities | 540.732 | [6 empty] | 0 | 540.732 | 310 | 230.732 | 74.43% | 1412
|  |  | Phil | 1413 - Mod Coil Fracture Analysis | 27.819 | [6 empty] | 0 | 27.819 | 23 | 4.819 | 20.95% | 1413
|  |  | Phil | 1414 - Coil Testing | 638.674 | [6 empty] | 0 | 638.674 |  | 638.674 | #DIV/0!
|  |  | Phil | 1415 - Dimensional Control Testing | 24.038 | [6 empty] | 0 | 24.038 |  | 24.038 | #DIV/0!
Mod Coil Design 1416 Coil Design, Job 1421 Interface design |  |  | Phil | 1416 &1421 - Mod Coil Interface Design-WILLIAMSON | 1108.49 |  | 1066 | 422 | 0 | 0 | 0 | 1488 | 2596.49 |  | 2596.49 | #DIV/0!
Job 1429 Interface R&D/Test |  |  | Phil | 1429 - MC Interface R&D-GETTELFINGER | 157.99 |  | 118 | 0 | 0 | 0 | 0 | 118 | 275.99 |  | 275.99 | #DIV/0!
|  |  | Phil | 1419 - Winding Facility Modification | 48.434 | [6 empty] | 0 | 48.434 |  | 48.434 | #DIV/0!
|  |  | Phil | 1431 - Mod. Coil Interface Hardware-DUDEK |  |  | 362 | 660 | 0 | 17 | 0 | 1039 | 1039 | 86 | 953 | 1108% | 1431
1451 - Mod Coil Winding (incl 1459 punch list and unplanned work) |  |  | Larry | 1451 - Mod Coil Winding-CHRZANOWSKI | 5982.2 | (1) | 1054 | 1813 | 0 | 0 | 0 | 2867 | 8849.2 | 5091 | 3758.2 | 73.82% | 1451
|  |  | Larry | 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  |  | 90 | 411 | 0 | 0 | 0 | 501 | 501 |  | 501 | #DIV/0!
|  |  | Phil | 1460 - 3rd Winding Fixture | 57.337 | [6 empty] | 0 | 57.337 |  | 57.337 | #DIV/0!
|  |  |  | Subtotal | 34195.962 |  | 2752 | 3478 | 0 | 17 | 0 | 6247 | 40442.962 | 28092 | 12350.962 | 43.97%
[15 empty] | 0 | #DIV/0!
1501 - Structures Design |  | 15 - Coil Structures | Phil | 1501 - Coil Structures Design-DAHLGREN | 330.94 | (1) | 164 | 22 | 0 | 0 | 0 | 186 | 516.94 | 221 | 295.94 | 133.9% | 1501
1550 - Structures Procurement |  |  | Phil | 1550 - Coil Struct. Procurement -DAHLGREN | 4.061 |  | 0 | 403 | 673 | 0 | 0 | 1076 | 1080.061 | 1191 | -110.939 | -9.315% | 1550
|  |  |  | Subtotal | 335.001 |  | 164 | 425 | 673 | 0 | 0 | 1262 | 1597.001 | 1412 | 185.001 | 13.1%
[15 empty] | 0 | #DIV/0!
1601 - Coil Services |  | 16 - Coil Services | Phil | 1601 - Coil Services Design-GORANSON | 2.614 |  | 6 | 323 | 372 | 160 | 0 | 861 | 863.614 | 1140 | -276.386 | -24.24% | 1601
[15 empty] | 0 | #DIV/0!
1701-Cryostat design |  | 17 - Cryostat and Base Support Structure | Phil | 1701 - Cryostat Design-GETTLEFINGER | 431.073 |  | 0 | 0 | 207 | 0 | 0 | 207 | 638.073 | 504 | 134.073 | 26.6% | 1701
|  |  | Phil | 1702 - Base Support Struct Design-DAHLGREN |  |  | 0 | 163 | 0 | 0 | 0 | 163 | 163 | 541 | -378 | -69.87% | 1751
|  |  | Phil | 1751 - Cryostat Procurement-GETTLEFINGER |  |  | 0 | 0 | 0 | 325 | 0 | 325 | 325 | 315 | 10 | 3.175% | 1752
|  |  | Phil | 1752 - Base Support Proc-DAHLGREN |  |  | 0 | 61 | 28 | 0 | 0 | 89 | 89 |  | 89 | #DIV/0!
|  |  |  | Subtotal | 431.073 |  | 0 | 224 | 235 | 325 | 0 | 784 | 1215.073 | 1360 | -144.927 | -10.66%
[15 empty] | 0 | #DIV/0!
|  | 18 - Field Period Assembly | Larry | 1801-Field Period Assy | 64.38 | [6 empty] | 0 | 64.38 | 61 | 3.38 | 5.541% | 1801
1802 - FP Assy Oversight Support |  |  | Larry | 1802 - FP Assy Oversight&Support-VIOLA | 986.703 | (1) | 253 | 790 | 858 | 88 | 0 | 1989 | 2975.703 | 1444 | 1531.703 | 106.1% | 1802
1803- FP Assy Tooling/Constructability |  |  | Larry | 1803 - FP Asy Tooling/Constrblty-BROWN | 1142.2 |  | 131 | 316 | 75 | 0 | 0 | 522 | 1664.2 | 1220 | 444.2 | 36.41% | 1803
|  |  | Larry | 1804-FP Assy Measurement | 558.937 | [6 empty] | 0 | 558.937 | 502 | 56.937 | 11.34% | 1804
|  |  | Larry | 1805 - FP Assy Hardware & Fixt Procurement | 6.876 | [6 empty] | 0 | 6.876 |  | 6.876 | #DIV/0!
1806 - FP Assy Specs and Drawings |  |  | Larry | 1806 - FP Assembly specs | 26.517 |  | 92 | 382 | 40 | 0 | 0 | 514 | 540.517 |  | 540.517 | #DIV/0!
1810 - Field Period Assembly plus 1859 unplanned work |  |  | Larry | 1810-Field Period Assy -Station 1 2 3 VIOLA | 693.632 | (1) | 1266 | 2353 | 1961 | 165 | 0 | 5745 | 6438.632 | 2203 | 4235.632 | 192.3% | 1810
|  |  | Larry | 1815 - Field Period Assy |  |  | 0 | 223 | 1017 | 94 | 0 | 1334 | 1334 |  | 1334 | #DIV/0!
|  |  |  | Subtotal | 3479.245 |  | 1742 | 4064 | 3951 | 347 | 0 | 10104 | 13583.245 | 5430 | 8153.245 | 150.2%
[15 empty] | 0 | #DIV/0!
1901 - Stellarator Core Mngt & Integr |  | 19 - Stellarator Core Management and Integration | Phil | 1901 - Stellarator Core Mngtt&Integr-COLE | 2128.2 |  | 162 | 408 | 432 | 448 | 170 | 1620 | 3748.2 | 2752 | 996.2 | 36.2% | 1901
|  |  |  | SUB TOTAL WBS 1 | 53551.035 |  | 4893 | 11072 | 6577 | 1784 | 170 | 24496 | 78047.035 | 54507 | 23540.035 | 43.19%
[15 empty] | 0 | #DIV/0!
[15 empty] | 0 | #DIV/0!
2001-VPS Gas& Cond Sys Oversight |  | 21 - Fueling Systems | Larry | 2101 - Fueling Systems-BLAMCHARD | 62.893 |  | 0 | 0 | 13 | 56 | 0 | 69 | 131.893 | 151 | -19.107 | -12.65% | 2101
|  | 22 - Torus Vacuum Pumping Systems | Larry | 2201 - Vacuum Pumping Systems-BLANCHARD |  |  | 0 | 0 | 70 | 102 | 0 | 172 | 172 | 349 | -177 | -50.72% | 2201
|  | 25 Neutral Beam Refurbishment | Larry | 2501 - Neutral Beam Refurbishment | 284.946 |  | 0 | 0 | 0 | 0 | 0 | 0 | 284.946 | 284 | 0.946 | 0.3331% | 2501
|  |  |  | SUB TOTAL WBS 2 | 347.839 |  | 0 | 0 | 83 | 158 | 0 | 241 | 588.839 | 784 | -195.161 | -24.89%
[15 empty] | 0 | #DIV/0!
3101 Magnetic Diagnostics |  | 31 - Magnetic Diagnostics | Larry | 3101 - Magnetic Diagnostics-STRATTON | 611.4 | (1) | 184 | 107 | 0 | 0 | 0 | 291 | 902.4 | 426 | 476.4 | 111.8% | 3101
|  | 36 - Edge and Divertor Diagnostics | Larry | 3601 - Edge Divertor Diagnostics-STRATTON |  |  | 0 | 0 | 0 | 31 | 0 | 31 | 31 | 46 | -15 | -32.61% | 3601
|  | 38 - Electron Beam (EB) Mapping | Larry | 3801 - Electron Beam Mapping-STRATTON |  |  | 0 | 0 | 101 | 162 | 0 | 263 | 263 | 310 | -47 | -15.16% | 3801
3901 - Diagnostics sys Integration |  | 39 - Diagnostics Integration | Larry | 3901 - Diagnostics sys Integration-STRATTON | 342.506 |  | 11 | 29 | 30 | 62 | 0 | 132 | 474.506 | 361 | 113.506 | 31.44% | 3901
|  |  |  | SUB TOTAL WBS 3 | 953.906 |  | 195 | 136 | 131 | 255 | 0 | 717 | 1670.906 | 1143 | 527.906 | 46.19%
[15 empty] | 0 | #DIV/0!
4101 - AC Power |  | 41 - AC Power | Al | 4101 - AC Power-RAMAKRISHNAN | 107.351 |  | -104 | 0 | 57 | 102 | 0 | 55 | 162.351 | 430 | -267.649 | -62.24% | 4101
4301 - DC Systems |  | 43 - DC Systems | Al | 4301 - DC Systems-RAMAKRISHNAN | 369.4 |  | 0 | 11 | 274 | 318 | 0 | 603 | 972.4 | 454 | 518.4 | 114.2% | 4301
4401 - Control & Protection |  | 44 - Control and protection Systems | Al | 4401 - Control & Protection-RAMAKRISHNAN | 80.521 |  | 0 | 0 | 314 | 770 | 0 | 1084 | 1164.521 | 1309 | -144.479 | -11.04% | 4401
4501 - Power Sys Dsn & Integr |  | 45 - Power System Design and Integration | Al | 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 161.056 |  | 0 | 0 | 356 | 274 | 53 | 683 | 844.056 | 1107 | -262.944 | -23.75% | 4501
|  | 46 FCPC Bldg Mods | Al | 4601 - FCPC Bldg Mods | 1.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1 | 0.3 | 30% | 4601
|  |  |  | SUB TOTAL WBS 4 | 719.628 |  | -104 | 11 | 1001 | 1464 | 53 | 2425 | 3144.628 | 3301 | -156.372 | -4.737%
[15 empty] | 0 | #DIV/0!
|  | 51 - Network and Fiber Infrastructure | Al | 5101 - Network and Fiber |  |  | 0 | 0 | 7 | 143 | 0 | 150 | 150 |  | 150 | #DIV/0!
|  | 52 - Central Instrumentation & Control | Al | 5201 - I&C Systems-SICHTA |  |  | 0 | 0 | 81 | 115 | 0 | 196 | 196 | 611 | -415 | -67.92% | 5201
|  | 53 - Data Acquisition & Facility Computing | Al | 5301 - Data Acquisition-SICHTA |  |  | 0 | 0 | 51 | 114 | 0 | 165 | 165 | 351 | -186 | -52.99% | 5301
|  | 54 - Facility Timing & Synchronization | Al | 5401 - Facility Timing & |  |  | 0 | 0 | 12 | 193 | 0 | 205 | 205 | 221 | -16 | -7.24% | 5401
|  | 55 - Real Time Plasma & Power Supply Control Sys | Al | 5501 - Real Time Control |  |  | 0 | 0 | 17 | 112 | 0 | 129 | 129 | 162 | -33 | -20.37% | 5501
|  | 56 - Central Safety and Interlock Systems | Al | 5601 - Central Safety &Interlock Sys-SICHTA |  |  | 0 | 0 | 12 | 210 | 0 | 222 | 222 | 382 | -160 | -41.88% | 5601
5801 -Central I&C Integr |  | 58 - Central I&C management and Integration | Al | 5801 - Central I&C Integr& Oversight-SICHTA | 33.022 |  | 7 | 24 | 19 | 19 | 0 | 69 | 102.022 | 323 | -220.978 | -68.41% | 5801
|  |  |  | SUB TOTAL WBS 5 | 33.022 |  | 7 | 24 | 199 | 906 | 0 | 1136 | 1169.022 | 2050 | -880.978 | -42.97% |  | 2373
[15 empty] | 0 | #DIV/0!
|  | 61 - Water Systems | Larry | 6163 - Facility Systems Support FY04 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0% | 6163
|  |  | Larry | 6101 - Water Systems-DUDEK |  |  | 0 | 0 | 46 | 0 | 0 | 46 | 46 | 95 | -49 | -51.58% | 6101
|  | 62 - Cryogenic Systems | Larry | 6201 - Cryogenic Systems-DUDEK |  |  | 0 | 0 | 271 | 384 | 0 | 655 | 655 | 463 | 192 | 41.47% | 6201
|  | 63 - Utility Systems | Larry | 6301 - Utility Systems-DUDEK |  |  | 0 | 0 | 105 | 0 | 0 | 105 | 105 | 109 | -4 | -3.67% | 6301
|  | 64 - PFC/VV Heating & Cooling (Bakeout) | Larry | 6401 - PFC/VV Htng/Cooling(bakeout)- DUDEK |  |  | 0 | 0 | 107 | 466 | 0 | 573 | 573 |  | 573 | #DIV/0!
|  |  |  | SUB TOTAL WBS 6 | 24 |  | 0 | 0 | 529 | 850 | 0 | 1379 | 1403 | 691 | 712 | 103%
[15 empty] | 0 | #DIV/0!
|  | 71 Shield Wall | Larry | 7101 - Shield Wall Modif | 32.605 |  | 0 | 0 | 0 | 0 | 0 | 0 | 32.605 | 80 | -47.395 | -59.24% | 7101
7301 - Platform Design & |  | 73 - Platform Design & Fabrication | Larry | 7301 - Platform Design & | 75.836 |  | 2 | 5 | 197 | 0 | 0 | 204 | 279.836 | 164 | 115.836 | 70.63% | 7301
7401 - TC Prep & Mach Assy Planning |  | 74 - Machine Assembly Planning and Oversight | Larry | 7401 - TC Prep & Mach Assy Planning-PERRY | 854.9 |  | -308 | 23 | 615 | 857 | 230 | 1417 | 2271.9 | 1565 | 706.9 | 45.17% | 7401
|  | 75 - Test Cell and Basement Assembly Operations | Larry | 7501 - Construction Support Crew-PERRY |  |  | 0 | 0 | 336 | 806 | 265 | 1407 | 1407 | 1111 | 296 | 26.64% | 7501
|  | 75 - Test Cell and Basement Assembly Operations | Larry | 7503 - Machine Assembly (station 6)-PERRY |  |  | 0 | 0 | 1668 | 2205 | 638 | 4511 | 4511 | 1254 | 3257 | 259.7% | 7503
|  | 76 - Tooling Design & Fabrication | Larry | 7601 - Tooling Design & Fabrication-PERRY |  |  | 0 | 0 | 207 | 205 | 0 | 412 | 412 | 238 | 174 | 73.11% | 7601
|  |  |  | SUB TOTAL WBS 7 | 963.341 |  | -306 | 28 | 3023 | 4073 | 1133 | 7951 | 8914.341 | 4412 | 4502.341 | 102%
[15 empty] | 0 | #DIV/0!
8101 - Project Management & Control |  | 81 - Project Management and Control | Jim | 8101 - Project Management & Control-NEILSON | 2822.4 | (1) | 278 | 1034 | 1158 | 1074 | 299 | 3843 | 6665.4 | 4197 | 2468.4 | 58.81% | 8101
8102 - NCSX MIE Management ORNL |  |  | Jim | 8102 - NCSX MIE Management ORNL-LYON | 553.747 |  | 60 | 159 | 159 | 102 | 19 | 499 | 1052.747 | 387 | 665.747 | 172% | 8102
8202 - Engr Mgmt & Sys Eng Support |  | 82 - Project Engineering | Phil | 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2646.4 | (1) | 476 | 665 | 663 | 660 | 185 | 2649 | 5295.4 | 2835 | 2460.4 | 86.79% | 8202
8203 - Design Integration |  |  | Phil | 8203 - Design Integration-BROWN | 985.511 | (1) | 160 | 377 | 376 | 374 | 121 | 1408 | 2393.511 | 1116 | 1277.511 | 114.5% | 8203
8204 - Systems Analysis |  |  | Phil | 8204 - Systems Analysis-BROOKS | 1276.406 | (1) | 181 | 295 | 293 | 292 | 93 | 1154 | 2430.406 | 601 | 1829.406 | 304.4% | 8204
8205 - Dimensional Control Coord. |  |  | Phil | 8205 - Dimensional Control Coordin-REIERSEN | 301.9 |  | 102 | 266 | 162 | 56 | 12 | 598 | 899.9 | 332 | 567.9 | 171.1% | 8205
8210 - Project Rebaseline Estimating |  |  | Phil | 8210 - FY07 Rebaseling tasks | 37.646 |  | 19 | 0 | 0 | 0 | 0 | 19 | 56.646 |  | 56.646 | #DIV/0!
|  |  | Phil | 8215 Plant Design |  |  | 15 | 32 | 32 | 32 | 10 | 121 | 121 |  | 121 | #DIV/0!
|  |  | Jim | 8998 - Allocations-STRYKOWSKY | 1415.99 | (1) | 144 | 384 | 406 | 431 | 88 | 1453 | 2868.99 | 1577 | 1291.99 | 81.93% | 8998
|  | 84 Project Physics | Jim | 8401 - Project Physics | 323.9 | [6 empty] | 0 | 323.9 | 324 | -0.1 | -0.03086% | 8401
|  |  | Jim | 8402 - Project Physics MIE ORNL | 146.467 | [6 empty] | 0 | 146.467 | 146 | 0.467 | 0.3199% | 8402
|  | 85 - Integrated Systems Testing | Al | 8501 - Integrated Systems Testing-GENTILE |  |  | 0 | 0 | 276 | 70 | 419 | 765 | 765 | 1189 | -424 | -35.66% | 8501
8998 - Allocations |  |  |  | SUB TOTAL WBS 8 | 10510.367 |  | 1435 | 3212 | 3525 | 3091 | 1246 | 12509 | 23019.367 | 12704 | 10315.367 | 81.2%
|  |  |  | TOTAL | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138 | 48.2%
|  |  |  | DCMA | 75 | [7 empty] | 75
|  | CC - Contingency |  | Contingency-Project |  |  | 144 | 2205 | 3492 | 4450 | 4089 | 14380 | 14380 | 12804
|  |  |  | TOTAL | 67178.138 |  | 6264 | 16688 | 18560 | 17031 | 6691 | 65234 | 132412.138 | 92401
|  |  |  | (1) ADJUSTED FOR PLANNED RETROACTIVE G&A rate reduction in FY07 (estimated) | [10 empty] | 30463.293 |  | 79.4%
|  |  | Jim |  | 5262.504 |  | 482 | 1577 | 1723 | 1607 | 406 | 5795 | 11057.504 | 6631 | 4426.504
|  |  | Larry |  | 20428.331 |  | 2748 | 6786 | 7718 | 5881 | 1133 | 24266 | 44694.331 | 25685 | 19009.331
|  |  | Phil |  | 40659.653 |  | 2987 | 6085 | 4151 | 2653 | 591 | 16467 | 57126.653 | 40736 | 16390.653
|  |  | AL |  | 752.65 |  | -97 | 35 | 1476 | 2440 | 472 | 4326 | 5078.65 | 6540 | -1461.35
[5 empty] | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138