## P3
RES | JJJJ | man months | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09 | OCT FY10 | NOV FY10 | DEC FY10
EA//EM - PPPL Analysis engineer | 1353 - Job: 1353 - CS Structure Procurement-DAHLGREN | 0.55556 | [12 empty] | 80
EA//EM - PPPL Analysis engineer | 1701 - Job: 1701 - Cryostat Design-GETTLEFINGER | 1.3889 | [8 empty] | 5 | 102 | 93
EA//EM - PPPL Analysis engineer | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 1.1111 | [9 empty] | 48 | 112
EA//EM - PPPL Analysis engineer | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 3.8958 | [10 empty] | 38 | 40 | 82 | 91 | 112 | 91 | 84 | 23
6.9514
EA//SB - PPPL Designer | 1353 - Job: 1353 - CS Structure Procurement-DAHLGREN | 0.69444 | [10 empty] | 30 | 67 | 3
EA//SB - PPPL Designer | 1701 - Job: 1701 - Cryostat Design-GETTLEFINGER | 5.5833 | [7 empty] | 46 | 115 | 126 | 121 | 115 | 126 | 126 | 29
EA//SB - PPPL Designer | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | 1.6389 | [9 empty] | 12 | 12 | 101 | 111
EA//SB - PPPL Designer | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 3.5486 |  |  |  |  | 68 | 53 | 50 | 106 | 114 | 120
EA//SB - PPPL Designer | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 5.0972 |  |  |  |  | 50 | 82 | 73 | 62 | 59 | 65 | 65 | 59 | 75 | 79 | 37 | 27 | 1
EA//SB - PPPL Designer | 6101 - Job: 6101 - Water Systems-DUDEK | 0.83333 |  |  |  |  | 120
EA//SB - PPPL Designer | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 2.2986 |  |  |  |  | 54 | 46 |  | 107 | 67 | 27 |  | 30
EA//SB - PPPL Designer | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 1.6667 | [12 empty] | 63 | 57 |  | 42 | 66 | 12
21.3611
EE//EM - PPPL Electrical engineer | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0.22222 | [7 empty] | 9 | 11 | 12
EE//EM - PPPL Electrical engineer | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 4.8333 |  |  |  |  | 85 | 72 | 64 | 56 | 53 | 58 | 58 | 53 | 63 | 69 | 37 | 27 | 1
EE//EM - PPPL Electrical engineer | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 1.1111 | [7 empty] | 107 | 53
6.1667
EM//EM - PPPL FO&M Engineer | 1701 - Job: 1701 - Cryostat Design-GETTLEFINGER | 2.7708 |  |  |  |  | 34 | 27 | 25 | 27 | 41 | 45 | 51 | 41 | 45 | 45 | 18
EM//EM - PPPL FO&M Engineer | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | 0.94444 | [9 empty] | 24 | 24 | 42 | 46
EM//EM - PPPL FO&M Engineer | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 2.7778 |  |  |  |  | 68 | 53 | 50 | 73 | 76 | 80
EM//EM - PPPL FO&M Engineer | 6101 - Job: 6101 - Water Systems-DUDEK | 0.41667 |  |  |  |  | 60
EM//EM - PPPL FO&M Engineer | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 3.5556 |  |  |  |  | 101 | 75 |  | 107 | 80 | 53 | 8 | 80 |  |  | 8
10.4653
ORNLEM - ORNL Engineer | 1260 - Job: 1260 - NBI port duct extensions-GORANSON | 2.7847 |  |  |  |  | 142 | 111 | 105 | 43
ORNLEM - ORNL Engineer | 1601 - Job: 1601 - Coil Services Design-GORANSON | 14.3542 | 124 | 130 | 124 | 124 | 214 | 167 | 158 | 150 | 118 | 130 | 130 | 118 | 130 | 130 | 120
17.1389