## FY08
BCWS Monthly
|  | ACWP | BTC | BCWS May 1,2007 - Sep 30,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08
11056.424 | Jim Anderson | 5262.504 | 5793.92 | 948.8 | 104 | 95 | 95 | 103 | 86 | 126 | 110.5 | 85 | 144.3 | 136.92 | 136.92 | 144.3 | 136.92 | 136.92 | 144.3 | 136.92 | 135.92
45121.891 | Larry Dudek | 20428.331 | 24693.56 | 5883.45 | 196.57 | 494.19 | 847.97 | 726.4 | 547.77 | 1204.61 | 641.77 | 490.99 | 733.18 | 615.01 | 599.26 | 565.74 | 520.27 | 441.47 | 567.25 | 382.9 | 368.82
58190.153 | Phil Heitzeroeder | 40659.653 | 17530.5 | 4451.5 | 423.8 | 618 | 608 | 497 | 433 | 608 | 413.6 | 344.9 | 505.2 | 417.8 | 461.8 | 418.7 | 375.5 | 644.8 | 856.7 | 999.1 | 943.7
5082.85 | Al vonHalle | 752.65 | 4330.2 | -85.8 | -102.8 | 1.2 | 1.3 | 2 | 1.3 | 3.1 | 3.1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Total BCWS | 67103.138 | 52348.18 | 11197.95 | 621.57 | 1208.39 | 1552.27 | 1328.4 | 1068.07 | 1941.71 | 1168.97 | 922.89 | 1385.68
|  |  | 119451.318 | 11197.95
|  | Jim Anderson |  | BCWS | 104 | 199 | 294 | 397 | 0 | 126 | 236.5 | 321.5 | 465.8 | 602.72 | 739.64 | 883.94 | 1020.86 | 1157.78 | 1302.08 | 1439 | 1574.92
|  |  |  | BCWP | 102 | 199 | 294 | 396.9789 | 0 | 145.138 | 272.367 | 318.2324 | 447.74
|  |  |  | ACWP | 111.7184 | 218.6445 | 309.5976 | 416.8916 | 0 | 96.262 | 239.355 | 335.75 | 427.744
|  |  |  | CPI | 0.91301 | 0.91015 | 0.94962 | 0.95224 | #DIV/0! | 1.5077 | 1.1379 | 0.94783 | 1.0467
|  |  |  | SPI | 0.98077 | 1 | 1 | 0.99995 | #DIV/0! | 1.1519 | 1.1517 | 0.98984 | 0.96123
|  | Larry Dudek |  | BCWS | 196.57 | 690.76 | 1538.73 | 2265.13 | 0 | 1204.61 | 1846.38 | 2337.37 | 3070.55 | 3685.56 | 4284.82 | 4850.56 | 5370.83 | 5812.3 | 6379.55 | 6762.45 | 7131.27
|  |  |  | BCWP | 122 | 778 | 1447 | 2191.7652 | 0 | 894.3855 | 1433.5786 | 1892.7934 | 2330.4895
|  |  |  | ACWP | 305.793 | 823.5043 | 1302.9008 | 2004.9938 | 0 | 426.885 | 998.801 | 1487.453 | 1985.856
|  |  |  | CPI | 0.39896 | 0.94474 | 1.1106 | 1.0932 | #DIV/0! | 2.0951 | 1.4353 | 1.2725 | 1.1735
|  |  |  | SPI | 0.62064 | 1.1263 | 0.94039 | 0.96761 | #DIV/0! | 0.74247 | 0.77643 | 0.8098 | 0.75898
|  | Phil Heitzeroeder |  | BCWS | 423.8 | 1041.8 | 1649.8 | 2146.8 | 0 | 608 | 1021.6 | 1366.5 | 1871.7 | 2289.5 | 2751.3 | 3170 | 3545.5 | 4190.3 | 5047 | 6046.1 | 6989.8
|  |  |  | BCWP | 300 | 817 | 1546 | 1938.6461 | 0 | 453.4431 | 822.6718 | 1241.7096 | 1727.39
|  |  |  | ACWP | 317.203 | 705.0554 | 1005.8607 | 1659.2607 | 0 | 348.902 | 720.505 | 1147.086 | 1496.555
|  |  |  | CPI | 0.94577 | 1.1588 | 1.537 | 1.1684 | #DIV/0! | 1.2996 | 1.1418 | 1.0825 | 1.1542
|  |  |  | SPI | 0.70788 | 0.78422 | 0.93708 | 0.90304 | #DIV/0! | 0.74579 | 0.80528 | 0.90868 | 0.9229
|  | Al vonHalle |  | BCWS | -102.8 | -101.6 | -100.3 | -98.3 | 0 | 3.1 | 6.2 | 8.2 | 11.2 | 14.2 | 17.2 | 20.2 | 23.2 | 26.2 | 29.2 | 32.2 | 35.2
|  |  |  | BCWP | -103 | -102 | -101 | -98.3768 | 0 | 2.32 | 6.0957 | 8.1979 | 11.29
|  |  |  | ACWP | -104.2596 | -104.2596 | -104.3015 | -104.3015 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | 0.98792 | 0.97833 | 0.96835 | 0.9432 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI | 1.0019 | 1.0039 | 1.007 | 1.0008 | #DIV/0! | 0.74839 | 0.98318 | 0.99974 | 1.008
[10 empty] | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08
|  | TOTAL PROJECT |  | BCWS | 621.57 | 1829.96 | 3382.23 | 4710.63 | BCWS | 1941.71 | 3110.68 | 4033.57 | 5419.25 | 6591.98 | 7792.96 | 8924.7 | 9960.39 | 11186.58 | 12757.83 | 14279.75 | 15731.19
|  |  |  | BCWP | 421 | 1692 | 3186 | 4429.0134 | BCWP | 1495.2866 | 2534.7131 | 3460.9333 | 4516.9095
|  |  |  | ACWP | 630.4547 | 1642.9445 | 2514.0576 | 3976.8446 | ACWP | 872.049 | 1958.661 | 2970.289 | 3910.155 | 5627.155 | 7177.155 | 8581.155 | 10034.155 | 11568.155 | 13161.155 | 14709.155 | 16399.155
|  |  |  | CPI | 0.66777 | 1.0299 | 1.2673 | 1.1137 | #VALUE! | 1.7147 | 1.2941 | 1.1652 | 1.1552
|  |  |  | SPI | 0.67732 | 0.92461 | 0.94198 | 0.94022 | #VALUE! | 0.77009 | 0.81484 | 0.85803 | 0.83349
[13 empty] | forecast | 1717 | 1550 | 1404 | 1453 | 1534 | 1593 | 1548 | 1690
Forecast (schedule forecast plus partial ETC's)

## Summary
BCWS Monthly
|  | ACWP | BTC | BCWS May 1,2007 - Sep 30,2007 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12
11056.424 | Jim Anderson | 5262.504 | 5793.92 | 948.8 | 104 | 95 | 95 | 103 | 86 | 126 | 110.5 | 85 | 144.3 | 136.92 | 136.92 | 144.3 | 136.92 | 136.92 | 144.3 | 136.92 | 135.92 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45121.891 | Larry Dudek | 20428.331 | 24693.56 | 5883.45 | 196.57 | 494.19 | 847.97 | 726.4 | 547.77 | 1204.61 | 641.77 | 490.99 | 733.18 | 615.01 | 599.26 | 565.74 | 520.27 | 441.47 | 567.25 | 382.9 | 368.82 | 467.28 | 499.05 | 700.13 | 870.14 | 709.69 | 742.23 | 653.24 | 657.74 | 669.4 | 589.32 | 545.17 | 610.17 | 830.32 | 573.51 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58190.153 | Phil Heitzeroeder | 40659.653 | 17530.5 | 4451.5 | 423.8 | 618 | 608 | 497 | 433 | 608 | 413.6 | 344.9 | 505.2 | 417.8 | 461.8 | 418.7 | 375.5 | 644.8 | 856.7 | 999.1 | 943.7 | 810.4 | 517 | 369.6 | 442.4 | 422.3 | 412.7 | 404.6 | 301.5 | 362.7 | 283.7 | 192 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5082.85 | Al vonHalle | 752.65 | 4330.2 | -85.8 | -102.8 | 1.2 | 1.3 | 2 | 1.3 | 3.1 | 3.1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total BCWS | 67103.138 | 52348.18 | 11197.95 | 621.57 | 1208.39 | 1552.27 | 1328.4 | 1068.07 | 1941.71 | 1168.97 | 922.89 | 1385.68
|  |  | 119451.318 | 11197.95
|  | Jim Anderson |  | BCWS | 104 | 199 | 294 | 397 | 483 | 609 | 719.5 | 804.5 | 948.8 | 1085.72 | 1222.64 | 1366.94 | 1503.86 | 1640.78 | 1785.08 | 1922 | 2057.92 | 2216.92 | 2342.92 | 2460.92 | 2606.92 | 2745.92 | 2897.92 | 3049.92 | 3188.92 | 3340.92 | 3492.92 | 3638.92 | 3780.92 | 3922.92 | 4045.92 | 4149.92 | 4279.92 | 4409.92 | 4558.92 | 4700.92 | 4830.92 | 4972.92 | 5108.92 | 5250.92 | 5386.92 | 5494.92 | 5597.92 | 5684.92 | 5792.92 | 5793.92
|  |  |  | BCWP | 102 | 199 | 294 | 396.9789 | 482.56 | 627.698 | 754.927 | 800.7924 | 930.3
|  |  |  | ACWP | 111.7184 | 218.6445 | 309.5976 | 416.8916 | 597.4836 | 693.7456 | 836.8386 | 933.2336 | 1025.2276
|  |  |  | CPI | 0.91301 | 0.91015 | 0.94962 | 0.95224 | 0.80765 | 0.9048 | 0.90212 | 0.85808 | 0.90741
|  |  |  | SPI | 0.98077 | 1 | 1 | 0.99995 | 0.99909 | 1.0307 | 1.0492 | 0.99539 | 0.9805
|  | Larry Dudek |  | BCWS | 196.57 | 690.76 | 1538.73 | 2265.13 | 2812.9 | 4017.51 | 4659.28 | 5150.27 | 5883.45 | 6498.46 | 7097.72 | 7663.46 | 8183.73 | 8625.2 | 9192.45 | 9575.35 | 9944.17 | 10411.45 | 10910.5 | 11610.63 | 12480.77 | 13190.46 | 13932.69 | 14585.93 | 15243.67 | 15913.07 | 16502.39 | 17047.56 | 17657.73 | 18488.05 | 19061.56 | 19478.56 | 20022.56 | 20411.56 | 20973.56 | 21592.56 | 22074.56 | 22502.56 | 22860.56 | 23235.56 | 23559.56 | 23969.56 | 24344.56 | 24662.56 | 24693.56
|  |  |  | BCWP | 122 | 778 | 1447 | 2191.7652 | 2900.1205 | 3794.506 | 4333.6991 | 4792.9139 | 5230.61
|  |  |  | ACWP | 305.793 | 823.5043 | 1302.9008 | 2004.9938 | 2727.8868 | 3154.7718 | 3726.6878 | 4215.3398 | 4713.7428
|  |  |  | CPI | 0.39896 | 0.94474 | 1.1106 | 1.0932 | 1.0631 | 1.2028 | 1.1629 | 1.137 | 1.1097
|  |  |  | SPI | 0.62064 | 1.1263 | 0.94039 | 0.96761 | 1.031 | 0.94449 | 0.93012 | 0.93061 | 0.88904
|  | Phil Heitzeroeder |  | BCWS | 423.8 | 1041.8 | 1649.8 | 2146.8 | 2579.8 | 3187.8 | 3601.4 | 3946.3 | 4451.5 | 4869.3 | 5331.1 | 5749.8 | 6125.3 | 6770.1 | 7626.8 | 8625.9 | 9569.6 | 10380 | 10897 | 11266.6 | 11709 | 12131.3 | 12544 | 12948.6 | 13250.1 | 13612.8 | 13896.5 | 14088.5 | 14297.5 | 14635.5 | 14930.5 | 15181.5 | 15464.5 | 15702.5 | 15950.5 | 16143.5 | 16293.5 | 16458.5 | 16616.5 | 16781.5 | 16939.5 | 17096.5 | 17246.5 | 17373.5 | 17526.5 | 17530.5
|  |  |  | BCWP | 300 | 817 | 1546 | 1938.6461 | 2268.7 | 2722.1431 | 3091.3718 | 3510.4096 | 3996.09
|  |  |  | ACWP | 317.203 | 705.0554 | 1005.8607 | 1659.2607 | 2055.8407 | 2404.7427 | 2776.3457 | 3202.9267 | 3552.3957
|  |  |  | CPI | 0.94577 | 1.1588 | 1.537 | 1.1684 | 1.1035 | 1.132 | 1.1135 | 1.096 | 1.1249
|  |  |  | SPI | 0.70788 | 0.78422 | 0.93708 | 0.90304 | 0.87941 | 0.85393 | 0.85838 | 0.88954 | 0.8977
|  | Al vonHalle |  | BCWS | -102.8 | -101.6 | -100.3 | -98.3 | -97 | -93.9 | -90.8 | -88.8 | -85.8 | -82.8 | -79.8 | -76.8 | -73.8 | -70.8 | -67.8 | -64.8 | -61.8 | -0.8 | 76.2 | 170.2 | 284.2 | 366.2 | 472.2 | 576.2 | 672.2 | 792.2 | 965.2 | 1228.2 | 1415.2 | 1657.2 | 1918.2 | 2144.2 | 2394.2 | 2666.2 | 3014.2 | 3267.2 | 3464.2 | 3632.2 | 3744.2 | 3799.2 | 3858.2 | 4027.2 | 4137.2 | 4231.2 | 4330.2
|  |  |  | BCWP | -103 | -102 | -101 | -98.3768 | -97.12 | -94.8 | -91.0243 | -88.9221 | -85.83
|  |  |  | ACWP | -104.2596 | -104.2596 | -104.3015 | -104.3015 | -104.6585 | -104.6585 | -104.6585 | -104.6585 | -104.6585
|  |  |  | CPI | 0.98792 | 0.97833 | 0.96835 | 0.9432 | 0.92797 | 0.9058 | 0.86973 | 0.84964 | 0.8201
|  |  |  | SPI | 1.0019 | 1.0039 | 1.007 | 1.0008 | 1.0012 | 1.0096 | 1.0025 | 1.0014 | 1.0003
|  | TOTAL PROJECT |  | BCWS | 621.57 | 1829.96 | 3382.23 | 4710.63 | 5778.7 | 7720.41 | 8889.38 | 9812.27 | 11197.95 | 12370.68 | 13571.66 | 14703.4 | 15739.09 | 16965.28 | 18536.53 | 20058.45 | 21509.89 | 23007.57 | 24226.62 | 25508.35 | 27080.89 | 28433.88 | 29846.81 | 31160.65 | 32354.89 | 33658.99 | 34857.01 | 36003.18 | 37151.35 | 38703.67 | 39956.18 | 40954.18 | 42161.18 | 43190.18 | 44497.18 | 45704.18 | 46663.18 | 47566.18 | 48330.18 | 49067.18 | 49744.18 | 50588.18 | 51326.18 | 51952.18 | 52343.18 | 23324.42 | 0
|  |  |  | BCWP | 421 | 1692 | 3186 | 4429.0134 | 5554.2605 | 7049.5471 | 8088.9736 | 9015.1938 | 10071.17
|  |  |  | ACWP | 630.4547 | 1642.9445 | 2514.0576 | 3976.8446 | 5276.5526 | 6148.6016 | 7235.2136 | 8246.8416 | 9186.7076
|  |  |  | CPI | 0.66777 | 1.0299 | 1.2673 | 1.1137 | 1.0526 | 1.1465 | 1.118 | 1.0932 | 1.0963
|  |  |  | SPI | 0.67732 | 0.92461 | 0.94198 | 0.94022 | 0.96116 | 0.91311 | 0.90996 | 0.91877 | 0.89938
|  | Mod Coil Design |  | BCWS | 219 | 518 | 827 | 1070 | 1184 | 1418 | 1500 | 1538 | 1580 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606 | 1606
|  | 1416/1421/1429 |  | BCWP | 96 | 292 | 797 | 897.5716 | 918.5 | 1122.391 | 1224.7874 | 1332.7488 | 1375.77
|  |  |  | ACWP | 123.9413 | 257.935 | 406.7498 | 700.8288 | 828.5818 | 943.1298 | 1073.1128 | 1227.9788 | 1333.9848
|  |  |  | CPI | 0.77456 | 1.1321 | 1.9594 | 1.2807 | 1.1085 | 1.1901 | 1.1413 | 1.0853 | 1.0313
|  |  |  | SPI | 0.43836 | 0.56371 | 0.96372 | 0.83885 | 0.77576 | 0.79153 | 0.81652 | 0.86655 | 0.87074
|  | Field Period Assy |  | BCWS | 254.37 | 497.46 | 838.33 | 1170.53 | 1417.1 | 1754.71 | 1998.28 | 2223.27 | 2531.45 | 2783.46 | 3079.72 | 3346.46 | 3596.73 | 3831.2 | 4258.45 | 4570.35 | 4851.17 | 5164.45 | 5448.5 | 5663.63 | 5966.77 | 6353.46 | 6781.69 | 7133.93 | 7480.67 | 7795.07 | 8142.39 | 8432.56 | 8725.73 | 8964.05 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56 | 9073.56
|  | 1802/1810/1815 |  | BCWP | 254 | 494 | 808 | 1064.6539 | 1359.15 | 1600.257 | 1777.2997 | 1926.6437 | 2098.58
|  |  |  | ACWP | 191.2809 | 363.5801 | 571.3968 | 851.3268 | 1075.1188 | 1226.7268 | 1443.2528 | 1622.8288 | 1781.5708
|  |  |  | CPI | 1.3279 | 1.3587 | 1.4141 | 1.2506 | 1.2642 | 1.3045 | 1.2315 | 1.1872 | 1.1779
|  |  |  | SPI | 0.99855 | 0.99304 | 0.96382 | 0.90955 | 0.95911 | 0.91198 | 0.88941 | 0.86658 | 0.829
|  | Mod Coil Winding Ops |  | BCWS | 237 | 408 | 639 | 821 | 957 | 1170 | 1358 | 1491 | 1713 | 1924 | 2107 | 2316 | 2509 | 2665 | 2752 | 2768 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769 | 2769
|  | 1451 |  | BCWP | 236 | 412 | 711 | 946.222 | 1184 | 1439.27 | 1546.0835 | 1710.7585 | 1916.44
|  |  |  | ACWP | 283.7075 | 502.5031 | 659.7907 | 900.0867 | 1090.4237 | 1245.0187 | 1436.4037 | 1596.1007 | 1694.4647
|  |  |  | CPI | 0.83184 | 0.8199 | 1.0776 | 1.0513 | 1.0858 | 1.156 | 1.0764 | 1.0718 | 1.131
|  |  |  | SPI | 0.99578 | 1.0098 | 1.1127 | 1.1525 | 1.2372 | 1.2301 | 1.1385 | 1.1474 | 1.1188
|  | Mod Coil Winding Ops Punch list |  | BCWS | 0 | 4 | 23 | 43 | 90 | 147 | 190 | 216 | 258 | 301 | 343 | 369 | 393 | 418 | 444 | 477 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501 | 501
|  | 1459 |  | BCWP | 0 | 18 | 32 | 44.1632 | 135.3 | 168.318 | 282.9757 | 304.8447 | 305.07
|  |  |  | ACWP | 42.2044 | 97.4829 | 149.185 | 213.991 | 289.453 | 339.23 | 370.053 | 392.805 | 427.645
|  |  |  | CPI | 0 | 0.18465 | 0.2145 | 0.20638 | 0.46743 | 0.49618 | 0.76469 | 0.77607 | 0.71337
|  |  |  | SPI |  | 4.5 | 1.3913 | 1.0271 | 1.5033 | 1.145 | 1.4893 | 1.4113 | 1.1824
|  | Engr Mgmt & Sys Eng Sup |  | BCWS | 82 | 158 | 221 | 290 | 343 | 404 | 457 | 497 | 556 | 612 | 668 | 727 | 783 | 839 | 898 | 954 | 1010 | 1071 | 1119 | 1164 | 1220 | 1273 | 1332 | 1391 | 1444 | 1503 | 1562 | 1618 | 1674 | 1733 | 1784 | 1827 | 1880 | 1933 | 1994 | 2053 | 2106 | 2165 | 2221 | 2280 | 2336 | 2384 | 2430 | 2469 | 2517 | 2519
|  | 8202 |  | BCWP | 108 | 208 | 295 | 289.203 | 342.46 | 403.1 | 456.8854 | 496.5652 | 554.64
|  |  |  | ACWP | 59.5964 | 118.2282 | 176.8311 | 264.2051 | 318.4291 | 373.1311 | 428.2571 | 491.1501 | 537.4581
|  |  |  | CPI | 1.8122 | 1.7593 | 1.6683 | 1.0946 | 1.0755 | 1.0803 | 1.0668 | 1.011 | 1.032
|  |  |  | SPI | 1.3171 | 1.3165 | 1.3348 | 0.99725 | 0.99843 | 0.99777 | 0.99975 | 0.99913 | 0.99755
|  | Design Integration |  | BCWS | 33 | 65 | 97 | 132 | 161 | 196 | 226 | 249 | 282 | 314 | 346 | 379 | 411 | 443 | 476 | 508 | 540 | 575 | 602 | 628 | 660 | 690 | 723 | 756 | 786 | 819 | 852 | 884 | 916 | 949 | 978 | 1002 | 1032 | 1062 | 1097 | 1130 | 1160 | 1193 | 1225 | 1258 | 1290 | 1322 | 1352 | 1378 | 1410 | 1412
|  | 8203 |  | BCWP | 31 | 60 | 89 | 130.9084 | 160.47 | 194.2511 | 225.2187 | 247.7406 | 280.12
|  |  |  | ACWP | 5.0798 | 10.3179 | 11.959 | 22.052 | 36.561 | 55.866 | 75.916 | 97.846 | 114.137
|  |  |  | CPI | 6.1027 | 5.8151 | 7.4421 | 5.9363 | 4.3891 | 3.4771 | 2.9667 | 2.5319 | 2.4542
|  |  |  | SPI | 0.93939 | 0.92308 | 0.91753 | 0.99173 | 0.99671 | 0.99108 | 0.99654 | 0.99494 | 0.99333
|  | Systems Analysis |  | BCWS | 37 | 73 | 109 | 148 | 180 | 207 | 231 | 249 | 275 | 300 | 325 | 351 | 376 | 401 | 427 | 452 | 477 | 504 | 525 | 545 | 570 | 594 | 620 | 646 | 670 | 696 | 722 | 747 | 772 | 798 | 820 | 839 | 863 | 887 | 914 | 940 | 964 | 990 | 1015 | 1041 | 1066 | 1091 | 1115 | 1135 | 1160
|  | 8204 |  | BCWP | 35 | 69 | 103 | 147.9102 | 180.95 | 207.311 | 231.4724 | 249.0443 | 275.4
|  |  |  | ACWP | 42.5836 | 95.7359 | 142.8443 | 193.3133 | 225.4093 | 272.0633 | 319.3953 | 374.1473 | 408.8333
|  |  |  | CPI | 0.82191 | 0.72073 | 0.72106 | 0.76513 | 0.80276 | 0.762 | 0.72472 | 0.66563 | 0.67362
|  |  |  | SPI | 0.94595 | 0.94521 | 0.94495 | 0.99939 | 1.0053 | 1.0015 | 1.002 | 1.0002 | 1.0015
|  | Dimensional Cont Coordin |  | BCWS | 0 | 27 | 54 | 84 | 102 | 123 | 143 | 158 | 180 | 205 | 240 | 277 | 312 | 330 | 342 | 354 | 366 | 379 | 393 | 407 | 425 | 443 | 459 | 475 | 489 | 500 | 509 | 518 | 527 | 536 | 542 | 545 | 549 | 553 | 557 | 561 | 565 | 569 | 573 | 577 | 581 | 585 | 589 | 592
|  | 8205 |  | BCWP | 0 | 21 | 42 | 75.2674 | 76 | 87.581 | 100.769 | 102.4979 | 102.51
|  |  |  | ACWP | 17.5068 | 37.5899 | 60.0821 | 81.5541 | 92.0961 | 96.1341 | 113.3171 | 125.1151 | 133.7801
|  |  |  | CPI | 0 | 0.55866 | 0.69904 | 0.92291 | 0.82522 | 0.91103 | 0.88927 | 0.81923 | 0.76626
|  |  |  | SPI |  | 0.77778 | 0.77778 | 0.89604 | 0.7451 | 0.71204 | 0.70468 | 0.64872 | 0.5695
|  | Diagnostic |  | BCWS | 14.2 | 31.3 | 55.4 | 153.6 | 192.8 | 252.8 | 279 | 298 | 310 | 313 | 315 | 318 | 320 | 322 | 325 | 327 | 329 | 332 | 334 | 336 | 339 | 341 | 369 | 396 | 426 | 453 | 456 | 459 | 461 | 499 | 532 | 554 | 587 | 623 | 669 | 691 | 696 | 702 | 707 | 713 | 718
|  | 3101;3601;3801;3901 |  | BCWP | 14 | 58 | 114 | 148.2661 | 155.7805 | 160.581 | 209.0172 | 233.4096 | 147.9
|  |  |  | ACWP | 29.6873 | 49.7738 | 94.6838 | 129.3728 | 141.1718 | 145.5328 | 151.1708 | 166.3768 | 176.4648
|  |  |  | CPI | 0.47158 | 1.1653 | 1.204 | 1.146 | 1.1035 | 1.1034 | 1.3827 | 1.4029 | 0.83813
|  |  |  | SPI | 0.98592 | 1.853 | 2.0578 | 0.96527 | 0.80799 | 0.63521 | 0.74917 | 0.78325 | 0.4771
|  | PF Coil Des/Procurement |  | BCWS | 5 | 5 | 5 | 14 | 44 | 79 | 104 | 134 | 182 | 214 | 251 | 282 | 322 | 458 | 631 | 956 | 1226 | 1409 | 1510 | 1566 | 1629 | 1694 | 1758 | 1827 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1859 | 1861 | 1873 | 1887
|  | 1302;1352 |  | BCWP | 5 | 5 | 5 | 47.3325 | 60.35 | 61.085 | 61.5946 | 114.5733 | 180.73
|  |  |  | ACWP | 4.26 | 5.8007 | 7.206 | 13.784 | 44.385 | 47.602 | 55.349 | 69.447 | 84.865
|  |  |  | CPI | 1.1737 | 0.86197 | 0.69387 | 3.4339 | 1.3597 | 1.2832 | 1.1128 | 1.6498 | 2.1296
|  |  |  | SPI | 1 | 1 | 1 | 3.3809 | 1.3716 | 0.77323 | 0.59226 | 0.85502 | 0.99302
|  | TF Fabrication |  | BCWS | 8 | 73 | 133 | 168 | 228 | 289 | 348 | 404 | 463 | 521 | 625 | 682 | 739 | 795 | 898 | 952 | 1004 | 1004
|  | 1361 |  | BCWP | 4 | 49 | 108 | 199.4121 | 267.65 | 331.282 | 363.6 | 422.595 | 447.46
|  |  |  | ACWP | -6.0157 | 34.3792 | 88.8075 | 185.3505 | 271.3235 | 340.5435 | 385.1965 | 434.9965 | 471.5475
|  |  |  | CPI | -0.66492 | 1.4253 | 1.2161 | 1.0759 | 0.98646 | 0.9728 | 0.94393 | 0.97149 | 0.94892
|  |  |  | SPI |  | 0.67123 | 0.81203 | 1.187 | 1.1739 | 1.1463 | 1.0448 | 1.046 | 0.96644
|  | Mod Coil Type AB Fnl Dsn |  | BCWS | 219 | 518 | 827 | 1070 | 1184 | 1418 | 1500 | 1538 | 1580 | 1606
|  | 1416;1421;1429 |  | BCWP | 96 | 292 | 797 | 897.5716 | 918.5 | 1122.391 | 1224.7874 | 1332.7488 | 1375.77
|  |  |  | ACWP | 123.9413 | 257.935 | 406.7498 | 700.8288 | 828.5818 | 943.1298 | 1073.1128 | 1227.9788 | 1333.9848
|  |  |  | CPI | 0.77456 | 1.1321 | 1.9594 | 1.2807 | 1.1085 | 1.1901 | 1.1413 | 1.0853 | 1.0313
|  |  |  | SPI | 0.43836 | 0.56371 | 0.96372 | 0.83885 | 0.77576 | 0.79153 | 0.81652 | 0.86655 | 0.87074
|  | Coil Structure Dsn/Proc |  | BCWS | 7 | 38 | 70 | 128 | 164 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 186 | 218 | 327 | 458 | 589 | 732 | 825 | 876 | 939 | 999 | 1065 | 1131 | 1191 | 1257 | 1260
|  | 1501;1550 |  | BCWP | 2 | 45 | 75 | 81.9424 | 136.7 | 145.001 | 145.1989 | 148.2502 | 167.87
|  |  |  | ACWP | 54.1006 | 101.4754 | 138.5961 | 174.6521 | 176.9141 | 160.0001 | 183.0811 | 207.9981 | 209.5641
|  |  |  | CPI | 0.036968 | 0.44346 | 0.54114 | 0.46917 | 0.77269 | 0.90626 | 0.79309 | 0.71275 | 0.80104
|  |  |  | SPI | 0.28571 | 1.1842 | 1.0714 | 0.64017 | 0.83354 | 0.77958 | 0.78064 | 0.79704 | 0.90253
|  | Coil Service Design |  | BCWS | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 34 | 61 | 88 | 116 | 143 | 191 | 222 | 269 | 327 | 404 | 465 | 518 | 544 | 564 | 587 | 610 | 630 | 653 | 676 | 697 | 701 | 743 | 785 | 824 | 858 | 861
|  | 1601 |  | BCWP | 0 | 6 | 6 | 6.2288 | 14.6 | 14.598 | 22.9678
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | 1 | 1 | 1.0381 | 2.4333 | 2.433 | 3.828
|  |  | Stellarator Core Mngtt&Integr | BCWS | 34 | 66 | 98 | 133 | 162 | 200 | 233 | 258 | 294 | 328 | 362 | 398 | 432 | 466 | 502 | 536 | 569 | 609 | 640 | 670 | 707 | 742 | 780 | 818 | 853 | 891 | 929 | 966 | 999 | 1039 | 1073 | 1102 | 1138 | 1174 | 1216 | 1256 | 1292 | 1332 | 1370 | 1410 | 1448 | 1493 | 1536 | 1573 | 1618
|  |  | 1901 | BCWP | 34 | 66 | 98 | 132.6417 | 161.56 | 199.131 | 232.2105 | 256.7132 | 292.65
|  |  |  | ACWP | 36.462 | 53.934 | 64.981 | 96.648 | 109.709 | 119.964 | 130.754 | 151.928 | 188.959
|  |  |  | CPI | 0.93248 | 1.2237 | 1.5081 | 1.3724 | 1.4726 | 1.6599 | 1.7759 | 1.6897 | 1.5487
|  |  |  | SPI | 1 | 1 | 1 | 0.99731 | 0.99728 | 0.99565 | 0.99661 | 0.99501 | 0.99541
|  |  | CS Structure Procurement | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 28 | 30 | 32 | 79 | 131 | 176 | 214 | 261 | 308 | 339
|  |  | 1353 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Trim Coil Design/Procurement | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 29.6 | 74.5 | 145.7 | 191.5 | 259.3 | 327 | 355.5 | 519.3 | 733 | 958.1 | 1172.8 | 1341.2 | 1431.2 | 1488.8 | 1584.2 | 1671.5 | 1713.2 | 1736.8 | 1738.3 | 1803 | 1867.7 | 1867.7
|  |  | 1354 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 9.652
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | I&C Proc & Coil Assy | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 12 | 17 | 20 | 27 | 31 | 31 | 46 | 58 | 61 | 67 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 71 | 73
|  |  | 1355 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | SPI |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Cryostat Dsn/Proc | BCWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 14 | 24 | 46 | 89 | 133 | 154 | 177 | 200 | 207 | 207 | 281 | 345 | 399 | 451 | 487 | 518 | 532
|  |  | 1701;1751 | BCWP | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | ACWP | -0.23265 | 2.8487 | 4.3022 | 4.3022 | 5.2332 | 5.2332
|  |  |  | CPI | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | SPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Base support Structure Dsn/Proc | BCWS | 0 | 0 | 0 | 0 | 0 | 43 | 79 | 107 | 148 | 163 | 165 | 166 | 167 | 173 | 191 | 208 | 226 | 246 | 252 | 253 | 254 | 255
|  |  | 1702;1752 | BCWP | 0 | 0 | 0 | 0 | 10.83 | 11.09 | 11.0679 | 40.5823 | 96.49
|  |  |  | ACWP | 0 | 0 | 0 | 0 | 0 | 32.6 | 31.743 | 31.743 | 52.979
|  |  |  | CPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.34018 | 0.34867 | 1.2785 | 1.8213
|  |  |  | SPI | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.25791 | 0.1401 | 0.37927 | 0.65196
|  |  | FP Assembly | BCWS | 9 | 24 | 41 | 67 | 92 | 120 | 139 | 164 | 201 | 236 | 271 | 307 | 339 | 371 | 404 | 438 | 477 | 496 | 503 | 510 | 517
|  |  | 1806 | BCWP | 0 | 3 | 25 | 27.7447 | 36.15 | 39.838 | 106.1322 | 117.4494 | 128.02
|  |  |  | ACWP | 0 | 0 | -0.128 | 2.007 | 2.007 | 2.007 | 2.89 | 3.243 | 6.422
|  |  |  | CPI | #DIV/0! | #DIV/0! | -195.3125 | 13.824 | 18.012 | 19.8495 | 36.7239 | 36.2163 | 19.9346
|  |  |  | SPI | 0 | 0.125 | 0.60976 | 0.4141 | 0.39293 | 0.33198 | 0.76354 | 0.71615 | 0.63692

## BCWS by JOB
[5 empty] | BCWS Monthly |  |  |  |  | BCWS Monthly | [11 empty] | BCWS Monthly | [11 empty] | FY 2010 BCWS Monthly | [11 empty] | FY 2011 BCWS Monthly
RLM | JOB | notes | BTC | BCWS May 1,2007 - Jan31 2008 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 |  | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON |  | 3843.92 | 567.8 | 61 | 54 | 54 | 59 | 49 | 76 | 66.5 | 52 | 96.3 | 91.92 | 91.92 | 96.3 | 91.92 | 91.92 | 96.3 | 91.92 | 91.92 | 107 | 84 | 79 | 98 | 93 | 102 | 102 | 93 | 102 | 102 | 98 | 98 | 95 | 82 | 69 | 87 | 87 | 100 | 95 | 87 | 95 | 91 | 95 | 91 | 80 | 76 | 64 | 80
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON |  | 497 | 112 | 13 | 12 | 12 | 13 | 11 | 14 | 13 | 10 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 13 | 13 | 14 | 12 | 11 | 13 | 13 | 14 | 14 | 13 | 14 | 14 | 13 | 13 | 9 | 8 | 7 | 8 | 8 | 9 | 9 | 8 | 9 | 9 | 9 | 9 | 5 | 5 | 4 | 5
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY |  | 1453 | 269 | 30 | 29 | 29 | 31 | 26 | 36 | 31 | 23 | 34 | 32 | 32 | 34 | 32 | 32 | 34 | 32 | 31 | 38 | 30 | 28 | 35 | 33 | 36 | 36 | 33 | 36 | 36 | 35 | 31 | 38 | 33 | 28 | 35 | 35 | 40 | 38 | 35 | 38 | 36 | 38 | 36 | 23 | 22 | 19 | 23 | 1
| Total Jim Anderson |  | 5793.92 | 948.8 | 104 | 95 | 95 | 103 | 86 | 126 | 110.5 | 85 | 144.3 | 136.92 | 136.92 | 144.3 | 136.92 | 136.92 | 144.3 | 136.92 | 135.92 | 159 | 126 | 118 | 146 | 139 | 152 | 152 | 139 | 152 | 152 | 146 | 142 | 142 | 123 | 104 | 130 | 130 | 149 | 142 | 130 | 142 | 136 | 142 | 136 | 108 | 103 | 87 | 108 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK |  | 409 | 104 |  | 17 | 25 | 4 |  | 27 | 29 | 2 |  |  |  | 30 | 27 | 12 | 12 | 12 | 12 | 1 | [11 empty] | 60 | 88 | 34 | 17
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** |  | -252 | -252 | -162 |  |  | -90
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI |  | 348 | 294 | 17 | 24 | 51 | 56 | 29 | 26 | 22 | 28 | 41 | 35 | 11 | 5 | 3
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK |  | 1039 | 926 | 144 | 7 | 103 | 82 | 27 | 452 | 64 | 22 | 25 | 23 | 20 | 11 | 10 | 10 | 10 | 6 | 6 | [12 empty] | 12 | 4 | 1
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI |  | 2769 | 1713 | 237 | 171 | 231 | 182 | 136 | 213 | 188 | 133 | 222 | 211 | 183 | 209 | 193 | 156 | 87 | 16 | 1
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  | 501 | 258 |  | 4 | 19 | 20 | 47 | 57 | 43 | 26 | 42 | 43 | 42 | 26 | 24 | 25 | 26 | 33 | 24
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA |  | 1987 | 496 | 64 | 47 | 47 | 52 | 43 | 79 | 58 | 43 | 63 | 60 | 86 | 71 | 67 | 66 | 68 | 64 | 63 | 89 | 65 | 60 | 74 | 81 | 84 | 83 | 74 | 68 | 62 | 59 | 59 | 61 | 27
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK |  | 522 | 300 |  | 11 | 54 | 42 | 23 | 30 | 24 | 35 | 81 | 46 | 43 | 13 | 9 |  |  |  | 36 | 39 | 31 | 5
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA |  | 5751.56 | 2035.45 | 190.37 | 196.09 | 293.87 | 280.2 | 203.57 | 258.61 | 185.57 | 181.99 | 245.18 | 192.01 | 210.26 | 195.74 | 183.27 | 168.47 | 204.25 | 192.9 | 204.82 | 221.28 | 189.05 | 115.13 | 171.14 | 256.69 | 252.23 | 167.24 | 160.74 | 136.4 | 113.32 | 108.17 | 108.17 | 113.32 | 51.51
D - Larry Dudek | Job: 1815 - Field Period Assy |  | 1335 | 0 | [14 empty] | 155 | 55 | 13 | 3 | 30 | 40 | 58 | 49 | 92 | 102 | 112 | 110 | 172 | 123 | 126 | 64 | 31
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD |  | 69 | 0 | [28 empty] | 13 | 21 | 3 | 2 | 3 | 2 | 0 | 2 | 12 | 11
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD |  | 170 | 0 | [20 empty] | 22 | 20 | 25 | 3 | [5 empty] | 0 | 7 | 15 | 19 | 19 | 22 | 16 | 2
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON |  | 290 | 289 | 12 | 15 | 22 | 96 | 37 | 57 | 24 | 17 | 9 | 1
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON |  | 31 | 0 | [29 empty] | 9 | 8 | 1 | 2 | 2 | 7 | 2
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON |  | 263 | 0 | [22 empty] | 25 | 24 | 28 | 24 |  |  |  | 23 | 20 | 17 | 26 | 29 | 33 | 14
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON |  | 134 | 21 | 2.2 | 2.1 | 2.1 | 2.2 | 2.2 | 3 | 2.2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 6 | 5 | 4 | 5 | 5 | 6 | 6 | 5 | 6 | 5 | 6 | 5
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK |  | 46 | 0 | [17 empty] | 13 | 1 | 1 | 2 | 2 | 1 | 5 | 11 | 8 | 2
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER |  | 654 | 0 | [17 empty] | 23 | 18 |  | 59 | 35 | 21 | 23 | 17 |  |  | 30 | 44 | 61 | 57 | 49 | 55 | 42 | 32 | 29 | 26 | 30 | 2 | 1
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK |  | 105 | 0 | [17 empty] | 18 | 18 | 11 | 13 | 10 |  |  | 15 | 16 | 4
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH |  | 573 | 0 | [23 empty] | 7 | 8 | 23 | 24 | 21 | 23 | 25 | 57 | 58 | 73 | 68 | 60 | 57 | 45 | 24
D - Larry Dudek | Job: 7301 - Platform Design & |  | 202 | 0 | [16 empty] | 5 | 43 | 74 | 68 | 12
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY |  | 1416 | -301 | -308 |  |  |  |  | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | 12 | 5 | 71 | 63 | 68 | 66 | 60 | 66 | 66 | 62 | 61 | 64 | 54 | 45 | 56 | 55 | 86 | 85 | 79 | 85 | 83 | 84 | 81 | 79 | 77 | 70 | 4
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY |  | 1406 | 0 | [20 empty] | 10 | 38 | 42 | 42 | 38 | 42 | 42 | 40 | 42 | 42 | 40 | 44 | 40 | 38 | 83 | 87 | 83 | 87 | 87 | 87 | 87 | 83 | 87 | 91 | 4
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY |  | 4511 | 0 | [18 empty] | 59 | 393 | 369 | 129 | 103 | 102 | 108 | 147 | 75 | 74 | 107 | 243 | 98 | 128 | 224 | 105 | 206 | 295 | 206 | 172 | 181 | 197 | 151 | 248 | 211 | 157 | 23
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY |  | 414 | 0 | [20 empty] | 6 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 23 | 19 | 24 | 24 | 27 | 26 | 24 | 13
| Total Larry Dudek |  | 24693.56 | 5883.45 | 196.57 | 494.19 | 847.97 | 726.4 | 547.77 | 1204.61 | 641.77 | 490.99 | 733.18 | 615.01 | 599.26 | 565.74 | 520.27 | 441.47 | 567.25 | 382.9 | 368.82 | 467.28 | 499.05 | 700.13 | 870.14 | 709.69 | 742.23 | 653.24 | 657.74 | 669.4 | 589.32 | 545.17 | 610.17 | 830.32 | 573.51 | 417 | 544 | 389 | 562 | 619 | 482 | 428 | 358 | 375 | 324 | 410 | 375 | 318 | 31 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH |  | 258 | 182 | 5 |  |  | 9 | 30 | 35 | 25 | 30 | 48 | 32 | 33 | 11
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH |  | 1629 | 0 | [10 empty] | 4 | 20 | 40 | 136 | 173 | 325 | 270 | 183 | 101 | 56 | 63 | 65 | 64 | 69 | 32 | [8 empty] | 2 | 12 | 14
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN |  | 339 | 0 | [23 empty] | 4 | 8 | 16 | 2 | 2 | 47 | 52 | 45 | 38 | 47 | 47 | 31
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | updated baseline to include trim coil 36 coil set | 1867.7 | 145.7 | [6 empty] | 29.6 | 44.9 | 71.2 | 45.8 | 67.8 | 67.7 | 28.5 | 163.8 | 213.7 | 225.1 | 214.7 | 168.4 | 90 | 57.6 | 95.4 | 87.3 | 41.7 | 23.6 | 1.5 | 64.7 | 64.7
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  | 73 | 0 | [9 empty] | 4 | 4 | 4 | 5 | 3 | 7 | 4 |  | 15 | 12 | 3 | 6 | 4 | [12 empty] | 2
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH |  | 1004 | 463 | 8 | 65 | 60 | 35 | 60 | 61 | 59 | 56 | 59 | 58 | 104 | 57 | 57 | 56 | 103 | 54 | 52
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod |  | -36 | -36 | -36
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER |  | -84 | -84 | 5 | 1 |  | -90
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON |  | 280 | 278 | 12 | 23 | 8 | 15 | 12 | 116 | 56 | 19 | 17 | 2
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON |  | 1208 | 1184 | 177 | 276 | 250 | 191 | 102 | 118 | 26 | 19 | 25 | 24
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER |  | 118 | 118 | 30 |  | 51 | 37
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN |  | 186 | 186 | 7 | 31 | 32 | 58 | 36 | 22 | 0
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN |  | 1074 | 0 | [13 empty] | 32 | 109 | 131 | 131 | 143 | 93 | 51 | 63 | 60 | 66 | 66 | 60 | 66 | 3
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON |  | 861 | 34 | 6 | [7 empty] | 28 | 27 | 27 | 28 | 27 | 48 | 31 | 47 | 58 | 77 | 61 | 53 | 26 | 20 | 23 | 23 | 20 | 23 | 23 | 21 | 4 | 42 | 42 | 39 | 34 | 3
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER |  | 207 | 0 | [17 empty] | 6 | 4 | 4 | 10 | 22 | 43 | 44 | 21 | 23 | 23 | 7
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN |  | 164 | 148 | [5 empty] | 43 | 36 | 28 | 41 | 15 | 1
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER |  | 325 | 0 | [29 empty] | 74 | 64 | 54 | 52 | 36 | 31 | 14
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN |  | 91 | 0 | [10 empty] | 1 | 1 | 1 | 6 | 18 | 17 | 18 | 20 | 6 | 1 | 1 | 1 | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs |  | 517 | 201 | 9 | 15 | 17 | 26 | 25 | 28 | 19 | 25 | 37 | 35 | 35 | 36 | 32 | 32 | 33 | 34 | 39 | 19 | 7 | 7 | 7
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE |  | 1618 | 294 | 34 | 32 | 32 | 35 | 29 | 38 | 33 | 25 | 36 | 34 | 34 | 36 | 34 | 34 | 36 | 34 | 33 | 40 | 31 | 30 | 37 | 35 | 38 | 38 | 35 | 38 | 38 | 37 | 33 | 40 | 34 | 29 | 36 | 36 | 42 | 40 | 36 | 40 | 38 | 40 | 38 | 45 | 43 | 37 | 45
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN |  | 2519 | 556 | 82 | 76 | 63 | 69 | 53 | 61 | 53 | 40 | 59 | 56 | 56 | 59 | 56 | 56 | 59 | 56 | 56 | 61 | 48 | 45 | 56 | 53 | 59 | 59 | 53 | 59 | 59 | 56 | 56 | 59 | 51 | 43 | 53 | 53 | 61 | 59 | 53 | 59 | 56 | 59 | 56 | 48 | 46 | 39 | 48 | 2
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN |  | 1412 | 282 | 33 | 32 | 32 | 35 | 29 | 35 | 30 | 23 | 33 | 32 | 32 | 33 | 32 | 32 | 33 | 32 | 32 | 35 | 27 | 26 | 32 | 30 | 33 | 33 | 30 | 33 | 33 | 32 | 32 | 33 | 29 | 24 | 30 | 30 | 35 | 33 | 30 | 33 | 32 | 33 | 32 | 32 | 30 | 26 | 32 | 2
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS |  | 1160 | 275 | 37 | 36 | 36 | 39 | 32 | 27 | 24 | 18 | 26 | 25 | 25 | 26 | 25 | 25 | 26 | 25 | 25 | 27 | 21 | 20 | 25 | 24 | 26 | 26 | 24 | 26 | 26 | 25 | 25 | 26 | 22 | 19 | 24 | 24 | 27 | 26 | 24 | 26 | 25 | 26 | 25 | 25 | 24 | 20 | 25
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS |  | 592 | 180 |  | 27 | 27 | 30 | 18 | 21 | 20 | 15 | 22 | 25 | 35 | 37 | 35 | 18 | 12 | 12 | 12 | 13 | 14 | 14 | 18 | 18 | 16 | 16 | 14 | 11 | 9 | 9 | 9 | 9 | 6 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks |  | 18.8 | 18.8 | 14.8 | 4
H - Phil Heitzenroeder | Job: 8215 Plant Design |  | 129 | 26 |  |  |  | 8 | 7 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3
| Total Phil Heitzenroeder |  | 17530.5 | 4451.5 | 423.8 | 618 | 608 | 497 | 433 | 608 | 413.6 | 344.9 | 505.2 | 417.8 | 461.8 | 418.7 | 375.5 | 644.8 | 856.7 | 999.1 | 943.7 | 810.4 | 517 | 369.6 | 442.4 | 422.3 | 412.7 | 404.6 | 301.5 | 362.7 | 283.7 | 192 | 209 | 338 | 295 | 251 | 283 | 238 | 248 | 193 | 150 | 165 | 158 | 165 | 158 | 157 | 150 | 127 | 153 | 4 | 0 | 0 | 0 | 0 | 0
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN |  | 52 | -104 | -104 | [16 empty] | 0 | 0 | 0 | 12 | 11 | 14 | 4 | 3 | 1 | 1 | 3 | 6 | 6 | 4 | 3 | 8 | 27 | 29 | 15 | 6 | 3
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN |  | 604 | 4 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 38 | 31 | 41 | 53 | 18 | 1 | 1 | 1 | 1 | 14 | 74 | 1 | 0 | 62 | 52 | 66 | 66 | 72
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN |  | 1084 | 0 | [21 empty] | 11 | 26 | 33 | 32 | 41 | 42 | 60 | 69 | 103 | 73 | 55 | 67 | 75 | 111 | 97 | 91 | 56 | 31 | 10 | 1
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN |  | 682 | 0 | [17 empty] | 21 | 23 | 20 | 18 | 17 | 37 | 34 | 29 | 37 | 43 | 40 | 37 | 39 | 22 | 18 | 19 | 13 |  |  | 3 | 35 | 33 | 35 | 56 | 53
V - Al vonHalle | Job: 5101 - Network and Fiber |  | 151 | 0 | [26 empty] | 3 | 2 | 2 | 2 | 14 | 14 | 18 | 23 | 32 | 31 | 10
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA |  | 197 | 0 | [22 empty] | 5 | 3 | 2 | 2 | 21 | 25 | 24 | 15 | 6 | 5 | 7 | 9 | 5 | 14 | 20 | 22 | 12
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA |  | 165 | 0 | [24 empty] | 4 | 7 | 11 | 21 | 7 | 7 | 12 | 10 | 12 | 9 | 10 | 13 | 17 | 15 | 10
V - Al vonHalle | Job: 5401 - Facility Timing & |  | 204 | 0 | [26 empty] | 5 | 4 | 3 | 16 | 25 | 24 | 15 | 16 | 32 | 24 | 10 | 15 | 12 | 3
V - Al vonHalle | Job: 5501 - Real Time Control |  | 131 | 0 | [26 empty] | 5 | 7 | 6 | 6 | 8 | 7 | 9 | 14 | 21 | 25 | 9 | 13 | 1
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA |  | 221 | 0 | [25 empty] | 2 | 2 | 3 | 4 | 19 | 20 | 17 | 18 | 18 | 34 | 32 | 29 | 7 | 11 | 5
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA |  | 72.2 | 14.2 | 1.2 | 1.2 | 1.3 | 2 | 1.3 | 2.1 | 2.1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE |  | 767 | 0 | [18 empty] | 22 | 32 | 29 | 24 | 21 | 27 | 24 | 27 | 24 | 22 | 26 | 27 | 14 | 20 | 9 | [8 empty] | 116 | 110 | 94 | 99
| Total Al vonHalle |  | 4330.2 | -85.8 | -102.8 | 1.2 | 1.3 | 2 | 1.3 | 3.1 | 3.1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 61 | 77 | 94 | 114 | 82 | 106 | 104 | 96 | 120 | 173 | 263 | 187 | 242 | 261 | 226 | 250 | 272 | 348 | 253 | 197 | 168 | 112 | 55 | 59 | 169 | 110 | 94 | 99 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 52348.18 | 11197.95 | 621.57 | 1208.39 | 1552.27 | 1328.4 | 1068.07 | 1941.71 | 1168.97 | 922.89 | 1385.68 | 1172.73 | 1200.98 | 1131.74 | 1035.69 | 1226.19 | 1571.25 | 1521.92 | 1451.44 | 1497.68 | 1219.05 | 1281.73 | 1572.54 | 1352.99 | 1412.93 | 1313.84 | 1194.24 | 1304.1 | 1198.02 | 1146.17 | 1148.17 | 1552.32 | 1252.51 | 998 | 1207 | 1029 | 1307 | 1207 | 959 | 903 | 764 | 737 | 677 | 844 | 738 | 626 | 391
23007.57
9812.27
corrected

## FY08 MR worksheet
NCSX FY08 Alternate Plan
FY08 Budget |  |  | FY08 Plan (base plus ETC's) |  |  | Acceleration Candidates
| 15.9 | BA |  | 1.96 | spent oct & nov |  | Design accelerations- Priority 1 Scope
| 1.777 | fy07 c/o |  | 13.515 | current plan BCWR (dec-sept) |  |  | 0.069 | NBI port exte dsn | Resource Requirements Priority 1 scope (manmonmths)
| 17.677 | fyg08 budget | [5 empty] | 0.028 | CS structure bus dsn/analysis | 7 | EA Engrs
| 3 | additional funding | [5 empty] | 0.352 | coil service leads (ornl) | 21.4 | Mech Designers
| 20.677 | total planning budget for alternate plan |  | 15.475 |  |  |  | 0.207 | cryostat | 6.2 | Electrical Engrs
[8 empty] | 0.198 | cryogenic sys design | 10.5 | FO&M Engrs
|  |  | APPARENT FREE BALANCE = | 5.202 |  |  |  | 0.109 | fueling (3 injectors) | 3 | I&C engr
[8 empty] | 0.213 | VPS | 17.1 | ORNL Engrs
|  |  | ETC's (estimated) |  |  |  |  | 0.025 | water systems
|  |  |  | -0.4 | rate reductions ~-5 points |  |  | 0.138 | bakeout sys
|  |  |  | 0.2 | wbs 82 simmons/phil +.65 fte |  |  | 0.065 | WBS 5 I&C Adv Concep design
|  |  |  | 0.1 | plant design +.5 fte designer |  |  | 0.215 | power systems design wbs 4
|  |  |  | 0.137 | Project mgr |  |  | 1.619
|  |  |  | 0.037 | allocations
|  |  |  | -0.2 | wbs 19 stell core mgt (ornl) |  | Procurement commitments carried over into fy09 (M&S loaded)
|  |  |  | 0.15 | make FPA schedule slip |  |  | 0.342 | PF
|  |  | ADJUSTED FREE BALANCE = | 5.226 |  |  |  | 0.472 | Trim Coils
[8 empty] | 0.55 | Coil Support Struct
[8 empty] | 0.055 | Station 6 Fixtures
1.419
[7 empty] | Other accelerations- Priority 2 Scope |  |  | Resource Requirements Priority 2 scope(manmonmths or $K)
[8 empty] | 0.1 | e-beam mapping | 1 | Mech Designers
[8 empty] | 0.1 | coil protection wbs4 | 2.3 | Electrical Engrs
[8 empty] | 0.2 | ISTP documentation (~50% ) | 4.7 | FO&M Engrs
[8 empty] | 0.444 | Award/Commit Lead HW | 4 | FO&M Tech
[8 empty] | 0.168 | Award/Commit LN2 distr sys HW | 2.2 | Reserach
[8 empty] | 1.012 |  | $342k | M&S
[7 empty] | Remaining unplanned free balance = | 1.176
Other candidates
NON MIE Scope-Long Lead Upgrade Scope
NB Armor Design (ornl)
[8 empty] | 1600 | 1 fte analysis engr
3.8 fte designer
2.1 fte engr
[8 empty] | 1206 | NB #1&#2 refurbishment

## ACWP by JOB
|  |  |  | ACWP Monthly |  |  |  |  | ACWP Monthly
RLM | JOB | ACWP May 1,2007 - Jan 31, 2008 |  | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12 | JAN fy12 | FEB fy12 | MAR fy12 | APR fy12 | MAY fy12 | JUN fy12 | JUL fy12 | AUG fy12 | SEP fy12
A - Jim Anderson | Job: 8101 - Project Management &Control-ANDERSON | 486.2368 | 8101 | 55.8777 | 58.9419 | 48.7333 | 48.726 | 80 | 47.586 | 52.458 | 49.307 | 44.607
A - Jim Anderson | Job: 8102 - NCSX MIE Management ORNL-LYON | 166.959 | 8102 | 30.964 | 22.991 | 13.862 | 23.695 | 17.316 | 15.755 | 12.535 | 15.277 | 14.564
A - Jim Anderson | Job: 8998 - Allocations-STRYKOWSKY | 372.0318 | 8998 | 24.8767 | 24.9933 | 28.3578 | 34.873 | 83.276 | 32.921 | 78.1 | 31.811 | 32.823
| Total Jim Anderson | 1025.2276 |  | 111.7184 | 106.9261 | 90.9531 | 107.294 | 180.592 | 96.262 | 143.093 | 96.395 | 91.994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 241.8109 | 1204 | 16.0209 | 1.3261 | 5.4769 | 16.8 | 100.76 | 25.926 | 19.061 | 12.728 | 43.712
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -251.7703 | 1250 | -161.88 | 0 | -92.5573 |  | 2.667
D - Larry Dudek | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 144.6134 | 1408 | 23.8679 | 11.6976 | 31.1989 | 21.389 | 8.337 | 8.641 | 11.699 | 13.077 | 14.706
D - Larry Dudek | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 471.1149 | 1431 | 144.2801 | 0 | 47.0428 |  | 96.358 | 16.395 | 66.906 | 55.497 | 44.636
D - Larry Dudek | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1694.4647 | 1451 | 283.7075 | 218.7955 | 157.2876 | 240.296 | 190.337 | 154.595 | 191.385 | 159.697 | 98.364
D - Larry Dudek | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 427.645 | 1459 | 42.2044 | 55.2785 | 51.7021 | 64.806 | 75.462 | 49.777 | 30.823 | 22.752 | 34.84
D - Larry Dudek | Job: 1802 - FP Assy Oversight&Support-VIOLA | 519.7007 | 1802 | 84.3784 | 51.4086 | 66.9277 | 81.881 | 56.68 | 34.76 | 56.159 | 52.953 | 34.553
D - Larry Dudek | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 282.9039 |  | 34.185 | 34.0075 | 22.4994 | 37.434 | 13.088 | 15.582 | 23.077 | 23.318 | 79.713
D - Larry Dudek | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 1261.8701 | 1810 | 106.9026 | 120.8905 | 140.889 | 198.049 | 167.112 | 116.848 | 160.367 | 126.623 | 124.189
D - Larry Dudek | Job: 1815 - Field Period Assy | 0 | [8 empty] | 0
D - Larry Dudek | Job: 2101 - Fueling Systems-BLANCHARD | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0
D - Larry Dudek | Job: 3101 - Magnetic Diagnostics-STRATTON | 142.0566 | 3101 | 27.0665 | 15.8846 | 38.1895 | 30.572 | 9.403 | 1.477 | 1.346 | 10.9 | 7.218
D - Larry Dudek | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mapping-STRATTON | 0
D - Larry Dudek | Job: 3901 - Diagnostics sys Integration-STRATTON | 34.4082 | 3901 | 2.6208 | 4.2019 | 6.7205 | 4.117 | 2.396 | 2.884 | 4.292 | 4.306 | 2.87
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 0
D - Larry Dudek | Job: 6201 - Cryogenic Syst-GETTELFINGER | 0
D - Larry Dudek | Job: 6301 - Utility Systems-DUDEK | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0
D - Larry Dudek | Job: 7301 - Platform Design & | 0
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -255.0753 | 7401 | -297.561 | 4.2205 | 4.0193 | 6.749 | 0.293 | 0 | 6.801 | 6.801 | 13.602
D - Larry Dudek | Job: 7501 - Construction Support Crew-PERRY | 0
D - Larry Dudek | Job: 7503 - Machine Assembly (station 6)-PERRY | 0
D - Larry Dudek | Job: 7601 - Tooling Design & Fabrication-PERRY | 0
| Total larry Dudek | 4713.7428 |  | 305.793 | 517.7113 | 479.3966 | 702.093 | 722.893 | 426.885 | 571.916 | 488.652 | 498.403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H - Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 77.033 | 1302 | 4.26 | 1.5406 | 1.4053 | 6.578 | 30.601 | 3.217 | 7.747 | 14.098 | 7.586
H - Phil Heitzenroeder | Job: 1352 - PF Coil Procurement-KALISH | 7.832 | 1352 | [7 empty] | 0 | 7.832
H - Phil Heitzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 0 | 1353 | [7 empty] | 0 | 0
H - Phil Heitzenroeder | Job: 1354 - Trim Coil Design &Procurement-KALISH | 49.246 | 1354 | [5 empty] | 9.652 | 8.422 | 9.32 | 21.852
H - Phil Heitzenroeder | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0 | 1355 | [7 empty] | 0 | 0
H - Phil Heitzenroeder | Job: 1361 - TF Fabrication-KALISH | 471.5475 | 1361 | -6.0157 | 40.395 | 54.4283 | 96.543 | 85.973 | 69.22 | 44.653 | 49.8 | 36.551
H - Phil Heitzenroeder | Job: 1404 - MCWF R&D 1st Prod | -34.9474 | 1404 | -35.9384 | 0 | 0 | 0.835 | 0.156 | 0 |  |  | 0
H - Phil Heitzenroeder | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -65.1126 | 1411 | 7.495 | 2.0635 | -92.7721 |  | 18.101 |  |  |  | 0
H - Phil Heitzenroeder | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 184.2659 | 1416 | 12.3179 | 9.522 | 18.891 | 27.345 | -0.069 | 19.257 | 34.792 | 38.45 | 23.76
H - Phil Heitzenroeder | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1062.0957 | 1421 | 81.6509 | 107.2854 | 109.3563 | 253.823 | 122.667 | 94.85 | 94.52 | 115.97 | 81.973
H - Phil Heitzenroeder | Job: 1429 - MC Interface R&D-GETTELFINGER | 87.6232 | 1429 | 29.9725 | 17.1863 | 20.5674 | 12.911 | 5.155 | 0.441 | 0.671 | 0.446 | 0.273
H - Phil Heitzenroeder | Job: 1501 - Coil Structures Design-DAHLGREN | 209.5641 | 1501 | 54.1006 | 47.3749 | 37.1207 | 36.056 | 2.262 | -16.914 | 23.081 | 24.917 | 1.566
H - Phil Heitzenroeder | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 1550 | [5 empty] | 0 |  | 0
H - Phil Heitzenroeder | Job: 1601 - Coil Services Design-GORANSON | 0 | [8 empty] | 0
H - Phil Heitzenroeder | Job: 1701 - Cryostat Design-GETTLEFINGER | 5.2332 | 1701 | -0.23265 | 3.0813 | 1.4536 |  | 0.931
H - Phil Heitzenroeder | Job: 1702 - Base Support Struct Design-DAHLGREN | 52.979 | 1702 | [5 empty] | 32.6 | -0.857 | 0 | 21.236
H - Phil Heitzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0
H - Phil Heitzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 0 | [8 empty] | 0
H - Phil Heitzenroeder | Job: 1806 - FP Assembly specs | 6.422 | 1806 |  |  | -0.128 | 2.135 |  |  | 0.883 | 0.353 | 3.179
H - Phil Heitzenroeder | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 188.959 | 1901 | 36.462 | 17.472 | 11.047 | 31.667 | 13.061 | 10.255 | 10.79 | 21.174 | 37.031
H - Phil Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 537.4581 | 8202 | 59.5964 | 58.6317 | 58.6029 | 87.374 | 54.224 | 54.702 | 55.126 | 62.893 | 46.308
H - Phil Heitzenroeder | Job: 8203 - Design Integration-BROWN | 114.137 | 8203 | 5.0798 | 5.2382 | 1.641 | 10.093 | 14.509 | 19.305 | 20.05 | 21.93 | 16.291
H - Phil Heitzenroeder | Job: 8204 - Systems Analysis-BROOKS | 408.8333 | 8204 | 42.5836 | 53.1523 | 47.1084 | 50.469 | 32.096 | 46.654 | 47.332 | 54.752 | 34.686
H - Phil Heitzenroeder | Job: 8205 - Dimensional Control Coordin-ELLIS | 133.7801 | 8205 | 17.5068 | 20.0831 | 22.4922 | 21.472 | 10.542 | 4.038 | 17.183 | 11.798 | 8.665
H - Phil Heitzenroeder | Job: 8210 - FY07 Rebaseling tasks | 55.4465 | 8210 | 8.3642 | 4.8261 | 9.5912 | 16.099 | 6.371 | 1.625 | 7.21 | 0.68 | 0.68
H - Phil Heitzenroeder | Job: 8215 Plant Design | 0
| Total Phil Heitzenroeder | 3552.3957 |  | 317.203 | 387.8524 | 300.8052 | 653.4 | 396.58 | 348.902 | 371.603 | 426.581 | 349.469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104.1027 | 4101 | -104.1027 | 0 | 0
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4401 - Control & Protection-RAMAKRISHNAN | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | -0.55581 | 4501 | -0.15696 | 0 | -0.041849 |  | -0.357
V - Al vonHalle | Job: 5101 - Network and Fiber | 0
V - Al vonHalle | Job: 5201 - I&C Systems-SICHTA | 0
V - Al vonHalle | Job: 5301 - Data Acquisition-SICHTA | 0
V - Al vonHalle | Job: 5401 - Facility Timing & | 0
V - Al vonHalle | Job: 5501 - Real Time Control | 0
V - Al vonHalle | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0
V - Al vonHalle | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 0
V - Al vonHalle | Job: 8501 - Integrated Systems Testing-GENTILE | 0
| Total Al vonHalle | -104.6585 |  | -104.2596 | 0 | -0.041849 | 0 | -0.357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total project | 9186.7076 |  | 630.4547 | 1012.4898 | 871.113 | 1462.787 | 1299.708 | 872.049 | 1086.612 | 1011.628 | 939.866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3910.155
1958.661
[11 empty] | 2970.289 | 3896.289
corrected

## BCWP by JOB
|  |  | BCWP Monthly |  |  |  |  | BCWP Monthly | [59 empty] | BCWP Cum |  |  | BCWP Cum | [11 empty] | FY 2009 BCWP Cum | [11 empty] | FY 2010 BCWP Cum | [17 empty] | oct | oct | oct | nov | nov | nov
RLM | JOB | BCWP May 1,2007 - Jan 31, 2008 | May Fy07 | June Fy07 | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | July Fy07 | Aug Fy07 | Sep Fy07 | Oct Fy08 | Nov Fy08 | Dec Fy08 | Jan Fy08 | Feb Fy08 | Mar Fy08 | Apr Fy08 | May Fy08 | Jun Fy08 | Jul Fy08 | Aug Fy08 | Sep Fy08 | Oct Fy09 | Nov Fy09 | Dec Fy09 | Jan Fy09 | Feb Fy09 | Mar Fy09 | Apr Fy09 | May Fy09 | Jun Fy09 | Jul Fy09 | Aug Fy09 | Sep Fy09 | Oct Fy10 | Nov Fy10 | Dec Fy10 | Jan Fy10 | Feb Fy10 | Mar Fy10 | Apr Fy10 | May Fy10 | Jun Fy10 | Jul Fy10 | Aug Fy10 | Sep Fy10 | Oct Fy11 | Nov Fy11 | Dec Fy11 | Jan Fy11 | Feb Fy11 | Mar Fy11 | Sum of EVC |  |  | RLMS | JJJJ | Total
A - Jjm Anderson | Job: 8101 - Project Management &Control-ANDERSON | 542.41 | 59 | 56 | 54 | 60.1165 | 48.9835 | 95.146 | 81.754 | 14.723 | 72.687 | [56 empty] | 169 | 229.1165 | 278.1 | 373.246 | 455 | 469.723 | 542.41 | [38 empty] | A | 8101 | 373.2469 | A | 8101 | 455.98 | A | 8101 | 469.7233
A - Jjm Anderson | Job: 8102 - NCSX MjE Management ORNL-LYON | 111.46 | 13 | 12 | 12 | 12.6048 | 10.8152 | 14.628 | 12.879 | 9.54 | 13.993 | [56 empty] | 37 | 49.6048 | 60.42 | 75.048 | 87.927 | 97.467 | 111.46 | [39 empty] | 8102 | 75.048 |  | 8102 | 87.927 |  | 8102 | 97.467
A - Jjm Anderson | Job: 8998 - Allocatjons-STRYKOWSKY | 276.43 | 30 | 29 | 29 | 30.2576 | 25.7824 | 35.364 | 32.596 | 21.6024 | 42.8276 | [56 empty] | 88 | 118.2576 | 144.04 | 179.404 | 212 | 233.6024 | 276.43 | [39 empty] | 8998 | 179.4042 |  | 8998 | 210.5393 |  | 8998 | 233.6024
| Total Jjm Anderson | 930.3 | 102 | 97 | 95 | 102.9789 | 85.5811 | 145.138 | 127.229 | 45.8654 | 129.5076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 294 | 396.9789 | 482.56 | 627.698 | 754.927 | 800.7924 | 930.3 | [38 empty] | A Total |  | 627.6991 |  |  |  | A Total |  | 800.7927
D - Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 172.03 |  | 55 | 9 | 4.4894 | 14.5406 | 36.153 | 21.8115 | -21.8109 | 52.8464 | [56 empty] | 64 | 68.4894 | 83.03 | 119.183 | 140.9945 | 119.1836 | 172.03 | [38 empty] | D | 1204 | 119.1836 | D | 1204 | 140.9945 | D | 1204 | 119.1836
D - Larry Dudek | Job: 1250 - Vacuum Vessel Fabrjcatjon**CLOSED** | -251.69 | -162 |  | -90 | 0.30528 | 0.00472 | -0.005 | 0.00028 | 0 | 0.00472 | [56 empty] | -252 | -251.6947 | -251.69 | -251.695 | -251.6947 | -251.6947 | -251.69 | [39 empty] | 1250 | -251.6947 |  | 1250 | -251.6947 |  | 1250 | -251.6947
D - Larry Dudek | Job: 1408 - MC Wjndjng Suppljes-CHRZANOWSKj | 267.34 | 7 | 33 | 23 | 93.4268 | 5.9732 | 41.568 | 22.4543 | 16.868 | 24.0497 | [56 empty] | 63 | 156.4268 | 162.4 | 203.968 | 226.4223 | 243.2903 | 267.34 | [39 empty] | 1408 | 203.9684 |  | 1408 | 226.4223 |  | 1408 | 243.2903
D - Larry Dudek | Job: 1431 - Mod. Cojl jnterface Hardware-DUDEK | 788.18 | 81 | 77 |  | 98.8971 | 52.7029 | 280.1 | 45.9104 | 90.3896 | 62.18 | [56 empty] | 158 | 256.8971 | 309.6 | 589.7 | 635.6104 | 726 | 788.18 | [39 empty] | 1431 | 589.746 |  | 1431 | 635.6104 |  | 1431 | 726
D - Larry Dudek | Job: 1451 - Mod Cojl Wjndjng-CHRZANOWSKj | 1916.44 | 236 | 176 | 299 | 235.222 | 237.778 | 255.27 | 106.8135 | 164.675 | 205.6815 | [56 empty] | 711 | 946.222 | 1184 | 1439.27 | 1546.0835 | 1710.7585 | 1916.44 | [39 empty] | 1451 | 1439.2702 |  | 1451 | 1546.0835 |  | 1451 | 1710.7585
D - Larry Dudek | Job: 1459 - Mod Cojl Fabr.Punch Ljst-CHRZANOWSKj | 305.07 |  | 18 | 14 | 12.1632 | 91.1368 | 33.018 | 114.6577 | 21.869 | 0.22533 | [56 empty] | 32 | 44.1632 | 135.3 | 168.318 | 282.9757 | 304.8447 | 305.07 | [39 empty] | 1459 | 168.3665 |  | 1459 | 282.9757 |  | 1459 | 304.8447
D - Larry Dudek | Job: 1802 - FP Assy Oversjght&Support-VjOLA | 425.71 | 64 | 47 | 47 | 52.1107 | 42.5393 | 54.06 | 47.0231 | 35.2615 | 36.7154 | [56 empty] | 158 | 210.1107 | 252.65 | 306.71 | 353.7331 | 388.9946 | 425.71 | [39 empty] | 1802 | 306.7178 |  | 1802 | 353.7331 |  | 1802 | 388.9946
D - Larry Dudek | Job: 1803/1805- FPA Tooljng/Constr-BROWN/DUDEK | 85.14 |  | 12 | 42 | 10.0883 | 4.2117 | 0.21 | 0.22777 | 12.1269 | 4.2754 | [56 empty] | 54 | 64.0883 | 68.3 | 68.51 | 68.7378 | 80.8646 | 85.14 | [39 empty] | 1803 | 68.5159 |  | 1803 | 68.7378 |  | 1803 | 80.8646
D - Larry Dudek | Job:1810-Fjeld Perjod Assy -Statjon 1 2 3 VjOLA | 1672.87 | 190 | 193 | 267 | 204.5431 | 251.9569 | 187.047 | 130.0196 | 114.0824 | 135.221 | [56 empty] | 650 | 854.5431 | 1106.5 | 1293.547 | 1423.5666 | 1537.649 | 1672.87 | [39 empty] | 1810 | 1293.58 |  | 1810 | 1423.5666 |  | 1810 | 1537.649
D - Larry Dudek | Job: 1815 - Fjeld Perjod Assy | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 1815 | 0 |  | 1815 | 0 |  | 1815 | 0
D - Larry Dudek | Job: 2101 - Fueljng Systems-BLANCHARD | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 2101 | 0 |  | 2101 | 0 |  | 2101 | 0
D - Larry Dudek | Job: 2201 - Vacuum Pumpjng Systems-BLANCHARD | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 2201 | 0 |  | 2201 | 0 |  | 2201 | 0
D - Larry Dudek | Job: 3101 - Magnetjc Djagnostjcs-STRATTON | 127.16 | 12 | 42 | 54 | 30.94 | 5.4811 | 2.1119 | 46.0682 | 22.6388 | -88.08 | [56 empty] | 108 | 138.94 | 144.4211 | 146.533 | 192.6012 | 215.24 | 127.16 | [39 empty] | 3101 | 146.5334 |  | 3101 | 192.6012 |  | 3101 | 215.2439
D - Larry Dudek | Job: 3601 - Edge Djvertor Djagnostjcs-STRATTON | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 3601 | 0 |  | 3601 | 0 |  | 3601 | 0
D - Larry Dudek | Job: 3801 - Electron Beam Mappjng-STRATTON | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 3801 | 0 |  | 3801 | 0 |  | 3801 | 0
D - Larry Dudek | Job: 3901 - Djagnostjcs sys jntegratjon-STRATTON | 20.74 | 2 | 2 | 2 | 3.3261 | 2.0333 | 2.6886 | 2.3679 | 1.7537 | 2.5703 | [56 empty] | 6 | 9.3261 | 11.3594 | 14.048 | 16.4159 | 18.1697 | 20.74 | [39 empty] | 3901 | 14.0484 |  | 3901 | 16.4159 |  | 3901 | 18.1696
D - Larry Dudek | Job: 6101 - Water Systems-DUDEK | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 6101 | 0 |  | 6101 | 0 |  | 6101 | 0
D - Larry Dudek | Job: 6201 - Cryogenjc Syst-GETTELFjNGER | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 6201 | 0 |  | 6201 | 0 |  | 6201 | 0
D - Larry Dudek | Job: 6301 - Utjljty Systems-DUDEK | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 6301 | 0 |  | 6301 | 0 |  | 6301 | 0
D - Larry Dudek | Job: 6401 - PFC/VV Htng/Cooljng(bakeout)- KALjSH | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 6401 | 0 |  | 6401 | 0 |  | 6401 | 0
D - Larry Dudek | Job: 7301 - Platform Desjgn & | 2.63 |  | 1 | 2 | -0.44672 | -0.003282 | 0.064 | 0.019634 | 0 | -0.003634 | [56 empty] | 3 | 2.5533 | 2.55 | 2.614 | 2.6336 | 2.6336 | 2.63 | [39 empty] | 7301 | 2.6149 |  | 7301 | 2.6336 |  | 7301 | 2.6336
D - Larry Dudek | Job: 7401 - TC Prep & Mach Assy Plannjng-PERRY | -301.01 | -308 |  |  | -0.3 | 0 | 2.1 | 1.8192 | 1.3608 | 2.01 | [56 empty] | -308 | -308.3 | -308.3 | -306.2 | -304.3808 | -303.02 | -301.01 | [39 empty] | 7401 | -306.1947 |  | 7401 | -304.3808 |  | 7401 | -303.0204
D - Larry Dudek | Job: 7501 - Constructjon Support Crew-PERRY | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 7501 | 0 |  | 7501 | 0 |  | 7501 | 0
D - Larry Dudek | Job: 7503 - Machjne Assembly (statjon 6)-PERRY | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 7503 | 0 |  | 7503 | 0 |  | 7503 | 0
D - Larry Dudek | Job: 7601 - Tooljng Desjgn & Fabrjcatjon-PERRY | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 7601 | 0 |  | 7601 | 0 |  | 7601 | 0
| Total larry Dudek | 5230.61 | 122 | 656 | 669 | 744.7652 | 708.3553 | 894.3855 | 539.1931 | 459.2148 | 437.6961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1447 | 2191.7652 | 2900.1205 | 3794.506 | 4333.6991 | 4792.9139 | 5230.61 | [38 empty] | D Total |  | 3794.6557 |  |  |  | D Total |  | 4814.4897
H - Phjl Hejtzenroeder | Job: 1302 - PF Desjgn -KALjSH | 180.73 | 5 |  |  | 42.3325 | 13.0175 | 0.735 | 0.50959 | 52.9787 | 66.1567 | [56 empty] | 5 | 47.3325 | 60.35 | 61.085 | 61.5946 | 114.5733 | 180.73 | [38 empty] | H | 1302 | 61.2847 | H | 1302 | 61.5946 | H | 1302 | 114.5733
H - Phjl Hejtzenroeder | Job: 1352 - PF Cojl Procurement-KALjSH | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 1352 | 0 |  | 1352 | 0 |  | 1352 | 0
H - Phjl Hejtzenroeder | Job: 1353 - CS Structure Procurement-DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 1353 | 0 |  | 1353 | 0 |  | 1353 | 0
H - Phjl Hejtzenroeder | Job: 1354 - Trjm Cojl Desjgn &Procurement-KALjSH | 124.91 |  |  |  | 0 | 0 | 0 | 1.4861 | 28.3098 | 95.1141 | [56 empty] | 0 | 0 | 0 |  | 1.4861 | 29.7959 | 124.91 | [39 empty] | 1354 | 0 |  | 1354 | 1.4861 |  | 1354 | 29.7959
H - Phjl Hejtzenroeder | Job: 1355 - WBS 13 j&C Proc and Cojl Assy-KALjSH | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 1355 | 0 |  | 1355 | 0 |  | 1355 | 0
H - Phjl Hejtzenroeder | Job: 1361 - TF Fabrjcatjon-KALjSH | 447.46 | 4 | 45 | 59 | 91.4121 | 68.2379 | 63.632 | 32.318 | 58.995 | 24.865 | [56 empty] | 108 | 199.4121 | 267.65 | 331.282 | 363.6 | 422.595 | 447.46 | [39 empty] | 1361 | 331.2825 |  | 1361 | 363.6 |  | 1361 | 422.595
H - Phjl Hejtzenroeder | Job: 1404 - MCWF R&D 1st Prod | -35.94 | -36 |  |  | 0.06 | 0 | 0 | 0 | 0 | 0 | [56 empty] | -36 | -35.94 | -35.94 | -35.94 | -35.94 | -35.94 | -35.94 | [39 empty] | 1404 | -35.94 |  | 1404 | -35.94 |  | 1404 | -35.94
H - Phjl Hejtzenroeder | Job: 1411 - MCWF Fabr. S005242-HEjTZENROEDER | -80.39 | 6 | 4 | -90 | -0.3908 | 0.0008 | 0 | -0.0008 | 0 | 0.0008 | [56 empty] | -80 | -80.3908 | -80.39 | -80.39 | -80.3908 | -80.3908 | -80.39 | [39 empty] | 1411 | -80.3908 |  | 1411 | -80.3908 |  | 1411 | -80.3908
H - Phjl Hejtzenroeder | Job: 1416 - Mod Cojl Type AB Fnl Dsn-WjLLjAMSON | 130.63 | 4 | 29 | 55 | 15.1533 | 0.046734 | 0.632 | 8.8077 | 17.3737 | 0.6166 | [56 empty] | 88 | 103.1533 | 103.2 | 103.832 | 112.6397 | 130.0134 | 130.63 | [39 empty] | 1416 | 103.5594 |  | 1416 | 112.6397 |  | 1416 | 130.0134
H - Phjl Hejtzenroeder | Job: 1421 - Mod Cojl jnterface Desjgn-WjLLjAMSON | 1151.36 | 62 | 167 | 406 | 76.1819 | 30.1181 | 199.194 | 93.3288 | 75.1282 | 42.409 | [56 empty] | 635 | 711.1819 | 741.3 | 940.494 | 1033.8228 | 1108.951 | 1151.36 | [39 empty] | 1421 | 940.2338 |  | 1421 | 1033.8228 |  | 1421 | 1108.9513
H - Phjl Hejtzenroeder | Job: 1429 - MC jnterface R&D-GETTELFjNGER | 93.78 | 30 |  | 44 | 9.2365 | -9.2365 | 4.065 | 0.25992 | 15.4595 | -0.00444 | [56 empty] | 74 | 83.2365 | 74 | 78.065 | 78.3249 | 93.7844 | 93.78 | [39 empty] | 1429 | 78.0654 |  | 1429 | 78.3249 |  | 1429 | 93.7844
H - Phjl Hejtzenroeder | Job: 1501 - Cojl Structures Desjgn-DAHLGREN | 148.25 | 2 | 43 | 30 | 6.9424 | 54.7576 | 8.301 | 0.19791 | 3.0513 | -0.0002 | [56 empty] | 75 | 81.9424 | 136.7 | 145.001 | 145.1989 | 148.2502 | 148.25 | [39 empty] | 1501 | 145.0015 |  | 1501 | 145.1989 |  | 1501 | 148.2502
H - Phjl Hejtzenroeder | Job: 1550 - Cojl Struct. Procurement -DAHLGREN | 19.62 |  |  |  | 0 | 0 | 0 | 0 | 0 | 19.62 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | 19.62 | [39 empty] | 1550 | 0 |  | 1550 | 0 |  | 1550 | 0
H - Phjl Hejtzenroeder | Job: 1601 - Cojl Servjces Desjgn-GORANSON | 56.79 |  | 6 |  | 0.2288 | 8.3712 | -0.002 | 8.3698 | 19.002 | 14.8203 | [56 empty] | 6 | 6.2288 | 14.6 | 14.598 | 22.9678 | 41.9697 | 56.79 | [39 empty] | 1601 | 14.5983 |  | 1601 | 22.9678 |  | 1601 | 41.9698
H - Phjl Hejtzenroeder | Job: 1701 - Cryostat Desjgn-GETTLEFjNGER | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 1701 | 0 |  | 1701 | 0 |  | 1701 | 0
H - Phjl Hejtzenroeder | Job: 1702 - Base Support Struct Desjgn-DAHLGREN | 96.49 |  |  |  | 0 | 10.83 | 0.26 | -0.022104 | 29.5144 | 55.9077 | [56 empty] | 0 | 0 | 10.83 | 11.09 | 11.0679 | 40.5823 | 96.49 | [39 empty] | 1702 | 11.0903 |  | 1702 | 11.0679 |  | 1702 | 40.5563
H - Phjl Hejtzenroeder | Job: 1751 - Cryostat Procurement-GETTLEFjNGER | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 1751 | 0 |  | 1751 | 0 |  | 1751 | 0
H - Phjl Hejtzenroeder | Job: 1752 - Base Support Proc-DAHLGREN | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 1752 | 0 |  | 1752 | 0 |  | 1752 | 0
H - Phjl Hejtzenroeder | Job: 1806 - FP Assembly specs | 128.02 |  | 3 | 22 | 2.7447 | 8.4053 | 3.688 | 66.2942 | 11.3172 | 10.5706 | [56 empty] | 25 | 27.7447 | 36.15 | 39.838 | 106.1322 | 117.4494 | 128.02 | [39 empty] | 1806 | 39.8389 |  | 1806 | 106.1322 |  | 1806 | 117.4586
H - Phjl Hejtzenroeder | Job: 1901 - Stellarator Core Mngtt&jntegr-COLE | 292.65 | 34 | 32 | 32 | 34.6417 | 28.9183 | 37.571 | 33.0795 | 24.5027 | 35.9368 | [56 empty] | 98 | 132.6417 | 161.56 | 199.131 | 232.2105 | 256.7132 | 292.65 | [39 empty] | 1901 | 199.1319 |  | 1901 | 232.2105 |  | 1901 | 256.7132
H - Phjl Hejtzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Support-REjERSEN | 554.64 | 108 | 100 | 87 | -5.797 | 53.257 | 60.64 | 53.7854 | 39.6798 | 58.0748 | [56 empty] | 295 | 289.203 | 342.46 | 403.1 | 456.8854 | 496.5652 | 554.64 | [39 empty] | 8202 | 403.1012 |  | 8202 | 456.8854 |  | 8202 | 496.5652
H - Phjl Hejtzenroeder | Job: 8203 - Desjgn jntegratjon-BROWN | 280.12 | 31 | 29 | 29 | 41.9084 | 29.5616 | 33.7811 | 30.9676 | 22.5219 | 32.3794 | [56 empty] | 89 | 130.9084 | 160.47 | 194.2511 | 225.2187 | 247.7406 | 280.12 | [39 empty] | 8203 | 194.2511 |  | 8203 | 225.2187 |  | 8203 | 247.7406
H - Phjl Hejtzenroeder | Job: 8204 - Systems Analysjs-BROOKS | 275.4 | 35 | 34 | 34 | 44.9102 | 33.0398 | 26.361 | 24.1614 | 17.5719 | 26.3557 | [56 empty] | 103 | 147.9102 | 180.95 | 207.311 | 231.4724 | 249.0443 | 275.4 | [39 empty] | 8204 | 207.311 |  | 8204 | 231.4724 |  | 8204 | 249.0443
H - Phjl Hejtzenroeder | Job: 8205 - Djmensjonal Control Coordjn-ELLjS | 102.51 |  | 21 | 21 | 33.2674 | 0.73264 | 11.581 | 13.188 | 1.7289 | 0.0121 | [56 empty] | 42 | 75.2674 | 76 | 87.581 | 100.769 | 102.4979 | 102.51 | [39 empty] | 8205 | 87.9122 |  | 8205 | 100.769 |  | 8205 | 102.4979
H - Phjl Hejtzenroeder | Job: 8210 - FY07 Rebaseljng tasks | 18.81 | 15 | 4 |  | -0.1858 | -0.0042 | 0.004 | 0.0002 | 0 | -0.0042 | [56 empty] | 19 | 18.8142 | 18.81 | 18.814 | 18.8142 | 18.8142 | 18.81 | [39 empty] | 8210 | 18.8142 |  | 8210 | 18.8142 |  | 8210 | 18.8142
H - Phjl Hejtzenroeder | Job: 8215 Plant Desjgn | 10.25 |  |  |  | 0 | 0 | 3 | 2.4974 | 1.9029 | 2.8497 | [56 empty] | 0 | 0 | 0 | 3 | 5.4974 | 7.4003 | 10.25 | [39 empty] | 8215 | 2.9601 |  | 8215 | 5.4974 |  | 8215 | 7.4003
| Total Phjl Hejtzenroeder | 3996.09 | 300 | 517 | 729 | 392.6461 | 330.0539 | 453.4431 | 369.2287 | 419.0378 | 485.6804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 1546 | 1938.6461 | 2268.7 | 2722.1431 | 3091.3718 | 3510.4096 | 3996.09 | [38 empty] | H Total |  | 2722.1059 |  |  |  | H Total |  | 3510.3931
V - Al vonHalle | Job: 4101 - AC Power-RAMAKRjSHNAN | -104.1 | -104 |  |  | -0.1 | 0 | 0 | 0 | 0 | 0 | [56 empty] | -104 | -104.1 | -104.1 | -104.1 | -104.1 | -104.1 | -104.1 | [38 empty] | V | 4101 | -104.1 | V | 4101 | -104.1 | V | 4101 | -104.1
V - Al vonHalle | Job: 4301 - DC Systems-RAMAKRjSHNAN | 3.52 |  |  |  | 0 | 0 | 0 | 1.8943 | 0.65573 | 0.97 | [56 empty] | 0 | 0 | 0 |  | 1.8943 | 2.55 | 3.52 | [39 empty] | 4301 | 1.0132 |  | 4301 | 1.8943 |  | 4301 | 2.5551
V - Al vonHalle | Job: 4401 - Control & Protectjon-RAMAKRjSHNAN | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 4401 | 0 |  | 4401 | 0 |  | 4401 | 0
V - Al vonHalle | Job: 4501 - Power Sys Dsn & jntegr-RAMAKRjSHNAN | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 4501 | 0 |  | 4501 | 0 |  | 4501 | 0
V - Al vonHalle | Job: 5101 - Network and Fjber | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 5101 | 0 |  | 5101 | 0 |  | 5101 | 0
V - Al vonHalle | Job: 5201 - j&C Systems-SjCHTA | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 5201 | 0 |  | 5201 | 0 |  | 5201 | 0
V - Al vonHalle | Job: 5301 - Data Acqujsjtjon-SjCHTA | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 5301 | 0 |  | 5301 | 0 |  | 5301 | 0
V - Al vonHalle | Job: 5401 - Facjljty Tjmjng & | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 5401 | 0 |  | 5401 | 0 |  | 5401 | 0
V - Al vonHalle | Job: 5501 - Real Tjme Control | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 5501 | 0 |  | 5501 | 0 |  | 5501 | 0
V - Al vonHalle | Job: 5601 - Central Safety &jnterlock Sys-SjCHTA | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 5601 | 0 |  | 5601 | 0 |  | 5601 | 0
V - Al vonHalle | Job: 5801 - Central j&C jntegr& Oversjght-SjCHTA | 14.75 | 1 | 1 | 1 | 2.7232 | 1.2568 | 2.32 | 1.8814 | 1.4464 | 2.1221 | [56 empty] | 3 | 5.7232 | 6.98 | 9.3 | 11.1814 | 12.6279 | 14.75 | [39 empty] | 5801 | 9.2529 |  | 5801 | 11.1814 |  | 5801 | 12.6279
V - Al vonHalle | Job: 8501 - jntegrated Systems Testjng-GENTjLE | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 0 | 0 | 0 |  | 0 | 0 | [40 empty] | 8501 | 0 |  | 8501 | 0 |  | 8501 | 0
| Total Al vonHalle | -85.83 | -103 | 1 | 1 | 2.6232 | 1.2568 | 2.32 | 3.7757 | 2.1022 | 3.0921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | -101 | -98.3768 | -97.12 | -94.8 | -91.0243 | -88.9221 | -85.83 | [38 empty] | V Total |  | -93.8339 | Grand Total |  | 8027.3488 | V Total |  | -88.9171
[119 empty] | Grand Total |  | 9036.7584
|  | 8088.9736 | 421 | 1271 | 1494 | 1243.0134 | 1125.2471 | 1495.2866 | 1039.4265 | 926.2202 | 1055.9762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3186 | 4429.0134 | 5554.2605 | 7049.5471 | 8088.9736 | 9015.1938 | 10071.17 | [38 empty] | Grand Total |  | 7050.6268 |  |  |  | 0
0
0
0
0
0
0
0
corrected
corrected

## critical path watch list
Total Float Trend (float in days/monthly status period)
(schedule slippage trends)
Schedule Total Float (work days)
FDR Forecast Date = |  |  |  | July | Aug | Sept | Oct | Nov
2/5/2008 | FDR Forecast Date =2/5/2008 |  | Job: 1302 - PF Design -KALISH | 87 | 75 | 72 | 49 | 54
4/17/2008 | FDR Forecast Date =4/17/2008 |  | Job: 1354 - Trim Coil Design &Procurement-KALISH | 13 | 13 | 13 | 15 | -11
5/23/2008 | FDR Forecast Date =5/23/2008 |  | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 86 | 86 | 86 | 83 | 83
3/6/2008 | FDR Forecast Date =3/6/2008 |  | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 65 | 56 | 37 | -2 | 24
11/27/2007 | FDR Forecast Date =11/27/2007 |  | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 0 | -23 | -57 | -38 | -37
|  |  | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 16 | 15 | -24 | -39 | -39
|  |  | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 14 | 13 | -10 | -18
12/7/2007 | FDR Forecast Date =12/7/2007 |  | Job: 1501 - Coil Structures Design-DAHLGREN | 56 | 17 | 110 | 110 | 106
Job: 1601 - Coil Services Design-GORANSON
8/10/2009 | FDR Forecast Date =8/10/2009 |  | Job: 1701 - Cryostat Design-GETTLEFINGER | 49 | 49 | 49 | 49 | 49
4/28/2008 | FDR Forecast Date =4/28/2008 |  | Job: 1702 - Base Support Struct Design-DAHLGREN | 38 | 22 | 0 | 0 | 32
Job: 1803/1805- FPA Tooling/Constr-BROWN -
|  |  | Job: 1803/1805- FPA Tooling/Constr-BROWN -Station 3 | 39 | 17 | 56 | 23 | -34
2/19/2008 | FDR Forecast Date =2/19/2008 |  | Job: 1803/1805- FPA Tooling/Constr-BROWN -Station 5 | 122 | 144 | 44 | 69 | 69
6/4/2008 | FDR Forecast Date =6/4/2008 |  | Job: 1803/1805- FPA Tooling/Constr-BROWN -Station 6 | 69 | 69 | 69 | 69 | 69
Job: 1806 - FP Assembly specs-COLE-
|  |  | Job: 1806 - FP Assembly specs-COLE-Station 2 | 0 | -23 | -35 | -28 | -23
|  |  | Job: 1806 - FP Assembly specs-COLE-Station 3 | 28 | 28 | 28 | 10 | -8
|  |  | Job: 1806 - FP Assembly specs-COLE-Station 5 | 92 | 97 | 97 | 80 | 57
|  |  | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 0 | -23 | -57 | -39 | -39
Total Float Trend (float in days/monthly status period)

## bottoms-up ETC
JJJJ | DESCRIPTION | Project cost to date (thru Jan 31,2008) | Feb1st through Sep30 FY08 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | ETC | EAC
1 | Job: 8101 - Project Management &Control-ANDERSON |  | 1021 | 1288 | 1170 | 1006 | 750 | 5235 | 5235
1 | Job: 8102 - NCSX MIE Management ORNL-LYON |  | 258 | 298 | 312 | 325 | 255 | 1448 | 1448
1 | Job: 8998 - Allocations-STRYKOWSKY |  | 369 | 460 | 489 | 514 | 286 | 2118 | 2118
2 | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK |  | 122 |  | 185 |  |  | 307 | 307
2 | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | [6 empty] | 0 | 0
2 | Job: 1260 NB Transition Ducts- GORANSON |  | 63 | 433 |  |  |  | 496 | 496
2 | Job: 1270 - Heater Control System-GORANSON |  |  | 500 |  |  |  | 500 | 500
2 | Job: 1408 - MC Winding Supplies-CHRZANOWSKI |  | 186 |  |  |  |  | 186 | 186
2 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK |  | 728 |  | 17 |  |  | 745 | 745
2 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI |  | 1723 |  |  |  |  | 1723 | 1723
2 | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  | 388 | 4 |  |  |  | 392 | 392
2 | Job: 1802 - FP Assy Oversight&Support-VIOLA |  | 840 | 1085 | 1030 |  |  | 2955 | 2955
2 | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK |  | 485 | 359 | 396 | 407 | 330 | 1977 | 1977
2 | Job: 1810 -Field Period Assy -Station 1 2 3 VIOLA |  | 4320 | 3412 | 1526 |  |  | 9258 | 9258
2 | Job: 1815 - Field Period Assy |  |  | 644 | 2116 |  |  | 2760 | 2760
2 | Job: 2101 - Fueling Systems-BLANCHARD |  |  | 12 | 55 |  |  | 67 | 67
2 | Job: 2201 - Vacuum Pumping Systems-BLANCHARD |  |  | 68 | 99 |  |  | 167 | 167
2 | Job: 3101 - Magnetic Diagnostics-STRATTON |  | 338 | 128 | 20 | 1 |  | 487 | 487
2 | Job: 3601 - Edge Divertor Diagnostics-STRATTON |  |  |  | 30 |  |  | 30 | 30
2 | Job: 3801 - Electron Beam Mapping-STRATTON |  |  | 171 | 84 |  |  | 255 | 255
2 | Job: 3901 - Diagnostics sys Integration-STRATTON |  | 29 | 30 | 31 | 32 |  | 122 | 122
2 | Job: 6101 - Water Systems-DUDEK |  |  | 107 |  |  |  | 107 | 107
2 | Job: 6201 - Cryogenic Syst-RAFTOPOLOUS |  |  | 273 | 363 |  |  | 636 | 636
2 | Job: 6301 - Utility Systems-DUDEK |  |  | 102 |  |  |  | 102 | 102
2 | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH |  |  | 117 | 496 |  |  | 613 | 613
2 | Job: 7301 - Platform Design & |  | 10 | 205 |  |  |  | 215 | 215
2 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY |  | 27 | 30 | 665 | 1166 | 734 | 2622 | 2622
2 | Job: 7501 - Construction Support Crew-PERRY |  |  |  | 350 | 853 | 568 | 1771 | 1771
2 | Job: 7503 - Machine Assembly (station 6)-PERRY |  |  |  | 1050 | 1755 | 2287 | 5092 | 5092
2 | Job: 7601 - Tooling Design & Fabrication-PERRY |  |  |  | 121 | 172 | 111 | 404 | 404
3 | Job: 1302 - PF Design -KALISH |  | 187 |  |  |  |  | 187 | 187
3 | Job: 1352 - PF Coil Procurement-CHRZANOWSKI |  | 1115 | 443 | 28 |  |  | 1586 | 1586
3 | Job: 1353 - CS Structure Procurement-DAHLGREN |  | 26 | 49 | 241 |  |  | 316 | 316
3 | Job: 1354 - Trim Coil Design &Procurement-KALISH |  | 846 | 991 |  |  |  | 1837 | 1837
3 | Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE |  | 69 | 39 | 2 |  |  | 110 | 110
3 | Job: 1361 - TF Fabrication-KALISH |  | 761 |  |  |  |  | 761 | 761
3 | Job: 1404 - MCWF R&D 1st Prod | [6 empty] | 0 | 0
3 | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | [6 empty] | 0 | 0
3 | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON |  | 172 | 7 |  |  |  | 179 | 179
3 | Job: 1421 - Mod Coil Interface Design-WILLIAMSON |  | 440 |  |  |  |  | 440 | 440
3 | Job: 1429 - MC Interface R&D-DUDEK |  | 61 |  |  |  |  | 61 | 61
3 | Job: 1501 - Coil Structures Design-DAHLGREN |  | 81 |  |  |  |  | 81 | 81
3 | Job: 1550 - Coil Struct. Procurement -DAHLGREN |  | 443 | 593 |  |  |  | 1036 | 1036
3 | Job: 1601 - Coil Services Design-GORANSON |  | 426 | 664 | 100 |  |  | 1190 | 1190
3 | Job: 1701 - Cryostat Design-RAFTOPOLOUS |  |  | 202 |  |  |  | 202 | 202
3 | Job: 1702 - Base Support Struct Design-DAHLGREN |  | 122 |  |  |  |  | 122 | 122
3 | Job: 1751 - Cryostat Procurement-RAFTOPOLOUS |  |  |  | 313 |  |  | 313 | 313
3 | Job: 1752 - Base Support Proc-DAHLGREN |  | 84 | 3 |  |  |  | 87 | 87
3 | Job: 1806 - FP Assembly specs |  | 431 | 44 |  |  |  | 475 | 475
3 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE |  | 393 | 407 | 433 | 437 | 351 | 2021 | 2021
3 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN |  | 709 | 780 | 792 | 741 | 543 | 3565 | 3565
3 | Job: 8203 - Design Integration-BROWN |  | 310 | 727 | 748 | 626 | 508 | 2919 | 2919
3 | Job: 8204 - Systems Analysis-BROOKS |  | 545 | 412 | 155 | 11 |  | 1123 | 1123
3 | Job: 8205 - Dimensional Control Coordin-ELLIS |  | 143 | 244 | 126 | 42 | 27 | 582 | 582
3 | Job: 8210 - FY07 Rebaseling tasks | [6 empty] | 0 | 0
3 | Job: 8215 Plant Design |  | 47 | 31 | 31 | 10 |  | 119 | 119
4 | Job: 4101 - AC Power-RAMAKRISHNAN |  |  | 54 | 97 |  |  | 151 | 151
4 | Job: 4301 - DC Systems-RAMAKRISHNAN |  | 11 | 261 | 301 |  |  | 573 | 573
4 | Job: 4401 - Control & Protection-RAMAKRISHNAN |  |  | 298 | 734 |  |  | 1032 | 1032
4 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN |  |  | 433 | 107 | 334 |  | 874 | 874
4 | Job: 5101 - Network and Fiber |  |  | 80 | 135 |  |  | 215 | 215
4 | Job: 5201 - I&C Systems-SICHTA |  |  | 193 | 209 |  |  | 402 | 402
4 | Job: 5301 - Data Acquisition-SICHTA |  |  | 79 | 83 |  |  | 162 | 162
4 | Job: 5401 - Facility Timing & |  |  | 40 | 313 |  |  | 353 | 353
4 | Job: 5501 - Real Time Control |  |  | 253 | 235 |  |  | 488 | 488
4 | Job: 5601 - Central Safety &Interlock Sys-SICHTA |  |  | 86 | 278 |  |  | 364 | 364
4 | Job: 5801 - Central I&C Integr& Oversight-SICHTA |  | 22 | 17 | 17 |  |  | 56 | 56
4 | Job: 8501 - Integrated Systems Testing-GENTILE |  |  | 275 | 70 |  | 444 | 789 | 789
|  | 0 | 18351 | 17431 | 16153 | 8432 | 7194 | 67561 | 67561
| Contingency-Project |  | 2205 | 3494 | 3837 | 2300
Actual Cost

## COST PERFORMANCE BY RLM & JOB
NCSX Cost Performance Report
Period May 1, 2007 through January 31, 2008
(Measured against unofficial proposed baseline)
|  | CUMULATIVE | [6 empty] | MONTHLY
RLM | JOB | BCWS | BCWP | ACWP | SPI | CPI | schedule variance | cost variance | BCWS | BCWP | ACWP | SPI | CPI | sched variance | cost variance | BUDGET to COMPLETE (from May 1,2007) | % plan | % work completed | % spent | ETC (bottoms-up) from 2/1/08 | Bottoms upEAC | increase (w-r) | Last month EAC |  | increase/ (decrease) |  |  | nov-dec etc growth
Don Rej | Job: 8101 - Project Management &Control-REJ | 567.8 | 542.41 | 486.2368 | 0.95528 | 1.1155 | -25.39 | 56.1732 | 66.5 | 81.754 | 52.458 | 1.2294 | 1.5585 | 15.254 | 29.296 | 3843 | 14.77% | 14.11% | 12.65% | 4804 | 5290.2368 | 1447.2368 | 4158 | Prelim RL WAF | 315 |  |  | 0
| Job: 8102 - NCSX MIE Management ORNL-HARRIS | 112 | 111.46 | 166.959 | 0.99518 | 0.66759 | -0.54 | -55.499 | 13 | 12.879 | 12.535 | 0.99069 | 1.0274 | -0.121 | 0.344 | 499 | 22.44% | 22.34% | 33.46% | 1300 | 1466.959 | 967.959 | 545 | Prelim RL WAF | 46 |  |  | 46
| Job: 8998 - Allocations-STRYKOWSKY | 269 | 276.43 | 372.0318 | 1.0276 | 0.74303 | 7.43 | -95.6018 | 31 | 32.596 | 78.1 | 1.0515 | 0.41736 | 1.596 | -45.504 | 1453 | 18.51% | 19.02% | 25.6% | 2118 | 2490.0318 | 1037.0318 | 1536 | Prelim RL WAF | 83 |  |  | 0
| Total Don Rej | 948.8 | 930.3 | 1025.2276 | 0.9805 | 0.90741 | -18.5 | -94.9276 | 110.5 | 127.229 | 143.093 | 1.1514 | 0.88914 | 16.729 | -15.864 | 5795 | 0.55733 | 0.55476 | 0.71716 | 8222 | 9247.2276 |  | 6239 |  | 444
[8 empty] | #REF! | [6 empty] | 0 | [12 empty] | 0
0
Larry Dudek | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 104 | 172.03 | 241.8109 | 1.6541 | 0.71142 | 68.03 | -69.7809 | 29 | 21.8115 | 19.061 | 0.75212 | 1.1443 | -7.1885 | 2.7505 | 408 | 25.49% | 42.16% | 59.27% | 235.97 | 477.7809 | 69.7809 | 916 | input received not input or analyzed | 508 |  | 203.2 | 0
| Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -252 | -251.69 | -251.7703 | 0.99877 | 0.99968 | 0.31 | 0.0803 | 0 | 0.00028 | 0 | #DIV/0! | #DIV/0! | 0.00028 | 0.00028 | -252 | 100% | 99.88% | 99.91% | 0 | -251.7703 | 0.2297 | -252 | closed | 0 |  |  | 0
| Job: 1260 NB Transition Ducts- GORANSON | [18 empty] | 496 | 496 | 496 |  | Prelim RL WAF |  | scope add-back
| Job: 1270 - Heater Control System-GORANSON | [18 empty] | 500 | 500 | 500 |  | missing WAF input
| Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 294 | 267.34 | 144.6134 | 0.90932 | 1.8487 | -26.66 | 122.7266 | 22 | 22.4543 | 11.699 | 1.0207 | 1.9193 | 0.45431 | 10.7553 | 350 | 84% | 76.38% | 41.32% | 186 | 330.6134 | -19.3866 | 281.6134 | input received not input or analyzed | -68.3866 |  |  | -68.3866
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 926 | 788.18 | 471.1149 | 0.85117 | 1.673 | -137.82 | 317.0651 | 64 | 45.9104 | 66.906 | 0.71735 | 0.68619 | -18.0896 | -20.9956 | 1039 | 89.12% | 75.86% | 45.34% | 745 | 1216.1149 | 177.1149 | 975 | input received not input or analyzed | -64 |  |  | -64 |  | 92449
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1713 | 1916.44 | 1694.4647 | 1.1188 | 1.131 | 203.44 | 221.9753 | 188 | 106.8135 | 191.385 | 0.56816 | 0.55811 | -81.1865 | -84.5715 | 2867 | 59.75% | 66.84% | 59.1% | 1173 | 2867.4647 | 0.46469 | 2534.9243 | input received not input or analyzed | -332.0757 |  |  | -332.0757 |  | 115418
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 258 | 305.07 | 427.645 | 1.1824 | 0.71337 | 47.07 | -122.575 | 43 | 114.6577 | 30.823 | 2.6665 | 3.7199 | 71.6577 | 83.8347 | 501 | 51.5% | 60.89% | 85.36% | 392 | 819.645 | 318.645 | 755.645 | input received not input or analyzed | 254.645 |  |  | 9.645 |  | 92448
| Job: 1802 - FP Assy Oversight&Support-VIOLA | 496 | 425.71 | 519.7007 | 0.85829 | 0.81914 | -70.29 | -93.9907 | 58 | 47.0231 | 56.159 | 0.81074 | 0.83732 | -10.9769 | -9.1359 | 1989 | 24.94% | 21.4% | 26.13% | 2955 | 3474.7007 | 1485.7007 | 3036.7007 | Prelim RL WAF | 1047.7007 |  |  | 1047.7007
| Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 300 | 85.14 | 282.9039 | 0.2838 | 0.30095 | -214.86 | -197.7639 | 24 | 0.22777 | 23.077 | 0.0094903 | 0.0098698 | -23.7722 | -22.8492 | 522 | 57.47% | 16.31% | 54.2% | 1786 | 2068.9039 | 1546.9039 | 522 | Prelim RL WAF | 0 |  |  | 0 |  | 92447 | 115417
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 2035.45 | 1672.87 | 1261.8701 | 0.82187 | 1.3257 | -362.58 | 410.9999 | 185.57 | 130.0196 | 160.367 | 0.70065 | 0.81076 | -55.5504 | -30.3474 | 5745 | 35.43% | 29.12% | 21.96% | 9258 | 10519.8701 | 4774.8701 | 8510.8701 | Prelim RL WAF | 2765.8701 |  |  | 2665.8701
| Job: 1815 - Field Period Assy Station 5 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1334 | 0% | 0% | 0% | 2760 | 2760 | 1426 | 1570 | Prelim RL WAF | 236 |  |  | 236
| Job: 2101 - Fueling Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 69 | 0% | 0% | 0% | 67 | 67 | -2 | 258 | Prelim RL WAF | 189 | scope add-back | 75.6 | 0
| Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 172 | 0% | 0% | 0% | 167 | 167 | -5 | 575 | Prelim RL WAF | 403 | scope add-back | 161.2 | 0
| Job: 3101 - Magnetic Diagnostics-STRATTON | 289 | 127.16 | 142.0566 | 0.44 | 0.89514 | -161.84 | -14.8966 | 24 | 46.0682 | 1.346 | 1.9195 | 34.226 | 22.0682 | 44.7222 | 291 | 99.31% | 43.7% | 48.82% | 487 | 629.0566 | 338.0566 | 326 | Prelim RL WAF | 35 | scope add-back | 14 | 0
| Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 31 | 0% | 0% | 0% | 30 | 30 | -1 | 31 | Prelim RL WAF | 0 |  |  | 0
| Job: 3801 - Electron Beam Mapping-STRATTON | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 263 | 0% | 0% | 0% | 255 | 255 | -8 | 263 | Prelim RL WAF | 0 |  |  | 0
| Job: 3901 - Diagnostics sys Integration-STRATTON | 21 | 20.74 | 34.4082 | 0.98762 | 0.60276 | -0.26 | -13.6682 | 2.2 | 2.3679 | 4.292 | 1.0763 | 0.55171 | 0.16794 | -1.9241 | 132 | 15.91% | 15.71% | 26.07% | 122 | 156.4082 | 24.4082 | 218.9915 | Prelim RL WAF | 86.9915 |  |  | 0.018305
| Job: 6101 - Water Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 46 | 0% | 0% | 0% | 107 | 107 | 61 | 95 | Prelim RL WAF | 49 | scope add-back | 19.6 | 0
| Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 655 | 0% | 0% | 0% | 655 | 655 | 0 | 655 | missing input | 0 |  |  | 0
| Job: 6301 - Utility Systems-DUDEK | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 105 | 0% | 0% | 0% | 102 | 102 | -3 | 105 | Prelim RL WAF | 0 |  |  | 0
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 573 | 0% | 0% | 0% | 613 | 613 | 40 | 573 | Prelim RL WAF | 0 |  |  | 0
| Job: 7301 - Platform Design & | 0 | 2.63 | 0 | #DIV/0! | #DIV/0! | 2.63 | 2.63 | 0 | 0.019634 | 0 | #DIV/0! | #DIV/0! | 0.019634 | 0.019634 | 204 | 0% | 1.289% | 0% | 215 | 215 | 11 | 204 | Prelim RL WAF | 0 |  |  | 0
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -301 | -301.01 | -255.0753 | 1 | 1.1801 | -0.01 | -45.9347 | 2 | 1.8192 | 6.801 | 0.90959 | 0.26749 | -0.18082 | -4.9818 | 1417 | -21.24% | -21.24% | -18% | 2239 | 1983.9247 | 566.9247 | 1417 | Prelim RL WAF | 0 |  |  | 0
| Job: 7501 - Construction Support Crew-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1407 | 0% | 0% | 0% | 1446 | 1446 | 39 | 1407 | Prelim RL WAF | 0 |  |  | 0
| Job: 7503 - Machine Assembly (station 6)-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 4511 | 0% | 0% | 0% | 5092 | 5092 | 581 | 4603 | Prelim RL WAF | 92 | scope add-back | 36.8 | 0
| Job: 7601 - Tooling Design & Fabrication-PERRY | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 412 | 0% | 0% | 0% | 404 | 404 | -8 | 412 | Prelim RL WAF | 0 |  |  | 0
| Total Larry Dudek | 5883.45 | 5230.61 | 4713.7428 | 0.88904 | 1.1097 | -652.84 | 516.8672 | 641.77 | 539.1931 | 571.916 | 0.84017 | 0.94278 | -102.5769 | -32.7229 | 24791 | 6.2168 | 5.2831 | 5.4947 | 32487.97 | 37201.7128 |  | 29993.745 |  | 5202.745
[15 empty] | 0 | [12 empty] | 0
Phil Heitzenroeder | Job: 1302 - PF Design -KALISH | 182 | 180.73 | 77.033 | 0.99302 | 2.3461 | -1.27 | 103.697 | 25 | 0.50959 | 7.747 | 0.020384 | 0.065779 | -24.4904 | -7.2374 | 257 | 70.82% | 70.32% | 29.97% | 180 | 257.033 | 0.033003 | 109.5418 | missing input | -147.4582 |  |  | -147.4582
| Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 0 | 0 | 7.832 | #DIV/0! | 0 | 0 | -7.832 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1630 | 0% | 0% | 0.4805% | 1622 | 1629.832 | -0.168 | 1630 | missing input | 0 |  |  | 0
| Job: 1353 - CS Structure Procurement-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 337 | 0% | 0% | 0% | 337 | 337 | 0 | 337 | input received not input or analyzed | 0 |  |  | 0
| Job: 1354 - Trim Coil Design &Procurement-KALISH | 145.7 | 124.91 | 49.246 | 0.85731 | 2.5364 | -20.79 | 75.664 | 29.6 | 1.4861 | 8.422 | 19.9182 | 0.17645 | -28.1139 | -6.9359 | 162 | 89.94% | 77.1% | 30.4% | 1837 | 1886.246 | 1724.246 | 1552 | input received not input or analyzed | 1390 | scope add-back | 556 | 36
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 73 | 0% | 0% | 0% | 110 | 110 | 37 | 169 | input received not input or analyzed | 96 |  |  | 96
| Job: 1361 - TF Fabrication-KALISH | 463 | 447.46 | 471.5475 | 0.96644 | 0.94892 | -15.54 | -24.0875 | 59 | 32.318 | 44.653 | 0.54776 | 0.72376 | -26.682 | -12.335 | 1003 | 46.16% | 44.61% | 47.01% | 531 | 1002.5475 | -0.45247 | 1003 | input received not input or analyzed | 0 |  |  | 0
| Job: 1404 - MCWF R&D 1st Prod | -36 | -35.94 | -34.9474 | 0.99833 | 1.0284 | 0.06 | -0.99262 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | -36 | 100% | 99.83% | 97.08% | 0 | -34.9474 | 1.0526 | -36 | closed | 0 |  |  | 0
| Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -84 | -80.39 | -65.1126 | 0.95702 | 1.2346 | 3.61 | -15.2774 | 0 | -0.0008 | 0 | 0 | #DIV/0! | -0.0008 | -0.0008 | -80 | 105% | 100.5% | 81.39% | 0 | -65.1126 | 14.8874 | -80 | closed | 0 |  |  | 0
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 278 | 130.63 | 184.2659 | 0.46989 | 0.70892 | -147.37 | -53.6359 | 56 | 8.8077 | 34.792 | 0.15728 | 0.25315 | -47.1923 | -25.9843 | 280 | 99.29% | 46.65% | 65.81% | 179 | 363.2659 | 83.2659 | 333.6359 | input received not input or analyzed | 53.6359 |  |  | 53.6359
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1184 | 1151.36 | 1062.0957 | 0.97243 | 1.084 | -32.64 | 89.2643 | 26 | 93.3288 | 94.52 | 3.5896 | 0.9874 | 67.3288 | -1.1912 | 1207 | 98.09% | 95.39% | 87.99% | 440 | 1502.0957 | 295.0957 | 1117.7357 | input received not input or analyzed | -89.2643 |  |  | -89.2643
| Job: 1429 - MC Interface R&D-GETTELFINGER | 118 | 93.78 | 87.6232 | 0.79475 | 1.0703 | -24.22 | 6.1568 | 0 | 0.25992 | 0.671 | 0 | 0.38737 | 0.25992 | -0.41108 | 118 | 100% | 79.47% | 74.26% | 61 | 148.6232 | 30.6232 | 110.2531 | input received not input or analyzed | -7.7469 |  |  | -7.7469
| Job: 1501 - Coil Structures Design-DAHLGREN | 186 | 148.25 | 209.5641 | 0.79704 | 0.70742 | -37.75 | -61.3141 | 0 | 0.19791 | 23.081 | #DIV/0! | 0.0085744 | 0.19791 | -22.8831 | 186 | 100% | 79.7% | 112.7% | 81 | 290.5641 | 104.5641 | 262.927 | input received not input or analyzed | 76.927 |  |  | 76.927
| Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 19.62 | 0 | #DIV/0! | #DIV/0! | 19.62 | 19.62 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1076 | 0% | 1.823% | 0% | 1036 | 1036 | -40 | 1227 | input received not input or analyzed | 151 |  |  | 151
| Job: 1601 - Coil Services Design-GORANSON | 34 | 56.79 | 0 | 1.6703 | #DIV/0! | 22.79 | 56.79 | 0 | 8.3698 | 0 | 0 | #DIV/0! | 8.3698 | 8.3698 | 861 | 3.949% | 6.596% | 0% | 1190 | 1190 | 329 | 1141 | Prelim RL WAF | 280 | scope add-back | 112 | 0
| Job: 1701 - Cryostat Design-RAFTOPOLOUS | 0 | 0 | 5.2332 | #DIV/0! | 0 | 0 | -5.2332 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 207 | 0% | 0% | 2.528% | 202 | 207.2332 | 0.23322 | 207 | missing input | 0 |  |  | 0
| Job: 1702 - Base Support Struct Design-DAHLGREN | 148 | 96.49 | 52.979 | 0.65196 | 1.8213 | -51.51 | 43.511 | 36 | -0.022104 | -0.857 | -0.00061401 | 0.025793 | -36.0221 | 0.8349 | 163 | 90.8% | 59.2% | 32.5% | 110 | 162.979 | -0.021 | 256 | input received not input or analyzed | 93 |  |  | 93
| Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 325 | 0% | 0% | 0% | 325 | 325 | 0 | 325 | missing input | 0 |  |  | 0
| Job: 1752 - Base Support Proc-DAHLGREN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 89 | 0% | 0% | 0% | 87 | 87 | -2 | 89 | input received not input or analyzed | 0 |  |  | 0
| Job: 1806 - FP Assembly specs | 201 | 128.02 | 6.422 | 0.63692 | 19.9346 | -72.98 | 121.598 | 19 | 66.2942 | 0.883 | 3.4892 | 0.013319 | 47.2942 | 65.4112 | 514 | 39.11% | 24.91% | 1.249% | 475 | 481.422 | -32.578 | 392.402 | input received not input or analyzed | -121.598 |  |  | -121.598
| Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 294 | 292.65 | 188.959 | 0.99541 | 1.5487 | -1.35 | 103.691 | 33 | 33.0795 | 10.79 | 1.0024 | 3.0658 | 0.079538 | 22.2895 | 1620 | 18.15% | 18.06% | 11.66% | 1819 | 2007.959 | 387.959 | 1516.309 | Prelim RL WAF | -103.691 |  |  | 604.1132
| Job: 8202 - Engr Mgmt & Sys Eng Support-HEITZENROEDER | 556 | 554.64 | 537.4581 | 0.99755 | 1.032 | -1.36 | 17.1819 | 53 | 53.7854 | 55.126 | 1.0148 | 0.97568 | 0.78545 | -1.3406 | 2649 | 20.99% | 20.94% | 20.29% | 3243 | 3780.4581 | 1131.4581 | 3149 | Prelim RL WAF | 500 |  |  | 0
| Job: 8203 - Design Integration-BROWN | 282 | 280.12 | 114.137 | 0.99333 | 2.4542 | -1.88 | 165.983 | 30 | 30.9676 | 20.05 | 1.0323 | 1.5445 | 0.96762 | 10.9176 | 1408 | 20.03% | 19.89% | 8.106% | 2619 | 2733.137 | 1325.137 | 1408 | Prelim RL WAF | 0 |  |  | 0
| Job: 8204 - Systems Analysis-BROOKS | 275 | 275.4 | 408.8333 | 1.0015 | 0.67362 | 0.4 | -133.4333 | 24 | 24.1614 | 47.332 | 1.0067 | 0.51047 | 0.16138 | -23.1706 | 1154 | 23.83% | 23.86% | 35.43% | 1123 | 1531.8333 | 377.8333 | 1713.1214 | Prelim RL WAF | 559.1214 |  |  | 120.7838
| Job: 8205 - Dimensional Control Coordin-ELLIS | 180 | 102.51 | 133.7801 | 0.5695 | 0.76626 | -77.49 | -31.2701 | 20 | 13.188 | 17.183 | 0.6594 | 0.76751 | -6.812 | -3.995 | 598 | 30.1% | 17.14% | 22.37% | 582 | 715.7801 | 117.7801 | 780.4166 | Prelim RL WAF | 182.4166 |  |  | 107.9518
| Job: 8210 - FY07 Rebaseling tasks | 18.8 | 18.81 | 55.4465 | 1.0005 | 0.33925 | 0.01 | -36.6365 | 0 | 0.0002 | 7.21 | 0 | 2.7739e-05 | 0.0002 | -7.2098 | 19 | 98.95% | 99% | 291.8% | 0 | 55.4465 | 36.4465 | 56.0066 | closed | 37.0066 |  |  | 1.3859
| Job: 8215 Plant Design | 26 | 10.25 | 0 | 0.39423 | #DIV/0! | -15.75 | 10.25 | 3 | 2.4974 | 0 | 1.2013 | #DIV/0! | -0.50261 | 2.4974 | 121 | 21.49% | 8.471% | 0% | 121 | 121 | 0 | 227 | missing input | 106 |  |  | 0
| Total Phil Heitzenroeder | 4451.5 | 3996.09 | 3552.3957 | 0.8977 | 1.1249 | -455.41 | 443.6943 | 413.6 | 369.2287 | 371.603 | 0.89272 | 0.99361 | -44.3713 | -2.3743 | 15941 | 11.7668 | 9.9348 | 10.5303 | 18310 | 21862.3957 |  | 18996.349 |  | 3055.349 |  | -1670
[17 empty] | #DIV/0! | [10 empty] | 0
0
Al vonHalle | Job: 4101 - AC Power-RAMAKRISHNAN | -104 | -104.1 | -104.1027 | 1.001 | 0.99997 | -0.1 | 0.00269 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 55 | -189.1% | -189.3% | -189.3% | 151 | 46.8973 | -8.1027 | 55.0014 | Prelim RL WAF | 0.0014212 |  |  | 0
| Job: 4301 - DC Systems-RAMAKRISHNAN | 4 | 3.52 | 0 | 0.88 | #DIV/0! | -0.48 | 3.52 | 1 | 1.8943 | 0 | 0.52791 | #DIV/0! | 0.89427 | 1.8943 | 603 | 0.6633% | 0.5837% | 0% | 573 | 573 | -30 | 603 | Prelim RL WAF | 0 |  |  | 0
| Job: 4401 - Control & Protection-RAMAKRISHNAN | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 1084 | 0% | 0% | 0% | 1032 | 1032 | -52 | 1084 | Prelim RL WAF | 0 |  |  | 0
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 0 | 0 | -0.55581 | #DIV/0! | 0 | 0 | 0.55581 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 683 | 0% | 0% | -0.08138% | 874 | 873.4442 | 190.4442 | 833 | Prelim RL WAF | 150 |  |  | 150
| Job: 5101 - Network and Fiber | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 150 | 0% | 0% | 0% | 215 | 215 | 65 | 226 | Prelim RL WAF | 76 | scope add-back | 30.4 | 0
| Job: 5201 - I&C Systems-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 196 | 0% | 0% | 0% | 402 | 402 | 206 | 432 | Prelim RL WAF | 236 | scope add-back | 94.4 | 0
| Job: 5301 - Data Acquisition-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 165 | 0% | 0% | 0% | 162 | 162 | -3 | 179 | Prelim RL WAF | 14 | scope add-back | 5.6 | 0
| Job: 5401 - Facility Timing & | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 205 | 0% | 0% | 0% | 353 | 353 | 148 | 376 | Prelim RL WAF | 171 | scope add-back | 68.4 | 0
| Job: 5501 - Real Time Control | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 129 | 0% | 0% | 0% | 488 | 488 | 359 | 349 | Prelim RL WAF | 220 | scope add-back | 88 | 0
| Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 222 | 0% | 0% | 0% | 364 | 364 | 142 | 387 | Prelim RL WAF | 165 | scope add-back | 66 | 0
| Job: 5801 - Central I&C Integr& Oversight-SICHTA | 14.2 | 14.75 | 0 | 1.0387 | #DIV/0! | 0.55 | 14.75 | 2.1 | 1.8814 | 0 | 1.1162 | #DIV/0! | -0.21856 | 1.8814 | 69 | 20.58% | 21.38% | 0% | 56 | 56 | -13 | 69 | Prelim RL WAF | 0 | scope add-back | 0 | 0 | 882
| Job: 8501 - Integrated Systems Testing-GENTILE | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 765 | 0% | 0% | 0% | 789 | 789 | 24 | 765 | Prelim RL WAF | 0 |  |  | 0
| Total Al vonHalle | -85.8 | -85.83 | -104.6585 | 1.0003 | 0.8201 | -0.03 | 18.8285 | 3.1 | 3.7757 | 0 | 1.218 | #DIV/0! | 0.67571 | 3.7757 | 4326 | #DIV/0! | -1.6731 | -1.8936 | 5459 | 5354.3415 |  | 5358.0014 |  | 1032.0014
[23 empty] | 1313 |  | 1313 |  |  | 808
[23 empty] | -780 |  | -780
| Total project (May 1 through completion) | 11197.95 | 10071.17 | 9186.7076 | 0.89938 | 1.0963 | -1126.78 | 884.4624 | 1168.97 | 1039.4265 | 1086.612 | 0.88918 | 0.95658 | -129.5435 | -47.1855 | 50853 | #DIV/0! | 14.0995 | 14.8485 | 64478.97 | 73665.6776 | 22812.6776 | 61120.0954 |  | 10267.0954 |  | 11047.0954 | 5473.5019 | -138.8
[8 empty] | Contingency = | [7 empty] | 14380 |  |  |  |  | 19343.691 | @ 30% | &30% | on etc from 2/1/08 |  |  | #VALUE!
[8 empty] | Cost through April 30,2007= | [7 empty] | 67178.138 | 0 | 6264 | 16688 |  | 67178.138
[8 empty] | TOTAL TEC = | [7 empty] | 132411.138 |  |  |  |  | 160187.5066 | 27776.3686 |  | increase |  |  | -132411.138
[20 empty] | %bottoms up initially analyzed and resource loaded into schedule= | 77.58% | [5 empty] | 5359.2 | scope add-back and 40% contingency
[27 empty] | 5906.0954 | re-estimate
[24 empty] | 5689.6 | 10267.0954 |  | 1313 | strecthout cost
[23 empty] | 11892.6954 |  |  | 0 | 7219.0954
[22 empty] | 57147.6008 |  |  |  | 9734.0954 | 10267.0954
[8 empty] | EAC Growth = | [7 empty] | 6203.0954
[8 empty] | Scope Add backs= | [7 empty] | 4064
[8 empty] | Contingency on scope add-backs= | [7 empty] | 1625.6
[8 empty] | Projected new baseline = | [7 empty] | 144303.8334 | [5 empty] | 73665.6776
| ornl jobs | 2103 | 1870.91 | 1608.7016 | 0.88964 | 1.163 |  | 262.2084 | 147 | 222.759 | 153.52 | 1.5154 | 1.451 |  | 69.239 | [7 empty] | 61900.0954 |  |  |  | #REF!
| pppl jobs | 9094.95 | 8200.26 | 7578.006 | 0.90163 | 1.0821 |  | 622.254 | 1021.97 | 816.6675 | 933.092 | 0.79911 | 0.87523 |  | -116.4245
|  | 11197.95 | 10071.17 | 9186.7076
|  | 582 | 365.26 | 397.0409 | 0.62759 | 0.91996 | -216.74 | -31.7809
Phil's jobs
| ornl jobs | 1790 | 1631.43 | 1435.3206 | 0.91141 | 1.1366 | -158.57 | 196.1094
| pppl jobs | 2661.5 | 2364.66 | 2117.0751 | 0.88847 | 1.1169 | -296.84 | 247.5849
|  | 4451.5 | 3996.09 | 3552.3957 | 0.8977 | 1.1249 | -455.41 | 443.6943
corrected
corrected

## TOTAL PROJECT REPORT
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
TOTAL PROJECT |  |  |  | Jim Anderson |  | 2007-12-30
Highlights and Progress:
[12 empty] | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 | 2007-10-31 | 2007-12-01 | 2
[12 empty] | INTRF-055 | AB/BC/AA inboard interface - FDR | 1421 | DW | 2007-09-04 | 27NOV07* | 2007-11-01 | 2
Issues (not currently impacting technical, cost, or schedule but being watched): | [11 empty] | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-11 | 2007-12-01 | 2
Problems and work around plans :
Schedule | [7 empty] | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Total float | Group 1
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Float (work days) | task- | 1416-506 | Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 1119 |  |  |  |  | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish | Variance target 1 early finish
Check and promote top-level models/drawings task- 1416-506 | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 1119 | task- | 1803-205 | Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2008-01-09 |  | 1146 |  |  |  |  | 8205 | BE | 01JUN07* | 2007-08-31 | 01JUN07A | 2007-09-21 | -14 | -14
Station 2 Assembly Drawings task- 1803-205 | 1806 | MC | 2007-09-11 | 2008-01-09 |  | 1146 | task- | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-09 | 2007-12-01 | -131 |  |  |  |  | 1806 | MC | 11JUN07* | 2007-09-11 | 11JUN07A | 2007-10-03 | -16 | -16
Shims required for 1st 3 pack MC assy task- S21-5.04X | 1431 | LD | 2007-09-20 | 2008-01-09 | 2007-12-01 | -131 | task- | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-30 |  | 318 |  |  |  |  | 1421 | DW | 2007-07-05 | 2007-07-18 | 25JUN07A | 29JUN07A | 12 | 12
Final Scan of VVSA #3 Station 1 complete task- R1810-1329 | 1810 | MV | 2008-02-06 | 2008-01-30 |  | 318 | task- | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-31 |  | 453 |  |  |  |  | 1806 | MC | 11JUN07* | 2007-09-11 | 01JUL07A | 2007-10-12 | -23 | -23
Mod Coil C-C Joint - FDR task- 1421-3144 | 1421 | DW | 2008-01-07 | 2008-01-31 |  | 453 | task- | 1702-515 | Base support - PDR | 1702 | FD | 2007-11-26 | 2008-01-31 |  | 47 |  |  |  |  | 1416 | DW | 2007-08-01 | 2007-11-21 | 01JUL07A | 2007-11-21 | 0 | 0
Base support - PDR task- 1702-515 | 1702 | FD | 2007-11-26 | 2008-01-31 |  | 47 | task- | METDCP-3 | Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2008-01-31 |  | -75 |  |  |  |  | 1803 | TB | 13JUL07* | 2007-07-13 | 02JUL07A | 17JUL07A | -2 | -2
Dimensional control plans for station 3 task- METDCP-3 | 8205 | BE | 2007-10-15 | 2008-01-31 |  | -75 | task- | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-11 |  | 32 |  |  |  |  | 1501 | FD | 20JUL07* | 2007-07-20 | 20JUL07A | 20JUL07A | 0 | 0
PF Coils - FDR task- 1302-270 | 1302 | MK | 2008-03-24 | 2008-02-11 |  | 32 | task- | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 51 |  |  |  |  | 3101 | BS |  | 2007-09-06 |  | 09AUG07A | 19 | 19
Station 5 FDR task- 1803-5.6 | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 51 | task- | 1702-525M | Base Support Structure FDR | 1702 | FD | 2008-02-04 | 2008-02-21 | 2008-05-01 | 47 |  |  |  |  | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2 | -2
Base Support Structure FDR task- 1702-525M | 1702 | FD | 2008-02-04 | 2008-02-21 | 2008-05-01 | 47 | task- | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2008-03-21 |  | 49 |  |  |  |  | 8205 | BE | 2007-09-04 | 2007-10-15 | 2007-09-24 | 2007-11-02 | -14 | -14
Coil Support Structures - FDR task- 1501-541 | 1501 | FD | 2007-09-21 | 2008-03-21 |  | 49 | task- | 191-002 | LN2 manifolds&piping- PDR | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 78 |  |  |  |  | 1416 | DW | 01OCT07* | 2007-11-06 | 01OCT07* | 2007-11-06 | 0 | 0
LN2 manifolds&piping- PDR task- 191-002 | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 78 | task- | TRIM-101 | ** Trim Coil PDR ** | 1354 | MK |  | 2008-04-16 |  | 0 |  |  |  |  | 1421 | DW |  | 2007-09-04 |  | 05OCT07* | -23 | -23
** Trim Coil PDR ** task- TRIM-101 | 1354 | MK |  | 2008-04-16 |  | 0 | task- | 141-036 | PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-05-01 | 2008-09-01 | 32 |  |  |  |  | 1302 | MK |  | 2007-12-11 |  | 2007-10-19 | 1900-02-03 | 35
PF Coils Awarded task- 141-036 | 1352 | MK | 2008-05-27 | 2008-05-01 | 2008-09-01 | 32 | task- | 141-038 | PF Conductor Awarded | 1352 | MK | 27MAY08* | 01MAY08* |  | 102 |  |  |  |  | 1361 | MK |  | 2007-09-28 |  | 2007-10-19 | -15 | -15
PF Conductor Awarded task- 141-038 | 1352 | MK | 27MAY08* | 01MAY08* |  | 102 | task- | 162-036.9 | Award Coil Support Structure | 1550 | FD | 16JUN08* | 23MAY08* | 2008-10-01 | 49 |  |  |  |  | 1803 | TB |  | 2007-11-21 |  | 2007-10-29 | 1900-01-16 | 17
Award Coil Support Structure task- 162-036.9 | 1550 | FD | 16JUN08* | 23MAY08* | 2008-10-01 | 49 | task- | TRIM-221 | ** Trim Coil + Structure FDR ** | 1354 | MK |  | 2008-06-03 |  | 0 |  |  |  |  | 8205 | BE | 2007-10-16 | 2008-02-15 | 2007-11-05 | 2008-03-06 | -14 | -14
** Trim Coil + Structure FDR ** task- TRIM-221 | 1354 | MK |  | 2008-06-03 |  | 0 | task- | P3-171VM | COMPLETE VPI OF 18th MOD COIL | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 14 |  |  |  |  | 1361 | MK | 23NOV07* | 2007-11-23 | 23NOV07* | 2007-11-23 | 0 | 0
COMPLETE VPI OF 18th MOD COIL task- P3-171VM | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 14 |  | S21-11.07M | Complete 1st MCHP Assy (Sta 2) | 1810 | MV | 2008-05-09 | 2008-07-22 | 2008-09-01 | -138 |  |  |  |  | 1302 | MK | 2008-03-21 | 2008-03-24 | 2007-12-19 | 2007-12-20 | 1900-02-28 | 60
Complete 1st MCHP Assy (Sta 2)S21-11.07M | 1810 | MV | 2008-05-09 | 2008-07-22 | 2008-09-01 | -138 | [13 empty] | 1421 | DW |  | 2008-01-07 |  | 2008-02-07 | -23 | -23
|  |  | Cost and schedule Performance | [16 empty] | 1501 | FD | 2007-09-21 | 2007-09-21 | 2008-02-21 | 2008-02-21 | -100 | -100
[5 empty] | From May 1,2007 | Current Month | [13 empty] | 1352 | MK |  | 2008-05-27 |  | 2008-03-03 | 1900-02-28 | 60
|  |  |  | BCWS = | 11197.95 | 1168.97 | [13 empty] | 1810 | MV | 2008-02-01 | 2008-02-06 | 2008-03-04 | 2008-03-07 | -22 | -22
|  |  |  | BCWP = | 10071.17 | 1039.4265 | [13 empty] | 8205 | BE | 2008-02-18 | 2008-06-09 | 2008-03-07 | 2008-06-27 | -14 | -14
|  |  |  | ACWP = | 9186.7076 | 1086.612 | [10 empty] | 2110 |  |  |  | 1702 | FD |  | 2008-02-04 |  | 2008-03-27 | -38 | -38
|  |  |  | CV = | 884.4624 | [11 empty] | 2D.1
|  |  |  | SV = | -1126.78
|  |  |  | CPI = | 1.0963 | 0.95658
|  |  |  | SPI = | 0.89938 | 0.88918
|  |  |  | BAC = | 118031.138
|  |  |  | EAC = | 124234.2334
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact

## Monthly Report-JIM
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Project Management |  |  |  | Jim Anderson |  | 2007-11-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
PPPL Project Management Job 8101 | JA
ORNL Project Management Job 8102 | JL
Allocations Job 8998 | RLS
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 948.8 | 110.5
|  |  |  | BCWP = | 930.3 | 127.229
|  |  |  | ACWP = | 1025.2276 | 143.093
|  |  |  | CV = | -94.9276
|  |  |  | SV = | -18.5
|  |  |  | CPI = | 0.90741 | 0.88914
|  |  |  | SPI = | 0.9805 | 1.1514
|  |  |  | BAC = | 11057.504
|  |  |  | EAC = | 11501.504
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
N/A

## Monthly Report-LARRY
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
NCSX Construction |  |  |  | Larry Dudek |  | 2007-12-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Mod Coil Fab Jobs 1408/1451/1459 | JC |  | Fueling & Vacuum WBS 21 & 22 |  | BB
Cryo Systems WBS 62 | GG |  | Diagnostics WBS 3 |  | BS
Assy Tooling design/fab Job 1803 | TB |  | Water/Utilities WBS 61/63 |  | LD
Field Period Assy Jobs 1802/1810/1815 | MV |  | Bakeout Systems WBS 64 |  | MK
Final Machine Assy WBS 75 | EP
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Float (work days) |  | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Total float | Group 1
Shims required for 1st 3 pack MC assy -(task S21-5.04X | 1431 | LD | 2007-09-20 | 2008-01-09 | 2007-12-01 | -131 | -(task | S21-5.04X | Shims required for 1st 3 pack MC assy | 1431 | LD | 2007-09-20 | 2008-01-09 | 2007-12-01 | -131 |  | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish | Variance target 1 early finish
Final Scan of VVSA #3 Station 1 complete -(task R1810-1329 | 1810 | MV | 2008-02-06 | 2008-01-30 |  | 318 | -(task | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 1810 | MV | 2008-02-06 | 2008-01-30 |  | 318 | X | 3 | 1803 | TB | 13JUL07* | 39276 | 02JUL07A | 17JUL07A | -2
Station 5 FDR -(task 1803-5.6 | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 51 | -(task | 1803-5.6 | Station 5 FDR | 1803 | TB | 2007-11-21 | 2008-02-19 |  | 51 | X | 3 | 3101 | BS |  | 39331 |  | 09AUG07A | 19
Station 6 FDR -(task 1803-6.6 | 1803 | TB | 2008-06-04 | 2008-06-25 |  | 54 | -(task | 1803-6.6 | Station 6 FDR | 1803 | TB | 2008-06-04 | 2008-06-25 |  | 54 | 2110 | 2 | 1431 | LD | 2007-09-20 |  | 2007-09-24 |  | -2
COMPLETE VPI OF 18th MOD COIL -(task P3-171VM | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 14 | -(task | P3-171VM | COMPLETE VPI OF 18th MOD COIL | 1451 | JC | 2008-07-15 | 2008-06-30 | 2008-11-01 | 14 | X | 3 | 1803 | TB |  | 39407 |  | 2007-10-29 | 17
Remove from stand Move A2-B2-C2 to holding area -(task S22-11.06 | 1810 | MV | 2008-06-19 | 2008-07-08 |  | -103 | -(task | S22-11.06 | Remove from stand Move A2-B2-C2 to holding area | 1810 | MV | 2008-06-19 | 2008-07-08 |  | -103 | X | 3 | 1810 | MV | 2008-02-01 | 39484 | 2008-03-04 | 2008-03-07 | -22
Complete 1st MCHP Assy (Sta 2) -(task S21-11.07M | 1810 | MV | 2008-05-09 | 2008-07-22 | 2008-09-01 | -138 | -(task | S21-11.07M | Complete 1st MCHP Assy (Sta 2) | 1810 | MV | 2008-05-09 | 2008-07-22 | 2008-09-01 | -138
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | 5883.45 | 641.77
|  |  |  | BCWP = | 5230.61 | 539.1931
|  |  |  | ACWP = | 4713.7428 | 571.916
|  |  |  | CV = | 516.8672
|  |  |  | SV = | -652.84
|  |  |  | CPI = | 1.1097 | 0.94278
|  |  |  | SPI = | 0.88904 | 0.84017
|  |  |  | BAC = | 45219.331
|  |  |  | EAC (excluding scope add-backs)= | 49146.076
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
NCSX
COST and SCHEDULE
PERFORMANCE REPORTS
JANUARY 2008

## Monthly Report- PHIL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Stellarator CoreDesign and Procurement |  |  |  | Phil Heitzenroeder |  | 2007-12-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Conventional Coils WBS 13 | Mike Kalish |  | Modular Coils Jobs 1416/1421/1429/1431 |  | Dave Williamson
Coil Services WBS 16 | Paul Goranson |  | Coil Structures & Base Support Structure WBS 15 |  | Fred Dahlgren
Cryostat Job 1701/1751 | Geoff Gettelfinger |  | Assembly Specs & Dwgs Job 1806 |  | Mike Cole
Assy tooling & constructability Job 1803 | Tom Brown |  | Systems Analysis Job 8204 |  | Art Brooks
Dimensional Control Job 8205 | Bob Ellis |  | Systems Engineering & Support Job 8202 |  | Wayne Reiersen
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (near term look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Float (work days) |  | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Total float | Group 1
Check and promote top-level models/drawings -(task 1416-506 | 1416 | DW | 2007-11-21 | 2008-01-07 |  |  | -(task | 1416-506 | Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 1119 | X
Station 2 Assembly Specification -(task 1803-201 | 1806 | MC | 2007-09-11 | 2008-01-09 |  |  | -(task | 1803-201 | Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2008-01-09 |  | 1146
Station 2 Assembly Drawings -(task 1803-205 | 1806 | MC | 2007-09-11 | 2008-01-09 |  |  | -(task | 1803-205 | Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2008-01-09 |  | 1146
Mod Coil C-C Joint - FDR -(task 1421-3144 | 1421 | DW | 2008-01-07 | 2008-01-31 |  | 453 | -(task | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-31 |  | 453 | X
Base support - PDR -(task 1702-515 | 1702 | FD | 2007-11-26 | 2008-01-31 |  | 47 | -(task | 1702-515 | Base support - PDR | 1702 | FD | 2007-11-26 | 2008-01-31 |  | 47
Dimensional control plans for station 3 -(task METDCP-3 | 8205 | BE | 2007-10-15 | 2008-01-31 |  | -75 | -(task | METDCP-3 | Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2008-01-31 |  | -75 | X
PF Coils - FDR -(task 1302-270 | 1302 | MK | 2008-03-24 | 2008-02-11 |  | 32 | -(task | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-11 |  | 32
Base Support Structure FDR -(task 1702-525M | 1702 | FD | 2008-02-04 | 2008-02-21 | 2008-05-01 | 47 | -(task | 1702-525M | Base Support Structure FDR | 1702 | FD | 2008-02-04 | 2008-02-21 | 2008-05-01 | 47
Prepare EM and structural analysis of leads -(task 1416-601 | 1416 | DW | 2007-11-06 | 2008-02-29 |  |  | -(task | 1416-601 | Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-02-29 |  | 1148
Prepare Type-ABC closeout FDR -(task 1416-605 | 1416 | DW | 2008-01-14 | 2008-02-29 |  |  | -(task | 1416-605 | Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-02-29 |  | 1095 | X
Coil Support Structures - FDR -(task 1501-541 | 1501 | FD | 2007-09-21 | 2008-03-21 |  | 49 | -(task | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2008-03-21 |  | 49 | X
LN2 manifolds&piping- PDR -(task 191-002 | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 78 | -(task | 191-002 | LN2 manifolds&piping- PDR | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 78
** Trim Coil PDR ** -(task TRIM-101 | 1354 | MK |  | 2008-04-16 |  | 0 | -(task | TRIM-101 | ** Trim Coil PDR ** | 1354 | MK |  | 2008-04-16 |  | 0 | X
PF Coils Awarded -(task 141-036 | 1352 | MK | 2008-05-27 | 2008-05-01 | 2008-09-01 | 32 | -(task | 141-036 | PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-05-01 | 2008-09-01 | 32 | X
PF Conductor Awarded -(task 141-038 | 1352 | MK | 27MAY08* | 01MAY08* |  | 102 | -(task | 141-038 | PF Conductor Awarded | 1352 | MK | 27MAY08* | 01MAY08* |  | 102 | X
Bid and award base support materials -(task 161-036.8 | 1752 | FD | 2008-06-19 | 2008-05-01 |  | 47 | -(task | 161-036.8 | Bid and award base support materials | 1752 | FD | 2008-06-19 | 2008-05-01 |  | 47 | X
Dimensional control plans for station 5 -(task METDCP-5 | 8205 | BE | 2008-02-15 | 2008-05-22 |  | 42 | -(task | METDCP-5 | Dimensional control plans for station 5 | 8205 | BE | 2008-02-15 | 2008-05-22 |  | 42 | X
Award Coil Support Structure -(task 162-036.9 | 1550 | FD | 16JUN08* | 23MAY08* | 2008-10-01 | 49 | -(task | 162-036.9 | Award Coil Support Structure | 1550 | FD | 16JUN08* | 23MAY08* | 39722 | 49 | X
** Trim Coil + Structure FDR ** -(task TRIM-221 | 1354 | MK |  | 2008-06-03 |  | 0 | -(task | TRIM-221 | ** Trim Coil + Structure FDR ** | 1354 | MK |  | 2008-06-03 |  | 0 | X
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month |  | Activity ID | Activity description | Job Number | Job Manager | Target 1 early finish | Early finish | WBS | Total float
|  |  |  | BCWS = | 4451.5 | 413.6 | -47 | 1416-506 | Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 | 2008-01-07 |  | 1119
|  |  |  | BCWP = | 3996.09 | 369.2287 | -120 | 1803-201 | Station 2 Assembly Specification | 1806 | MC | 2007-09-11 | 2008-01-09 |  | 1146
|  |  |  | ACWP = | 3552.3957 | 371.603 | -120 | 1803-205 | Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 | 2008-01-09 |  | 1146
|  |  |  | CV = | 443.6943 |  | -24 | 1421-3144 | Mod Coil C-C Joint - FDR | 1421 | DW | 2008-01-07 | 2008-01-31 |  | 453
|  |  |  | SV = | -455.41 |  | -66 | 1702-515 | Base support - PDR | 1702 | FD | 2007-11-26 | 2008-01-31 |  | 47
|  |  |  | CPI = | 1.1249 | 0.99361 | -108 | METDCP-3 | Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 | 2008-01-31 |  | -75
|  |  |  | SPI = | 0.8977 | 0.89272 | 42 | 1302-270 | PF Coils - FDR | 1302 | MK | 2008-03-24 | 2008-02-11 |  | 32
|  |  |  | BAC = | 56600.653 |  | -17 | 1702-525M | Base Support Structure FDR | 1702 | FD | 2008-02-04 | 2008-02-21 | 2008-05-01 | 47
|  |  |  | EAC = | 57986.002 |  | -115 | 1416-601 | Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 | 2008-02-29 |  | 1148
|  |  |  | Projected cost variance = |  |  | -46 | 1416-605 | Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 | 2008-02-29 |  | 1095
|  |  |  | EAC Variance Explanation |  |  | -182 | 1501-541 | Coil Support Structures - FDR | 1501 | FD | 2007-09-21 | 2008-03-21 |  | 49
[7 empty] | 0 | 191-002 | LN2 manifolds&piping- PDR | 1601 | PG | 2008-04-02 | 2008-04-02 |  | 78
[7 empty] | -39554 | TRIM-101 | ** Trim Coil PDR ** | 1354 | MK |  | 2008-04-16 |  | 0
Analysis | [6 empty] | 26 | 141-036 | PF Coils Awarded | 1352 | MK | 2008-05-27 | 2008-05-01 | 2008-09-01 | 32
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  | #VALUE! | 141-038 | PF Conductor Awarded | 1352 | MK | 27MAY08* | 01MAY08* |  | 102
[7 empty] | 49 | 161-036.8 | Bid and award base support materials | 1752 | FD | 2008-06-19 | 2008-05-01 |  | 47
[7 empty] | -97 | METDCP-5 | Dimensional control plans for station 5 | 8205 | BE | 2008-02-15 | 2008-05-22 |  | 42
[7 empty] | #VALUE! | 162-036.9 | Award Coil Support Structure | 1550 | FD | 16JUN08* | 23MAY08* | 2008-10-01 | 49
[7 empty] | -39602 | TRIM-221 | ** Trim Coil + Structure FDR ** | 1354 | MK |  | 2008-06-03 |  | 0
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact

## Monthly Report-AL
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Electrical, I&C and Startup |  |  |  | Al vonHalle |  | 2007-07-30
Scope (jobs): | Job Manager | Initials | Scope (jobs): |  | Job Manager | Initials
Electrical Powers Systems WBS 4 | RR
Instrumentation and Controls | PS
Startup | CG
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level
[10 empty] | Activity ID | Activity description | Early start | Early finish | Milestones | Job Number | Job Manager
[10 empty] | 1803-3.4 | Stage 3 support FDR | 13JUL07* | 2007-07-13 | 3 | 1803 | TB
[10 empty] | 3101-326 | FDR - ROWGOSKI COIL |  | 2007-09-06 | 3 | 3101 | BS
[10 empty] | S21-5.04X | Shims required for 1st 3 pack MC assy |  | 2007-09-20 | 2 | 1431 | LD
[10 empty] | 1803-5.6 | Station 5 FDR |  | 2007-11-21 | 3 | 1803 | TB
[10 empty] | R1810-1329 | Final Scan | 2008-02-01 | 2008-02-06 | 3 | 1810 | MV
Cost and schedule Performance
[5 empty] | From May 1,2007 | Current Month
|  |  |  | BCWS = | -85.8 | 1.3
BCWP =
ACWP =
CV =
SV =
CPI =
SPI =
|  |  |  | BAC = | 5082.85
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 |  |  | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 |  |  | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 |  |  | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2
No Milestones during the period

## Contingency
| period ending | MAY fy07 | JUN fy07 | JUL fy07 | AUG fy07 | SEP fy07 | OCT fy08 | NOV fy08 | DEC fy08 | JAN fy08 | FEB fy08 | MAR fy08 | APR fy08 | MAY fy08 | JUN fy08 | JUL fy08 | AUG fy08 | SEP fy08 | OCT fy09 | NOV fy09 | DEC fy09 | JAN fy09 | FEB fy09 | MAR fy09 | APR fy09 | MAY fy09 | JUN fy09 | JUL fy09 | AUG fy09 | SEP fy09 | OCT fy10 | NOV fy10 | DEC fy10 | JAN fy10 | FEB fy10 | MAR fy10 | APR fy10 | MAY fy10 | JUN fy10 | JUL fy10 | AUG fy10 | SEP fy10 | OCT fy11 | NOV fy11 | DEC fy11 | JAN fy11 | FEB fy11 | MAR fy11 | APR fy11 | MAY fy11 | JUN fy11 | JUL fy11 | AUG fy11 | SEP fy11 | OCT fy12 | NOV fy12 | DEC fy12
Cost
| Baseline | 14380 | 14380 | 14380 | 14380 | 14380 | 14380 | 14380 | 14380
| ECP drawdown | 0 | 0 | 0 | 0
| (ECP Number) | none | none | none | none | none | none | none
| EAC (overrun)/underrun | 0 | 0 | 0 | 0 | -531 | -43 | -1277 | -4890.0954
| Cost Variance (overrun)/underrun | -209.4547 | 49.0555 | 671.9424 | 452.1688 | 278 | 901 | 854 | incl above
| Schedule Slip (@$202k/mo.) | 0 | 0 | 0 | -221.2381 | -548.2857 | -375.114 | -505 | -1313
| FREE BALANCE ($K) | 14170.5453 | 14429.0554 | 15051.9424 | 14610.9308 | 13578.7143 | 14862.886 | 13452 | 8176.9046
| ETC | 50433 | 49162 | 47668 | 46424 | 46655.2857 | 45123.114 | 45400 | 47869.3878
| FREE BALANCE (% of ETC) | 28.1% | 29.35% | 31.58% | 31.47% | 29.1% | 32.94% | 29.63% | 17.08%
| Target Drawdown Rate (%) | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3% | 28.3%
| BCWR | 50004 | 48796 | 47244 | 45880 | 44747 | 42784 | 41635 | 40752 | 39450 | 38335 | 37213 | 36161 | 35165 | 34114 | 32769 | 31484 | 30259 | 28922 | 27784 | 26546 | 25056 | 23790 | 22420 | 21112 | 19903 | 18646 | 17495 | 16340 | 15192 | 13640 | 12387 | 11389 | 10182 | 9153 | 7846 | 6639 | 5680 | 4777 | 4013 | 3276 | 2599 | 1755 | 1017 | 391 | 0
| BCWS | 621 | 1208 | 1552 | 1364 | 1133 | 1963 | 1149 | 883 | 1302 | 1115 | 1122 | 1052 | 996 | 1051 | 1345 | 1285 | 1225 | 1337 | 1138 | 1238 | 1490 | 1266 | 1370 | 1308 | 1209 | 1257 | 1151 | 1155 | 1148 | 1552 | 1253 | 998 | 1207 | 1029 | 1307 | 1207 | 959 | 903 | 764 | 737 | 677 | 844 | 738 | 626 | 391 |  | 50625
| Target Contingency Freebalance ($K) | 14151.132 | 13809.268 | 13370.052 | 12984.04 | 12663.401 | 12107.872 | 11782.705 | 11532.816 | 11164.35 | 10848.805 | 10531.279 | 10233.563 | 9951.695 | 9654.262 | 9273.627 | 8909.972 | 8563.297 | 8184.926 | 7862.872 | 7512.518 | 7090.848 | 6732.57 | 6344.86 | 5974.696 | 5632.549 | 5276.818 | 4951.085 | 4624.22 | 4299.336 | 3860.12 | 3505.521 | 3223.087 | 2881.506 | 2590.299 | 2220.418 | 1878.837 | 1607.44 | 1351.891 | 1135.679 | 927.108 | 735.517 | 496.665 | 287.811 | 110.653 | 0
Schedule
| Baseline | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
| ECP Schedule Drawdown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Critical path Schedule Slip (months) | 0 | 0 | 0 | -1.0952 | -2.7143 | -1.857 | -2.5 | -6.5
| FREE BALANCE (months) | 11 | 11 | 11 | 9.9048 | 8.2857 | 9.143 | 8.5 | 4.5
| Target (months) | 10.8036 | 10.6071 | 10.4107 | 10.2143 | 10.0179 | 9.8214 | 9.625 | 9.4286 | 9.2321 | 9.0357 | 8.8393 | 8.6429 | 8.4464 | 8.25 | 8.0536 | 7.8571 | 7.6607 | 7.4643 | 7.2679 | 7.0714 | 6.875 | 6.6786 | 6.4821 | 6.2857 | 6.0893 | 5.8929 | 5.6964 | 5.5 | 5.3036 | 5.1071 | 4.9107 | 4.7143 | 4.5179 | 4.3214 | 4.125 | 3.9286 | 3.7321 | 3.5357 | 3.3393 | 3.1429 | 2.9464 | 2.75 | 2.5536 | 2.3571 | 2.1607 | 1.9643 | 1.7679 | 1.5714 | 1.375 | 1.1786 | 0.98214 | 0.78571 | 0.58929 | 0.39286 | 0.19643 | 7.272e-15

## EAC calculation
Project start | current date | Baseline Finish | current total float (work days from primavera) | available 2 shift operation remaining on CP (mo.) | Projected Finish | Projected slip (mo.)
2007-05-01 | 2007-09-30 | 2011-01-11 | -57 | 18 | 2014-05-14 14:39 | 40.1188
[6 empty] | 8103.991 | = Stretchout cost impact @( $202k/mo.)
[6 empty] | 576 | = second shift supervision cost @ $64k/mo.
|  |  | BAC | EAC (from cpr)
|  |  | 50853 | #REF! | ETC increase = | #REF!
[5 empty] | Total Increase = | #REF!
[5 empty] | Projected EAC = | #REF!
[5 empty] | TEC = | 132412
[5 empty] | (under)/over = | #REF!
Formulas:
Projected Finish = ((([Baseline Finish]-[Project start])/(([current date]-[Project start]+(F6*7/5))/([current date]-[Project start]))+([Project start])))-(G6/2*30.4)

## Summary analysis
NCSX Summary Overview
DECEMBER 2007
Cost Performance |  |  |  | BCWS | BCWP | ACWP
| Cumulative from May 1st, 2007 = |  |  | 11197.95 | 10071.17 | 9186.7076
| Cost Through April 2007 = |  |  |  |  | 67178
| Cost to date = |  |  |  |  | 76364.7076
| BCWR (work to go) = |  |  |  | 40781.83
| Contingency = |  |  |  | 14380
| Total TEC = |  |  |  | 132411
CPI = | 1.0963 | 1.15 last month |  | Cost Variance = |  | 884.4624 | Major Cost Variances
SPI = | 0.89938 | .91 last month |  | Schedule Variance = |  | -1126.78 | Mod Coil Punch List |  | CPI = .78 | -88 | (.76 last month)
[7 empty] | FP Assy tooling (job 1803) |  | CPI = .40 | -122 | (.38 last month)
[7 empty] | Systems Analysis (job 8204) |  | CPI =.67 | -125 | (.72 last month)
[7 empty] | Allocations (job 8998) |  | CPI=.69 | -106 | (.69 last month)
EAC= | 6102 |  |  |  |  | Scope Add-backs = |  | 5690
| 5569 | re-estimate
|  | 1800 | Field period assy-add'l metrology crews |  |  |  |  | scope add-back and 40% contingency
|  | 1513 | Field period assy-oversight/mgr/supervision |  |  |  |  | 1973 | Trim coils incl coil services & instl (54coil set)
|  | 500 | Field period assy-add'l tasks/complexity |  |  |  |  | 985 | VPS (incl NB ducts, pumps,instl, water systems
|  | 200 | Field period assy-laser tracker |  |  |  |  | 189 | Injectors
|  | -312 | Field period assy-CV to date |  |  |  |  | 35 | Diagnostics
|  | 500 | WBS 82 project engineering management |  |  |  |  | 882 | I&C
|  | 712 | system analysis & dsn integration 8203/4 |  |  |  |  | 1626 | Contingency @40%
|  | 361 | Project management/oversight wbs 81
|  | 220 | mc punch list
|  | 294 | Other
|  | -219 | WBS 19 stell core mgt & FP specs/dwgs
| 1313 | stretch-out cost (6.5mos. 2.5 last month's report)
| -780 | Rate reductions
Cost/Schedule Uncertainties and Opportunities
| Uncertainties | [5 empty] | Opportunities
| 1) | Field period assy critical path plan uncertain. Unresolved resource issues (crane, space, metrology HW, metrology crews, 2nd shift use) |  |  |  |  | 1) | Further overhead rate reductions
| 2) | Trim coil and PF coil fabrication schedule from vendors
| 3) | Station 5 and 6 assy sequence design not schedule until Feb and June will impact assy cost & schedule
| 4) | Contingency cost and schedule analysis; will determine final ETC
Critical path assessment
| #1 | Critical path through field period and final machine assembly. Recent ETC updates indicate impact of 6 1/2 months. However, this current forecast has not been adopted by the job managers citing issues of crane utilization, laydown assy space at d-site and c-site, metrology crews needs, metrology hardware needs, and the reasonableness of extensive 2nd shift utilization.
| #2 | Trim coil design, fabrication required for assembly in station 5. zero float
Level II milestone status (near term) | [12 empty] | Activity ID | Activity description | Target 1 early finish | Early finish | WBS | Milestones | Total float | Variance target 1 early finish |  | Float | Slip relative to target
| Design Reviews | [5 empty] | Baseline | Forecast | DOE Date | Float (mos.) | Slip relative to baseline (mos.) | d | 1702-515 | Base support - PDR | 2007-11-26 | 2008-01-31 |  | 3 | 47 | -41 |  | 2.2381 | -1.9524
|  | Base support - PDR |  |  |  |  | 2007-11-26 | 2008-01-31 |  | 2.2381 | -1.9524 | d | METDCP-3 | Dimensional control plans for station 3 | 2007-10-15 | 2008-01-31 |  | 3 | -75 | -69 |  | -3.5714 | -3.2857
|  | Dimensional control plans for station 3 |  |  |  |  | 2007-10-15 | 2008-01-31 |  | -3.5714 | -3.2857 | d | 1302-270 | PF Coils - FDR | 2008-03-24 | 2008-02-11 |  | 3 | 32 | 30 |  | 1.5238 | 1.4286
|  | PF Coils - FDR |  |  |  |  | 2008-03-24 | 2008-02-11 |  | 1.5238 | 1.4286 | d | 1803-5.6 | Station 5 FDR | 2007-11-21 | 2008-02-19 |  | 3 | 51 | -55 |  | 2.4286 | -2.619
|  | Station 5 FDR |  |  |  |  | 2007-11-21 | 2008-02-19 |  | 2.4286 | -2.619 | d | 1702-525M | Base Support Structure FDR | 2008-02-04 | 2008-02-21 | 2008-05-01 | 2 | 47 | -13 |  | 2.2381 | -0.61905
|  | Base Support Structure FDR |  |  |  |  | 2008-02-04 | 2008-02-21 | 2008-05-01 | 2.2381 | -0.61905 | d | 1416-605 | Prepare Type-ABC closeout FDR | 2008-01-14 | 2008-02-29 |  | 3 | 1095 | -34 |  | 52.1429 | -1.619
|  | Prepare Type-ABC closeout FDR |  |  |  |  | 2008-01-14 | 2008-02-29 |  |  | -1.619 | d | 1501-541 | Coil Support Structures - FDR | 2007-09-21 | 2008-03-21 |  | 3 | 49 | -121 |  | 2.3333 | -5.7619
|  | Coil Support Structures - FDR |  |  |  |  | 2007-09-21 | 2008-03-21 |  | 2.3333 | -5.7619 | d | 191-002 | LN2 manifolds&piping- PDR | 2008-04-02 | 2008-04-02 |  | 3 | 78 | 0 |  | 3.7143 | 0
|  | LN2 manifolds&piping- PDR |  |  |  |  | 2008-04-02 | 2008-04-02 |  | 3.7143 | 0 | d | TRIM-101 | ** Trim Coil PDR ** |  | 2008-04-16 |  | 3 | 0 | 0 |  | 0 | 0
|  | ** Trim Coil PDR ** | [5 empty] | 2008-04-16 |  | 0 | 0 | d | TRIM-221 | ** Trim Coil + Structure FDR ** |  | 2008-06-03 |  | 3 | 0 | 0 |  | 0 | 0
|  | ** Trim Coil + Structure FDR ** | [5 empty] | 2008-06-03 |  | 0 | 0 | d | 1803-6.6 | Station 6 FDR | 2008-06-04 | 2008-06-25 |  | 3 | 1900-02-22 | -15 |  | 2.5714 | -0.71429
|  | Station 6 FDR |  |  |  |  | 2008-06-04 | 2008-06-25 |  | 2.5714 | -0.71429 | f | S21-5.04X | Shims required for 1st 3 pack MC assy | 2007-09-20 | 2008-01-09 | 2007-12-01 | 2 | -131 | -70 |  | -6.2381 | -3.3333
| Fabrication/Assembly | [10 empty] | f | S21-11.07M | Complete 1st MCHP Assy (Sta 2) | 2008-05-09 | 2008-07-22 | 2008-09-01 | 1900-01-01 | -138 | -50 |  | -6.5714 | -2.381
|  | Shims required for 1st 3 pack MC assy |  |  |  |  | 2007-09-20 | 2008-01-09 | 2007-12-01 | -6.2381 | -3.3333 | f | 730.9 | CD-4 | 2011-01-31 | 2011-08-15 | Dec-11 | 1 | -138 | 0 | 0 | -6.5714 | 0
|  | Complete 1st MCHP Assy (Sta 2) |  |  |  |  | 2008-05-09 | 2008-07-22 | 2008-09-01 | -6.5714 | -2.381 |  | 1416-506 | Check and promote top-level models/drawings | 2007-11-21 | 2008-01-07 |  | 3 | 1119 | -24
|  | COMPLETE VPI OF 18th MOD COIL |  |  |  |  | 2008-07-15 | 2008-06-30 | 2008-11-01 | 0.66667 | 0.47619 |  | 1803-201 | Station 2 Assembly Specification | 2007-09-11 | 2008-01-09 |  | 3 | -131 | -77
|  | CD-4 |  |  |  |  | 2011-01-31 | 2011-08-15 | Dec-11 | -6.5714 | 0 |  | 1803-205 | Station 2 Assembly Drawings | 2007-09-11 | 2008-01-09 |  | 3 | -131 | -77
Contingency | [6 empty] | BCWR | [5 empty] | R1810-1329 | Final Scan of VVSA #3 Station 1 complete | 2008-02-06 | 2008-01-30 |  | 3 | 318 | 5
|  | Planned (baseline)= |  |  | 14380 |  | 50853 | 28.28% |  |  |  |  | 1421-3144 | Mod Coil C-C Joint - FDR | 2008-01-07 | 2008-01-31 |  | 3 | 453 | -18
|  | Drawdown to date = |  |  | 0 | [7 empty] | 1416-601 | Prepare EM and structural analysis of leads | 2007-11-06 | 2008-02-29 |  | 3 | 1148 | -74
|  | EAC (overrun)/underrun = |  |  | -4890.0954 | [7 empty] | 141-036 | PF Coils Awarded | 2008-05-27 | 2008-05-01 | 2008-09-01 | 2 | 32 | 17
|  | Cost Variance (overrun)/underrun = |  |  | incl above | [7 empty] | 141-038 | PF Conductor Awarded | 27MAY08* | 01MAY08* |  | 3 | 102 | 17
|  | Schedule Slip (@$202k/mo.) = |  |  | -1313 |  | ETC | [5 empty] | 161-036.8 | Bid and award base support materials | 2008-06-19 | 2008-05-01 |  | 3 | 1900-02-15 | 34
[5 empty] | 8176.9046 |  | 47869.3878 | 17.08% |  |  |  |  | METDCP-5 | Dimensional control plans for station 5 | 2008-02-15 | 2008-05-22 |  | 3 | 1900-02-10 | -69
|  | Current free balance contingency on remaining scope = |  |  |  |  | 17.08% | [5 empty] | 162-036.9 | Award Coil Support Structure | 16JUN08* | 23MAY08* | 2008-10-01 | 2 | 1900-02-17 | 15
Risks (from updated risk registry) | [12 empty] | P3-171VM | COMPLETE VPI OF 18th MOD COIL | 2008-07-15 | 2008-06-30 | 2008-11-01 | 2 | 14 | 10 |  | 0.66667 | 0.47619
|  | No risks retired or added. | [10 empty] | S22-11.06 | Remove from stand Move A2-B2-C2 to holding area | 2008-06-19 | 2008-07-08 |  | 3 | -103 | -12
ISSUES | [12 empty] | 161-036.9 | Deliver base support materials | 2008-09-22 | 2008-08-04 |  | 3 | 47 | 34
| 1) Critical path; A field period and final machine assembly plan needs o be adopted by Viola & Perry that can be used as the backbone of the new proposed baseline. Current schedule forecast show a 6 1/2 slip but this nay grow significantly greater once resource constraints are resolved. | [11 empty] | 1351-195X | ALL TF COILS DELIVERED | 2008-09-18 | 2008-09-12 |  | 3 | 349 | 4
| 2) upcoming design review dates for the Trim Coils, PF coils, Base support structure, and Coil support structure must be met to ensure reasonable chance of hardware deliveries. | [11 empty] | METDCP-6 | Dimensional control plans for station 6 | 2008-06-09 | 2008-09-16 |  | 3 | 42 | -69
| 3) The coil services lead design and fabrication schedule should be accelerated into FY08 to ensure supporting the field period assembly schedule. | [11 empty] | 1803-605M | Station 6 Specification & Assy Drawings Complete | 2008-10-02 | 2008-10-02 | 2009-03-01 | 2 | 30 | 0
[13 empty] | PLCT-C6M | COMPLETE MODULAR COIL FABRICATION | 2008-09-30 | 2008-10-06 | 2009-02-01 | 2 | -6 | -4
[13 empty] | 1803-609 | Detail dwgs-spool piece | 2008-10-31 | 2008-10-31 |  | 3 | 298 | 0
[13 empty] | 451-2-3 | Power system - PDR | 2008-12-18 | 2008-12-18 | 2009-06-01 | 2 | 146 | 0
Contents
Page
[24 empty] | Summary |  | 3
[24 empty] | Cost Performance Report (CPR) |  | 3 - 4
January performance data
Rebaseline Preliminary Results
[24 empty] | Cost Growth Reconciliation |  | 5
[24 empty] | Schedule Growth Reconciliation |  | 6
[24 empty] | Summary Performance Curve |  | 7
[24 empty] | FY08 Spending trend |  | 8
[24 empty] | Milestones |  | n/a
[24 empty] | Contingency Analysis |  | n/a
[24 empty] | Responsible Line Manager Analysis Reports |  | n/a
[24 empty] | Schedule Barcharts |  | n/a
10-11
12
[24 empty] | Critical Path |  | 13
Issued under separate cover
Issued under separate cover

## Baseline Reconciliation
NCSX EAC - Reconciliation Detail
|  | WBS II |  | JOB | COST TO DATE 4/1/03 - 4/30/07 |  | ETC 5/1/07 THROUGH COMPLETION |  |  |  |  | TOTAL |  | ecp31 | deltas
[7 empty] | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | ETC | TOTAL EAC
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18
|  | 12 - Vacuum Vessel Systems | Phil | 1201 - Vacuum Vessel Prelim Dsn | 424 | [6 empty] | 0 | 424 | 424 | 0 | 0% | 1201
|  |  | Phil | 1202 - Vacuum Vessel R&D | 1770.9 | [6 empty] | 0 | 1770.9 | 1791 | -20.1 | -1.122% | 1202
|  |  | Phil | 1203 - Vacuum Vessel Final Dsn | 1217 | [6 empty] | 0 | 1217 | 944 | 273 | 28.92% | 1203
1204-VV Sys Procurements (non VVSA) |  |  | Larry | 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 535.9 |  | 47 | 162 | 1 | 198 | 0 | 408 | 943.9 | 557 | 386.9 | 69.46% | 1204
|  |  | Phil | 1206 - VV Field Weld Joint R&D | 15.954 | [6 empty] | 0 | 15.954 | 74 | -58.046 | -78.44% | 1206
|  |  | Larry | 1250 - Vacuum Vessel Fabrication | 5788.9 |  | -252 | 0 | 0 | 0 | 0 | -252 | 5536.9 | 5741 | -204.1 | -3.555% | 1250
|  |  |  | Subtotal | 9752.654 |  | -205 | 162 | 1 | 198 | 0 | 156 | 9908.654 | 9531 | 377.654 | 3.962%
[15 empty] | 0 | #DIV/0!
|  | 13 - Conventional Coils | Phil | 1301 - TF Design | 970.1 | [6 empty] | 0 | 970.1 | 837 | 133.1 | 15.9% | 1301
1302 - PF Design |  |  | Phil | 1302 - PF Design -KALISH | 19.338 |  | 44 | 213 | 0 | 0 | 0 | 257 | 276.338 | 253 | 23.338 | 9.225% | 1302
|  |  | Phil | 1303 - Central Solenoid Support Design | 154.9 | [6 empty] | 0 | 154.9 |  | 154.9 | #DIV/0!
|  |  | Phil | 1350 - TF Coil Fabr Prep | 535.99 | [6 empty] | 0 | 535.99 | 400 | 135.99 | 34% | 1350
|  |  | Phil | 1351 - TF Coil Fabr Supplies | 482.959 | [6 empty] | 0 | 482.959 | 1318 | -835.041 | -63.36% | 1351
|  |  | Phil | 1352 - PF Coil Procurement-KALISH |  |  | 0 | 968 | 634 | 28 | 0 | 1630 | 1630 | 1362 | 268 | 19.68% | 1352
|  |  | Phil | 1353 - CS Structure Procurement-DAHLGREN |  |  | 0 | 0 | 78 | 259 | 0 | 337 | 337 | 270 | 67 | 24.81% | 1353
|  |  | Phil | 1354 - Trim Coil Design &Procurement-KALISH |  |  | 0 | 0 | 162 | 0 | 0 | 162 | 162 | 258 | -96 | -37.21% | 1354
|  |  | Phil | 1355 - WBS 13 I&C Proc and Coil Assy-KALISH |  |  | 0 | 32 | 39 | 2 | 0 | 73 | 73 | 92 | -19 | -20.65% | 1355
|  |  | Phil | 1361 - TF Fabrication-KALISH | 1062.999 | (1) | 228 | 775 | 0 | 0 | 0 | 1003 | 2065.999 |  | 2065.999 | #DIV/0!
|  |  |  | Subtotal | 3226.286 |  | 272 | 1988 | 913 | 289 | 0 | 3462 | 6688.286 | 4790 | 1898.286 | 39.63%
[15 empty] | 0 | #DIV/0!
|  | 14 - Modular Coils | Phil | 1401 - Mod Coil Prel.Dsn | 304.5 | [6 empty] | 0 | 304.5 | 303 | 1.5 | 0.495% | 1401
|  |  | Phil | 1402 - Mod.Coil Analyses | 239.14 | [6 empty] | 0 | 239.14 | 239 | 0.14 | 0.05858% | 1402
|  |  | Phil | 1403 modular coil winding form design | 3310.9 | [6 empty] | 0 | 3310.9 | 3149 | 161.9 | 5.141% | 1403
|  |  | Phil | 1404-MCWF R&D & 1st Prod Casting | 2554.9 |  | -36 | 0 | 0 | 0 | 0 | -36 | 2518.9 | 2534 | -15.1 | -0.5959% | 1404
|  |  | Phil | 1405-Mod Coil Winding R&D Prep | 168 | [6 empty] | 0 | 168 | 168 | 0 | 0% | 1405
|  |  | Phil | 1406 - Mod. Coil Winding Facility | 2263 | [6 empty] | 0 | 2263 | 2214 | 49 | 2.213% | 1406
|  |  | Phil | 1407 -Mod Coil Winding Facility | 2569 | [6 empty] | 0 | 2569 | 2523 | 46 | 1.823% | 1407
1408-Mod Coil Winding Supplies |  |  | Larry | 1408 - MC Winding Supplies-CHRZANOWSKI | 2353 |  | 178 | 172 | 0 | 0 | 0 | 350 | 2703 | 1836 | 867 | 47.22% | 1408
|  |  | Phil | 1409 - Mod. Coil Test Stand | 832.9 | [6 empty] | 0 | 832.9 | 488 | 344.9 | 70.68% | 1409
|  |  | Phil | 1410 MC Twisted Racetrack Fabr | 1049.908 | [6 empty] | 0 | 1049.908 | 799 | 250.908 | 31.4% | 1410
1411-MCWF Fabrication S005242 |  |  | Phil | 1411 - MCWF Fabr. S005242-HEITZENROEDER | 9965 |  | -80 | 0 | 0 | 0 | 0 | -80 | 9885 | 8329 | 1556 | 18.68% | 1411
|  |  | Phil | 1412 - Complete Winding Facilities | 540.732 | [6 empty] | 0 | 540.732 | 310 | 230.732 | 74.43% | 1412
|  |  | Phil | 1413 - Mod Coil Fracture Analysis | 27.819 | [6 empty] | 0 | 27.819 | 23 | 4.819 | 20.95% | 1413
|  |  | Phil | 1414 - Coil Testing | 638.674 | [6 empty] | 0 | 638.674 |  | 638.674 | #DIV/0!
|  |  | Phil | 1415 - Dimensional Control Testing | 24.038 | [6 empty] | 0 | 24.038 |  | 24.038 | #DIV/0!
Mod Coil Design 1416 Coil Design, Job 1421 Interface design |  |  | Phil | 1416 &1421 - Mod Coil Interface Design-WILLIAMSON | 1108.49 |  | 1066 | 422 | 0 | 0 | 0 | 1488 | 2596.49 |  | 2596.49 | #DIV/0!
Job 1429 Interface R&D/Test |  |  | Phil | 1429 - MC Interface R&D-GETTELFINGER | 157.99 |  | 118 | 0 | 0 | 0 | 0 | 118 | 275.99 |  | 275.99 | #DIV/0!
|  |  | Phil | 1419 - Winding Facility Modification | 48.434 | [6 empty] | 0 | 48.434 |  | 48.434 | #DIV/0!
|  |  | Phil | 1431 - Mod. Coil Interface Hardware-DUDEK |  |  | 362 | 660 | 0 | 17 | 0 | 1039 | 1039 | 86 | 953 | 1108% | 1431
1451 - Mod Coil Winding (incl 1459 punch list and unplanned work) |  |  | Larry | 1451 - Mod Coil Winding-CHRZANOWSKI | 5982.2 | (1) | 1054 | 1813 | 0 | 0 | 0 | 2867 | 8849.2 | 5091 | 3758.2 | 73.82% | 1451
|  |  | Larry | 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  |  | 90 | 411 | 0 | 0 | 0 | 501 | 501 |  | 501 | #DIV/0!
|  |  | Phil | 1460 - 3rd Winding Fixture | 57.337 | [6 empty] | 0 | 57.337 |  | 57.337 | #DIV/0!
|  |  |  | Subtotal | 34195.962 |  | 2752 | 3478 | 0 | 17 | 0 | 6247 | 40442.962 | 28092 | 12350.962 | 43.97%
[15 empty] | 0 | #DIV/0!
1501 - Structures Design |  | 15 - Coil Structures | Phil | 1501 - Coil Structures Design-DAHLGREN | 330.94 | (1) | 164 | 22 | 0 | 0 | 0 | 186 | 516.94 | 221 | 295.94 | 133.9% | 1501
1550 - Structures Procurement |  |  | Phil | 1550 - Coil Struct. Procurement -DAHLGREN | 4.061 |  | 0 | 403 | 673 | 0 | 0 | 1076 | 1080.061 | 1191 | -110.939 | -9.315% | 1550
|  |  |  | Subtotal | 335.001 |  | 164 | 425 | 673 | 0 | 0 | 1262 | 1597.001 | 1412 | 185.001 | 13.1%
[15 empty] | 0 | #DIV/0!
1601 - Coil Services |  | 16 - Coil Services | Phil | 1601 - Coil Services Design-GORANSON | 2.614 |  | 6 | 323 | 372 | 160 | 0 | 861 | 863.614 | 1140 | -276.386 | -24.24% | 1601
[15 empty] | 0 | #DIV/0!
1701-Cryostat design |  | 17 - Cryostat and Base Support Structure | Phil | 1701 - Cryostat Design-GETTLEFINGER | 431.073 |  | 0 | 0 | 207 | 0 | 0 | 207 | 638.073 | 504 | 134.073 | 26.6% | 1701
|  |  | Phil | 1702 - Base Support Struct Design-DAHLGREN |  |  | 0 | 163 | 0 | 0 | 0 | 163 | 163 | 541 | -378 | -69.87% | 1751
|  |  | Phil | 1751 - Cryostat Procurement-GETTLEFINGER |  |  | 0 | 0 | 0 | 325 | 0 | 325 | 325 | 315 | 10 | 3.175% | 1752
|  |  | Phil | 1752 - Base Support Proc-DAHLGREN |  |  | 0 | 61 | 28 | 0 | 0 | 89 | 89 |  | 89 | #DIV/0!
|  |  |  | Subtotal | 431.073 |  | 0 | 224 | 235 | 325 | 0 | 784 | 1215.073 | 1360 | -144.927 | -10.66%
[15 empty] | 0 | #DIV/0!
|  | 18 - Field Period Assembly | Larry | 1801-Field Period Assy | 64.38 | [6 empty] | 0 | 64.38 | 61 | 3.38 | 5.541% | 1801
1802 - FP Assy Oversight Support |  |  | Larry | 1802 - FP Assy Oversight&Support-VIOLA | 986.703 | (1) | 253 | 790 | 858 | 88 | 0 | 1989 | 2975.703 | 1444 | 1531.703 | 106.1% | 1802
1803- FP Assy Tooling/Constructability |  |  | Larry | 1803 - FP Asy Tooling/Constrblty-BROWN | 1142.2 |  | 131 | 316 | 75 | 0 | 0 | 522 | 1664.2 | 1220 | 444.2 | 36.41% | 1803
|  |  | Larry | 1804-FP Assy Measurement | 558.937 | [6 empty] | 0 | 558.937 | 502 | 56.937 | 11.34% | 1804
|  |  | Larry | 1805 - FP Assy Hardware & Fixt Procurement | 6.876 | [6 empty] | 0 | 6.876 |  | 6.876 | #DIV/0!
1806 - FP Assy Specs and Drawings |  |  | Larry | 1806 - FP Assembly specs | 26.517 |  | 92 | 382 | 40 | 0 | 0 | 514 | 540.517 |  | 540.517 | #DIV/0!
1810 - Field Period Assembly plus 1859 unplanned work |  |  | Larry | 1810-Field Period Assy -Station 1 2 3 VIOLA | 693.632 | (1) | 1266 | 2353 | 1961 | 165 | 0 | 5745 | 6438.632 | 2203 | 4235.632 | 192.3% | 1810
|  |  | Larry | 1815 - Field Period Assy |  |  | 0 | 223 | 1017 | 94 | 0 | 1334 | 1334 |  | 1334 | #DIV/0!
|  |  |  | Subtotal | 3479.245 |  | 1742 | 4064 | 3951 | 347 | 0 | 10104 | 13583.245 | 5430 | 8153.245 | 150.2%
[15 empty] | 0 | #DIV/0!
1901 - Stellarator Core Mngt & Integr |  | 19 - Stellarator Core Management and Integration | Phil | 1901 - Stellarator Core Mngtt&Integr-COLE | 2128.2 |  | 162 | 408 | 432 | 448 | 170 | 1620 | 3748.2 | 2752 | 996.2 | 36.2% | 1901
|  |  |  | SUB TOTAL WBS 1 | 53551.035 |  | 4893 | 11072 | 6577 | 1784 | 170 | 24496 | 78047.035 | 54507 | 23540.035 | 43.19%
[15 empty] | 0 | #DIV/0!
[15 empty] | 0 | #DIV/0!
2001-VPS Gas& Cond Sys Oversight |  | 21 - Fueling Systems | Larry | 2101 - Fueling Systems-BLAMCHARD | 62.893 |  | 0 | 0 | 13 | 56 | 0 | 69 | 131.893 | 151 | -19.107 | -12.65% | 2101
|  | 22 - Torus Vacuum Pumping Systems | Larry | 2201 - Vacuum Pumping Systems-BLANCHARD |  |  | 0 | 0 | 70 | 102 | 0 | 172 | 172 | 349 | -177 | -50.72% | 2201
|  | 25 Neutral Beam Refurbishment | Larry | 2501 - Neutral Beam Refurbishment | 284.946 |  | 0 | 0 | 0 | 0 | 0 | 0 | 284.946 | 284 | 0.946 | 0.3331% | 2501
|  |  |  | SUB TOTAL WBS 2 | 347.839 |  | 0 | 0 | 83 | 158 | 0 | 241 | 588.839 | 784 | -195.161 | -24.89%
[15 empty] | 0 | #DIV/0!
3101 Magnetic Diagnostics |  | 31 - Magnetic Diagnostics | Larry | 3101 - Magnetic Diagnostics-STRATTON | 611.4 | (1) | 184 | 107 | 0 | 0 | 0 | 291 | 902.4 | 426 | 476.4 | 111.8% | 3101
|  | 36 - Edge and Divertor Diagnostics | Larry | 3601 - Edge Divertor Diagnostics-STRATTON |  |  | 0 | 0 | 0 | 31 | 0 | 31 | 31 | 46 | -15 | -32.61% | 3601
|  | 38 - Electron Beam (EB) Mapping | Larry | 3801 - Electron Beam Mapping-STRATTON |  |  | 0 | 0 | 101 | 162 | 0 | 263 | 263 | 310 | -47 | -15.16% | 3801
3901 - Diagnostics sys Integration |  | 39 - Diagnostics Integration | Larry | 3901 - Diagnostics sys Integration-STRATTON | 342.506 |  | 11 | 29 | 30 | 62 | 0 | 132 | 474.506 | 361 | 113.506 | 31.44% | 3901
|  |  |  | SUB TOTAL WBS 3 | 953.906 |  | 195 | 136 | 131 | 255 | 0 | 717 | 1670.906 | 1143 | 527.906 | 46.19%
[15 empty] | 0 | #DIV/0!
4101 - AC Power |  | 41 - AC Power | Al | 4101 - AC Power-RAMAKRISHNAN | 107.351 |  | -104 | 0 | 57 | 102 | 0 | 55 | 162.351 | 430 | -267.649 | -62.24% | 4101
4301 - DC Systems |  | 43 - DC Systems | Al | 4301 - DC Systems-RAMAKRISHNAN | 369.4 |  | 0 | 11 | 274 | 318 | 0 | 603 | 972.4 | 454 | 518.4 | 114.2% | 4301
4401 - Control & Protection |  | 44 - Control and protection Systems | Al | 4401 - Control & Protection-RAMAKRISHNAN | 80.521 |  | 0 | 0 | 314 | 770 | 0 | 1084 | 1164.521 | 1309 | -144.479 | -11.04% | 4401
4501 - Power Sys Dsn & Integr |  | 45 - Power System Design and Integration | Al | 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 161.056 |  | 0 | 0 | 356 | 274 | 53 | 683 | 844.056 | 1107 | -262.944 | -23.75% | 4501
|  | 46 FCPC Bldg Mods | Al | 4601 - FCPC Bldg Mods | 1.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1 | 0.3 | 30% | 4601
|  |  |  | SUB TOTAL WBS 4 | 719.628 |  | -104 | 11 | 1001 | 1464 | 53 | 2425 | 3144.628 | 3301 | -156.372 | -4.737%
[15 empty] | 0 | #DIV/0!
|  | 51 - Network and Fiber Infrastructure | Al | 5101 - Network and Fiber |  |  | 0 | 0 | 7 | 143 | 0 | 150 | 150 |  | 150 | #DIV/0!
|  | 52 - Central Instrumentation & Control | Al | 5201 - I&C Systems-SICHTA |  |  | 0 | 0 | 81 | 115 | 0 | 196 | 196 | 611 | -415 | -67.92% | 5201
|  | 53 - Data Acquisition & Facility Computing | Al | 5301 - Data Acquisition-SICHTA |  |  | 0 | 0 | 51 | 114 | 0 | 165 | 165 | 351 | -186 | -52.99% | 5301
|  | 54 - Facility Timing & Synchronization | Al | 5401 - Facility Timing & |  |  | 0 | 0 | 12 | 193 | 0 | 205 | 205 | 221 | -16 | -7.24% | 5401
|  | 55 - Real Time Plasma & Power Supply Control Sys | Al | 5501 - Real Time Control |  |  | 0 | 0 | 17 | 112 | 0 | 129 | 129 | 162 | -33 | -20.37% | 5501
|  | 56 - Central Safety and Interlock Systems | Al | 5601 - Central Safety &Interlock Sys-SICHTA |  |  | 0 | 0 | 12 | 210 | 0 | 222 | 222 | 382 | -160 | -41.88% | 5601
5801 -Central I&C Integr |  | 58 - Central I&C management and Integration | Al | 5801 - Central I&C Integr& Oversight-SICHTA | 33.022 |  | 7 | 24 | 19 | 19 | 0 | 69 | 102.022 | 323 | -220.978 | -68.41% | 5801
|  |  |  | SUB TOTAL WBS 5 | 33.022 |  | 7 | 24 | 199 | 906 | 0 | 1136 | 1169.022 | 2050 | -880.978 | -42.97% |  | 2373
[15 empty] | 0 | #DIV/0!
|  | 61 - Water Systems | Larry | 6163 - Facility Systems Support FY04 | 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0% | 6163
|  |  | Larry | 6101 - Water Systems-DUDEK |  |  | 0 | 0 | 46 | 0 | 0 | 46 | 46 | 95 | -49 | -51.58% | 6101
|  | 62 - Cryogenic Systems | Larry | 6201 - Cryogenic Systems-DUDEK |  |  | 0 | 0 | 271 | 384 | 0 | 655 | 655 | 463 | 192 | 41.47% | 6201
|  | 63 - Utility Systems | Larry | 6301 - Utility Systems-DUDEK |  |  | 0 | 0 | 105 | 0 | 0 | 105 | 105 | 109 | -4 | -3.67% | 6301
|  | 64 - PFC/VV Heating & Cooling (Bakeout) | Larry | 6401 - PFC/VV Htng/Cooling(bakeout)- DUDEK |  |  | 0 | 0 | 107 | 466 | 0 | 573 | 573 |  | 573 | #DIV/0!
|  |  |  | SUB TOTAL WBS 6 | 24 |  | 0 | 0 | 529 | 850 | 0 | 1379 | 1403 | 691 | 712 | 103%
[15 empty] | 0 | #DIV/0!
|  | 71 Shield Wall | Larry | 7101 - Shield Wall Modif | 32.605 |  | 0 | 0 | 0 | 0 | 0 | 0 | 32.605 | 80 | -47.395 | -59.24% | 7101
7301 - Platform Design & |  | 73 - Platform Design & Fabrication | Larry | 7301 - Platform Design & | 75.836 |  | 2 | 5 | 197 | 0 | 0 | 204 | 279.836 | 164 | 115.836 | 70.63% | 7301
7401 - TC Prep & Mach Assy Planning |  | 74 - Machine Assembly Planning and Oversight | Larry | 7401 - TC Prep & Mach Assy Planning-PERRY | 854.9 |  | -308 | 23 | 615 | 857 | 230 | 1417 | 2271.9 | 1565 | 706.9 | 45.17% | 7401
|  | 75 - Test Cell and Basement Assembly Operations | Larry | 7501 - Construction Support Crew-PERRY |  |  | 0 | 0 | 336 | 806 | 265 | 1407 | 1407 | 1111 | 296 | 26.64% | 7501
|  | 75 - Test Cell and Basement Assembly Operations | Larry | 7503 - Machine Assembly (station 6)-PERRY |  |  | 0 | 0 | 1668 | 2205 | 638 | 4511 | 4511 | 1254 | 3257 | 259.7% | 7503
|  | 76 - Tooling Design & Fabrication | Larry | 7601 - Tooling Design & Fabrication-PERRY |  |  | 0 | 0 | 207 | 205 | 0 | 412 | 412 | 238 | 174 | 73.11% | 7601
|  |  |  | SUB TOTAL WBS 7 | 963.341 |  | -306 | 28 | 3023 | 4073 | 1133 | 7951 | 8914.341 | 4412 | 4502.341 | 102%
[15 empty] | 0 | #DIV/0!
8101 - Project Management & Control |  | 81 - Project Management and Control | Jim | 8101 - Project Management & Control-NEILSON | 2822.4 | (1) | 278 | 1034 | 1158 | 1074 | 299 | 3843 | 6665.4 | 4197 | 2468.4 | 58.81% | 8101
8102 - NCSX MIE Management ORNL |  |  | Jim | 8102 - NCSX MIE Management ORNL-LYON | 553.747 |  | 60 | 159 | 159 | 102 | 19 | 499 | 1052.747 | 387 | 665.747 | 172% | 8102
8202 - Engr Mgmt & Sys Eng Support |  | 82 - Project Engineering | Phil | 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2646.4 | (1) | 476 | 665 | 663 | 660 | 185 | 2649 | 5295.4 | 2835 | 2460.4 | 86.79% | 8202
8203 - Design Integration |  |  | Phil | 8203 - Design Integration-BROWN | 985.511 | (1) | 160 | 377 | 376 | 374 | 121 | 1408 | 2393.511 | 1116 | 1277.511 | 114.5% | 8203
8204 - Systems Analysis |  |  | Phil | 8204 - Systems Analysis-BROOKS | 1276.406 | (1) | 181 | 295 | 293 | 292 | 93 | 1154 | 2430.406 | 601 | 1829.406 | 304.4% | 8204
8205 - Dimensional Control Coord. |  |  | Phil | 8205 - Dimensional Control Coordin-REIERSEN | 301.9 |  | 102 | 266 | 162 | 56 | 12 | 598 | 899.9 | 332 | 567.9 | 171.1% | 8205
8210 - Project Rebaseline Estimating |  |  | Phil | 8210 - FY07 Rebaseling tasks | 37.646 |  | 19 | 0 | 0 | 0 | 0 | 19 | 56.646 |  | 56.646 | #DIV/0!
|  |  | Phil | 8215 Plant Design |  |  | 15 | 32 | 32 | 32 | 10 | 121 | 121 |  | 121 | #DIV/0!
|  |  | Jim | 8998 - Allocations-STRYKOWSKY | 1415.99 | (1) | 144 | 384 | 406 | 431 | 88 | 1453 | 2868.99 | 1577 | 1291.99 | 81.93% | 8998
|  | 84 Project Physics | Jim | 8401 - Project Physics | 323.9 | [6 empty] | 0 | 323.9 | 324 | -0.1 | -0.03086% | 8401
|  |  | Jim | 8402 - Project Physics MIE ORNL | 146.467 | [6 empty] | 0 | 146.467 | 146 | 0.467 | 0.3199% | 8402
|  | 85 - Integrated Systems Testing | Al | 8501 - Integrated Systems Testing-GENTILE |  |  | 0 | 0 | 276 | 70 | 419 | 765 | 765 | 1189 | -424 | -35.66% | 8501
8998 - Allocations |  |  |  | SUB TOTAL WBS 8 | 10510.367 |  | 1435 | 3212 | 3525 | 3091 | 1246 | 12509 | 23019.367 | 12704 | 10315.367 | 81.2%
|  |  |  | TOTAL | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138 | 48.2%
|  |  |  | DCMA | 75 | [7 empty] | 75
|  | CC - Contingency |  | Contingency-Project |  |  | 144 | 2205 | 3492 | 4450 | 4089 | 14380 | 14380 | 12804
|  |  |  | TOTAL | 67178.138 |  | 6264 | 16688 | 18560 | 17031 | 6691 | 65234 | 132412.138 | 92401
|  |  |  | (1) ADJUSTED FOR PLANNED RETROACTIVE G&A rate reduction in FY07 (estimated) | [10 empty] | 30463.293 |  | 79.4%
|  |  | Jim |  | 5262.504 |  | 482 | 1577 | 1723 | 1607 | 406 | 5795 | 11057.504 | 6631 | 4426.504
|  |  | Larry |  | 20428.331 |  | 2748 | 6786 | 7718 | 5881 | 1133 | 24266 | 44694.331 | 25685 | 19009.331
|  |  | Phil |  | 40659.653 |  | 2987 | 6085 | 4151 | 2653 | 591 | 16467 | 57126.653 | 40736 | 16390.653
|  |  | AL |  | 752.65 |  | -97 | 35 | 1476 | 2440 | 472 | 4326 | 5078.65 | 6540 | -1461.35
[5 empty] | 67103.138 |  | 6120 | 14483 | 15068 | 12581 | 2602 | 50854 | 117957.138 | 79592 | 38365.138