## P3
NCSX Electrical Power systems upgrades required for Phase III ops
cost estimate without contingency
NCSX or GPP |  | FY2010 | FY2011 | FY2012 | FY2013 | TOTAL
gpp | 411 - Auxliary AC Power Systems |  | 258.3 | 99.3 |  | 357.6
ncsx | 412 - Experimental AC Power Systems |  | 55.7 | 23.8 |  | 79.5
gpp | 421 - C-Site AC/DC Converters (based on 24 circuit 121 turn trim coils) |  |  | 900 |  | 900
gpp | 422 - D-Site AC/DC Converters |  | 69.5 |  |  | 69.5
gpp | 431 - C-Site DC Systems |  | 819 | 813.7 |  | 1632.7
gpp | 432 - D-to-C Site DC Systems | 2456 | 868.4 |  |  | 3324.4
gpp | 433 - D-Site DC Systems | 619.5 | 581.6 |  |  | 1201.1
ncsx | 441 - Electrical Interlocks |  | 603.8 | 46.5 |  | 650.3
ncsx | 442 - Kirk Key Interlocks |  | 87.4 | 18 |  | 105.4
ncsx | 443 - Real Time Control Systems |  | 42.1 |  |  | 42.1
gpp | 444 - Instrument Systems |  | 343.6 | 88.5 |  | 432.1
ncsx | 445 - Coil protection Systems |  | 371.9 | 76.3 |  | 448.2
ncsx | 446 - Ground Fault Monitoring |  | 318.5 | 24.6 |  | 343.1
ncsx | 451 - System Design and Interfaces |  | 267.1 | 77.1 |  | 344.2
ncsx | 452 - Electrical Systems Support |  | 644.6 | 185 |  | 829.6
ncsx | 453 - System Testing (PTP's) |  |  | 215.5 |  | 215.5
gpp | 460 - FCPC Mods |  | 112 |  |  | 112
| NCSX (plus 30% contingency added) | 0 | 2391.1 | 666.8 | 0 | 3057.9
| GPP (plus 30% contingency added) | 3075.5 | 3052.4 | 1901.5 | 0 | 8029.4
cost estimate with 30%contingency
NCSX or GPP |  | FY2010 | FY2011 | FY2012 | FY2013 | TOTAL
gpp | 411 - Auxliary AC Power Systems | 0 | 335.79 | 129.09 | 0 | 464.88
ncsx | 412 - Experimental AC Power Systems | 0 | 72.41 | 30.94 | 0 | 103.35
gpp | 421 - C-Site AC/DC Converters (based on 24 circuit 121 turn trim coils) | 0 | 0 | 1170 | 0 | 1170
gpp | 422 - D-Site AC/DC Converters | 0 | 90.35 | 0 | 0 | 90.35
gpp | 431 - C-Site DC Systems | 0 | 1064.7 | 1057.81 | 0 | 2122.51
gpp | 432 - D-to-C Site DC Systems | 3192.8 | 1128.92 | 0 | 0 | 4321.72
gpp | 433 - D-Site DC Systems | 805.35 | 756.08 | 0 | 0 | 1561.43
ncsx | 441 - Electrical Interlocks | 0 | 784.94 | 60.45 | 0 | 845.39
ncsx | 442 - Kirk Key Interlocks | 0 | 113.62 | 23.4 | 0 | 137.02
ncsx | 443 - Real Time Control Systems | 0 | 54.73 | 0 | 0 | 54.73
gpp | 444 - Instrument Systems | 0 | 446.68 | 115.05 | 0 | 561.73
ncsx | 445 - Coil protection Systems | 0 | 483.47 | 99.19 | 0 | 582.66
ncsx | 446 - Ground Fault Monitoring | 0 | 414.05 | 31.98 | 0 | 446.03
ncsx | 451 - System Design and Interfaces | 0 | 347.23 | 100.23 | 0 | 447.46
ncsx | 452 - Electrical Systems Support | 0 | 837.98 | 240.5 | 0 | 1078.48
ncsx | 453 - System Testing (PTP's) | 0 | 0 | 280.15 | 0 | 280.15
gpp | 460 - FCPC Mods | 0 | 145.6 | 0 | 0 | 145.6
| NCSX (plus 30% contingency added) | 0 | 3108.43 | 866.84 | 0 | 3975.27
| GPP (plus 30% contingency added) | 3998.15 | 3968.12 | 2471.95 | 0 | 10438.22
|  | 3998.15 | 7076.55 | 3338.79 | 0 | 14413.49