| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: April 29, 2005 |
| ECP No: 030 | ECP Title: Planning Changes for Risk Management |
| Required Reviewers |
| Required Reviewers for this ECP: WBS Managers, Project Engineers, NCSX QA, NCSX ES&H, NCSX Engineering Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Adopt new baseline |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 29, 2005 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: This change is being made within the currently approved performance baseline for cost, schedule, and quality risk management reasons. This ECP reflects a redistribution of budget to address cost growth risks with offsetting work reductions. It also re-aligns the schedule consistent with recent planning updates for the modular coil winding design, various vacuum vessel jobs, dimensional control planning, and other jobs. The cooling water system design and ISTP document preparation tasks have been optimized within the CD-4 requirements, resulting in some reductions. This ECP incorporates a new plan for fabricating the TF coil windings at PPPL instead of procuring them from industry. This decision was made following a “make or buy” analysis which concluded that the change to in-house fabrication would be cost-neutral while reducing quality risks in the finished product. These changes do not affect CD-4 deliverables nor require application of contingency. The project is in the process of planning a new performance baseline in response to reduced DOE funding guidance for future years. It is currently estimated that those funding-related changes will delay the project completion date by 14 months (to July, 2009) and increase the TEC by $6.0M (to $92.3M). That proposed DOE directed baseline change has been submitted to DOE and is pending. Although that directed baseline change has not been approved yet, the attached resource-loaded schedule anticipates its approval and is being used for planning purposes. The changes in the performance measurement baseline being implemented with this ECP are necessary, independent of the pending funding-driven changes in the overall baseline. Impacted WBS Elements: All Attachments: Updated Resource Loaded Schedule reflecting the new PMB Assessment of Other Options: Not making these proposed budget and schedule changes would result in excessive cost and schedule risks. Procuring the TF coils from industry would result in excessive quality risks. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 29, 2005 |
| Detailed Description of the Change: Impacts of Change (Briefly Describe): WBS ECP-029 ($K) ECP-030 ($K) Change ($K) Major Reasons 12 – Vacuum Vessel $9,168K $9,204K $36K ($137K) full size well sample; +$43K seals; +$5K templates for VVSA; +99K for Engrg Admin; +$31K ORNL VVSA design sppt. 13 – Conventional Coils $4,552 $4,552 - 14 – Modular Coils $26,839K $27,062K $223K +$223K TRC & final Winding Dsn & Analysis 15 - Structures $1,381K $1,381K - 16 – Coil Services $1,036K $1,036K - 17 – Cryostat & Base Sppt $1,321K $1,321K - 18 – Field Period Assembly $5,118K $5,118K - 19 – Sellarator Core Mgmt $2,421K $2,421K - WBS 1 - Stellarator Core $51,837K $52,096K $259K WBS 2 – Fueling & Pumping $778K $778K - WBS 3 – Diagnostics $1,117K $1,117K - WBS 4 – Power Systems $3,214K $3,214K - WBS 5 – Central I&C $1,915K $1,915K - WBS 6 – Facility Systems $825K $674K ($151K) ($151K) C-Site Cooling Water Commissioning WBS 7 – Machine Assembly $4,208K $4,208K - WBS 8 – Project Mgmt & Oversight $9,713K $9,605K ($108K) $50K dimensional control coordination in FY2005; ($37K) project management sppt in FY2006; ($121K) ISATP documentation req’d for CD-4 PPPL Allocations $1,129K $1,129K - Contingency $11,610K $11,610K - TOTALS $86,345K $86,345K - Check typo in WBS 6 ECP-030 entry |