| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: April 21, 2005 |
| ECP No: 030 | ECP Title: DOE Directed FY2005 Rebaseline |
| Required Reviewers |
| Required Reviewers for this ECP: WBS Managers, Project Engineers, NCSX QA, ES&H, NCSX Engineering Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions (1) Revise cost and schedule baseline by April 30, 2005 to reflect revised DOE annual funding guidance. |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 19, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: DOE directed rebaseline to reflect revised annual funding guidance. Impacted WBS Elements: WBS Elements: 12, 13, 14, 15, 16, 17, 18, 19, 2, 3, 4, 5, 6, 7, & 8. In addition, contingency adjusted to reflect added stretch-out costs. Impacts of Change (Briefly Describe): At DOE direction, NCSX Project rebaselined to support a flat funding profile of $15.9 peak (FY2006-FY2008). As a result of this direction, the following cost and schedule impacts were noted: Project Stretch Out and Rate Adjustments Work scope stretched out; Overhead rates revised to reflect most recent PPPL and ORNL rates; Impact of escalation due to stretch out included; First plasma revised to July 2009 with 5 months schedule contingency; and Re-evaluated contingency balance for the remaining work scope. Contingency balance is $12.8M, or 25% of work remaining from April 1, 2005. Summary of Level I baseline parameters: TEC = $92.3M (Increase of ~$6.0M) Project completion date: July, 2009 Funding profile (BA) for remainder of the project: FY2006 FY2007 FY2008 FY2009 $15.9M $15.9M $15.9M 3.4M Assessment of Other Options: None |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 21, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Revised Resource Loaded Baseline Update PEP to reflect this data Description of Change: The Table Below Summarizes the Cost Impact of this ECP: WBS Element Previous Baseline (ECP-029) ($) Current Baseline ($) Change Due to Stretchout ($) 12 – Vacuum Vessel $9,168K $9,439K $271K 13 – Conventional Coils $4,552K $4,779K $226K 14 – Modular Coils $26,839K $28,046K $1,207K 15 - Structures $1,381K $1,413K $32K 16 – Coil Services $1,036K $1,146K $110K 17 – Cryostat & Base Suppt Structure $1,321K $1,361K $40K 18 – Field Period Assembly $5,118K $5,424K $306K 19 – Stellarator Core Mgmt & Integr $2,421K $2,752K $331K Subtotal WBS 1 – Stellarator Core $51,837K $54,360K $2,523K WBS 2 – Auxilliary Systems $778K $783K $5K WBS 3 – Diagnostic Systems $1,117K $1,143K $26K WBS 4 – Electrical Power Systems $3,214K $3,301K $87K WBS 5 – I&C Systems $1,915K $2,050K $134K WBS 6 – Facility Systems $825K $842K $17K WBS 7 Test Cell Prep & Machine Assy $4,208K $4,411K $203K Subtotal WBS 8 – Project Oversight & Suppt $10,841K $12,633K $1,791K Subtotal $74,736K $79,523K $4,787K Contingency $11,610K $12,804K $1,194K TOTALS $86,345K $92.326K $5,981K Of this cost increase of $4,787K (before contingency): Management (Period Dependent) - $1,186K Field Oversight & Supervision (Task Dependent) - $1,225K Overhead and Rates - $2,375K Overall contingency ($12,804K) increased to 25% on the work remaining. |
| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 21, 2005 |
| Continuation Sheet: The Table Below Summarizes the Schedule Impact of this ECP: |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 21, 2005 |
| Continuation Sheet: The Table Below Provides the Contingency Analysis: The Major Drivers of Contingency are: WBS 12 (Vacuum Vessel) and 14 (Modular Coils) – maintain 10% on the balance of the VVSA and MCWF contracts WBS 13 (Conventional Coils) – fabrication risk based upon preliminary estimate to complete – FDR scheduled in May 2005 WBS 18 (Field Period Assembly) – estimate for field period assembly fixturing based upon initial supplier contacts – hardware design still in conceptual stage WBS 18 (Field Period Assembly) and WBS 82 (Project Engineering) – dimensional control coordination and support WBS 14 (Modular Coil) – modular coil assembly hardware (nuts, bolts, & shims) and MC winding operations |