## Sheet1
NCSX Budget Status
Changes to Date
[8 empty] | CD-2 Baseline Jan 04 |  |  | ECP-6 (Apr 2004) |  | ECP-11 (July 2004) | [6 empty] | ECP 8 Oct 04
[9 empty] | Contingency ETC (From Jan 04) | [13 empty] | Contingency ETC (From Oct 04)
[6 empty] | WBS |  | BAC | $ | % | Changes | BAC | Changes | BAC |  |  |  |  | Potential Increases | EAC | Forecast thru FY04 | ETC | $ | %
[6 empty] | 11 | Limiters | 8 |  |  | -0.4 | 7.6 | 0 | 7.6 | [5 empty] | 7.6 | 8 | -0.4 | 0.4
[6 empty] | 12 | Vacuum Vessel | 6065 | 1776.1292 | 38.86% | 843 | 6908 | 381 | 7289 | Approved Changes ECP 9 & 11) |  |  | Risk Identified | 0 | 6908 | 3093 | 3815 | 933.1292 | 24.46%
[6 empty] | 13 | Conventional Coils | 4168 | 1023.3425 | 25.62% | 45 | 4213 | 0 | 4213 |  |  |  | in June |  | 4213 | 580 | 3633 | 978.3425 | 26.93%
[6 empty] | 14 | Modular Coils | 20548 | 5822.6763 | 34.35% | -53 | 20495 | 1735 | 22230 | WBS 12 Add'l Ports |  | 240 | 300 | 0 | 20495 | 9718 | 10777 | 5875.6763 | 54.52%
[6 empty] | 15 | Structures | 1450 | 441.2795 | 30.66% | -14 | 1436 | 0 | 1436 | WBS 18 Add'l port welding |  | 75 | 75 |  | 1436 | 171 | 1265 | 455.2795 | 35.99%
[6 empty] | 16 | Coil Services | 1037 | 248.86 | 24% | 0 | 1037 | 0 | 1037 | WBS 12 Port extensions |  | 150 | 150 |  | 1037 | 0 | 1037 | 248.86 | 24%
[6 empty] | 17 | Cryostat & Base Sprt Struct | 1306 | 365.2385 | 28.31% | -6 | 1300 | 0 | 1300 | WBS 14 MCWF production casting |  | 75 |  |  | 1300 | 134 | 1166 | 371.2385 | 31.84%
[6 empty] | 18 | Field Period Assembly | 5110 | 1471.0973 | 29.17% | 54 | 5164 | -91 | 5073 | WBS 14 Protype Winding |  | -344.7 | -265 | 0 | 5164 | 779 | 4385 | 1417.0973 | 32.32%
[6 empty] | 19 | Stellarator Core Mngmt/Integr | 2663 | 328.5676 | 14.68% | 2 | 2665 | 0 | 2665 | WBS 18 Eliminate Full Size M-U |  | -196.4 | -199 |  | 2665 | 936 | 1729 | 326.5676 | 18.89%
[6 empty] | 1 | Stellarator Core Systems | 42355 | 11477.1909 | 31.39% | 870.6 | 43225.6 | 2025 | 45250.6 | WBS 14 MCWF Design & Analysis |  | 925 | 498 | 0 | 43225.6 | 15419 | 27806.6 | 10606.5909 | 38.14%
[6 empty] | 2 | Heating, Fueling & Vac Sys | 1630 | 204.6875 | 14.42% | 63 | 1693 | 0 | 1693 | WBS 14 R&D (TRC dsn,mat'l test) |  | 649.7 | 547 |  | 1693 | 531 | 1162 | 141.6875 | 12.19%
[6 empty] | 3 | Diagnostics | 1685 | 399.2023 | 26.63% | 8 | 1693 | 0 | 1693 | WBS 14 Winding Facilities |  | 205 |  |  | 1693 | 239 | 1454 | 391.2023 | 26.91%
[6 empty] | 4 | Electrical Power Systems | 5325 | 997.9747 | 19.22% | 6 | 5331 | 0 | 5331 | WBS 14 Winding Fab |  | 216 | 750 |  | 5331 | 1566 | 3765 | 991.9747 | 26.35%
[6 empty] | 5 | Central I&C Systems | 2580 | 243.6191 | 9.547% | -0.3 | 2579.7 | 0 | 2579.7 | WBS 18 Reschedul tooling dsn |  | 30 |  |  | 2579.7 | 34 | 2545.7 | 243.9191 | 9.582%
[6 empty] | 6 | Facility Systems | 2039 | 391.1473 | 19.41% | 31.6 | 2070.6 | 0 | 2070.6 | [5 empty] | 2070.6 | 31 | 2039.6 | 359.5473 | 17.63%
[6 empty] | 7 | Test Cell Prep/ Machine Assy | 4254 | 788.1555 | 19.5% | -16.7 | 4237.3 | 0 | 4237.3 |  |  | 2024.6 | 1856 | 0 | 4237.3 | 566 | 3671.3 | 804.8555 | 21.92%
[6 empty] | 8 | Project Oversight/Support | 10566 | 1408.0228 | 16.28% | 227.4 | 10793.4 | 0 | 10793.4 |  |  |  |  | 0 | 10793.4 | 4081 | 6712.4 | 1180.6228 | 17.59%
[6 empty] | subtotal |  | 70434 | 15910 | 25.67% | 1189.6 | 71623.6 | 2025 | 73648.6 |  |  |  |  | 0 | 71623.6 | 22467 | 49156.6 | 14720.4 | 29.95%
[6 empty] | Contingency |  | 15910 |  |  | -1190 | 14720 | -2025 | 12695 |  |  |  |  | 0 | 14720
[6 empty] | Pct of ETC |  | 25.67% |  |  |  | 25.47% |  | 22.35% | [5 empty] | 29.94%
[6 empty] | Total |  | 86344 |  |  |  | 86343.6 |  | 86343.6 | [5 empty] | 86343.6
[6 empty] | Spent |  | 8466 | thru Dec 04 |  | thru Apr 04 | 13830 | thru July 04 | 17522 | [5 empty] | 22460
[6 empty] | ETC |  | 61968 |  |  |  | 57793.6 |  | 56810 | [5 empty] | 49163.6
5
[6 empty] | 6 | [8 empty] | 2 - | Plasma Heating, Fueling & Vac Systems |  |  | Risk-low | WBS 121 Design
[6 empty] | 6 | [8 empty] | 3 - | Diagnostics |  |  | Risk -Moderate | WBS 121 VVSA FFP 20% increase
[6 empty] | 6 | [8 empty] | 4 - | Electrical Power Systems |  |  | Risk-High | WBS 142 MC Winding (chill plate instl) | $260 M&S *1.29 + 18 x 2 x 4 x 40 x $72/hr
[6 empty] | 6 | [8 empty] | 5 - | Central I&C Systems |  |  | Risk-Moderate | WBS 141 MCWF 20% increase
[6 empty] | 6 | [8 empty] | 6 - | Facility Systems
[6 empty] | 5 | [8 empty] | 7 - | Test Cell Preparation and Machine Assy |  |  | - Risk-high | WBS 142 MCWF Prototype Winding
[6 empty] | 6 | [8 empty] | 8 - | Project Oversight and Support |  |  | Risk -Moderate | WBS 142 MC winding TRC & conductor testing
[6 empty] | 5 | [12 empty] | - Risk-high | Eliminate design and fab of full size mockups. Use production articles for training.
[6 empty] | 5 | [12 empty] | ? | WBS 18 add'l port installation
[6 empty] | 5 | [12 empty] | 0 | WBS 18 LOE oversight FY04
[11 empty] | 1994.6 | [7 empty] | Risk-High | WBS 7 TC crane capacity upgrade
[19 empty] | Risk-moderate | WBS 81 Project oversight
NCSX Budget Status | [18 empty] | Risk-Moderate | WBS 82 Project Engr design & analysis support
0
|  | ECP-14 (CD-3 Sept 04) |  | ECP 18 (Dec 04)
WBS |  | BAC | Change | BAC | Changes
11 | Limiters | 0.06 | 0 | 0.06
12 | Vacuum Vessel | 8531.4 | 205.97 | 8737.37 | VVSA contract oversight & Field weld joint full size sample
13 | Conventional Coils | 4303.7 | 137.39 | 4441.09 | Simplification of trim coil -$200k; Re-estimatedTF design & fab +337k
14 | Modular Coils | 25055.1 | 1145.25 | 26200.35 | Winding facility+515; MCWF prototype +230; MC design & oversight +400
15 | Structures | 1447.8 | -67.09 | 1380.71 | Re-estimate & re-allocate design labor
16 | Coil Services | 1036.9 | -0.9 | 1036 | Rates, escalation etc.
17 | Cryostat & Base Sprt Struct | 1301.1 | 20.04 | 1321.14 | Rates, escalation etc.
18 | Field Period Assembly | 5065.7 | 52.39 | 5118.09 | Re-estimate & re-allocate design labor
19 | Stellarator Core Mngmt/Integr | 2651.5 | -230.48 | 2421.02 | Re-estimated oversight
1 | Stellarator Core Systems | 49393.26 | 1262.57 | 50655.83
2 | Heating, Fueling & Vac Sys | 837 | -57.32 | 779.68 | Simplified fueling system
3 | Diagnostics | 1160.9 | -44.2 | 1116.7 | Rates, escalation etc.
4 | Electrical Power Systems | 3707.2 | -491.6 | 3215.6 | D-site pwr supplies transferred to a non-MIE account (-439)
5 | Central I&C Systems | 2188.8 | -272.1 | 1916.7 | Re-estimated design & programming labor
6 | Facility Systems | 1143.4 | -318.2 | 825.2 | NB and bakeout water cooling system scope reduction.
7 | Test Cell Prep/ Machine Assy | 4274.4 | -66.51 | 4207.89 | Reduced FY06 oversight & planning; Reduced platform estimate.
8 | Project Oversight/Support | 10186.1 | 392.5 | 10578.6 | Project design integration and Indirect allocations
subtotal |  | 72891.06 | 405.14 | 73296.2
Contingency |  | 13454.9 | -402.01 | 13052.89
| TEC = | 86345.96 |  | 86349.09
Contingency
| VVSA and MCWF |  | 10% | 1269
| Balance of project |  | 30% | 11784
|  |  | 25% | 13053 |  |  |  | High = | Change Candidate. Additional scope or task being pereformed. Additional tech complexity. Offsetting savings not apparent. Cost yet to be estimated.
[8 empty] | Moderate = | Probable Change Candidate. Additional scope or task being pereformed. Additional tech complexity. Cost yet to be estimated but may be offset.
[8 empty] | Low = | Current issues but future offsets/controls may limit impact.