## Sheet10
NCSX Contingency Analysis
|  |  | Project Estimate | [9 empty] | DOE Assessment |  |  |  |  | Variance ($K)
[6 empty] | Contingency Remaining (baseline Risk assessment |  |  | Subjective add'l |  |  |  | To Date | To Go | Contingency |  | Total ($K)
|  |  | ECP18 Budget | BCWP (11/1/04) | BCWR | % on BCWR | $ | Sub total | contingency allowance | TOTAL CONT | TOTAL % | TEC | Cost | Cost | $ | %
| 11 | In Vessel Components | 60 | 60 |  |  |  | 60 |  | 0 |  | 60
| 12 | Vacuum Vessel Systems | 4005043.48 | 2877340.8748 | 1127702.6052 | 35.31% | 398210.4003 | 4403253.8803 |  | 398210.4003 | 35.31% | 4403253.8803
|  | VVSA | 4732000 | 138865.275 | 4593139.725 | 10% | 459313.9725 | 5191313.9725 | 100000 | 559313.9725 | 12.18% | 5291313.9725
| 13 | Conventional Coils | 4441000 | 456473.0865 | 3984526.9135 | 25.23% | 1005439.8068 | 5446439.8068 | 200000 | 1205439.8068 | 30.25% | 5646439.8068
| 14 | Mod Coils | 17992000 | 9990253.834 | 8001746.166 | 39.46% | 3157713.5079 | 21149713.5079 | 300000 | 3457713.5079 | 43.21% | 21449713.5079
|  | MCWF | 8207990 | 111120 | 8096870 | 10% | 809687 | 9017677 |  | 809687 | 10% | 9017677
| 15 | Coil Support Structures | 1380705.64 | 53673.8 | 1327031.84 | 31.88% | 423018.016 | 1803723.656 |  | 423018.016 | 31.88% | 1803723.656
| 16 | Coil Services | 1035439.93 | 0 | 1035439.93 | 24.86% | 257412.8362 | 1292852.7662 |  | 257412.8362 | 24.86% | 1292852.7662
| 17 | Cryostat & Base Support Structure | 1321940.2 | 164186.18 | 1157754.02 | 29.38% | 340187.2412 | 1662127.4412 |  | 340187.2412 | 29.38% | 1662127.4412
| 18 | Field Period Assembly | 5118000 | 613715.904 | 4504284.096 | 36.51% | 1644330.5286 | 6762330.5286 | 200000 | 1844330.5286 | 40.95% | 6962330.5286
| 19 | Stellarator Core Mgmt. & Integration | 2421000 | 998240.2331 | 1422759.7669 | 9.558% | 135992.5957 | 2556992.5957 |  | 135992.5957 | 9.558% | 2556992.5957
1 Total | Stellarator Core Systems |  | 50655179.25 | 15403929.1873 | 35251255.0627 | 24.49% | 8631305.9054 | 59286485.1554 |  | 9431305.9054 | 26.75% | 60086485.1554
| 21 | Fueling Systems | 80716.25 | 0 | 80716.25 | 14% | 11300.275 | 92016.525 |  | 11300.275 | 14% | 92016.525
| 22 | Torus Vacuum Pump | 390077.67 | 60196 | 329881.67 | 14% | 46183.4338 | 436261.1038 |  | 46183.4338 | 14% | 436261.1038
| 25 | Neutral Beam Injection System | 308883 | 308883.41 | 0 |  | 0 | 308883 |  | 0 |  | 308883
2 Total | Plasma Heating Fueling & Vac Systems |  | 779676.92 | 369079.41 | 410597.92 | 14% | 57483.7088 | 837160.6288 |  | 57483.7088 | 14% | 837160.6288
| 31 | Magnetic Diagnostics | 413882.95 | 0 | 413882.95 | 30% | 124164.885 | 538047.835 |  | 124164.885 | 30% | 538047.835
| 36 | Edge & Divertor Diagnostics | 42865.2 | 0 | 42865.2 | 20% | 8573.04 | 51438.24 |  | 8573.04 | 20% | 51438.24
| 38 | Electron Beam (EB) Mapping | 290578.3 | 0 | 290578.3 | 34% | 98796.622 | 389374.922 |  | 98796.622 | 34% | 389374.922
| 39 | Diagnostics Integration | 369405.96 | 239126.7596 | 130279.2004 | 30% | 39083.7601 | 408489.7201 |  | 39083.7601 | 30% | 408489.7201
3 Total | Diagnostics |  | 1116732.41 | 239126.7596 | 877605.6504 | 30.84% | 270618.3071 | 1387350.7171 |  | 270618.3071 | 30.84% | 1387350.7171
| 41 | AC Power | 484848.3 | 157226.72 | 327621.58 | 18% | 58971.8844 | 543820.1844 |  | 58971.8844 | 18% | 543820.1844
| 43 | DC Systems | 445515.54 | 29652.924 | 415862.616 | 18% | 74855.2709 | 520370.8109 |  | 74855.2709 | 18% | 520370.8109
| 44 | Control & protection system | 1216096.4 | 1054.9 | 1215041.5 | 19.6% | 238100.87 | 1454197.27 |  | 238100.87 | 19.6% | 1454197.27
| 45 | Power System Design & Integration | 1067788.43 | 146517.3 | 921271.13 | 20.12% | 185345.8386 | 1253134.2686 |  | 185345.8386 | 20.12% | 1253134.2686
| 46 | FCPC Building Modification | 1300 | 1300 |  | 0% |  | 1300 |  | 0 | 0% | 1300
4 Total | Electrical Power Systems |  | 3215548.67 | 335751.844 | 2879796.826 | 19.35% | 557273.8639 | 3772822.5339 |  | 557273.8639 | 19.35% | 3772822.5339
| 51 | TCP/IP Infrastructure System | 288918.42 | 24258.2 | 264660.22 | 5% | 13233.011 | 302151.431 |  | 13233.011 | 5% | 302151.431
| 52 | Central Instrumentation & Controls System | 570784.93 | 0 | 570784.93 | 10% | 57078.493 | 627863.423 |  | 57078.493 | 10% | 627863.423
| 53 | Data Acquisition & Facility Computing | 328360.65 | 0 | 328360.65 | 16% | 52537.704 | 380898.354 |  | 52537.704 | 16% | 380898.354
| 54 | Facility Timing & Synchronization System | 206792.2 | 0 | 206792.2 | 14% | 28950.908 | 235743.108 |  | 28950.908 | 14% | 235743.108
| 55 | Real Time Plasma & Power Control Systems | 151245.8 | 0 | 151245.8 | 8% | 12099.664 | 163345.464 |  | 12099.664 | 8% | 163345.464
| 56 | Central Safety Interlock System | 357661 | 0 | 357661 | 8% | 28612.88 | 386273.88 |  | 28612.88 | 8% | 386273.88
| 58 | Central I&C Integration | 12900 | 1083.6 | 11816.4 | 3% | 354.492 | 13254.492 |  | 354.492 | 3% | 13254.492
5 Total | Central I&C Systems |  | 1916663 | 25341.8 | 1891321.2 | 10.2% | 192867.152 | 2109530.152 |  | 192867.152 | 10.2% | 2109530.152
| 61 | Water Cooling Systems | 240451.64 | 0 | 240451.64 | 20% | 48090.328 | 288541.968 |  | 48090.328 | 20% | 288541.968
| 62 | Cryogenic System | 439590.05 | 0 | 439590.05 | 20% | 87918.01 | 527508.06 |  | 87918.01 | 20% | 527508.06
| 63 | Utility Systems | 103482.56 | 0 | 103482.56 | 20% | 20696.512 | 124179.072 |  | 20696.512 | 20% | 124179.072
| 65 | Facility System Integration | 41600 | 41600 | 0 | 0% | 0 | 41600 |  | 0 | 0% | 41600
6 Total | Facility Systems |  | 825124.25 | 41600 | 783524.25 | 20% | 156704.85 | 981829.1 |  | 156704.85 | 20% | 981829.1
| 71 | Shield Wall Reconfiguration | 32150 | 32150 |  |  |  | 32150 |  | 0 | 0% | 32150
| 72 | Control Room Refurbishment | 50210.16 | 0 | 50210.16 | 10% | 5021.016 | 55231.176 |  | 5021.016 | 10% | 55231.176
| 73 | Platform Design | 161261.2 | 0 | 161261.2 | 8.476% | 13669.24 | 174930.44 |  | 13669.24 | 8.476% | 174930.44
| 74 | Planning/Oversight | 1503001.4 | 380841.942 | 1122159.458 | 15.57% | 174767.8107 | 1677769.2107 |  | 174767.8107 | 15.57% | 1677769.2107
| 75 | Machine Assembly Planning & Oversight | 2238679.26 | 0 | 2238679.26 | 24.18% | 541287.9984 | 2779967.2584 | 333000 | 874287.9984 | 39.05% | 3112967.2584
| 76 | Tooling Design & Fabrication | 223039.74 | 0 | 223039.74 | 24% | 53529.5376 | 276569.2776 |  | 53529.5376 | 24% | 276569.2776
7 Total | Test Cell Preparation & Machine Assy |  | 4208341.76 | 412991.942 | 3795349.818 | 20.77% | 788275.6027 | 4996617.3627 |  | 1121275.6027 | 29.54% | 5329617.3627
| 81 | Project Management & Control | 3450278.9 | 1360955.0813 | 2089323.8187 | 17% | 355185.0492 | 3805463.9492 | 100000 | 455185.0492 | 21.79% | 3905463.9492
| 82 | Project Engineering | 4367524.65 | 1879044.9421 | 2488479.7079 | 17% | 423041.5503 | 4790566.2003 |  | 423041.5503 | 17% | 4790566.2003
| 84 | Project Physics | 412167.16 | 412167.16 |  |  |  | 412167.16 |  | 0 | 0% | 412167.16
| 85 | Integrated System Testing | 1220071.79 | 0 | 1220071.79 | 25.39% | 309836.868 | 1529908.658 |  | 309836.868 | 25.39% | 1529908.658
| A | Allocations | 1128560.93 | 352365.4404 | 776195.4896 | 10% | 77619.549 | 1206180.479 |  | 77619.549 | 10% | 1206180.479
8 Total | Project Oversight & Support |  | 10578603.43 | 4004532.6238 | 6574070.8062 | 17.73% | 1165683.0165 | 11744286.4465 |  | 1265683.0165 | 19.25% | 11844286.4465
[8 empty] | 0 |  | 0 |  | 0
|  |  | 73295869.69 | 20832353.5668 | 52463521.5332 | 22.53% | 11820212.4063 | 85116082.0963 | 1233000 | 13053212.4063 | 24.88% | 86349082.0963
73295875.1
|  | VVSA & MCWF | 12939990 | 249985.275 | 12690009.725 | 10% | 1269000.9725 | 14208990.9725 |  | 1369000.9725 | 10.79% | 14308990.9725
|  | Balance of Project | 60355879.69 | 20582368.2918 | 39773511.8082 | 26.53% | 10551211.4338 | 70907091.1238 |  | 11684211.4338 | 29.38% | 72040091.1238

## Sheet13
Sum of $

## P3
ACT | TITLE | BCWP | ECP18 Budget | BCWR | WBS1 | WBS2 | WBS3 | JJJJ | CCXX | PCT | $
121-100 | S005243 #1-Die Material | 138865.275 | 298635 | 159769.725 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 15976.9725
121-125 | S005243 #6-Second 1/3 of vsl plates formed | 0 | 200000 | 200000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 20000
121-130 | S005243 #7-Last 1/3 of vsl plates formed | 0 | 200000 | 200000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 20000
121-110 | S005243 #3-Fixture material procured | 0 | 220000 | 220000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 22000
121-120 | S005243 #5-1/3 of Vessel plates formed | 0 | 260000 | 260000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 26000
121-140 | S005243 #9-Second VVSA fabricated | 0 | 350000 | 350000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 35000
121-145 | S005243 #10-Third VVSA fabricated | 0 | 350000 | 350000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 35000
121-135 | S005243 #8-One VVSA fabricated | 0 | 375000 | 375000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 37500
121-155 | S005243 #12-Receipt /Acceptance of 2nd VVSA | 0 | 375000 | 375000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 37500
121-160 | S005243 #13-Receipt/Acceptance of 3rd VVSA | 0 | 375000 | 375000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 37500
121-150 | S005243 #11-Receipt/Acceptance of 1st VVSA | 0 | 375560 | 375560 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 37556
121-105 | S005243 #2-Vessel material procured | 0 | 402810 | 402810 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 40281
121-115 | S005243 #4-Dies Manufactured | 0 | 464000 | 464000 | 1 | 12vvsa | 121 | 1250 | 10 | 10% | 46400
121-165 | S005243 #14-Delivefy of tooling,dies,fixtures | 0 | 486000 | 486000 | 1 | 12vvsa | 121 | 4593139.725 | 10 | 10% | 48600
124-031 | Title III engr WBS 124 | 0 | 341.6 | 341.6 | 1 | 12 | 124 | 1204 | 30 | 30% | 102.48
124-041 | VV Supports Fab/assy WBS 124 | 0 | 675.99 | 675.99 | 1 | 12 | 124 | 1204 | 30 | 30% | 202.797
125-015 | Title III design Local I&C | 0 | 2650.32 | 2650.32 | 1 | 12 | 125 | 1204 | 30 | 30% | 795.096
125-037 | Procurement Local I&C | 0 | 3179.16 | 3179.16 | 1 | 12 | 125 | 1204 | 30 | 30% | 953.748
124-011 | Final design WBS 124 VV supports | 5465.11 | 10930.22 | 5465.11 | 1 | 12 | 124 | 1203 | 30 | 30% | 1639.533
124-011 | Final design WBS 124 VV supports | 5605.24 | 11210.48 | 5605.24 | 1 | 12 | 124 | 1203 | 30 | 30% | 1681.572
124-031 | Title III engr WBS 124 | 0 | 8834.4 | 8834.4 | 1 | 12 | 124 | 1204 | 30 | 30% | 2650.32
124-011.1 | Lateral VV supports | 0 | 11484.72 | 11484.72 | 1 | 12 | 124 | 1203 | 30 | 30% | 3445.416
125-001 | Prelim design WBS 125 local I&C | 0 | 11631.96 | 11631.96 | 1 | 12 | 125 | 1203 | 30 | 30% | 3489.588
125-011 | Final design WBS 125 local I&C | 0 | 11661.41 | 11661.41 | 1 | 12 | 125 | 1203 | 30 | 30% | 3498.423
124-011.1 | Lateral VV supports | 0 | 11779.2 | 11779.2 | 1 | 12 | 124 | 1203 | 30 | 30% | 3533.76
124-037 | VV Supports Procurement WBS 124 | 0 | 31089 | 31089 | 1 | 12 | 124 | 1204 | 30 | 30% | 9326.7
123-031 | Title III engr WBS 123 | 0 | 1344.24 | 1344.24 | 1 | 12 | 123 | 1204 | 32 | 32% | 430.1568
122-011 | Final design WBS 122 Thermal insulation | 823.8225 | 3295.29 | 2471.4675 | 1 | 12 | 122 | 1203 | 32 | 32% | 790.8696
122-037 | VV Insulation Procurement WBS 122 | 0 | 3470 | 3470 | 1 | 12 | 122 | 1204 | 32 | 32% | 1110.4
122-031 | Title III engr WBS 122 | 0 | 3695.07 | 3695.07 | 1 | 12 | 122 | 1204 | 32 | 32% | 1182.4224
123-041 | VV Heating/Cooling Fab/Assy WBS 123 | 0 | 3774 | 3774 | 1 | 12 | 123 | 1204 | 32 | 32% | 1207.68
122-011 | Final design WBS 122 Thermal insulation | 2220.7875 | 8883.15 | 6662.3625 | 1 | 12 | 122 | 1203 | 32 | 32% | 2131.956
123-031 | Title III engr WBS 123 | 0 | 7067.52 | 7067.52 | 1 | 12 | 123 | 1204 | 32 | 32% | 2261.6064
123-041 | VV Heating/Cooling Fab/Assy WBS 123 | 0 | 11113.44 | 11113.44 | 1 | 12 | 123 | 1204 | 32 | 32% | 3556.3008
122-011 | Final design WBS 122 Thermal insulation | 17833.2054 | 31507.43 | 13674.2246 | 1 | 12 | 122 | 1203 | 32 | 32% | 4375.7519
122-031 | Title III engr WBS 122 | 0 | 18257.76 | 18257.76 | 1 | 12 | 122 | 1204 | 32 | 32% | 5842.4832
122-037 | VV Insulation Procurement WBS 122 | 0 | 105792.9 | 105792.9 | 1 | 12 | 122 | 1204 | 32 | 32% | 33853.728
123-037 | VV Heating/Cooling Distr Procurement WBS 123 | 0 | 318062.4 | 318062.4 | 1 | 12 | 123 | 1204 | 32 | 32% | 101779.968
1202-848 | Bid,eval,award full size test sample *ECP6* | 1403.3222 | 1631.77 | 228.4478 | 1 | 12 | 121 | 1206 | 40 | 40% | 91.3791
1203-239 | Perform Analysis of VV Supports | 9952.5705 | 10476.39 | 523.8195 | 1 | 12 | 121 | 1203 | 40 | 40% | 209.5278
1206-110 | Weld | 0 | 636.4 | 636.4 | 1 | 12 | 121 | 1206 | 40 | 40% | 254.56
1202-854 | Instrument sample *ECP6* | 0 | 694.5 | 694.5 | 1 | 12 | 121 | 1206 | 40 | 40% | 277.8
1203-201 | Update/Perform FMECA Analyses | 4510.1425 | 5306.05 | 795.9075 | 1 | 12 | 121 | 1203 | 40 | 40% | 318.363
1203-232 | Structural Analysis of Vac Vsl | 76006.2226 | 77557.37 | 1551.1474 | 1 | 12 | 121 | 1203 | 40 | 40% | 620.459
1202-851 | vendor fab & deliver full size sample *ECP6* | 0 | 1674.9 | 1674.9 | 1 | 12 | 121 | 1206 | 40 | 40% | 669.96
1203-161 | Finalize & Sign All ICDs | 13429.694 | 15799.64 | 2369.946 | 1 | 12 | 121 | 1203 | 40 | 40% | 947.9784
1202-854 | Instrument sample *ECP6* | 0 | 2612.16 | 2612.16 | 1 | 12 | 121 | 1206 | 40 | 40% | 1044.864
1206-100 | Prep Sample | 0 | 2612.16 | 2612.16 | 1 | 12 | 121 | 1206 | 40 | 40% | 1044.864
1202-854 | Instrument sample *ECP6* | 0 | 2679.84 | 2679.84 | 1 | 12 | 121 | 1206 | 40 | 40% | 1071.936
1202-860 | Measure Results *ECP6* | 0 | 4019.76 | 4019.76 | 1 | 12 | 121 | 1206 | 40 | 40% | 1607.904
1202-863 | Report Results *ECP6* | 0 | 4019.76 | 4019.76 | 1 | 12 | 121 | 1206 | 40 | 40% | 1607.904
1206-115 | Analyze | 0 | 6715.6 | 6715.6 | 1 | 12 | 121 | 1206 | 40 | 40% | 2686.24
1202-857 | Perform welds on sample *ECP6* | 0 | 8707.2 | 8707.2 | 1 | 12 | 121 | 1206 | 40 | 40% | 3482.88
1203-361 | Final Design of Heating/Cooling | 15879.265 | 31758.53 | 15879.265 | 1 | 12 | 123 | 1203 | 40 | 40% | 6351.706
1203-271 | Develop/Confirm & Installation Process | 0 | 29448 | 29448 | 1 | 12 | 121 | 1203 | 40 | 40% | 11779.2
121-033 | VVSA Contract oversight FY05 & FY06 | 2960.874 | 41702.45 | 38741.5761 | 1 | 12 | 121 | 1250 | 40 | 40% | 15496.6304
121-031 | VVSA Title III engr | 16503.7915 | 93241.76 | 76737.9685 | 1 | 12 | 121 | 1250 | 40 | 40% | 30695.1874
121-033 | VVSA Contract oversight FY05 & FY06 | 11207.5871 | 157853.34 | 146645.7529 | 1 | 12 | 121 | 1250 | 40 | 40% | 58658.3011
1202-851 | vendor fab & deliver full size sample *ECP6* | 0 | 173625 | 173625 | 1 | 12 | 121 | 1206 | 40 | 40% | 69450
133-015 | Title III WBS 134 Conv Coil I&C | 0 | 359.56 | 359.56 | 1 | 13 | 134 | 1355 | 20 | 20% | 71.912
133-015 | Title III WBS 134 Conv Coil I&C | 0 | 699.3 | 699.3 | 1 | 13 | 134 | 1355 | 20 | 20% | 139.86
133-015 | Title III WBS 134 Conv Coil I&C | 0 | 2783.88 | 2783.88 | 1 | 13 | 134 | 1355 | 20 | 20% | 556.776
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 12190 | 12190 | 1 | 13 | 134 | 1355 | 20 | 20% | 2438
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 14335.65 | 14335.65 | 1 | 13 | 134 | 1355 | 20 | 20% | 2867.13
1355-100 | CS and PF 1-3 Pre-Assy incl coil I&C procurement | 0 | 20443.2 | 20443.2 | 1 | 13 | 134 | 1355 | 20 | 20% | 4088.64
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 41823.38 | 41823.38 | 1 | 13 | 134 | 1355 | 20 | 20% | 8364.676
1301-100 | Prepare Scope Sheet to define interfaces | 1258.2115 | 1935.71 | 677.4985 | 1 | 13 | 130 | 1301 | 24 | 24% | 162.5996
1301R-23 | Document and Summerize Analysis | 1274 | 2548 | 1274 | 1 | 13 | 130 | 1301 | 24 | 24% | 305.76
1301R-23 | Document and Summerize Analysis | 1343.12 | 2686.24 | 1343.12 | 1 | 13 | 130 | 1301 | 24 | 24% | 322.3488
1301R-33 | Prepare PDR Material | 0 | 2548 | 2548 | 1 | 13 | 130 | 1301 | 24 | 24% | 611.52
1301R-35 | Prepare for TF FDR | 0 | 2548 | 2548 | 1 | 13 | 130 | 1301 | 24 | 24% | 611.52
1301-175.7 | Complete PDR Drawings | 10562.632 | 13203.29 | 2640.658 | 1 | 13 | 130 | 1301 | 24 | 24% | 633.7579
1301-86 | Fab/Assemble Fixture | 0 | 3645 | 3645 | 1 | 13 | 131 | 1351 | 24 | 24% | 874.8
1351-110A | Assemble TF to Wedge Casting TF#1 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-115A | Assemble TF to Wedge Casting TF#2 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-120A | Assemble TF to Wedge Casting TF#3 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-125A | Assemble TF to Wedge Casting TF#4 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-130A | Assemble TF to Wedge Casting TF#5 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-135A | Assemble TF to Wedge Casting TF#6 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-140A | Assemble TF to Wedge Casting TF#7 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-145A | Assemble TF to Wedge Casting TF#8 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-150A | Assemble TF to Wedge Casting TF#9 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-155A | Assemble TF to Wedge Casting TF#10 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-160A | Assemble TF to Wedge Casting TF#11 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-165A | Assemble TF to Wedge Casting TF#12 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-170A | Assemble TF to Wedge Casting TF#13 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-175A | Assemble TF to Wedge Casting TF#14 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-180A | Assemble TF to Wedge Casting TF#15 | 0 | 3893.76 | 3893.76 | 1 | 13 | 131 | 1351 | 24 | 24% | 934.5024
1351-185A | Assemble TF to Wedge Casting TF#16 | 0 | 4023.68 | 4023.68 | 1 | 13 | 131 | 1351 | 24 | 24% | 965.6832
1351-190A | Assemble TF to Wedge Casting TF#17 | 0 | 4088.64 | 4088.64 | 1 | 13 | 131 | 1351 | 24 | 24% | 981.2736
1351-195A | Assemble TF to Wedge Casting TF#18 | 0 | 4088.64 | 4088.64 | 1 | 13 | 131 | 1351 | 24 | 24% | 981.2736
1301R-00 | Oversight,suprevision,job management | 49027.913 | 55461.44 | 6433.527 | 1 | 13 | 130 | 1301 | 24 | 24% | 1544.0465
1301-88 | Setup Wedge Casting Fixture | 0 | 6489.6 | 6489.6 | 1 | 13 | 131 | 1351 | 24 | 24% | 1557.504
1301R-11 | Design Test Fixtures | 0 | 6715.6 | 6715.6 | 1 | 13 | 130 | 1301 | 24 | 24% | 1611.744
1301R-12 | Build Test Fixture | 0 | 6715.6 | 6715.6 | 1 | 13 | 130 | 1301 | 24 | 24% | 1611.744
1301R-16 | Evaluate Samples | 0 | 6715.6 | 6715.6 | 1 | 13 | 130 | 1301 | 24 | 24% | 1611.744
131-031 | Title III engr | 0 | 9163.29 | 9163.29 | 1 | 13 | 131 | 1351 | 24 | 24% | 2199.1896
141-031 | Title III engr WBS 132 | 0 | 9496.23 | 9496.23 | 1 | 13 | 132 | 1352 | 24 | 24% | 2279.0952
1301R-14 | Build Samples | 0 | 13060.8 | 13060.8 | 1 | 13 | 130 | 1301 | 24 | 24% | 3134.592
1301R-10 | Check or Re-Run Analysis with new data | 0 | 13431.2 | 13431.2 | 1 | 13 | 130 | 1301 | 24 | 24% | 3223.488
1301R-36 | Final Design Leads | 0 | 13431.2 | 13431.2 | 1 | 13 | 130 | 1301 | 24 | 24% | 3223.488
133-010 | Design WBS 134 Conv Coil I&C | 0 | 13431.2 | 13431.2 | 1 | 13 | 130 | 1301 | 24 | 24% | 3223.488
1301-86 | Fab/Assemble Fixture | 0 | 16224 | 16224 | 1 | 13 | 131 | 1351 | 24 | 24% | 3893.76
131-031 | Title III engr | 0 | 16423.31 | 16423.31 | 1 | 13 | 131 | 1351 | 24 | 24% | 3941.5944
141-031 | Title III engr WBS 132 | 0 | 17093.3 | 17093.3 | 1 | 13 | 132 | 1352 | 24 | 24% | 4102.392
1301R-38 | Analysis, Final with Leads Terminals & Supports | 0 | 19110 | 19110 | 1 | 13 | 130 | 1301 | 24 | 24% | 4586.4
1301R-34 | Final Design Coil Windings | 0 | 20146.8 | 20146.8 | 1 | 13 | 130 | 1301 | 24 | 24% | 4835.232
1351-110 | Wind,wrap,VPI & test TF #1 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-115 | Wind,wrap,VPI & test TF #2 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-120 | Wind,wrap,VPI & test TF #3 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-125 | Wind,wrap,VPI & test TF #4 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-130 | Wind,wrap,VPI & test TF # 5 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-135 | Wind,wrap,VPI & test TF # 6 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-140 | Wind,wrap,VPI & test TF # 7 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-145 | Wind,wrap,VPI & test TF # 8 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-150 | Wind,wrap,VPI & test TF # 9 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-155 | Wind,wrap,VPI & test TF # 10 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-160 | Wind,wrap,VPI & test TF # 11 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-165 | Wind,wrap,VPI & test TF # 12 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-170 | Wind,wrap,VPI & test TF # 13 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-175 | Wind,wrap,VPI & test TF # 14 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-180 | Wind,wrap,VPI & test TF # 15 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-185 | Wind,wrap,VPI & test TF # 16 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-190 | Wind,wrap,VPI & test TF # 17 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1351-195 | Wind,wrap,VPI & test TF # 18 | 0 | 23450 | 23450 | 1 | 13 | 131 | 1351 | 24 | 24% | 5628
1301R-15 | Cryo Test for Coil Sample | 0 | 26862.4 | 26862.4 | 1 | 13 | 130 | 1301 | 24 | 24% | 6446.976
1352-145 | Fabricate/Dlvr PF 5 lower | 0 | 43009.5 | 43009.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 10322.28
1352-150 | Fabricate/Dlvr PF 6 lower | 0 | 43009.5 | 43009.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 10322.28
1352-155 | Fabricate/Dlvr PF 4 upper | 0 | 43009.5 | 43009.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 10322.28
1352-160 | Fabricate/Dlvr PF 5 upper | 0 | 43009.5 | 43009.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 10322.28
1352-165 | Fabricate/Dlvr PF 6 upper | 0 | 43009.5 | 43009.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 10322.28
130-000 | TF PDR & FDR Engineering | 0 | 52045.9 | 52045.9 | 1 | 13 | 130 | 1301 | 24 | 24% | 12491.016
1352-140 | Fabricate/Dlvr PF 4 lower | 0 | 52668.75 | 52668.75 | 1 | 13 | 132 | 1352 | 24 | 24% | 12640.5
1352-105 | Tooling for PF 1,2 and 3 | 0 | 69562.5 | 69562.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 16695
1352-110 | Tooling for PF 4 | 0 | 69562.5 | 69562.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 16695
1352-115 | Tooling for PF 5 | 0 | 69562.5 | 69562.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 16695
1352-120 | Tooling for PF 6 | 0 | 69562.5 | 69562.5 | 1 | 13 | 132 | 1352 | 24 | 24% | 16695
1352-125 | Fabricate/Dlvr PF 1 upper & lower | 0 | 86019 | 86019 | 1 | 13 | 132 | 1352 | 24 | 24% | 20644.56
1352-130 | Fabricate/Dlvr PF 2 upper & lower | 0 | 86019 | 86019 | 1 | 13 | 132 | 1352 | 24 | 24% | 20644.56
1352-135 | Fabricate/Dlvr PF 3 upper & lower | 0 | 86019 | 86019 | 1 | 13 | 132 | 1352 | 24 | 24% | 20644.56
1351-105 | materials & leads | 0 | 93000 | 93000 | 1 | 13 | 131 | 1351 | 24 | 24% | 22320
131-031 | Title III engr | 0 | 113936.72 | 113936.72 | 1 | 13 | 131 | 1351 | 24 | 24% | 27344.8128
141-031 | Title III engr WBS 132 | 0 | 125350.88 | 125350.88 | 1 | 13 | 132 | 1352 | 24 | 24% | 30084.2112
1351-100 | Tooling | 0 | 195334.32 | 195334.32 | 1 | 13 | 131 | 1351 | 24 | 24% | 46880.2368
1351-85D | Vendor Fab TF Castings | 0 | 195729.23 | 195729.23 | 1 | 13 | 131 | 1351 | 24 | 24% | 46975.0152
1352-100 | Material & leads | 0 | 329150 | 329150 | 1 | 13 | 132 | 1352 | 24 | 24% | 78996
1351-105 | materials & leads | 0 | 452245.96 | 452245.96 | 1 | 13 | 131 | 1351 | 24 | 24% | 108539.0304
163-037 | CS Support Structure Procurement/Fab | 0 | 3623.41 | 3623.41 | 1 | 13 | 132 | 1353 | 32 | 32% | 1159.4912
163-015 | Title III design CS sprt struc | 0 | 4713.87 | 4713.87 | 1 | 13 | 132 | 1353 | 32 | 32% | 1508.4384
163-015 | Title III design CS sprt struc | 0 | 14672.83 | 14672.83 | 1 | 13 | 132 | 1353 | 32 | 32% | 4695.3056
1302-CSS | Center Stack Support Design | 0 | 14887.35 | 14887.35 | 1 | 13 | 132 | 1302 | 32 | 32% | 4763.952
1303-TRIM | Trim Coil Design | 0 | 30819.6 | 30819.6 | 1 | 13 | 132 | 1303 | 32 | 32% | 9862.272
1303-TRIM | Trim Coil Design | 0 | 30819.6 | 30819.6 | 1 | 13 | 132 | 1303 | 32 | 32% | 9862.272
1302-CSS | Center Stack Support Design | 0 | 37218.37 | 37218.37 | 1 | 13 | 132 | 1302 | 32 | 32% | 11909.8784
1302-PF | PF Design | 0 | 37218.37 | 37218.37 | 1 | 13 | 132 | 1302 | 32 | 32% | 11909.8784
1302-PF | PF Design | 0 | 37218.37 | 37218.37 | 1 | 13 | 132 | 1302 | 32 | 32% | 11909.8784
1303-TRIM | Trim Coil Design | 0 | 37668.4 | 37668.4 | 1 | 13 | 132 | 1303 | 32 | 32% | 12053.888
1302-PF | PF Design | 0 | 39248.47 | 39248.47 | 1 | 13 | 132 | 1302 | 32 | 32% | 12559.5104
163-015 | Title III design CS sprt struc | 0 | 44195.27 | 44195.27 | 1 | 13 | 132 | 1353 | 32 | 32% | 14142.4864
1302-CSS | Center Stack Support Design | 0 | 62256.19 | 62256.19 | 1 | 13 | 132 | 1302 | 32 | 32% | 19921.9808
163-037 | CS Support Structure Procurement/Fab | 0 | 190640 | 190640 | 1 | 13 | 132 | 1353 | 32 | 32% | 61004.8
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 4547.43 | 4547.43 | 1 | 13 | 133 | 1354 | 40 | 40% | 1818.972
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 7174.01 | 7174.01 | 1 | 13 | 133 | 1354 | 40 | 40% | 2869.604
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 11278.59 | 11278.59 | 1 | 13 | 133 | 1354 | 40 | 40% | 4511.436
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 40884.87 | 40884.87 | 1 | 13 | 133 | 1354 | 40 | 40% | 16353.948
184-037 | External Trim Coil Procurement/Fab*ecp16 | 0 | 81750.92 | 81750.92 | 1 | 13 | 133 | 1354 | 40 | 40% | 32700.368
1064.4 | Payment #4 Pattern work | 0 | 145570 | 145570 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 14557
1064.2 | Payment #2 Pattern work | 0 | 153270 | 153270 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 15327
1064.6 | Payment #6 Pattern Work&Deliver C1 for machining | 0 | 158510 | 158510 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 15851
1064.7 | Payment #7 Deliver C-2 for Machining | 0 | 178670 | 178670 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 17867
C-441B | Payment #24 Castings C-6 | 0 | 192770 | 192770 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 19277
C-301B | Payment #22 Castings-B-6 | 0 | 244250 | 244250 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 24425
C-301B.1 | Payment #22 Castings- C-4 | 0 | 244250 | 244250 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 24425
1064.5 | Payment #5 Pattern work and Major Tool | 0 | 256650 | 256650 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 25665
1064.1 | Payment #1 Reporting &Materials | 0 | 324750 | 324750 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 32475
1112 | Payment #10 Ship A-1 to PPPL | 0 | 333580 | 333580 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33358
C-281 | Payment #16 Castings-A-5 | 0 | 333580 | 333580 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33358
1071 | Payment #8 Ship C-1 to PPPL | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
1092 | Payment #9 Ship C-2 to PPPL | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-141 | Payment #14 Castings-A-3 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-161B | Payment #20 Castings-B-4 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-201 | Payment #15 Castings-A-4 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-221B | Payment #21 Castings-B-5 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-321 | Payment #11 Castings-C-3 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-341 | Payment #17 Castings-A-6 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-361B | Payment #23 Castings-C-5 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-401 | Payment #12 Castings-B-1 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-421 | Paymenmt #18 Castings-B-2 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-461.1 | Payment #13 accrual | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
C-481 | Payment #19 Castings-B-3 | 0 | 333590 | 333590 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 33359
1064.1 | Payment #1 Reporting &Materials | 111120 | 694500 | 583380 | 1 | 14mcwf | 141 | 1411 | 10 | 10% | 58338
1064.3 | Payment #3 Pattern work and Major Tool Startup | 0 | 610970 | 610970 | 1 | 14mcwf | 141 | 8096870 | 10 | 10% | 61097
174-036 | Modular Coil local I&C -Title III | 0 | 1776 | 1776 | 1 | 14 | 143 | 1431 | 24 | 24% | 426.24
174-036 | Modular Coil local I&C -Title III | 0 | 3828.24 | 3828.24 | 1 | 14 | 143 | 1431 | 24 | 24% | 918.7776
174-001 | Title I design WBS 143 Mod coil local I&C | 0 | 14252.83 | 14252.83 | 1 | 14 | 143 | 1431 | 24 | 24% | 3420.6792
174-011 | Title II design WBS 143 Mod coil local I&C | 0 | 14252.83 | 14252.83 | 1 | 14 | 143 | 1431 | 24 | 24% | 3420.6792
174-035 | Modular Coil local I&C -Procurement | 0 | 17195.7 | 17195.7 | 1 | 14 | 143 | 1431 | 24 | 24% | 4126.968
174-037 | Modular Coil local I&C -Install | 0 | 20046.6 | 20046.6 | 1 | 14 | 143 | 1431 | 24 | 24% | 4811.184
174-037 | Modular Coil local I&C -Install | 0 | 49063.68 | 49063.68 | 1 | 14 | 143 | 1431 | 24 | 24% | 11775.2832
1407-100.6 | Complete Electr hookup turning fixtures 4 | 0 | 1431.9 | 1431.9 | 1 | 14 | 144 | 1412 | 28 | 28% | 400.932
1407-100.6 | Complete Electr hookup turning fixtures 4 | 0 | 1959.12 | 1959.12 | 1 | 14 | 144 | 1412 | 28 | 28% | 548.5536
1407-110.3 | Compl Fabr Winding clamp sets (300 of 400) | 0 | 4773 | 4773 | 1 | 14 | 144 | 1412 | 28 | 28% | 1336.44
1407-100.5 | Complete Fab & Instl Turning Fixt 4 | 0 | 4788.96 | 4788.96 | 1 | 14 | 144 | 1412 | 28 | 28% | 1340.9088
1407-110.3 | Compl Fabr Winding clamp sets (300 of 400) | 0 | 8334 | 8334 | 1 | 14 | 144 | 1412 | 28 | 28% | 2333.52
1407-100.5 | Complete Fab & Instl Turning Fixt 4 | 0 | 15512.25 | 15512.25 | 1 | 14 | 144 | 1412 | 28 | 28% | 4343.43
1407-110.3 | Compl Fabr Winding clamp sets (300 of 400) | 0 | 61385.76 | 61385.76 | 1 | 14 | 144 | 1412 | 28 | 28% | 17188.0128
1407-126.1 | Complete Fab Type A casting supports (6) sets | 2792.205 | 3102.45 | 310.245 | 1 | 14 | 144 | 1412 | 34 | 34% | 105.4833
1407-126.1 | Complete Fab Type A casting supports (6) sets | 2792.205 | 3102.45 | 310.245 | 1 | 14 | 144 | 1412 | 34 | 34% | 105.4833
1409-029 | Oversight/Supervision | 2038.2318 | 3078.9 | 1040.6682 | 1 | 14 | 144 | 1409 | 34 | 34% | 353.8272
1409-029 | Oversight/Supervision | 5823.5213 | 8796.86 | 2973.3387 | 1 | 14 | 144 | 1409 | 34 | 34% | 1010.9352
1407-107 | Perform epoxy mixing trials with delivery sys | 0 | 3182 | 3182 | 1 | 14 | 144 | 1412 | 34 | 34% | 1081.88
1407-107 | Perform epoxy mixing trials with delivery sys | 0 | 3182 | 3182 | 1 | 14 | 144 | 1412 | 34 | 34% | 1081.88
1409-160 | Test Closed Loop Cooling | 0 | 3182 | 3182 | 1 | 14 | 144 | 1409 | 34 | 34% | 1081.88
1407-130.1 | Misc tools & equipt FY05 | 1088.4 | 4353.6 | 3265.2 | 1 | 14 | 144 | 1412 | 34 | 34% | 1110.168
1407-127.1 | Complete Fab Type B casting supports (6) sets | 7652.71 | 11773.4 | 4120.69 | 1 | 14 | 144 | 1412 | 34 | 34% | 1401.0346
1407-127.1 | Complete Fab Type B casting supports (6) sets | 7652.71 | 11773.4 | 4120.69 | 1 | 14 | 144 | 1412 | 34 | 34% | 1401.0346
1409-028 | System Testing (planar racetrack) | 0 | 5170.75 | 5170.75 | 1 | 14 | 144 | 1409 | 34 | 34% | 1758.055
1409-130 | Cryostat (specimen shroud) dsn | 0 | 6699.6 | 6699.6 | 1 | 14 | 144 | 1409 | 34 | 34% | 2277.864
1407-109 | Fab & assemble VPI delivery sys | 1193.25 | 7955 | 6761.75 | 1 | 14 | 144 | 1412 | 34 | 34% | 2298.995
1407-109 | Fab & assemble VPI delivery sys | 1193.25 | 7955 | 6761.75 | 1 | 14 | 144 | 1412 | 34 | 34% | 2298.995
1407-109 | Fab & assemble VPI delivery sys | 1193.25 | 7955 | 6761.75 | 1 | 14 | 144 | 1412 | 34 | 34% | 2298.995
1409-027 | Cryo Line Installation | 370.6795 | 7413.59 | 7042.9105 | 1 | 14 | 144 | 1409 | 34 | 34% | 2394.5896
1409-029 | Oversight/Supervision | 15750.2643 | 23791.94 | 8041.6757 | 1 | 14 | 144 | 1409 | 34 | 34% | 2734.1697
1409-027 | Cryo Line Installation | 463.636 | 9272.72 | 8809.084 | 1 | 14 | 144 | 1409 | 34 | 34% | 2995.0886
1409-135 | Cryostat (specimen shroud) Fabr & Install | 0 | 9546 | 9546 | 1 | 14 | 144 | 1409 | 34 | 34% | 3245.64
1409-150 | Proc Matl's/pump f/closed LN2 | 9991.205 | 19982.41 | 9991.205 | 1 | 14 | 144 | 1409 | 34 | 34% | 3397.0097
1409-027 | Cryo Line Installation | 582.1945 | 11643.89 | 11061.6955 | 1 | 14 | 144 | 1409 | 34 | 34% | 3760.9765
1409-155 | Fab/Instl Closed Loop LN2 sys | 0 | 13060.8 | 13060.8 | 1 | 14 | 144 | 1409 | 34 | 34% | 4440.672
1409-028 | System Testing (planar racetrack) | 0 | 13399.2 | 13399.2 | 1 | 14 | 144 | 1409 | 34 | 34% | 4555.728
1409-135 | Cryostat (specimen shroud) Fabr & Install | 0 | 13890 | 13890 | 1 | 14 | 144 | 1409 | 34 | 34% | 4722.6
1407-130.1 | Misc tools & equipt FY05 | 6945 | 27780 | 20835 | 1 | 14 | 144 | 1412 | 34 | 34% | 7083.9
1403-40.2Z | Update nonlinear winding pack analysis | 440.04 | 550.05 | 110.01 | 1 | 14 | 141 | 1403 | 40 | 40% | 44.004
1406-016.7 | PPPL Fabricate TRC Tubing | 0 | 277.8 | 277.8 | 1 | 14 | 142 | 1410 | 40 | 40% | 111.12
1406-016.A | fab trc lead components | 745.262 | 1064.66 | 319.398 | 1 | 14 | 142 | 1406 | 40 | 40% | 127.7592
1406-016.5 | PPPL Fabricate TRC Cladding | 998.625 | 1331.5 | 332.875 | 1 | 14 | 142 | 1406 | 40 | 40% | 133.15
1406-016.A | fab trc lead components | 1094.226 | 1563.18 | 468.954 | 1 | 14 | 142 | 1406 | 40 | 40% | 187.5816
1406-016.5 | PPPL Fabricate TRC Cladding | 1407.15 | 1876.2 | 469.05 | 1 | 14 | 142 | 1406 | 40 | 40% | 187.62
1403-204 | Chill Plate Dwgs (66)-Type C | 342.111 | 1140.37 | 798.259 | 1 | 14 | 142 | 1403 | 40 | 40% | 319.3036
1406-016.6 | PPPL Fabricate TRC Chill plates | 0 | 1041.75 | 1041.75 | 1 | 14 | 142 | 1410 | 40 | 40% | 416.7
1403-200 | Winding & Insulation Dwgs (8)-Type C | 1044.22 | 2088.44 | 1044.22 | 1 | 14 | 142 | 1403 | 40 | 40% | 417.688
1403-40.2Z | Update nonlinear winding pack analysis | 4400.4 | 5500.5 | 1100.1 | 1 | 14 | 141 | 1403 | 40 | 40% | 440.04
1403-40.2Z | Update nonlinear winding pack analysis | 5096 | 6370 | 1274 | 1 | 14 | 141 | 1403 | 40 | 40% | 509.6
1406-104 | Prepare Draft of Coil Test Plan | 3903.825 | 5205.1 | 1301.275 | 1 | 14 | 142 | 1403 | 40 | 40% | 520.51
1408-137L5 | Chill plates ,cladsding,tubing Fab Type A2 | 0 | 1341.48 | 1341.48 | 1 | 14 | 142 | 1408 | 40 | 40% | 536.592
1408-137L | Chill plates ,cladsding,tubing Fab Type C1 | 0 | 1389 | 1389 | 1 | 14 | 142 | 1408 | 40 | 40% | 555.6
1408-137L1 | Chill plates ,cladsding,tubing Fab Type C2 | 0 | 1389 | 1389 | 1 | 14 | 142 | 1408 | 40 | 40% | 555.6
1408-137L2 | Chill plates ,cladsding,tubing Fab Type A1 | 0 | 1389 | 1389 | 1 | 14 | 142 | 1408 | 40 | 40% | 555.6
1408-137L3 | Chill plates ,cladsding,tubing Fab Type C3 | 0 | 1389 | 1389 | 1 | 14 | 142 | 1408 | 40 | 40% | 555.6
1408-137L4 | Chill plates ,cladsding,tubing Fab Type B1 | 0 | 1389 | 1389 | 1 | 14 | 142 | 1408 | 40 | 40% | 555.6
1408-186 | Manifolds | 0 | 1389 | 1389 | 1 | 14 | 142 | 1408 | 40 | 40% | 555.6
1403-200 | Winding & Insulation Dwgs (8)-Type C | 1865.3 | 3730.6 | 1865.3 | 1 | 14 | 142 | 1403 | 40 | 40% | 746.12
1406-016.6 | PPPL Fabricate TRC Chill plates | 0 | 1909.2 | 1909.2 | 1 | 14 | 142 | 1410 | 40 | 40% | 763.68
1406-200 | Transverse compression at LN2 | 669.96 | 2679.84 | 2009.88 | 1 | 14 | 142 | 1406 | 40 | 40% | 803.952
1403-201 | Leads & crossover Dwgs (10)-Type C | 1492.24 | 3730.6 | 2238.36 | 1 | 14 | 142 | 1403 | 40 | 40% | 895.344
1406-103.3 | Resolve TRC FDR Issues | 0 | 2355.84 | 2355.84 | 1 | 14 | 142 | 1403 | 40 | 40% | 942.336
1406-157 | Build to specification | 0 | 2355.84 | 2355.84 | 1 | 14 | 142 | 1403 | 40 | 40% | 942.336
1406-016.A | fab trc lead components | 5994.751 | 8563.93 | 2569.179 | 1 | 14 | 142 | 1406 | 40 | 40% | 1027.6716
1406-110 | Finalize, Approve coil test plan | 7869.1875 | 10492.25 | 2623.0625 | 1 | 14 | 142 | 1403 | 40 | 40% | 1049.225
1403-40.2X | Multifilament coils file incl leads | 2944.8 | 5889.6 | 2944.8 | 1 | 14 | 141 | 1403 | 40 | 40% | 1177.92
1403-42G | WP beam FEA modeling | 0 | 2944.8 | 2944.8 | 1 | 14 | 141 | 1403 | 40 | 40% | 1177.92
1403-71.05 | Update MIT/QA Plans for Type A Winding Fab | 0 | 2944.8 | 2944.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1177.92
1403-81 | Prepare FDR doc | 0 | 2944.8 | 2944.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1177.92
1403-900 | Prep FDR Documentation | 0 | 2944.8 | 2944.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1177.92
1403-901 | Resolve FDR comments | 0 | 2944.8 | 2944.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1177.92
1403-902 | Update build-to spec | 0 | 2944.8 | 2944.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1177.92
1406-016.2 | Install Studs | 0 | 3182 | 3182 | 1 | 14 | 142 | 1410 | 40 | 40% | 1272.8
1406-016.7 | PPPL Fabricate TRC Tubing | 0 | 3182 | 3182 | 1 | 14 | 142 | 1410 | 40 | 40% | 1272.8
1406-023 | Dissect Coil | 0 | 3182 | 3182 | 1 | 14 | 142 | 1410 | 40 | 40% | 1272.8
1406-023 | Dissect Coil | 0 | 3182 | 3182 | 1 | 14 | 142 | 1410 | 40 | 40% | 1272.8
1403-42D.0 | Determine Fatigue properties | 0 | 3357.8 | 3357.8 | 1 | 14 | 141 | 1403 | 40 | 40% | 1343.12
1403-72.05 | Update MIT/QA Plans for Type C Winding Fab | 0 | 3357.8 | 3357.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1343.12
1403-72.06 | Update build-to spec | 0 | 3357.8 | 3357.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1343.12
1403-72.07 | Resolve FDR comments | 0 | 3357.8 | 3357.8 | 1 | 14 | 142 | 1403 | 40 | 40% | 1343.12
1403-17 | Assembly shims | 8316.1152 | 11779.2 | 3463.0848 | 1 | 14 | 141 | 1403 | 40 | 40% | 1385.2339
1403-90 | Compile Material properties database | 9401.84 | 13431.2 | 4029.36 | 1 | 14 | 141 | 1403 | 40 | 40% | 1611.744
1406-021 | Test Coil | 0 | 4391.52 | 4391.52 | 1 | 14 | 142 | 1410 | 40 | 40% | 1756.608
1406-000.2 | Supervision & Oversight | 4680.9907 | 9142.56 | 4461.5693 | 1 | 14 | 142 | 1406 | 40 | 40% | 1784.6277
1406-021 | Test Coil | 0 | 4533.6 | 4533.6 | 1 | 14 | 142 | 1410 | 40 | 40% | 1813.44
1403-219 | MCWF studs,modifications-Type C | 1177.92 | 5889.6 | 4711.68 | 1 | 14 | 142 | 1403 | 40 | 40% | 1884.672
1406-100 | Single conductor torsion test | 1674.9 | 6699.6 | 5024.7 | 1 | 14 | 142 | 1406 | 40 | 40% | 2009.88
1406-ST1 | Fab Straight Tee Specimen | 954.6 | 6364 | 5409.4 | 1 | 14 | 142 | 1410 | 40 | 40% | 2163.76
1406-ST1 | Fab Straight Tee Specimen | 954.6 | 6364 | 5409.4 | 1 | 14 | 142 | 1410 | 40 | 40% | 2163.76
1406-017 | Instl cladding(station 2) | 636.4 | 6364 | 5727.6 | 1 | 14 | 142 | 1410 | 40 | 40% | 2291.04
1406-017 | Instl cladding(station 2) | 636.4 | 6364 | 5727.6 | 1 | 14 | 142 | 1410 | 40 | 40% | 2291.04
1403-11.1 | Compl assembly / interface drawings for ICDs | 0 | 5889.6 | 5889.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2355.84
1403-16 | Assembly bolts, nuts,washers | 5889.6 | 11779.2 | 5889.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2355.84
1403-208 | I&C Dwgs (1) -Type C | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-223 | Top level coil assembly-Type C | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-300 | Winding pack assy Dwgs (8)-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-301 | Leads & crossover Dwgs (10)-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-303 | Clamp Dwgs (5)-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-306 | Cooling, Electr Schematic Dwgs (1)-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-308 | I&C Dwgs (1) -Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-319 | MCWF studs,modifications-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-321 | Lead ends & closure-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-322 | Terminal assembly-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-323 | Top level coil assembly-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-324 | VPI mold assembly0-Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-400 | Winding pack assy Dwgs (8)-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-401 | Leads & crossover Dwgs (10)-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-403 | Clamp Dwgs (5)-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-406 | Cooling, Electr Schematic Dwgs (1)-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-408 | I&C Dwgs (1) -Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-419 | MCWF studs,modifications-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-421 | Lead ends & closure-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-422 | Terminal assembly-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-423 | Top level coil assembly-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-424 | VPI mold assembly0-Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-42A | WP beam bending results documentation | 0 | 5889.6 | 5889.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2355.84
1403-47A | Update,review & approve FMECA | 0 | 5889.6 | 5889.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2355.84
1403-49 | Update cost / schedule estimates | 0 | 5889.6 | 5889.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2355.84
1403-58A | Check and promote models / drawings -Type A | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-58B | Check and promote models / drawings -Type B | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-59 | Update build-to specifications | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-62 | Prepare FDR documentation / presentations | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-70.05 | Update MIT/QA Plans for Type C Winding Fab | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-76 | Structural analysis of leads | 5889.6 | 11779.2 | 5889.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2355.84
1403-80 | Update design basis doc & cost sched est | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1403-904 | Update cost/sched estimates&Design Basis doc. | 0 | 5889.6 | 5889.6 | 1 | 14 | 142 | 1403 | 40 | 40% | 2355.84
1406-017.2 | Instl chill plates & tubing (station 2) | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-017.2 | Instl chill plates & tubing (station 2) | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-018 | Apply bag mold (station 4) | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-018 | Apply bag mold (station 4) | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-019.1 | Instl permanent clamps | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-019.1 | Instl permanent clamps | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-106.3 | Winding Trials (wo/ cladding) | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-106.3 | Winding Trials (wo/ cladding) | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-ST2 | Straight Tee VPI Prep | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-ST2 | Straight Tee VPI Prep | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-ST3 | VPI Tee Specimen | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1406-ST3 | VPI Tee Specimen | 0 | 6364 | 6364 | 1 | 14 | 142 | 1410 | 40 | 40% | 2545.6
1408-137L | Chill plates ,cladsding,tubing Fab Type C1 | 0 | 6364 | 6364 | 1 | 14 | 142 | 1408 | 40 | 40% | 2545.6
1408-137L1 | Chill plates ,cladsding,tubing Fab Type C2 | 0 | 6364 | 6364 | 1 | 14 | 142 | 1408 | 40 | 40% | 2545.6
1408-137L2 | Chill plates ,cladsding,tubing Fab Type A1 | 0 | 6364 | 6364 | 1 | 14 | 142 | 1408 | 40 | 40% | 2545.6
1408-137L3 | Chill plates ,cladsding,tubing Fab Type C3 | 0 | 6364 | 6364 | 1 | 14 | 142 | 1408 | 40 | 40% | 2545.6
1408-137L4 | Chill plates ,cladsding,tubing Fab Type B1 | 0 | 6364 | 6364 | 1 | 14 | 142 | 1408 | 40 | 40% | 2545.6
1403-47B | det boundary conditions single nonlinear windng | 0 | 6370 | 6370 | 1 | 14 | 141 | 1403 | 40 | 40% | 2548
1408-137L5 | Chill plates ,cladsding,tubing Fab Type A2 | 0 | 6424.29 | 6424.29 | 1 | 14 | 142 | 1408 | 40 | 40% | 2569.716
1408-154 | G-11 Filler Fabrication - Production Type B | 0 | 6450 | 6450 | 1 | 14 | 142 | 1408 | 40 | 40% | 2580
1408-155 | G-11 Filler Fabrication - Production Type A | 0 | 6450 | 6450 | 1 | 14 | 142 | 1408 | 40 | 40% | 2580
1406-021 | Test Coil | 0 | 6477.6 | 6477.6 | 1 | 14 | 142 | 1410 | 40 | 40% | 2591.04
1406-021 | Test Coil | 0 | 6699.6 | 6699.6 | 1 | 14 | 142 | 1410 | 40 | 40% | 2679.84
1403-20.2 | Resolve FDR chits | 0 | 6715.6 | 6715.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2686.24
1403-47C | Backup analysis/check of leads | 0 | 6715.6 | 6715.6 | 1 | 14 | 141 | 1403 | 40 | 40% | 2686.24
1406-000.2 | Supervision & Oversight | 7220.6131 | 14102.76 | 6882.1469 | 1 | 14 | 142 | 1406 | 40 | 40% | 2752.8588
1408-107 | Insulation-Delivery for Production | 0 | 6945 | 6945 | 1 | 14 | 142 | 1408 | 40 | 40% | 2778
1408-153 | G-11 Filler Fabrication - Production Type C | 0 | 6945 | 6945 | 1 | 14 | 142 | 1408 | 40 | 40% | 2778
1406-019 | VPI TRC in autoclave | 0 | 7159.5 | 7159.5 | 1 | 14 | 142 | 1410 | 40 | 40% | 2863.8
1406-019 | VPI TRC in autoclave | 0 | 7159.5 | 7159.5 | 1 | 14 | 142 | 1410 | 40 | 40% | 2863.8
1406-019 | VPI TRC in autoclave | 0 | 7159.5 | 7159.5 | 1 | 14 | 142 | 1410 | 40 | 40% | 2863.8
1406-019 | VPI TRC in autoclave | 0 | 7159.5 | 7159.5 | 1 | 14 | 142 | 1410 | 40 | 40% | 2863.8
1408-138L | Chill plates ,cladsding,tubing Fab Bal of A's | 0 | 7740 | 7740 | 1 | 14 | 142 | 1408 | 40 | 40% | 3096
1408-139L | Chill plates ,cladsding,tubing Fab Bal of B's | 0 | 7749.4 | 7749.4 | 1 | 14 | 142 | 1408 | 40 | 40% | 3099.76
1406-000.2 | Supervision & Oversight | 8252.1293 | 16117.44 | 7865.3107 | 1 | 14 | 142 | 1406 | 40 | 40% | 3146.1243
1403-42H | calculate EM loads at leads | 0 | 8834.4 | 8834.4 | 1 | 14 | 141 | 1403 | 40 | 40% | 3533.76
1408-999 | 3rd winding line conductor payout sys | 0 | 9546 | 9546 | 1 | 14 | 142 | 1412 | 40 | 40% | 3818.4
1403-201 | Leads & crossover Dwgs (10)-Type C | 6395.32 | 15988.3 | 9592.98 | 1 | 14 | 142 | 1403 | 40 | 40% | 3837.192
1403-201 | Leads & crossover Dwgs (10)-Type C | 6448.616 | 16121.54 | 9672.924 | 1 | 14 | 142 | 1403 | 40 | 40% | 3869.1696
1403-42D | Fracture fatigue analysis for MCWF | 0 | 10073.4 | 10073.4 | 1 | 14 | 141 | 1403 | 40 | 40% | 4029.36
1406-016.0 | Oversight & Supervision | 0 | 10073.4 | 10073.4 | 1 | 14 | 142 | 1410 | 40 | 40% | 4029.36
1406-021 | Test Coil | 0 | 10182.4 | 10182.4 | 1 | 14 | 142 | 1410 | 40 | 40% | 4072.96
1403-200 | Winding & Insulation Dwgs (8)-Type C | 10658.87 | 21317.74 | 10658.87 | 1 | 14 | 142 | 1403 | 40 | 40% | 4263.548
PPC-6 | Oversight/Reporting | 16278.08 | 27040 | 10761.92 | 1 | 14 | 141 | 1404 | 40 | 40% | 4304.768
1403-11.1 | Compl assembly / interface drawings for ICDs | 0 | 11779.2 | 11779.2 | 1 | 14 | 141 | 1403 | 40 | 40% | 4711.68
1403-11.1 | Compl assembly / interface drawings for ICDs | 0 | 11779.2 | 11779.2 | 1 | 14 | 141 | 1403 | 40 | 40% | 4711.68
1403-18 | Eccentric ball assembly | 0 | 11779.2 | 11779.2 | 1 | 14 | 141 | 1403 | 40 | 40% | 4711.68
1403-206 | Cooling, Electr Schematic Dwgs (1)- Type C | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-221 | Lead ends & closure-Type C | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-222 | Terminal assembly-Type C | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-224 | VPI mold assembly0-Type C | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-304 | Chill Plate Dwgs (66)-Type A | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-320 | Cladding assembly-Type A | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-404 | Chill Plate Dwgs (66)-TypeB | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-420 | Cladding assembly-Type B | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-60 | Update design basis document | 0 | 11779.2 | 11779.2 | 1 | 14 | 142 | 1403 | 40 | 40% | 4711.68
1403-73 | Prep struct analysis report | 0 | 11779.2 | 11779.2 | 1 | 14 | 141 | 1403 | 40 | 40% | 4711.68
1403-19 | Top assembly dwgs for mod coil shell | 5300.64 | 17668.8 | 12368.16 | 1 | 14 | 141 | 1403 | 40 | 40% | 4947.264
1408-999 | 3rd winding line conductor payout sys | 0 | 13890 | 13890 | 1 | 14 | 142 | 1412 | 40 | 40% | 5556
1406-017.1 | Instl grnd wrap & wind coil(station 2) | 0 | 15910 | 15910 | 1 | 14 | 142 | 1410 | 40 | 40% | 6364
1406-017.1 | Instl grnd wrap & wind coil(station 2) | 0 | 15910 | 15910 | 1 | 14 | 142 | 1410 | 40 | 40% | 6364
1408-138 | Misc. Supplies | 0 | 15930.31 | 15930.31 | 1 | 14 | 142 | 1408 | 40 | 40% | 6372.124
PPC-4 | Build Pattern & Pour Casting | 0 | 16610 | 16610 | 1 | 14 | 141 | 1404 | 40 | 40% | 6644
1408-164 | Lead hardware Fabrication - Production Type B | 0 | 16770 | 16770 | 1 | 14 | 142 | 1408 | 40 | 40% | 6708
1408-165 | Lead hardware Fabrication - Production Type A | 0 | 16770 | 16770 | 1 | 14 | 142 | 1408 | 40 | 40% | 6708
1408-163 | Lead hardware Fabrication - Production Type C | 0 | 18057 | 18057 | 1 | 14 | 142 | 1408 | 40 | 40% | 7222.8
1408-119 | Epoxy -2nd Delivery for Production | 0 | 19350 | 19350 | 1 | 14 | 142 | 1408 | 40 | 40% | 7740
1408-121 | Epoxy -3rd Delivery for Production | 0 | 19350 | 19350 | 1 | 14 | 142 | 1408 | 40 | 40% | 7740
1408-123 | Epoxy -4th Delivery for Production | 0 | 19350 | 19350 | 1 | 14 | 142 | 1408 | 40 | 40% | 7740
1408-125 | Epoxy -5th Delivery for Production | 0 | 19350 | 19350 | 1 | 14 | 142 | 1408 | 40 | 40% | 7740
1408-127 | Epoxy -6th Delivery for Production | 0 | 19350 | 19350 | 1 | 14 | 142 | 1408 | 40 | 40% | 7740
1408-137 | Safety & Disposable supplies | 0 | 19912.89 | 19912.89 | 1 | 14 | 142 | 1408 | 40 | 40% | 7965.156
1408-117 | Epoxy -1st Delivery for Production | 0 | 20835 | 20835 | 1 | 14 | 142 | 1408 | 40 | 40% | 8334
1408-185 | Valves and Fittings | 0 | 20835 | 20835 | 1 | 14 | 142 | 1408 | 40 | 40% | 8334
1403-220 | Cladding assembly-Type C | 5300.64 | 26503.2 | 21202.56 | 1 | 14 | 142 | 1403 | 40 | 40% | 8481.024
1403-40.2Z | Update nonlinear winding pack analysis | 44224.0401 | 66006.03 | 21781.9899 | 1 | 14 | 141 | 1403 | 40 | 40% | 8712.796
TITLE2TRC | Titel III Design-TRC FAB | 1696.2048 | 23558.4 | 21862.1952 | 1 | 14 | 142 | 1403 | 40 | 40% | 8744.8781
1403-204 | Chill Plate Dwgs (66)-Type C | 9921.246 | 33070.82 | 23149.574 | 1 | 14 | 142 | 1403 | 40 | 40% | 9259.8296
1408-173 | Epoxy for Shell Mold (Hysol) | 0 | 23220 | 23220 | 1 | 14 | 142 | 1408 | 40 | 40% | 9288
172-031 | Title III engr | 5486.2139 | 28874.81 | 23388.5961 | 1 | 14 | 141 | 1411 | 40 | 40% | 9355.4384
1403-74 | check analysis using simplified models | 16117.44 | 40293.6 | 24176.16 | 1 | 14 | 141 | 1403 | 40 | 40% | 9670.464
1403-203 | Clamp Dwgs (5)-Type C | 0 | 24200.86 | 24200.86 | 1 | 14 | 142 | 1403 | 40 | 40% | 9680.344
1403-42F | Perform WP beam tests at ORNL | 0 | 26503.2 | 26503.2 | 1 | 14 | 141 | 1403 | 40 | 40% | 10601.28
1408-112.1 | Grndwrap-Delivery | 0 | 27780 | 27780 | 1 | 14 | 142 | 1408 | 40 | 40% | 11112
TITLE2TRC | Titel III Design-TRC FAB | 2252.448 | 31284 | 29031.552 | 1 | 14 | 142 | 1403 | 40 | 40% | 11612.6208
1403-58C | Check and promote models / drawings -Type C | 0 | 29448 | 29448 | 1 | 14 | 142 | 1403 | 40 | 40% | 11779.2
1406-215 | 4 turn racetrack fatigue tests | 0 | 29478.24 | 29478.24 | 1 | 14 | 142 | 1406 | 40 | 40% | 11791.296
PPC-5C | contract resolution setaside | 0 | 30000 | 30000 | 1 | 14 | 141 | 1404 | 40 | 40% | 12000
1408-184 | Vulcanizing tape, felt and RTV | 0 | 30558 | 30558 | 1 | 14 | 142 | 1408 | 40 | 40% | 12223.2
TITLE3WIND | Titel III Design-PRODUCTION WINDING | 0 | 31262.03 | 31262.03 | 1 | 14 | 142 | 1451 | 40 | 40% | 12504.812
171-041CT | PBR Increment for cold testing | 0 | 37233 | 37233 | 1 | 14 | 142 | 1451 | 40 | 40% | 14893.2
1408-138L | Chill plates ,cladsding,tubing Fab Bal of A's | 0 | 38937.6 | 38937.6 | 1 | 14 | 142 | 1408 | 40 | 40% | 15575.04
1408-139L | Chill plates ,cladsding,tubing Fab Bal of B's | 0 | 39024.86 | 39024.86 | 1 | 14 | 142 | 1408 | 40 | 40% | 15609.944
PPC-3 | Materials | 0 | 39150 | 39150 | 1 | 14 | 141 | 1404 | 40 | 40% | 15660
TITLE3WIND | Titel III Design-PRODUCTION WINDING | 0 | 41227.2 | 41227.2 | 1 | 14 | 142 | 1451 | 40 | 40% | 16490.88
171-041CT | PBR Increment for cold testing | 0 | 41996.15 | 41996.15 | 1 | 14 | 142 | 1451 | 40 | 40% | 16798.46
1408-999 | 3rd winding line conductor payout sys | 0 | 46148.16 | 46148.16 | 1 | 14 | 142 | 1412 | 40 | 40% | 18459.264
172-031 | Title III engr | 10928.7848 | 57519.92 | 46591.1352 | 1 | 14 | 141 | 1411 | 40 | 40% | 18636.4541
171-041CT | PBR Increment for cold testing | 0 | 47999.05 | 47999.05 | 1 | 14 | 142 | 1451 | 40 | 40% | 19199.62
1408-183 | Tubing (Chem flor and Poly) | 0 | 48615 | 48615 | 1 | 14 | 142 | 1408 | 40 | 40% | 19446
171-041 | Modular Coil Winding (18 coils) | 0 | 49236.97 | 49236.97 | 1 | 14 | 142 | 1451 | 40 | 40% | 19694.788
PPC-2 | Lawton mold Assy | 161162.04 | 227630 | 66467.96 | 1 | 14 | 141 | 1404 | 40 | 40% | 26587.184
172-031 | Title III engr | 15826.3122 | 83296.38 | 67470.0678 | 1 | 14 | 141 | 1411 | 40 | 40% | 26988.0271
1406-016.0 | Oversight & Supervision | 0 | 73140.48 | 73140.48 | 1 | 14 | 142 | 1410 | 40 | 40% | 29256.192
1408-153 | G-11 Filler Fabrication - Production Type C | 0 | 78364.8 | 78364.8 | 1 | 14 | 142 | 1408 | 40 | 40% | 31345.92
1408-163 | Lead hardware Fabrication - Production Type C | 0 | 78364.8 | 78364.8 | 1 | 14 | 142 | 1408 | 40 | 40% | 31345.92
1408-186 | Manifolds | 0 | 79550 | 79550 | 1 | 14 | 142 | 1408 | 40 | 40% | 31820
1408-154 | G-11 Filler Fabrication - Production Type B | 0 | 79920 | 79920 | 1 | 14 | 142 | 1408 | 40 | 40% | 31968
1408-155 | G-11 Filler Fabrication - Production Type A | 0 | 79920 | 79920 | 1 | 14 | 142 | 1408 | 40 | 40% | 31968
1408-164 | Lead hardware Fabrication - Production Type B | 0 | 79920 | 79920 | 1 | 14 | 142 | 1408 | 40 | 40% | 31968
1408-165 | Lead hardware Fabrication - Production Type A | 0 | 79920 | 79920 | 1 | 14 | 142 | 1408 | 40 | 40% | 31968
171-041CT | PBR Increment for cold testing | 0 | 104597.19 | 104597.19 | 1 | 14 | 142 | 1451 | 40 | 40% | 41838.876
1408-137P | Clamps Production Type C | 0 | 116100 | 116100 | 1 | 14 | 142 | 1408 | 40 | 40% | 46440
1408-138P | Clamps Production Type B | 0 | 116100 | 116100 | 1 | 14 | 142 | 1408 | 40 | 40% | 46440
1408-139P | Clamps Production Type A | 0 | 117013.5 | 117013.5 | 1 | 14 | 142 | 1408 | 40 | 40% | 46805.4
1406-016.0 | Oversight & Supervision | 0 | 128939.52 | 128939.52 | 1 | 14 | 142 | 1410 | 40 | 40% | 51575.808
1408-145 | Copper Conductor -Delivery #2 PE005371 | 0 | 130149.3 | 130149.3 | 1 | 14 | 142 | 1408 | 40 | 40% | 52059.72
1408-147 | Copper Conductor -Delivery #1 PE005371 | 0 | 130149.3 | 130149.3 | 1 | 14 | 142 | 1408 | 40 | 40% | 52059.72
171-041 | Modular Coil Winding (18 coils) | 0 | 147900.12 | 147900.12 | 1 | 14 | 142 | 1451 | 40 | 40% | 59160.048
171-041CT | PBR Increment for cold testing | 0 | 212203.85 | 212203.85 | 1 | 14 | 142 | 1451 | 40 | 40% | 84881.54
171-041 | Modular Coil Winding (18 coils) | 0 | 223649.67 | 223649.67 | 1 | 14 | 142 | 1451 | 40 | 40% | 89459.868
171-041 | Modular Coil Winding (18 coils) | 0 | 233849.59 | 233849.59 | 1 | 14 | 142 | 1451 | 40 | 40% | 93539.836
171-040 | Winding Oversight (LOE) | 0 | 255758.85 | 255758.85 | 1 | 14 | 142 | 1451 | 40 | 40% | 102303.54
171-040 | Winding Oversight (LOE) | 0 | 394514.58 | 394514.58 | 1 | 14 | 142 | 1451 | 40 | 40% | 157805.832
171-041 | Modular Coil Winding (18 coils) | 0 | 2520378.93 | 2520378.93 | 1 | 14 | 142 | 1451 | 40 | 40% | 1008151.572
153.015 | Title III design WBS 153 localI&C | 0 | 932.4 | 932.4 | 1 | 15 | 151 | 1550 | 20 | 20% | 186.48
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 1364.63 | 1364.63 | 1 | 15 | 151 | 1550 | 20 | 20% | 272.926
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 3294.01 | 3294.01 | 1 | 15 | 151 | 1550 | 20 | 20% | 658.802
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 3989.24 | 3989.24 | 1 | 15 | 151 | 1550 | 20 | 20% | 797.848
153.015 | Title III design WBS 153 localI&C | 0 | 4021.16 | 4021.16 | 1 | 15 | 151 | 1550 | 20 | 20% | 804.232
162-037 | WBS 151Coil Support Assy Procurement [A/1] | 0 | 3503.73 | 3503.73 | 1 | 15 | 151 | 1550 | 32 | 32% | 1121.1936
162-031 | Title III engr WBS 151 | 0 | 9206.48 | 9206.48 | 1 | 15 | 151 | 1550 | 32 | 32% | 2946.0736
162-031 | Title III engr WBS 151 | 0 | 23461.32 | 23461.32 | 1 | 15 | 151 | 1550 | 32 | 32% | 7507.6224
1501-FY05 | Prelim & Final Design Structures | 0 | 44658.74 | 44658.74 | 1 | 15 | 151 | 1501 | 32 | 32% | 14290.7968
1501-FY05 | Prelim & Final Design Structures | 0 | 62958.75 | 62958.75 | 1 | 15 | 151 | 1501 | 32 | 32% | 20146.8
1501-FY05 | Prelim & Final Design Structures | 0 | 63126.64 | 63126.64 | 1 | 15 | 151 | 1501 | 32 | 32% | 20200.5248
162-031 | Title III engr WBS 151 | 0 | 124317.98 | 124317.98 | 1 | 15 | 151 | 1550 | 32 | 32% | 39781.7536
162-037 | WBS 151Coil Support Assy Procurement [A/1] | 0 | 334244.95 | 334244.95 | 1 | 15 | 151 | 1550 | 32 | 32% | 106958.384
162-037 | WBS 151Coil Support Assy Procurement [A/1] | 0 | 647951.81 | 647951.81 | 1 | 15 | 151 | 1550 | 32 | 32% | 207344.5792
132-015 | Title III design WBS 162 Coil leads | 0 | 932.4 | 932.4 | 1 | 16 | 162 |  | 22 | 22% | 205.128
132-001 | Title I design WBS 162 Coil leads | 0 | 3686.6 | 3686.6 | 1 | 16 | 162 |  | 22 | 22% | 811.052
132-011 | Title II design WBS 162 Coil leads | 0 | 3723.48 | 3723.48 | 1 | 16 | 162 |  | 22 | 22% | 819.1656
132-015 | Title III design WBS 162 Coil leads | 0 | 15156.68 | 15156.68 | 1 | 16 | 162 |  | 22 | 22% | 3334.4696
132-001 | Title I design WBS 162 Coil leads | 0 | 127951.56 | 127951.56 | 1 | 16 | 162 |  | 22 | 22% | 28149.3432
132-011 | Title II design WBS 162 Coil leads | 0 | 130530.75 | 130530.75 | 1 | 16 | 162 |  | 22 | 22% | 28716.765
132-037 | Coil Leads Procurement WBS 162 | 0 | 296296.5 | 296296.5 | 1 | 16 | 162 |  | 22 | 22% | 65185.23
191-031 | Title III engr WBS 161 | 0 | 1417.94 | 1417.94 | 1 | 16 | 161 |  | 28 | 28% | 397.0232
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 0 | 8275.05 | 8275.05 | 1 | 16 | 161 |  | 28 | 28% | 2317.014
163.001 | Title I design WBS 163 Coil protection | 0 | 12073.68 | 12073.68 | 1 | 16 | 163 |  | 28 | 28% | 3380.6304
163.011 | Title II design WBS 163 Coil protection | 0 | 12073.68 | 12073.68 | 1 | 16 | 163 |  | 28 | 28% | 3380.6304
163.001 | Title I design WBS 163 Coil protection | 0 | 12612 | 12612 | 1 | 16 | 163 |  | 28 | 28% | 3531.36
163.011 | Title II design WBS 163 Coil protection | 0 | 12612 | 12612 | 1 | 16 | 163 |  | 28 | 28% | 3531.36
191-031 | Title III engr WBS 161 | 0 | 13111.6 | 13111.6 | 1 | 16 | 161 |  | 28 | 28% | 3671.248
191-001 | Title I design WBS 161 LN2 manifolds&piping | 0 | 13697.6 | 13697.6 | 1 | 16 | 161 |  | 28 | 28% | 3835.328
163.001 | Title I design WBS 163 Coil protection | 0 | 14746.4 | 14746.4 | 1 | 16 | 163 |  | 28 | 28% | 4128.992
163.011 | Title II design WBS 163 Coil protection | 0 | 14746.4 | 14746.4 | 1 | 16 | 163 |  | 28 | 28% | 4128.992
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 0 | 24191.12 | 24191.12 | 1 | 16 | 161 |  | 28 | 28% | 6773.5136
191-011 | Title II design WBS 161 LN2 manifolds&piping | 0 | 27395.2 | 27395.2 | 1 | 16 | 161 |  | 28 | 28% | 7670.656
191-001 | Title I design WBS 161 LN2 manifolds&piping | 0 | 36957.24 | 36957.24 | 1 | 16 | 161 |  | 28 | 28% | 10348.0272
191-037 | Procurement WBS 161 | 0 | 69873.63 | 69873.63 | 1 | 16 | 161 |  | 28 | 28% | 19564.6164
191-011 | Title II design WBS 161 LN2 manifolds&piping | 0 | 74061.72 | 74061.72 | 1 | 16 | 161 |  | 28 | 28% | 20737.2816
191-042 | PDR #17,25,3 | 0 | 2680.65 | 2680.65 | 1 | 16 | 161 |  | 30 | 30% | 804.195
132-000 | PDR #17 & 25 | 0 | 2997.77 | 2997.77 | 1 | 16 | 162 |  | 30 | 30% | 899.331
191-042 | PDR #17,25,3 | 0 | 7666.2 | 7666.2 | 1 | 16 | 161 |  | 30 | 30% | 2299.86
132-000 | PDR #17 & 25 | 0 | 37195.08 | 37195.08 | 1 | 16 | 162 |  | 30 | 30% | 11158.524
191-038 | PDR#17 | 0 | 58777 | 58777 | 1 | 16 | 161 |  | 30 | 30% | 17633.1
151-037 | Cryostat Procurement [A/1] | 0 | 3670 | 3670 | 1 | 17 | 171 | 1751 | 28 | 28% | 1027.6
151-031 | Title III engr | 0 | 6057 | 6057 | 1 | 17 | 171 | 1751 | 28 | 28% | 1695.96
151-001 | Title I design WBS 171 cryostat shell & struct | 41093.08 | 48344.8 | 7251.72 | 1 | 17 | 171 | 1701 | 28 | 28% | 2030.4816
151-001 | Title I design WBS 171 cryostat shell & struct | 67707.991 | 79656.46 | 11948.469 | 1 | 17 | 171 | 1701 | 28 | 28% | 3345.5713
151-031 | Title III engr | 0 | 24488.97 | 24488.97 | 1 | 17 | 171 | 1751 | 28 | 28% | 6856.9116
151-011 | Final Design Cryostat WBS 171 | 0 | 63003.13 | 63003.13 | 1 | 17 | 171 | 1701 | 28 | 28% | 17640.8764
151-011 | Final Design Cryostat WBS 171 | 0 | 165959.09 | 165959.09 | 1 | 17 | 171 | 1701 | 28 | 28% | 46468.5452
151-037 | Cryostat Procurement [A/1] | 0 | 474972.75 | 474972.75 | 1 | 17 | 171 | 1751 | 28 | 28% | 132992.37
161-001 | Title I design WBS 172 base support struct | 15178.4415 | 17856.99 | 2678.5485 | 1 | 17 | 172 | 1701 | 32 | 32% | 857.1355
161-037 | Machine Base&supports Procurement [A/1] | 0 | 3470 | 3470 | 1 | 17 | 172 | 1752 | 32 | 32% | 1110.4
161-001 | Title I design WBS 172 base support struct | 28026.6675 | 32972.55 | 4945.8825 | 1 | 17 | 172 | 1701 | 32 | 32% | 1582.6824
161-031 | Title III engr WBS 172 | 0 | 10248 | 10248 | 1 | 17 | 172 | 1752 | 32 | 32% | 3279.36
161-011 | Final Design Base Support Structure WBS 172 | 0 | 28541.3 | 28541.3 | 1 | 17 | 172 | 1701 | 32 | 32% | 9133.216
161-011 | Final Design Base Support Structure WBS 172 | 0 | 33832.98 | 33832.98 | 1 | 17 | 172 | 1701 | 32 | 32% | 10826.5536
161-031 | Title III engr WBS 172 | 0 | 37104.48 | 37104.48 | 1 | 17 | 172 | 1752 | 32 | 32% | 11873.4336
161-037 | Machine Base&supports Procurement [A/1] | 0 | 279581.7 | 279581.7 | 1 | 17 | 172 | 1752 | 32 | 32% | 89466.144
722.010 | Receive/Inspect TF & PF Coils | 0 | 30136.02 | 30136.02 | 1 | 18 | 183 | 1808 | 20 | 20% | 6027.204
722.010 | Receive/Inspect TF & PF Coils | 0 | 48978.76 | 48978.76 | 1 | 18 | 183 | 1808 | 20 | 20% | 9795.752
740.020 | Faculity Prep | 0 | 10410 | 10410 | 1 | 18 | 187 | 1804 | 24 | 24% | 2498.4
181.110 | PPPL EM LOE FY05 | 1167.936 | 13904 | 12736.064 | 1 | 18 | 181 | 1802 | 24 | 24% | 3056.6554
181.120 | PPPL EM LOE FY06 | 0 | 13883.2 | 13883.2 | 1 | 18 | 181 | 1802 | 24 | 24% | 3331.968
740.020 | Faculity Prep | 0 | 18648 | 18648 | 1 | 18 | 187 | 1804 | 24 | 24% | 4475.52
181.110 | PPPL EM LOE FY05 | 2813.832 | 33498 | 30684.168 | 1 | 18 | 181 | 1802 | 24 | 24% | 7364.2003
740.020 | Faculity Prep | 0 | 31799.04 | 31799.04 | 1 | 18 | 187 | 1804 | 24 | 24% | 7631.7696
740.050 | Purchase- targets [A/9] | 0 | 34725 | 34725 | 1 | 18 | 187 | 1804 | 24 | 24% | 8334
740.035 | Deliver Metrology Software | 0 | 62435.55 | 62435.55 | 1 | 18 | 187 | 1804 | 24 | 24% | 14984.532
181.210 | HP Coverage in the TFTR TC LOE FY05 | 11938.836 | 142129 | 130190.164 | 1 | 18 | 181 | 1802 | 24 | 24% | 31245.6394
181.220 | HP Coverage in the TFTR TC LOE FY06 | 0 | 144966.02 | 144966.02 | 1 | 18 | 181 | 1802 | 24 | 24% | 34791.8448
181.121 | PPPL EM LOE FY06 | 0 | 179340 | 179340 | 1 | 18 | 181 | 1802 | 24 | 24% | 43041.6
181.120 | PPPL EM LOE FY06 | 0 | 206709.33 | 206709.33 | 1 | 18 | 181 | 1802 | 24 | 24% | 49610.2392
1803-3.04 | VV support stand - model design and drawing deta | 0 | 671.56 | 671.56 | 1 | 18 | 186 | 1803 | 40 | 40% | 268.624
1803-1.07 | Design check and sign-off | 0 | 837.2 | 837.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 334.88
1803-2.07 | Design check and sign-off | 0 | 837.2 | 837.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 334.88
1803-3.09 | Design check and sign-off | 0 | 837.2 | 837.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 334.88
1803-4.09 | Design check and sign-off | 0 | 853.76 | 853.76 | 1 | 18 | 186 | 1803 | 40 | 40% | 341.504
S1P1-102 | Mount VV on VV Prep fixture (top side up) | 0 | 973.44 | 973.44 | 1 | 18 | 184 | 1810 | 40 | 40% | 389.376
S1P2-102 | Mount VV on VV Prep fixture (top side up) | 0 | 973.44 | 973.44 | 1 | 18 | 184 | 1810 | 40 | 40% | 389.376
S1P3-102 | Mount VV on VV Prep fixture (top side up) | 0 | 973.44 | 973.44 | 1 | 18 | 184 | 1810 | 40 | 40% | 389.376
1803-3.05 | Platform - design and drawing details | 0 | 1007.34 | 1007.34 | 1 | 18 | 186 | 1803 | 40 | 40% | 402.936
1803-3.08 | PDR Platform & Support Stands | 0 | 1007.34 | 1007.34 | 1 | 18 | 186 | 1803 | 40 | 40% | 402.936
1803-3.081 | FDR Platform & Support Stands | 0 | 1007.34 | 1007.34 | 1 | 18 | 186 | 1803 | 40 | 40% | 402.936
1803-3.082 | PDR Turning Fixture,base&gantry crane | 0 | 1007.34 | 1007.34 | 1 | 18 | 186 | 1803 | 40 | 40% | 402.936
1803-3.083 | FDR Turning Fixture,base&gantry crane | 0 | 1007.34 | 1007.34 | 1 | 18 | 186 | 1803 | 40 | 40% | 402.936
1803-1.02 | VV Support Fixture - model design& drawing detai | 0 | 1343.12 | 1343.12 | 1 | 18 | 186 | 1803 | 40 | 40% | 537.248
1803-2.02 | MC Holding Fixture 1 - model design and drawing | 0 | 1343.12 | 1343.12 | 1 | 18 | 186 | 1803 | 40 | 40% | 537.248
S4P1-110 | Inspect Welds | 0 | 1362.88 | 1362.88 | 1 | 18 | 185 | 1810 | 40 | 40% | 545.152
S4P2-110 | Inspect Welds | 0 | 1362.88 | 1362.88 | 1 | 18 | 185 | 1810 | 40 | 40% | 545.152
S4P3-110 | Inspect Welds | 0 | 1362.88 | 1362.88 | 1 | 18 | 185 | 1810 | 40 | 40% | 545.152
1803-4.06 | Metrology - sightline layout design details metr | 0 | 1369.76 | 1369.76 | 1 | 18 | 186 | 1803 | 40 | 40% | 547.904
1803-4.08 | PDR | 0 | 1369.76 | 1369.76 | 1 | 18 | 186 | 1803 | 40 | 40% | 547.904
1803-4.081 | FDR | 0 | 1369.76 | 1369.76 | 1 | 18 | 186 | 1803 | 40 | 40% | 547.904
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 1797.8 | 1797.8 | 1 | 18 | 186 | 1803 | 40 | 40% | 719.12
S1P1-110 | Flip VV to expose lower surface | 0 | 1946.88 | 1946.88 | 1 | 18 | 184 | 1810 | 40 | 40% | 778.752
S1P2-110 | Flip VV to expose lower surface | 0 | 1946.88 | 1946.88 | 1 | 18 | 184 | 1810 | 40 | 40% | 778.752
S1P3-109 | Flip VV to expose lower surface | 0 | 1946.88 | 1946.88 | 1 | 18 | 184 | 1810 | 40 | 40% | 778.752
1803-1.06 | Design review PDR | 0 | 2014.68 | 2014.68 | 1 | 18 | 186 | 1803 | 40 | 40% | 805.872
1803-1.061 | Design review FDR | 0 | 2014.68 | 2014.68 | 1 | 18 | 186 | 1803 | 40 | 40% | 805.872
1803-2.03 | MC Assembly Fixture 2- design & drawing details | 0 | 2014.68 | 2014.68 | 1 | 18 | 186 | 1803 | 40 | 40% | 805.872
1803-2.06 | PDR | 0 | 2014.68 | 2014.68 | 1 | 18 | 186 | 1803 | 40 | 40% | 805.872
1803-2.061 | FDR | 0 | 2014.68 | 2014.68 | 1 | 18 | 186 | 1803 | 40 | 40% | 805.872
1803-3.02 | MC Turning Fixture and base - model design and d | 0 | 2014.68 | 2014.68 | 1 | 18 | 186 | 1803 | 40 | 40% | 805.872
1803-3.03 | MC Gantry Crane - model design and drawing detai | 0 | 2014.68 | 2014.68 | 1 | 18 | 186 | 1803 | 40 | 40% | 805.872
S3P1-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 2044.32 | 2044.32 | 1 | 18 | 185 | 1810 | 40 | 40% | 817.728
S3P2-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 2044.32 | 2044.32 | 1 | 18 | 185 | 1810 | 40 | 40% | 817.728
S3P3-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 2044.32 | 2044.32 | 1 | 18 | 185 | 1810 | 40 | 40% | 817.728
1803-4.02 | MC Support Stand - model design and drawing deta | 0 | 2054.64 | 2054.64 | 1 | 18 | 186 | 1803 | 40 | 40% | 821.856
1803-4.03 | TF HP support turning fixture - model design d | 0 | 2054.64 | 2054.64 | 1 | 18 | 186 | 1803 | 40 | 40% | 821.856
1803-4.04 | FP Assembly platform - model design drawing det | 0 | 2054.64 | 2054.64 | 1 | 18 | 186 | 1803 | 40 | 40% | 821.856
1803-4.05 | VV Port Alignment/Weldment Fixture - design and | 0 | 2054.64 | 2054.64 | 1 | 18 | 186 | 1803 | 40 | 40% | 821.856
1803-5.01 | Finalize TFTR test cell FPA assembly layout draw | 0 | 2511.6 | 2511.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 1004.64
1803-1.07 | Design check and sign-off | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-1.08 | Prep & Issue Spec,dwgs,and requisition | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-1.09 | Safety Review documentation / presentation | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-1.10 | Fab / Design Review - follow-up activities | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-2.07 | Design check and sign-off | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-2.08 | Procurement Lead Time and Award | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-2.09 | Safety Review documentation / presentation | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-2.10 | Fab / Design Review - follow-up activities | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-3.09 | Design check and sign-off | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
1803-3.12 | Safety Review documentation / presentation | 0 | 2686.24 | 2686.24 | 1 | 18 | 186 | 1803 | 40 | 40% | 1074.496
S3P1-110 | Perform final metrology position check | 0 | 2725.76 | 2725.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1090.304
S3P2-110 | Perform final metrology position check | 0 | 2725.76 | 2725.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1090.304
S3P3-110 | Perform final metrology position check | 0 | 2725.76 | 2725.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1090.304
1803-4.09 | Design check and sign-off | 0 | 2739.52 | 2739.52 | 1 | 18 | 186 | 1803 | 40 | 40% | 1095.808
1803-4.11 | Safety Review documentation / presentation | 0 | 2739.52 | 2739.52 | 1 | 18 | 186 | 1803 | 40 | 40% | 1095.808
1803-4.12 | Fabrication - follow-up activities | 0 | 2739.52 | 2739.52 | 1 | 18 | 186 | 1803 | 40 | 40% | 1095.808
S3P1-101 | Mount VV to MC turning fixt base; metr check | 0 | 3893.76 | 3893.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1557.504
S3P1-102 | Mount MC on turning fixt; perform metr checks | 0 | 3893.76 | 3893.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1557.504
S3P1-104 | Transfer load to crane and recheck position | 0 | 3893.76 | 3893.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1557.504
S3P1-105 | Move MC turning fixt; mount MC on turning fixt | 0 | 3893.76 | 3893.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1557.504
S3P1-107 | Move left & right MC to final position & measure | 0 | 3893.76 | 3893.76 | 1 | 18 | 185 | 1810 | 40 | 40% | 1557.504
S3P1-109 | Bolt together at flange interface. | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P1-111 | Secure VV to MC's using temporary supports. | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P2-101 | Mount VV to MC turning fixt base; metr check | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P2-102 | Mount MC on turning fixt; perform metr checks | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P2-104 | Transfer load to crane and recheck position | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P2-105 | Move MC turning fixt; mount MC on turning fixt | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P2-107 | Move left & right MC to final position & measure | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P2-109 | Bolt together at flange interface. | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P2-111 | Secure VV to MC's using temporary supports. | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P3-101 | Mount VV to MC turning fixt base; metr check | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P3-102 | Mount MC on turning fixt; perform metr checks | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P3-104 | Transfer load to crane and recheck position | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P3-105 | Move MC turning fixt; mount MC on turning fixt | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P3-107 | Move left & right MC to final position & measure | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P3-109 | Bolt together at flange interface. | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S3P3-111 | Secure VV to MC's using temporary supports. | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P1-101 | Mount MC/VV assembly to support frame a | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P1-105 | Change platforms | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P1-113 | Adjust final support base interfaces | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P1-114 | Prepare Field Period for shipment | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P2-101 | Mount MC/VV assembly to support frame a | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P2-105 | Change platforms | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P2-113 | Adjust final support base interfaces | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P2-114 | Prepare Field Period for shipment | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P3-101 | Mount MC/VV assembly to support frame a | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P3-105 | Change platforms | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P3-113 | Adjust final support base interfaces | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
S4P3-114 | Prepare Field Period for shipment | 0 | 4088.64 | 4088.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 1635.456
1803-4.10 | Procurement lead time | 0 | 4109.28 | 4109.28 | 1 | 18 | 186 | 1803 | 40 | 40% | 1643.712
1803-1.10 | Fab / Design Review - follow-up activities | 0 | 4186 | 4186 | 1 | 18 | 186 | 1803 | 40 | 40% | 1674.4
1803-2.10 | Fab / Design Review - follow-up activities | 0 | 4186 | 4186 | 1 | 18 | 186 | 1803 | 40 | 40% | 1674.4
1803-3.01 | Concept definition and requirements | 0 | 4186 | 4186 | 1 | 18 | 186 | 1803 | 40 | 40% | 1674.4
1803-3.13 | Fabrication - follow-up activities | 0 | 4230.95 | 4230.95 | 1 | 18 | 186 | 1803 | 40 | 40% | 1692.38
1803-4.01 | Concept definition and requirements | 0 | 4268.8 | 4268.8 | 1 | 18 | 186 | 1803 | 40 | 40% | 1707.52
1803-4.12 | Fabrication - follow-up activities | 0 | 4268.8 | 4268.8 | 1 | 18 | 186 | 1803 | 40 | 40% | 1707.52
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 4662 | 4662 | 1 | 18 | 186 | 1803 | 40 | 40% | 1864.8
S4P1-108 | Change platforms | 0 | 5451.52 | 5451.52 | 1 | 18 | 185 | 1810 | 40 | 40% | 2180.608
S4P2-108 | Change platforms | 0 | 5451.52 | 5451.52 | 1 | 18 | 185 | 1810 | 40 | 40% | 2180.608
S4P3-108 | Change platforms | 0 | 5451.52 | 5451.52 | 1 | 18 | 185 | 1810 | 40 | 40% | 2180.608
S1P1-103 | Establish metrology setting; align VV base | 0 | 5840.64 | 5840.64 | 1 | 18 | 184 | 1810 | 40 | 40% | 2336.256
S1P1-116 | Prepare and transfer completed VV to holding are | 0 | 5840.64 | 5840.64 | 1 | 18 | 184 | 1810 | 40 | 40% | 2336.256
S1P2-103 | Establish metrology setting; align VV base | 0 | 5840.64 | 5840.64 | 1 | 18 | 184 | 1810 | 40 | 40% | 2336.256
S1P2-116 | Prepare and transfer completed VV to holding are | 0 | 5840.64 | 5840.64 | 1 | 18 | 184 | 1810 | 40 | 40% | 2336.256
S1P3-103 | Establish metrology setting; align VV base | 0 | 5840.64 | 5840.64 | 1 | 18 | 184 | 1810 | 40 | 40% | 2336.256
S3P1-103 | Rotate right MC to stand-off position&chk | 0 | 5840.64 | 5840.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 2336.256
S3P1-106 | Rotate left MC to stand-off position and check p | 0 | 5840.64 | 5840.64 | 1 | 18 | 185 | 1810 | 40 | 40% | 2336.256
S1P3-114 | Prepare and transfer completed VV to holding are | 0 | 6132.96 | 6132.96 | 1 | 18 | 184 | 1810 | 40 | 40% | 2453.184
S3P2-103 | Rotate right MC to stand-off position&chk | 0 | 6132.96 | 6132.96 | 1 | 18 | 185 | 1810 | 40 | 40% | 2453.184
S3P2-106 | Rotate left MC to stand-off position and check p | 0 | 6132.96 | 6132.96 | 1 | 18 | 185 | 1810 | 40 | 40% | 2453.184
S3P3-103 | Rotate right MC to stand-off position&chk | 0 | 6132.96 | 6132.96 | 1 | 18 | 185 | 1810 | 40 | 40% | 2453.184
S3P3-106 | Rotate left MC to stand-off position and check p | 0 | 6132.96 | 6132.96 | 1 | 18 | 185 | 1810 | 40 | 40% | 2453.184
S4P1-107 | Attach TF coils to MC's | 0 | 6132.96 | 6132.96 | 1 | 18 | 185 | 1810 | 40 | 40% | 2453.184
S4P2-107 | Attach TF coils to MC's | 0 | 6132.96 | 6132.96 | 1 | 18 | 185 | 1810 | 40 | 40% | 2453.184
S4P3-107 | Attach TF coils to MC's | 0 | 6132.96 | 6132.96 | 1 | 18 | 185 | 1810 | 40 | 40% | 2453.184
1803-1.01 | Concept definition and requirements | 0 | 6279 | 6279 | 1 | 18 | 186 | 1803 | 40 | 40% | 2511.6
1803-2.01 | Concept definition and requirements | 0 | 6279 | 6279 | 1 | 18 | 186 | 1803 | 40 | 40% | 2511.6
1803-2.02 | MC Holding Fixture 1 - model design and drawing | 0 | 6279 | 6279 | 1 | 18 | 186 | 1803 | 40 | 40% | 2511.6
1803-1.13 | FAB VV Prep Station Platform | 0 | 6450 | 6450 | 1 | 18 | 186 | 1803 | 40 | 40% | 2580
1803-1.14 | FAB VV Prep Station metrology stands | 0 | 6450 | 6450 | 1 | 18 | 186 | 1803 | 40 | 40% | 2580
1803-3.16B | FAB -MC Installation Metrology sprt stands | 0 | 6450 | 6450 | 1 | 18 | 186 | 1803 | 40 | 40% | 2580
1803-3.01 | Concept definition and requirements | 0 | 6715.6 | 6715.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 2686.24
1803-3.06 | Metrology - sightline layout design details metr | 0 | 6715.6 | 6715.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 2686.24
1803-5.01 | Finalize TFTR test cell FPA assembly layout draw | 0 | 6715.6 | 6715.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 2686.24
1803-5.02 | Establish an assembly interface requirements doc | 0 | 6715.6 | 6715.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 2686.24
1803-5.03 | Develop test components as needed to qualify ass | 0 | 6715.6 | 6715.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 2686.24
1803-3.13 | Fabrication - follow-up activities | 0 | 6787.91 | 6787.91 | 1 | 18 | 186 | 1803 | 40 | 40% | 2715.164
S4P1-103 | Inspect Welds | 0 | 6814.4 | 6814.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 2725.76
S4P1-115 | Transfer completed assy to C-site test cell | 0 | 6814.4 | 6814.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 2725.76
S4P2-103 | Inspect Welds | 0 | 6814.4 | 6814.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 2725.76
S4P2-115 | Transfer completed assy to C-site test cell | 0 | 6814.4 | 6814.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 2725.76
S4P3-103 | Inspect Welds | 0 | 6814.4 | 6814.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 2725.76
S4P3-115 | Transfer completed assy to C-site test cell | 0 | 6814.4 | 6814.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 2725.76
1803-4.01 | Concept definition and requirements | 0 | 6848.8 | 6848.8 | 1 | 18 | 186 | 1803 | 40 | 40% | 2739.52
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 7420 | 7420 | 1 | 18 | 186 | 1803 | 40 | 40% | 2968
S1P1-101 | Receive VV and inspect | 0 | 7787.52 | 7787.52 | 1 | 18 | 184 | 1810 | 40 | 40% | 3115.008
S1P2-101 | Receive VV and inspect | 0 | 7787.52 | 7787.52 | 1 | 18 | 184 | 1810 | 40 | 40% | 3115.008
S1P3-101 | Receive VV and inspect | 0 | 7787.52 | 7787.52 | 1 | 18 | 184 | 1810 | 40 | 40% | 3115.008
S4P1-104 | Assemble left TF Coil Assembly check position | 0 | 8177.28 | 8177.28 | 1 | 18 | 185 | 1810 | 40 | 40% | 3270.912
S4P1-106 | Assemble right TF Coil Assembly | 0 | 8177.28 | 8177.28 | 1 | 18 | 185 | 1810 | 40 | 40% | 3270.912
S4P2-104 | Assemble left TF Coil Assembly check position | 0 | 8177.28 | 8177.28 | 1 | 18 | 185 | 1810 | 40 | 40% | 3270.912
S4P2-106 | Assemble right TF Coil Assembly | 0 | 8177.28 | 8177.28 | 1 | 18 | 185 | 1810 | 40 | 40% | 3270.912
S4P3-104 | Assemble left TF Coil Assembly check position | 0 | 8177.28 | 8177.28 | 1 | 18 | 185 | 1810 | 40 | 40% | 3270.912
S4P3-106 | Assemble right TF Coil Assembly | 0 | 8177.28 | 8177.28 | 1 | 18 | 185 | 1810 | 40 | 40% | 3270.912
1803-2.04 | Metrology - sightline layout design details metr | 0 | 8372 | 8372 | 1 | 18 | 186 | 1803 | 40 | 40% | 3348.8
1803-3.04 | VV support stand - model design and drawing deta | 0 | 8372 | 8372 | 1 | 18 | 186 | 1803 | 40 | 40% | 3348.8
1803-3.05 | Platform - design and drawing details | 0 | 8372 | 8372 | 1 | 18 | 186 | 1803 | 40 | 40% | 3348.8
1803-3.06 | Metrology - sightline layout design details metr | 0 | 8372 | 8372 | 1 | 18 | 186 | 1803 | 40 | 40% | 3348.8
1803-4.06 | Metrology - sightline layout design details metr | 0 | 8537.6 | 8537.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 3415.04
184-100 | Assemble 3 TF coils&structure -Left-Period #1 | 0 | 8880 | 8880 | 1 | 18 | 185 | 1808 | 40 | 40% | 3552
184-105 | Assemble 3 TF coils&structure -Right -Period #1 | 0 | 8880 | 8880 | 1 | 18 | 185 | 1808 | 40 | 40% | 3552
184-110 | Assemble 3 TF coils&structure -Left-Period #2 | 0 | 8880 | 8880 | 1 | 18 | 185 | 1808 | 40 | 40% | 3552
184-115 | Assemble 3 TF coils&structure -Right -Period #2 | 0 | 8880 | 8880 | 1 | 18 | 185 | 1808 | 40 | 40% | 3552
184-120 | Assemble 3 TF coils&structure -Left -Period #3 | 0 | 8880 | 8880 | 1 | 18 | 185 | 1808 | 40 | 40% | 3552
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 8964.8 | 8964.8 | 1 | 18 | 186 | 1803 | 40 | 40% | 3585.92
184-125 | Assemble 3 TF coils&structure -Right -Period #3 | 0 | 9324 | 9324 | 1 | 18 | 185 | 1808 | 40 | 40% | 3729.6
713A.040 | General procurements | 0 | 9806.25 | 9806.25 | 1 | 18 | 186 | 1803 | 40 | 40% | 3922.5
713A.050 | Welding tools, materials & equipt | 0 | 9806.25 | 9806.25 | 1 | 18 | 186 | 1803 | 40 | 40% | 3922.5
1803-1.01 | Concept definition and requirements | 0 | 10073.4 | 10073.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 4029.36
1803-2.01 | Concept definition and requirements | 0 | 10073.4 | 10073.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 4029.36
1803-2.04 | Metrology - sightline layout design details metr | 0 | 10073.4 | 10073.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 4029.36
1803-3.10 | Procurement lead time turning fixt,base&gantry | 0 | 10073.4 | 10073.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 4029.36
1803-3.101 | Procurement lead time platforms & supports | 0 | 10073.4 | 10073.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 4029.36
1803-7.02 | Develop and maintain concept definition document | 0 | 10073.4 | 10073.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 4029.36
1803-1.02 | VV Support Fixture - model design& drawing detai | 0 | 12558 | 12558 | 1 | 18 | 186 | 1803 | 40 | 40% | 5023.2
1803-1.04 | Metrology -sightline layout metrology support | 0 | 12558 | 12558 | 1 | 18 | 186 | 1803 | 40 | 40% | 5023.2
1803-2.03 | MC Assembly Fixture 2- design & drawing details | 0 | 12558 | 12558 | 1 | 18 | 186 | 1803 | 40 | 40% | 5023.2
1803-3.02 | MC Turning Fixture and base - model design and d | 0 | 12558 | 12558 | 1 | 18 | 186 | 1803 | 40 | 40% | 5023.2
1803-3.03 | MC Gantry Crane - model design and drawing detai | 0 | 12558 | 12558 | 1 | 18 | 186 | 1803 | 40 | 40% | 5023.2
1803-5.03 | Develop test components as needed to qualify ass | 0 | 12558 | 12558 | 1 | 18 | 186 | 1803 | 40 | 40% | 5023.2
1803-4.02 | MC Support Stand - model design and drawing deta | 0 | 12806.4 | 12806.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 5122.56
1803-4.03 | TF HP support turning fixture - model design d | 0 | 12806.4 | 12806.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 5122.56
1803-4.04 | FP Assembly platform - model design drawing det | 0 | 12806.4 | 12806.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 5122.56
1803-4.05 | VV Port Alignment/Weldment Fixture - design and | 0 | 12806.4 | 12806.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 5122.56
1803-1.12 | FAB - VV support Fixture | 0 | 12900 | 12900 | 1 | 18 | 186 | 1803 | 40 | 40% | 5160
1803-2.12 | Fab MC MC HP Assy Metrology support stands (2) | 0 | 12900 | 12900 | 1 | 18 | 186 | 1803 | 40 | 40% | 5160
1803-3.16A | FAB -Platform | 0 | 12900 | 12900 | 1 | 18 | 186 | 1803 | 40 | 40% | 5160
1803-4.16 | FAB-MC Temporary End Supports (2) | 0 | 12900 | 12900 | 1 | 18 | 186 | 1803 | 40 | 40% | 5160
1803-4.17 | FAB-Final FP Assy Metrology suprt stands (2) | 0 | 12900 | 12900 | 1 | 18 | 186 | 1803 | 40 | 40% | 5160
1803-4.18 | FAB-VV Port alignment/weldment fixtures (2) | 0 | 12900 | 12900 | 1 | 18 | 186 | 1803 | 40 | 40% | 5160
1803-1.04 | Metrology -sightline layout metrology support | 0 | 13431.2 | 13431.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 5372.48
1803-1.05 | Structural / Seismic Analysis check | 0 | 13431.2 | 13431.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 5372.48
1803-2.05 | Structural / Seismic Analysis check | 0 | 13431.2 | 13431.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 5372.48
1803-5.03 | Develop test components as needed to qualify ass | 0 | 13431.2 | 13431.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 5372.48
1803-7.03 | Develop and maintain assembly plan document | 0 | 13431.2 | 13431.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 5372.48
S1P3-106 | Attach studs, coolant lines and insulation on to | 0 | 13628.16 | 13628.16 | 1 | 18 | 184 | 1810 | 40 | 40% | 5451.264
S1P3-110 | Attach studs, coolant lines and insulation on bo | 0 | 13628.16 | 13628.16 | 1 | 18 | 184 | 1810 | 40 | 40% | 5451.264
1803-4.07 | Structural / Seismic Analysis check | 0 | 13697.6 | 13697.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 5479.04
1803-7.01 | Meetings Prep and Reporting | 0 | 14102.76 | 14102.76 | 1 | 18 | 186 | 1803 | 40 | 40% | 5641.104
1803-3.15A | FAB - MC Gantry Crane | 0 | 15480 | 15480 | 1 | 18 | 186 | 1803 | 40 | 40% | 6192
S1P1-106 | Attach studs, coolant lines and insulation on to | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P1-107 | Wind magnetic diagnostic sensors to top surface | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P1-112 | Attach studs, coolant lines and insulation on bo | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P1-113 | Wind magnetic diagnostic sensors to bot surface | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P2-106 | Attach studs, coolant lines and insulation on to | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P2-107 | Wind magnetic diagnostic sensors to top surface | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P2-112 | Attach studs, coolant lines and insulation on bo | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P2-113 | Wind magnetic diagnostic sensors to bot surface | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P3-107 | Install cooling/htg lines to vac vsl top surface | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S1P3-112 | Install cooling/htg lines to vac vsl bot surface | 0 | 15575.04 | 15575.04 | 1 | 18 | 184 | 1810 | 40 | 40% | 6230.016
S4P1-109 | Position, weld two large horizontal diag ports | 0 | 16354.56 | 16354.56 | 1 | 18 | 185 | 1810 | 40 | 40% | 6541.824
S4P2-109 | Position, weld two large horizontal diag ports | 0 | 16354.56 | 16354.56 | 1 | 18 | 185 | 1810 | 40 | 40% | 6541.824
S4P3-109 | Position, weld two large horizontal diag ports | 0 | 16354.56 | 16354.56 | 1 | 18 | 185 | 1810 | 40 | 40% | 6541.824
1803-3.16 | FAB - VV suprt stand & misc crane fixtures | 0 | 19350 | 19350 | 1 | 18 | 186 | 1803 | 40 | 40% | 7740
1803-4.14 | FAB-TF HP support & Turning Fixtures (2) | 0 | 19350 | 19350 | 1 | 18 | 186 | 1803 | 40 | 40% | 7740
1803-7.01 | Meetings Prep and Reporting | 0 | 19883.5 | 19883.5 | 1 | 18 | 186 | 1803 | 40 | 40% | 7953.4
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 20443.2 | 20443.2 | 1 | 18 | 186 | 1803 | 40 | 40% | 8177.28
S4P1-111 | Assemble external trim coils to TF Coil | 0 | 20443.2 | 20443.2 | 1 | 18 | 185 | 1810 | 40 | 40% | 8177.28
S4P2-111 | Assemble external trim coils to TF Coil | 0 | 20443.2 | 20443.2 | 1 | 18 | 185 | 1810 | 40 | 40% | 8177.28
S4P3-111 | Assemble external trim coils to TF Coil | 0 | 20443.2 | 20443.2 | 1 | 18 | 185 | 1810 | 40 | 40% | 8177.28
S1P1-108 | Install cooling/htg lines to vac vsl top surface | 0 | 20766.72 | 20766.72 | 1 | 18 | 184 | 1810 | 40 | 40% | 8306.688
S1P1-114 | Install cooling/htg lines to vac vsl bot surface | 0 | 20766.72 | 20766.72 | 1 | 18 | 184 | 1810 | 40 | 40% | 8306.688
S1P2-108 | Install cooling/htg lines to vac vsl top surface | 0 | 20766.72 | 20766.72 | 1 | 18 | 184 | 1810 | 40 | 40% | 8306.688
S1P2-114 | Install cooling/htg lines to vac vsl bot surface | 0 | 20766.72 | 20766.72 | 1 | 18 | 184 | 1810 | 40 | 40% | 8306.688
1803-5.03 | Develop test components as needed to qualify ass | 0 | 20835 | 20835 | 1 | 18 | 186 | 1803 | 40 | 40% | 8334
S3P1-108 | Install shims ( as reqd); ream 24 holes | 0 | 22713.6 | 22713.6 | 1 | 18 | 185 | 1810 | 40 | 40% | 9085.44
1803-7.04 | Mike Cole's FY05 on-site involvement in assembly | 0 | 23558.4 | 23558.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 9423.36
S3P2-108 | Install shims ( as reqd); ream 24 holes | 0 | 23850.4 | 23850.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 9540.16
S3P3-108 | Install shims ( as reqd); ream 24 holes | 0 | 23850.4 | 23850.4 | 1 | 18 | 185 | 1810 | 40 | 40% | 9540.16
1803-7.01 | Meetings Prep and Reporting | 0 | 24906.7 | 24906.7 | 1 | 18 | 186 | 1803 | 40 | 40% | 9962.68
1803-3.11 | Procurement Technical Rep | 0 | 25794.05 | 25794.05 | 1 | 18 | 186 | 1803 | 40 | 40% | 10317.62
1803-2.11 | Fab MC HP Assy Fixtures (2) | 0 | 25800 | 25800 | 1 | 18 | 186 | 1803 | 40 | 40% | 10320
1803-4.13 | FAB-MC Support Stands (2) | 0 | 25800 | 25800 | 1 | 18 | 186 | 1803 | 40 | 40% | 10320
184-100 | Assemble 3 TF coils&structure -Left-Period #1 | 0 | 25958.4 | 25958.4 | 1 | 18 | 185 | 1808 | 40 | 40% | 10383.36
184-105 | Assemble 3 TF coils&structure -Right -Period #1 | 0 | 25958.4 | 25958.4 | 1 | 18 | 185 | 1808 | 40 | 40% | 10383.36
184-110 | Assemble 3 TF coils&structure -Left-Period #2 | 0 | 25958.4 | 25958.4 | 1 | 18 | 185 | 1808 | 40 | 40% | 10383.36
184-115 | Assemble 3 TF coils&structure -Right -Period #2 | 0 | 25958.4 | 25958.4 | 1 | 18 | 185 | 1808 | 40 | 40% | 10383.36
184-120 | Assemble 3 TF coils&structure -Left -Period #3 | 0 | 25958.4 | 25958.4 | 1 | 18 | 185 | 1808 | 40 | 40% | 10383.36
1803-3.07 | Structural / Seismic Analysis check | 0 | 26862.4 | 26862.4 | 1 | 18 | 186 | 1803 | 40 | 40% | 10744.96
184-125 | Assemble 3 TF coils&structure -Right -Period #3 | 0 | 27257.6 | 27257.6 | 1 | 18 | 185 | 1808 | 40 | 40% | 10903.04
S1P1-109 | Install insulation to vac vsl to top surface | 0 | 32448 | 32448 | 1 | 18 | 184 | 1810 | 40 | 40% | 12979.2
S1P1-115 | Install insulation to vac vsl to bot surface | 0 | 32448 | 32448 | 1 | 18 | 184 | 1810 | 40 | 40% | 12979.2
S1P2-109 | Install insulation to vac vsl to top surface | 0 | 32448 | 32448 | 1 | 18 | 184 | 1810 | 40 | 40% | 12979.2
S1P2-115 | Install insulation to vac vsl to bot surface | 0 | 32448 | 32448 | 1 | 18 | 184 | 1810 | 40 | 40% | 12979.2
S1P3-108 | Install insulation to vac vsl to top surface | 0 | 32448 | 32448 | 1 | 18 | 184 | 1810 | 40 | 40% | 12979.2
S1P3-113 | Install insulation to vac vsl to bot surface | 0 | 33584.8 | 33584.8 | 1 | 18 | 184 | 1810 | 40 | 40% | 13433.92
1803-4.15 | FAB-FP Assy platforms (2) | 0 | 38700 | 38700 | 1 | 18 | 186 | 1803 | 40 | 40% | 15480
1803-8 | Metrology Support | 0 | 40293.6 | 40293.6 | 1 | 18 | 186 | 1803 | 40 | 40% | 16117.44
S4P1-112 | Close up VV, bakeout 350 deg C, leak check | 0 | 54515.2 | 54515.2 | 1 | 18 | 185 | 1810 | 40 | 40% | 21806.08
S4P2-112 | Close up VV, bakeout 350 deg C, leak check | 0 | 54515.2 | 54515.2 | 1 | 18 | 185 | 1810 | 40 | 40% | 21806.08
S4P3-112 | Close up VV, bakeout 350 deg C, leak check | 0 | 54515.2 | 54515.2 | 1 | 18 | 185 | 1810 | 40 | 40% | 21806.08
1803-7.01 | Meetings Prep and Reporting | 0 | 57250.49 | 57250.49 | 1 | 18 | 186 | 1803 | 40 | 40% | 22900.196
S2P1-100 | Assemble Mod-Coils a1.b1,c1 FP 1 left | 0 | 65544.96 | 65544.96 | 1 | 18 | 185 | 1808 | 40 | 40% | 26217.984
S2P1-200 | Assemble Mod-Coils a2.b2,c2 FP 1 right | 0 | 65544.96 | 65544.96 | 1 | 18 | 185 | 1808 | 40 | 40% | 26217.984
S2P2-100 | Assemble Mod-Coils a3.b3,c3 FP 2 left | 0 | 67002.95 | 67002.95 | 1 | 18 | 185 | 1808 | 40 | 40% | 26801.18
S2P2-200 | Assemble Mod-Coils a4.b4,c4 FP 2 right *2 shift* | 0 | 68825.44 | 68825.44 | 1 | 18 | 185 | 1808 | 40 | 40% | 27530.176
S2P3-100 | Assemble Mod-Coils a5.b5,c5 FP 3 left*2 shift* | 0 | 68825.44 | 68825.44 | 1 | 18 | 185 | 1808 | 40 | 40% | 27530.176
S2P3-200 | Assemble Mod-Coils a6.b6,c6 FP 3 right*2 shift* | 0 | 68825.44 | 68825.44 | 1 | 18 | 185 | 1808 | 40 | 40% | 27530.176
S4P1-102 | Position and weld all ports to VV | 0 | 81772.8 | 81772.8 | 1 | 18 | 185 | 1810 | 40 | 40% | 32709.12
S4P2-102 | Position and weld all ports to VV | 0 | 81772.8 | 81772.8 | 1 | 18 | 185 | 1810 | 40 | 40% | 32709.12
S4P3-102 | Position and weld all ports to VV*2 shift* | 0 | 81772.8 | 81772.8 | 1 | 18 | 185 | 1810 | 40 | 40% | 32709.12
1803-3.15 | FAB - MC Turning fixture & Base | 0 | 161250 | 161250 | 1 | 18 | 186 | 1803 | 40 | 40% | 64500
S1P1-000 | LOE support staff for FP assemblies | 0 | 297683.26 | 297683.26 | 1 | 18 | 185 | 1810 | 40 | 40% | 119073.304
0192-91 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
0192-92 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
0192-93 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
0192-94 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
0192-95 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
0192-96 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
0192-97 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
0192-98 | LOE-F1 mo SO | 0 | 552.04 | 552.04 | 1 | 19 | 192 | 1901 | 10 | 10% | 55.204
192-6.01 | Document coil tolerance and trim coil requiremen | 18558.383 | 19535.14 | 976.757 | 1 | 19 | 192 | 1901 | 10 | 10% | 97.6757
0192-5 | LOE-FY05 WBS 192 | 364.98 | 4345 | 3980.02 | 1 | 19 | 192 | 1901 | 10 | 10% | 398.002
0192-6 | LOE-FY06 WBS 192 | 0 | 4338.5 | 4338.5 | 1 | 19 | 192 | 1901 | 10 | 10% | 433.85
192-6.02 | Check critical coil tolerance calculations. | 5389.725 | 10779.45 | 5389.725 | 1 | 19 | 192 | 1901 | 10 | 10% | 538.9725
192-6.06 | Coil positions to minimize islands. | 16836.883 | 24052.69 | 7215.807 | 1 | 19 | 192 | 1901 | 10 | 10% | 721.5807
0192-91 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0192-92 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0192-93 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0192-94 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0192-95 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0192-96 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0192-97 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0192-98 | LOE-F1 mo SO | 0 | 7733 | 7733 | 1 | 19 | 192 | 1901 | 10 | 10% | 773.3
0191-5 | LOE-FY05 WBS 191 | 729.96 | 8690 | 7960.04 | 1 | 19 | 191 | 1901 | 10 | 10% | 796.004
0191-6 | LOE-FY06 WBS 191 | 0 | 8677 | 8677 | 1 | 19 | 191 | 1901 | 10 | 10% | 867.7
192-6.031 | Demo Method for current center on TRC | 0 | 8707.2 | 8707.2 | 1 | 19 | 192 | 1901 | 10 | 10% | 870.72
0191-6X | LOE-FY07 WBS 191 | 0 | 9175 | 9175 | 1 | 19 | 191 | 1901 | 10 | 10% | 917.5
0192-6X | LOE-FY06 WBS 192 | 0 | 9175 | 9175 | 1 | 19 | 192 | 1901 | 10 | 10% | 917.5
192-6.031 | Demo Method for current center on TRC | 0 | 11779.2 | 11779.2 | 1 | 19 | 192 | 1901 | 10 | 10% | 1177.92
192-6.06 | Coil positions to minimize islands. | 28061.474 | 40087.82 | 12026.346 | 1 | 19 | 192 | 1901 | 10 | 10% | 1202.6346
192-6.031 | Demo Method for current center on TRC | 0 | 13431.2 | 13431.2 | 1 | 19 | 192 | 1901 | 10 | 10% | 1343.12
192-6.03 | Method for determining current center | 68446.328 | 85557.91 | 17111.582 | 1 | 19 | 192 | 1901 | 10 | 10% | 1711.1582
0192-5 | LOE-FY05 WBS 192 | 2660.8781 | 31677.12 | 29016.2419 | 1 | 19 | 192 | 1901 | 10 | 10% | 2901.6242
0192-6 | LOE-FY06 WBS 192 | 0 | 32313.12 | 32313.12 | 1 | 19 | 192 | 1901 | 10 | 10% | 3231.312
0192-6X | LOE-FY06 WBS 192 | 0 | 33067.2 | 33067.2 | 1 | 19 | 192 | 1901 | 10 | 10% | 3306.72
0192-5 | LOE-FY05 WBS 192 | 4947.264 | 58896 | 53948.736 | 1 | 19 | 192 | 1901 | 10 | 10% | 5394.8736
192-6.031 | Demo Method for current center on TRC | 0 | 54601.59 | 54601.59 | 1 | 19 | 192 | 1901 | 10 | 10% | 5460.159
0192-6X | LOE-FY06 WBS 192 | 0 | 92796 | 92796 | 1 | 19 | 192 | 1901 | 10 | 10% | 9279.6
0191-5 | LOE-FY05 WBS 191 | 13604.976 | 161964 | 148359.024 | 1 | 19 | 191 | 1901 | 10 | 10% | 14835.9024
0192-5 | LOE-FY05 WBS 192 | 14841.792 | 176688 | 161846.208 | 1 | 19 | 192 | 1901 | 10 | 10% | 16184.6208
0191-6 | LOE-FY06 WBS 191 | 0 | 161996.65 | 161996.65 | 1 | 19 | 191 | 1901 | 10 | 10% | 16199.665
0191-6X | LOE-FY07 WBS 191 | 0 | 170126 | 170126 | 1 | 19 | 191 | 1901 | 10 | 10% | 17012.6
0192-6 | LOE-FY06 WBS 192 | 0 | 235631.49 | 235631.49 | 1 | 19 | 192 | 1901 | 10 | 10% | 23563.149
21-65 | Integrated Systems Testing/Tech Support | 0 | 2427.4 | 2427.4 | 2 | 21 |  |  | 14 | 14% | 339.836
21-40 | Fabrication/Install Hardware | 0 | 3496.5 | 3496.5 | 2 | 21 |  |  | 14 | 14% | 489.51
21-35 | Eng. Work Planning and Design during fab | 0 | 3586.8 | 3586.8 | 2 | 21 |  |  | 14 | 14% | 502.152
21-60 | Integrated Systems Testing/Eng | 0 | 3586.8 | 3586.8 | 2 | 21 |  |  | 14 | 14% | 502.152
21-15 | Design Gas Handling Hardware | 0 | 4440 | 4440 | 2 | 21 |  |  | 14 | 14% | 621.6
21-55 | Install PLC Controls | 0 | 4854.8 | 4854.8 | 2 | 21 |  |  | 14 | 14% | 679.672
21-10 | Eng. Work Planning and Design | 0 | 5978 | 5978 | 2 | 21 |  |  | 14 | 14% | 836.92
21-45 | Fabrication/installation | 0 | 6388.5 | 6388.5 | 2 | 21 |  |  | 14 | 14% | 894.39
21-45 | Fabrication/installation | 0 | 6625 | 6625 | 2 | 21 |  |  | 14 | 14% | 927.5
21-30 | Drafting | 0 | 8537.6 | 8537.6 | 2 | 21 |  |  | 14 | 14% | 1195.264
21-45 | Fabrication/installation | 0 | 8741.25 | 8741.25 | 2 | 21 |  |  | 14 | 14% | 1223.775
21-20 | Design PLC Controls | 0 | 9247.2 | 9247.2 | 2 | 21 |  |  | 14 | 14% | 1294.608
21-25 | Electrical Drafting for pumping system | 0 | 12806.4 | 12806.4 | 2 | 21 |  |  | 14 | 14% | 1792.896
22-75 | Integrated Systems Testing/Tech Support | 0 | 4854.8 | 4854.8 | 2 | 22 |  |  | 14 | 14% | 679.672
22-70 | Integrated Systems Testing/Eng | 0 | 7173.6 | 7173.6 | 2 | 22 |  |  | 14 | 14% | 1004.304
22-25 | Eng. Work Planning and Design | 0 | 8880 | 8880 | 2 | 22 |  |  | 14 | 14% | 1243.2
22-50 | Perform maint. & repair of pmpg sys | 0 | 9324 | 9324 | 2 | 22 |  |  | 14 | 14% | 1305.36
22-55 | Repair and Calibration of vac instrumentation | 0 | 9324 | 9324 | 2 | 22 |  |  | 14 | 14% | 1305.36
22-45 | Eng. Work Planning and Design during fab | 0 | 16140.6 | 16140.6 | 2 | 22 |  |  | 14 | 14% | 2259.684
22-25 | Eng. Work Planning and Design | 0 | 17080 | 17080 | 2 | 22 |  |  | 14 | 14% | 2391.2
22-40 | Drafting | 0 | 17861.25 | 17861.25 | 2 | 22 |  |  | 14 | 14% | 2500.575
22-65 | Fab PLC conrols | 0 | 19419.2 | 19419.2 | 2 | 22 |  |  | 14 | 14% | 2718.688
22-35 | Electrical Drafting for pumping system | 0 | 23442.89 | 23442.89 | 2 | 22 |  |  | 14 | 14% | 3282.0046
22-60 | Fabrication/installation | 0 | 30475 | 30475 | 2 | 22 |  |  | 14 | 14% | 4266.5
22-60 | Fabrication/installation | 0 | 32368.4 | 32368.4 | 2 | 22 |  |  | 14 | 14% | 4531.576
22-30 | Design PLC based control system | 0 | 38690.43 | 38690.43 | 2 | 22 |  |  | 14 | 14% | 5416.6602
22-65 | Fab PLC conrols | 0 | 42400 | 42400 | 2 | 22 |  |  | 14 | 14% | 5936
22-60 | Fabrication/installation | 0 | 52447.5 | 52447.5 | 2 | 22 |  |  | 14 | 14% | 7342.65
2501-014 | FY04 work accomplished | 4340.16 | 4340.16 | 0 | 2 | 25 | 250 | 2501 | 16 | 16% | 0
25-190.1 | 33) Fabr BL alignment measur fixture, | 26.85 | 26.85 | 0 | 2 | 25 | 250 | 2501 | 16 | 16% | 0
25-099 | FY04 work accomplished | 7627 | 7627 | 0 | 2 | 25 | 250 | 2501 | 16 | 16% | 0
310-030 | Design & Fab Magnetic integrators | 0 | 1915.27 | 1915.27 | 3 | 31 |  | 3101 | 30 | 30% | 574.581
310-020 | Design other ex-vessel sensors | 0 | 3091.8 | 3091.8 | 3 | 31 |  | 3101 | 30 | 30% | 927.54
310-026 | Install ex-vessel sensors on coils | 0 | 5284.48 | 5284.48 | 3 | 31 |  | 3101 | 30 | 30% | 1585.344
310-030 | Design & Fab Magnetic integrators | 0 | 6591.82 | 6591.82 | 3 | 31 |  | 3101 | 30 | 30% | 1977.546
310-025 | Procure matl for ex-vsl sensors | 0 | 6605.6 | 6605.6 | 3 | 31 |  | 3101 | 30 | 30% | 1981.68
310-016 | Install terminal boxes and terminate | 0 | 7431.3 | 7431.3 | 3 | 31 |  | 3101 | 30 | 30% | 2229.39
310-015 | Fabricate Magnetics | 0 | 13211.2 | 13211.2 | 3 | 31 |  | 3101 | 30 | 30% | 3963.36
310-030 | Design & Fab Magnetic integrators | 0 | 13982.11 | 13982.11 | 3 | 31 |  | 3101 | 30 | 30% | 4194.633
310-030 | Design & Fab Magnetic integrators | 0 | 14649.16 | 14649.16 | 3 | 31 |  | 3101 | 30 | 30% | 4394.748
310-025 | Procure matl for ex-vsl sensors | 0 | 14925.3 | 14925.3 | 3 | 31 |  | 3101 | 30 | 30% | 4477.59
310-010 | Design Mag Diagnostics | 0 | 16695.72 | 16695.72 | 3 | 31 |  | 3101 | 30 | 30% | 5008.716
310-025 | Procure matl for ex-vsl sensors | 0 | 17760 | 17760 | 3 | 31 |  | 3101 | 30 | 30% | 5328
310-016 | Install terminal boxes and terminate | 0 | 23695.95 | 23695.95 | 3 | 31 |  | 3101 | 30 | 30% | 7108.785
310-015 | Fabricate Magnetics | 0 | 24639 | 24639 | 3 | 31 |  | 3101 | 30 | 30% | 7391.7
310-015 | Fabricate Magnetics | 0 | 27741.6 | 27741.6 | 3 | 31 |  | 3101 | 30 | 30% | 8322.48
310-010 | Design Mag Diagnostics | 0 | 28501.44 | 28501.44 | 3 | 31 |  | 3101 | 30 | 30% | 8550.432
310-026 | Install ex-vessel sensors on coils | 0 | 34632 | 34632 | 3 | 31 |  | 3101 | 30 | 30% | 10389.6
310-020 | Design other ex-vessel sensors | 0 | 58604 | 58604 | 3 | 31 |  | 3101 | 30 | 30% | 17581.2
310-020 | Design other ex-vessel sensors | 0 | 93925.2 | 93925.2 | 3 | 31 |  | 3101 | 30 | 30% | 28177.56
361-015 | Fab/Assy/Installation Visible Camera | 0 | 3586.8 | 3586.8 | 3 | 36 |  |  | 20 | 20% | 717.36
361-001 | Design Visible Camera sys | 0 | 4648 | 4648 | 3 | 36 |  |  | 20 | 20% | 929.6
361-001 | Design Visible Camera sys | 0 | 7173.6 | 7173.6 | 3 | 36 |  |  | 20 | 20% | 1434.72
361-015 | Fab/Assy/Installation Visible Camera | 0 | 11188.8 | 11188.8 | 3 | 36 |  |  | 20 | 20% | 2237.76
361-015 | Fab/Assy/Installation Visible Camera | 0 | 16268 | 16268 | 3 | 36 |  |  | 20 | 20% | 3253.6
380-015 | Fab & Install Beam probe | 0 | 9709.6 | 9709.6 | 3 | 38 |  |  | 34 | 34% | 3301.264
380-015 | Fab & Install Beam probe | 0 | 10404 | 10404 | 3 | 38 |  |  | 34 | 34% | 3537.36
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 11206 | 11206 | 3 | 38 |  |  | 34 | 34% | 3810.04
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 11620 | 11620 | 3 | 38 |  |  | 34 | 34% | 3950.8
380-015 | Fab & Install Beam probe | 0 | 19813.5 | 19813.5 | 3 | 38 |  |  | 34 | 34% | 6736.59
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 21520.8 | 21520.8 | 3 | 38 |  |  | 34 | 34% | 7317.072
380-015 | Fab & Install Beam probe | 0 | 26560 | 26560 | 3 | 38 |  |  | 34 | 34% | 9030.4
380-015 | Fab & Install Beam probe | 0 | 28694.4 | 28694.4 | 3 | 38 |  |  | 34 | 34% | 9756.096
380-015 | Fab & Install Beam probe | 0 | 151050 | 151050 | 3 | 38 |  |  | 34 | 34% | 51357
390-015 | LOE Support FY05 **reduced scope | 2298.4441 | 27362.43 | 25063.9859 | 3 | 39 |  | 3901 | 30 | 30% | 7519.1958
390-020 | LOE Support FY06 | 0 | 27904.05 | 27904.05 | 3 | 39 |  |  | 30 | 30% | 8371.215
390-015 | LOE Support FY05 **reduced scope | 3354.8155 | 39938.28 | 36583.4645 | 3 | 39 |  | 3901 | 30 | 30% | 10975.0393
390-020 | LOE Support FY06 | 0 | 40727.7 | 40727.7 | 3 | 39 |  |  | 30 | 30% | 12218.31
4101-100.1 | Prepare Preliminary One line diagram | 0 | 170.75 | 170.75 | 4 | 41 | 411 | 4101 | 18 | 18% | 30.735
4101-100.1 | Prepare Preliminary One line diagram | 0 | 184.94 | 184.94 | 4 | 41 | 411 | 4101 | 18 | 18% | 33.2892
4101-100.1 | Prepare Preliminary One line diagram | 0 | 255.9 | 255.9 | 4 | 41 | 411 | 4101 | 18 | 18% | 46.062
4101-100.1 | Prepare Preliminary One line diagram | 0 | 396.34 | 396.34 | 4 | 41 | 411 | 4101 | 18 | 18% | 71.3412
411-3-2 | Test Cell AC Power Distr-Dsn | 0 | 1321.12 | 1321.12 | 4 | 41 | 411 | 4101 | 18 | 18% | 237.8016
411-3-2 | Test Cell AC Power Distr-Dsn | 0 | 2134.4 | 2134.4 | 4 | 41 | 411 | 4101 | 18 | 18% | 384.192
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 2774.4 | 2774.4 | 4 | 41 | 412 | 4101 | 18 | 18% | 499.392
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 2774.72 | 2774.72 | 4 | 41 | 411 | 4101 | 18 | 18% | 499.4496
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 2912.88 | 2912.88 | 4 | 41 | 412 | 4101 | 18 | 18% | 524.3184
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 3358.8 | 3358.8 | 4 | 41 | 412 | 4101 | 18 | 18% | 604.584
411-2-8 | Grounding-Commission | 0 | 4161.6 | 4161.6 | 4 | 41 | 411 | 4101 | 18 | 18% | 749.088
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 4161.6 | 4161.6 | 4 | 41 | 412 | 4101 | 18 | 18% | 749.088
412-1-2 | D-site Pulsed AC Power Distr-Dsn | 0 | 4268.8 | 4268.8 | 4 | 41 | 412 | 4101 | 18 | 18% | 768.384
411-3-6 | Test Cell AC Power Distr-Install | 0 | 4723.64 | 4723.64 | 4 | 41 | 411 | 4101 | 18 | 18% | 850.2552
411-2-8 | Grounding-Commission | 0 | 4854.8 | 4854.8 | 4 | 41 | 411 | 4101 | 18 | 18% | 873.864
411-2-4 | Grounding-Procure | 0 | 6450 | 6450 | 4 | 41 | 411 | 4101 | 18 | 18% | 1161
412-1-4 | D-site Pulsed AC Power Distr-Procure | 0 | 6455.6 | 6455.6 | 4 | 41 | 412 | 4101 | 18 | 18% | 1162.008
412-1-2 | D-site Pulsed AC Power Distr-Dsn | 0 | 6605.6 | 6605.6 | 4 | 41 | 412 | 4101 | 18 | 18% | 1189.008
411-2-8 | Grounding-Commission | 0 | 6717.6 | 6717.6 | 4 | 41 | 411 | 4101 | 18 | 18% | 1209.168
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 6717.6 | 6717.6 | 4 | 41 | 412 | 4101 | 18 | 18% | 1209.168
411-3-6 | Test Cell AC Power Distr-Install | 0 | 6748.56 | 6748.56 | 4 | 41 | 411 | 4101 | 18 | 18% | 1214.7408
411-2-6 | Grounding-Install | 0 | 6936 | 6936 | 4 | 41 | 411 | 4101 | 18 | 18% | 1248.48
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 7166.58 | 7166.58 | 4 | 41 | 411 | 4101 | 18 | 18% | 1289.9844
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 7740 | 7740 | 4 | 41 | 411 | 4101 | 18 | 18% | 1393.2
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 7767.68 | 7767.68 | 4 | 41 | 412 | 4101 | 18 | 18% | 1398.1824
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 8316.88 | 8316.88 | 4 | 41 | 411 | 4101 | 18 | 18% | 1497.0384
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 8323.2 | 8323.2 | 4 | 41 | 411 | 4101 | 18 | 18% | 1498.176
411-2-6 | Grounding-Install | 0 | 9709.6 | 9709.6 | 4 | 41 | 411 | 4101 | 18 | 18% | 1747.728
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 9709.6 | 9709.6 | 4 | 41 | 411 | 4101 | 18 | 18% | 1747.728
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 10238.68 | 10238.68 | 4 | 41 | 411 | 4101 | 18 | 18% | 1842.9624
411-2-2 | Grounding-Dsn | 0 | 11890.08 | 11890.08 | 4 | 41 | 411 | 4101 | 18 | 18% | 2140.2144
411-2-6 | Grounding-Install | 0 | 13435.2 | 13435.2 | 4 | 41 | 411 | 4101 | 18 | 18% | 2418.336
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 13435.2 | 13435.2 | 4 | 41 | 411 | 4101 | 18 | 18% | 2418.336
411-2-2 | Grounding-Dsn | 0 | 17075.2 | 17075.2 | 4 | 41 | 411 | 4101 | 18 | 18% | 3073.536
411-3-6 | Test Cell AC Power Distr-Install | 0 | 19608.18 | 19608.18 | 4 | 41 | 411 | 4101 | 18 | 18% | 3529.4724
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 20640 | 20640 | 4 | 41 | 411 | 4101 | 18 | 18% | 3715.2
411-2-6 | Grounding-Install | 0 | 33125 | 33125 | 4 | 41 | 411 | 4101 | 18 | 18% | 5962.5
411-3-4 | Test Cell AC Power Distr-Procure(pnls & xfrmrs) | 0 | 44354.85 | 44354.85 | 4 | 41 | 411 | 4101 | 18 | 18% | 7983.873
431-200 | Condition/spare parts inventory | 1943.28 | 3886.56 | 1943.28 | 4 | 43 | 431 | 4301 | 18 | 18% | 349.7904
431-225 | Reactivate DF & PEI units | 0 | 2591.04 | 2591.04 | 4 | 43 | 431 | 4301 | 18 | 18% | 466.3872
431-250 | c-site dc sys DGS dsn documentation | 0 | 2591.04 | 2591.04 | 4 | 43 | 431 | 4301 | 18 | 18% | 466.3872
431-265 | Fabricate bus components | 0 | 2606.82 | 2606.82 | 4 | 43 | 431 | 4301 | 18 | 18% | 469.2276
431-225 | Reactivate DF & PEI units | 0 | 2720.16 | 2720.16 | 4 | 43 | 431 | 4301 | 18 | 18% | 489.6288
431-210 | Organize & verify documentation | 3264.192 | 7253.76 | 3989.568 | 4 | 43 | 431 | 4301 | 18 | 18% | 718.1222
431-250 | c-site dc sys DGS dsn documentation | 0 | 4186 | 4186 | 4 | 43 | 431 | 4301 | 18 | 18% | 753.48
431-265 | Fabricate bus components | 0 | 4561.33 | 4561.33 | 4 | 43 | 431 | 4301 | 18 | 18% | 821.0394
431-215 | Document status | 647.76 | 6477.6 | 5829.84 | 4 | 43 | 431 | 4301 | 18 | 18% | 1049.3712
431-225 | Reactivate DF & PEI units | 0 | 6273.6 | 6273.6 | 4 | 43 | 431 | 4301 | 18 | 18% | 1129.248
431-230 | Load | 0 | 6477.6 | 6477.6 | 4 | 43 | 431 | 4301 | 18 | 18% | 1165.968
431-275 | Power cabling & Installation | 0 | 6605.6 | 6605.6 | 4 | 43 | 431 | 4301 | 18 | 18% | 1189.008
431-200 | Condition/spare parts inventory | 6800.4 | 13600.8 | 6800.4 | 4 | 43 | 431 | 4301 | 18 | 18% | 1224.072
431-275 | Power cabling & Installation | 0 | 9030 | 9030 | 4 | 43 | 431 | 4301 | 18 | 18% | 1625.4
431-210 | Organize & verify documentation | 7578.792 | 16841.76 | 9262.968 | 4 | 43 | 431 | 4301 | 18 | 18% | 1667.3342
431-230 | Load | 0 | 9410.4 | 9410.4 | 4 | 43 | 431 | 4301 | 18 | 18% | 1693.872
431-265 | Fabricate bus components | 0 | 9467.71 | 9467.71 | 4 | 43 | 431 | 4301 | 18 | 18% | 1704.1878
431-210 | Organize & verify documentation | 9418.5 | 20930 | 11511.5 | 4 | 43 | 431 | 4301 | 18 | 18% | 2072.07
431-240 | Simulate each of 6 pwr loops in PSCAD | 0 | 12955.2 | 12955.2 | 4 | 43 | 431 | 4301 | 18 | 18% | 2331.936
431-275 | Power cabling & Installation | 0 | 27741.6 | 27741.6 | 4 | 43 | 431 | 4301 | 18 | 18% | 4993.488
431-260 | Power loop design | 0 | 36274.56 | 36274.56 | 4 | 43 | 431 | 4301 | 18 | 18% | 6529.4208
431-260 | Power loop design | 0 | 37674 | 37674 | 4 | 43 | 431 | 4301 | 18 | 18% | 6781.32
431-260 | Power loop design | 0 | 37674 | 37674 | 4 | 43 | 431 | 4301 | 18 | 18% | 6781.32
431-275 | Power cabling & Installation | 0 | 41584.4 | 41584.4 | 4 | 43 | 431 | 4301 | 18 | 18% | 7485.192
431-275 | Power cabling & Installation | 0 | 116100 | 116100 | 4 | 43 | 431 | 4301 | 18 | 18% | 20898
441-130 | Pre-commissioning tests | 0 | 1297.03 | 1297.03 | 4 | 44 | 441 | 4401 | 18 | 18% | 233.4654
442-1-8 | Kirk Keys-Commission | 0 | 1679.4 | 1679.4 | 4 | 44 | 442 | 4401 | 18 | 18% | 302.292
442-1-6 | Kirk Keys-Install | 0 | 1941.92 | 1941.92 | 4 | 44 | 442 | 4401 | 18 | 18% | 349.5456
442-1-8 | Kirk Keys-Commission | 0 | 2427.4 | 2427.4 | 4 | 44 | 442 | 4401 | 18 | 18% | 436.932
441-125 | Program Control pages | 0 | 2464.09 | 2464.09 | 4 | 44 | 441 | 4401 | 18 | 18% | 443.5362
442-1-6 | Kirk Keys-Install | 0 | 2774.4 | 2774.4 | 4 | 44 | 442 | 4401 | 18 | 18% | 499.392
442-1-8 | Kirk Keys-Commission | 0 | 2774.4 | 2774.4 | 4 | 44 | 442 | 4401 | 18 | 18% | 499.392
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 2774.4 | 2774.4 | 4 | 44 | 444 | 4401 | 18 | 18% | 499.392
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 2912.88 | 2912.88 | 4 | 44 | 444 | 4401 | 18 | 18% | 524.3184
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 2912.88 | 2912.88 | 4 | 44 | 444 | 4401 | 18 | 18% | 524.3184
444-3-8 | DC Shunts-Commission | 0 | 2912.88 | 2912.88 | 4 | 44 | 444 | 4401 | 18 | 18% | 524.3184
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 3358.8 | 3358.8 | 4 | 44 | 444 | 4401 | 18 | 18% | 604.584
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 0 | 3963.36 | 3963.36 | 4 | 44 | 444 | 4401 | 18 | 18% | 713.4048
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 4161.6 | 4161.6 | 4 | 44 | 444 | 4401 | 18 | 18% | 749.088
444-3-8 | DC Shunts-Commission | 0 | 4161.6 | 4161.6 | 4 | 44 | 444 | 4401 | 18 | 18% | 749.088
444-4-6 | Signal Conditioning & Cabling-Install | 0 | 4161.6 | 4161.6 | 4 | 44 | 444 | 4401 | 18 | 18% | 749.088
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 4854.8 | 4854.8 | 4 | 44 | 444 | 4401 | 18 | 18% | 873.864
442-1-6 | Kirk Keys-Install | 0 | 5038.2 | 5038.2 | 4 | 44 | 442 | 4401 | 18 | 18% | 906.876
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 5038.2 | 5038.2 | 4 | 44 | 444 | 4401 | 18 | 18% | 906.876
441-125 | Program Control pages | 0 | 5333.53 | 5333.53 | 4 | 44 | 441 | 4401 | 18 | 18% | 960.0354
444-3-6 | DC Shunts-Install | 0 | 5548.8 | 5548.8 | 4 | 44 | 444 | 4401 | 18 | 18% | 998.784
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 0 | 6403.2 | 6403.2 | 4 | 44 | 444 | 4401 | 18 | 18% | 1152.576
441-100 | PLC Specification | 0 | 6473.04 | 6473.04 | 4 | 44 | 441 | 4401 | 18 | 18% | 1165.1472
441-100 | PLC Specification | 0 | 6605.6 | 6605.6 | 4 | 44 | 441 | 4401 | 18 | 18% | 1189.008
441-105 | Prep Block diagrams | 0 | 6605.6 | 6605.6 | 4 | 44 | 441 | 4401 | 18 | 18% | 1189.008
441-110 | PLC CWD's & Cabling | 0 | 6605.6 | 6605.6 | 4 | 44 | 441 | 4401 | 18 | 18% | 1189.008
441-120 | Program PLC Logic | 0 | 6605.6 | 6605.6 | 4 | 44 | 441 | 4401 | 18 | 18% | 1189.008
442-1-2 | Kirk Keys-Dsn | 0 | 6605.6 | 6605.6 | 4 | 44 | 442 | 4401 | 18 | 18% | 1189.008
444-3-2 | DC Shunts-Dsn | 0 | 6605.6 | 6605.6 | 4 | 44 | 444 | 4401 | 18 | 18% | 1189.008
441-130 | Pre-commissioning tests | 0 | 6671.99 | 6671.99 | 4 | 44 | 441 | 4401 | 18 | 18% | 1200.9582
444-2-4 | DC Potential Transducers (DCPTs)-Procure | 0 | 7740 | 7740 | 4 | 44 | 444 | 4401 | 18 | 18% | 1393.2
444-3-6 | DC Shunts-Install | 0 | 7767.68 | 7767.68 | 4 | 44 | 444 | 4401 | 18 | 18% | 1398.1824
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 8323.2 | 8323.2 | 4 | 44 | 444 | 4401 | 18 | 18% | 1498.176
442-1-2 | Kirk Keys-Dsn | 0 | 8537.6 | 8537.6 | 4 | 44 | 442 | 4401 | 18 | 18% | 1536.768
444-3-2 | DC Shunts-Dsn | 0 | 8537.6 | 8537.6 | 4 | 44 | 444 | 4401 | 18 | 18% | 1536.768
444-4-2 | Signal Conditioning & Cabling-Dsn | 0 | 8537.6 | 8537.6 | 4 | 44 | 444 | 4401 | 18 | 18% | 1536.768
441-105 | Prep Block diagrams | 0 | 9247.2 | 9247.2 | 4 | 44 | 441 | 4401 | 18 | 18% | 1664.496
441-135 | Install I/O Cabling | 0 | 9396.36 | 9396.36 | 4 | 44 | 441 | 4401 | 18 | 18% | 1691.3448
444-3-8 | DC Shunts-Commission | 0 | 10076.4 | 10076.4 | 4 | 44 | 444 | 4401 | 18 | 18% | 1813.752
441-135 | Install I/O Cabling | 0 | 10410.32 | 10410.32 | 4 | 44 | 441 | 4401 | 18 | 18% | 1873.8576
442-1-4 | Kirk Keys-Procure | 0 | 12900 | 12900 | 4 | 44 | 442 | 4401 | 18 | 18% | 2322
441-135 | Install I/O Cabling | 0 | 13001.65 | 13001.65 | 4 | 44 | 441 | 4401 | 18 | 18% | 2340.297
441-095 | Design Interlock sys | 0 | 13211.2 | 13211.2 | 4 | 44 | 441 | 4401 | 18 | 18% | 2378.016
441-097 | Install Interlock sys | 0 | 13211.2 | 13211.2 | 4 | 44 | 441 | 4401 | 18 | 18% | 2378.016
443-1-2 | Develop Control Algorithms-Dsn | 0 | 13346.15 | 13346.15 | 4 | 44 | 443 | 4401 | 18 | 18% | 2402.307
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 13435.2 | 13435.2 | 4 | 44 | 444 | 4401 | 18 | 18% | 2418.336
444-3-6 | DC Shunts-Install | 0 | 13435.2 | 13435.2 | 4 | 44 | 444 | 4401 | 18 | 18% | 2418.336
441-097 | Install Interlock sys | 0 | 13870.8 | 13870.8 | 4 | 44 | 441 | 4401 | 18 | 18% | 2496.744
441-110 | PLC CWD's & Cabling | 0 | 13870.8 | 13870.8 | 4 | 44 | 441 | 4401 | 18 | 18% | 2496.744
441-120 | Program PLC Logic | 0 | 13870.8 | 13870.8 | 4 | 44 | 441 | 4401 | 18 | 18% | 2496.744
441-125 | Program Control pages | 0 | 13999.51 | 13999.51 | 4 | 44 | 441 | 4401 | 18 | 18% | 2519.9118
441-130 | Pre-commissioning tests | 0 | 14010.17 | 14010.17 | 4 | 44 | 441 | 4401 | 18 | 18% | 2521.8306
444-4-4 | Signal Conditioning & Cabling-Procure | 0 | 15480 | 15480 | 4 | 44 | 444 | 4401 | 18 | 18% | 2786.4
441-095 | Design Interlock sys | 0 | 17075.2 | 17075.2 | 4 | 44 | 441 | 4401 | 18 | 18% | 3073.536
441-135 | Install I/O Cabling | 0 | 17350.81 | 17350.81 | 4 | 44 | 441 | 4401 | 18 | 18% | 3123.1458
441-135 | Install I/O Cabling | 0 | 20136.54 | 20136.54 | 4 | 44 | 441 | 4401 | 18 | 18% | 3624.5772
444-4-6 | Signal Conditioning & Cabling-Install | 0 | 23511.6 | 23511.6 | 4 | 44 | 444 | 4401 | 18 | 18% | 4232.088
444-3-6 | DC Shunts-Install | 0 | 26500 | 26500 | 4 | 44 | 444 | 4401 | 18 | 18% | 4770
444-4-2 | Signal Conditioning & Cabling-Dsn | 0 | 33028 | 33028 | 4 | 44 | 444 | 4401 | 18 | 18% | 5945.04
442-1-6 | Kirk Keys-Install | 0 | 33125 | 33125 | 4 | 44 | 442 | 4401 | 18 | 18% | 5962.5
441-135 | Install I/O Cabling | 0 | 39038.71 | 39038.71 | 4 | 44 | 441 | 4401 | 18 | 18% | 7026.9678
444-3-4 | DC Shunts-Procure | 0 | 58050 | 58050 | 4 | 44 | 444 | 4401 | 18 | 18% | 10449
441-115 | deliver PLC | 0 | 64500 | 64500 | 4 | 44 | 441 | 4401 | 18 | 18% | 11610
445-1-8 | Ground Fault Protection-Commission | 0 | 2687.04 | 2687.04 | 4 | 44 | 445 | 4401 | 22 | 22% | 591.1488
445-1-8 | Ground Fault Protection-Commission | 0 | 2912.88 | 2912.88 | 4 | 44 | 445 | 4401 | 22 | 22% | 640.8336
445-1-8 | Ground Fault Protection-Commission | 0 | 4161.6 | 4161.6 | 4 | 44 | 445 | 4401 | 22 | 22% | 915.552
445-1-6 | Ground Fault Protection-Install | 0 | 5825.76 | 5825.76 | 4 | 44 | 445 | 4401 | 22 | 22% | 1281.6672
445-2-135 | Overload Protect-Documentation | 0 | 6605.6 | 6605.6 | 4 | 44 | 445 | 4401 | 22 | 22% | 1453.232
445-1-6 | Ground Fault Protection-Install | 0 | 6936 | 6936 | 4 | 44 | 445 | 4401 | 22 | 22% | 1525.92
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 7859.76 | 7859.76 | 4 | 44 | 445 | 4401 | 22 | 22% | 1729.1472
445-2-110 | Overload Protect-Design | 0 | 8537.6 | 8537.6 | 4 | 44 | 445 | 4401 | 22 | 22% | 1878.272
445-2-110 | Overload Protect-Design | 0 | 9247.2 | 9247.2 | 4 | 44 | 445 | 4401 | 22 | 22% | 2034.384
445-2-120 | Overload Protect-Test 4 units | 0 | 9247.2 | 9247.2 | 4 | 44 | 445 | 4401 | 22 | 22% | 2034.384
445-2-130 | Overload Protect-Write & perform ISTP | 0 | 9247.2 | 9247.2 | 4 | 44 | 445 | 4401 | 22 | 22% | 2034.384
445-1-6 | Ground Fault Protection-Install | 0 | 10076.4 | 10076.4 | 4 | 44 | 445 | 4401 | 22 | 22% | 2216.808
445-1-2 | Ground Fault Protection-Dsn | 0 | 12806.4 | 12806.4 | 4 | 44 | 445 | 4401 | 22 | 22% | 2817.408
445-2-105 | Overload Protect-Write spec and approve | 0 | 13211.2 | 13211.2 | 4 | 44 | 445 | 4401 | 22 | 22% | 2906.464
445-2-120 | Overload Protect-Test 4 units | 0 | 13211.2 | 13211.2 | 4 | 44 | 445 | 4401 | 22 | 22% | 2906.464
445-2-130 | Overload Protect-Write & perform ISTP | 0 | 13211.2 | 13211.2 | 4 | 44 | 445 | 4401 | 22 | 22% | 2906.464
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 13315.26 | 13315.26 | 4 | 44 | 445 | 4401 | 22 | 22% | 2929.3572
445-2-135 | Overload Protect-Documentation | 0 | 17075.2 | 17075.2 | 4 | 44 | 445 | 4401 | 22 | 22% | 3756.544
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 19740.27 | 19740.27 | 4 | 44 | 445 | 4401 | 22 | 22% | 4342.8594
445-1-2 | Ground Fault Protection-Dsn | 0 | 19816.8 | 19816.8 | 4 | 44 | 445 | 4401 | 22 | 22% | 4359.696
445-2-115 | Overload Protect-Fabr 4 chassis 120 modls | 0 | 19816.8 | 19816.8 | 4 | 44 | 445 | 4401 | 22 | 22% | 4359.696
445-2-125 | Overload Protect-Install & Rack wiring | 0 | 19816.8 | 19816.8 | 4 | 44 | 445 | 4401 | 22 | 22% | 4359.696
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 21953.06 | 21953.06 | 4 | 44 | 445 | 4401 | 22 | 22% | 4829.6732
445-2-125 | Overload Protect-Install & Rack wiring | 0 | 22193.28 | 22193.28 | 4 | 44 | 445 | 4401 | 22 | 22% | 4882.5216
445-1-4 | Ground Fault Protection-Procure | 0 | 23220 | 23220 | 4 | 44 | 445 | 4401 | 22 | 22% | 5108.4
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 32749 | 32749 | 4 | 44 | 445 | 4401 | 22 | 22% | 7204.78
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 42122.93 | 42122.93 | 4 | 44 | 445 | 4401 | 22 | 22% | 9267.0446
445-2-115 | Overload Protect-Fabr 4 chassis 120 modls | 0 | 44386.56 | 44386.56 | 4 | 44 | 445 | 4401 | 22 | 22% | 9765.0432
445-2-110 | Overload Protect-Design | 0 | 52844.8 | 52844.8 | 4 | 44 | 445 | 4401 | 22 | 22% | 11625.856
451-1-2 | Calculations-Dsn | 0 | 859.88 | 859.88 | 4 | 45 | 451 | 4501 | 18 | 18% | 154.7784
451-4-2 | FDR AC auxiliaries & grounding-Dsn | 0 | 4268.8 | 4268.8 | 4 | 45 | 451 | 4501 | 18 | 18% | 768.384
451-4-2 | FDR AC auxiliaries & grounding-Dsn | 0 | 6605.6 | 6605.6 | 4 | 45 | 451 | 4501 | 18 | 18% | 1189.008
451-2-2.1 | FDR C-Site | 0 | 12558 | 12558 | 4 | 45 | 451 | 4501 | 18 | 18% | 2260.44
451-6-2 | FDR C-Site -Cabling | 0 | 12558 | 12558 | 4 | 45 | 451 | 4501 | 18 | 18% | 2260.44
453-1-8 | Testing PTPs, ISTPs | 0 | 13250 | 13250 | 4 | 45 | 453 | 4501 | 18 | 18% | 2385
451-2-1 | CDR Power system -Dsn | 0 | 16744 | 16744 | 4 | 45 | 451 | 4501 | 18 | 18% | 3013.92
451-2-2 | PDR Power system -Dsn | 0 | 16744 | 16744 | 4 | 45 | 451 | 4501 | 18 | 18% | 3013.92
451-2-2.1 | FDR C-Site | 0 | 19432.8 | 19432.8 | 4 | 45 | 451 | 4501 | 18 | 18% | 3497.904
451-6-2 | FDR C-Site -Cabling | 0 | 19432.8 | 19432.8 | 4 | 45 | 451 | 4501 | 18 | 18% | 3497.904
453-1-2 | New Procedures | 0 | 25612.8 | 25612.8 | 4 | 45 | 453 | 4501 | 18 | 18% | 4610.304
451-2-1 | CDR Power system -Dsn | 0 | 25910.4 | 25910.4 | 4 | 45 | 451 | 4501 | 18 | 18% | 4663.872
451-2-2 | PDR Power system -Dsn | 0 | 25910.4 | 25910.4 | 4 | 45 | 451 | 4501 | 18 | 18% | 4663.872
453-1-8 | Testing PTPs, ISTPs | 0 | 29128.8 | 29128.8 | 4 | 45 | 453 | 4501 | 18 | 18% | 5243.184
453-1-8 | Testing PTPs, ISTPs | 0 | 31572.72 | 31572.72 | 4 | 45 | 453 | 4501 | 18 | 18% | 5683.0896
453-1-4 | Preop Testing-Procure test equipt | 0 | 33125 | 33125 | 4 | 45 | 453 | 4501 | 18 | 18% | 5962.5
453-1-2 | New Procedures | 0 | 39633.6 | 39633.6 | 4 | 45 | 453 | 4501 | 18 | 18% | 7134.048
451-3-2 | Dwgs,asbuilts -Elect Dsn | 0 | 41459.9 | 41459.9 | 4 | 45 | 451 | 4501 | 18 | 18% | 7462.782
451-1-2 | Calculations-Dsn | 0 | 53223.83 | 53223.83 | 4 | 45 | 451 | 4501 | 18 | 18% | 9580.2894
451-3-2 | Dwgs,asbuilts -Elect Dsn | 0 | 116105.66 | 116105.66 | 4 | 45 | 451 | 4501 | 18 | 18% | 20899.0188
453-1-8 | Testing PTPs, ISTPs | 0 | 133171.2 | 133171.2 | 4 | 45 | 453 | 4501 | 18 | 18% | 23970.816
452-1-4 | Diagnostics AC Power Distr-Procure | 0 | 1290.14 | 1290.14 | 4 | 45 | 452 | 4501 | 26 | 26% | 335.4364
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 1387.2 | 1387.2 | 4 | 45 | 452 | 4501 | 26 | 26% | 360.672
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 1941.92 | 1941.92 | 4 | 45 | 452 | 4501 | 26 | 26% | 504.8992
452-2-4 | Diagnostics sensor cabling-Procure | 0 | 2580 | 2580 | 4 | 45 | 452 | 4501 | 26 | 26% | 670.8
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 2687.04 | 2687.04 | 4 | 45 | 452 | 4501 | 26 | 26% | 698.6304
452-2-6 | Diagnostics sensor cabling-Install | 0 | 3883.84 | 3883.84 | 4 | 45 | 452 | 4501 | 26 | 26% | 1009.7984
452-2-6 | Diagnostics sensor cabling-Install | 0 | 4161.6 | 4161.6 | 4 | 45 | 452 | 4501 | 26 | 26% | 1082.016
452-2-2 | Diagnostics sensor cabling-Dsn | 0 | 6605.6 | 6605.6 | 4 | 45 | 452 | 4501 | 26 | 26% | 1717.456
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 6936 | 6936 | 4 | 45 | 452 | 4501 | 26 | 26% | 1803.36
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 9709.6 | 9709.6 | 4 | 45 | 452 | 4501 | 26 | 26% | 2524.496
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 9709.6 | 9709.6 | 4 | 45 | 452 | 4501 | 26 | 26% | 2524.496
452-1-2 | Diagnostics AC Power Distr-Dsn | 0 | 13211.2 | 13211.2 | 4 | 45 | 452 | 4501 | 26 | 26% | 3434.912
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 13435.2 | 13435.2 | 4 | 45 | 452 | 4501 | 26 | 26% | 3493.152
452-2-6 | Diagnostics sensor cabling-Install | 0 | 13435.2 | 13435.2 | 4 | 45 | 452 | 4501 | 26 | 26% | 3493.152
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 13872 | 13872 | 4 | 45 | 452 | 4501 | 26 | 26% | 3606.72
452-2-2 | Diagnostics sensor cabling-Dsn | 0 | 17075.2 | 17075.2 | 4 | 45 | 452 | 4501 | 26 | 26% | 4439.552
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 53740.8 | 53740.8 | 4 | 45 | 452 | 4501 | 26 | 26% | 13972.608
452-1-2 | Diagnostics AC Power Distr-Dsn | 0 | 68300.8 | 68300.8 | 4 | 45 | 452 | 4501 | 26 | 26% | 17758.208
51-10 | Preliminary Design (Title I) | 0 | 6212.12 | 6212.12 | 5 | 51 |  |  | 5 | 5% | 310.606
51-20 | Final Network Design (Title II) | 0 | 6408.8 | 6408.8 | 5 | 51 |  |  | 5 | 5% | 320.44
51-30 | Installation, Testing, Documentation (Title III) | 0 | 17929.6 | 17929.6 | 5 | 51 |  |  | 5 | 5% | 896.48
51-30 | Installation, Testing, Documentation (Title III) | 0 | 35248.4 | 35248.4 | 5 | 51 |  |  | 5 | 5% | 1762.42
51-30 | Installation, Testing, Documentation (Title III) | 0 | 89813.8 | 89813.8 | 5 | 51 |  |  | 5 | 5% | 4490.69
51-30 | Installation, Testing, Documentation (Title III) | 0 | 109047.5 | 109047.5 | 5 | 51 |  |  | 5 | 5% | 5452.375
52-10 | Preliminary Design (Title I) | 0 | 24414.4 | 24414.4 | 5 | 52 |  |  | 10 | 10% | 2441.44
52-30 | Installation, Testing, Documentation (Title III) | 0 | 58572.28 | 58572.28 | 5 | 52 |  |  | 10 | 10% | 5857.228
52-20 | Final Design (Title II) | 0 | 62485.8 | 62485.8 | 5 | 52 |  |  | 10 | 10% | 6248.58
52-30 | Installation, Testing, Documentation (Title III) | 0 | 72969.42 | 72969.42 | 5 | 52 |  |  | 10 | 10% | 7296.942
52-30 | Installation, Testing, Documentation (Title III) | 0 | 143285.41 | 143285.41 | 5 | 52 |  |  | 10 | 10% | 14328.541
52-30 | Installation, Testing, Documentation (Title III) | 0 | 209057.62 | 209057.62 | 5 | 52 |  |  | 10 | 10% | 20905.762
53-10 | Preliminary Design (Title I) | 0 | 25997.95 | 25997.95 | 5 | 53 |  |  | 16 | 16% | 4159.672
53-20 | Final Design (Title II) | 0 | 52872.6 | 52872.6 | 5 | 53 |  |  | 16 | 16% | 8459.616
53-30 | Coding, Configuration, Testing (Title III) | 0 | 76452.5 | 76452.5 | 5 | 53 |  |  | 16 | 16% | 12232.4
53-30 | Coding, Configuration, Testing (Title III) | 0 | 173037.6 | 173037.6 | 5 | 53 |  |  | 16 | 16% | 27686.016
54-10 | Preliminary Design (Title I) | 0 | 22430.8 | 22430.8 | 5 | 54 |  |  | 14 | 14% | 3140.312
54-20 | Final Design (Title II) | 0 | 25635.2 | 25635.2 | 5 | 54 |  |  | 14 | 14% | 3588.928
54-30 | Installation, Testing, Documentation (Title III) | 0 | 32860 | 32860 | 5 | 54 |  |  | 14 | 14% | 4600.4
54-30 | Installation, Testing, Documentation (Title III) | 0 | 57679.2 | 57679.2 | 5 | 54 |  |  | 14 | 14% | 8075.088
54-30 | Installation, Testing, Documentation (Title III) | 0 | 68187 | 68187 | 5 | 54 |  |  | 14 | 14% | 9546.18
55-10 | Preliminary Design (Title I) | 0 | 12817.6 | 12817.6 | 5 | 55 |  |  | 8 | 8% | 1025.408
55-20 | Final Design (Title II) | 0 | 12817.6 | 12817.6 | 5 | 55 |  |  | 8 | 8% | 1025.408
55-30 | Installation, Testing, Documentation (Title III) | 0 | 48705 | 48705 | 5 | 55 |  |  | 8 | 8% | 3896.4
55-30 | Installation, Testing, Documentation (Title III) | 0 | 76905.6 | 76905.6 | 5 | 55 |  |  | 8 | 8% | 6152.448
56-10 | Preliminary Design (Title I) | 0 | 25635.2 | 25635.2 | 5 | 56 |  |  | 8 | 8% | 2050.816
56-20 | Final Design (Title II) | 0 | 25635.2 | 25635.2 | 5 | 56 |  |  | 8 | 8% | 2050.816
56-30 | Installation, Testing, Documentation (Title III) | 0 | 35775 | 35775 | 5 | 56 |  |  | 8 | 8% | 2862
56-30 | Installation, Testing, Documentation (Title III) | 0 | 124971.6 | 124971.6 | 5 | 56 |  |  | 8 | 8% | 9997.728
56-30 | Installation, Testing, Documentation (Title III) | 0 | 145644 | 145644 | 5 | 56 |  |  | 8 | 8% | 11651.52
51-02 | FY05 LOE support | 1083.6 | 12900 | 11816.4 | 5 | 58 |  | 5801 | 3 | 3% | 354.492
623.011 | Design WBS 612 | 0 | 8964.8 | 8964.8 | 6 | 61 | 613 |  | 20 | 20% | 1792.96
615.011 | Engr recommissioning of C-Site Water systems | 0 | 10401.72 | 10401.72 | 6 | 61 | 611 |  | 20 | 20% | 2080.344
623.011 | Design WBS 612 | 0 | 14347.2 | 14347.2 | 6 | 61 | 613 |  | 20 | 20% | 2869.44
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 14347.2 | 14347.2 | 6 | 61 | 613 |  | 20 | 20% | 2869.44
615.021 | Replace valves, resins, filters | 0 | 18398.88 | 18398.88 | 6 | 61 | 611 |  | 20 | 20% | 3679.776
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 24531.84 | 24531.84 | 6 | 61 | 613 |  | 20 | 20% | 4906.368
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 27162.5 | 27162.5 | 6 | 61 | 613 |  | 20 | 20% | 5432.5
615.021 | Replace valves, resins, filters | 0 | 122297.5 | 122297.5 | 6 | 61 | 611 |  | 20 | 20% | 24459.5
631-010 | Final Design**reduced scope | 0 | 1792.96 | 1792.96 | 6 | 62 | 621 |  | 20 | 20% | 358.592
631-015 | Fab/Assy/Installation**reduced scope | 0 | 2797.2 | 2797.2 | 6 | 62 | 621 |  | 20 | 20% | 559.44
633-010 | Final Design | 0 | 8964.8 | 8964.8 | 6 | 62 | 623 |  | 20 | 20% | 1792.96
631-001 | Preliminary Design | 0 | 15961.26 | 15961.26 | 6 | 62 | 621 |  | 20 | 20% | 3192.252
631-010 | Final Design**reduced scope | 0 | 15961.26 | 15961.26 | 6 | 62 | 621 |  | 20 | 20% | 3192.252
631-015 | Fab/Assy/Installation**reduced scope | 0 | 15961.26 | 15961.26 | 6 | 62 | 621 |  | 20 | 20% | 3192.252
633-001 | Preliminary Design | 0 | 15961.26 | 15961.26 | 6 | 62 | 623 |  | 20 | 20% | 3192.252
633-010 | Final Design | 0 | 15961.26 | 15961.26 | 6 | 62 | 623 |  | 20 | 20% | 3192.252
633-015 | Fab/Assy/Installation | 0 | 15961.26 | 15961.26 | 6 | 62 | 623 |  | 20 | 20% | 3192.252
631-015 | Fab/Assy/Installation**reduced scope | 0 | 17461.9 | 17461.9 | 6 | 62 | 621 |  | 20 | 20% | 3492.38
631-015 | Fab/Assy/Installation**reduced scope | 0 | 34923.8 | 34923.8 | 6 | 62 | 621 |  | 20 | 20% | 6984.76
631-020 | Procurement **reduced scope | 0 | 48495 | 48495 | 6 | 62 | 621 |  | 20 | 20% | 9699
633-015 | Fab/Assy/Installation | 0 | 55878.08 | 55878.08 | 6 | 62 | 623 |  | 20 | 20% | 11175.616
631-020 | Procurement **reduced scope | 0 | 67575 | 67575 | 6 | 62 | 621 |  | 20 | 20% | 13515
633-020 | Procurement | 0 | 105933.75 | 105933.75 | 6 | 62 | 623 |  | 20 | 20% | 21186.75
640.021 | Assembly/Fabrication | 0 | 8608.32 | 8608.32 | 6 | 63 |  |  | 20 | 20% | 1721.664
640.011 | Design GN2, Air & Vent Systems | 0 | 14347.2 | 14347.2 | 6 | 63 |  |  | 20 | 20% | 2869.44
640.011 | Design GN2, Air & Vent Systems | 0 | 17929.6 | 17929.6 | 6 | 63 |  |  | 20 | 20% | 3585.92
640.021 | Assembly/Fabrication | 0 | 23585 | 23585 | 6 | 63 |  |  | 20 | 20% | 4717
640.021 | Assembly/Fabrication | 0 | 39012.44 | 39012.44 | 6 | 63 |  |  | 20 | 20% | 7802.488
711B.050 | Complete Control Room Flooring | 0 | 2720.16 | 2720.16 | 7 | 72 | 720 | 7201 | 10 | 10% | 272.016
711B.050 | Complete Control Room Flooring | 0 | 2863.8 | 2863.8 | 7 | 72 | 720 | 7201 | 10 | 10% | 286.38
711B.050 | Complete Control Room Flooring | 0 | 2863.8 | 2863.8 | 7 | 72 | 720 | 7201 | 10 | 10% | 286.38
710.001 | Block Wall east side control room | 0 | 16668 | 16668 | 7 | 72 | 720 | 7201 | 10 | 10% | 1666.8
710.001 | Block Wall east side control room | 0 | 25094.4 | 25094.4 | 7 | 72 | 720 | 7201 | 10 | 10% | 2509.44
712.020 | Fab & Assemble Platform | 0 | 1708 | 1708 | 7 | 73 | 730 | 7401 | 10 | 10% | 170.8
712.020 | Fab & Assemble Platform | 0 | 2553 | 2553 | 7 | 73 | 730 | 7401 | 10 | 10% | 255.3
712.020 | Fab & Assemble Platform | 0 | 20280 | 20280 | 7 | 73 | 730 | 7401 | 10 | 10% | 2028
712.030 | Miscs Hardware/Material | 0 | 45150 | 45150 | 7 | 73 | 730 | 7401 | 10 | 10% | 4515
712.008 | Update Platform Specification | 0 | 6699.6 | 6699.6 | 7 | 73 | 730 | 7301 | 24 | 24% | 1607.904
711A.040 | Platform nut plates | 0 | 1389 | 1389 | 7 | 73 | 730 | 7301 | 6 | 6% | 83.34
712.010 | Final Design | 0 | 23448.6 | 23448.6 | 7 | 73 | 730 | 7301 | 6 | 6% | 1406.916
711A.040 | Platform nut plates | 0 | 28638 | 28638 | 7 | 73 | 730 | 7301 | 6 | 6% | 1718.28
712.010 | Final Design | 0 | 31395 | 31395 | 7 | 73 | 730 | 7301 | 6 | 6% | 1883.7
714.010 | LOE FY05 | 1609.0906 | 19155.84 | 17546.7494 | 7 | 74 | 742 | 7401 | 15 | 15% | 2632.0124
714.010 | LOE FY05 | 1675.6186 | 19947.84 | 18272.2214 | 7 | 74 | 742 | 7401 | 15 | 15% | 2740.8332
714.020 | LOE FY06 prior to assy starting | 0 | 19536 | 19536 | 7 | 74 | 742 | 7401 | 15 | 15% | 2930.4
714.020 | LOE FY06 prior to assy starting | 0 | 20343.84 | 20343.84 | 7 | 74 | 742 | 7401 | 15 | 15% | 3051.576
714.010 | LOE FY05 | 6317.0528 | 75203.01 | 68885.9572 | 7 | 74 | 742 | 7401 | 15 | 15% | 10332.8936
714.020 | LOE FY06 prior to assy starting | 0 | 76689.2 | 76689.2 | 7 | 74 | 742 | 7401 | 15 | 15% | 11503.38
714.031 | WBS 7 mgt stretch out cost | 0 | 112797.36 | 112797.36 | 7 | 74 | 742 | 7401 | 15 | 15% | 16919.604
714.031 | WBS 7 mgt stretch out cost | 0 | 173571.84 | 173571.84 | 7 | 74 | 742 | 7401 | 15 | 15% | 26035.776
714.030 | LOE FY07 thru first plasma | 0 | 217003.59 | 217003.59 | 7 | 74 | 742 | 7401 | 15 | 15% | 32550.5385
714.030 | LOE FY07 thru first plasma | 0 | 333913.9 | 333913.9 | 7 | 74 | 742 | 7401 | 15 | 15% | 50087.085
613.030 | Test Cell copper ground plane cuts | 0 | 1389 | 1389 | 7 | 74 | 740 | 7401 | 24 | 24% | 333.36
613.030 | Test Cell copper ground plane cuts | 0 | 4773 | 4773 | 7 | 74 | 740 | 7401 | 24 | 24% | 1145.52
613.030 | Test Cell copper ground plane cuts | 0 | 4773 | 4773 | 7 | 74 | 740 | 7401 | 24 | 24% | 1145.52
7502-002 | Test Cell 208v outlets | 0 | 8707.2 | 8707.2 | 7 | 74 | 740 | 7401 | 24 | 24% | 2089.728
7502-010 | Ready Rooms (under control room) 110v outlets | 0 | 8707.2 | 8707.2 | 7 | 74 | 740 | 7401 | 24 | 24% | 2089.728
7502-001 | Test Cell 110v outlets | 0 | 17414.4 | 17414.4 | 7 | 74 | 740 | 7401 | 24 | 24% | 4179.456
713.010 | General procurements | 0 | 20835 | 20835 | 7 | 74 | 740 | 7401 | 24 | 24% | 5000.4
7503-170 | FPA Metrology Checks to Assure Alignment | 0 | 1022.16 | 1022.16 | 7 | 75 | 750 | 7503 | 24 | 24% | 245.3184
7503-060 | Install Lower PF 4,5&6 into prelim position | 0 | 1864.8 | 1864.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 447.552
7503-170 | FPA Metrology Checks to Assure Alignment | 0 | 2157.36 | 2157.36 | 7 | 75 | 750 | 7503 | 24 | 24% | 517.7664
7503-060 | Install Lower PF 4,5&6 into prelim position | 0 | 2725.76 | 2725.76 | 7 | 75 | 750 | 7503 | 24 | 24% | 654.1824
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 2876.48 | 2876.48 | 7 | 75 | 750 | 7503 | 24 | 24% | 690.3552
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 3595.6 | 3595.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 862.944
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 3729.6 | 3729.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 895.104
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 4314.72 | 4314.72 | 7 | 75 | 750 | 7503 | 24 | 24% | 1035.5328
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 4314.72 | 4314.72 | 7 | 75 | 750 | 7503 | 24 | 24% | 1035.5328
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 4314.72 | 4314.72 | 7 | 75 | 750 | 7503 | 24 | 24% | 1035.5328
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 4662 | 4662 | 7 | 75 | 750 | 7503 | 24 | 24% | 1118.88
7503-240 | Bolt on preassembled pump duct | 0 | 4662 | 4662 | 7 | 75 | 750 | 7503 | 24 | 24% | 1118.88
7503-370 | Install Cryostat Circulation Duct | 0 | 4820.4 | 4820.4 | 7 | 75 | 750 | 7503 | 24 | 24% | 1156.896
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 5594.4 | 5594.4 | 7 | 75 | 750 | 7503 | 24 | 24% | 1342.656
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 5594.4 | 5594.4 | 7 | 75 | 750 | 7503 | 24 | 24% | 1342.656
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 5594.4 | 5594.4 | 7 | 75 | 750 | 7503 | 24 | 24% | 1342.656
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 7191.2 | 7191.2 | 7 | 75 | 750 | 7503 | 24 | 24% | 1725.888
7503-090 | Install local Platforms around FPA-1 | 0 | 7191.2 | 7191.2 | 7 | 75 | 750 | 7503 | 24 | 24% | 1725.888
7503-130 | Install local Platforms around FPA-2 | 0 | 7191.2 | 7191.2 | 7 | 75 | 750 | 7503 | 24 | 24% | 1725.888
7503-190 | Install local Platforms around FPA-3 | 0 | 7191.2 | 7191.2 | 7 | 75 | 750 | 7503 | 24 | 24% | 1725.888
7503-210 | Fit-up all TF coils | 0 | 7191.2 | 7191.2 | 7 | 75 | 750 | 7503 | 24 | 24% | 1725.888
7502-035 | Control room firesealing | 0 | 8880 | 8880 | 7 | 75 | 750 | 7502 | 24 | 24% | 2131.2
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-090 | Install local Platforms around FPA-1 | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-130 | Install local Platforms around FPA-2 | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-190 | Install local Platforms around FPA-3 | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-210 | Fit-up all TF coils | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-260 | PTP Pumpdown & leak check VV | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-310 | Complete LN2 connections **2 SHIFT** | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-340 | Install Cryostat Base, vapor barrie& port boots | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-350 | Install Cryostat upper section,VB and port boots | 0 | 9324 | 9324 | 7 | 75 | 750 | 7503 | 24 | 24% | 2237.76
7503-020 | Install & Level Support Base Plates | 0 | 10786.8 | 10786.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 2588.832
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 10786.8 | 10786.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 2588.832
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 10903.04 | 10903.04 | 7 | 75 | 750 | 7503 | 24 | 24% | 2616.7296
7502-020 | Resurface TC floor | 0 | 12900 | 12900 | 7 | 75 | 750 | 7502 | 24 | 24% | 3096
7502-030 | TC Floor firesealing | 0 | 13320 | 13320 | 7 | 75 | 750 | 7502 | 24 | 24% | 3196.8
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 13628.8 | 13628.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 3270.912
7503-240 | Bolt on preassembled pump duct | 0 | 13628.8 | 13628.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 3270.912
7503-020 | Install & Level Support Base Plates | 0 | 13986 | 13986 | 7 | 75 | 750 | 7503 | 24 | 24% | 3356.64
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 13986 | 13986 | 7 | 75 | 750 | 7503 | 24 | 24% | 3356.64
7503-200 | Mate-up and weld all VV-to-Spool interfaces | 0 | 13986 | 13986 | 7 | 75 | 750 | 7503 | 24 | 24% | 3356.64
7503-370 | Install Cryostat Circulation Duct | 0 | 14091.2 | 14091.2 | 7 | 75 | 750 | 7503 | 24 | 24% | 3381.888
7503-360 | Install Midplane Cryostat sections and port boot | 0 | 14302.8 | 14302.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 3432.672
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 16354.56 | 16354.56 | 7 | 75 | 750 | 7503 | 24 | 24% | 3925.0944
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 16354.56 | 16354.56 | 7 | 75 | 750 | 7503 | 24 | 24% | 3925.0944
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 16354.56 | 16354.56 | 7 | 75 | 750 | 7503 | 24 | 24% | 3925.0944
7502-020 | Resurface TC floor | 0 | 17760 | 17760 | 7 | 75 | 750 | 7502 | 24 | 24% | 4262.4
7503-320 | Complete Elect Pwr connections **2 SHIFT** | 0 | 18648 | 18648 | 7 | 75 | 750 | 7503 | 24 | 24% | 4475.52
7503-321 | Complete mag diag & machine I&C **2 SHIFT** | 0 | 18648 | 18648 | 7 | 75 | 750 | 7503 | 24 | 24% | 4475.52
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 21573.6 | 21573.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 5177.664
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-090 | Install local Platforms around FPA-1 | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-130 | Install local Platforms around FPA-2 | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-190 | Install local Platforms around FPA-3 | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-310 | Complete LN2 connections **2 SHIFT** | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-321 | Complete mag diag & machine I&C **2 SHIFT** | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-340 | Install Cryostat Base, vapor barrie& port boots | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-350 | Install Cryostat upper section,VB and port boots | 0 | 27257.6 | 27257.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 6541.824
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 27972 | 27972 | 7 | 75 | 750 | 7503 | 24 | 24% | 6713.28
7501-07 | Construction Support Crew during cryostat instl | 0 | 32774.19 | 32774.19 | 7 | 75 | 750 | 7501 | 24 | 24% | 7865.8056
7503-020 | Install & Level Support Base Plates | 0 | 40886.4 | 40886.4 | 7 | 75 | 750 | 7503 | 24 | 24% | 9812.736
7503-210 | Fit-up all TF coils | 0 | 40886.4 | 40886.4 | 7 | 75 | 750 | 7503 | 24 | 24% | 9812.736
7503-260 | PTP Pumpdown & leak check VV | 0 | 40886.4 | 40886.4 | 7 | 75 | 750 | 7503 | 24 | 24% | 9812.736
7503-360 | Install Midplane Cryostat sections and port boot | 0 | 41811.2 | 41811.2 | 7 | 75 | 750 | 7503 | 24 | 24% | 10034.688
7501-07 | Construction Support Crew during cryostat instl | 0 | 59898.2 | 59898.2 | 7 | 75 | 750 | 7501 | 24 | 24% | 14375.568
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 61329.6 | 61329.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 14719.104
7503-200 | Mate-up and weld all VV-to-Spool interfaces | 0 | 61329.6 | 61329.6 | 7 | 75 | 750 | 7503 | 24 | 24% | 14719.104
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 81772.8 | 81772.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 19625.472
7503-320 | Complete Elect Pwr connections **2 SHIFT** | 0 | 81772.8 | 81772.8 | 7 | 75 | 750 | 7503 | 24 | 24% | 19625.472
7501-06 | Construction Support Crew during e-beam mapping | 0 | 95732.09 | 95732.09 | 7 | 75 | 750 | 7501 | 24 | 24% | 22975.7016
7501-05 | Construction Support Crew during machine assy | 0 | 287951.5 | 287951.5 | 7 | 75 | 750 | 7501 | 24 | 24% | 69108.36
7501-05 | Construction Support Crew during machine assy | 0 | 526270.64 | 526270.64 | 7 | 75 | 750 | 7501 | 24 | 24% | 126304.9536
730.8200 | PTP and Cooldown | 0 | 9640.8 | 9640.8 | 7 | 75 | 750 | 7503 | 30 | 30% | 2892.24
730.8200 | PTP and Cooldown | 0 | 14835.2 | 14835.2 | 7 | 75 | 750 | 7503 | 30 | 30% | 4450.56
730.8200 | PTP and Cooldown | 0 | 42273.6 | 42273.6 | 7 | 75 | 750 | 7503 | 30 | 30% | 12682.08
713.020 | Lab Fab/Assy/Installation | 0 | 4882.18 | 4882.18 | 7 | 76 |  | 7601 | 24 | 24% | 1171.7232
713.020 | Lab Fab/Assy/Installation | 0 | 11893.53 | 11893.53 | 7 | 76 |  | 7601 | 24 | 24% | 2854.4472
713.020 | Lab Fab/Assy/Installation | 0 | 14309.4 | 14309.4 | 7 | 76 |  | 7601 | 24 | 24% | 3434.256
713.050 | Welding tools, materials & equipt | 0 | 52953 | 52953 | 7 | 76 |  | 7601 | 24 | 24% | 12708.72
713.040 | General procurements | 0 | 59572.13 | 59572.13 | 7 | 76 |  | 7601 | 24 | 24% | 14297.3112
713.030 | Tooling,assy fixtures,misc equipt | 0 | 79429.5 | 79429.5 | 7 | 76 |  | 7601 | 24 | 24% | 19063.08
810.900 | Project Management Office PPPL FY08 | 0 | 917.5 | 917.5 | 8 | 81 | 810 | 8101 | 17 | 17% | 155.975
810.103 | Project Management Office ORNL FY05 | 174.0384 | 2122.42 | 1948.3816 | 8 | 81 | 810 | 8102 | 17 | 17% | 331.2249
810.104 | Project Management Office ORNL FY06 | 0 | 2164.86 | 2164.86 | 8 | 81 | 810 | 8102 | 17 | 17% | 368.0262
810.104X | Project Management Office ORNL FY06 | 0 | 2208.16 | 2208.16 | 8 | 81 | 810 | 8102 | 17 | 17% | 375.3872
810.004 | Project Management Office PPPL FY06 | 0 | 2580 | 2580 | 8 | 81 | 810 | 8101 | 17 | 17% | 438.6
810.005 | Project Management OfficePPPL FY07 | 0 | 2650 | 2650 | 8 | 81 | 810 | 8101 | 17 | 17% | 450.5
810.103 | Project Management Office ORNL FY05 | 261.0577 | 3183.63 | 2922.5723 | 8 | 81 | 810 | 8102 | 17 | 17% | 496.8373
810.004 | Project Management Office PPPL FY06 | 0 | 6940 | 6940 | 8 | 81 | 810 | 8101 | 17 | 17% | 1179.8
810.005 | Project Management OfficePPPL FY07 | 0 | 7340 | 7340 | 8 | 81 | 810 | 8101 | 17 | 17% | 1247.8
810.003 | Project Management Office PPPL FY05 | 683.388 | 8334 | 7650.612 | 8 | 81 | 810 | 8101 | 17 | 17% | 1300.604
810.900 | Project Management Office PPPL FY08 | 0 | 10497.76 | 10497.76 | 8 | 81 | 810 | 8101 | 17 | 17% | 1784.6192
810.003 | Project Management Office PPPL FY05 | 1140.128 | 13904 | 12763.872 | 8 | 81 | 810 | 8101 | 17 | 17% | 2169.8582
810.104 | Project Management Office ORNL FY06 | 0 | 13979.23 | 13979.23 | 8 | 81 | 810 | 8102 | 17 | 17% | 2376.4691
810.103 | Project Management Office ORNL FY05 | 2193.9248 | 26755.18 | 24561.2552 | 8 | 81 | 810 | 8102 | 17 | 17% | 4175.4134
810.003 | Project Management Office PPPL FY05 | 2381.6875 | 29044.97 | 26663.2825 | 8 | 81 | 810 | 8101 | 17 | 17% | 4532.758
810.003 | Project Management Office PPPL FY05 | 2608.8497 | 31815.24 | 29206.3903 | 8 | 81 | 810 | 8101 | 17 | 17% | 4965.0864
810.104 | Project Management Office ORNL FY06 | 0 | 33179.4 | 33179.4 | 8 | 81 | 810 | 8102 | 17 | 17% | 5640.498
810.104X | Project Management Office ORNL FY06 | 0 | 34009.2 | 34009.2 | 8 | 81 | 810 | 8102 | 17 | 17% | 5781.564
810.005 | Project Management OfficePPPL FY07 | 0 | 41991.04 | 41991.04 | 8 | 81 | 810 | 8101 | 17 | 17% | 7138.4768
810.900 | Project Management Office PPPL FY08 | 0 | 44343.81 | 44343.81 | 8 | 81 | 810 | 8101 | 17 | 17% | 7538.4477
810.003 | Project Management Office PPPL FY05 | 4025.216 | 49088 | 45062.784 | 8 | 81 | 810 | 8101 | 17 | 17% | 7660.6733
810.004 | Project Management Office PPPL FY06 | 0 | 49982.4 | 49982.4 | 8 | 81 | 810 | 8101 | 17 | 17% | 8497.008
810.103 | Project Management Office ORNL FY05 | 5215.1705 | 63599.64 | 58384.4695 | 8 | 81 | 810 | 8102 | 17 | 17% | 9925.3598
810.004 | Project Management Office PPPL FY06 | 0 | 59070.9 | 59070.9 | 8 | 81 | 810 | 8101 | 17 | 17% | 10042.053
810.900 | Project Management Office PPPL FY08 | 0 | 70552.04 | 70552.04 | 8 | 81 | 810 | 8101 | 17 | 17% | 11993.8468
810.003 | Project Management Office PPPL FY05 | 17768.3758 | 216687.51 | 198919.1342 | 8 | 81 | 810 | 8101 | 17 | 17% | 33816.2528
810.005 | Project Management OfficePPPL FY07 | 0 | 204707.88 | 204707.88 | 8 | 81 | 810 | 8101 | 17 | 17% | 34800.3396
810.004 | Project Management Office PPPL FY06 | 0 | 220824.04 | 220824.04 | 8 | 81 | 810 | 8101 | 17 | 17% | 37540.0868
810.005 | Project Management OfficePPPL FY07 | 0 | 257069.69 | 257069.69 | 8 | 81 | 810 | 8101 | 17 | 17% | 43701.8473
810.004 | Project Management Office PPPL FY06 | 0 | 305112.6 | 305112.6 | 8 | 81 | 810 | 8101 | 17 | 17% | 51869.142
810.003 | Project Management Office PPPL FY05 | 27790.725 | 338911.28 | 311120.555 | 8 | 81 | 810 | 8101 | 17 | 17% | 52890.4944
820.005 | Proj engr FY08 | 0 | 5505 | 5505 | 8 | 82 | 820 | 8202 | 17 | 17% | 935.85
820.004 | Proj engr FY06 | 0 | 8675 | 8675 | 8 | 82 | 820 | 8202 | 17 | 17% | 1474.75
820.004Z | Proj engr FY07 | 0 | 9175 | 9175 | 8 | 82 | 820 | 8202 | 17 | 17% | 1559.75
820.003 | Proj engr FY05 | 997.612 | 12166 | 11168.388 | 8 | 82 | 820 | 8202 | 17 | 17% | 1898.626
820.003 | Proj engr FY05 | 1171.7636 | 14289.8 | 13118.0364 | 8 | 82 | 820 | 8202 | 17 | 17% | 2230.0662
820.003 | Proj engr FY05 | 1181.1395 | 14404.14 | 13223.0005 | 8 | 82 | 820 | 8202 | 17 | 17% | 2247.9101
820.004 | Proj engr FY06 | 0 | 14843.4 | 14843.4 | 8 | 82 | 820 | 8202 | 17 | 17% | 2523.378
820.004Z | Proj engr FY07 | 0 | 15414.3 | 15414.3 | 8 | 82 | 820 | 8202 | 17 | 17% | 2620.431
820.004Z | Proj engr FY07 | 0 | 31025.82 | 31025.82 | 8 | 82 | 820 | 8202 | 17 | 17% | 5274.3894
8203FY07 | Design Integration FY07 | 0 | 38665.83 | 38665.83 | 8 | 82 | 820 | 8203 | 17 | 17% | 6573.1911
8203FY05 | Design Integration FY05 LOE | 0 | 47848.65 | 47848.65 | 8 | 82 | 820 | 8203 | 17 | 17% | 8134.2705
820.004 | Proj engr FY06 | 0 | 88474.4 | 88474.4 | 8 | 82 | 820 | 8202 | 17 | 17% | 15040.648
8203FY06 | Design Integration FY06 | 0 | 92099.36 | 92099.36 | 8 | 82 | 820 | 8203 | 17 | 17% | 15656.8912
8203FY07 | Design Integration FY07 | 0 | 93138.4 | 93138.4 | 8 | 82 | 820 | 8203 | 17 | 17% | 15833.528
820.005 | Proj engr FY08 | 0 | 96291.02 | 96291.02 | 8 | 82 | 820 | 8202 | 17 | 17% | 16369.4734
8204FY06 | Systems Analysis FY06 | 0 | 103416.88 | 103416.88 | 8 | 82 | 820 | 8204 | 17 | 17% | 17580.8696
820.003 | Proj engr FY05 | 9476.5842 | 115568.1 | 106091.5158 | 8 | 82 | 820 | 8202 | 17 | 17% | 18035.5577
8203FY05 | Design Integration FY05 LOE | 0 | 108312.75 | 108312.75 | 8 | 82 | 820 | 8203 | 17 | 17% | 18413.1675
8205FY07 | Systems Engineering Support FY06 | 0 | 119024.24 | 119024.24 | 8 | 82 | 820 | 8202 | 17 | 17% | 20234.1208
8203FY06 | Design Integration FY06 | 0 | 147762.86 | 147762.86 | 8 | 82 | 820 | 8203 | 17 | 17% | 25119.6862
8205FY06 | Systems Engineering Support FY06 | 0 | 161959.21 | 161959.21 | 8 | 82 | 820 | 8202 | 17 | 17% | 27533.0657
820.004Z | Proj engr FY07 | 0 | 186252.08 | 186252.08 | 8 | 82 | 820 | 8202 | 17 | 17% | 31662.8536
8205FY05 | System Engr Support FY05 | 18229.2757 | 222308.24 | 204078.9643 | 8 | 82 | 820 | 8202 | 17 | 17% | 34693.4239
8204FY05 | Systems Analysis FY05 | 21380.1199 | 260733.17 | 239353.0501 | 8 | 82 | 820 | 8204 | 17 | 17% | 40690.0185
820.003 | Proj engr FY05 | 22577.8472 | 275339.6 | 252761.7528 | 8 | 82 | 820 | 8202 | 17 | 17% | 42969.498
820.004 | Proj engr FY06 | 0 | 280800.8 | 280800.8 | 8 | 82 | 820 | 8202 | 17 | 17% | 47736.136
920.001 | Procedure and Document Preparation | 0 | 221309.16 | 221309.16 | 8 | 85 |  |  | 20 | 20% | 44261.832
920.001 | Procedure and Document Preparation | 0 | 340537.53 | 340537.53 | 8 | 85 |  |  | 20 | 20% | 68107.506
920.000 | Startup Personnel | 0 | 37838.16 | 37838.16 | 8 | 85 |  |  | 30 | 30% | 11351.448
920.000 | Startup Personnel | 0 | 71177.04 | 71177.04 | 8 | 85 |  |  | 30 | 30% | 21353.112
920.000 | Startup Personnel | 0 | 74609.28 | 74609.28 | 8 | 85 |  |  | 30 | 30% | 22382.784
920.000 | Startup Personnel | 0 | 77029.2 | 77029.2 | 8 | 85 |  |  | 30 | 30% | 23108.76
920.000 | Startup Personnel | 0 | 83643 | 83643 | 8 | 85 |  |  | 30 | 30% | 25092.9
920.000 | Startup Personnel | 0 | 117333.15 | 117333.15 | 8 | 85 |  |  | 30 | 30% | 35199.945
920.000 | Startup Personnel | 0 | 196595.27 | 196595.27 | 8 | 85 |  |  | 30 | 30% | 58978.581
99.07 | PPPL Allocations FY07 | 0 | 166893.23 | 166893.23 | 8 | AA | AAA | 8998 | 10 | 10% | 16689.323
99.05 | PPPL Allocations FY05 | 25775.2404 | 314332.2 | 288556.9596 | 8 | AA | AAA | 8998 | 10 | 10% | 28855.696
99.06 | PPPL Allocations FY06 | 0 | 320745.3 | 320745.3 | 8 | AA | AAA | 8998 | 10 | 10% | 32074.53
3110 | Contract balance | 74000 | 74000 |  | 1 | 14 | 141
1030.1 | Review & Evaluate Proposals | 4821 | 4821 |  | 1 | 14 | 141
1030.1 | Review & Evaluate Proposals | 4821 | 4821 |  | 1 | 14 | 141
1030.1 | Review & Evaluate Proposals | 4845 | 4845 |  | 1 | 14 | 141
1030.1 | Review & Evaluate Proposals | 3860.7 | 3860.7 |  | 1 | 14 | 141
1030.1 | Review & Evaluate Proposals | 3860.7 | 3860.7 |  | 1 | 14 | 141
1101-100 | Update Conceptual Design | 60 | 60 |  | 1 | 11 | 111
1201-002 | Apr-Sept MIE Cost ORNL | 319050 | 319050 |  | 1 | 12 | 121
1201-003 | Apr-MSept MIE Cost PPPL | 105370 | 105370 |  | 1 | 12 | 121
1202-002 | Apr-Sept MIE Cost ORNL | 60 | 60 |  | 1 | 12 | 121
1202-003 | Apr-Sept MIE Cost PPPL | 128340 | 128340 |  | 1 | 12 | 121
1202-303 | MT-Issue VVSA MIT/QA plans and C&S Est (3.1) | 17153.6 | 17153.6 |  | 1 | 12 | 121
1202-305 | MT-Issue Draft MIT/QA plan (3.2.1) | 10050.56 | 10050.56 |  | 1 | 12 | 121
1202-324 | MT-PVVS Begin Fabrication (3.2.2) | 368464.16 | 368464.16 |  | 1 | 12 | 121
1202-325 | MT-PVVS Complete Fabrication (3.2.2) [A/ 1] | 290115.28 | 290115.28 |  | 1 | 12 | 121
1202-325 | MT-PVVS Complete Fabrication (3.2.2) [A/ 1] | 85000 | 85000 |  | 1 | 12 | 121
1202-325A | Vist MT for welding | 2584 | 2584 |  | 1 | 12 | 121
1202-327 | PPPL Receipt Inspection of MT PVVS | 12856 | 12856 |  | 1 | 12 | 121
1202-327 | PPPL Receipt Inspection of MT PVVS | 1292 | 1292 |  | 1 | 12 | 121
1202-330 | MT-Final MIT/QA plans for VVSA (3.3.1) | 6370 | 6370 |  | 1 | 12 | 121
1202-335 | MT-Firm Fixed Price Proposal for VVSA (3.3.2) | 6370 | 6370 |  | 1 | 12 | 121
1202-400 | Oversight and Contract Management | 41990 | 41990 |  | 1 | 12 | 121
1202-400 | Oversight and Contract Management | 20748 | 20748 |  | 1 | 12 | 121
1202-401 | Oversight and Contract Management | 27939.5 | 27939.5 |  | 1 | 12 | 121
1202-401 | Oversight and Contract Management | 20748 | 20748 |  | 1 | 12 | 121
1202-402 | Oversight and Contract Management | 18572.5 | 18572.5 |  | 1 | 12 | 121
1202-403 | RW-Issue VVSA MIT/QA plans and C&S Est (3.1) | 71888.08 | 71888.08 |  | 1 | 12 | 121
1202-405 | RW-Issue Draft MIT/QA plan (3.2.1) | 19352.16 | 19352.16 |  | 1 | 12 | 121
1202-424 | RW-PVVS Begin Fabrication (3.2.2) | 143280.88 | 143280.88 |  | 1 | 12 | 121
1202-425 | RW-PVVS Complete Fabrication (3.2.2) | 183532.44 | 183532.44 |  | 1 | 12 | 121
1202-425 | RW-PVVS Complete Fabrication (3.2.2) | 127527.4 | 127527.4 |  | 1 | 12 | 121
1202-427 | PPPL Receipt Inspection of RW PVVS | 12856 | 12856 |  | 1 | 12 | 121
1202-427 | PPPL Receipt Inspection of RW PVVS | 1292 | 1292 |  | 1 | 12 | 121
1202-430 | RW-Final MIT/QA plans for VVSA (3.3.1) | 23709.14 | 23709.14 |  | 1 | 12 | 121
1202-435 | RW-Firm Fixed Price Proposal for VVSA (3.3.2) | 15122.38 | 15122.38 |  | 1 | 12 | 121
1202-800 | Inconnel Procurement *ECP6* | 1783.6 | 1783.6 |  | 1 | 12 | 121
1202-803 | Drawings for Arc/Samples *ECP6* | 3230 | 3230 |  | 1 | 12 | 121
1202-806 | Waterjet Arcs *ECP6* | 1228.8 | 1228.8 |  | 1 | 12 | 121
1202-809 | Machine weld groove *ECP6* | 3369.6 | 3369.6 |  | 1 | 12 | 121
1202-812 | Anneal Samples *ECP6* | 1684.8 | 1684.8 |  | 1 | 12 | 121
1202-815 | Setup weld test *ECP6* | 1228.8 | 1228.8 |  | 1 | 12 | 121
1202-818 | Weld samples *ECP6* | 2527.2 | 2527.2 |  | 1 | 12 | 121
1202-821 | Eval & Redesign Joint iteration 2 *ECP6* | 3230 | 3230 |  | 1 | 12 | 121
1202-824 | Machine iteration 2 *ECP6* | 3369.6 | 3369.6 |  | 1 | 12 | 121
1202-827 | Anneal iteration 2 *ECP6* | 1684.8 | 1684.8 |  | 1 | 12 | 121
1202-833 | Eval & redesign joint iteration 3 *ECP6* | 3230 | 3230 |  | 1 | 12 | 121
1202-836 | Machine iteration 3 *ECP6* | 3369.6 | 3369.6 |  | 1 | 12 | 121
1202-839 | Anneal iteration 3 *ECP6* | 1684.8 | 1684.8 |  | 1 | 12 | 121
1202-842 | Weld iteration 3 *ECP6* | 2527.2 | 2527.2 |  | 1 | 12 | 121
1202-845 | SOW for full size test sample *ECP6* | 6460 | 6460 |  | 1 | 12 | 121
1202-866 | Engineering Oversght *ECP6* | 18249.5 | 18249.5 |  | 1 | 12 | 121
1202-ECP16 | ecp-16 | 14600 | 14600 |  | 1 | 12 | 121
1203-101 | Prepare documents for PDR closeout | 7721.4 | 7721.4 |  | 1 | 12 | 121
1203-111 | Response to chits, prepare FY04 WP/WAF/Checklist | 7721.4 | 7721.4 |  | 1 | 12 | 121
1203-121 | Review, revise, and approve SRD | 7721.4 | 7721.4 |  | 1 | 12 | 121
1203-131 | Complete preliminary design of insulation and he | 7721.4 | 7721.4 |  | 1 | 12 | 121
1203-131 | Complete preliminary design of insulation and he | 3860.7 | 3860.7 |  | 1 | 12 | 121
1203-141 | Finalize Spec for VVSA | 5147.6 | 5147.6 |  | 1 | 12 | 121
1203-141 | Finalize Spec for VVSA | 12920 | 12920 |  | 1 | 12 | 121
1203-151 | Update VVSA Drawings incl ECP6 add'l port config | 15442.8 | 15442.8 |  | 1 | 12 | 121
1203-151 | Update VVSA Drawings incl ECP6 add'l port config | 186960.83 | 186960.83 |  | 1 | 12 | 121
1203-181 | Start Thermal Analyses | 514.76 | 514.76 |  | 1 | 12 | 121
1203-181 | Start Thermal Analyses | 22498 | 22498 |  | 1 | 12 | 121
1203-191 | Start Eddy Current Analyses | 643.45 | 643.45 |  | 1 | 12 | 121
1203-191 | Start Eddy Current Analyses | 2892.6 | 2892.6 |  | 1 | 12 | 121
1203-202 | Start Port Nozzle Analysis | 5142.4 | 5142.4 |  | 1 | 12 | 121
1203-233 | Check structural analysis | 12638.08 | 12638.08 |  | 1 | 12 | 121
1203-234 | Perform Global Seismic Analysis | 37914.24 | 37914.24 |  | 1 | 12 | 121
1203-235 | Perform Local Thermal Analysis | 15442.8 | 15442.8 |  | 1 | 12 | 121
1203-236 | Checdk Local Thermal Analysis | 15442.8 | 15442.8 |  | 1 | 12 | 121
1203-237 | Perform Thermal-Hydraulic Analysis VV htg/clng | 10295.2 | 10295.2 |  | 1 | 12 | 121
1203-238 | Check Thermal-Hydraulic Analysis VV htg/clng | 12856 | 12856 |  | 1 | 12 | 121
1203-240 | Check Analysis of VV Supports | 5147.6 | 5147.6 |  | 1 | 12 | 121
1203-261 | Startup Plan | 26019.26 | 26019.26 |  | 1 | 12 | 121
1203-291 | Update Design Basis Document | 2059.04 | 2059.04 |  | 1 | 12 | 121
1203-301 | Update Cost and Schedule Estimates | 3311.16 | 3311.16 |  | 1 | 12 | 121
1203-311 | Prepare Final Design ECP | 3088.56 | 3088.56 |  | 1 | 12 | 121
1203-321 | Assemble FDR Drawing Package, Check & Promote | 4118.08 | 4118.08 |  | 1 | 12 | 121
1203-331 | Prepare Presentations | 12869 | 12869 |  | 1 | 12 | 121
1203-400 | 350c Bakeout Study | 25738 | 25738 |  | 1 | 12 | 121
1203-405 | Field Weld joint design and Specific spool piece | 5791.05 | 5791.05 |  | 1 | 12 | 121
1203-405 | Field Weld joint design and Specific spool piece | 32815.95 | 32815.95 |  | 1 | 12 | 121
121-032 | VVSA Contract oversight FY04 | 20187.5 | 20187.5 |  | 1 | 12 | 121
121-6-6 | Finalize tech Doc package & Resolve chits | 1286.9 | 1286.9 |  | 1 | 12 | 121
121-6-8 | Evaluate and Select VV Production Vendor | 1615 | 1615 |  | 1 | 12 | 121
121-6-8 | Evaluate and Select VV Production Vendor | 1286.9 | 1286.9 |  | 1 | 12 | 121
121-6-83 | Negotiate with vendor | 1615 | 1615 |  | 1 | 12 | 121
1301-0002 | Apr-Sept MIE Cost ORNL | 0 | 0 |  | 1 | 13 | 130
1301-0003 | Apr-Sept MIE Cost PPPL | 91660 | 91660 |  | 1 | 13 | 130
1301-105 | Prepare Interface Dwgs for ICD's | 2904.42 | 2904.42 |  | 1 | 13 | 130
1301-140 | Complete Draft SOW | 4821 | 4821 |  | 1 | 13 | 130
1301-145 | Post Draft SOW on WEB to Solicit Vendr Input | 1285.6 | 1285.6 |  | 1 | 13 | 130
1301-150 | Vendor Responses | 7231.5 | 7231.5 |  | 1 | 13 | 130
1301-155 | Trim Coil Layouts | 5624.5 | 5624.5 |  | 1 | 13 | 130
1301-155 | Trim Coil Layouts | 50138.4 | 50138.4 |  | 1 | 13 | 130
1301-160 | Trim Coil Leads | 642.8 | 642.8 |  | 1 | 13 | 130
1301-160 | Trim Coil Leads | 6428 | 6428 |  | 1 | 13 | 130
1301-165 | PF1-PF3 Support System Layouts | 2089.1 | 2089.1 |  | 1 | 13 | 130
1301-165 | PF1-PF3 Support System Layouts | 19284 | 19284 |  | 1 | 13 | 130
1301-170 | New Lead Details | 1285.6 | 1285.6 |  | 1 | 13 | 130
1301-170 | New Lead Details | 12856 | 12856 |  | 1 | 13 | 130
1301-175.2 | Revised Design Stress Analysis | 3822 | 3822 |  | 1 | 13 | 130
1301-175.3 | Layout New Wedge Concept | 5142.4 | 5142.4 |  | 1 | 13 | 130
1301-175.8 | Rerun Analysis | 6370 | 6370 |  | 1 | 13 | 130
1301-180 | Update ANSYS model & structure | 803.5 | 803.5 |  | 1 | 13 | 130
1301-180 | Update ANSYS model & structure | 7491.12 | 7491.12 |  | 1 | 13 | 130
1301-185 | FEA Analysis Coils,Stress deflection | 1124.9 | 1124.9 |  | 1 | 13 | 130
1301-185 | FEA Analysis Coils,Stress deflection | 11147.5 | 11147.5 |  | 1 | 13 | 130
1301-190 | FEA Analysis PF Supports,Stress Deflection | 899.92 | 899.92 |  | 1 | 13 | 130
1301-190 | FEA Analysis PF Supports,Stress Deflection | 8918 | 8918 |  | 1 | 13 | 130
1301-195 | Seismic Analysis | 1124.9 | 1124.9 |  | 1 | 13 | 130
1301-195 | Seismic Analysis | 11147.5 | 11147.5 |  | 1 | 13 | 130
1301-300 | Investigate Experimental Data *ECP6* | 642.8 | 642.8 |  | 1 | 13 | 130
1301-303 | Prepare Test Reqmnts *ECP6* | 803.5 | 803.5 |  | 1 | 13 | 130
1301-318 | Evaluate 3D glass *ECP6* | 642.8 | 642.8 |  | 1 | 13 | 130
1301-FY04 | FY04 cost variance | 27000 | 27000 |  | 1 | 13 | 130
1301R-03 | ReEvaluate Analysis, Dahlgren | 19284 | 19284 |  | 1 | 13 | 130
1301R-05 | Change Insulation Scheme | 1285.6 | 1285.6 |  | 1 | 13 | 130
1301R-07 | Procure Test Services | 2628.72 | 2628.72 |  | 1 | 13 | 130
1301R-22 | Hydraulic Analysis | 12856 | 12856 |  | 1 | 13 | 130
1301R-25 | Final Determination ofLaunching Loads | 1274 | 1274 |  | 1 | 13 | 130
1301R-26 | Final Launch Load Analysis | 3822 | 3822 |  | 1 | 13 | 130
1301R-27 | Obtain Stresses from Deflection Analysis | 2548 | 2548 |  | 1 | 13 | 130
1401-002 | Apr-Sept MIE Cost ORNL | 303040 | 303040 |  | 1 | 14 | 141
1401-003 | Apr-Sept MIE Cost PPPL | 0 | 0 |  | 1 | 14 | 141
1402-002 | Apr-Sept MIE Cost ORNL | 84220 | 84220 |  | 1 | 14 | 141
1402-003 | Apr-Sept MIE Cost PPPL | 154920 | 154920 |  | 1 | 14 | 141
1402-004 | Subcontract analysis upport for PDR | 5096 | 5096 |  | 1 | 13 | 130
1402-005 | VV/MCC PDR support | 4178.2 | 4178.2 |  | 1 | 13 | 130
1403-03 | Increase for actual cost of Final Design ECP 11 | 1000 | 1000 |  | 1 | 14 | 141
1403-03 | Increase for actual cost of Final Design ECP 11 | 357000 | 357000 |  | 1 | 14 | 141
1403-04 | Plan response to PDR chits | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-05 | Prepare FY04 WP / WAF / Checklists | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-06 | Prepare documents for PDR closeout | 10295.2 | 10295.2 |  | 1 | 14 | 141
1403-07 | Prepare PBR documentation | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-10 | Review, revise, and approve SRD | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-11 | Prepare assembly / interface drawings for ICDs | 4632.84 | 4632.84 |  | 1 | 14 | 141
1403-11 | Prepare assembly / interface drawings for ICDs | 4671.45 | 4671.45 |  | 1 | 14 | 141
1403-12 | Finalize and approve all ICDs | 4632.84 | 4632.84 |  | 1 | 14 | 141
1403-13 | Finalize winding pack ref xsec, conductor dims | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-14 | Revise winding form and windings/asm models | 13769.83 | 13769.83 |  | 1 | 14 | 141
1403-14 | Revise winding form and windings/asm models | 13769.83 | 13769.83 |  | 1 | 14 | 141
1403-14 | Revise winding form and windings/asm models | 13769.83 | 13769.83 |  | 1 | 14 | 141
1403-15 | Prepare winding form asm / detail drawings | 23421.58 | 23421.58 |  | 1 | 14 | 141
1403-15 | Prepare winding form asm / detail drawings | 18531.36 | 18531.36 |  | 1 | 14 | 141
1403-15 | Prepare winding form asm / detail drawings | 20075.64 | 20075.64 |  | 1 | 14 | 141
1403-202 | G-10 Filler Dwgs (24)-Type C ????????????? | 1029.52 | 1029.52 |  | 1 | 14 | 142
1403-202 | G-10 Filler Dwgs (24)-Type C ????????????? | 7721.4 | 7721.4 |  | 1 | 14 | 142
1403-202 | G-10 Filler Dwgs (24)-Type C ????????????? | 4761.53 | 4761.53 |  | 1 | 14 | 142
1403-203 | Clamp Dwgs (5)-Type C | 3132.66 | 3132.66 |  | 1 | 14 | 142
1403-203 | Clamp Dwgs (5)-Type C | 1305.28 | 1305.28 |  | 1 | 14 | 142
1403-21 | Document electrical, insulation parameters | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-22 | Update thermal analysis to current WP design | 5147.6 | 5147.6 |  | 1 | 14 | 141
1403-23 | Update thermo-hydraulic analysis of coils | 6428 | 6428 |  | 1 | 14 | 141
1403-25 | Check EM loads calculation for ref scenarios | 5147.6 | 5147.6 |  | 1 | 14 | 141
1403-26 | Perform scan of EM fault load conditions | 10295.2 | 10295.2 |  | 1 | 14 | 141
1403-26.1 | Check thermal & electrical calculations | 10295.2 | 10295.2 |  | 1 | 14 | 141
1403-27 | Prepare thermal, electrical analysis report | 20590.4 | 20590.4 |  | 1 | 14 | 141
1403-27A | Update winding pack thermal/hydraulic analysis | 20590.4 | 20590.4 |  | 1 | 14 | 141
1403-29 | Complete ANSYS model of coil structure asm | 160700 | 160700 |  | 1 | 14 | 141
1403-30 | Analyze global stress /deflect winding form asm | 16070 | 16070 |  | 1 | 14 | 141
1403-31 | Analyze stress in bolted connections | 6428 | 6428 |  | 1 | 14 | 141
1403-32 | Update MECHANICA model of 3 coil types | 10295.2 | 10295.2 |  | 1 | 14 | 141
1403-33 | Anlyz wind pack deflect/stress fo thrml, EM lds | 5147.6 | 5147.6 |  | 1 | 14 | 141
1403-34 | Analyze and optimize clamp locations | 5147.6 | 5147.6 |  | 1 | 14 | 141
1403-35 | Perform supporting analysis for material tests | 16727.62 | 16727.62 |  | 1 | 14 | 141
1403-36 | Update EM loads for reference scenarios | 10357.62 | 10357.62 |  | 1 | 14 | 141
1403-37 | Perform check og global structural analysis | 16727.62 | 16727.62 |  | 1 | 14 | 141
1403-38 | Check nonlinear winding pack analysis | 10357.62 | 10357.62 |  | 1 | 14 | 141
1403-39 | Analyze gravity, equip, seismic loading | 6428 | 6428 |  | 1 | 14 | 141
1403-40 | Analyze combined loads and fault conditions | 6428 | 6428 |  | 1 | 14 | 141
1403-40.1 | Check Structural Calculations | 9265.68 | 9265.68 |  | 1 | 14 | 141
1403-40.1A | Prepare plate element model of coil structure | 9265.68 | 9265.68 |  | 1 | 14 | 141
1403-40.1B | Confirm global deflection/stress, re-inf of shel | 10295.2 | 10295.2 |  | 1 | 14 | 141
1403-40.1C | Check all struct calculkations | 9265.68 | 9265.68 |  | 1 | 14 | 141
1403-40.2A | Develop multi-filament model of all coils | 3088.56 | 3088.56 |  | 1 | 14 | 141
1403-40.2B | Confirm Plasma performance & surface quality | 3856.8 | 3856.8 |  | 1 | 14 | 141
1403-40.2C | Model expected deflections under thermal/EM load | 6177.12 | 6177.12 |  | 1 | 14 | 141
1403-40.2D | Confirm plasma performance & surface quality | 7713.6 | 7713.6 |  | 1 | 14 | 141
1403-40.3X | Modify MCWF Contract Documents & drawings | 20590.4 | 20590.4 |  | 1 | 14 | 141
1403-41 | Prepare structural analysis report | 18531.36 | 18531.36 |  | 1 | 14 | 141
1403-42 | Complete FDR Struct Analysis Report | 25712 | 25712 |  | 1 | 14 | 141
1403-42 | Complete FDR Struct Analysis Report | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-42 | Complete FDR Struct Analysis Report | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-42B | Modify ORNL beam test setup provide torsional ld | 5147.6 | 5147.6 |  | 1 | 14 | 141
1403-42C | Revise analysis incorp final modeling changes | 19110 | 19110 |  | 1 | 14 | 141
1403-42C | Revise analysis incorp final modeling changes | 15442.8 | 15442.8 |  | 1 | 14 | 141
1403-42E | Complete checking struct calculations | 6428 | 6428 |  | 1 | 14 | 141
1403-42E | Complete checking struct calculations | 6370 | 6370 |  | 1 | 14 | 141
1403-42E | Complete checking struct calculations | 5147.6 | 5147.6 |  | 1 | 14 | 141
1403-43 | Incorporate changes due to prototype fabr | 3474.63 | 3474.63 |  | 1 | 14 | 141
1403-43 | Incorporate changes due to prototype fabr | 3474.63 | 3474.63 |  | 1 | 14 | 141
1403-43 | Incorporate changes due to prototype fabr | 3474.63 | 3474.63 |  | 1 | 14 | 141
1403-44 | Prepare final drawings for winding forms, asm | 27410.97 | 27410.97 |  | 1 | 14 | 141
1403-44 | Prepare final drawings for winding forms, asm | 27410.97 | 27410.97 |  | 1 | 14 | 141
1403-44 | Prepare final drawings for winding forms, asm | 27410.97 | 27410.97 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 20590.4 | 20590.4 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 20590.4 | 20590.4 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 5147.6 | 5147.6 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 20590.4 | 20590.4 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 3856.8 | 3856.8 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 2571.2 | 2571.2 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 10295.2 | 10295.2 |  | 1 | 14 | 141
1403-45 | Check and promote models / drawings | 37062.72 | 37062.72 |  | 1 | 14 | 141
1403-46 | Update build-to specification / SOW | 15442.8 | 15442.8 |  | 1 | 14 | 141
1403-47 | Prepare failure modes assessment (FMECA) | 4504.15 | 4504.15 |  | 1 | 14 | 141
1403-48 | Update design basis document | 15442.8 | 15442.8 |  | 1 | 14 | 141
1403-50 | Prepare FDR documentation / presentations | 10295.2 | 10295.2 |  | 1 | 14 | 141
1403-53 | Resolve FDR comments and recommendations | 15442.8 | 15442.8 |  | 1 | 14 | 141
1403-54 | Final bid package( specs,models,dwgs) | 2573.8 | 2573.8 |  | 1 | 14 | 141
1403-54 | Final bid package( specs,models,dwgs) | 1029.52 | 1029.52 |  | 1 | 14 | 141
1403-54 | Final bid package( specs,models,dwgs) | 1292 | 1292 |  | 1 | 14 | 141
1403-54 | Final bid package( specs,models,dwgs) | 3214 | 3214 |  | 1 | 14 | 141
1403-ECP16 | ecp16 | 139000 | 139000 |  | 1 | 14 | 142
1403-FY04 | Analysis fy04 | 5096 | 5096 |  | 1 | 14 | 141
1403-FY04 | Analysis fy04 | 11249 | 11249 |  | 1 | 14 | 141
1403-FY04 | Analysis fy04 | 32172.5 | 32172.5 |  | 1 | 14 | 141
1404-002 | Apr-Sept YTD MIE Cost ORNL | 100220 | 100220 |  | 1 | 14 | 141
1404-003 | Apr-Sept YTD MIE Cost PPPL | 64670 | 64670 |  | 1 | 14 | 141
1404-100 | EIO-Cost FY03 | 307170.24 | 307170.24 |  | 1 | 14 | 141
1404-105 | EIO-FY04 Cost Through June 30,2004 ECP 11 | 313047.28 | 313047.28 |  | 1 | 14 | 141
1404-105 | EIO-FY04 Cost Through June 30,2004 ECP 11 | 258290 | 258290 |  | 1 | 14 | 141
1404-106 | contract balance ECP 11 | 119610 | 119610 |  | 1 | 14 | 141
1404-200 | JPP- cost FY03 | 92170.4 | 92170.4 |  | 1 | 14 | 141
1404-205 | JPP-FY04 Cost Through June 30,2004 ECP 11 | 417120.34 | 417120.34 |  | 1 | 14 | 141
1404-206 | JPP- July forecast ECP 11 | 20750 | 20750 |  | 1 | 14 | 141
1404-206 | JPP- July forecast ECP 11 | 122622.5 | 122622.5 |  | 1 | 14 | 141
1404-65 | Fabrication oversight by Project | 82000 | 82000 |  | 1 | 14 | 141
1404-65 | Fabrication oversight by Project | 50000 | 50000 |  | 1 | 14 | 141
1404-66 | Proposal evaluation & contract oversight | 6949.26 | 6949.26 |  | 1 | 14 | 141
1404-66 | Proposal evaluation & contract oversight | 8677.8 | 8677.8 |  | 1 | 14 | 141
1404-ECP16 | ecp16 | 93000 | 93000 |  | 1 | 14 | 141
1404-FR1 | Rough machine specimens, Lot 1 (17 pcs.) at PPPL | 1305.6 | 1305.6 |  | 1 | 14 | 141
1404-FR2 | Machine Lot 1 specimens to ASTM spec (Crystal En | 1082.9 | 1082.9 |  | 1 | 14 | 141
1404-FR3 | Test Lot 1 specimens - 17 pcs. At $260 | 5844.57 | 5844.57 |  | 1 | 14 | 141
1404-FR4 | Rough machine Lot 2 (11 specimens) at PPPL | 856.56 | 856.56 |  | 1 | 14 | 141
1404-FR5 | Machine Lot 2 specimens to ASTM spec. (Crystal E | 1041.75 | 1041.75 |  | 1 | 14 | 141
1404-FR6 | Test Lot 2 specimens @NHMFL 11 pcs. | 3972.54 | 3972.54 |  | 1 | 14 | 141
1404-FR7 | Engineering coordination | 6507.47 | 6507.47 |  | 1 | 14 | 141
1405-002 | Apr-Sep YTD MIE Cost ORNL | 0 | 0 |  | 1 | 14 | 142
1405-003 | Apr-Sep YTD MIE Cost PPPL | 168070 | 168070 |  | 1 | 14 | 142
1406-000 | Supervision & Oversight | 57048.5 | 57048.5 |  | 1 | 14 | 142
1406-000 | Supervision & Oversight | 49596.3 | 49596.3 |  | 1 | 14 | 142
1406-000.1 | Supervision & Oversight | 46281.6 | 46281.6 |  | 1 | 14 | 142
1406-000.1 | Supervision & Oversight | 45489.6 | 45489.6 |  | 1 | 14 | 142
1406-000.1 | Supervision & Oversight | 23140.8 | 23140.8 |  | 1 | 14 | 142
1406-0002 | Apr-Sep YTD MIE Cost ORNL | 0 | 0 |  | 1 | 14 | 142
1406-0003 | Apr-Sep YTD MIE Cost PPPL | 831120 | 831120 |  | 1 | 14 | 142
1406-001 | Purchase 10 spools conductor (twisted racetrack) | 7644 | 7644 |  | 1 | 14 | 142
1406-003 | Purchase 8 spools conductor (long twisted windin | 7644 | 7644 |  | 1 | 14 | 142
1406-005 | Purchase epoxy & Insulation | 5516.42 | 5516.42 |  | 1 | 14 | 142
1406-010 | Keystone Test for New Conductor | 6144 | 6144 |  | 1 | 14 | 142
1406-011 | Purchase add'l copper Conductor | 8918 | 8918 |  | 1 | 14 | 142
1406-016 | Procure casting from EIO (new scope) | 127387.26 | 127387.26 |  | 1 | 14 | 142
1406-016.9 | fab trc clamps | 24206 | 24206 |  | 1 | 14 | 142
1406-029 | Fab New Specimen Molds | 6144 | 6144 |  | 1 | 14 | 142
1406-029 | Fab New Specimen Molds | 16848 | 16848 |  | 1 | 14 | 142
1406-030 | Fab & Pot samples | 31334.4 | 31334.4 |  | 1 | 14 | 142
1406-031 | Prep fixtures and test equipt | 25840 | 25840 |  | 1 | 14 | 142
1406-031 | Prep fixtures and test equipt | 16848 | 16848 |  | 1 | 14 | 142
1406-031 | Prep fixtures and test equipt | 25272 | 25272 |  | 1 | 14 | 142
1406-031 | Prep fixtures and test equipt | 1274 | 1274 |  | 1 | 14 | 142
1406-032 | Test samples | 31008 | 31008 |  | 1 | 14 | 142
1406-032 | Test samples | 20217.6 | 20217.6 |  | 1 | 14 | 142
1406-048 | Testing & Strain Gauge Design | 14050.5 | 14050.5 |  | 1 | 14 | 142
1406-048 | Testing & Strain Gauge Design | 10203 | 10203 |  | 1 | 14 | 142
1406-049 | Increased cost of FDR support ECP 11 | 292000 | 292000 |  | 1 | 14 | 142
1406-097 | Verify Conductor Dims | 2573.8 | 2573.8 |  | 1 | 14 | 142
1406-098 | Complete Drawings of Casting | 7721.4 | 7721.4 |  | 1 | 14 | 142
1406-098 | Complete Drawings of Casting | 7721.4 | 7721.4 |  | 1 | 14 | 142
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 1 | 14 | 142
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 1 | 14 | 142
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 1 | 14 | 142
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 1 | 14 | 142
1406-101 | Prepare Clamp & Chill Plate detail Drawings | 20590.4 | 20590.4 |  | 1 | 14 | 142
1406-101 | Prepare Clamp & Chill Plate detail Drawings | 30113.46 | 30113.46 |  | 1 | 14 | 142
1406-101.1 | Winding block dwgs for prototype leads????????? | 20590.4 | 20590.4 |  | 1 | 14 | 142
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 2646.61 | 2646.61 |  | 1 | 14 | 142
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 3969.92 | 3969.92 |  | 1 | 14 | 142
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 1058.65 | 1058.65 |  | 1 | 14 | 142
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 5028.56 | 5028.56 |  | 1 | 14 | 142
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 9527.81 | 9527.81 |  | 1 | 14 | 142
1406-103.0 | Prep MIT plan | 2686.24 | 2686.24 |  | 1 | 14 | 142
1406-103.1 | Prepare for Twisted Racetrack FDR | 4138.95 | 4138.95 |  | 1 | 14 | 142
1406-103.1 | Prepare for Twisted Racetrack FDR | 4138.95 | 4138.95 |  | 1 | 14 | 142
1406-103.1 | Prepare for Twisted Racetrack FDR | 4138.95 | 4138.95 |  | 1 | 14 | 142
1406-103.1 | Prepare for Twisted Racetrack FDR | 4138.95 | 4138.95 |  | 1 | 14 | 142
1406-105 | Prepare ANSYS thermal analysis model | 2573.8 | 2573.8 |  | 1 | 14 | 142
1406-106 | Analyze Thermal Behavior due to pulse | 2573.8 | 2573.8 |  | 1 | 14 | 142
1406-107 | Calculate EM Loads due to max current | 5147.6 | 5147.6 |  | 1 | 14 | 142
1406-108 | Prep MECHANICA Struct Analysis Model | 5147.6 | 5147.6 |  | 1 | 14 | 142
1406-109 | Analyze Stress/deflection due to cooldown,pulse | 5147.6 | 5147.6 |  | 1 | 14 | 142
1406-111 | Write papers and present at conferences | 30885.6 | 30885.6 |  | 1 | 14 | 142
1406-119 | Join straight sections w/2 end loops | 15795 | 15795 |  | 1 | 14 | 142
1406-119 | Join straight sections w/2 end loops | 15795 | 15795 |  | 1 | 14 | 142
1406-120 | Wind Conductor | 18432 | 18432 |  | 1 | 14 | 142
1406-150 | Winding pack assy | 1177.92 | 1177.92 |  | 1 | 14 | 142
1406-151 | Lead ends & closure | 1177.92 | 1177.92 |  | 1 | 14 | 142
1406-152 | Terminal Assy | 1177.92 | 1177.92 |  | 1 | 14 | 142
1406-153 | VPI mold assy | 1177.92 | 1177.92 |  | 1 | 14 | 142
1406-154 | Clamp assy | 1177.92 | 1177.92 |  | 1 | 14 | 142
1406-155 | Cooling ,electr schematics | 1177.92 | 1177.92 |  | 1 | 14 | 142
1406-156 | I&C dwgs | 1177.92 | 1177.92 |  | 1 | 14 | 142
1406-210 | Dogbone test @RT | 1339.92 | 1339.92 |  | 1 | 14 | 142
1406-50 | Fab Straight Tee Specimen | 8601.6 | 8601.6 |  | 1 | 14 | 142
1406-50 | Fab Straight Tee Specimen | 8601.6 | 8601.6 |  | 1 | 14 | 142
1406-51 | VPI Tee specimen | 3840 | 3840 |  | 1 | 14 | 142
1406-51 | VPI Tee specimen | 3840 | 3840 |  | 1 | 14 | 142
1406-52 | Ship Tee specimen to ORNL | 637 | 637 |  | 1 | 14 | 142
1406-54 | Complete shear modulus & cyclic testing | 15163.2 | 15163.2 |  | 1 | 14 | 142
1406-54 | Complete shear modulus & cyclic testing | 16796 | 16796 |  | 1 | 14 | 142
1406-54 | Complete shear modulus & cyclic testing | 318.5 | 318.5 |  | 1 | 14 | 142
1406-55 | Fab chill plate specimens | 4608 | 4608 |  | 1 | 14 | 142
1406-55 | Fab chill plate specimens | 637 | 637 |  | 1 | 14 | 142
1406-55 | Fab chill plate specimens | 3840 | 3840 |  | 1 | 14 | 142
1406-55 | Fab chill plate specimens | 3840 | 3840 |  | 1 | 14 | 142
1406-56 | test chill plate specimens | 3072 | 3072 |  | 1 | 14 | 142
1406-56 | test chill plate specimens | 3072 | 3072 |  | 1 | 14 | 142
1406-57 | fab cooling tube/chill plate assy | 3072 | 3072 |  | 1 | 14 | 142
1406-57 | fab cooling tube/chill plate assy | 254.8 | 254.8 |  | 1 | 14 | 142
1406-57 | fab cooling tube/chill plate assy | 3072 | 3072 |  | 1 | 14 | 142
1406-58 | fab MC lead braze specimens | 3108.09 | 3108.09 |  | 1 | 14 | 142
1407-001 | Apr-Sep YTD MIE Cost PPPL | 267550 | 267550 |  | 1 | 14 | 144
1407-002 | Winding Facility, Tooling, Materials Oversight | 61226.7 | 61226.7 |  | 1 | 14 | 144
1407-002 | Winding Facility, Tooling, Materials Oversight | 47911.5 | 47911.5 |  | 1 | 14 | 144
1407-002 | Winding Facility, Tooling, Materials Oversight | 61066 | 61066 |  | 1 | 14 | 144
1407-003 | Winding Facility, Tooling, Design | 115614.8 | 115614.8 |  | 1 | 14 | 144
1407-003.1 | Facility Drawings | 10520 | 10520 |  | 1 | 14 | 144
1407-003.2 | Final Drawings for winding clamps | 8416 | 8416 |  | 1 | 14 | 144
1407-003.3 | Final Drawings -type C casting supports | 4208 | 4208 |  | 1 | 14 | 144
1407-003.4 | Final Drawings -casting to ring fixture | 6732.8 | 6732.8 |  | 1 | 14 | 144
1407-003.5 | Final Drawings -Type A casting supports | 6732.8 | 6732.8 |  | 1 | 14 | 144
1407-003.6 | Final Drawings -Type B casting supports | 8416 | 8416 |  | 1 | 14 | 144
1407-003.7 | Final Drawings -casting stud fixture | 2524.8 | 2524.8 |  | 1 | 14 | 144
1407-003.8 | Misc Drawings (ecn's etc) | 12624 | 12624 |  | 1 | 14 | 144
1407-003.9 | Electrical design support/oversight | 10520 | 10520 |  | 1 | 14 | 144
1407-005 | Domes & cylinder Fab & Deliver (PE4226) | 20167.42 | 20167.42 |  | 1 | 14 | 144
1407-006.2 | Blower/Elec HW- Fab & Deliver (PE 4218) | 509.6 | 509.6 |  | 1 | 14 | 144
1407-008 | Remaining Autoclave components-Deliver | 11466 | 11466 |  | 1 | 14 | 144
1407-011 | Fabricate Autoclave | 30326.4 | 30326.4 |  | 1 | 14 | 144
1407-011 | Fabricate Autoclave | 132710.4 | 132710.4 |  | 1 | 14 | 144
1407-011.1 | Autoclave assembly | 9216 | 9216 |  | 1 | 14 | 144
1407-011.1 | Autoclave assembly | 9216 | 9216 |  | 1 | 14 | 144
1407-011.2 | Rebuild vacuum pumps (2) | 9216 | 9216 |  | 1 | 14 | 144
1407-011.2 | Rebuild vacuum pumps (2) | 9216 | 9216 |  | 1 | 14 | 144
1407-012 | Autoclave PTP | 3072 | 3072 |  | 1 | 14 | 144
1407-012 | Autoclave PTP | 3072 | 3072 |  | 1 | 14 | 144
1407-012 | Autoclave PTP | 2524.8 | 2524.8 |  | 1 | 14 | 144
1407-100 | Fabricate turning fixtures and coil supports | 63700 | 63700 |  | 1 | 14 | 144
1407-100 | Fabricate turning fixtures and coil supports | 31590 | 31590 |  | 1 | 14 | 144
1407-100 | Fabricate turning fixtures and coil supports | 149760 | 149760 |  | 1 | 14 | 144
1407-100.2 | Fabr turning fixt&coil supports **2nd line** | 19110 | 19110 |  | 1 | 14 | 144
1407-100.2 | Fabr turning fixt&coil supports **2nd line** | 7371 | 7371 |  | 1 | 14 | 144
1407-100.2 | Fabr turning fixt&coil supports **2nd line** | 104832 | 104832 |  | 1 | 14 | 144
1407-100.3 | Fab & Instl Turning Fixt 2,3&4 | 41698.8 | 41698.8 |  | 1 | 14 | 144
1407-100.3 | Fab & Instl Turning Fixt 2,3&4 | 134784 | 134784 |  | 1 | 14 | 144
1407-100.4 | Electr hookup turning fixtures 2,3&4 | 4422.6 | 4422.6 |  | 1 | 14 | 144
1407-100.4 | Electr hookup turning fixtures 2,3&4 | 3225.6 | 3225.6 |  | 1 | 14 | 144
1407-105 | Anchor VPI platforms | 3072 | 3072 |  | 1 | 14 | 144
1407-105 | Anchor VPI platforms | 3072 | 3072 |  | 1 | 14 | 144
1407-106 | Instl electric to VPI platforms & cntrl panel | 12288 | 12288 |  | 1 | 14 | 144
1407-106 | Instl electric to VPI platforms & cntrl panel | 12288 | 12288 |  | 1 | 14 | 144
1407-108 | Mount mixing tanks onto VPI platforms | 1228.8 | 1228.8 |  | 1 | 14 | 144
1407-108 | Mount mixing tanks onto VPI platforms | 1228.8 | 1228.8 |  | 1 | 14 | 144
1407-110 | Fabricate Winding clamp sets (125) | 9555 | 9555 |  | 1 | 14 | 144
1407-110 | Fabricate Winding clamp sets (125) | 26325 | 26325 |  | 1 | 14 | 144
1407-110 | Fabricate Winding clamp sets (125) | 4608 | 4608 |  | 1 | 14 | 144
1407-110.2 | Compl Fabr Winding clamp sets (100 of 400) | 2548 | 2548 |  | 1 | 14 | 144
1407-110.2 | Compl Fabr Winding clamp sets (100 of 400) | 19796.4 | 19796.4 |  | 1 | 14 | 144
1407-110.2 | Compl Fabr Winding clamp sets (100 of 400) | 1536 | 1536 |  | 1 | 14 | 144
1407-115 | Fabricate Conductor payout spool system | 12740 | 12740 |  | 1 | 14 | 144
1407-115 | Fabricate Conductor payout spool system | 15163.2 | 15163.2 |  | 1 | 14 | 144
1407-115 | Fabricate Conductor payout spool system | 66355.2 | 66355.2 |  | 1 | 14 | 144
1407-115.2 | Fabr Conduct payout spool syst ** 2nd line** | 10530 | 10530 |  | 1 | 14 | 144
1407-115.2 | Fabr Conduct payout spool syst ** 2nd line** | 2548 | 2548 |  | 1 | 14 | 144
1407-124 | Fab casting to ring assy fixture station 1 | 21768 | 21768 |  | 1 | 14 | 144
1407-124.5 | Electrical Installations | 21637.6 | 21637.6 |  | 1 | 14 | 144
1407-125 | Fab Type C casting supports (6) sets | 4915.2 | 4915.2 |  | 1 | 14 | 144
1407-125 | Fab Type C casting supports (6) sets | 4915.2 | 4915.2 |  | 1 | 14 | 144
1407-126 | Fab Type A casting supports (6) sets | 3456 | 3456 |  | 1 | 14 | 144
1407-126 | Fab Type A casting supports (6) sets | 3456 | 3456 |  | 1 | 14 | 144
1407-127 | Fab Type B casting supports (6) sets | 1228.8 | 1228.8 |  | 1 | 14 | 144
1407-127 | Fab Type B casting supports (6) sets | 1228.8 | 1228.8 |  | 1 | 14 | 144
1407-128 | Setup facility stations 2&5 | 3072 | 3072 |  | 1 | 14 | 144
1407-128 | Setup facility stations 2&5 | 3072 | 3072 |  | 1 | 14 | 144
1407-128 | Setup facility stations 2&5 | 3072 | 3072 |  | 1 | 14 | 144
1407-128 | Setup facility stations 2&5 | 3072 | 3072 |  | 1 | 14 | 144
1407-130 | Misc tools & equipt FY04 | 25480 | 25480 |  | 1 | 14 | 144
1407-130 | Misc tools & equipt FY04 | 4212 | 4212 |  | 1 | 14 | 144
1407-135 | construct cleanroom mech and electrical | 6144 | 6144 |  | 1 | 14 | 144
1407-135 | construct cleanroom mech and electrical | 6144 | 6144 |  | 1 | 14 | 144
1407-135 | construct cleanroom mech and electrical | 6144 | 6144 |  | 1 | 14 | 144
1407-135 | construct cleanroom mech and electrical | 6144 | 6144 |  | 1 | 14 | 144
1407-200 | Decon TFTR test Cell Crane | 18432 | 18432 |  | 1 | 14 | 144
1407-202 | Setup facility stations | 6121.8 | 6121.8 |  | 1 | 14 | 144
1407-202 | Setup facility stations | 23040 | 23040 |  | 1 | 14 | 144
1407-204 | Build cleanrooms (2) locations | 65280 | 65280 |  | 1 | 14 | 144
1407-204 | Build cleanrooms (2) locations | 27072.5 | 27072.5 |  | 1 | 14 | 144
1407-204.2 | Build cleanroom (1 add'l) **2nd line** | 23040 | 23040 |  | 1 | 14 | 144
1407-204.2 | Build cleanroom (1 add'l) **2nd line** | 9555 | 9555 |  | 1 | 14 | 144
1407-ECP16 | ecp16 | 507000 | 507000 |  | 1 | 14 | 144
1407.002.2 | Winding Facility, Tooling, Materials Oversight | 46281.6 | 46281.6 |  | 1 | 14 | 144
1407.002.2 | Winding Facility, Tooling, Materials Oversight | 21060 | 21060 |  | 1 | 14 | 144
1407.002.2 | Winding Facility, Tooling, Materials Oversight | 46281.6 | 46281.6 |  | 1 | 14 | 144
1407.002.3 | Winding Facility, Tooling, Materials Oversight | 19475.24 | 19475.24 |  | 1 | 14 | 144
1407.011.3 | Fab & Install vacuum lines | 18432 | 18432 |  | 1 | 14 | 144
1407.011.4 | Instl insulation on autoclave | 8601.6 | 8601.6 |  | 1 | 14 | 144
1407.011.4 | Instl insulation on autoclave | 8601.6 | 8601.6 |  | 1 | 14 | 144
1407.011.5 | Write autoclave PTP | 841.6 | 841.6 |  | 1 | 14 | 144
1408-001 | Apr-Sep YTD MIE Cost PPPL | 29790 | 29790 |  | 1 | 14 | 142
1408-141 | Copper Conductor -Spec & Requisition | 2571.2 | 2571.2 |  | 1 | 14 | 142
1409-000 | FY04 Oct-Mar | 58070.4 | 58070.4 |  | 1 | 14 | 144
1409-000 | FY04 Oct-Mar | 230.4 | 230.4 |  | 1 | 14 | 144
1409-000 | FY04 Oct-Mar | 26970.5 | 26970.5 |  | 1 | 14 | 144
1409-000 | FY04 Oct-Mar | 130559.52 | 130559.52 |  | 1 | 14 | 144
1409-025 | Complete Design | 26931.2 | 26931.2 |  | 1 | 14 | 144
1409-032 | Design I2T Protection | 6028 | 6028 |  | 1 | 14 | 144
1409-034 | Fabricate I2T Cards | 12636 | 12636 |  | 1 | 14 | 144
1409-034 | Fabricate I2T Cards | 3159 | 3159 |  | 1 | 14 | 144
1409-040 | Install N2 Ejection Scheme | 12740 | 12740 |  | 1 | 14 | 144
1409-100 | Design Controls Modifications | 9690 | 9690 |  | 1 | 14 | 144
1409-100 | Design Controls Modifications | 27126 | 27126 |  | 1 | 14 | 144
1409-100 | Design Controls Modifications | 9880.8 | 9880.8 |  | 1 | 14 | 144
1409-120 | Install Control Modifications | 12288 | 12288 |  | 1 | 14 | 144
141TITLE2P | PDR #1,4,26 Access,Tolerance Budget,Bolting | 26896.21 | 26896.21 |  | 1 | 14 | 141
1501-109 | Prepare FY 04 WP/WAF | 12856 | 12856 |  | 1 | 15 | 151
1501-113 | Prepare PBR documentation | 6428 | 6428 |  | 1 | 15 | 151
1501-125 | Update drawings & models based on vendor recomm | 6267.3 | 6267.3 |  | 1 | 15 | 151
1501-125 | Update drawings & models based on vendor recomm | 22498 | 22498 |  | 1 | 15 | 151
1501-133 | Prepare a "scope sheet" which defines all interf | 5624.5 | 5624.5 |  | 1 | 15 | 151
161-011 | Final Design Base Support Structure WBS 172 | 0 | 0 |  | 1 | 17 | 172
163-001 | Title I design CS sprt struc | 3474.63 | 3474.63 |  | 1 | 13 | 130
163-001 | Title I design CS sprt struc | 27319 | 27319 |  | 1 | 13 | 130
163-001 | Title I design CS sprt struc | 15909.3 | 15909.3 |  | 1 | 13 | 130
1701-001 | Apr-Sept MIE Costs PPPL | 12180 | 12180 |  | 1 | 17 | 171
1801-001 | Apr-Sept MIE Costs PPPL | 7750 | 7750 |  | 1 | 18 | 181
1801-002 | Apr-Sept MIE Costs ORNL | 53050 | 53050 |  | 1 | 18 | 181
1803-2.05 | Structural / Seismic Analysis check | 0 | 0 |  | 1 | 18 | 186
1803-7.04 | Mike Cole's FY05 on-site involvement in assembly | 0 | 0 |  | 1 | 18 | 186
181.100 | PPPL EM LOE FY04 | 64115.5 | 64115.5 |  | 1 | 18 | 181
181.100 | PPPL EM LOE FY04 | 13832 | 13832 |  | 1 | 18 | 181
181.200 | HP Coverage in the TFTR TC LOE FY04 | 115320 | 115320 |  | 1 | 18 | 181
181.201 | D-Site Shift Supervisor LOE FY04 | 25920.4 | 25920.4 |  | 1 | 18 | 181
1901-002 | Apr-Sept MIE Costs ORNL | 187090 | 187090 |  | 1 | 19 | 191
1901-003 | Apr-Sept MIE Costs PPPL | 67070 | 67070 |  | 1 | 19 | 192
1901-ECP16 | ecp16 | 30000 | 30000 |  | 1 | 19 | 191
191-4 | LOE-FY04 WBS 191-4 Management Activities | 137054.85 | 137054.85 |  | 1 | 19 | 191
191-4 | LOE-FY04 WBS 191-4 Management Activities | 8645 | 8645 |  | 1 | 19 | 191
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 38568 | 38568 |  | 1 | 19 | 192
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 4322.5 | 4322.5 |  | 1 | 19 | 192
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 152368.96 | 152368.96 |  | 1 | 19 | 192
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 10938.65 | 10938.65 |  | 1 | 19 | 192
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 31159.98 | 31159.98 |  | 1 | 19 | 192
192-5 | LOE-FY05 WBS 192-5 VV & Coil Services Integr | 0 | 0 |  | 1 | 19 | 192
192-5 | LOE-FY05 WBS 192-5 VV & Coil Services Integr | 25738 | 25738 |  | 1 | 19 | 192
192-5 | LOE-FY05 WBS 192-5 VV & Coil Services Integr | 10938.65 | 10938.65 |  | 1 | 19 | 192
192-6 | LOE-FY05 WBS 192-6 Integrated Analysis | 0 | 0 |  | 1 | 19 | 192
192-6 | LOE-FY05 WBS 192-6 Integrated Analysis | 44031.8 | 44031.8 |  | 1 | 19 | 192
192-6.07 | Time constant calcs using SPARK | 6428 | 6428 |  | 1 | 19 | 192
192-6.08 | Indep check time constant calcs using EDDYCUFF | 10295.2 | 10295.2 |  | 1 | 19 | 192
192-6.09 | Revised VV geometry | 3214 | 3214 |  | 1 | 19 | 192
192-6.10 | MC interf during assly, geometry, assly trajecto | 19284 | 19284 |  | 1 | 19 | 192
192-6.10 | MC interf during assly, geometry, assly trajecto | 5147.6 | 5147.6 |  | 1 | 19 | 192
192-6.10 | MC interf during assly, geometry, assly trajecto | 9642 | 9642 |  | 1 | 19 | 192
192-6.11 | Range of motion reqts for Assly MC fixture. | 12856 | 12856 |  | 1 | 19 | 192
192-6.11 | Range of motion reqts for Assly MC fixture. | 5147.6 | 5147.6 |  | 1 | 19 | 192
192-6.12 | Final Check & Verification | 3856.8 | 3856.8 |  | 1 | 19 | 192
2001-001 | Apr-May MIE Cost | 35300 | 35300 |  | 2 | 22
2001-100 | PDR Support | 24896 | 24896 |  | 2 | 22
25-099 | FY04 work accomplished | 0 | 0 |  | 2 | 25 | 250
25-099 | FY04 work accomplished | 5047.8 | 5047.8 |  | 2 | 25 | 250
25-099 | FY04 work accomplished | 3609.6 | 3609.6 |  | 2 | 25 | 250
25-099 | FY04 work accomplished | 4841.2 | 4841.2 |  | 2 | 25 | 250
25-099 | FY04 work accomplished | 646 | 646 |  | 2 | 25 | 250
25-190.1 | 33) Fabr BL alignment measur fixture, | 1019.2 | 1019.2 |  | 2 | 25 | 250
25-190.1 | 33) Fabr BL alignment measur fixture, | 646 | 646 |  | 2 | 25 | 250
25-190.1 | 33) Fabr BL alignment measur fixture, | 384 | 384 |  | 2 | 25 | 250
25-225.1 | Cabling-Design & WP Procedures | 4845 | 4845 |  | 2 | 25 | 250
25-230.1 | Cabling-Fabr and Install new Junction Box | 429.6 | 429.6 |  | 2 | 25 | 250
25-230.1 | Cabling-Fabr and Install new Junction Box | 307.2 | 307.2 |  | 2 | 25 | 250
25-310.1 | Drafting Labor Support | 2524.8 | 2524.8 |  | 2 | 25 | 250
2501-001 | Apr-Sept MIE Cost | 146310 | 146310 |  | 2 | 25 | 250
2501-014 | FY04 work accomplished | 64654.8 | 64654.8 |  | 2 | 25 | 250
2501-014 | FY04 work accomplished | 1228.8 | 1228.8 |  | 2 | 25 | 250
2501-014 | FY04 work accomplished | 11147.5 | 11147.5 |  | 2 | 25 | 250
2501-014.1 | FY04 work closeout *TBD* | 753.5 | 753.5 |  | 2 | 25 | 250
2501-014.1 | FY04 work closeout *TBD* | 20406 | 20406 |  | 2 | 25 | 250
2501-014.1 | FY04 work closeout *TBD* | 15974.4 | 15974.4 |  | 2 | 25 | 250
2501-014.1 | FY04 work closeout *TBD* | 2548 | 2548 |  | 2 | 25 | 250
2501-014.1 | FY04 work closeout *TBD* | 4418.4 | 4418.4 |  | 2 | 25 | 250
2501-014.1 | FY04 work closeout *TBD* | 5147.6 | 5147.6 |  | 2 | 25 | 250
361-015 | Fab/Assy/Installation Visible Camera | 0 | 0 |  | 3 | 36
390-001 | LOE Support FY03 | 155450 | 155450 |  | 3 | 39
390-010 | LOE Support FY04 | 31863 | 31863 |  | 3 | 39
390-010 | LOE Support FY04 | 46160.5 | 46160.5 |  | 3 | 39
390-015 | LOE Support FY05 **reduced scope | 0 | 0 |  | 3 | 39
390-015 | LOE Support FY05 **reduced scope | 0 | 0 |  | 3 | 39
390-020 | LOE Support FY06 | 0 | 0 |  | 3 | 39
390-020 | LOE Support FY06 | 0 | 0 |  | 3 | 39
4101-100 | Prepare Preliminary One line diagram | 1514.88 | 1514.88 |  | 4 | 41 | 411
4101-100 | Prepare Preliminary One line diagram | 3255.12 | 3255.12 |  | 4 | 41 | 411
4101-100 | Prepare Preliminary One line diagram | 1546.56 | 1546.56 |  | 4 | 41 | 411
4101-100 | Prepare Preliminary One line diagram | 2180.16 | 2180.16 |  | 4 | 41 | 411
411-3-2.04 | Test Cell AC Power fy04 | 148730 | 148730 |  | 4 | 41 | 411
445-2-0 | Overload Protection & Cabling-Prelim Dsn | 1054.9 | 1054.9 |  | 4 | 44 | 445
4501-001 | Apr-Sept MIE Cost | 112340 | 112340 |  | 4 | 45 | 451
4501-100 | Design Drawings | 1788.4 | 1788.4 |  | 4 | 45 | 451
4501-100 | Design Drawings | 22152.9 | 22152.9 |  | 4 | 45 | 451
451-7-2 | FDR DC transmission-Dsn | 4208 | 4208 |  | 4 | 45 | 451
451-7-2 | FDR DC transmission-Dsn | 6028 | 6028 |  | 4 | 45 | 451
4601-001 | Apr-Sept MIE Cost | 1300 | 1300 |  | 4 | 46 | 460
51-00 | FY03 | 11900 | 11900 |  | 5 | 51
51-01 | FY04 LOE support | 12358.2 | 12358.2 |  | 5 | 51
55-30 | Installation, Testing, Documentation (Title III) | 0 | 0 |  | 5 | 55
632-001 | Preliminary Design**deleted scope | 0 | 0 |  | 6 | 62 | 622
632-010 | Final Design**deleted scope | 0 | 0 |  | 6 | 62 | 622
632-010 | Final Design**deleted scope | 0 | 0 |  | 6 | 62 | 622
65-03 | LOE WBS 6 | 16070 | 16070 |  | 6 | 65 | 650
65-03 | LOE WBS 6 | 16150 | 16150 |  | 6 | 65 | 650
6501-001 | Apr-Sept MIE Cost PPPL | 9380 | 9380 |  | 6 | 65 | 612
7101-000 | Apr-Sept MIE Cost PPPL | 32150 | 32150 |  | 7 | 71 | 740
711A.020 | LOE FY04 | 139374.5 | 139374.5 |  | 7 | 74 | 741
711A.020 | LOE FY04 | 10520 | 10520 |  | 7 | 74 | 741
740.010 | Final Design Measurement systems | 69422.4 | 69422.4 |  | 1 | 18 | 187
740.030 | Deliver 3-D Scanner & Romer Arm | 171990 | 171990 |  | 1 | 18 | 187
740.045 | Purchase- second Faro Arm PE005330 | 76395 | 76395 |  | 1 | 18 | 187
7401-001 | Apr-Sept MIE Cost PPPL | 131680 | 131680 |  | 7 | 74 | 741
7502-000 | Outlet Design | 25272 | 25272 |  | 7 | 74 | 740
7502-011 | Cable Removal in test cell (S04335-32) | 9937.2 | 9937.2 |  | 7 | 74 | 740
7502-025 | TC Floor penetration covers | 16848 | 16848 |  | 7 | 74 | 740
810.001 | Apr-Sept MIE Cost PPPL | 387340 | 387340 |  | 8 | 81 | 810
810.002 | Project Management Office PPPL FY04 | 314964.9 | 314964.9 |  | 8 | 81 | 810
810.002 | Project Management Office PPPL FY04 | 116864.8 | 116864.8 |  | 8 | 81 | 810
810.002 | Project Management Office PPPL FY04 | 28285.92 | 28285.92 |  | 8 | 81 | 810
810.002 | Project Management Office PPPL FY04 | 13832 | 13832 |  | 8 | 81 | 810
810.002 | Project Management Office PPPL FY04 | 20638.8 | 20638.8 |  | 8 | 81 | 810
810.002 | Project Management Office PPPL FY04 | 189794.8 | 189794.8 |  | 8 | 81 | 810
810.002 | Project Management Office PPPL FY04 | 5000 | 5000 |  | 8 | 81 | 810
810.009 | PDR Support | 35888.58 | 35888.58 |  | 8 | 81 | 810
810.009 | PDR Support | 5274.5 | 5274.5 |  | 8 | 81 | 810
810.101 | Apr-Sept MIE Cost ORNL | 58600 | 58600 |  | 8 | 81 | 810
810.102 | Project Management Office ORNL FY04 | 61454.28 | 61454.28 |  | 8 | 81 | 810
810.102 | Project Management Office ORNL FY04 | 51491.14 | 51491.14 |  | 8 | 81 | 810
810.102 | Project Management Office ORNL FY04 | 3121.2 | 3121.2 |  | 8 | 81 | 810
810.102 | Project Management Office ORNL FY04 | 4161.6 | 4161.6 |  | 8 | 81 | 810
810.104X | Project Management Office ORNL FY06 | 0 | 0 |  | 8 | 81 | 810
810.901 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
810.980 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
810.981 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
810.982 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
810.983 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
810.984 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
810.985 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
810.986 | Project Management Office ORNL 1 mo SO | 0 | 0 |  | 8 | 81 | 810
820.002 | LOE FY04 | 235746.9 | 235746.9 |  | 8 | 82 | 820
820.002 | LOE FY04 | 13832 | 13832 |  | 8 | 82 | 820
820.002 | LOE FY04 | 97546 | 97546 |  | 8 | 82 | 820
820.002 | LOE FY04 | 6837 | 6837 |  | 8 | 82 | 820
820.002 | LOE FY04 | 38220 | 38220 |  | 8 | 82 | 820
820.002 | LOE FY04 | 234569.4 | 234569.4 |  | 8 | 82 | 820
820.110 | Apr-Sept MIE Cost PPPL | 295530 | 295530 |  | 8 | 82 | 820
820.150 | Apr-Sept MIE Cost PPPL | 178750 | 178750 |  | 8 | 82 | 820
820.173 | Apr-Sept MIE Cost PPPL | 44620 | 44620 |  | 8 | 82 | 820
820.174 | LOE FY04 | 150254.5 | 150254.5 |  | 8 | 82 | 820
820.200 | LOE FY04 | 166485.2 | 166485.2 |  | 8 | 82 | 820
820.200 | LOE FY04 | 90787.6 | 90787.6 |  | 8 | 82 | 820
8202-ECP16 | ecp16 | 68000 | 68000 |  | 8 | 82 | 820
8203-ECP16 | ecp16 | 125000 | 125000 |  | 8 | 82 | 820
8204.01 | Assess magnetic material in test cell | 38568 | 38568 |  | 8 | 82 | 820
8204.02 | Model effects local high MU regions on MCWF | 19284 | 19284 |  | 8 | 82 | 820
840.201 | Apr-Sept MIE Cost PPPL | 210270 | 210270 |  | 8 | 84 | 840
840.202 | Project Physics/Engr Analysis FY04 | 94255.2 | 94255.2 |  | 8 | 84 | 840
840.202 | Project Physics/Engr Analysis FY04 | 3822 | 3822 |  | 8 | 84 | 840
840.202 | Project Physics/Engr Analysis FY04 | 1729 | 1729 |  | 8 | 84 | 840
840.301 | Apr-Sept MIE Cost ORNL | 40980 | 40980 |  | 8 | 84 | 840
840.302 | Project Physics/Engr Analysis FY04 | 61110.96 | 61110.96 |  | 8 | 84 | 840
920.000 | Startup Personnel | 0 | 0 |  | 8 | 85
99.03 | Apr-Sept MIE Cost PPPL | 60670 | 60670 |  | A | AA | AAA
99.04 | PPPL Allocations FY04 | 265920.2 | 265920.2 |  | A | AA | AAA
EXFAC001.2 | Complete Crane Modifications (S04354) | 37608.48 | 37608.48 |  | 7 | 74 | 740
PPC-1 | Engr & Flow Solidification | 21570 | 21570 |  | 1 | 14 | 141
|  | 20832353.5668 | 73150026.54