## Sheet1
JJJJ | ACT ID |  | OCT FY05 | NOV FY05 | DEC FY05 | JAN FY05 | FEB FY05 | MAR FY05 | APR FY05 | MAY FY05 | JUN FY05 | JUL FY05 | AUG FY05 | SEP FY05 | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08
1404 - Job:1404-MCWF R&D & 1st Prod Casting-HEITZENROED | EM//TB | 0 | 0
1406 - Job: 1406 - Mod. Coil Winding R&D-CHRZANOWSKI | EE//SM | 0
1406 - Job: 1406 - Mod. Coil Winding R&D-CHRZANOWSKI | EM//SM | 0.7 | 0.4 | 0.3
1406 - Job: 1406 - Mod. Coil Winding R&D-CHRZANOWSKI | EM//TB | 0.1 | 0.1
1410 - Job: 1410 MC Twisted Racetrack Fabr-CHRZANOWSKI | EE//SM | 0.3 | [7 empty] | 0.3
1410 - Job: 1410 MC Twisted Racetrack Fabr-CHRZANOWSKI | EE//TB | 0.4 | [7 empty] | 0.4
1410 - Job: 1410 MC Twisted Racetrack Fabr-CHRZANOWSKI | EM//SM | 4.2 |  | 0.7 | 0.6 | 0.7 | 0.7 | 0.8 | 0.7
1410 - Job: 1410 MC Twisted Racetrack Fabr-CHRZANOWSKI | EM//TB | 14.6 |  | 1.7 | 2.3 | 3.9 | 1.1 | 1.2 | 2.3 | 2.1
1407 - Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | EE//SM | 0
1407 - Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | EM//SM | 0
1407 - Job: 1407 -Mod Coil Winding Facility-CHRZANOWSKI | EM//TB | 0
1412 - Job: 1412 - Complete Winding Facilities-CHRZANOW | EM//SM | 8.1 | 0.8 | 0.8 | 0.6 | 1.6 | 2.2 | 0.8 | 0.7 | 0.6
1412 - Job: 1412 - Complete Winding Facilities-CHRZANOW | EM//TB | 9 | 2.3 | 2.9 | 0.5 | 0.8 | 1.9 | 0.2 | 0.2 | 0.2
1408 - Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | EM//SM | 27.1 |  |  |  |  | 0.6 | 1.3 | 1.2 | 1.2 | 1.2 | 1.1 | 1.3 | 1.1 | 1.3 | 1.3 | 1.1 | 1.4 | 1.3 | 1.5 | 2.6 | 2.2 | 1.9 | 1.6 | 1.9
1408 - Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | EM//TB | 15.3 |  |  |  | 1 | 1 | 1.1 | 1.5 | 1.6 | 1.5 | 0.4 | 0.5 | 0.4 | 0.4 | 0.3 | 0.3 | 0.4 | 0.3 | 0.4 | 0.8 | 0.9 | 0.9 | 0.5 | 0.5 | 0.4 | 0.2
1409 - Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | EE//SM | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
1409 - Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | EM//SM | 1.2 | 0.4 | 0.4 | 0.3 | 0.1
1409 - Job: 1409 - Mod. Coil Test Stand-GETTELFINGER | EM//TB | 2.1 | 0.7 | 0 |  | 0.1 | 0.6 | 0.4 | 0.3
1431 - Job: 1431 - Modular Coil Local I&C | EM//SM | 1.1 | [15 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0.7 | 0.4
1431 - Job: 1431 - Modular Coil Local I&C | EM//TB | 3.6 | [27 empty] | 2.3 | 1.3
1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | EE//SM | 2.3 | [14 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0
1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | EE//TB | 8.1 | [14 empty] | 0.2 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0.6 | 0.8 | 0.7 | 0.7 | 0.7 | 0.1
1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | EM//SM | 14 | [7 empty] | 0.4 | 0.8 | 0.7 | 0.8 | 0.8 | 0.8 | 0.7 | 0.6 | 0.8 | 0.7 | 0.8 | 0.7 | 0.8 | 0.8 | 0.7 | 0.8 | 0.7 | 0.8 | 0.7 | 0.1
1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | EM//TB | 228 | [7 empty] | 6 | 12 | 10.9 | 12.5 | 11.4 | 11.4 | 10.9 | 9.7 | 12.8 | 12.2 | 14 | 12.2 | 13.4 | 13.4 | 11.6 | 14 | 12.2 | 13.4 | 12.2 | 1.8
- | EE//SM | 16.9 | [15 empty] | 0.1 | 0.2 | 0.2 | 0.1 |  |  |  |  | 0.1 | 1 | 1.1 | 0.9 | 1 | 1.1 | 1.3 | 1.9 | 2.4 | 1.7 | 1.5 | 1.6 | 0.7
- | EM//SM | 7.8 | [15 empty] | 0.1 | 0.1 | 0.1 | 0 |  |  |  | 0.3 | 0.2 | 0.2 | 0.2 | 0.4 | 0.6 | 1 | 1.3 | 1.3 | 1.3 | 0.4 | 0.2 | 0.1 | 0
- | EM//TB | 19.2 | [24 empty] | 0.2 | 0.2 | 0.7 | 1.7 | 1.2 | 1 | 2.7 | 3.5 | 2.8 | 2.7 | 2.2 | 0.3
1202 - Job: 1202 - Vacuum Vessel R&D - DUDEK | EM//SM | 0
1202 - Job: 1202 - Vacuum Vessel R&D - DUDEK | EM//TB | 0
1204 - Job:1204-VV Sys Procurements (non VVSA)-GORANSON | EM//SM | 0.2 | [14 empty] | 0 | 0.1 | 0.1 | [7 empty] | 0 | 0
1204 - Job:1204-VV Sys Procurements (non VVSA)-GORANSON | EM//TB | 0.8 | [14 empty] | 0.2 | 0.4 | 0.2
1206 - Job: 1206 - VV Field Weld Joint R&D-DUDEK | EM//SM | 0.9 |  | 0.2 | [5 empty] | 0.1 | 0.6
1206 - Job: 1206 - VV Field Weld Joint R&D-DUDEK | EM//TB | 0.1 |  | 0.1
1301 - Job: 1301 - TF Design-KALISH | EM//SM | 0.8 |  | 0.3 | 0.5
1351 - Job: 1351 - TF Coil Procurement-KALISH | EM//TB | 7.2 | [13 empty] | 1.3 | 0.8 | 0.6 | 0.6 | 0.3 | 0.6 | 0.3 | 0.6 | 0.3 | 0.6 | 0.5 | 0.4 | 0.3
1355 - Job: 1355 - WBS 13 I&C Proc & Coil Assy-KALISH | EM//SM | 0.7 | [24 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
1355 - Job: 1355 - WBS 13 I&C Proc & Coil Assy-KALISH | EM//TB | 4.6 | [24 empty] | 0.5 | 0.5 | 0.4 | 0.5 | 0.5 | 0.5 | 0.2 |  |  | 1.5
1550 - Job:1550 - Structures Procurement -KALISH | EM//SM | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1550 - Job:1550 - Structures Procurement -KALISH | EM//TB | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1803 - Job: 1803- FP Assy Toolg/Constructability-BROWN | EM//SM | 0.3 | [24 empty] | 0.1 | 0.1 | 0.1 | 0
1803 - Job: 1803- FP Assy Toolg/Constructability-BROWN | EM//TB | 1.6 | [24 empty] | 0.5 | 0.5 | 0.4 | 0.2
1804 - Job: 1804-FP Assy Measurement Sys-RAFTOPOULOS | EM//SM | 1 | [12 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
1804 - Job: 1804-FP Assy Measurement Sys-RAFTOPOULOS | EM//TB | 2.3 | [12 empty] | 0.5 | 0.5 | 0.4 | 0.5 | 0.4
1808 - 1808 - TF/Mod Coil Sub-Assembly-VIOLA | EM//SM | 4.5 | [14 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.8 | 1.1 | 0.5 | 0.6 | 0.1 | 0.1 | 0.6 | 0.1
1808 - 1808 - TF/Mod Coil Sub-Assembly-VIOLA | EM//TB | 46.1 | [14 empty] | 0.2 | 0.3 | 0.3 | 0.3 | 3.1 | 2.5 | 3.1 | 4.1 | 5.3 | 6.6 | 4.3 | 8.2 | 6.5 | 1.3
1810 - Job:1810 - Field Period Assembly-VIOLA | EM//TB | 107.5 | [14 empty] | 2.3 | 4.1 | 3.5 | 4.9 | 2.9 | 6.1 | 3.6 | 4 | 3.7 | 6 | 9.8 | 6.4 | 7.1 | 11.3 | 17.6 | 9.5 | 4.7
1901 - Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | EM//SM | 0.6 | [7 empty] | 0.2 | 0.3 | 0.1
2501 - Job: 2501 - Neutral Beam Refurbishment-STEVENSON | EE//SM | 0
2501 - Job: 2501 - Neutral Beam Refurbishment-STEVENSON | EE//TB | 0
2501 - Job: 2501 - Neutral Beam Refurbishment-STEVENSON | EM//TB | 0
3101 - Job: 3101 Magnetic Diagnostics | EE//SM | 3.6 | [11 empty] | 0.1 | 1 | 1 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3
3101 - Job: 3101 Magnetic Diagnostics | EE//TB | 0 | [11 empty] | 0 | 0 | 0 | 0
3101 - Job: 3101 Magnetic Diagnostics | EM//SM | 2.9 | [12 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.1
4101 - Job: 4101 - AC Power-RAMAKRISHNAN | EE//SM | 2.2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.8 | 0.7 | 0.2 | 0.2
4101 - Job: 4101 - AC Power-RAMAKRISHNAN | EE//TB | 5.7 | [12 empty] | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.4 | 0.3 | 1.6 | 1.4 | 0.5 | 0.4
4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | EE//SM | 2.9 |  | 0.5 | 0.4 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3
4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | EE//TB | 5.2 |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.6 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6
4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | EE//SM | 12.9 | [12 empty] | 0.2 | 0.3 | 0.3 | 0.9 | 1 | 1.1 | 1 | 1.2 | 1.9 | 1.1 | 0.7 | 0.4 | 0.8 | 0.6 | 0.3 | 0.7 | 0.2 | 0.1 | 0.1
4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | EE//TB | 8.9 | [16 empty] | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 2.3 | 2 | 1.2 | 1.6 | 0.3 | 0.1 | 0.1
4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | EE//SM | 2.9 | [24 empty] | 0.2 | 0.2 | 0.1 | 0.5 | 0.4 | 0.6 | 0.6 | 0.3
4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | EE//TB | 8.7 | [24 empty] | 1.2 | 1.1 | 0.9 | 1.5 | 1.3 | 1.1 | 1.1 | 0.5
7201 - Job: 7201 - Control Room Walls&Floors-PERRY | EE//SM | 0.1 |  |  |  |  | 0.1 | 0
7201 - Job: 7201 - Control Room Walls&Floors-PERRY | EE//TB | 2 |  |  |  | 1.7 | 0.3
7201 - Job: 7201 - Control Room Walls&Floors-PERRY | EM//TB | 0.5 |  |  |  |  | 0.4 | 0.1
7301 - Job: 7301 - Platform Design & Fab-PERRY | EM//TB | 2.2 |  |  |  |  | 0.7 | 0.8 | 0.7 | 0
7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | EE//SM | 2.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | EM//SM | 15.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.8 | 0.8 | 0.6 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.9 | 0.7 | 0.9 | 0.8 | 0.7 | 1.1
7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | EM//TB | 2.2 |  |  |  |  | 0.8 | [7 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.1
7501 - 7501 - Construction Support Crew | EM//SM | 16.9 | [24 empty] | 1.3 | 1.2 | 0.9 | 1.3 | 1.2 | 1.3 | 1.2 | 1.3 | 1.2 | 1.2 | 1.5 | 1.9 | 1.4
7501 - 7501 - Construction Support Crew | EM//TB | 50 | [24 empty] | 3.3 | 3 | 2.4 | 3.3 | 3 | 3.3 | 3.1 | 3.3 | 3.1 | 3.1 | 3.8 | 4.9 | 3.5 | 2.7 | 2.5 | 1.7
7502 - 7502 - Test Cell Facility Preparations | EM//SM | 2.3 | [12 empty] | 0.5 | 0.5 | 0.3 | 0.4 | 0.3 | 0.3 | 0
7503 - 7503 - Machine Assembly | EM//SM | 13.8 | [24 empty] | 1.1 | 1 | 0.7 |  | 0.1 | 1.3 | 0.1 | 1 | 1.1 | 1.8 | 3.2 | 1 | 1.2 | 0.2
7503 - 7503 - Machine Assembly | EM//TB | 59.7 | [24 empty] | 4.4 | 4 | 2.6 |  | 0.2 | 5 | 0.4 | 4.4 | 6.3 | 9.6 | 12.6 | 3.8 | 5.2 | 1.2
7601 - Job: 7601 - Tooling Design & Fabrication | EM//SM | 0 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7601 - Job: 7601 - Tooling Design & Fabrication | EM//TB | 0.7 | [21 empty] | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0 | 0
8501 - Job: 8501 - Intergated System Testing | EE//SM | 0
8501 - Job: 8501 - Intergated System Testing | EE//TB | 5.4 | [35 empty] | 0.8 | 1.7 | 1.5 | 1.1 | 0.3
8501 - Job: 8501 - Intergated System Testing | EM//SM | 17.9 | [24 empty] | 0.6 | 0.9 | 0.8 | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1.8 | 2.5 | 1.7 | 1.3 | 0.3
8501 - Job: 8501 - Intergated System Testing | EM//TB | 2.9 | [35 empty] | 0.4 | 0.9 | 0.8 | 0.6 | 0.2
|  | 814 | 5 | 8.2 | 5.8 | 10.8 | 11.1 | 7.2 | 7.9 | 13.4 | 16.7 | 13.5 | 15.4 | 14.1 | 18 | 18.7 | 18.4 | 26.1 | 24.3 | 27.3 | 26.1 | 29.6 | 28.5 | 26.6 | 30.3 | 29.4 | 51 | 48.4 | 30.4 | 31.2 | 31.6 | 28.4 | 19.4 | 19.9 | 18.4 | 23.4 | 27.1 | 16.3 | 17.4 | 8.9 | 6.2 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
1410, 1408 |  | Winding Facility and Component Fab | 0 | 2.4 | 2.9 | 5.6 | 3.4 | 4.4 | 5.7 | 5.6 | 2.7 | 1.5 | 1.8 | 1.5 | 1.7 | 1.6 | 1.4 | 1.8 | 1.6 | 1.9 | 3.4 | 3.1 | 2.8 | 2.1 | 2.4 | 0.4 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1451 |  | MC Winding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4 | 12.8 | 11.6 | 13.3 | 12.2 | 12.2 | 11.6 | 10.6 | 14.5 | 13.8 | 15.8 | 13.8 | 15.1 | 15.1 | 13.1 | 15.8 | 13.8 | 15.1 | 13.8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18081810 |  | Field Period Assy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 4.5 | 3.9 | 5.3 | 6.1 | 8.7 | 7.5 | 9.2 | 9.5 | 13.2 | 14.2 | 14.7 | 14.2 | 12.7 | 17.6 | 9.5 | 4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
750375018501 |  | Machine Assy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.3 | 0.4 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 10.1 | 7.4 | 5.6 | 5.4 | 11.9 | 5.8 | 11 | 12.7 | 16.7 | 22.2 | 14.6 | 16.4 | 8.1 | 5.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | 5 | 5.8 | 2.9 | 5.2 | 7.7 | 2.8 | 2.2 | 1.4 | 1.2 | 0.4 | 0.3 | 0.4 | 3.6 | 5 | 3.5 | 4.9 | 4.7 | 4 | 2.8 | 2.7 | 3.1 | 2.2 | 2.6 | 2 | 10.8 | 9.8 | 6.8 | 12.9 | 8.6 | 7 | 8.9 | 8.9 | 5.7 | 6.7 | 4.9 | 1.7 | 1 | 0.8 | 0.7 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 5 | 8.2 | 5.8 | 10.8 | 11.1 | 7.2 | 7.9 | 13.4 | 16.7 | 13.5 | 15.4 | 14.1 | 18 | 18.7 | 18.4 | 26.1 | 24.3 | 27.3 | 26.1 | 29.6 | 28.5 | 26.6 | 30.3 | 29.4 | 51 | 48.4 | 30.4 | 31.2 | 31.6 | 28.4 | 19.4 | 19.9 | 18.4 | 23.4 | 27.1 | 16.3 | 17.4 | 8.9 | 6.2 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
|  | Winding Facility and Component Fab | 1.7667 | 1.7667 | 3.6333 | 3.9667 | 4.4667 | 4.5 | 5.2333 | 4.6667 | 3.2667 | 2 | 1.6 | 1.6667 | 1.6 | 1.5667 | 1.6 | 1.6 | 1.7667 | 2.3 | 2.8 | 3.1 | 2.6667 | 2.4333 | 1.6333 | 1 | 0.2 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MC Winding | 0 | 0 | 0 | 0 | 0 | 0 | 2.1333 | 6.4 | 10.2667 | 12.5667 | 12.3667 | 12.5667 | 12 | 11.4667 | 12.2333 | 12.9667 | 14.7 | 14.4667 | 14.9 | 14.6667 | 14.4333 | 14.6667 | 14.2333 | 14.9 | 14.2333 | 10.3 | 5.2667 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Field Period Assy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86667 | 2.3667 | 3.6667 | 4.5667 | 5.1 | 6.7 | 7.4333 | 8.4667 | 8.7333 | 10.6333 | 12.3 | 14.0333 | 14.3667 | 13.8667 | 14.8333 | 13.2667 | 10.6 | 4.7333 | 1.5667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machine Assy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.33333 | 0.43333 | 0.4 | 0.33333 | 0.33333 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 3.5667 | 6.9333 | 9.4 | 7.7 | 6.1333 | 7.6333 | 7.7 | 9.5667 | 9.8333 | 13.4667 | 17.2 | 17.8333 | 17.7333 | 13.0333 | 10 | 5.3667 | 2.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other | 4.5667 | 4.5667 | 4.6333 | 5.2667 | 5.2333 | 4.2333 | 2.1333 | 1.6 | 1 | 0.63333 | 0.36667 | 1.4333 | 3 | 4.0333 | 4.4667 | 4.3667 | 4.5333 | 3.8333 | 3.1667 | 2.8667 | 2.6667 | 2.6333 | 2.2667 | 5.1333 | 7.5333 | 9.1333 | 9.8333 | 9.4333 | 9.5 | 8.1667 | 8.2667 | 7.8333 | 7.1 | 5.7667 | 4.4333 | 2.5333 | 1.1667 | 0.83333 | 0.86667 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P3
RES | RESOURCE |  |  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| B///CB | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.5 | 0.5 | 0.6 | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.5 | 0.4 | 0.6 | 0.5 | 0.6 | 0.5 | 0.6 | 0.6 | 0.5 | 0.6 | 0.5 | 0.5 | 0.4 | 0.3 | 0.5 | 0.4 | 0.5 | 0.4 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.2 | 0.2 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| EA//EM | 4.8 | 4.8 | 4.8 | 4.8 | 7.1 | 5.2 | 8.7 | 6.8 | 6.6 | 5.7 | 5.7 | 7.6 | 6.6 | 6.5 | 5.9 | 6.1 | 5.6 | 6 | 6 | 5.3 | 6.1 | 4.9 | 5.5 | 5.2 | 4.9 | 6 | 5.3 | 5.2 | 4.6 | 2.3 | 2.4 | 2 | 2.7 | 2 | 2 | 1.6 | 1.7 | 1.3 | 0.7 | 0.5 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| EA//SM | 1.4 | 1.4 | 1.4 | 1.4 | 3.9 | 3.4 | 4.3 | 3.7 | 3.8 | 2.4 | 3.6 | 3 | 2.8 | 2 | 1.2 | 5 | 5 | 4.1 | 4.5 | 2.5 | 2.1 | 1.6 | 1.5 | 1.4 | 1.3 | 1.4 | 1.2 | 2.8 | 2.6 | 1.5 | 1.4 | 1.1 | 1 | 0.8 | 0.7 | 0.5 | 0.5 | 0.6 | 0.5 | 0.4 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3
| EC//EM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0.1 | 1.1 | 1 | 2.4 | 2.3 | 1.9 | 2.8 | 3 | 3.5 | 3.6 | 4 | 3.6 | 3.1 | 3.4 | 2.4 | 1.4 | 0.8 | 0.6 | 0.2
| EC//SM |  |  |  | J: 0.4; F: 0.8; M: 1.4; A: 1.7; M: 1.8; J: 1.7; J: 1.1; A: 1.2; S: 0.9; O: 0.2
| EE//AM | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| EE//EM |  |  |  |  | 0.6 | 0.6 | 1.1 | 0.8 | 0.9 | 0.7 | 2.5 | 2.3 | 2.1 | 0.7 | 0.1 | 2.7 | 2.6 | 2 | 2.5 | 2 | 1.1 | 0.9 | 1.6 | 1.7 | 1.3 | 1.1 | 0.7 | 1.6 | 1.3 | 0.8 | 2.3 | 1.6 | 1.6 | 1.4 | 1 | 0.1 | 0.1 | 0.1 | 0.4 | 0.9 | 0.8 | 0.6 | 0.2 | 0.1 | 0.1
| EE//SM | 0.2 | 0.2 | 0.2 | 0.2 | 0.6 | 0.6 | 0.4 | 0.4 | 0.2 | 0.1 | 0.4 | 0.1 | 0.1 | 0.1 | 0.2 | 1.7 | 1.7 | 0.9 | 1.8 | 2 | 2.1 | 1.6 | 1.8 | 2.2 | 1.4 | 1.1 | 0.8 | 2.9 | 2.7 | 1.6 | 2.3 | 1.7 | 1.9 | 2.6 | 2.7 | 1.7 | 1.5 | 1.6 | 0.7
| EE//TB | [5 empty] | 0.3 | 2 | 0.6 | 0.3 | 0.1 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.8 | 0.7 | 0.8 | 1.3 | 1.3 | 1.5 | 0.8 | 1 | 1 | 1.1 | 1.4 | 1.2 | 5.8 | 5.2 | 2.7 | 3.5 | 1.7 | 1.2 | 1.2 | 0.5 |  |  |  | 0.8 | 1.7 | 1.5 | 1.1 | 0.3
| EM//EM | 1.6 | 1.6 | 1.6 | 1.6 | 2.7 | 2.8 | 2.1 | 2.1 | 1.6 | 1.4 | 1.7 | 1.9 | 1.4 | 2.1 | 2 | 2.5 | 2.3 | 1.7 | 2.1 | 2 | 2.3 | 2 | 1.8 | 1.5 | 1.3 | 1.9 | 1.6 | 4.1 | 4 | 2.7 | 4 | 3.4 | 3.2 | 3.1 | 3.2 | 3.1 | 2.9 | 2.4 | 2.7 | 3.9 | 2.9 | 2.1 | 1.5 | 1.1 | 1.1 | 1.1 | 1
| EM//SM | 1.7 | 1.7 | 1.7 | 1.7 | 2.5 | 2.1 | 2.6 | 3.5 | 3 | 2.7 | 2.5 | 3 | 2 | 2.2 | 2 | 3.3 | 3.1 | 2.7 | 3.5 | 3.2 | 3.4 | 4 | 3.7 | 3.8 | 3.5 | 3.6 | 1.7 | 5.3 | 5.2 | 4.3 | 4.8 | 4.5 | 5.9 | 4.5 | 5.5 | 4.5 | 5 | 6.7 | 5.4 | 5.9 | 2.7 | 2 | 1.5 | 1.1 | 1.1 | 1.1 | 1
| EM//TB | 3.1 | 3.1 | 3.1 | 3.1 | 4.7 | 2.8 | 5.8 | 6.3 | 3.8 | 5.1 | 9.8 | 13.4 | 11.3 | 13 | 11.8 | 12.6 | 13.2 | 14.1 | 19.3 | 17.8 | 20.2 | 19.7 | 23.2 | 21.6 | 20.6 | 24.2 | 25.8 | 37.1 | 35.3 | 21.9 | 20.6 | 23.8 | 19.4 | 11.2 | 11.2 | 12.2 | 16.9 | 18.7 | 9.4 | 9.6 | 4.6 | 3.1 | 1.8
| FC//AM | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.6 | 0.8 | 0.8 | 0.9 | 0.8 | 0.8 | 0.8 | 0.8 | 0.9 | 0.8 | 0.8 | 0.8 | 0.6 | 0.8 | 0.8 | 0.9 | 0.8 | 0.8 | 0.8 | 0.7 | 0.9 | 0.8 | 0.7 | 0.7 | 0.5 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.8 | 0.6 | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3
| FC//EM | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.6 | 0.6 | 0.7 | 0.6 | 0.6 | 0.7 | 0.6 | 0.7 | 0.6 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5 | 0.4 | 0.5 | 0.5 | 0.4 | 0.5 | 0.4 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0
| ORNL35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ORNL41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNL81
| ORNLAM | 0.1 | 0.1 | 0.1 | O: 0.1; N: 0.1; D: 0.1; J: 0.1; F: 0.1; M: 0.1; A: 0.1; M: 0.1; J: 0.1; J: 0.1; A: 0.1; S: 0.1; O: 0; N: 0; D: 0; J: 0; F: 0; M: 0.1; A: 0; M: 0; J: 0; J: 0; A: 0.1; S: 0
| ORNLEM | 7 | 7 | 7 | 7 | 10 | 7.7 | 7.6 | 5.1 | 4.3 | 3.3 | 3.5 | 4.7 | 2.4 | 2.9 | 2.1 | 2.8 | 2.6 | 3.3 | 3.6 | 3.4 | 4.1 | 3.7 | 4 | 3 | 2.5 | 3.1 | 2.6 | 2.3 | 2 | 1.3 | 1.4 | 1.2 | 1.2 | 1.1 | 1.1 | 1 | 1 | 1.1 | 0.4 | 0.6 | 0.6 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0
| ORNLRM | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| R///RM2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.3 | 0.4 | 0.3 | 0.1 | 0.1 | 0.3 | 0.2 | 0.2 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.1 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 |  |  | 0.4 | 1 | 0.9 | 0.6 | 0.2
| R///RM3 | 1 | 1 | 1 | 1 | 0.9 | 0.8 | 1 | 0.9 | 1 | 1 | 1 | 1 | 0.9 | 1 | 1 | 0.8 | 0.8 | 0.6 | 0.8 | 0.8 | 0.9 | 0.8 | 0.8 | 0.8 | 0.7 | 0.9 | 0.8 | 0.6 | 0.5 | 0.4 | 0.6 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| SH//TB | 0.7 | 0.7 | 0.7 | O: 0.7; N: 0.7; D: 0.6; J: 0.7; F: 0.7; M: 0.7; A: 0.7; M: 0.7; J: 0.7; J: 0.7; A: 0.7; S: 0.7; O: 0.7; N: 0.7; D: 0.6; J: 0.7; F: 0.7; M: 0.8; A: 0.7; M: 0.7; J: 0.7; J: 0.6; A: 0.8; S: 0.7; O: 0
RES |  |  |  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| Techs | 5 | 5 | 5 | 5 | 8.4 | 6.1 | 9.9 | 11 | 7.9 | 8.6 | 15.2 | 18.8 | 15.5 | 16 | 14.1 | 20.3 | 20.6 | 19.7 | 27.1 | 25 | 26.8 | 26.2 | 30.3 | 29.3 | 26.8 | 30 | 29 | 51.9 | 47.5 | 30.6 | 30 | 31.6 | 28.8 | 19.7 | 20.4 | 18.5 | 23.5 | 27.1 | 15.9 | 16.4 | 8.1 | 5.7 | 3.5 | 1.2 | 1.2 | 1.1 | 1
| PPPL Engrs | 6.4 | 6.4 | 6.4 | 6.4 | 10.4 | 8.6 | 11.9 | 9.7 | 9.1 | 7.8 | 9.9 | 11.8 | 10.1 | 9.3 | 8 | 11.3 | 10.5 | 9.7 | 10.6 | 9.3 | 9.5 | 7.8 | 8.9 | 8.4 | 7.6 | 10.1 | 8.6 | 13.3 | 12.2 | 7.7 | 11.5 | 10 | 11 | 10.1 | 10.2 | 8.4 | 7.8 | 7.2 | 6.2 | 6.7 | 4.9 | 3.6 | 2.3 | 1.6 | 1.6 | 1.5 | 1.4
| ORNL Engrs | 7 | 7 | 7 | 7 | 10 | 7.7 | 7.6 | 5.1 | 4.3 | 3.3 | 3.5 | 4.7 | 2.4 | 2.9 | 2.1 | 2.8 | 2.6 | 3.3 | 3.6 | 3.4 | 4.1 | 3.7 | 4 | 3 | 2.5 | 3.1 | 2.6 | 2.3 | 2 | 1.3 | 1.4 | 1.2 | 1.2 | 1.1 | 1.1 | 1 | 1 | 1.1 | 0.4 | 0.6 | 0.6 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
| Total Manpower | 23.9 | 23.9 | 23.9 | 23.9 | 36.1 | 28.9 | 38.7 | 33.3 | 28.9 | 25.7 | 34.4 | 40.7 | 33 | 34 | 29.5 | 41.6 | 40.5 | 38.8 | 48.8 | 43.5 | 47.3 | 42.8 | 47.9 | 45.2 | 41.3 | 49.1 | 45.5 | 72.2 | 67.7 | 42.7 | 48.5 | 47.3 | 45.7 | 35.7 | 36.3 | 32.3 | 36 | 39.5 | 26.7 | 26.9 | 16.1 | 11.6 | 7.7 | 4.3 | 4.3 | 3.9 | 3.6
Total
PPPL Engr
Techs
ORNL Engr