## Sheet1
NCSX Critical Path Summary Schedule
FY02 |  |  |  |  | FY03 | [11 empty] | FY04 | [11 empty] | FY05 | [11 empty] | FY06 | [13 empty] | FY07 | [11 empty] | FY08
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N |  | D | J | F | M | A | M | J | J | A | S |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
| CDR |  |  |  | DOE Milestones
|  | CD-1 | [13 empty] | MC/VV PDR | [5 empty] | CD-2
FY04 D: EIR; FY05 O: CD-3 Start of Fab | [19 empty] | Pumpdown Vac Vsl
[12 empty] | Start of Preliminary Design | [10 empty] | Vac Vsl FDR
Modular Coil FDR
FY04 D: Joule #1 Authorize Protype Fab; FY05 J: Joule #1 Award VVSA,MWCF,Cond | [23 empty] | ORA
[22 empty] | Joule #2 Demonstarte Winding Process on 3-D Surface | [12 empty] | Joule #2 Cmplt Assy TRC
FY04 J: Joule #3 First Prototype Casting Produced for Machining; FY05 J: Joule #3 Mod Coil Winding Type C FDR | [31 empty] | CD-4 Completion of MIE Project
[28 empty] | Joule #4 CD-3 Prereq Complete | [12 empty] | Joule #4 Cmplt Winding First MC
VACUUM VESSEL
[10 empty] | Title I & II Design | [16 empty] | Vessel Award
Manuf Devel
Vessel Fab
MODULAR COILS
Title I & II MCWF
[19 empty] | Title II Design for Winding | [10 empty] | Type C |  |  |  | Type B |  |  | Type A
Twisted Racetrack Fabrication
Component Fabrication
MCWF Manufacturing Development
[16 empty] | Fabricate Prototype Type "C" | [12 empty] | Award Winding Form Contract
Fab Winding Forms
Station 2-Wind & VPI Type C1 C3 A3 A6 B4 C4
Station 3-Wind & VPI Type C2 B1 A4 B2 B5 C5
Station 4-Wind & VPI Type A1 A2 A5 B3 B6 C6
VPI,Clamps,& Test
FY04 O: FIELD PERIOD ASSEMBLY | Attach Cooling,Diag, Insulation
Pre-Assemble Mod Coils
MC Installation
Assemble 1st Period
Assemble 2nd Period
Assemble 3rd Period
FY04 A: MACHINE ASSEMBLY | [8 empty] | Install Supports and Lower PF Coils
Install,align, connect Field Period Assemblies
FY03 O: Legend: | [22 empty] | Pump Down
FY03 O: Completed Task | [20 empty] | Connect to Ancilliary Systems
FY03 O: Critical Paths | [22 empty] | Install Cryostat & PTP
FY03 O: Off critical path | [24 empty] | Startup Testing and E-Beam Mapping
[44 empty] | Ancilliary Systems Installation | [28 empty] | First Plasma
FY02 M: FY02; FY03 O: FY03; FY04 O: FY04; FY05 O: FY05; FY06 O: FY06 | [12 empty] | FY07 | [11 empty] | FY08
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N |  | D | J | F | M | A | M | J | J | A |  | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1
C1 C2 A1 C3 B1 A2 A3 A4 A5 A6 B2 B3 B4 B5 B6 C4 C5 C6