## Sheet1
NCSX Budget Status
Changes to Date
[16 empty] | CD-2 Baseline Jan 04 |  |  | ECP-6 (April 2004) | [7 empty] | ECP 8 Oct 04
[17 empty] | Contingency ETC (From Jan 04) | [12 empty] | Contingency ETC (From Oct 04)
[14 empty] | WBS |  | BAC | $ | % | Changes | BAC | [5 empty] | Potential Increases | EAC | Forecast thru FY04 | ETC | $ | %
[14 empty] | 11 | Limiters | 8 |  |  | -0.4 | 7.6 | [6 empty] | 7.6 | 8 | -0.4 | 0.4
[14 empty] | 12 | Vacuum Vessel | 6065 | 1776.1292 | 38.86% | 835 | 6900 | Approved ECP Changes |  |  |  | Contingency Setaside | 0 | 6900 | 3093 | 3807 | 941.1292 | 24.72%
[14 empty] | 13 | Conventional Coils | 4168 | 1023.3425 | 25.62% | 53 | 4221 | [6 empty] | 4221 | 580 | 3641 | 970.3425 | 26.65%
[14 empty] | 14 | Modular Coils | 20548 | 5822.6763 | 34.35% | -53 | 20495 | WBS 121 Dsn, Weld joint R&D |  |  | 500 | 1776 | 0 | 20495 | 9718 | 10777 | 5875.6763 | 54.52%
[14 empty] | 15 | Structures | 1450 | 441.2795 | 30.66% | -14 | 1436 | WBS 144 MC Fabrication Facility |  |  | 218 | 87 |  | 1436 | 171 | 1265 | 455.2795 | 35.99%
[14 empty] | 16 | Coil Services | 1037 | 248.86 | 24% | 0 | 1037 | WBS 121 VV prototype contracts |  |  | 213 |  |  | 1037 | 0 | 1037 | 248.86 | 24%
[14 empty] | 17 | Cryostat & Base Sprt Struct | 1306 | 365.2385 | 28.31% | -6 | 1300 | WBS 121 Port location dsn |  |  | 75 |  |  | 1300 | 134 | 1166 | 371.2385 | 31.84%
[14 empty] | 18 | Field Period Assembly | 5110 | 1471.0973 | 29.17% | 54 | 5164 | WBS 13 Conv Coil Material Analysis |  |  | 53 |  | 0 | 5164 | 779 | 4385 | 1417.0973 | 32.32%
[14 empty] | 19 | Stellarator Core Mngmt/Integr | 2663 | 328.5676 | 14.68% | 2 | 2665 | WBS 18 FP assy updated dsn est |  |  | 50 |  |  | 2665 | 936 | 1729 | 326.5676 | 18.89%
[14 empty] | 1 | Stellarator Core Systems | 42355 | 11477.1909 | 31.39% | 870.6 | 43225.6 | WBS 121 VV weld joint R&D -full size |  |  | 44 |  | 0 | 43225.6 | 15419 | 27806.6 | 10606.5909 | 38.14%
[14 empty] | 2 | Heating, Fueling & Vac Sys | 1630 | 204.6875 | 14.42% | 63 | 1693 | WBS 141 MCWF port addition impact |  |  | 27 |  |  | 1693 | 531 | 1162 | 141.6875 | 12.19%
[14 empty] | 3 | Diagnostics | 1685 | 399.2023 | 26.63% | 8 | 1693 | WBS 1-8 WAF re-estimates |  |  | 10 |  |  | 1693 | 239 | 1454 | 391.2023 | 26.91%
[14 empty] | 4 | Electrical Power Systems | 5325 | 997.9747 | 19.22% | 6 | 5331 | [6 empty] | 5331 | 1566 | 3765 | 991.9747 | 26.35%
[14 empty] | 5 | Central I&C Systems | 2580 | 243.6191 | 9.547% | -0.3 | 2579.7 | [6 empty] | 2579.7 | 34 | 2545.7 | 243.9191 | 9.582%
[14 empty] | 6 | Facility Systems | 2039 | 391.1473 | 19.41% | 31.6 | 2070.6 |  |  |  | 1190 | 1190 |  | 2070.6 | 31 | 2039.6 | 359.5473 | 17.63%
[14 empty] | 7 | Test Cell Prep/ Machine Assy | 4254 | 788.1555 | 19.5% | -16.7 | 4237.3 | No impacts to project critical path |  |  |  |  | 0 | 4237.3 | 566 | 3671.3 | 804.8555 | 21.92%
[14 empty] | 8 | Project Oversight/Support | 10566 | 1408.0228 | 16.28% | 227.4 | 10793.4 | [5 empty] | 0 | 10793.4 | 4081 | 6712.4 | 1180.6228 | 17.59%
[14 empty] | subtotal |  | 70434 | 15910 | 25.67% | 1189.6 | 71623.6 | [5 empty] | 0 | 71623.6 | 22467 | 49156.6 | 14720.4 | 29.95%
[14 empty] | Contingency |  | 15910 |  |  | -1190 | 14720 | [5 empty] | 0 | 14720
[14 empty] | Pct of ETC |  | 25.67% |  |  |  | 25.47% | [6 empty] | 29.94%
[14 empty] | Total |  | 86344 |  |  |  | 86343.6 | [6 empty] | 86343.6
[14 empty] | Spent |  | 8466 | thru Dec 04 |  | thru Apr 04 | 13830 | [6 empty] | 22460
[14 empty] | ETC |  | 61968 |  |  |  | 57793.6 | [6 empty] | 49163.6
5
[14 empty] | 6 | [6 empty] | 2 - | Plasma Heating, Fueling & Vac Systems |  |  |  | Risk-low | WBS 121 Design
[14 empty] | 6 | [6 empty] | 3 - | Diagnostics |  |  |  | Risk -Moderate | WBS 121 VVSA FFP 20% increase
[14 empty] | 6 | [6 empty] | 4 - | Electrical Power Systems |  |  |  | Risk-High | WBS 142 MC Winding (chill plate instl) | $260 M&S *1.29 + 18 x 2 x 4 x 40 x $72/hr
[14 empty] | 6 | [6 empty] | 5 - | Central I&C Systems |  |  |  | Risk-Moderate | WBS 141 MCWF 20% increase
[14 empty] | 6 | [6 empty] | 6 - | Facility Systems
[14 empty] | 5 | [6 empty] | 7 - | Test Cell Preparation and Machine Assy |  |  |  | - Risk-high | WBS 142 MCWF Prototype Winding
[14 empty] | 6 | [6 empty] | 8 - | Project Oversight and Support |  |  |  | Risk -Moderate | WBS 142 MC winding TRC & conductor testing
[14 empty] | 5 | [11 empty] | - Risk-high | Eliminate design and fab of full size mockups. Use production articles for training.
[14 empty] | 5 | [11 empty] | ? | WBS 18 add'l port installation
[14 empty] | 5 | [11 empty] | 0 | WBS 18 LOE oversight FY04
[19 empty] | 1190 | [6 empty] | Risk-High | WBS 7 TC crane capacity upgrade
[26 empty] | Risk-moderate | WBS 81 Project oversight
[7 empty] | NCSX Budget Status | [18 empty] | Risk-Moderate | WBS 82 Project Engr design & analysis support
Future Changes
0
ECP-6 (April 2004)
[7 empty] | WBS |  | BAC | Change | EAC | Change Candidates
[7 empty] | 11 | Limiters | 7.6 |  | 7.6
[7 empty] | 12 | Vacuum Vessel | 6900 | 300 | 7200 | WBS 121 add'l VV ports | 300
[7 empty] | 13 | Conventional Coils | 4221 |  | 4221
[7 empty] | 14 | Modular Coils | 20495 | 490 | 20985 | WBS 141 MCWF design & analysis | 498
[7 empty] | 15 | Structures | 1436 |  | 1436 | WBS 142 MC winding R&D | 257
[7 empty] | 16 | Coil Services | 1037 |  | 1037 | WBS 142 Eliminate Full Prototype Winding | -265
[7 empty] | 17 | Cryostat & Base Sprt Struct | 1300 |  | 1300
[7 empty] | 18 | Field Period Assembly | 5164 | -160 | 5004 | WBS 18 Eliminate Full mockup procurement | -160
[7 empty] | 19 | Stellarator Core Mngmt/Integr | 2665 |  | 2665
[7 empty] | 1 | Stellarator Core Systems | 43225.6 |  | 43855.6
[7 empty] | 2 | Heating, Fueling & Vac Sys | 1693 |  | 1693 | WBS 82 Design Integration | 80
[7 empty] | 3 | Diagnostics | 1693 |  | 1693 |  | 710
[7 empty] | 4 | Electrical Power Systems | 5331 |  | 5331
[7 empty] | 5 | Central I&C Systems | 2579.7 |  | 2579.7
[7 empty] | 6 | Facility Systems | 2070.6 |  | 2070.6 |  |  |  | Potential Impact on Critical Path;
[7 empty] | 7 | Test Cell Prep/ Machine Assy | 4237.3 |  | 4237.3 |  |  |  | WBS 14 - Impact approx 2 weeks due to mod coil
[7 empty] | 8 | Project Oversight/Support | 10793.4 | 80 | 10873.4 |  |  |  | winding design and component fabrication
[7 empty] | subtotal |  | 71623.6 | 710 | 72333.6
[7 empty] | Contingency |  | 14720 | -710 | 14010
[7 empty] | Cost Thru May |  |  |  | 15338
[7 empty] | ETC |  |  |  | 56995.6
[7 empty] | % on ETC |  |  |  | 24.58%
Cost Risks & Opportunities
(To be quanified as part of September Re-baselining)
|  |  | Est Cost Range |  | Risk Based Contingency | Schedule
| Scheduled | Very Likely | Likely | Unknown | Assessment | Impact?
RISKS
WBS 121 VVSA FFP Proposal | July 04 | >$0 | + $580 (20%) |  | 1160
WBS 141 MCWF FFP Proposal | July 04 | >$0 | + $970 (20%) |  | 1920 | Potential - Maintain option of split order
WBS 121 Removable Port Extensions | FY04 |  | + $150
WBS 142 MC winding R&D | FY04 |  |  | +$ 290 | 223
WBS 82 Design Integration | FY04 |  |  | +$ 150 | 563
WBS 142 MC Winding Fabrication | FY05/06 |  |  | +$750 | 1638 | Potential - Design workshop Scheduled (second shift possible if needed to maintain sched float) | [16 empty] | Managing Cost Pressures
WBS 18 add'l port installation | FY06 |  | +$75 |  | 58
|  | >$0 | +$1,775 | +$ 1,190 | 5562
OPPORTUNITIES
WBS 18 Eliminate design of mockups. | FY04 |  |  | -$39
WBS 187 Eliminate GPS Metrology System | FY05 |  | -$129
WBS 64 Inductive vs He VV heating | FY05 |  |  | - $375
WBS 4 Hybrid Power Supply | FY04/05 |  |  | -1000
|  |  | -$129 | -$1,414
[16 empty] | High = | Change Candidate. Additional scope or task being pereformed. Additional tech complexity. Offsetting savings not apparent. Cost yet to be estimated.
[16 empty] | Moderate = | Probable Change Candidate. Additional scope or task being pereformed. Additional tech complexity. Cost yet to be estimated but may be offset.
[16 empty] | Low = | Current issues but future offsets/controls may limit impact.