## Sheet1
NCSX Budget Status
| CD-2 Baseline Jan 04 |  |  |  |  | ECP 6 April 04 |  | ECP 8 Oct 04
|  | Contingency ETC (From Jan 04) | [8 empty] | Contingency ETC (From Oct 04)
WBS | Budget | $ | % |  | Changes | Budget | Potential Increases | EAC | Cost Forecast thru FY04 | ETC | $ | %
11 | 8 |  |  |  | -0.4 | 7.6 |  | 7.6 | 8 | -0.4 | 0.4
12 | 6065 | 1776.1292 | 38.86% |  | 835 | 6900 | 858 | 7758 | 3093 | 4665 | 83.1292 | 1.782%
13 | 4168 | 1023.3425 | 25.62% |  | 53 | 4221 |  | 4221 | 580 | 3641 | 970.3425 | 26.65%
14 | 20548 | 5822.6763 | 34.35% |  | -53 | 20495 | 2340 | 22835 | 9718 | 13117 | 3535.6763 | 26.95%
15 | 1450 | 441.2795 | 30.66% |  | -14 | 1436 |  | 1436 | 171 | 1265 | 455.2795 | 35.99%
16 | 1037 | 248.86 | 24% |  | 0 | 1037 |  | 1037 | 0 | 1037 | 248.86 | 24%
17 | 1306 | 365.2385 | 28.31% |  | -6 | 1300 |  | 1300 | 134 | 1166 | 371.2385 | 31.84%
18 | 5110 | 1471.0973 | 29.17% |  | 54 | 5164 | -18 | 5146 | 779 | 4367 | 1435.0973 | 32.86%
19 | 2663 | 328.5676 | 14.68% |  | 2 | 2665 |  | 2665 | 936 | 1729 | 326.5676 | 18.89%
1 | 42355 | 11477.1909 | 31.39% |  | 870.6 | 43225.6 | 3180 | 46405.6 | 15419 | 30986.6 | 7426.5909 | 23.97%
2 | 1627 | 204.6875 | 14.42% |  | 66 | 1693 |  | 1693 | 531 | 1162 | 138.6875 | 11.94%
3 | 1681 | 399.2023 | 26.63% |  | 12 | 1693 |  | 1693 | 239 | 1454 | 387.2023 | 26.63%
4 | 5318 | 997.9747 | 19.22% |  | 13 | 5331 |  | 5331 | 1566 | 3765 | 984.9747 | 26.16%
5 | 2580 | 243.6191 | 9.547% |  | -0.3 | 2579.7 |  | 2579.7 | 34 | 2545.7 | 243.9191 | 9.582%
6 | 2038 | 391.1473 | 19.41% |  | 32.6 | 2070.6 |  | 2070.6 | 31 | 2039.6 | 358.5473 | 17.58%
7 | 4254 | 788.1555 | 19.5% |  | -16.7 | 4237.3 | 200 | 4437.3 | 566 | 3871.3 | 604.8555 | 15.62%
8 | 10566 | 1408.0228 | 16.28% |  | 227.4 | 10793.4 | 357 | 11150.4 | 4081 | 7069.4 | 823.6228 | 11.65%
subtotal | 70419 | 15910 | 25.68% |  | 1204.6 | 71623.6 | 3737 | 75360.6 | 22467 | 52893.6 | 10968.4 | 20.74%
Contingency | 15910 |  |  |  | -1190 | 14720 | -3737 | 10983
Pct of ETC | 25.68% |  |  |  |  | 25.47% |  | 20.76%
Total | 86329 |  |  |  | 14.6 | 86343.6 |  | 86343.6
spent | 8466 |  |  |  |  | 13830 |  | 22460
ETC | 61953 |  |  |  |  | 57793.6 |  | 52900.6
ecp
|  |  |  | 5 | 500 | WBS 12 dsn, weld joint,R&D | 300 | WBS 12 add'l VV ports
|  |  |  | 6 | 75 | WBS 12 Port location dsn | -22 | WBS 12 Design
|  |  |  | 6 | 213 | WBS 12 VV prototype contract cost increase | 580 | WBS 12 VVSA FFP 20% increase
|  |  |  | 6 | 44 | WBS 12 VV weld joint R&D -full size sector | 500 | WBS 14 MC Winding (chill plate instl)
|  |  |  | 6 | 53 | WBS 13 conv coil material analysis | 970 | WBS 14 MCWF 20% increase
|  |  |  | 6 | 218 | WBS 14 Coil test Facility electrical and closed cooling dsn | 498 | WBS 14 MCWF design & analysis
|  |  |  | 5 | -300 | WBS 14 fabr tooling & MCWF R&D | -78 | WBS 14 MCWF Prototype Fab
|  |  |  | 6 | 27 | WBS 14 MCWF port addition impact | 450 | WBS 14MC winding TRC & conductor testing
|  |  |  | 5 | 50 | WBS 18 FP assy updated dsn est | ? | WBS 18 add'l port installation
|  |  |  | 5 | 100 | WBS 2-7 misc re-est | -18 | WBS 18 LOE oversight FY04
|  |  |  | 5 | 210 | WBS 8 Rev FY04 est, indirect cost | 200 | WBS 7 TC crane capacity upgrade
[7 empty] | 107 | WBS 81 Project oversight
[7 empty] | 250 | WBS 82 Project Engr design & analysis support
[5 empty] | 1190 |  | 3737