## Responsibility Matrix
Department of Energy Review
of the
National Compact Stellarator Experiment (NCSX) Project
November 18-20, 2003
Dan Lehman, DOE/SC, Chairperson
1. | 2. | 3. | 4. | 5.
Stellarator Core Systems | Plasma Heating Fueling & Vac Systems | Diagnostics | Electrical Power Systems | Central I&C Systems
*Harold Weitzner, NYU | *Jorst-Henrich Feist, M-PI | *Jeffrey Harris, ANU | *Ron Parker, MIT | *Jeffrey Harris, ANU
Jeffrey Harris, ANU | Peter Politzer, GA | Dave Anderson, U. of Wisconsin | Jorst-Henrich Feist, M-PI | Peter Polizer, GA
Peter Polizer, GA |  | Peter Polizer, GA
*Dave Anderson, U. of Wisconsin
Paul Anderson, GA
Jorst-Henrich Feist, M-PI
Ron Parker, MIT
[Harold Weitzner, NYU]
6. | 7 | 8 | 9
Facility Systems | Test Cell Preparation and Machine Assembly | Project Oversight and Support | Preparations for Operations | ES&H
* Paul Anderson, GA | *Dave Anderson, U. of Wisconsin | * Ron Parker, MIT | *Harold Weitzner, NYU | Clarence Hickey, DOE/SC
Joseph Minervini, MIT | Paul Anderson, GA | Jeff Hoy, DOE/SC | Peter Polizer, GA | Ray Schwartz, DOE/SC
| Jorst-Henrich Feist, M-PI | Joseph Minervini, MIT | Jeffrey Harris, ANU
Joseph Minervini, MIT
Cost, Schedule, & Funding
Jeff Hoy, DOE/SC
Marty Fallier, BNL

## Cost Breakdown
WBS | WBS Title | Project Estimate | [5 empty] | DOE Assessment |  |  |  |  | Variance ($K) | Comments | Comment
|  | Base Cost ECP-6 ($K) | Base To Date (April) | Base To Go | Contingency Remaining |  | Total ($K) | To Date | To Go | Contingency |  | Total ($K)
|  |  | Cost | Cost | % | $ |  | Cost | Cost | $ | %
1 | Stellarator Core Systems | 43226 | 9972 | 33254 | 31.89% | 10606 | 53832 | [6 empty] | JM1
11 | In Vessel Components | 8 |  | 8 |  |  | 8
12 | Vacuum Vessel Systems | 6900 | 2361 | 4539 | 20.73% | 941 | 7841
13 | Conventional Coils | 4221 | 255 | 3966 | 24.46% | 970 | 5191
14 | Mod Coils | 20495 | 6390 | 14105 | 41.66% | 5876 | 26371
15 | Coil Support Structures | 1436 | 15 | 1421 | 32.02% | 455 | 1891
16 | Coil Services | 1037 | 0 | 1037 | 24.01% | 249 | 1286
17 | Cryostat & Base Support Structure | 1300 | 58 | 1242 | 29.87% | 371 | 1671
171 | Cryostat |  |  | 0 | #DIV/0! |  | 0
172 | Base Support Structure |  |  | 0 | #DIV/0! |  | 0
18 | Field Period Assembly | 5164 | 265 | 4899 | 28.92% | 1417 | 6581
181 | Planning & Oversight |  |  | 0 | #DIV/0! |  | 0
182 | Preparation of the TFTR Test Cell |  |  | 0 | #DIV/0! |  | 0
183 | Receipt, Inspection, & Testing of Coils |  |  | 0 | #DIV/0! |  | 0
184 | Receipt, Inspection, & Testing of Vacuum Vessel |  |  | 0 | #DIV/0! |  | 0
185 | Field Period Assembly |  |  | 0 | #DIV/0! |  | 0
186 | Tooling Design & Fabrication |  |  | 0 | #DIV/0! |  | 0
187 | Measurement Systems |  |  | 0 | #DIV/0! |  | 0
19 | Stellarator Core Mgmt. & Integration | 2665 | 628 | 2037 | 16.05% | 327 | 2992
2 | Plasma Heating Fueling & Vac Systems | 1693.3 | 248 | 1445.3 | 9.825% | 142 | 1835.3 | [6 empty] | PP1
21 | Fueling Systems | 140 |  | 140 | 10% | 14 | 154
22 | Torus Vacuum Pump | 384.2 | 63 | 321.2 | 9.651% | 31 | 415.2
23 | Wall Conditioning System |  |  | 0 |  | 0 | 0
231 | Glow Discharge Cleaning System |  |  | 0 | #DIV/0! | 0 | 0
232 | Boranization System |  |  | 0 | #DIV/0! | 0 | 0
233 | Lithiumization System |  |  | 0 | #DIV/0! | 0 | 0
25 | Neutral Beam Injection System | 1169.1 | 185 | 984.1 | 9.857% | 97 | 1266.1
3 | Diagnostics | 1692.7 | 203 | 1489.7 | 26.25% | 391 | 2083.7 | [6 empty] | FD1
31 | Magnetic Diagnostics | 454.1 |  | 454.1 | 29.73% | 135 | 589.1
35 | Profile Diagnostics | 0 |  | 0 |  |  | 0
36 | Edge & Divertor Diagnostics | 99.3 |  | 99.3 | 19.13% | 19 | 118.3
38 | Electron Beam (EB) Mapping | 292.1 |  | 292.1 | 33.21% | 97 | 389.1
39 | Diagnostics Integration | 847.2 | 203 | 644.2 | 21.73% | 140 | 987.2
4 | Electrical Power Systems | 5330.9 | 212 | 5118.9 | 19.38% | 992 | 6322.9 | [6 empty] | DM1
41 | AC Power | 612.1 | 9 | 603.1 | 18.07% | 109 | 721.1
42 | AC/DC Converter | 23.5 | 0 | 23.5 | 17.02% | 4 | 27.5
43 | DC Systems | 2143.3 | 66 | 2077.3 | 21.76% | 452 | 2595.3
44 | Control & protection system | 1598.6 | 0 | 1598.6 | 16.51% | 264 | 1862.6
45 | Power System Design & Integration | 874.8 | 136 | 738.8 | 19.22% | 142 | 1016.8
46 | FCPC Building Modification | 78.6 | 1 | 77.6 | 27.06% | 21 | 99.6
5 | Central I&C Systems | 2579.7 | 28 | 2551.7 | 9.562% | 244 | 2823.7 | [6 empty] | TC1
51 | TCP/IP Infrastructure System | 429 | 28 | 401 | 4.988% | 20 | 449 | [6 empty] | TC2
52 | Central Instrumentation & Controls System | 578 |  | 578 | 9.516% | 55 | 633 | [6 empty] | TC3
53 | Data Acquisition & Facility Computing | 407.8 |  | 407.8 | 15.2% | 62 | 469.8 | [6 empty] | TC4
54 | Facility Timing & Synchronization System | 352 |  | 352 | 13.64% | 48 | 400 | [6 empty] | TC5
55 | Real Time Plasma & Power Control Systems | 293.3 |  | 293.3 | 7.842% | 23 | 316.3 | [6 empty] | TC6
56 | Central Safety Interlock System | 399.9 |  | 399.9 | 8.002% | 32 | 431.9 | [6 empty] | TC7
57 | Control Room Facility | 119.7 |  | 119.7 | 3.342% | 4 | 123.7 | [6 empty] | TC8
6 | Facility Systems | 2070.6 | 24 | 2046.6 | 17.54% | 359 | 2429.6 | [6 empty] | TM1
61 | Water Cooling Systems | 531.7 | 15 | 516.7 | 17.61% | 91 | 622.7
611 | C-Site Cooling Systems |  |  | 0 | #DIV/0! |  | 0
612 | Neutral Beam Water Cooling System |  |  | 0 | #DIV/0! |  | 0
613 | Vacuum Pumping Water Cooling System |  |  | 0 | #DIV/0! |  | 0
614 | Bakeout Water System |  |  | 0 | #DIV/0! |  | 0
615 | Diagnostic Water Cooling System |  |  | 0 | #DIV/0! |  | 0
62 | Cryogenic System | 747.5 |  | 747.5 | 17.79% | 133 | 880.5
63 | Utility Systems | 120.9 |  | 120.9 | 19.85% | 24 | 144.9
64 | Bakeout System | 628.9 |  | 628.9 | 17.65% | 111 | 739.9
65 | Facility System | 41.6 | 9 | 32.6 | 0% |  | 41.6
7 | Test Cell Preparation & Machine Assy | 4237.3 | 325 | 3912.3 | 20.58% | 805 | 5042.3
71 | Shield Wall Reconfiguration | 32.2 | 32 | 0.2 | 0% | 0 | 32.2
72 | Control Room Refurbishment | 47.6 |  | 47.6 | 10.5% | 5 | 52.6
73 | Platform Design | 159.6 |  | 159.6 | 10.03% | 16 | 175.6
74 | Planning/Oversight | 1614.2 | 293 | 1321.2 | 14.76% | 195 | 1809.2
75 | Machine Assembly Planning & Oversight | 2160 |  | 2160 | 24.77% | 535 | 2695 | [6 empty] | GD1, GD2
76 | Tooling Design & Fabrication | 223.7 |  | 223.7 | 24.14% | 54 | 277.7
8 | Project Oversight & Support | 10793.4 | 2815 | 7978.4 | 14.8% | 1181 | 11974.4 | [6 empty] | LP1
81 | Project Management & Control | 3354.3 | 1037 | 2317.3 | 16.36% | 379 | 3733.3
82 | Project Engineering | 4723.1 | 1233 | 3490.1 | 15.62% | 545 | 5268.1
83 | Environmental & Safety/QA/QC in overhead |  |  | 0 |  |  | 0
84 | Project Physics | 507.7 | 396 | 111.7 | 6.267% | 7 | 514.7
85 | Integrated System Testing | 1225 |  | 1225 | 12.57% | 154 | 1379
A | Allocations | 983.3 | 149 | 834.3 | 11.51% | 96 | 1079.3
| TOTAL | 71623.9 | 13827 | 57796.9 | 25.47% | 14720 | 86343.9
Note on N68: SC: Module magnet positioning/shimming cost low. Field joint/spool piece positioning/adjusting cost low.
Note on L68: SC: Module magnet positioning/shimming and field joint positioning/adjusting is complex & has high cost risk.
Note on L69: SC: Module magnet positioning/shimming and field joint positioning/adjusting is complex & has high cost risk.
Note on O44: SC: Install computers & networks & connect existing software systems for controls and data acquisition.
Note on O45: SC: Layout and install standard computer networks.
Note on O46: SC: EPICS control configuration and testing for 5 systems--lots of experience.
Note on O47: SC: Install computer hardware and configure MDS Plus data acquisition--lots of experience
Note on O48: SC: Design and deploy timing and synchronization system based on NSTX.
Note on O49: SC: Clone NSTX real-time control systems
Note on O50: SC: Layout and install safety interlock systems
Note on O51: SC: Computers for first plasma and PA system in control room
Note on O37: SC: All technology and costing data drawn from NSTX.
Note on O4: SC: The committee believes that the NCSX Team has made a credible estimate of the base costs and applied an appropriate level of contingency made on the basis of technical and schedule risk. The base costs estimates have benefited significantly from preliminary manufacturing feasibility studies performed by potential vendors of both the Modular Coil forms and the Vacuum Vessel. The NCSX Team has performed significant analysis of the components deemed to be the most technically risky (modular coils and VV). They have included an appropriate level of manufacturing R&D to mitigate these risks.
Note on O31: SC: Viable budget estimate for planned effort using new hardware.
Note on O23: SC: Refurbishment of existing systems.
Note on O52: SC: Extensive use of existing systems with refurbishing. Recent experience with NSTX for cost estimates
Note on O70: SC: Cost reasonable based on review