## P3
Contingency drawdown profile
based on ECP 4 CD-2 baseline
None | ACT CODE | DESCRIPTION | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | TOTAL
0 - | 0 | 0% | APR: 17; MAY: 18; JUN: 18; JUL: 18; AUG: 19; SEP: 16; OCT: 107; NOV: 94; DEC: 74; JAN: 85; FEB: 80; MAR: 80; APR: 85; MAY: 77; JUN: 6 | 794
3 - | 3 | 3% | JAN: 14; FEB: 14; MAR: 16; APR: 16; MAY: 14; JUN: 16; JUL: 15; AUG: 16; SEP: 15; OCT: 9; NOV: 9; DEC: 9; JAN: 9; FEB: 9; MAR: 10; APR: 9; MAY: 9; JUN: 9; JUL: 9; AUG: 10; SEP: 9; SEP: 6; OCT: 6; NOV: 12; DEC: 16; JAN: 24; FEB: 22; MAR: 24; APR: 11 | 367
5 - | 5 | 5% | AUG: 1; SEP: 3; OCT: 4; NOV: 24; DEC: 52; JAN: 72; FEB: 65; MAR: 72; APR: 68; MAY: 42 | 403
8 - | 8 | 8% | MAY: 3; JUN: 6; JUL: 6; AUG: 13; SEP: 14; OCT: 26; NOV: 59; DEC: 88; JAN: 120; FEB: 109; MAR: 120; APR: 115; MAY: 13 | 692
10 - | 10 | 10% | 17 | 16 | 19 | 27 | 18 | 39 | 36 | 18 | 17 | 21 | 17 | 18 | 17 | 17 | 19 | 17 | 17 | 18 | 17 | 19 | 18 | 41 | 27 | 28 | 28 | 27 | 42 | 31 | 40 | 43 | 39 | 45 | 63 | 83 | 71 | 60 | 78 | 71 | 78 | 74 | 59 | 19 | 19 | 20 | 18 | [12 empty] | 1526
14 - | 14 | 14% | OCT: 13; NOV: 12; DEC: 13; JAN: 36; FEB: 38; MAR: 44; APR: 13; MAY: 8; JUN: 26; JUL: 18; AUG: 48; SEP: 56; OCT: 86; NOV: 96; DEC: 92; JAN: 56; FEB: 45; MAR: 44; APR: 40; MAY: 33 | 817
15 - | 15 | 15% | 12 | 12 | 13 | 13 | 12 | 13 | 12 | 13 | 12 | 20 | 19 | 16 | 19 | 19 | 22 | 20 | 20 | 21 | 19 | 22 | 20 | 20 | 19 | 16 | 20 | 19 | 22 | 30 | 33 | 33 | 30 | 35 | 30 | 33 | 30 | 24 | 33 | 30 | 33 | 32 | 33 | 32 | 32 | 33 | 22 | 37 | 32 | 24 | 37 | 34 | 34 | 35 | 34 |  |  |  |  | 1290
16 - | 16 | 16% | 6 | 8 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 4 | 5 | 5 | 5 | 7 | 7 | 8 | 8 | 15 | 16 | 17 | 17 | 16 | 38 | 41 | 42 | 40 | 36 | 42 | 50 | 107 | 98 | 91 | 108 | 98 | 91 | 86 | 82 | 37 | 6 | 3 | [13 empty] | 1328
17 - | 17 | 17% | 184 | 182 | 209 | 200 | 182 | 200 | 191 | 200 | 191 | 190 | 181 | 184 | 181 | 181 | 208 | 190 | 190 | 199 | 181 | 208 | 196 | 153 | 146 | 146 | 153 | 146 | 168 | 146 | 160 | 160 | 146 | 168 | 151 | 176 | 160 | 152 | 167 | 151 | 166 | 159 | 166 | 159 | 164 | 174 | 144 | 50 | 43 | 43 | 47 | 45 | 45 | 47 | 47 |  |  |  |  | 8176
18 - | 18 | 18% | 33 | 28 | 31 | 47 | 49 | 54 | 40 | 40 | 37 | 31 | 29 | 25 | 27 | 25 | 27 | 24 | 24 | 25 | 23 | 24 | 22 | 181 | 193 | 152 | 187 | 145 | 236 | 116 | 128 | 114 | 101 | 131 | 126 | 208 | 176 | 125 | 144 | 112 | 61 | 42 | 41 | 28 | 14 | 8 | 6 | 3 | [11 empty] | 3443
20 - | 20 | 20% | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 33 | 32 | 27 | 37 | 36 | 77 | 109 | 130 | 174 | 164 | 185 | 149 | 191 | 215 | 209 | 345 | 325 | 311 | 266 | 151 | [16 empty] | 3205
22 - | 22 | 22% | JAN: 3; FEB: 3; MAR: 0; NOV: 0; DEC: 0; JAN: 0; FEB: 0; MAR: 0; APR: 0; MAY: 0; JUN: 0; JUL: 0; AUG: 0; SEP: 0; OCT: 38; NOV: 40; DEC: 51; JAN: 47; FEB: 33; MAR: 38; APR: 31; MAY: 31; JUN: 31; JUL: 28; AUG: 32; SEP: 27; OCT: 34; NOV: 32; DEC: 51; JAN: 123; FEB: 106; MAR: 64 | 843
24 - | 24 | 24% | 150 | 51 | 27 | 55 | 58 | 55 | 105 | 115 | 110 | 162 | 153 | 130 | 1400 | 38 | 43 | 40 | 40 | 42 | 38 | 43 | 40 | 109 | 104 | 84 | 144 | 135 | 144 | 804 | 591 | 140 | 132 | 197 | 180 | 227 | 202 | 128 | 171 | 151 | 165 | 95 | 88 | 21 | 18 | 31 | 49 | 76 | 46 | [10 empty] | 7127
26 - | 26 | 26% | 4 | 2 |  | 3 | 3 | 3 | 450 | 6 | 6 | 6 | 5 | 5 | 5 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 155 | 4 | 4 | 626 | 9 | 8 | 2 | 2 | 5 | 5 | 6 | 5 | 6 | 8 | 3 | 4 | 0 | [19 empty] | 1372
28 - | 28 | 28% | 7 | 7 | 17 | 66 | 68 | 71 | 97 | 102 | 72 | 31 | 36 | 31 | 36 | 36 | 68 | 61 | 25 | 26 | 23 | 27 | 25 | 37 | 35 | 43 | 59 | 58 | 65 | 535 | 65 | 44 | 38 | 28 | 15 | 16 | 37 | 34 | 45 | 29 | 10 | 2 | 1 | 1 | 1 | [14 empty] | 2130
30 - | 30 | 30% | 47 | 44 | 20 | 25 | 18 | 16 | 10 | 7 | 6 | 16 | 15 | 13 | 15 | 15 | 17 | 16 | 16 | 16 | 24 | 59 | 54 | 146 | 137 | 128 | 71 | 55 | 64 | 62 | 52 | 51 | 47 | 39 | 21 | 21 | 19 | 22 | 34 | 31 | 32 | 10 | 10 | 148 | 149 | 167 | 143 | 230 | 132 | 68 | [9 empty] | 2558
32 - | 32 | 32% | 5 | 9 | 10 | 12 | 49 | 54 | 66 | 69 | 50 | 56 | 51 | 43 | 51 | 26 | 11 | 5 |  |  |  | 987 | 25 | 69 | 65 | 66 | 51 | 42 | 324 | 40 | 44 | 44 | 39 | 31 | 27 | 27 | 20 | 16 | 22 | 19 | [19 empty] | 2525
34 - | 34 | 34% | JAN: 197; FEB: 195; MAR: 247; APR: 264; MAY: 238; JUN: 66; JUL: 44; AUG: 44; SEP: 31; OCT: 10; NOV: 10; DEC: 8; JAN: 10; FEB: 4; OCT: 44; NOV: 49; DEC: 39; JAN: 54; FEB: 49; MAR: 15 | 1618
40 - | 40 | 40% | 371 | 247 | 411 | 438 | 330 | 430 | 8628 | 318 | 1108 | 203 | 166 | 70 | 226 | 241 | 301 | 275 | 275 | 279 | 254 | 292 | 254 | 334 | 318 | 272 | 334 | 317 | 343 | 300 | 408 | 390 | 456 | 404 | 259 | 173 | 92 | 65 | 3 | [20 empty] | 19585
|  |  | 1051 | 819 | 1030 | 1175 | 1050 | 1028 | 9705 | 959 | 1666 | 756 | 692 | 554 | 1996 | 615 | 734 | 666 | 625 | 646 | 599 | 1703 | 675 | 1354 | 1158 | 1055 | 1820 | 1080 | 1613 | 2260 | 1737 | 1301 | 1285 | 1405 | 1182 | 1468 | 1400 | 1267 | 1603 | 1413 | 1286 | 1017 | 737 | 463 | 421 | 455 | 398 | 503 | 347 | 209 | 169 | 159 | 159 | 167 | 158 | 6 | 0 | 0 | 0 | 59799
|  |  | 1088.8577 | 848.5009 | 1067.1013 | 1217.3243 | 1087.8217 | 1065.0292 | 10054.5806 | 993.5438 | 1726.0104 | 783.2316 | 716.9263 | 573.9555 | 2067.8973 | 637.1527 | 760.4392 | 689.9898 | 647.5129 | 669.2694 | 620.5764 | 1764.3432 | 699.314 | 1402.772 | 1199.7119 | 1093.0018 | 1885.5576 | 1118.9023 | 1671.1013 | 2341.4067 | 1799.5679 | 1347.8629 | 1331.2866 | 1455.609 | 1224.5764 | 1520.8783 | 1450.4289 | 1312.6382 | 1660.7411 | 1463.8972 | 1332.3226 | 1053.633 | 763.5472 | 479.6776 | 436.1647 | 471.3894 | 412.3362 | 521.1184 | 359.4992 | 216.5283 | 175.0875 | 164.7273 | 164.7273 | 173.0155 | 163.6913 | 6.2161 | 0 | 0 | 0 | 61953
|  |  | 61953 | 60864.1423 | 60015.6413 | 58948.5401 | 57731.2158 | 56643.3941 | 55578.3648 | 45523.7842 | 44530.2404 | 42804.23 | 42020.9983 | 41304.072 | 40730.1166 | 38662.2193 | 38025.0666 | 37264.6275 | 36574.6377 | 35927.1248 | 35257.8554 | 34637.279 | 32872.9358 | 32173.6219 | 30770.8499 | 29571.138 | 28478.1362 | 26592.5785 | 25473.6762 | 23802.5749 | 21461.1682 | 19661.6003 | 18313.7374 | 16982.4508 | 15526.8418 | 14302.2653 | 12781.387 | 11330.9581 | 10018.3199 | 8357.5787 | 6893.6815 | 5561.359 | 4507.7259 | 3744.1787 | 3264.5011 | 2828.3364 | 2356.947 | 1944.6108 | 1423.4924 | 1063.9932 | 847.4649 | 672.3774 | 507.6501 | 342.9228 | 169.9074 | 6.2161 | 1.7726e-11 | 1.7726e-11 | 1.7726e-11 | 61953
|  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3% | 0.42 | 0.42 | 0.48 | 0.48 | 0.42 | 0.48 | 0.45 | 0.48 | 0.45 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.3 | 0.27 | 0.27 | 0.27 | 0.27 | 0.3 | 0.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0.18 | 0.36 | 0.48 | 0.72 | 0.66 | 0.72 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.01
|  | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.15 | 0.2 | 1.2 | 2.6 | 3.6 | 3.25 | 3.6 | 3.4 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.15
|  | 8% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0.48 | 0.48 | 1.04 | 1.12 | 2.08 | 4.72 | 7.04 | 9.6 | 8.72 | 9.6 | 9.2 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.36
|  | 10% | 1.7 | 1.6 | 1.9 | 2.7 | 1.8 | 3.9 | 3.6 | 1.8 | 1.7 | 2.1 | 1.7 | 1.8 | 1.7 | 1.7 | 1.9 | 1.7 | 1.7 | 1.8 | 1.7 | 1.9 | 1.8 | 4.1 | 2.7 | 2.8 | 2.8 | 2.7 | 4.2 | 3.1 | 4 | 4.3 | 3.9 | 4.5 | 6.3 | 8.3 | 7.1 | 6 | 7.8 | 7.1 | 7.8 | 7.4 | 5.9 | 1.9 | 1.9 | 2 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152.6
|  | 14% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.82 | 1.68 | 1.82 | 5.04 | 5.32 | 6.16 | 1.82 | 1.12 | 3.64 | 2.52 | 6.72 | 7.84 | 12.04 | 13.44 | 12.88 | 7.84 | 6.3 | 6.16 | 5.6 | 4.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.38
|  | 15% | 1.8 | 1.8 | 1.95 | 1.95 | 1.8 | 1.95 | 1.8 | 1.95 | 1.8 | 3 | 2.85 | 2.4 | 2.85 | 2.85 | 3.3 | 3 | 3 | 3.15 | 2.85 | 3.3 | 3 | 3 | 2.85 | 2.4 | 3 | 2.85 | 3.3 | 4.5 | 4.95 | 4.95 | 4.5 | 5.25 | 4.5 | 4.95 | 4.5 | 3.6 | 4.95 | 4.5 | 4.95 | 4.8 | 4.95 | 4.8 | 4.8 | 4.95 | 3.3 | 5.55 | 4.8 | 3.6 | 5.55 | 5.1 | 5.1 | 5.25 | 5.1 | 0 | 0 | 0 | 0 | 193.5
|  | 16% | 0.96 | 1.28 | 1.44 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.12 | 0.64 | 0.8 | 0.8 | 0.8 | 1.12 | 1.12 | 1.28 | 1.28 | 2.4 | 2.56 | 2.72 | 2.72 | 2.56 | 6.08 | 6.56 | 6.72 | 6.4 | 5.76 | 6.72 | 8 | 17.12 | 15.68 | 14.56 | 17.28 | 15.68 | 14.56 | 13.76 | 13.12 | 5.92 | 0.96 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212.48
|  | 17% | 31.28 | 30.94 | 35.53 | 34 | 30.94 | 34 | 32.47 | 34 | 32.47 | 32.3 | 30.77 | 31.28 | 30.77 | 30.77 | 35.36 | 32.3 | 32.3 | 33.83 | 30.77 | 35.36 | 33.32 | 26.01 | 24.82 | 24.82 | 26.01 | 24.82 | 28.56 | 24.82 | 27.2 | 27.2 | 24.82 | 28.56 | 25.67 | 29.92 | 27.2 | 25.84 | 28.39 | 25.67 | 28.22 | 27.03 | 28.22 | 27.03 | 27.88 | 29.58 | 24.48 | 8.5 | 7.31 | 7.31 | 7.99 | 7.65 | 7.65 | 7.99 | 7.99 | 0 | 0 | 0 | 0 | 1389.92
|  | 18% | 5.94 | 5.04 | 5.58 | 8.46 | 8.82 | 9.72 | 7.2 | 7.2 | 6.66 | 5.58 | 5.22 | 4.5 | 4.86 | 4.5 | 4.86 | 4.32 | 4.32 | 4.5 | 4.14 | 4.32 | 3.96 | 32.58 | 34.74 | 27.36 | 33.66 | 26.1 | 42.48 | 20.88 | 23.04 | 20.52 | 18.18 | 23.58 | 22.68 | 37.44 | 31.68 | 22.5 | 25.92 | 20.16 | 10.98 | 7.56 | 7.38 | 5.04 | 2.52 | 1.44 | 1.08 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 619.74
|  | 20% | 0.2 | 0.2 | 0.2 | 0.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.4 | 0.6 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 6.6 | 6.4 | 5.4 | 7.4 | 7.2 | 15.4 | 21.8 | 26 | 34.8 | 32.8 | 37 | 29.8 | 38.2 | 43 | 41.8 | 69 | 65 | 62.2 | 53.2 | 30.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641
|  | 22% | 0.66 | 0.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.36 | 8.8 | 11.22 | 10.34 | 7.26 | 8.36 | 6.82 | 6.82 | 6.82 | 6.16 | 7.04 | 5.94 | 7.48 | 7.04 | 11.22 | 27.06 | 23.32 | 14.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.46
|  | 24% | 36 | 12.24 | 6.48 | 13.2 | 13.92 | 13.2 | 25.2 | 27.6 | 26.4 | 38.88 | 36.72 | 31.2 | 336 | 9.12 | 10.32 | 9.6 | 9.6 | 10.08 | 9.12 | 10.32 | 9.6 | 26.16 | 24.96 | 20.16 | 34.56 | 32.4 | 34.56 | 192.96 | 141.84 | 33.6 | 31.68 | 47.28 | 43.2 | 54.48 | 48.48 | 30.72 | 41.04 | 36.24 | 39.6 | 22.8 | 21.12 | 5.04 | 4.32 | 7.44 | 11.76 | 18.24 | 11.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710.48
|  | 26% | 1.04 | 0.52 | 0 | 0.78 | 0.78 | 0.78 | 117 | 1.56 | 1.56 | 1.56 | 1.3 | 1.3 | 1.3 | 0.52 | 0.52 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 40.3 | 1.04 | 1.04 | 162.76 | 2.34 | 2.08 | 0.52 | 0.52 | 1.3 | 1.3 | 1.56 | 1.3 | 1.56 | 2.08 | 0.78 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356.72
|  | 28% | 1.96 | 1.96 | 4.76 | 18.48 | 19.04 | 19.88 | 27.16 | 28.56 | 20.16 | 8.68 | 10.08 | 8.68 | 10.08 | 10.08 | 19.04 | 17.08 | 7 | 7.28 | 6.44 | 7.56 | 7 | 10.36 | 9.8 | 12.04 | 16.52 | 16.24 | 18.2 | 149.8 | 18.2 | 12.32 | 10.64 | 7.84 | 4.2 | 4.48 | 10.36 | 9.52 | 12.6 | 8.12 | 2.8 | 0.56 | 0.28 | 0.28 | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596.4
|  | 30% | 14.1 | 13.2 | 6 | 7.5 | 5.4 | 4.8 | 3 | 2.1 | 1.8 | 4.8 | 4.5 | 3.9 | 4.5 | 4.5 | 5.1 | 4.8 | 4.8 | 4.8 | 7.2 | 17.7 | 16.2 | 43.8 | 41.1 | 38.4 | 21.3 | 16.5 | 19.2 | 18.6 | 15.6 | 15.3 | 14.1 | 11.7 | 6.3 | 6.3 | 5.7 | 6.6 | 10.2 | 9.3 | 9.6 | 3 | 3 | 44.4 | 44.7 | 50.1 | 42.9 | 69 | 39.6 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 767.4
|  | 32% | 1.6 | 2.88 | 3.2 | 3.84 | 15.68 | 17.28 | 21.12 | 22.08 | 16 | 17.92 | 16.32 | 13.76 | 16.32 | 8.32 | 3.52 | 1.6 | 0 | 0 | 0 | 315.84 | 8 | 22.08 | 20.8 | 21.12 | 16.32 | 13.44 | 103.68 | 12.8 | 14.08 | 14.08 | 12.48 | 9.92 | 8.64 | 8.64 | 6.4 | 5.12 | 7.04 | 6.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808
|  | 34% | 66.98 | 66.3 | 83.98 | 89.76 | 80.92 | 22.44 | 14.96 | 14.96 | 10.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 3.4 | 2.72 | 3.4 | 1.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.96 | 16.66 | 13.26 | 18.36 | 16.66 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550.12
|  | 40% | 148.4 | 98.8 | 164.4 | 175.2 | 132 | 172 | 3451.2 | 127.2 | 443.2 | 81.2 | 66.4 | 28 | 90.4 | 96.4 | 120.4 | 110 | 110 | 111.6 | 101.6 | 116.8 | 101.6 | 133.6 | 127.2 | 108.8 | 133.6 | 126.8 | 137.2 | 120 | 163.2 | 156 | 182.4 | 161.6 | 103.6 | 69.2 | 36.8 | 26 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7834
|  |  | 313.04 | 237.84 | 315.9 | 357.83 | 313.4 | 302.31 | 3707.04 | 271.37 | 564.62 | 198.17 | 178.01 | 128.77 | 500.77 | 170.07 | 205.62 | 186.45 | 174.77 | 179.41 | 166.19 | 515.66 | 187.01 | 364.57 | 312.85 | 282.82 | 479.43 | 287.89 | 429.46 | 584.98 | 453.53 | 341.71 | 351.72 | 360.36 | 279.42 | 317.53 | 282.4 | 240.52 | 293.64 | 256.76 | 219.97 | 158.64 | 121.93 | 94.41 | 87.36 | 95.99 | 85.32 | 101.83 | 62.75 | 31.31 | 13.54 | 12.75 | 12.75 | 13.24 | 13.09 | 0 | 0 | 0 | 0 | 16218.72 | 27.12%
|  |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | 15911
|  | Contingency | 307.1006 | 233.3274 | 309.9064 | 351.0408 | 307.4538 | 296.5742 | 3636.7058 | 266.2213 | 553.9074 | 194.4101 | 174.6326 | 126.3268 | 491.2688 | 166.8432 | 201.7187 | 182.9125 | 171.4541 | 176.006 | 163.0369 | 505.8763 | 183.4618 | 357.653 | 306.9143 | 277.454 | 470.3337 | 282.4278 | 421.3118 | 573.8811 | 444.9251 | 335.2267 | 345.0468 | 353.5228 | 274.1185 | 311.5055 | 277.042 | 235.9566 | 288.0687 | 251.8885 | 215.7965 | 155.6301 | 119.6166 | 92.6187 | 85.7025 | 94.1688 | 83.7012 | 99.898 | 61.5594 | 30.716 | 13.2831 | 12.5081 | 12.5081 | 12.9888 | 12.8416 | 0 | 0 | 0 | 0 | 15911
|  | Contingency Spend Plan | 307.1006 | 540.4281 | 850.3345 | 1201.3753 | 1508.8291 | 1805.4034 | 5442.1092 | 5708.3304 | 6262.2378 | 6456.6479 | 6631.2805 | 6757.6073 | 7248.8762 | 7415.7194 | 7617.4381 | 7800.3506 | 7971.8047 | 8147.8107 | 8310.8476 | 8816.7239 | 9000.1857 | 9357.8387 | 9664.7529 | 9942.2069 | 10412.5406 | 10694.9685 | 11116.2803 | 11690.1614 | 12135.0865 | 12470.3132 | 12815.3599 | 13168.8828 | 13443.0013 | 13754.5068 | 14031.5487 | 14267.5053 | 14555.574 | 14807.4625 | 15023.259 | 15178.8891 | 15298.5057 | 15391.1244 | 15476.8269 | 15570.9957 | 15654.6969 | 15754.5949 | 15816.1543 | 15846.8703 | 15860.1534 | 15872.6615 | 15885.1696 | 15898.1584 | 15911 | 15911 | 15911 | 15911 | 15911
|  | Contingency Drawdown Plan | 15911 | 15603.8994 | 15370.5719 | 15060.6655 | 14709.6247 | 14402.1709 | 14105.5966 | 10468.8908 | 10202.6696 | 9648.7622 | 9454.3521 | 9279.7195 | 9153.3927 | 8662.1238 | 8495.2806 | 8293.5619 | 8110.6494 | 7939.1953 | 7763.1893 | 7600.1524 | 7094.2761 | 6910.8143 | 6553.1613 | 6246.2471 | 5968.7931 | 5498.4594 | 5216.0315 | 4794.7197 | 4220.8386 | 3775.9135 | 3440.6868 | 3095.6401 | 2742.1172 | 2467.9987 | 2156.4932 | 1879.4513 | 1643.4947 | 1355.426 | 1103.5375 | 887.741 | 732.1109 | 612.4943 | 519.8756 | 434.1731 | 340.0043 | 256.3031 | 156.4051 | 94.8457 | 64.1297 | 50.8466 | 38.3385 | 25.8304 | 12.8416 | 0 | 0 | 0 | 0
|  | Contingency on work to go | 25.68% | 25.64% | 25.61% | 25.55% | 25.48% | 25.43% | 25.38% | 23% | 22.91% | 22.54% | 22.5% | 22.47% | 22.47% | 22.4% | 22.34% | 22.26% | 22.18% | 22.1% | 22.02% | 21.94% | 21.58% | 21.48% | 21.3% | 21.12% | 20.96% | 20.68% | 20.48% | 20.14% | 19.67% | 19.2% | 18.79% | 18.23% | 17.66% | 17.26% | 16.87% | 16.59% | 16.4% | 16.22% | 16.01% | 15.96% | 16.24% | 16.36% | 15.93% | 15.35% | 14.43% | 13.18% | 10.99% | 8.914% | 7.567% | 7.562% | 7.552% | 7.532% | 7.558% | 0% | 0% | 0% | 0%
|  |  | 15.911 | 15.6039 | 15.3706 | 15.0607 | 14.7096 | 14.4022 | 14.1056 | 10.4689 | 10.2027 | 9.6488