## Sheet1
NCSX ETC status
WBS |  | cost variances to date | ETC increases | CD-4 Impact
12 | Vac Vsl hardware design | 92 | 70 | 06 costs
12 | Vac Vsl hardware fabrication | 62 | 36 | 06 costs
12 | VVSA Contract oversight | 57
13 | TF Fab Facility | 64
13 | TF coil- fabrication |  | 384
13 | TF coil -PPPL oversight/title III | 101 | 205 | Risk mitigation due to vendor history.
13 | jobs 1302,1303 1503 cs suprt, pf design & coil suprts | 5 | 10
13 | PF coil procurement |  | -100 | recent experience from domestic vendor
13,15 | combine base ,& coil support struct into one procurement |  | -63
13 | Job 1353 CS support procurement |  | -144 | Simpler design to be fabricated by PPPL
14 | Cryogenic test facility (job 1414) | 130 | 66 | near term cost increase
14 | MC winding (job 1451 & 1459) | 492 | 600 | About half reflects the learning curve which did not materialize, and another half that the costs are greater. AWAITING INPUT TO INCORP LEARNING CURVE.
14 | WBS 14 other | 12
14 | Mod Coil design type C | 233 | 10 | 06 costs
14 | Mod Coil design type A | -212 | 22 | 06 costs
14 | Mod Coil design type B |  | -129
14 | Mod Coil interface design |  | 125 | 06 costs
14 | Mod Coil interface hardware |  | 70 | 07 cost but new problem not addressed, $100k risk
17 | WBS 17 cryostat and base support | 47 | 0 | a 50% savings but does not give good diagnostic views. Can accommodate CD4 but does not accommodate beam extension, and future diagnostics. Low risk design.
18 | FP assy stage 1 (job 1810) |  | 163 | 06 cost and completes in May 7
18 | FP assy tooling & fixtures (job 1803)-fixture fabr increase |  | 52
18 | FP assy tooling & fixtures (job 1803)-add'l fixture for stage 5 |  | 60
18 | FP assy tooling & fixtures (job 1803)-engr& design increase |  | 140
18 | Metrology H/W maint and support (job 1804) |  | 74 | For FY06 and FY07 - March '07
18 | WBS 18 Field period assy fuxtures & prep | 79
18,14 | Metrology engr supervision (raftopolous) for MC and stage 1 FP assy |  | 168 | 06 and '07 -March '07
2 | Fueling and Vacuum Pumping |  | -306 | CD-4 reqmnt:vac pumping speed of 1,300 l/s and base pressure of 4x10-7 torr
3 | Magnetic Diagmnostics | 70
3 | E-beam mapping diagnostic hardware |  | -176
3 | Edge & diverter diagnostics |  | -36
4 | Electrical Power Systems | 141 | -337.711
5 | Instrumentation and Control |  | -1091.9
61 | Water systems |  | -78.4
62 | cryogenic systems
7 | Machine assy-Control room flooring and Ready Rooms |  | -19
7 | Machine assy-TC floor resurface |  | -35
7 | Machine assy-2 shift ops on select tasks (reduced support crews | 37 | -100 | a -$100k effeciency may not materialize, desribe schedule improvements.
81 | Project management office | 83 | -5
8202 | Proj Engr (Reierson,Dudek, Simmons) | 44 | 109 | change to cover only thru March '07 | -21 260 173 36 | -21 | 260 | 173 | 36 | 239 | 209
8203 | Design Integration (brown, Designer) | -4 | 66 | change to cover only thru March '07 | 4 123 210 62 | 4 | 123 | 210 | 62 | 127 | 272
8204 | Systems Analysis (Brooks) | 142 | 77 | change to cover only thru March '07 | 0 153 126 101 | 0 | 153 | 126 | 101 | 153 | 227
8205 | Dimensional Control (Stratton, Raftopolous) | 0 | 75 | change to cover only thru March '07 | 14 122 47 99 | 14 | 122 | 47 | 99 | 136 | 146
85 | wbs 85 PTP & ISTP startup |  | -396.6
| other cost variances | 6
| PPPL overhnead rate forecast | -107 | -299
|  | 1574 | -734.611
|  | ecp43 |  | incl cost variances and ETC increases
| contingency | 8.72 |  | 7.8806
|  | 23.35% |  | 21.53%
| bcwr | 37.338 |  | 36.6034
Risk |  | Opportunities
410 | MCWF delivery incentives | 375 | PF fabrication by ASIPP
18 | Metrology H/W & S/W calibration, maintenance,repair | 100 | cryostat design simplification
339 | Proj Engr (Reierson,Dudek, Simmons) FY08/09 increase | 44 | Mach Assy eliminate hole reaming
333 | Design Integration (brown, Designer) FY08/09 increase | 250 | cryostat fabrication
304 | Systems Analysis (Brooks) FY08/09 increase
207 | Dimensional Control (Stratton, Raftopolous) FY08/09 increase
618 | MC Winding
2229 |  | 769
Drop red
| wbs | cv | etc increases
| 1 | 1162 | 1819
| 2 | 0 | -306
| 3 | 70 | -212
| 4 | 141 | -337.711
| 5 | 0 | -1091.9
| 6 | 0 | -78.4
| 7 | 37 | -154
| 8 | 265 | -74.6
| rates | -101 | -299
|  | 1574 | -734.611