## Sheet1
NCSX ETC status
| cost variances to date | ETC increases
job 1414 coil testing |  | 168 | reviewed | GG,WR,HN,MW,RLS
fp assy stage 1 |  | 163 | reviewed | MV,MW,WR,HN,RLS
metrology engr supervision (raftopolous) |  | 113 | reviewed | SR,WR.HN,LD,RLS
TF coil fabr | 118 | 589 |  | RLS
job 1451 MC winding | 381 | 1020 |  | JC
wbs 85 startup |  | -396.6 | reviewed | CG,MW,AvH,RLS
wbs 4 | 132 | 70 | reviewed | RR,WR,HN,RLS
wbs 14 design | 63 | 28 | reviewed | DW,WR,HN,JL,MW,RLS
wbs 14 interface hardware |  | 70 | reviewed | DW,WR,HN,JL,MW,RLS
wbs 12 design | 77 | 70 | reviewed | PG,WR,HN,JL,MW,RLS
wbs 12 hardware | 57 | 36 | reviewed | PG,WR,HN,JL,MW,RLS
fan,brooks fy06 | 106 | 100 |  | WR
brooks fy07 |  | 225 |  | WR
jobs 1303,1303 1503 cs suprt, pf design & coil suprts |  | 10 | reviewed | FD,MK,MW,WR,HN,RLS
combine CS,base ,& coil support struct into one procurement |  | -120 |  | RLS
other cost variances | 475
| 1409 | 2145.4
| ecp43 | ecp-TF | incl balance of cost variances and ETC's
contingency | 8.72 | 8.131 | 4.6946
| 22.4% | 20.57% | 11.43%
bcwr | 38.932 | 39.521 | 41.0774
EAC scenario
| bcwp fy06 thru 2/28/06 | 6449
| acwp fy06 thru 2/28/06 | 7858
| cv fy06 only = | 1409
| % over budget= | 21.85% |  | assume project continues at this rate
|  | projected ETC= | 50.0521
|  | ACWP cum thru 2/28= | 46.172
|  | EAC = | 96.2241 | potential EAC
|  | TEC= | 92.4
|  | Underfunded= | 3.8241