## Sheet1
9450-1***-1451
| EAEM | EAEM | EMSM
TASK DESCRIPTION | Chrz. | Raft. | Meighan
| hours | hours | hours
Engineering and Oversight | 70% | 40% | 70%
LOE FY06 (March thru September) | 705 | 403 | 705
LOE FY07 (October thru September) | 1208 | 690 | 1208
LOE FY08 (October thru December) | 324 | 175 | 0
| 2237 | 1268 | 1913
TASK DESCRIPTION | Total | No. of | Hours per | No. of | No. of | Total | Total
| Shifts | Tech./Shift | Shift | Person-hours | coils | Manhrs | Manhrs | COMMENTS | Difference | Difference
|  |  |  | per coil | remaining | ORIG. | Revised |  | (+/-) | (+/-)
Station No. 1- Casting Preparation | [8 empty] | 2006-04-06 | 2006-03-06
Winding form modifications [grinding deburring, etc.] | 1 | 2 | 8 | 16 | 15 | 240
| 3 | 2 | 8 | 48 | 15 |  | 720 | REVISED | 480 | 480
Measure casting wings using metrology equipment | 1 | 1 | 8 | 8 | 15 | 0 | 120 | NEW TASK | 120 | 120
Electrical test poloidal break | 1 | 1 | 8 | 8 | 15 | 120
REVISED | 0.5 | 1 | 8 | 4 | 15 |  | 60 | REVISED | -60 | -60
Position & mount casting to support ring
1st. of each type coil [A & B] | 5 | 4 | 10 | 200 | 2 | 400
REVISED | 4 | 4 | 10 | 160 | 2 |  | 320 | REVISED | -80 | -80 | 64
Remaining coils [2-6 of each type] | 3 | 3 | 8 | 72 | 13 | 936
REVISED | 1 | 4 | 10 | 40 | 13 |  | 520 | REVISED | -416 | -416 | 104
Install coil in station 1b turning fixture | 1 | 3 | 8 | 24 | 15 | 360
REVISED | 1 | 4 | 10 | 40 | 15 |  | 600 | REVISED | 240 | 240 | 120
Install weights and balance casting and ring assembly | 1 | 2 | 10 | 20 | 15 |  | 300 | NEW TASK | 300 | 300 | 60
Weld monuments, stud adapters & lead nuts | 2 | 2 | 8 | 32 | 18 | 576 | 576 | NO CHANGE | 0 | 0
Inspect casting[surfaces, magnetic permeability]
1st. of each type coil | 3 | 2 | 8 | 48 | 2 | 96
Remaining coils [2-6 of each type] | 2 | 2 | 8 | 32 | 13 | 416
REVISED | 0.5 | 1 | 10 | 5 | 15 |  | 75 | REVISED | -437 | -437 | 15
Install studs for winding clamps | 3 | 3 | 8 | 72 | 15 | 1080
| 2 | 3 | 10 | 60 | 15 |  | 900 | REVISED | -180 | -180 | 180
Clean casting [Inspect and clean all holes] | 1 | 2 | 8 | 16 | 15 | 240 | 240 | NO CHANGE | 0 | 0
Install Kapton edging | 1 | 2 | 10 | 20 | 15 |  | 300 | NEW TASK | 300 | 300 | 60
Fitup Lead blocks and terminals [Remove lead blocks] | 2 | 2 | 8 | 32 | 15 | 480
| 1 | 2 | 8 | 16 | 15 |  | 240 | REVISED | -240 | -240
Install inner cladding plates | 6 | 4 | 8 | 192 | 16 | 3072
Final clean & Kapton | 4 | 1 | 10 | 40 | 16 |  | 640 |  |  |  | 128
Install inner cladding plates | 5 | 3 | 10 | 150 | 16 |  | 2400 | REVISED | -32 | -32 | 480
[6 empty] | 8016 | 8011 | TOTALS | -5 | -5 | 1211
| 27 |  |  |  |  | hours | hours
TASK DESCRIPTION | Total | No. of | Hours per | No. of | No. of | Total | Total
| Shifts | Tech./Shift | Shift | man-hours | coils | Manhrs | Manhrs | COMMENTS | Difference | Difference
|  |  |  | per coil | remaining | ORIG. | Revised |  | (+/-) | (+/-)
Coil Winding Station 2 and 4
Prepare coil for winding
Install coil in turning fixture | 1 | 3 | 8 | 24 | 15 | 360 | 360 | NO CHANGE | 0 | 0 | 0
Dimensional measure surface [Metrology requirement] | 1 | 2 | 10 | 20 | 17 | 340
Note: Allow one to two additional shifts to obtain shim data | 2 | 2 | 9 | 36 | 16 |  | 576 | REVISED | 236 | 620 | 64
Install/set winding clamps side bars A & B | 3 | 2.5 | 8 | 60 | 16 | 960
| 3 | 3 | 9 | 81 | 16 |  | 1296 | REVISED | 336 | 480 | 144
Position inner GW insulation onto winding form (sides A & B) | 9 | 2.5 | 10 | 225 | 16 | 3600
| 9 | 2 | 9 | 162 | 16 |  | 2592 | REVISED | -1008 | -720 | 288
Position lacing strips sides A & B | 2 | 2.5 | 10 | 50 | 16 | 800
| 2 | 2 | 9 | 36 | 16 |  | 576 | REVISED | -224 | 0 | 64
Wind Side "A"
Braze & secure 1st. coil lead set [inc. brazing] | 2 | 2.5 | 10 | 50 | 16 | 800
| 3 | 2 | 9 | 54 | 16 |  | 864 | REVISED | 64 | 160 | 96
Type C- Position leads & Wind side A - [10] turns | 11 | 2.5 | 10 | 275 | 4 | 1100 | 1100 | NO CHANGE | 0 | 0 | 220
Types A & B- Position leads & Wind side A - [11] turns | 12 | 2.5 | 10 | 300 | 12 | 3600 | 3600 | NO CHANGE | 0 | 0 | 720
Prepare station for Side "B"
Reposition coil from side A to side B | 1 | 3 | 8 | 24 | 16 | 384
| 1 | 4 | 8 | 32 | 16 |  | 512 | REVISED | 128 | 128 | 0
Wind Side "B"
Braze & secure 1st. coil lead set [inc. brazing] | 2 | 2.5 | 10 | 50 | 16 | 800
| 3 | 2 | 9 | 54 | 16 |  | 864 | REVISED | 64 | 160 | 96
Type C- Position leads & Wind side B - [10] turns | 11 | 2.5 | 10 | 275 | 4 | 1100
| 10 | 2 | 9 | 180 | 4 |  | 720 | REVISED | -380 | 0 | 80
Types A & B- Position leads & Wind side B - [11] turns | 12 | 2.5 | 10 | 300 | 12 | 3600 |  |  |  |  | 0
| 11 | 2 | 9 | 198 | 12 |  | 2376 | REVISED | -1224 | 0 | 264
Final coil winding activities
Measure, reposition & re-measure coil bundle [sides A & B] | 4 | 2 | 10 | 80 | 16 | 1280
Note: Allow one to two additional shifts to analyze data | 6 | 2 | 9 | 108 | 16 |  | 1728 | REVISED | 448 | 1280 | 192
Secure Lacing | 2 | 2 | 10 | 40 | 16 | 640 |  |  |  |  | 0
| 3 | 2 | 9 | 54 | 16 |  | 864 | REVISED | 224 | 320
Remeasure after lacing is secured | 1 | 2 | 8 | 16 | 16 | 256 |  |  |  |  | 0
DELETE Activity | 0 | 0 | 0 | 0 | 0 |  | 0 | REVISED | -256 | -256
Complete groundwrap installation | 6 | 2.5 | 10 | 150 | 16 | 2400
| 7 | 2 | 9 | 126 | 16 |  | 2016 | REVISED | -384 | 0 | 224
[6 empty] | 22020 | 20044 | TOTALS | -1976 | 2172
[6 empty] | hours | hours |  |  |  | 2452
TASK DESCRIPTION | Total | No. of | Hours per | No. of | No. of | Total | Total
| Shifts | Tech./Shift | Shift | man-hours | coils | Manhrs | Manhrs | COMMENTS | Difference | Difference
|  |  |  | per coil | remaining | ORIG. | Revised |  | (+/-) | (+/-)
NEW TASK
Rework the type C chill plates and cladding [C3 thru C6]
| 11 | 2 | 10 | 220 | 3 | 0 | 660 | NEW TASK | 660 | 660 | 132
TASK DESCRIPTION | Total | No. of | Hours per | No. of | No. of | Total | Total
| Shifts | Tech./Shift | Shift | man-hours | coils | Manhrs | Manhrs | COMMENTS | Difference | Difference
|  |  |  | per coil | remaining | ORIG. | Revised |  | (+/-) | (+/-)
Final coil prep & Mold Application (Station 2 & 4)
Install chill plates & Tubing | 12 | 2.5 | 9 | 270 | 17 | 4590 | 5100 | NO CHANGE | -510 | 0 | 566.6667
Cut, braze and position 2nd. coil lead set [side A] | 2 | 2.5 | 9 | 45 | 16 | 720 |  |  |  |  | 0
| 3 | 2 | 9 | 54 | 16 |  | 864 | REVISED | 144 | 160 | 96
Cut, braze and position 2nd. Coil lead set [side B] | 2 | 2.5 | 9 | 45 | 16 | 720 |  |  |  |  | 0
| 3 | 2 | 9 | 54 | 16 |  | 864 | REVISED | 144 | 160 | 96
Install outer Diagnostic loops | 2 | 2 | 8 | 32 | 17 | 544 | 544 | NO CHANGE | 0 | 0 | 0
Perform pre-VPI elect. & pressure tests | 1 | 2 | 8 | 16 | 17 | 272 | 272 | NO CHANGE | 0 | 0 | 0
Pressure test cryo lines
Perform preliminary [pre-vpi] electrical tests
Install bag mold around modular coil
Install silicone bag & sprues | 4 | 2.5 | 8 | 80 | 17 | 1360 |  |  |  |  | 0
| 4 | 2 | 9 | 72 | 17 |  | 1224 | REVISED | -136 | 340 | 136
Vacuum pumpdown & leak repair | 2 | 2.5 | 8 | 40 | 17 | 680 |  |  |  |  | 0
| 2 | 2.5 | 9 | 45 | 17 |  | 765 | REVISED | 85 | 170 | 85
Install epoxy shell | 2 | 2.5 | 8 | 40 | 17 | 680 |  |  |  |  | 0
| 2 | 3 | 9 | 54 | 17 |  | 918 | REVISED | 238 | 850 | 102
[6 empty] | 9566 | 10551 | TOTALS | 475 | 1680 | 1081.6667
[6 empty] | hours | hours
TASK DESCRIPTION | Total | No. of | Hours per | No. of | No. of | Total | Total
| Shifts | Tech./Shift | Shift | man-hours | coils | Manhrs | Manhrs | COMMENTS | Difference | Difference
|  |  |  | per coil | remaining | ORIG. | Revised |  | (+/-) | (+/-)
VPI Activities (Station 5)
Transfer modular coil to Autoclave | 1 | 3 | 8 | 24 | 17 | 408
| 1 | 4 | 8 | 32 | 17 |  | 544 | REVISED | 136 | 136 | 0
Prepare modular coil for VPI | 3 | 3 | 8 | 72 | 17 | 1224 |  |  |  |  | 0
(Connect fill lines, manifolds, hookup thermocouples & leak check)
| 3 | 3 | 9 | 81 | 17 |  | 1377 | REVISED | 153 | 306 | 153
VPI modular coil
Vacuum pumpdown & preheat mold and autoclave | 2 | 3 | 8 | 48 | 17 | 816 | 816 | NO CHANGE | 0 | 0 | 0
Epoxy fill coil | 2 | 3 | 8 | 48 | 17 | 816 |  |  |  |  | 0
| 2 | 3 | 9 | 54 | 17 |  | 918 | REVISED | 102 | 544 | 102
Temperature rampup and Cure | 3 | 2 | 8 | 48 | 17 | 816 | 816 | NO CHANGE | 0 | 0 | 0
Temperature rampup and Post cure | 2 | 2 | 8 | 32 | 17 | 544 |  |  |  |  | 0
| 1 | 2 | 12 | 24 | 17 |  | 408 | REVISED | -136 | -136 | 136
Temperature rampdown | 1 | 1 | 8 | 8 | 17 | 136 | 136 | NO CHANGE | 0 | 0 | 0
Cleanup & ready autoclave | 2 | 3 | 8 | 48 | 17 | 816 |  |  |  |  | 0
| 8 | 2 | 10 | 160 | 17 |  | 2720 | REVISED | 1904 | 1904 | 544
[6 empty] | 5576 | 7735 | TOTALS | 2159 | 2754 | 935
[6 empty] | hours | hours
TASK DESCRIPTION | Total | No. of | Hours per | No. of | No. of | Total | Total
| Shifts | Tech./Shift | Shift | man-hours | coils | Manhrs | Manhrs | COMMENTS | Difference | Difference
|  |  |  | per coil | remaining | ORIG. | Revised |  | (+/-) | (+/-)
Post VPI Activities (Station 1)
Transfer modular coil from Autoclave to Station #1 | 1 | 3 | 8 | 24 | 17 | 408 | 408 | NO CHANGE | 0 | 0 | 0
Remove studs, structural shell & sprues | 2 | 2 | 8 | 32 | 17 | 544 |  |  |  |  | 0
| 2 | 2 | 10 | 40 | 17 |  | 680 | REVISED | 136 | 476 | 136
Finalize coil & install final coil clamps (40 to 50 clamps/per coil) | 3 | 2 | 8 | 48 | 17 | 816 | 816 | NO CHANGE | 0 | 0 | 0
Perform (room temperature) electrical & Pressure Tests | 1 | 2 | 8 | 16 | 17 | 272 | 272 | NO CHANGE | 0 | 0 | 0
Remove coil from ring assembly | 2 | 2 | 8 | 32 | 17 | 544 |  |  |  |  | 0
| 1 | 4 | 8 | 32 | 17 |  | 544 | NO CHANGE | 0 | 0 | 0
[6 empty] | 2584 | 2720 | TOTALS | 136 | 476 | 136
9450-1***-1408 | [5 empty] | hours | hours
| Machinist | Technician | M&S | M&S
MATERIAL & SUPPLIES | Man-hours | Man-hours | Original | Revised |  |  |  |  | Delta | Costs
Coil Supplies | [8 empty] | 2006-04-06 | 2006-03-06
1) Insulation [Uncommitteded] |  |  | 10000 | 2000 |  |  |  |  | 1449 | 7737
2) Epoxy- CTD-101 [$4500.00 per coil @ assume 20 injections] |  |  | 90000 | 78000 |  |  | 49721 | 4087066.2 |  |  | 5947.6667 | 488898.2 | 112446.586 | 2.751%
[11 empty] | 0.0014552 |  | OT
3) Chill Plates and cladding [estimate $5.6 k per coil x 18 coils] |  |  | 100800 |  |  |  |  | 30595
[estimate $8.8 k per coil x 12 coils] |  |  |  | 105600
4) Copper pre-tinned tubing |  |  | 2000 |  |  |  | 15320.6667 | 125935.88
|  |  |  | 0 |  |  |  | 54000 | budgeted 2nd shft
4) Coil Clamps [900 clamps x $300.00 each] |  |  | 270000 |  |  |  |  | 71935.88 | increased 2nd shft |  |  |  | 184382.466
10000
5) Copper conductor [committed] |  |  | 178000
0
7) Lead hardware & fillers | 150 |  | 478200 | 180000
8) Safety and PPE equipment and supplies |  |  | 15000 | 5000
Includes gloves, masks, safety equipment & supplies
9) Miscellaneous supplies |  |  | 12000 | 10000
Includes rags, hardware, etc.
10) Prostetic pieces to replace VPI groove [3 ea. A & B] |  |  |  | 30000 | NEW SCOPE
11) Support feet for finished coils [ 2 each C and A] |  |  |  | 2500 | NEW SCOPE
VPI Supplies
1) Epoxy for mold shell [Hysol] |  |  | 18000 | 15000
2) Vulcanizing tape, glass, RTV and silicone caulking |  |  | 22000 | 10000
3) Disposable VPI hardware
valves & fittings |  |  | 15000 | 2000
High & low temperature vac. Tubing |  |  | 35000 | 2000
VPI manifolds |  | 200 | 66100 | 5000
| 150 | 200
| hours | hours | 1312100 | 457100