## Sheet1
1
2
3 | WBS2 | Sum of BUDGET (BAC) | Sum of CV | Sum of etc increases
4 | 12 | 9409005.99 | 212270.7162 | 106000
7 | 13 | 4820215.58 | 167968.6451 | 265054.2649
10 | 14 | 32264096.33 | 656517.9951 | 612829.8091
13 | 15 | 1390770.91 | 2349.25 | -63000
16 | 16 | 1131647.95 | 2792 | 0
19 | 17 | 1532378.78 | 46485.938 | 0
22 | 18 | 5274008.61 | 77760.4361 | 657000
25 | 19 | 2768760.87 | 2538.4095 | 0
|  | 58590885.02 | 1168683.3899 | 1577884.0739
28 | 21 | 151759.99 | -774 | 0
31 | 22 | 355156.69 | 0 | -306000
34 | 25 | 284367.67 | 648.33 | 0
|  | 791284.35 | -125.67 | -306000
37 | 31 | 523726.79 | 76409.8345 | 0
40 | 36 | 45581.15 | 0 | -36000
43 | 38 | 206196.8 | 0 | -183379.0567
46 | 39 | 345322.33 | -6500.6647 | 0
|  | 1120827.07 | 69909.1698 | -219379.0567
49 | 41 | 423012.85 | -397.719 | -67977
52 | 43 | 537668.92 | 113127.0865 | 70000
55 | 44 | 1344443.7 | 22888.9405 | -339734
58 | 45 | 1056150.65 | 5399.8038 | 0
61 | 46 | 1300 | 0 | 0
|  | 3362576.12 | 141018.1118 | -337711
64 | 51 | 280385.9 | 0 | -106486
67 | 52 | 530112.41 | 0 | -383452
70 | 53 | 329072.83 | 0 | -176857
73 | 54 | 195823.11 | 0 | -102971
76 | 55 | 179331.4 | 0 | -85716
79 | 56 | 325498.85 | 0 | -200080
82 | 58 | 33362.26 | -340.26 | 24217
|  | 1873586.76 | -340.26 | -1031345
85 | 61 | 107271.78 | -127 | -78000
88 | 62 | 455033.04 | 0 | 0
91 | 63 | 106903.92 | 0 | 0
94 | 65 | 9380 | -10 | 0
|  | 678588.74 | -137 | -78000
97 | 71 | 32150 | 485 | 0
100 | 72 | 9097.92 | 0 | -9098
103 | 73 | 109811.07 | 3735.69 | 0
106 | 74 | 1752911.82 | 32123.294 | -10480
109 | 75 | 2416928.04 | 0 | -135000
112 | 76 | 237778.59 | 0 | 0
|  | 4558677.44 | 36343.984 | -154578
115 | 81 | 6061279.99 | 83350.7694 | -88803.6866
118 | 82 | 4902058.73 | 182685.4398 | 275619.6694
121 | 84 | 469932.2 | 83.8 | 0
124 | 85 | 1195741.84 | 0 | -397000
|  | 12629012.76 | 266120.0093 | -210184.0173
127 | dcma | 75000
128 |  | 83680438.26 | 1681471.7348 | -759313 | 0
129
130 |  | 8720000
131 |  | 92400438.26
132

## Sheet2
1 | WBS | Data | etc | cont
2 | 12 - Vacuum Vessel Systems | Sum of ETC total | 627946.7062 | 103607.8659 | 16.5%
|  | VVSA | 1059311 | 52950 | 4.999%
4 | 13 - Conventional Coils | Sum of ETC total | 3154943.4899 | 512905.3869 | 16.26%
6 | 14 - Modular Coils | Sum of ETC total | 6830118.1342 | 1477602.6924 | 21.63%
|  | MCWF | 3316002 | 410000 | 12.36%
8 | 15 - Structures | Sum of ETC total | 1247719.16 | 398126.3112 | 31.91%
10 | 16 - Coil Services | Sum of ETC total | 1131647.95 | 280747.6374 | 24.81%
12 | 17 - Cryostat and Base Support Structure | Sum of ETC total | 1164089.718 | 344643.5516 | 29.61%
14 | 18 - Field Period Assembly | Sum of ETC total | 4233121.0461 | 1987101.3129 | 46.94%
16 | 19 - Stellarator Core Management and Integration | Sum of ETC total | 1024933.2795 | 102493.328 | 10%
18 | 21 - Fueling Systems | Sum of ETC total | 88092.99 | 12333.0186 | 14%
20 | 22 - Torus Vacuum Pumping Systems | Sum of ETC total | 49156.69 | 6881.9366 | 14%
22 | 25 - Neutral Beam Injection System | Sum of ETC total | 0 | 0 | #DIV/0!
24 | 31 - Magnetic Diagnostics | Sum of ETC total | 224480.6245 | 67344.1873 | 30%
26 | 36 - Edge and Divertor Diagnostics | Sum of ETC total | 9581.15 | 1916.23 | 20%
28 | 38 - Electron Beam (EB) Mapping | Sum of ETC total | 22817.7433 | 7758.0327 | 34%
30 | 39 - Diagnostics Integration | Sum of ETC total | 35962.6653 | 10788.7996 | 30%
32 | 41 - AC Power | Sum of ETC total | 247287.131 | 44511.6836 | 18%
34 | 43 - DC Systems | Sum of ETC total | 336130.0065 | 60503.4012 | 18%
36 | 44 - Control and protection Systems | Sum of ETC total | 945911.6405 | 185457.3855 | 19.61%
38 | 45 - Power System Design and Integration | Sum of ETC total | 923256.4538 | 186926.5121 | 20.25%
40 | 46 - FCPC Building Modifications | Sum of ETC total | 0 | 0 | #DIV/0!
42 | 51 - TCP/IP Infrastructure Systems | Sum of ETC total | 173899.9 | 8694.995 | 5%
44 | 52 - Central Instrumentation & Control | Sum of ETC total | 146660.41 | 14666.041 | 10%
46 | 53 - Data Acquisition & Facility Computing | Sum of ETC total | 152215.83 | 24354.5328 | 16%
48 | 54 - Facility Timing & Synchronization | Sum of ETC total | 92852.11 | 12999.2954 | 14%
50 | 55 - Real Time Plasma & Power Supply Control Sys | Sum of ETC total | 93615.4 | 7489.232 | 8%
52 | 56 - Central Safety Interlock Systems | Sum of ETC total | 125418.85 | 10033.508 | 8%
54 | 58 - Central I&C management and Integration | Sum of ETC total | 24217 | 0 | 0%
56 | 61 - Water Systems | Sum of ETC total | 14271.78 | 2854.356 | 20%
58 | 62 - Cryogenic Systems | Sum of ETC total | 455033.04 | 91006.608 | 20%
60 | 63 - Utility Systems | Sum of ETC total | 106903.92 | 21380.784 | 20%
62 | 65 - Facility Systems Integration | Sum of ETC total | 0 | 0 | #DIV/0!
64 | 71 - Shield Wall Seismic Modifications | Sum of ETC total | 0 | 0 | #DIV/0!
66 | 72 - Control Room Refurbishment | Sum of ETC total | -0.08 | -0.008 | 10%
68 | 73 - Platform Design & Fabrication | Sum of ETC total | 37606.76 | 3644.1906 | 9.69%
70 | 74 - Machine Assembly Planning and Oversight | Sum of ETC total | 941514.114 | 143084.0442 | 15.2%
72 | 75 - Test Cell and Basement Assembly Operations | Sum of ETC total | 2281928.04 | 804685.3612 | 35.26%
74 | 76 - Tooling Design & Fabrication | Sum of ETC total | 237778.59 | 57066.8616 | 24%
76 | 81 - Project Management and Control | Sum of ETC total | 2429033.0728 | 153654.6177 | 6.326%
78 | 82 - Project Engineering | Sum of ETC total | 1711366.8392 | 85568.342 | 5%
80 | 84 - Project Physics | Sum of ETC total | 0 | 0 | #DIV/0!
82 | 85 - Integrated Systems Testing | Sum of ETC total | 798741.84 | 207257.0119 | 25.95%
84 | dcma | Sum of ETC total | 0 | 0 | #DIV/0!
86 | Total Sum of ETC total |  | 36495566.9948 | 7903039.0468 | 21.65%
87 | Total Sum of Total Contingency Balance %$ |  | 7903039.0468

## Lehman worksheet
WBS | WBS Title | Project Estimate | [5 empty] | DOE Assessment |  |  |  |  | Variance ($K) | Comments | Comment
|  | Base Cost ($K) | Base To Date | Base To Go | Contingency |  | Total ($K) | To Date | To Go | Contingency |  | Total ($K)
|  |  | Cost | Cost | % | $ |  | Cost | Cost | $ | %
1 | Stellarator Core Systems | 61345832.4839 | 37547620 | 23798212.4839 | 23.83% | 5670479.2863 | 67016311.7702
11 | In Vessel Components |  | 0 | 0 |  |  | 0
12 | Vacuum Vessel Systems | 9727276.7062 | 8040019 | 1687257.7062 | 9.279% | 156557.8659 | 9883834.5721
13 | Conventional Coils | 5261618.4899 | 2098295 | 3163323.4899 | 16.27% | 514606.5869 | 5776225.0768
14 | Mod Coils | 33533444.1342 | 23387324 | 10146120.1342 | 18.6% | 1887602.6924 | 35421046.8266
15 | Coil Support Structures | 1330120.16 | 82401 | 1247719.16 | 31.91% | 398126.3112 | 1728246.4712
16 | Coil Services | 1134439.95 | 2792 | 1131647.95 | 24.81% | 280747.6374 | 1415187.5874
17 | Cryostat & Base Support Structure | 1578864.718 | 414775 | 1164089.718 | 29.61% | 344643.5516 | 1923508.2696
18 | Field Period Assembly | 6008769.0461 | 1775648 | 4233121.0461 | 46.91% | 1985701.3129 | 7994470.359
19 | Stellarator Core Mgmt. & Integration | 2771299.2795 | 1746366 | 1024933.2795 | 10% | 102493.328 | 2873792.6075
2 | Plasma Heating Fueling & Vac Systems | 485158.68 | 347909 | 137249.68 | 14% | 19214.9552 | 504373.6352
21 | Fueling Systems | 150985.99 | 62893 | 88092.99 | 14% | 12333.0186 | 163319.0086
22 | Torus Vacuum Pump | 49156.69 | 0 | 49156.69 | 14% | 6881.9366 | 56038.6266
23 | Wall Conditioning System | 0 |  |  |  |  | 0
25 | Neutral Beam Injection System | 285016 | 285016 | 0 |  |  | 285016
3 | Diagnostics | 971357.1831 | 678515 | 292842.1831 | 30.09% | 88102.4119 | 1059459.595
31 | Magnetic Diagnostics | 592757.5678 | 375656 | 217101.5678 | 30% | 65130.4703 | 657888.0382
36 | Edge & Divertor Diagnostics | 9581.15 | 0 | 9581.15 | 20% | 1916.23 | 11497.38
38 | Electron Beam (EB) Mapping | 30196.8 | 0 | 30196.8 | 34% | 10266.912 | 40463.712
39 | Diagnostics Integration | 338821.6653 | 302859 | 35962.6653 | 30% | 10788.7996 | 349610.4649
4 | Electrical Power Systems | 3165883.2318 | 713298 | 2452585.2318 | 19.47% | 477398.9824 | 3643282.2142
41 | AC Power | 354638.131 | 107351 | 247287.131 | 18% | 44511.6836 | 399149.8146
43 | DC Systems | 720796.0065 | 384666 | 336130.0065 | 18% | 60503.4012 | 781299.4077
44 | Control & protection system | 1027598.6405 | 81687 | 945911.6405 | 19.61% | 185457.3855 | 1213056.026
45 | Power System Design & Integration | 1061550.4538 | 138294 | 923256.4538 | 20.25% | 186926.5121 | 1248476.9659
46 | FCPC Building Modification | 1300 | 1300 | 0 | #DIV/0! | 0 | 1300
5 | Central I&C Systems | 841901.5 | 33022 | 808879.5 | 9.672% | 78237.6042 | 920139.1042
51 | TCP/IP Infrastructure System | 173899.9 | 0 | 173899.9 | 5% | 8694.995 | 182594.895
52 | Central Instrumentation & Controls System | 146660.41 | 0 | 146660.41 | 10% | 14666.041 | 161326.451
53 | Data Acquisition & Facility Computing | 152215.83 | 0 | 152215.83 | 16% | 24354.5328 | 176570.3628
54 | Facility Timing & Synchronization System | 92852.11 | 0 | 92852.11 | 14% | 12999.2954 | 105851.4054
55 | Real Time Plasma & Power Control Systems | 93615.4 | 0 | 93615.4 | 8% | 7489.232 | 101104.632
56 | Central Safety Interlock System | 125418.85 | 0 | 125418.85 | 8% | 10033.508 | 135452.358
58 | Central I&C management and Integration | 57239 | 33022 | 24217 |  | 0 | 57239
6 | Facility Systems | 600451.74 | 24243 | 576208.74 | 20% | 115241.748 | 715693.488
61 | Water Cooling Systems | 29144.78 | 14873 | 14271.78 | 20% | 2854.356 | 31999.136
62 | Cryogenic System | 455033.04 | 0 | 455033.04 | 20% | 91006.608 | 546039.648
63 | Utility Systems | 116273.92 | 9370 | 106903.92 | 20% | 21380.784 | 137654.704
65 | Facility System | 0 |  |  | #DIV/0! |  | 0
7 | Test Cell Preparation & Machine Assy | 4440443.424 | 941616 | 3498827.424 | 28.82% | 1008480.4496 | 5448923.8736
71 | Shield Wall Reconfiguration | 32635 | 32635 | 0 |  | 0 | 32635
72 | Control Room Refurbishment | -0.08 | 0 | -0.08 | 10% | -0.008 | -0.088
73 | Platform Design | 113546.76 | 75940 | 37606.76 | 9.69% | 3644.1906 | 117190.9506
74 | Planning/Oversight | 1774555.114 | 833041 | 941514.114 | 15.2% | 143084.0442 | 1917639.1582
75 | Machine Assembly Planning & Oversight | 2281928.04 | 0 | 2281928.04 | 35.26% | 804685.3612 | 3086613.4012
76 | Tooling Design & Fabrication | 237778.59 | 0 | 237778.59 | 24% | 57066.8616 | 294845.4516
8 | Project Oversight & Support | 12684948.752 | 7745807 | 4939141.752 | 8.918% | 440479.9715 | 13125428.7235
81 | Project Management & Control | 4423308.7922 | 2638335 | 1784973.7922 | 5% | 89248.6896 | 4512557.4818
82 | Project Engineering | 5360363.8392 | 3648997 | 1711366.8392 | 4.649% | 79568.342 | 5439932.1812
84 | Project Physics | 470016 | 470016 | 0 |  |  | 470016
85 | Integrated System Testing | 798741.84 | 0 | 798741.84 | 25.95% | 207257.0119 | 1005998.8519
A | Allocations | 1632518.2806 | 988459 | 644059.2806 | 10% | 64405.9281 | 1696924.2087
| YTD cost variance |  | -107000 |  |  |  | -107000
| TOTAL | 84428976.9948 | 47925030 | 36503946.9948 | 21.64% | 7897635.409 | 92326612.4039 |  |  |  |  | 0 | -92326612.4039
| DCMA | 75000 | 75000 |  |  |  | 75000
|  | 84503976.9948 | 48000030 |  |  |  | 92401612.4039
92401612.4039
ECP-38
[16 empty] | 12 - Vacuum Vessel Systems | 9439.3 | 9439300
[16 empty] | 13 - Conventional Coils | 4831 | 4831000
[16 empty] | 14 - Modular Coils | 31355.9 | 31355900
[16 empty] | 15 - Structures | 1386.2 | 1386200
[16 empty] | 16 - Coil Services | 1135 | 1135000
[16 empty] | 17 - Cryostat and Base Support Structure | 1532.9 | 1532900
[16 empty] | 18 - Field Period Assembly | 5280.8 | 5280800
[16 empty] | 19 - Stellarator Core Management and Integration | 2767 | 2767000
[16 empty] | 21 - Fueling Systems | 88.1 | 88100
[16 empty] | 22 - Torus Vacuum Pumping Systems | 418.8 | 418800
[16 empty] | 25 - Neutral Beam Injection System | 284.4 | 284400
[16 empty] | 31 - Magnetic Diagnostics | 551.6 | 551600
[16 empty] | 36 - Edge and Divertor Diagnostics | 45.6 | 45600
[16 empty] | 38 - Electron Beam (EB) Mapping | 206.2 | 206200
[16 empty] | 39 - Diagnostics Integration | 345.3 | 345300
[16 empty] | 41 - AC Power | 423.9 | 423900
[16 empty] | 43 - DC Systems | 478.8 | 478800
[16 empty] | 44 - Control and protection Systems | 1346 | 1346000
[16 empty] | 45 - Power System Design and Integration | 1055.1 | 1055100
[16 empty] | 46 - FCPC Building Modifications | 1.3 | 1300
[16 empty] | 51 - TCP/IP Infrastructure Systems | 308.3 | 308300
[16 empty] | 52 - Central Instrumentation & Control | 530.1 | 530100
[16 empty] | 53 - Data Acquisition & Facility Computing | 329.1 | 329100
[16 empty] | 54 - Facility Timing & Synchronization | 195.8 | 195800
[16 empty] | 55 - Real Time Plasma & Power Supply Control Sys | 179.3 | 179300
[16 empty] | 56 - Central Safety Interlock Systems | 325.5 | 325500
[16 empty] | 58 - Central I&C management and Integration | 5.5 | 5500
[16 empty] | 61 - Water Systems | 92.3 | 92300
[16 empty] | 62 - Cryogenic Systems | 455 | 455000
[16 empty] | 63 - Utility Systems | 106.9 | 106900
[16 empty] | 65 - Facility Systems Integration | 24 | 24000
[16 empty] | 71 - Shield Wall Seismic Modifications | 32.2 | 32200
[16 empty] | 72 - Control Room Refurbishment | 9.1 | 9100
[16 empty] | 73 - Platform Design & Fabrication | 109.1 | 109100
[16 empty] | 74 - Machine Assembly Planning and Oversight | 1753.2 | 1753200
[16 empty] | 75 - Test Cell and Basement Assembly Operations | 2413.8 | 2413800
[16 empty] | 76 - Tooling Design & Fabrication | 237.8 | 237800
[16 empty] | 81 - Project Management and Control | 4452.9 | 4452900
[16 empty] | 82 - Project Engineering | 4904.1 | 4904100
[16 empty] | 84 - Project Physics | 469.9 | 469900
[16 empty] | 85 - Integrated Systems Testing | 1197.7 | 1197700
[16 empty] | PPPL Allocations | 1608.4 | 1608400
[17 empty] | 82713.2 | 82713200
Note on O4: SC: The committee believes that the NCSX Team has made a credible estimate of the base costs and applied an appropriate level of contingency made on the basis of technical and schedule risk. The base costs estimates have benefited significantly from preliminary manufacturing feasibility studies performed by potential vendors of both the Modular Coil forms and the Vacuum Vessel. The NCSX Team has performed significant analysis of the components deemed to be the most technically risky (modular coils and VV). They have included an appropriate level of manufacturing R&D to mitigate these risks.
Note on O14: SC: Refurbishment of existing systems.
Note on O19: SC: Viable budget estimate for planned effort using new hardware.
Note on O24: SC: All technology and costing data drawn from NSTX.
Note on O30: SC: Install computers & networks & connect existing software systems for controls and data acquisition.
Note on O31: SC: Layout and install standard computer networks.
Note on O32: SC: EPICS control configuration and testing for 5 systems--lots of experience.
Note on O33: SC: Install computer hardware and configure MDS Plus data acquisition--lots of experience
Note on O34: SC: Design and deploy timing and synchronization system based on NSTX.
Note on O35: SC: Clone NSTX real-time control systems
Note on O36: SC: Layout and install safety interlock systems
Note on O38: SC: Extensive use of existing systems with refurbishing. Recent experience with NSTX for cost estimates
Note on O50: SC: Cost reasonable based on review