## Sheet3
3340.3651
| WBS2 | JJJJ |  | BUDGET | COST TO DATE (BCWP plus cost variance) | REMAINING SCOPE | ETC Increases | rate adjustments anticipated | ETC total | Risk | Opportunities | undefined | Total Contingency Balance %$ | Total Contingency Balance % |  | CONTINGENCY $ calculated based on risk % assigned
1 | 12 | 1201 | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 424420 | 424495 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0
5 | 12 | 1202 | Job: 1202 - Vacuum Vessel R&D **CLOSED** | 1770181.86 | 1770580 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0
9 | 12 | 1203 | Job: 1206 - VV Field Weld Joint R&D-**CLOSED** | 1097382.7 | 1119389 | 69865.95 | 70000 |  | 139865.95 |  |  | 13986.595 | 13986.595 | 10% | 10% | 25824.8088 | 36.96% | -26.96%
13 | 12 | 1204 | Job: 1203 - Vacuum Vessel Final Dsn-GORANSON | 431580.4 | 95398 | 398677.8874 | 36000 |  | 434677.8874 |  |  | 86935.5775 | 86935.5775 | 20% | 20% | 124741.4104 | 31.29% | -11.29%
17 | 12 | 1206 | Job: 1204-VV Sys Procurements (non VVSA)-DUDEK | 15639.37 | 15954 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
21 | 12 | 1250 | Job: 1250 - Vacuum Vessel Fabrication-VIOLA | 5669801.66 | 4614203 | 1112713.8688 |  |  | 1112713.8688 |  |  | 111271.3869 | 111271.3869 | 10% | 10% | 127292.5475 | 11.44% | -1.44%
25 | 13 | 1301 | Job: 1301 - TF Design-KALISH | 946845.95 | 964415 | 1356.165 |  |  | 1356.165 |  |  | 0 | 0 | 0% | 0% | 325.4796 | 24% | -24%
29 | 13 | 1302 | Job: 1302 - PF Design -KALISH | 127946.49 | 2328 | 118714.7322 | 10000 | -4248.3818 | 124466.3504 |  |  | 37339.9051 | 37339.9051 | 30% | 30% | 37013.7918 | 31.18% | -1.179%
33 | 13 | 1303 | Job: 1303 -Centrol Solenoid Support Dsn-DAHLGREN | 99910.44 | 81499 | 28456.3732 |  | -1018.3533 | 27438.0199 |  |  | 8231.406 | 8231.406 | 30% | 30% | 9106.0394 | 32% | -2%
37 | 13 | 1350 | Job: 1350 TF Coil Fab Preparation-CHRZANOWSKI | 771023.91 | 545444 | 270299.197 | -260299 |  | 10000.197 |  |  | 2000.0394 | 2000.0394 | 20% | 20% | 64871.8073 | 24% | -4%
41 | 13 | 1351 | Job: 1351 - TF Coil Fabr Supplies-KALISH | 863670.64 | 424000 | 503631.74 | -472632 |  | 30999.74 |  |  | 6199.948 | 6199.948 | 20% | 20% | 120871.6176 | 24% | -4%
61 | 13 | 1361 | Job: 1361 - TF Fabrication-KALISH | 659135.39 | 80609 | 615748.2577 | 1237252 |  | 1853000.2577 |  |  | 185300.0258 | 185300.0258 | 10% | 10% | 412551.3327 | 67% | -57%
45 | 13 | 1352 | Job: 1352 - PF Coil Procurement-KALISH | 895944.98 |  | 895944.98 | -100000 |  | 795944.98 |  |  | 189915.4186 | 189915.4186 | 23.86% | 23.86% | 213775.7888 | 23.86% | 0%
49 | 13 | 1353 | Job: 1353 - CS Structure Procurement-DAHLGREN | 261233.41 |  | 261233.41 | -144000 |  | 117233.41 |  |  | 37514.6912 | 37514.6912 | 32% | 32% | 83594.6912 | 32% | 0%
53 | 13 | 1354 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 103265.03 |  | 103265.03 |  |  | 103265.03 |  |  | 28156.0848 | 28156.0848 | 27.27% | 27.27% | 28156.0848 | 27.27% | 0%
57 | 13 | 1355 | Job: 1355 - WBS 13 I&C Proc & Coil Assy-KALISH | 91239.34 |  | 91239.34 |  |  | 91239.34 |  |  | 18247.868 | 18247.868 | 20% | 20% | 18247.868 | 20% | 0%
65 | 14 | 1401 | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 304040 | 304356 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
69 | 14 | 1402 | Job: 1402 - Mod.Coil Analyses**CLOSED** | 239140 | 239140 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
73 | 14 | 1403 | Job: 1403 - Modular Coil Final Design-WILLIAMSON | 3164248.6 | 3431690 | 55116.699 | 10000 |  | 65116.699 |  |  | 3255.8349 | 3255.8349 | 5% | 5% | 16535.0097 | 30% | -25%
77 | 14 | 1404 | Job: 1404-MCWF R&D & 1st Prod Casting**CLOSED** | 2543518.06 | 2543679 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
81 | 14 | 1405 | Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 168070 | 168000 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
85 | 14 | 1406 | Job: 1406 - Mod. Coil Winding R&D-**CLOSED** | 2246588.41 | 2263565 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
89 | 14 | 1407 | Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 2545993.12 | 2571368 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
93 | 14 | 1408 | Job: 1408-Mod Coil Winding Supplies-CHRZANOWSKI | 1812571.43 | 1156321 | 677450.5865 |  |  | 677450.5865 |  |  | 67745.0586 | 67745.0586 | 10% | 10% | 202138.6501 | 29.84% | -19.84%
97 | 14 | 1409 | Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* | 915941.31 | 861721 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
101 | 14 | 1410 | Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** | 1050211.32 | 1049967 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
105 | 14 | 1411 | Job: 1411-MCWF Fabrication S005242-HEITZENROEDER | 9589016.45 | 6164980 | 3416294.9769 |  |  | 3416294.9769 | 410000 |  | 0 | 410000 | 12% | 0% | 352510.7954 | 10.32% | 1.683%
109 | 14 | 1412 | Job: 1412 - Complete Winding Facilities-*CLOSED* | 537436.88 | 540987 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
113 | 14 | 1413 | Job: 1413 -MCWF Fracture Analysis-**CLOSED** | 28169.4 | 27819 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
117 | 14 | 1414 | Job: 1414 Coil Testing-Gettelfinger | 295356.88 | 345839 | 79584.45 | 66000 |  | 145584.45 |  |  | 21837.6675 | 21837.6675 | 15% | 15% | 24157.6678 | 30.35% | -15.35%
121 | 14 | 1415 | Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** | 23850 | 24038 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
125 | 14 | 1416 | Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON | 759854.45 | 208505 | 339650.222 | -107000 |  | 232650.222 |  |  | 23265.0222 | 23265.0222 | 10% | 10% | 67930.0444 | 20% | -10%
129 | 14 | 1419 | Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* | 48000 | 55216 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
133 | 14 | 1421 | Job: 1421-Mod Coil Interface Hardware-WILLIAMSON | 830273.33 |  | 740966.51 | 195000 |  | 935966.51 |  |  | 374386.604 | 374386.604 | 40% | 40% | 296386.604 | 40% | 0%
137 | 14 | 1451 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5161816.69 | 1430133 | 4224226.8807 | 600000 | -151170.1909 | 4673056.6898 | 618000 |  | 264552.8345 | 882552.8345 | 18.89% | 5% | 1238723.502 | 29.32% | -10.44%
0%
145 | 15 | 1501 | Job: 1501 - Structures Design- DAHLGREN | 213033.59 | 82401 | 132981.84 |  |  | 132981.84 |  |  | 42554.1888 | 42554.1888 | 32% | 32% | 42554.1888 | 32% | 0%
149 | 15 | 1550 | Job: 1550 - Structures Procurement -DAHLGREN | 1177737.32 |  | 1177737.32 | -63000 |  | 1114737.32 |  |  | 355572.1224 | 355572.1224 | 31.9% | 31.9% | 375667.4788 | 31.9% | 0%
153 | 16 | 1601 | Job: 1601 - Coil Services Design-WILLIAMSON | 1131647.95 | 2792 | 1131647.95 |  |  | 1131647.95 |  |  | 280747.6374 | 280747.6374 | 24.81% | 24.81% | 280747.6374 | 24.81% | 0%
157 | 17 | 1701 | Job: 1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 680400.07 | 414775 | 312111.008 |  |  | 312111.008 |  |  | 90512.1923 | 90512.1923 | 29% | 29% | 90182.2442 | 28.89% | 0.1057%
161 | 17 | 1751 | Job: 1751 - Cryostat Procurement | 540573.45 |  | 540573.45 |  |  | 540573.45 |  | -250000 | 81360.566 | -168639.434 | -31.2% | 28% | 151360.566 | 28% | -59.2%
165 | 17 | 1752 | Job: 1752 - Base Support Structure Procurement | 311405.26 |  | 311405.26 |  |  | 311405.26 |  |  | 99649.6832 | 99649.6832 | 32% | 32% | 99649.6832 | 32% | 0%
169 | 18 | 1801 | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 60800 | 64685 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
173 | 18 | 1802 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1484981.24 | 504658 | 966048.3638 | 168000 |  | 1134048.3638 |  |  | 272171.6073 | 272171.6073 | 24% | 24% | 231851.6073 | 24% | 0%
177 | 18 | 1803 | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1037244.73 | 663923 | 379373.6506 | 252000 |  | 631373.6506 |  |  | 279757.8562 | 279757.8562 | 44.31% | 44.31% | 168098.1762 | 44.31% | 0%
181 | 18 | 1804 | Job: 1804-FP Assy Measurement Sys-RAFTOPOULOS | 491881.92 | 532184 | 41389.1 | 74000 |  | 115389.1 | 18000 |  | 9337.237 | 27337.237 | 23.69% | 7% | 9933.384 | 24% | -0.3086%
185 | 18 | 1810 | Job: 1810 - Field Period Assembly-VIOLA | 2199100.72 | 10198 | 2189309.9318 | 163000 |  | 2352309.9318 |  |  | 940923.9727 | 940923.9727 | 40% | 40% | 867051.766 | 39.6% | 0.3961%
189 | 19 | 1901 | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 2768760.87 | 1746366 | 1024933.2795 |  |  | 1024933.2795 |  |  | 102493.328 | 102493.328 | 10% | 10% | 102493.3279 | 10% | 0%
193 | 20 | 2001 | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 63667 | 62893 |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
197 | 21 | 2101 | Job: 2101 - Fueling Systems | 88092.99 |  | 88092.99 |  |  | 88092.99 |  |  | 12333.0186 | 12333.0186 | 14% | 14% | 12333.0186 | 14% | 0%
205 | 22 | 2201 | Job: 2201 - Vacuum Pumping Systems | 355156.69 |  | 355156.69 | -306000 |  | 49156.69 |  |  | 6881.9366 | 6881.9366 | 14% | 14% | 49721.9366 | 14% | 0%
209 | 25 | 2501 | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 284367.67 | 285016 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
213 | 31 | 3101 | Job: 3101 Magnetic Diagnostics | 523726.79 | 375656 | 224480.6245 |  |  | 224480.6245 |  |  | 67344.1873 | 67344.1873 | 30% | 30% | 67344.1873 | 30% | 0%
217 | 36 | 3601 | Job: 3601 - Edge and Divertor Diagnostics | 45581.15 |  | 45581.15 | -36000 |  | 9581.15 |  |  | 1916.23 | 1916.23 | 20% | 20% | 9116.23 | 20% | 0%
221 | 38 | 3801 | Job: 3801 - Electron Beam Mapping | 206196.8 |  | 206196.8 | -176000 | -7379.0567 | 22817.7433 |  |  | 7758.0327 | 7758.0327 | 34% | 34% | 70106.912 | 34% | 0%
225 | 39 | 3901 | Job: 3901 - Diagnostics sys Integration-JOHNSON | 345322.33 | 302859 | 35962.6653 |  |  | 35962.6653 |  |  | 10788.7996 | 10788.7996 | 30% | 30% | 10788.7996 | 30% | 0%
229 | 41 | 4101 | Job: 4101 - AC Power-RAMAKRISHNAN | 423012.85 | 107351 | 315264.131 | -67977 |  | 247287.131 |  |  | 44511.6836 | 44511.6836 | 18% | 18% | 56747.5436 | 18% | 0%
233 | 43 | 4301 | Job: 4301 - DC Systems-RAMAKRISHNAN | 537668.92 | 384666 | 266130.0065 | 70000 |  | 336130.0065 |  |  | 60503.4012 | 60503.4012 | 18% | 18% | 47903.4012 | 18% | 0%
237 | 44 | 4401 | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1344443.7 | 81687 | 1285645.6405 | -339734 |  | 945911.6405 |  |  | 185457.3855 | 185457.3855 | 19.61% | 19.61% | 252066.3337 | 19.61% | 0%
241 | 45 | 4501 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1056150.65 | 138294 | 923256.4538 |  |  | 923256.4538 |  |  | 186926.5121 | 186926.5121 | 20.25% | 20.25% | 186926.5121 | 20.25% | 0%
245 | 46 | 4601 | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 1300 | 1300 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
249 | 51 | 5101 | Job: 5101 - TCP/IP Infrastructure Systems | 280385.9 |  | 280385.9 | -106486 |  | 173899.9 |  |  | 8694.995 | 8694.995 | 5% | 5% | 14019.295 | 5% | 0%
253 | 52 | 5201 | Job: 5201 - I&C Systems | 530112.41 |  | 530112.41 | -383452 |  | 146660.41 |  |  | 14666.041 | 14666.041 | 10% | 10% | 53011.241 | 10% | 0%
257 | 53 | 5301 | Job: 5301 - Data Acquisition | 329072.83 |  | 329072.83 | -176857 |  | 152215.83 |  |  | 24354.5328 | 24354.5328 | 16% | 16% | 52651.6528 | 16% | 0%
261 | 54 | 5401 | Job: 5401 - Facility Timing & Synchronization | 195823.11 |  | 195823.11 | -102971 |  | 92852.11 |  |  | 12999.2954 | 12999.2954 | 14% | 14% | 27415.2354 | 14% | 0%
265 | 55 | 5501 | Job: 5501 - Real Time Control System | 179331.4 |  | 179331.4 | -85716 |  | 93615.4 |  |  | 7489.232 | 7489.232 | 8% | 8% | 14346.512 | 8% | 0%
269 | 56 | 5601 | Job: 5601 - Central Safety Interlock Systems | 325498.85 |  | 325498.85 | -200080 |  | 125418.85 |  |  | 10033.508 | 10033.508 | 8% | 8% | 26039.908 | 8% | 0%
273 | 58 | 5801 | Job: 5801 -Central I&C Integr & Oversight-SICHTA | 33362.26 | 33022 | 0 | 24217 |  | 24217 |  |  | 0 | 0 | 0% |  | 0 |  | 0%
277 | 61 | 6101 | Job: 6101 - Water Systems | 92271.78 |  | 92271.78 | -78000 |  | 14271.78 |  |  | 2854.356 | 2854.356 | 20% | 20% | 18454.356 | 20% | 0%
281 | 61 | 6163 | Job: 6163 - Facility Systems Support FY04 | 15000 | 14873 |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
285 | 62 | 6201 | Job: 6201 - Cryogenic Systems | 455033.04 |  | 455033.04 |  |  | 455033.04 |  |  | 91006.608 | 91006.608 | 20% | 20% | 91006.608 | 20% | 0%
289 | 63 | 6301 | Job: 6301 - Utility Systems | 106903.92 |  | 106903.92 |  |  | 106903.92 |  |  | 21380.784 | 21380.784 | 20% | 20% | 21380.784 | 20% | 0%
297 | 65 | 6501 | Job: 6501 - Facility Systems Integration-DUDEK | 9380 | 9370 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
301 | 71 | 7101 | Job: 7101 - Shield Wall Modif Design-PERRY | 32150 | 32635 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
305 | 72 | 7201 | Job: 7201 - Control Room Walls&Floors-PERRY | 9097.92 |  | 9097.92 | -9098 |  | -0.08 |  |  | -0.008 | -0.008 | 10% | 10% | 909.792 | 10% | 0%
309 | 73 | 7301 | Job: 7301 - Platform Design & Fab-PERRY | 109811.07 | 75940 | 37606.76 |  |  | 37606.76 |  |  | 3644.1906 | 3644.1906 | 9.69% | 9.69% | 3644.1906 | 9.69% | 0%
313 | 74 | 7401 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1752911.82 | 833041 | 951994.114 | -10480 |  | 941514.114 |  |  | 143084.0442 | 143084.0442 | 15.2% | 15.2% | 144676.7137 | 15.2% | 0%
317 | 75 | 7501 | Job: 7501 - Construction Support Crew | 1063414.52 |  | 1063414.52 | -135000 |  | 928414.52 |  |  | 222819.4848 | 222819.4848 | 24% | 24% | 255219.4848 | 24% | 0%
321 | 75 | 7502 | Job: 7502 - Test Cell Facility Preparations | 74580 |  | 74580 |  |  | 74580 |  |  | 17899.2 | 17899.2 | 24% | 24% | 17899.2 | 24% | 0%
325 | 75 | 7503 | Job: 7503 - Machine Assembly | 1278933.52 |  | 1278933.52 |  |  | 1278933.52 |  |  | 311195.0688 | 311195.0688 | 24.33% | 24.33% | 311195.0688 | 24.33% | 0%
329 | 76 | 7601 | Job: 7601 - Tooling Design & Fabrication | 237778.59 |  | 237778.59 |  |  | 237778.59 |  |  | 57066.8616 | 57066.8616 | 24% | 24% | 57066.8616 | 24% | 0%
333 | 81 | 8101 | Job: 8101 - Project Management & Control-NEILSON | 3937093.83 | 2292540 | 1673806.4526 | -5000 | -59899.6333 | 1608906.8194 |  |  | 80445.341 | 80445.341 | 5% | 5% | 83690.3226 | 5% | 0%
337 | 81 | 8102 | Job: 8102 - NCSX MIE Management ORNL-LYON | 515757.95 | 345795 | 176066.9728 |  |  | 176066.9728 |  |  | 8803.3486 | 8803.3486 | 5% | 5% | 17606.6973 | 10% | -5%
345 | 82 | 8202 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2789387.82 | 1965095 | 868735.2384 | 109000 | -31088.9722 | 946646.2662 | 339000 |  | 0 | 339000 | 35.81% | 0% | 43436.7619 | 5% | 30.81%
349 | 82 | 8203 | Job: 8203 - Design Integration-BROWN | 959530.24 | 750990 | 204763.1397 | 66000 | -7327.751 | 263435.3886 | 333000 |  | 0 | 333000 | 126.4% | 0% | 10238.157 | 5% | 121.4%
353 | 82 | 8204 | Job: 8204 - Systems Analysis-BROOKS | 724459.95 | 750967 | 115408.7424 | 77000 | -4130.0721 | 188278.6703 | 304000 |  | 0 | 304000 | 161.5% | 0% | 5770.4371 | 5% | 156.5%
357 | 82 | 8205 | Job: 8205 - Dimensional Control Coordination | 428680.72 | 181945 | 246840.0494 | 75000 | -8833.5353 | 313006.514 | 207000 |  | 0 | 207000 | 66.13% | 0% | 61710.0123 | 5% | 61.13%
361 | 84 | 8401 | Job: 8401 - Project Physcis-ZARNSTORFF | 324076.2 | 323549 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
365 | 84 | 8402 | Job: 8402 - Project Physics MIE ORNL-LYON | 145856 | 146467 | 0 |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
369 | 85 | 8501 | Job: 8501 - Integrated Systems Testing | 1195741.84 |  | 1195741.84 | -397000 |  | 798741.84 |  |  | 207257.0119 | 207257.0119 | 25.95% | 25.95% | 310270.313 | 25.95% | 0%
341 | 81 | 8998 | Job: 8998 - Allocations | 1608428.21 | 988459 | 667963.334 |  | -23904.0534 | 644059.2806 |  |  | 64405.9281 | 64405.9281 | 10% | 10% | 66796.3334 | 10% | 0%
377 | dcma | dcma |  | 75000 | 75000 |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 |  | 0%
|  | FY06 ytd | [5 empty] | -107000 |  |  |  |  | -107000 |  |  |  |  | 0%
0%
|  |  |  | 83680438.26 | 48107030 | 37254879.9948 | -460313 | -406000 | 36495566.9948 | 2229000 | -250000 | 5929743.3703 | 7801743.3703 | 21.38% | 9.323% | 8355856.4142 | 22.43% | -1.052%
7880000
[13 empty] | -78256.6297 |  |  | 92036294.6742
8720000
|  |  |  | 92400438.26 | 48032030 | [6 empty] | 92404340.3651 | 7908743.3703
|  |  |  | 92399909.9948 | [7 empty] | 92401000
3340.3651

## CONT14
ACT | TITLE | EVC | BC | Cost to Date | BCWR | cont % | cont$ | WBS1 | WBS2 | WBS3 | CCCC | JJJJ | PHAS | WBS4 | ORDR | DSNR | WAF | JOBX | CCXX | PCTC
FY05CV-29 | FY05 unrecoverable cost variance | -148000 | -148000 |  | 0 | 0% | 0 | 1 | 18 | 186 | 9450 | 1803
FY05CV-37 | FY05 unrecoverable cost variance | -52000 | -52000 |  | 0 | 0% | 0 | 4 | 45 | 451 | 9450 | 4501
FY05CV-39 | FY05 unrecoverable cost variance | -50000 | -50000 |  | 0 | 0% | 0 | 7 | 73 | 730 | 9450 | 7301
FY05CV-4 | FY05 unrecoverable cost variance | -49000 | -49000 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1250 | [7 empty] | 100
FY05CV-45 | FY05 unrecoverable cost variance | -36000 | -36000 |  | 0 | 0% | 0 | 8 | 82 | 820 | 9450 | 8203
FY05CV-15 | FY05 unrecoverable cost variance | -30000 | -30000 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1410 | [7 empty] | 100
FY05CV-6 | FY05 unrecoverable cost variance | -22000 | -22000 |  | 0 | 0% | 0 | 1 | 13 | 132 | 9450 | 1302 |  | TFIC
FY05CV-1 | FY05 unrecoverable cost variance | -21000 | -21000 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | [7 empty] | 100
FY05CV-47 | FY05 unrecoverable cost variance | -20000 | -20000 |  | 0 | 0% | 0 | 8 | 82 | 820 | 9450 | 8205
FY05CV-44 | FY05 unrecoverable cost variance | -19000 | -19000 |  | 0 | 0% | 0 | 8 | 82 | 820 | 9450 | 8202
FY05CV-33 | FY05 unrecoverable cost variance | -12000 | -12000 |  | 0 | 0% | 0 | 3 | 39 | 390 | 9450 | 3901
FY05CV-38 | FY05 unrecoverable cost variance | -7000 | -7000 |  | 0 | 0% | 0 | 5 | 58 | 580 | 9450 | 5801
FY05CV-17 | FY05 unrecoverable cost variance | -3000 | -3000 |  | 0 | 0% | 0 | 1 | 14 | 144 | 9450 | 1412 | [7 empty] | 100
FY05CV-41 | FY05 unrecoverable cost variance | -3000 | -3000 |  | 0 | 0% | 0 | 8 | 81 | 810 | 9450 | 8101
FY05CV-3 | FY05 unrecoverable cost variance | -2000 | -2000 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1206 | [7 empty] | 100
25-190.1 | 33) Fabr BL alignment measur fixture, | 26.85 | 26.85 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | F | 2515 | 10 | 1 |  | 25 | 16
1202-002 | Apr-Sept MIE Cost ORNL | 60 | 60 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 0000 | 10 | 1 |  |  | 0 | 100
4101-100.1 | Prepare Preliminary One line diagram | 0 | 189.38 |  | 189.38 | 18% | 34.0884 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
4101-100.1 | Prepare Preliminary One line diagram | 0 | 207.07 |  | 207.07 | 18% | 37.2726 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
1409-000 | FY04 Oct-Mar | 223.56 | 223.56 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1351-140A | Assemble TF to Wedge Casting TF#7 | 0 | 249.66 |  | 249.66 | 67% | 167.2722 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1406-57 | fab cooling tube/chill plate assy | 254.8 | 254.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
3101-154 | Fab Installation Templates (for spacers) | 0 | 256.4 |  | 256.4 | 30% | 76.92 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 19 |  |  |  | 30
4101-100.1 | Prepare Preliminary One line diagram | 0 | 268.26 |  | 268.26 | 18% | 48.2868 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
1206-110 | Weld | 298.08 | 298.08 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1206 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
25-230.1 | Cabling-Fabr and Install new Junction Box | 298.08 | 298.08 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | F | 2520 | 12 | 1 |  | 25 | 16
3101-153 | Fab Installation Templates (for FP assy) | 312.32 | 312.32 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 16 |  |  |  | 30 | 100
1406-54 | Complete shear modulus & cyclic testing | 318.5 | 318.5 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
133-015 | Title III WBS 134 Conv Coil I&C | 0 | 355.72 |  | 355.72 | 20% | 71.144 | 1 | 13 | 134 | 9450 | 1355 | F | 134 |  | 1 |  |  | 20
25-190.1 | 33) Fabr BL alignment measur fixture, | 372.6 | 372.6 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | F | 2515 | 10 | 1 |  | 25 | 16
4101-100.1 | Prepare Preliminary One line diagram | 0 | 412.25 |  | 412.25 | 18% | 74.205 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
25-230.1 | Cabling-Fabr and Install new Junction Box | 429.6 | 429.6 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | F | 2520 | 12 | 1 |  | 25 | 16
1406-016.6 | PPPL Fabricate TRC Chill plates | 486.78 | 486.78 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1351-865 | Warm Test Coil #9 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-867 | Warm Test Coil #10 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-869 | Warm Test Coil #11 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-871 | Warm Test Coil #12 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-873 | Warm Test Coil #13 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-875 | Warm Test Coil #14 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-877 | Warm Test Coil #15 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-879 | Warm Test Coil #16 | 0 | 499.32 |  | 499.32 | 67% | 334.5444 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1407-006.2 | Blower/Elec HW- Fab & Deliver (PE 4218) | 509.6 | 509.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 11 | 1 |  |  | 34 | 100
1351-881 | Warm Test Coil #17 | 0 | 512.76 |  | 512.76 | 67% | 343.5492 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-883 | Warm Test Coil #18 | 0 | 512.76 |  | 512.76 | 67% | 343.5492 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1203-181 | Start Thermal Analyses | 514.76 | 514.76 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1301FD-09 | Electrical Test 1st Sample | 596.16 | 596.16 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1301FD-11 | Machine Copper Bars 2nd Sample | 596.16 | 596.16 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1406-017.G | Reposition Coil Side a | 596.16 | 596.16 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-017.G | Reposition Coil Side a | 596.16 | 596.16 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1301-160 | Trim Coil Leads | 618 | 618 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1301-300 | Investigate Experimental Data *ECP6* | 618 | 618 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1301-318 | Evaluate 3D glass *ECP6* | 618 | 618 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1403-40.2Z | Update nonlinear winding pack analysis | 564.228 | 626.92 |  | 62.692 | 30% | 18.8076 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 08 | 1 |  |  | 30 | 90
1406-52 | Ship Tee specimen to ORNL | 637 | 637 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-55 | Fab chill plate specimens | 637 | 637 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
25-099 | FY04 work accomplished | 641.68 | 641.68 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 2510 |  | 1 |  | 25 | 16
25-190.1 | 33) Fabr BL alignment measur fixture, | 641.68 | 641.68 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | F | 2515 | 10 | 1 |  | 25 | 16
1203-191 | Start Eddy Current Analyses | 643.45 | 643.45 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1803-3.04 | VV support stand - model design and drawing deta | 661 | 661 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 25 | 1 |  |  | 40 | 100
1351-857 | Warm Test Coil #5 | 0 | 665.76 |  | 665.76 | 67% | 446.0592 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-859 | Warm Test Coil #6 | 0 | 665.76 |  | 665.76 | 67% | 446.0592 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-861 | Warm Test Coil #7 | 0 | 665.76 |  | 665.76 | 67% | 446.0592 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-863 | Warm Test Coil #8 | 0 | 665.76 |  | 665.76 | 67% | 446.0592 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
S3P1-110.1 | Remove temp interference strips&sensors | 0 | 665.76 |  | 665.76 | 40% | 266.304 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P2-110.1 | Remove temp interference strips&sensors | 0 | 665.76 |  | 665.76 | 40% | 266.304 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
1416A-213 | Clamp Assy-Clamp Hardware | 674.8 | 674.8 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416A-217 | Clamp Assy-Check and Promote | 674.8 | 674.8 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416B-213 | Clamp Assy-Clamp HardwareDELETED | 674.8 | 674.8 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-217 | Clamp Assy-Check and Promote DELETED | 674.8 | 674.8 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
S3P3-110.1 | Remove temp interference strips&sensors | 0 | 683.68 |  | 683.68 | 40% | 273.472 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
2501-014.1 | FY04 work closeout *TBD* | 753.5 | 753.5 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16 | LOE
1413-140 | Wire EDM 12 specimens (Crystal) | 768.6 | 768.6 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1413 | 2 |  | 30 |  |  |  | 10 | 100
1301-303 | Prepare Test Reqmnts *ECP6* | 772.5 | 772.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1301-180 | Update ANSYS model & structure | 772.5 | 772.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
133-015 | Title III WBS 134 Conv Coil I&C | 0 | 786 |  | 786 | 20% | 157.2 | 1 | 13 | 134 | 9450 | 1355 | F | 134 |  | 1 |  |  | 20
1407.011.5 | Write autoclave PTP | 811.2 | 811.2 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1404-FR4 | Rough machine Lot 2 (11 specimens) at PPPL | 819.72 | 819.72 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | 2 | FRAC | 15 |  |  |  | 40 | 100
1351-851 | Warm Test Coil #2 | 0 | 832.2 |  | 832.2 | 67% | 557.574 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-853 | Warm Test Coil #3 | 0 | 832.2 |  | 832.2 | 67% | 557.574 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
1351-855 | Warm Test Coil #4 | 0 | 832.2 |  | 832.2 | 67% | 557.574 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
3101-517A | Install termination boxes | 0 | 832.2 |  | 832.2 | 30% | 249.66 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30
121-033 | VVSA Contract oversight FY05 | 832.5 | 832.5 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
3101-337 | INSTALL COILS AND TERMINATIONS | 0 | 846.39 |  | 846.39 | 30% | 253.917 | 3 | 31 | 310 | 9450 | 3101 | F | MD3 |  |  |  |  | 30
1301-190 | FEA Analysis PF Supports,Stress Deflection | 865.2 | 865.2 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 45 | 1 |  |  | 24 | 100
1406-016.6 | PPPL Fabricate TRC Chill plates | 894.24 | 894.24 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1803-1.07 | Design check and sign-off | 894.29 | 894.29 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 55 | 1 |  |  | 20 | 100
451-1-2 | Calculations-Dsn | 0 | 946.88 |  | 946.88 | 18% | 170.4384 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 16 | 1 |  | 45 | 18
1404-FR5 | Machine Lot 2 specimens to ASTM spec. (Crystal E | 960.75 | 960.75 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | 2 | FRAC | 15 |  | C |  | 40 | 100
S1P1-102 | Mount VV on VV Prep fixture (top side up) | 0 | 977.28 |  | 977.28 | 40% | 390.912 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 11 |  |  |  | 40
S1P2-102 | Mount VV on VV Prep fixture (top side up) | 0 | 977.28 |  | 977.28 | 40% | 390.912 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 11 |  |  |  | 40
1803-3.05 | Platform - design and drawing details | 991.5 | 991.5 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 30 | 1 |  |  | 40 | 100
S1P3-102 | Mount VV on VV Prep fixture (top side up) | 0 | 998.64 |  | 998.64 | 40% | 399.456 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 12 |  |  |  | 40
FY05CV-9 | FY05 unrecoverable cost variance | 1000 | 1000 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1401 | [7 empty] | 100
1403-03 | Increase for actual cost of Final Design ECP 11 | 1000 | 1000 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW06 | 01 | 1 |  |  | 40 | 100
3101-105 | DEVELOP LOCATING, MOUNTING STRATEGY | 1000 | 1000 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
25-190.1 | 33) Fabr BL alignment measur fixture, | 1019.2 | 1019.2 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | F | 2515 | 10 | 1 |  | 25 | 16
1406-016.A | fab trc lead components | 1022.81 | 1022.81 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-4 | 63 | 1 |  | 141 | 40 | 100
7503-170 | FPA Metrology Checks to Assure Alignment | 0 | 1025.52 |  | 1025.52 | 24% | 246.1248 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 03 |  |  |  | 24
1403-54 | Final bid package( specs,models,dwgs) | 1029.52 | 1029.52 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW07 | 11 | 1 |  | 141 | 40 | 100
1403-202 | G-10 Filler DwgsType C ????????????? | 1029.52 | 1029.52 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
153.015 | Title III design WBS 153 localI&C | 0 | 1048.11 |  | 1048.11 | 20% | 209.622 | 1 | 15 | 151 | 9450 | 1550 | F |  | 18 | 1 |  |  | 20
445-2-0 | Overload Protection & Cabling-Prelim Dsn | 1054.9 | 1054.9 |  | 0 | 22% | 0 | 4 | 44 | 445 | 9450 | 4401 | 2 | 445 |  | 1 |  | 44 | 22
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 1070.83 | 1070.83 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
132-015 | Title III design WBS 162 Coil leads | 0 | 1076.16 |  | 1076.16 | 22% | 236.7552 | 1 | 16 | 162 | 9450 | 1601 | F | 162 | 01 | 1 |  |  | 22
1301-185 | FEA Analysis Coils,Stress deflection | 1081.5 | 1081.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
1301-195 | Seismic Analysis | 1081.5 | 1081.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
1404-FR2 | Machine Lot 1 specimens to ASTM spec (Crystal En | 1082.9 | 1082.9 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | 2 | FRAC | 15 |  |  |  | 40 | 100
1403-203 | Start Clamp Dwgs (5)-Type C | 1085 | 1085 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1413-120 | Weld quartered discs (Metal Tek) | 1127.28 | 1127.28 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1413 | 2 |  | 30 |  |  |  | 10 | 100
1202-806 | Waterjet Arcs *ECP6* | 1192.32 | 1192.32 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-815 | Setup weld test *ECP6* | 1192.32 | 1192.32 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1407-127 | Fab Type B casting supports (6) sets | 1192.32 | 1192.32 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1407-127 | Fab Type B casting supports (6) sets | 1192.32 | 1192.32 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1407-108 | Mount mixing tanks onto VPI platforms | 1192.32 | 1192.32 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | VPI | 20 | 1 |  | 141 | 34 | 100
1407-108 | Mount mixing tanks onto VPI platforms | 1192.32 | 1192.32 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | VPI | 20 | 1 |  | 141 | 34 | 100
1406-017.C | Position & prep 1st coil lead set Side b | 1192.32 | 1192.32 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-017.C | Position & prep 1st coil lead set Side b | 1192.32 | 1192.32 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-019.2 | Electrical & Pressure tests | 1192.32 | 1192.32 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 70 | 1 | C | 141 | 30 | 100
2501-014 | FY04 work accomplished | 1192.32 | 1192.32 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16
3101-129 | DESIGN AND PROTOTYPE SADDLE LOOP TERMINATIONS | 1226.72 | 1226.72 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
1301-145 | Post Draft SOW on WEB to Solicit Vendr Input | 1236 | 1236 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1301-170 | New Lead Details | 1236 | 1236 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
1301R-05 | Change Insulation Scheme | 1236 | 1236 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 69 | 1 |  |  | 24 | 100
1403-60 | Start Update design basis document | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1406-150 | Winding pack assy | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-151 | Lead ends & closure | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-152 | Terminal Assy | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-153 | VPI mold assy | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-154 | Clamp assy | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-155 | Cooling ,electr schematics | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-156 | I&C dwgs | 1240 | 1240 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1206-100 | Prep Sample | 1260.24 | 1260.24 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1206 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1404-FR1 | Rough machine specimens, Lot 1 (17 pcs.) at PPPL | 1266.84 | 1266.84 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | 2 | FRAC | 15 |  |  |  | 40 | 100
1301R-25 | Final Determination ofLaunching Loads | 1274 | 1274 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 74 | 1 |  |  | 24 | 100
1406-031 | Prep fixtures and test equipt | 1274 | 1274 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-016.5 | PPPL Fabricate TRC Cladding | 1279.14 | 1279.14 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-4 | 63 | 1 | C | 141 | 40 | 100
1406-016.7 | Finish TRC Chill plates | 1281 | 1281 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 30 | 100
1202-327 | PPPL Receipt Inspection of MT PVVS | 1283.36 | 1283.36 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 40 | 100
1202-427 | PPPL Receipt Inspection of RW PVVS | 1283.36 | 1283.36 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 50 | 1 |  |  | 40 | 100
1406-210 | Dogbone test @RT | 1283.36 | 1283.36 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 20 | 1 |  |  | 40 | 100
1403-54 | Final bid package( specs,models,dwgs) | 1283.36 | 1283.36 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW07 | 11 | 1 |  | 141 | 40 | 100
121-6-6 | Finalize tech Doc package & Resolve chits | 1286.9 | 1286.9 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12VS | 17 | 1 |  | 12 | 40 | 100
121-6-8 | Evaluate and Select VV Production Vendor | 1286.9 | 1286.9 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12VS | 18 | 1 |  | 12 | 40 | 100
4601-001 | Apr-Sept MIE Cost | 1300 | 1300 |  | 0 | 0% | 0 | 4 | 46 | 460 | 9450 | 4601 | 1 | 0000 |  | 1 |  |  | 0 | 100
1351-849 | Warm Test Coil #1 | 0 | 1303.04 |  | 1303.04 | 67% | 873.0368 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
711A.040 | Platform nut plates | 1178.46 | 1309.4 |  | 130.94 | 6% | 7.8564 | 7 | 73 | 730 | 9450 | 7301 | F |  | 27 | 1 |  |  | 6 | 90
1803-1.02 | VV Support Fixture - model design& drawing detai | 1322 | 1322 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 15 | 1 |  |  | 20 | 100
1352-135X | Refurbish NSTX PF1a | 0 | 1331.52 |  | 1331.52 | 24% | 319.5648 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 48 | 1 |  | 13 | 24
613.030 | Test Cell copper ground plane cuts | 1066.008 | 1332.51 |  | 266.502 | 24% | 63.9605 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  | 7 | 24 | 80
1407-100.6 | Complete Electr hookup turning fixtures 4 | 1341.36 | 1341.36 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  | 141 | 28 | 100
12003-952 | Personnel Access Port FDR | 1349.6 | 1349.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 124P | 08 | 1 |  |  | 40 | 100
S4P1-110 | Inspect Welds | 0 | 1367.36 |  | 1367.36 | 40% | 546.944 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P2-110 | Inspect Welds | 0 | 1367.36 |  | 1367.36 | 40% | 546.944 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-110 | Inspect Welds | 0 | 1367.36 |  | 1367.36 | 40% | 546.944 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
1350-510 | Taping Machine Conditioning | 1096.8 | 1371 |  | 274.2 | 24% | 65.808 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 80
452-1-4 | Diagnostics AC Power Distr-Procure | 0 | 1372.12 |  | 1372.12 | 26% | 356.7512 | 4 | 45 | 452 | 9450 | 4501 | T | 452 |  | 1 |  | 45 | 26
411-3-2 | Test Cell AC Power Distr-Dsn | 0 | 1374.16 |  | 1374.16 | 18% | 247.3488 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
441-130 | Pre-commissioning tests | 0 | 1403.25 |  | 1403.25 | 18% | 252.585 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 1411.12 |  | 1411.12 | 26% | 366.8912 | 4 | 45 | 452 | 9450 | 4501 | S | 452 |  | 1 |  | 45 | 26
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 1423.62 |  | 1423.62 | 30% | 427.086 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 46 | 1 |  | 141 | 30
191-031 | Title III engr WBS 161 | 0 | 1435.61 |  | 1435.61 | 28% | 401.9708 | 1 | 16 | 161 | 9450 | 1601 | F | 161 |  | 1 |  |  | 28
4101-100 | Prepare Preliminary One line diagram | 1460.16 | 1460.16 |  | 0 | 18% | 0 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18 | 100
1202-848 | Bid,eval,award full size test sample **ECP36** | 1471.05 | 1471.05 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1206 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1407-110.2 | Compl Fabr Winding clamp sets (100 of 400) | 1490.4 | 1490.4 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 24 | 1 |  |  | 28 | 100
1406-016.A | fab trc lead components | 1490.4 | 1490.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-4 | 63 | 1 |  | 141 | 40 | 100
3101-209 | PROTOTYPE ON TWISTED RACETRACK | 1533.4 | 1533.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 00 |  |  |  | 30 | 100
4101-100 | Prepare Preliminary One line diagram | 1546.56 | 1546.56 |  | 0 | 18% | 0 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18 | 100
3101-157 | Design & fab tooling and clamps | 1571.19 | 1571.19 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 20 |  |  |  | 30 | 100
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 1572.17 |  | 1572.17 | 20% | 314.434 | 1 | 15 | 151 | 9450 | 1550 | T |  | 17 | 1 |  |  | 20
3101-301 | LAYOUT LOCATION ROWGOSKI COIL &EST COIL DIMEN | 1591.7 | 1591.7 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30 | 100
121-6-8 | Evaluate and Select VV Production Vendor | 1604.2 | 1604.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12VS | 18 | 1 |  | 12 | 40 | 100
121-6-83 | Negotiate with vendor | 1604.2 | 1604.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12VS | 19 | 1 |  | 12 | 40 | 100
1350-610 | Setup copper delivery system | 1645.2 | 1645.2 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1350-615 | Install taping machine | 1645.2 | 1645.2 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1302-PF | Start PF Preliminary Design | 1652.5 | 1652.5 |  | 0 | 32% | 0 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 05 | 1 |  | 13 | 32 | 100
3101-317 | PDR PREP- ROWGOWSKI COIL | 0 | 1655.9 |  | 1655.9 | 30% | 496.77 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30
3101-513 | PDR PREP -MC SHELL SADDLE LOOPS | 0 | 1655.9 |  | 1655.9 | 30% | 496.77 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
1202-812 | Anneal Samples *ECP6* | 1684.8 | 1684.8 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-827 | Anneal iteration 2 *ECP6* | 1684.8 | 1684.8 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-839 | Anneal iteration 3 *ECP6* | 1684.8 | 1684.8 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
442-1-8 | Kirk Keys-Commission | 0 | 1721.8 |  | 1721.8 | 18% | 309.924 | 4 | 44 | 442 | 9450 | 4401 | S | 442 |  | 1 |  | 44 | 18
4501-100 | Design Drawings | 1723.8 | 1723.8 |  | 0 | 18% | 0 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 01 | 1 |  | 45 | 18 | 100
3101-145 | Procure MI Cable | 1724.71 | 1724.71 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 10 |  |  |  | 30 | 100
840.202 | Project Physics/Engr Analysis FY04 | 1729 | 1729 |  | 0 | 3% | 0 | 8 | 84 | 840 | 9450 | 8401 | P | FY04 |  | 1 |  |  | 3 | LOE
3101-169 | Voltage loop connection peer review | 0 | 1735.1 |  | 1735.1 | 30% | 520.53 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 26 |  |  |  | 30
3101-517 | Fab termination boxes (24) | 0 | 1735.1 |  | 1735.1 | 30% | 520.53 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30
1501-229 | Create Prelim Assemblies | 0 | 1740.6 |  | 1740.6 | 32% | 556.992 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1501-233 | PDR Preparation | 0 | 1740.6 |  | 1740.6 | 32% | 556.992 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
3101-517A | Install termination boxes | 0 | 1773 |  | 1773 | 30% | 531.9 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30
712.020 | Platform Parts | 0 | 1773 |  | 1773 | 10% | 177.3 | 7 | 73 | 730 | 9450 | 7301 | F |  |  | 1 |  |  | 10
1202-800 | Inconnel Procurement *ECP6* | 1783.6 | 1783.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1406-016.5 | PPPL Fabricate TRC Cladding | 1788.48 | 1788.48 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-4 | 63 | 1 | C | 141 | 40 | 100
1406-017.F | Position Ground wrap onto winding form Side a | 1788.48 | 1788.48 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-017.F | Position Ground wrap onto winding form Side a | 1788.48 | 1788.48 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1302-PF | Start PF Preliminary Design | 1817.75 | 1817.75 |  | 0 | 32% | 0 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 05 | 1 |  | 13 | 32 | 100
1403-208 | Start I&C Dwgs -Type C | 1860 | 1860 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1403-223 | Start tp level coil assembly-Type C | 1860 | 1860 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
810.909 | Project Management Office PPPL FY09 | 0 | 1884 |  | 1884 | 5% | 94.2 | 8 | 81 | 810 | 9450 | 8101 | S |  | 10 | 1 |  | STRO | 5
1407-100.6 | Complete Electr hookup turning fixtures 4 | 1890.36 | 1890.36 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  | 141 | 28 | 100
1301-100 | Prepare Scope Sheet & define interfaces | 1892.9 | 1892.9 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1403-017.D | Wind layer #1 9 turns Side b | 1937.52 | 1937.52 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1403-017.D | Wind layer #1 9 turns Side b | 1937.52 | 1937.52 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 1941.3 |  | 1941.3 | 30% | 582.39 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 21 | 1 |  | 141 | 30
631-010 | Final Design**reduced scope | 0 | 1944.8 |  | 1944.8 | 20% | 388.96 | 6 | 62 | 621 | 9450 | 6201 | 2 | 621 | 11 | F |  |  | 20
1803-1.06 | Design review PDR VV Prep Station | 1983 | 1983 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 40 | P |  |  | 20 | 100
1803-1.061 | Design review FDR VV Prep Station | 1983 | 1983 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 50 | F |  |  | 20 | 100
1803-3.02 | MC Turning Fixture and base - model design and d | 1983 | 1983 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 15 | 1 |  |  | 40 | 100
1803-3.03 | MC Gantry Crane - model design and drawing detai | 1983 | 1983 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 20 | 1 |  |  | 40 | 100
1803-4.03 | TF HP support turning fixture - model design d | 1983 | 1983 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 01 | 1 |  |  | 40 | 100
1803-4.02 | MC Support Stand - model design and drawing deta | 1983 | 1983 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 4.00 | 00 | 1 |  |  | 40 | 100
1351-150A | Assemble TF to Wedge Casting TF#9 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-155A | Assemble TF to Wedge Casting TF#10 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-160A | Assemble TF to Wedge Casting TF#11 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-165A | Assemble TF to Wedge Casting TF#12 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-170A | Assemble TF to Wedge Casting TF#13 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-175A | Assemble TF to Wedge Casting TF#14 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-180A | Assemble TF to Wedge Casting TF#15 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-185A | Assemble TF to Wedge Casting TF#16 | 0 | 1997.28 |  | 1997.28 | 67% | 1338.1776 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
S3P1-105 | Move MC turning fixt; mount MC on crane | 0 | 1997.28 |  | 1997.28 | 40% | 798.912 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 1997.28 |  | 1997.28 | 40% | 798.912 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P2-105 | Move MC turning fixt; mount MC on crane | 0 | 1997.28 |  | 1997.28 | 40% | 798.912 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 1997.28 |  | 1997.28 | 40% | 798.912 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
FY05CV-34 | FY05 unrecoverable cost variance | 2000 | 2000 |  | 0 | 0% | 0 | 4 | 41 | 411 | 9450 | 4101
810.103 | Project Management Office ORNL FY05 | 2000 | 2000 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8102 | P |  |  | 1 |  |  | 10 | LOE
1301-165 | PF1-PF3 Support System Layouts | 2008.5 | 2008.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
810.104 | Project Management Office ORNL FY06 | 992.592 | 2034 |  | 1041.408 | 10% | 104.1408 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10 | LOE
1351-190A | Assemble TF to Wedge Casting TF#17 | 0 | 2051.04 |  | 2051.04 | 67% | 1374.1968 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-195A | Assemble TF to Wedge Casting TF#18 | 0 | 2051.04 |  | 2051.04 | 67% | 1374.1968 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
S3P3-105 | Move MC turning fixt; mount MC on crane | 0 | 2051.04 |  | 2051.04 | 40% | 820.416 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S3P3-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 2051.04 |  | 2051.04 | 40% | 820.416 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
1203-291 | Update Design Basis Document | 2059.04 | 2059.04 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 2061.24 |  | 2061.24 | 30% | 618.372 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 21 | 1 |  | 141 | 30
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 2061.24 |  | 2061.24 | 30% | 618.372 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 46 | 1 |  | 141 | 30
810.104X | Project Management Office ORNL FY07 | 0 | 2068 |  | 2068 | 10% | 206.8 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10
442-1-6 | Kirk Keys-Install | 0 | 2070.72 |  | 2070.72 | 18% | 372.7296 | 4 | 44 | 442 | 9450 | 4401 | F | 442 |  | 1 |  | 44 | 18
810.105X | Project Management Office ORNL FY08 | 0 | 2104 |  | 2104 | 10% | 210.4 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10
MCWF-051 | C1-MTK-casting upgrade | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 30 |  |  |  | 10 | 100
MCWF-081 | C2-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 32 |  |  |  | 10 | 100
MCWF-141 | C3-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 33 |  |  |  | 10 | 100
MCWF-201 | C4-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 34 |  |  |  | 10 | 100
MCWF-261 | C5-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 35 |  |  |  | 10 | 100
MCWF-111 | A1-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 36 |  |  |  | 10 | 100
MCWF-171 | A2-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 38 |  |  |  | 10 | 100
MCWF-351 | A3-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 39 |  |  |  | 10 | 100
MCWF-231 | B1-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 40 |  |  |  | 10 | 100
MCWF-381 | A4-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 41 |  |  |  | 10 | 100
MCWF-321 | B2-MTK-casting | 1371.5 | 2110 |  | 738.5 | 10% | 73.85 | 1 | 14 | 141 | 9450 | 1411 | P |  | 44 |  |  |  | 10 | 65
MCWF-471 | B3-MTK-casting | 1160.5 | 2110 |  | 949.5 | 10% | 94.95 | 1 | 14 | 141 | 9450 | 1411 | P |  | 45 |  |  |  | 10 | 55
MCWF-501 | B4-MTK-casting | 1055 | 2110 |  | 1055 | 10% | 105.5 | 1 | 14 | 141 | 9450 | 1411 | P |  | 46 |  |  |  | 10 | 50
MCWF-531 | B5-MTK-casting | 316.5 | 2110 |  | 1793.5 | 10% | 179.35 | 1 | 14 | 141 | 9450 | 1411 | P |  | 47 |  |  |  | 10 | 15
MCWF-561 | B6-MTK-casting | 0 | 2110 |  | 2110 | 10% | 211 | 1 | 14 | 141 | 9450 | 1411 | P |  | 48 |  |  |  | 10
MCWF-411 | A5-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 49 |  |  |  | 10 | 100
MCWF-441 | A6-MTK-casting | 1688 | 2110 |  | 422 | 10% | 42.2 | 1 | 14 | 141 | 9450 | 1411 | P |  | 50 |  |  |  | 10 | 80
MCWF-291 | C6-MTK-casting | 2110 | 2110 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 51 |  |  |  | 10 | 100
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 2126.56 |  | 2126.56 | 26% | 552.9056 | 4 | 45 | 452 | 9450 | 4501 | S | 452 |  | 1 |  | 45 | 26
7503-060 | Install Lower PF 4,5&6 into prelim position | 0 | 2152.32 |  | 2152.32 | 24% | 516.5568 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
4101-100 | Prepare Preliminary One line diagram | 2180.16 | 2180.16 |  | 0 | 18% | 0 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18 | 100
7503-170 | FPA Metrology Checks to Assure Alignment | 0 | 2191.8 |  | 2191.8 | 24% | 526.032 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 03 |  |  |  | 24
3101-153 | Fab Installation Templates (for FP assy) | 2307.6 | 2307.6 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 16 |  |  |  | 30 | 100
1803-2.04 | Metrology - sightline layout design details metr | 2313.5 | 2313.5 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 13 | 1 |  |  | 20 | 100
411-3-2 | Test Cell AC Power Distr-Dsn | 0 | 2367.2 |  | 2367.2 | 18% | 426.096 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
1407-012 | Autoclave PTP | 2433.6 | 2433.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407-003.7 | Final Drawings -casting stud fixture | 2433.6 | 2433.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
25-310.1 | Drafting Labor Support | 2433.6 | 2433.6 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | F | 2525 | 12 | 1 |  | 25 | 16
1803-5.01 | Finalize TFTR test cell FPA assembly layout draw | 2456.4 | 2456.4 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 6.00 | 00 | 1 |  |  | 40 | 100
1403-45 | Check and promote models / drawings | 2472 | 2472 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1408-141 | Copper Conductor -Spec & Requisition | 2472 | 2472 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | COPP | 20 | 1 |  |  | 40 | 100
121-037 | Purchase seals and ship to MTM | 2480 | 2480 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | 100
121-039 | Design Seal Template | 2480 | 2480 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | 100
1406-103.3 | Resolve TRC FDR Issues | 2480 | 2480 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-157 | Build to specification | 2480 | 2480 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1351-145A | Assemble TF to Wedge Casting TF#8 | 0 | 2496.6 |  | 2496.6 | 67% | 1672.722 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
0192-5 | LOE-FY05 WBS 192 | 2500 | 2500 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 07 | 1 |  |  | 10 | LOE
441-125 | Program Control pages | 0 | 2504.16 |  | 2504.16 | 18% | 450.7488 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
1202-818 | Weld samples *ECP6* | 2527.2 | 2527.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-842 | Weld iteration 3 *ECP6* | 2527.2 | 2527.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 2533.2 |  | 2533.2 | 30% | 759.96 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 10 | 1 |  | 141 | 30
1301R-23 | Document and Summerize Analysis | 2548 | 2548 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 74 | 1 | C |  | 24 | 100
1301R-27 | Obtain Stresses from Deflection Analysis | 2548 | 2548 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 74 | 1 |  |  | 24 | 100
1301R-33 | Prepare PDR Material | 2548 | 2548 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 74 | 1 | C |  | 24 | 100
1407-115.2 | Fabr Conduct payout spool syst ** 2nd line** | 2548 | 2548 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  |  | 28 | 100
1407-110.2 | Compl Fabr Winding clamp sets (100 of 400) | 2548 | 2548 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 24 | 1 |  |  | 28 | 100
2501-014.1 | FY04 work closeout *TBD* | 2548 | 2548 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16 | LOE
1301R-07 | Procure Test Services | 2558 | 2558 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 80 | 1 | C |  | 24 | 100
1301FD-20 | Test 1st Sample | 2562 | 2562 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1301FD-21 | Test 2nd Sample | 2562 | 2562 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 80 | 1 | C |  | 24 | 100
1202-325A | Vist MT for welding | 2566.72 | 2566.72 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 40 | 100
1406-200 | Transverse compression at LN2 | 2566.72 | 2566.72 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 20 | 1 |  |  | 40 | 100
1803-3.50 | Test Evaluation and Write up | 2566.72 | 2566.72 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
1403-04 | Plan response to PDR chits | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW01 |  | 1 |  |  | 40 | 100
1403-05 | Prepare FY04 WP / WAF / Checklists | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW01 |  | 1 |  |  | 40 | 100
1403-07 | Prepare PBR documentation | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW01 |  | 1 |  |  | 40 | 100
1403-10 | Review, revise, and approve SRD | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW02 |  | 1 |  |  | 40 | 100
1403-13 | Finalize winding pack ref xsec, conductor dims | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW02 |  | 1 |  |  | 40 | 100
1403-21 | Document electrical, insulation parameters | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW03 |  | 1 |  |  | 40 | 100
1403-54 | Final bid package( specs,models,dwgs) | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW07 | 11 | 1 |  | 141 | 40 | 100
1403-42 | Complete FDR Struct Analysis Report | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-42 | Complete FDR Struct Analysis Report | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1406-097 | Verify Conductor Dims | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-105 | Prepare ANSYS thermal analysis model | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-106 | Analyze Thermal Behavior due to pulse | 2573.8 | 2573.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1403-203 | Start Clamp Dwgs (5)-Type C | 2604 | 2604 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1501-201 | Write ICD's | 0 | 2610.9 |  | 2610.9 | 32% | 835.488 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1501-246 | Update Models | 0 | 2610.9 |  | 2610.9 | 32% | 835.488 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 | 1 |  |  | 32
431-225 | Reactivate DF & PEI units | 2370.528 | 2633.92 |  | 263.392 | 18% | 47.4106 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 90
1301R-23 | Document and Summerize Analysis | 2644 | 2644 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 74 | 1 | C |  | 24 | 100
1406-103.0 | Prep MIT plan | 2644 | 2644 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1803-1.09 | Safety Review documentation / presentation | 2644 | 2644 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 45 | 1 |  |  | 20 | 100
21-65 | Integrated Systems Testing/Tech Support | 0 | 2658.2 |  | 2658.2 | 14% | 372.148 | 2 | 21 | 210 | 9450 | 2101 | F | EC16 |  | 1 |  |  | 14
442-1-8 | Kirk Keys-Commission | 0 | 2658.2 |  | 2658.2 | 18% | 478.476 | 4 | 44 | 442 | 9450 | 4401 | S | 442 |  | 1 |  | 44 | 18
S3P1-101.1 | Attach local protective strips to VV&locate sens | 0 | 2663.04 |  | 2663.04 | 40% | 1065.216 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-110 | Perform final metrology position check | 0 | 2663.04 |  | 2663.04 | 40% | 1065.216 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P2-101.1 | Attach local protective strips to VV&locate sens | 0 | 2663.04 |  | 2663.04 | 40% | 1065.216 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-110 | Perform final metrology position check | 0 | 2663.04 |  | 2663.04 | 40% | 1065.216 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P3-101.1 | Attach local protective strips to VV&locate sens | 0 | 2663.04 |  | 2663.04 | 40% | 1065.216 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 2677.07 | 2677.07 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
445-1-8 | Ground Fault Protection-Commission | 0 | 2682.56 |  | 2682.56 | 22% | 590.1632 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 2689.44 |  | 2689.44 | 30% | 806.832 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 10 | 1 |  | 141 | 30
1421-100 | Submet Requisition for - Assy bolts,nuts,washers | 0 | 2699.2 |  | 2699.2 | 40% | 1079.68 | 1 | 14 | 142 | 9450 | 1421 | T |  | 25 | 1 | C | 141 | 40
1421-200 | Submet Requisition for - Assembly shims | 0 | 2699.2 |  | 2699.2 | 40% | 1079.68 | 1 | 14 | 142 | 9450 | 1421 | T |  | 25 | 1 | C | 141 | 40
1421-400 | Submet Requisition for - Bladders | 0 | 2699.2 |  | 2699.2 | 40% | 1079.68 | 1 | 14 | 142 | 9450 | 1421 | T |  | 25 | 1 | C | 141 | 40
7503-060 | Install Lower PF 4,5&6 into prelim position | 0 | 2734.72 |  | 2734.72 | 24% | 656.3328 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
S3P3-110 | Perform final metrology position check | 0 | 2734.72 |  | 2734.72 | 40% | 1093.888 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
121-036 | Ship vac equipt from PPPL to MTM for vac testing | 2742 | 2742 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | 100
1408-765 | Deliver Tubing | 2742 | 2742 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | TUBE | 25 | 1 | C | 141 | 30 | 100
452-2-4 | Diagnostics sensor cabling-Procure | 0 | 2742 |  | 2742 | 26% | 712.92 | 4 | 45 | 452 | 9450 | 4501 | T | 452 |  | 1 |  | 45 | 26
810.005 | Project Management OfficePPPL FY07 | 0 | 2742 |  | 2742 | 5% | 137.1 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5
1803-1.07 | Design check and sign-off | 2742.67 | 2742.67 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 55 | 1 |  |  | 20 | 100
1803-1.10 | Fab / Design Review - follow-up activities | 2742.67 | 2742.67 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 60 | 1 |  |  | 20 | 100
431-250 | c-site dc sys DGS dsn documentation | 0 | 2748.32 |  | 2748.32 | 18% | 494.6976 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
442-1-6 | Kirk Keys-Install | 0 | 2748.32 |  | 2748.32 | 18% | 494.6976 | 4 | 44 | 442 | 9450 | 4401 | F | 442 |  | 1 |  | 44 | 18
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 2754.88 |  | 2754.88 | 26% | 716.2688 | 4 | 45 | 452 | 9450 | 4501 | S | 452 |  | 1 |  | 45 | 26
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 2757.02 |  | 2757.02 | 18% | 496.2636 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
1203-191 | Start Eddy Current Analyses | 2781 | 2781 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
431-265 | Fabricate bus components | 0 | 2791.33 |  | 2791.33 | 18% | 502.4394 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
1301-105 | Prepare Interface Dwgs for ICD's | 2798.67 | 2798.67 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 2822.24 |  | 2822.24 | 18% | 508.0032 | 4 | 41 | 412 | 9450 | 4101 | F | 412 |  | 1 |  | 41 | 18
442-1-8 | Kirk Keys-Commission | 0 | 2822.24 |  | 2822.24 | 18% | 508.0032 | 4 | 44 | 442 | 9450 | 4401 | S | 442 |  | 1 |  | 44 | 18
1351-657 | GW & Apply Mold Coil #5 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-659 | GW & Apply Mold Coil #6 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-661 | GW & Apply Mold Coil #7 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-663 | GW & Apply Mold Coil #8 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-665 | GW & Apply Mold Coil #9 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-667 | GW & Apply Mold Coil #10 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-669 | GW & Apply Mold Coil #11 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-671 | GW & Apply Mold Coil #12 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-673 | GW & Apply Mold Coil #13 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-675 | GW & Apply Mold Coil #14 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-677 | GW & Apply Mold Coil #15 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-679 | GW & Apply Mold Coil #16 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-681 | GW & Apply Mold Coil #17 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-683 | GW & Apply Mold Coil #18 | 0 | 2912.7 |  | 2912.7 | 67% | 1951.509 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 2922.4 |  | 2922.4 | 24% | 701.376 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
431-225 | Reactivate DF & PEI units | 2633.67 | 2926.3 |  | 292.63 | 18% | 52.6734 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 90
1406-016.0 | Oversight & Supervision | 2974.5 | 2974.5 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 00 | 1 | C | 141 | 40 | 100
1803-4.04 | FP Assembly platform - model design drawing det | 2974.5 | 2974.5 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 4.00 | 03 | 1 |  |  | 40 | 100
1413-130 | Machine test blanks (PPPL) | 2980.8 | 2980.8 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1413 | 2 |  | 30 |  |  |  | 10 | 100
1407-012 | Autoclave PTP | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407-012 | Autoclave PTP | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407-128 | Setup facility stations 2&5 | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  | 141 | 34 | 100
1407-128 | Setup facility stations 2&5 | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  | 141 | 34 | 100
1407-128 | Setup facility stations 2&5 | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  | 141 | 34 | 100
1407-128 | Setup facility stations 2&5 | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  | 141 | 34 | 100
1407-105 | Anchor VPI platforms | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | VPI | 20 | 1 |  | 141 | 34 | 100
1407-105 | Anchor VPI platforms | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | VPI | 20 | 1 |  | 141 | 34 | 100
1407-107 | Perform epoxy mixing trials with delivery sys | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | VPI | 21 | 1 |  | 141 | 34 | 100
1407-107 | Perform epoxy mixing trials with delivery sys | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | VPI | 21 | 1 |  | 141 | 34 | 100
1406-56 | test chill plate specimens | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-56 | test chill plate specimens | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-57 | fab cooling tube/chill plate assy | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-57 | fab cooling tube/chill plate assy | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-58 | fab MC lead braze specimens | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 11 | 1 |  |  | 40 | 100
1406-016.2 | Install Studs | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-016.7 | Finish TRC Chill plates | 2980.8 | 2980.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 30 | 100
1406-017 | Instl cladding(station 2) Side A | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-017 | Instl cladding(station 2) Side A | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-017B | Instl cladding(station 2) Side B | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-017B | Instl cladding(station 2) Side B | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-ST2 | Straight Tee VPI Prep | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-T | 81 | 1 | C | 141 | 40 | 100
1406-ST2 | Straight Tee VPI Prep | 2980.8 | 2980.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-T | 81 | 1 | C | 141 | 40 | 100
1409-160 | Test Closed Loop Cooling | 2980.8 | 2980.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 65 | 1 | C | 141 | 34 | 100
3101-133 | Prototype loops on vsl proto segment using ARI | 2980.8 | 2980.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
711B.050 | Complete Control Room Flooring | 0 | 2995.92 |  | 2995.92 | 10% | 299.592 | 7 | 72 | 720 | 9450 | 7201 | F |  | 11 | 1 |  |  | 10
711B.050 | Complete Control Room Flooring | 0 | 2995.92 |  | 2995.92 | 10% | 299.592 | 7 | 72 | 720 | 9450 | 7201 | F |  | 11 | 1 |  |  | 10
FY05CV-2 | FY05 unrecoverable cost variance | 3000 | 3000 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1203 |  | 05FD | [5 empty] | 100
810.103 | Project Management Office ORNL FY05 | 3000 | 3000 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8102 | P |  |  | 1 |  |  | 10 | LOE
712.020 | Platform Parts | 0 | 3013 |  | 3013 | 10% | 301.3 | 7 | 73 | 730 | 9450 | 7301 | F |  |  | 1 |  |  | 10
191-042 | PDR #17,25,3 | 0 | 3022.96 |  | 3022.96 | 30% | 906.888 | 1 | 16 | 161 | 9450 | 1601 | F | 161 |  | 1 |  |  | 30
1409-029 | Oversight/Supervision | 3061.84 | 3061.84 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 14 | 1 |  | 141 | 34 | 100
3101-125 | PDR PREP -VESSEL SADDLE LOOP MOUNTING | 3066.8 | 3066.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
3101-401 | MOUNTING/LOCATING TECHNIQUE TF CO-WOUND LOOPS | 3066.8 | 3066.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD4 |  |  |  |  | 30 | 100
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 3077.36 |  | 3077.36 | 18% | 553.9248 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
1203-311 | Prepare Final Design ECP | 3088.56 | 3088.56 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1403-40.2A | Develop multi-filament model of all coils | 3088.56 | 3088.56 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-54 | Final bid package( specs,models,dwgs) | 3090 | 3090 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW07 | 11 | 1 |  | 141 | 40 | 100
192-6.09 | Revised VV geometry | 3090 | 3090 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
1403-42G | WP beam FEA modeling | 3100 | 3100 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 06 | 1 | C |  | 40 | 100
1403-62 | Prepare FDR documentation / presentations | 3100 | 3100 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 04 | 1 |  |  | 40 | 100
1403-20.00 | Resolve FDR chits | 3100 | 3100 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 08 | F | C | 141 | 40 | 100
1403-49 | Update cost / schedule estimates | 3100 | 3100 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 39 | 1 | C |  | 40 | 100
445-1-8 | Ground Fault Protection-Commission | 0 | 3106.08 |  | 3106.08 | 22% | 683.3376 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
711B.050 | Complete Control Room Flooring | 0 | 3106.08 |  | 3106.08 | 10% | 310.608 | 7 | 72 | 720 | 9450 | 7201 | F |  | 11 | 1 |  |  | 10
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 3115.93 |  | 3115.93 | 18% | 560.8674 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
1407-100.4 | Electr hookup turning fixtures 2,3&4 | 3129.84 | 3129.84 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 20 | 1 |  | 141 | 28 | 100
1409-034 | Fabricate I2T Cards | 3159 | 3159 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 3189.84 |  | 3189.84 | 18% | 574.1712 | 4 | 41 | 412 | 9450 | 4101 | S | 412 |  | 1 |  | 41 | 18
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 3189.84 |  | 3189.84 | 18% | 574.1712 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
444-3-8 | DC Shunts-Commission | 0 | 3189.84 |  | 3189.84 | 18% | 574.1712 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
3101-221 | PROCURE MATERIALS | 3202.5 | 3202.5 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD2 | 00 |  |  |  | 30 | 100
1202-803 | Drawings for Arc/Samples *ECP6* | 3208.4 | 3208.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-821 | Eval & Redesign Joint iteration 2 *ECP6* | 3208.4 | 3208.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-833 | Eval & redesign joint iteration 3 *ECP6* | 3208.4 | 3208.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
3101-113 | INTEGRATE LAYOUT, MEAS NEEDS W/ VSL METRO PLANS | 3208.4 | 3208.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
3101-133 | Prototype loops on vsl proto segment using ARI | 3208.4 | 3208.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
3101-205 | MOUNTING/LOCATING STRATEGY MC CO-WOUND LOOPS | 3208.4 | 3208.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 00 |  |  |  | 30 | 100
3101-209 | PROTOTYPE ON TWISTED RACETRACK | 3208.4 | 3208.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 00 |  |  |  | 30 | 100
3101-213 | DESIGN TERMINATION | 3208.4 | 3208.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 00 |  |  |  | 30 | 100
3101-221 | PROCURE MATERIALS | 3208.4 | 3208.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD2 | 00 |  |  |  | 30 | 100
3101-401 | MOUNTING/LOCATING TECHNIQUE TF CO-WOUND LOOPS | 3208.4 | 3208.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD4 |  |  |  |  | 30 | 100
631-015 | Fab/Assy/Installation**reduced scope | 0 | 3228.48 |  | 3228.48 | 20% | 645.696 | 6 | 62 | 621 | 9450 | 6201 | F | 621 | 14 | 1 |  |  | 20
4101-100 | Prepare Preliminary One line diagram | 3255.12 | 3255.12 |  | 0 | 18% | 0 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18 | 100
1406-023 | Hi-pot & Dissect Coil | 3257.6 | 3257.6 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 73 | 1 | C | 141 | 30 | 100
1406-023 | Hi-pot & Dissect Coil | 3257.6 | 3257.6 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 73 | 1 | C | 141 | 30 | 100
3101-422 | Fab Prototype term. Box | 0 | 3257.6 |  | 3257.6 | 30% | 977.28 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30
122-011 | Final design WBS 122 Thermal insulation | 2463.0525 | 3284.07 |  | 821.0175 | 32% | 262.7256 | 1 | 12 | 122 | 9450 | 1203 | 2 | 122 | 08 | 1 |  |  | 32 | 75
125-037 | Procurement Local I&C WBS 125 | 0 | 3290.4 |  | 3290.4 | 30% | 987.12 | 1 | 12 | 125 | 9450 | 1204 | T | 125 | 91 | 1 |  |  | 30
1403-42D.0 | Determine Fatigue properties | 3305 | 3305 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 10 | 1 |  |  | 40 | 100
1803-2.02 | MC Holding Fixture - model design and drawing | 3305 | 3305 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 11 | 1 |  |  | 20 | 100
3101-505 | MOUNTING/LOCATING TECHN MC SHELL SADDLE LOOPS | 0 | 3311.8 |  | 3311.8 | 30% | 993.54 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
3101-521 | FINALIZE LOOP LOCATION/MOUNTING TECHNIQUE | 0 | 3311.8 |  | 3311.8 | 30% | 993.54 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
3101-301 | LAYOUT LOCATION ROWGOSKI COIL &EST COIL DIMEN | 3332.99 | 3332.99 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30 | 100
1407-126 | Fab Type A casting supports (6) sets | 3353.4 | 3353.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1407-126 | Fab Type A casting supports (6) sets | 3353.4 | 3353.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1202-809 | Machine weld groove *ECP6* | 3369.6 | 3369.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-824 | Machine iteration 2 *ECP6* | 3369.6 | 3369.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1202-836 | Machine iteration 3 *ECP6* | 3369.6 | 3369.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1416B-109 | -Check and Promote top level drawings | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-129 | MCWF mods-Check and Promote | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-149 | Lead Block Assy-Check and Promote | 2360.617 | 3372.31 |  | 1011.693 | 20% | 202.3386 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 70
1416B-153 | Lead Terminals-Splice Plates | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-157 | Lead Terminals-Check and Promote | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-169 | Side A Coil Assy-Magnetic Loops | 1348.924 | 3372.31 |  | 2023.386 | 20% | 404.6772 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 40
1416B-189 | Side B Coil Assy-Magnetic Loops | 674.462 | 3372.31 |  | 2697.848 | 20% | 539.5696 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 20
1416B-201 | Coil Post VPI mods-Studs Removed | 1011.693 | 3372.31 |  | 2360.617 | 20% | 472.1234 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 30
1416B-209 | Coil Post VPI mods-Check and Promote | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-221 | I&C-Strain Gages and T/C | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-229 | I&C-Check and Promote | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-233 | Coil-to-Coil -Current Feed Insul, Covers | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-237 | Coil-to-Coil -Windings Insul Blanket | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-241 | Coil-to-Coil -Bushing Installation | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-245 | Coil-to-Coil -Check and Promote | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-253 | -Review and Approve Type-B Spec | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-257 | -Update Coil Fab Procedures | 0 | 3372.31 |  | 3372.31 | 20% | 674.462 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416A-109 | -Check and Promote Top Level Drawings | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 01 |  |  |  | 20
1416A-129 | MCWF mods-Check and Promote | 1012.2 | 3374 |  | 2361.8 | 20% | 472.36 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 30
1416A-149 | Lead Block Assy-Check and Promote | 2699.2 | 3374 |  | 674.8 | 20% | 134.96 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 80
1416A-153 | Lead Terminals-Splice Plates | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-157 | Lead Terminals-Check and Promote | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-169 | Side A Coil Assy-Magnetic Loops | 3374 | 3374 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416A-189 | Side B Coil Assy-Magnetic Loops | 3374 | 3374 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416A-201 | Coil Post VPI mods-Studs Removed | 2699.2 | 3374 |  | 674.8 | 20% | 134.96 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 80
1416A-209 | Coil Post VPI mods-Check and Promote | 2699.2 | 3374 |  | 674.8 | 20% | 134.96 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 80
1416A-221 | I&C-Strain Gages and T/C | 1012.2 | 3374 |  | 2361.8 | 20% | 472.36 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 30
1416A-229 | I&C-Check and Promote | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-233 | Coil-to-Coil -Current Feed Insul, Covers | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-237 | Coil-to-Coil -Windings Insul Blanket | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-241 | Coil-to-Coil -Bushing Installation | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-245 | Coil-to-Coil -Check and Promote | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-253 | -Review and Approve Type-A Spec | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-257 | -Update Coil Fab Procedures | 0 | 3374 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1203-301 | Update Cost and Schedule Estimates | 3404.28 | 3404.28 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
3101-333 | Complete termination box design & prototyping | 3419.85 | 3419.85 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30 | 100
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 3437.03 |  | 3437.03 | 30% | 1031.109 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 46 | 1 |  | 141 | 30
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 3443.6 |  | 3443.6 | 18% | 619.848 | 4 | 41 | 412 | 9450 | 4101 | S | 412 |  | 1 |  | 41 | 18
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 3443.6 |  | 3443.6 | 18% | 619.848 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 3455.26 |  | 3455.26 | 20% | 691.052 | 1 | 15 | 151 | 9450 | 1550 | T |  | 17 | 1 |  |  | 20
1203-241 | Check FMECA Analyses | 2764.952 | 3456.19 |  | 691.238 | 40% | 276.4952 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 01 | 1 |  |  | 40 | 80
3101-309 | DESIGN COIL MOUNTING TECHNIQUE | 3459.89 | 3459.89 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30 | 100
1409-136 | Valve/pump repairs&safety mods to cryo pp sys | 3470.2 | 3470.2 |  | 0 | 34% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 6 | 02 | 1 | C | 141 | 34 | 100
3101-167 | Design voltage loops | 2949.67 | 3470.2 |  | 520.53 | 30% | 156.159 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 25 |  |  |  | 30 | 85
3101-305 | work on coil design with vendor | 2082.12 | 3470.2 |  | 1388.08 | 30% | 416.424 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30 | 60
3101-313 | DESIGN LEAD ROUTING AND TERMINATION | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30
3101-317 | PDR PREP- ROWGOWSKI COIL | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30
3101-321 | Specify Rogowski Coils | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30
3101-325 | FDR PREP ROWGOSKI COIL | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD3 |  |  |  |  | 30
3101-329 | FAB ROWGOWSKI COILS (2) | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | F | MD3 |  |  |  |  | 30
3101-417 | PROCURE MATERIALS | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | F | MD4 |  |  |  |  | 30
3101-505 | MOUNTING/LOCATING TECHN MC SHELL SADDLE LOOPS | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
3101-513 | PDR PREP -MC SHELL SADDLE LOOPS | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
3101-529 | PROCURE MATERIALS | 0 | 3470.2 |  | 3470.2 | 30% | 1041.06 | 3 | 31 | 310 | 9450 | 3101 | F | MD5 |  |  |  |  | 30
132-000 | PDR #17 & 25 | 0 | 3471.21 |  | 3471.21 | 30% | 1041.363 | 1 | 16 | 162 | 9450 | 1601 | F | 162 | 01 | 1 |  |  | 30
163-001 | Title I design CS sprt struc | 3474.63 | 3474.63 |  | 0 | 32% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | 0000 | 07 | 1 |  |  | 32 | 100
1403-43 | Incorporate changes due to prototype fabr | 3474.63 | 3474.63 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW06 | 10 | 1 |  |  | 40 | 100
1403-43 | Incorporate changes due to prototype fabr | 3474.63 | 3474.63 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW06 | 10 | 1 |  |  | 40 | 100
1403-43 | Incorporate changes due to prototype fabr | 3474.63 | 3474.63 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW06 | 10 | 1 |  |  | 40 | 100
1501-257 | Detailed Hardware Analysis | 0 | 3481.2 |  | 3481.2 | 32% | 1113.984 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
1501-261 | Write Statement of work | 0 | 3481.2 |  | 3481.2 | 32% | 1113.984 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
1501-265 | Approve Purchase Spec | 0 | 3481.2 |  | 3481.2 | 32% | 1113.984 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
25-099 | FY04 work accomplished | 3502.44 | 3502.44 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 2510 |  | 1 |  | 25 | 16
3101-229 | SUPPORT NSTALLATION, TERMINATION, TESTING | 2633.5575 | 3511.41 |  | 877.8525 | 30% | 263.3558 | 3 | 31 | 310 | 9450 | 3101 | F | MD2 | 13 |  |  |  | 30 | 75
3101-165 | Identify lead wires at multiple locations | 0 | 3512.08 |  | 3512.08 | 30% | 1053.624 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 30 |  |  |  | 30
161-037 | Machine Base&supports Procurement [A/1] | 0 | 3542 |  | 3542 | 32% | 1133.44 | 1 | 17 | 172 | 9450 | 1752 | T | 172 | 20 | 1 |  | 17 | 32
162-037 | WBS 151Coil Support Struc Procurement [A/1] | 0 | 3542.18 |  | 3542.18 | 32% | 1133.4976 | 1 | 15 | 151 | 9450 | 1550 | T |  | 15 | 1 |  | 15 | 32
163-037 | CS Support Structure Procurement/Fab | 0 | 3543.06 |  | 3543.06 | 32% | 1133.7792 | 1 | 13 | 132 | 9450 | 1353 | T | 132A | 23 | 1 |  | 13 | 32
21-35 | Eng. Work Planning and Design during fab | 0 | 3548.94 |  | 3548.94 | 14% | 496.8516 | 2 | 21 | 210 | 9450 | 2101 | 2 | EC16 |  | 1 |  |  | 14
1301FD-13 | Impregnate and Complete Sample 2nd Sample | 3576.96 | 3576.96 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
810.900 | Project Management Office PPPL FY08 | 0 | 3586 |  | 3586 | 5% | 179.3 | 8 | 81 | 810 | 9450 | 8101 | S |  | 10 | 1 |  | STRO | 5
151-037 | Cryostat Procurement [A/1] | 0 | 3586 |  | 3586 | 28% | 1004.08 | 1 | 17 | 171 | 9450 | 1751 | T | 171 | 20 | 1 |  | 17 | 28
1408-505 | PPPL Fabr Cladding Type C for Coil c1 | 3586.65 | 3586.65 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 23 | 1 | C | 141 | 30 | 100
3101-537 | INSTALL TERMINATIONS | 0 | 3594.6 |  | 3594.6 | 30% | 1078.38 | 3 | 31 | 310 | 9450 | 3101 | F | MD5 |  |  |  |  | 30
3101-231 | Terminate MC co-wound loops | 0 | 3606.57 |  | 3606.57 | 30% | 1081.971 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 14 |  |  |  | 30
3101-337 | INSTALL COILS AND TERMINATIONS | 0 | 3606.57 |  | 3606.57 | 30% | 1081.971 | 3 | 31 | 310 | 9450 | 3101 | F | MD3 |  |  |  |  | 30
3101-429 | INSTALL TERMINATIONS | 0 | 3606.57 |  | 3606.57 | 30% | 1081.971 | 3 | 31 | 310 | 9450 | 3101 | F | MD4 |  |  |  |  | 30
21-60 | Integrated Systems Testing/Eng | 0 | 3641.6 |  | 3641.6 | 14% | 509.824 | 2 | 21 | 210 | 9450 | 2101 | F | EC16 |  | 1 |  |  | 14
361-015 | Fab/Assy/Installation Visible Camera | 0 | 3641.6 |  | 3641.6 | 20% | 728.32 | 3 | 36 | 360 | 9450 | 3601 | F |  |  | 1 |  |  | 20
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 3653 |  | 3653 | 24% | 876.72 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
1404-FR6 | Test Lot 2 specimens @NHMFL 11 pcs. | 3663.66 | 3663.66 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | 2 | FRAC | 15 |  | C |  | 40 | 100
1403-40.2B | Confirm Plasma performance & surface quality | 3708 | 3708 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-45 | Check and promote models / drawings | 3708 | 3708 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
192-6.12 | Final Check & Verification | 3708 | 3708 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
1403-206 | Start Cooling, Electr Schematic Dwgs- Type C | 3720 | 3720 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1403-221 | Lead ends assy-Type C | 3720 | 3720 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1403-222 | Terminal / elec services assembly-Type C | 3720 | 3720 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1403-224 | Start PI mold assembly-Type C | 3720 | 3720 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 3723.3 |  | 3723.3 | 30% | 1116.99 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 21 | 1 |  | 141 | 30
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 3723.3 |  | 3723.3 | 30% | 1116.99 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 46 | 1 |  | 141 | 30
1406-51 | VPI Tee specimen | 3726 | 3726 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-51 | VPI Tee specimen | 3726 | 3726 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-55 | Fab chill plate specimens | 3726 | 3726 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-55 | Fab chill plate specimens | 3726 | 3726 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
132-001 | Title I design WBS 162 Coil leads | 0 | 3778 |  | 3778 | 22% | 831.16 | 1 | 16 | 162 | 9450 | 1601 | 1 | 162 | 01 | 1 |  | 16 | 22
132-011 | Title II design WBS 162 Coil leads | 0 | 3783.25 |  | 3783.25 | 22% | 832.315 | 1 | 16 | 162 | 9450 | 1601 | 2 | 162 | 01 | 1 |  | 16 | 22
1301-175.2 | Revised Design Stress Analysis | 3822 | 3822 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
1301R-26 | Final Launch Load Analysis | 3822 | 3822 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 74 | 1 |  |  | 24 | 100
840.202 | Project Physics/Engr Analysis FY04 | 3822 | 3822 |  | 0 | 3% | 0 | 8 | 84 | 840 | 9450 | 8401 | P | FY04 |  | 1 |  |  | 3 | LOE
1408-507 | PPPL Fabr Cladding Type C for Coil c2 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 24 | 1 | C | 141 | 30 | 100
1408-509 | Fabr Cladding Type C for Coil c3 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30 | 100
1408-511 | Fabr Cladding Type C for Coil c4 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30 | 100
1408-513 | Fabr Cladding Type C for Coil c5 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30 | 100
1408-515 | Fabr Cladding Type C for Coil c6 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30 | 100
1408-521 | Fabr Cladding Type A for Coil a1 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-523 | Fabr Cladding Type A for Coil a2 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-525 | Fabr Cladding Type A for Coil a3 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-527 | Fabr Cladding Type A for Coil a4 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-529 | Fabr Cladding Type A for Coil a5 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-531 | Fabr Cladding Type A for Coil a6 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-537 | Fabr Cladding Type B for Coil b1 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-539 | Fabr Cladding Type B for Coil b2 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-541 | Fabr Cladding Type B for Coil b3 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-543 | Fabr Cladding Type B for Coil b4 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-545 | Fabr Cladding Type B for Coil b5 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-547 | Fabr Cladding Type B for Coil b6 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CLAD | 25 | 1 | C | 141 | 30
1408-605 | PPPL Fabr Chill Plts Type C for Coil c1 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 21 | 1 | C | 141 | 30 | 100
1408-607 | Fabr Chill Plts Type C for Coil c2 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30 | 100
1408-609 | Fabr Chill Plts Type C for Coil c3 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30 | 100
1408-611 | Fabr Chill Plts Type C for Coil c4 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30 | 100
1408-613 | Fabr Chill Plts Type C for Coil c5 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30 | 100
1408-615 | Fabr Chill Plts Type C for Coil c6 | 3838.8 | 3838.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30 | 100
1408-621 | Fabr Chill Plts Type A for Coil a1 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-623 | Fabr Chill Plts Type A for Coil a2 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-625 | Fabr Chill Plts Type A for Coil a3 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-627 | Fabr Chill Plts Type A for Coil a4 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-629 | Fabr Chill Plts Type A for Coil a5 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-631 | Fabr Chill Plts Type A for Coil a6 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-637 | Fabr Chill Plts Type B for Coil b1 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-639 | Fabr Chill Plts Type B for Coil b2 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-641 | Fabr Chill Plts Type B for Coil b3 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-643 | Fabr Chill Plts Type B for Coil b4 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-645 | Fabr Chill Plts Type B for Coil b5 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1408-647 | Fabr Chill Plts Type B for Coil b6 | 0 | 3838.8 |  | 3838.8 | 30% | 1151.64 | 1 | 14 | 142 | 9450 | 1408 | T | CHLP | 25 | 1 | C | 141 | 30
1301FD-14 | Update Analysis for Front Puller | 3843 | 3843 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1350-605 | Install winding table | 3843 | 3843 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1803-3.49 | Run Test | 3850.08 | 3850.08 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
431-200 | Condition/spare parts inventory | 3657.861 | 3850.38 |  | 192.519 | 18% | 34.6534 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 95
1203-131 | Complete preliminary design of insulation and he | 3860.7 | 3860.7 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | PDRX | 05 | 1 |  |  | 40 | 100
1030.1 | Review & Evaluate Proposals | 3860.7 | 3860.7 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | R | DW07 | 14 |  |  |  | 40 | 100
1030.1 | Review & Evaluate Proposals | 3860.7 | 3860.7 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | R | DW07 | 14 |  |  |  | 40 | 100
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-099 | Review/Approve Casting Drawings | 3860.7 | 3860.7 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
122-031 | Title III engr WBS 12 non vvsa | 250.7923 | 3918.63 |  | 3667.8377 | 32% | 1173.7081 | 1 | 12 | 122 | 9450 | 1204 | F |  | 99 | 1 |  |  | 32
21-40 | Fabrication/Install Hardware | 0 | 3933.25 |  | 3933.25 | 14% | 550.655 | 2 | 21 | 210 | 9450 | 2101 | F | EC16 |  | 1 |  |  | 14
S3P1-101 | VV to MC turning fixt base; metr check | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-102 | Mount MC on crane; perform metr checks | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-104 | Transfer load to sprt sys and recheck position | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-106 | Rotate left MC to stand-off position and check p | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-107 | Move left & right MC to final position & measure | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-109 | Bolt together at flange interface. | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P1-111 | Secure VV to MC's using temporary supports. | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P2-101 | Mount VV to MC turning fixt base; metr check | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-102 | Mount MC on crane; perform metr checks | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-104 | Transfer load to supt sys and recheck position | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-106 | Rotate left MC to stand-off position and check p | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-107 | Move left & right MC to final position & measure | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-109 | Bolt together at flange interface. | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P2-111 | Secure VV to MC's using temporary supports. | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S3P3-101 | Mount VV to MC turning fixt base; metr check | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S4P1-101 | Mount MC/VV assembly to support frame a | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P1-105 | Change platforms | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P2-101 | Mount MC/VV assembly to support frame a | 0 | 3994.56 |  | 3994.56 | 40% | 1597.824 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 3994.99 |  | 3994.99 | 20% | 798.998 | 1 | 15 | 151 | 9450 | 1550 | T |  | 17 | 1 |  |  | 20
1413-150 | Perform fracture tests (NHMFL) | 3996.72 | 3996.72 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1413 | 2 |  | 30 |  |  |  | 10 | 100
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 4015.61 | 4015.61 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1402-005 | VV/MCC PDR support | 4017 | 4017 |  | 0 | 0% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 10 | 1 |  |  | 0 | 100
125-001 | Prelim design WBS 125 local I&C | 4030 | 4030 |  | 0 | 30% | 0 | 1 | 12 | 125 | 9450 | 1203 | 1 | 05FD | 00 | 1 |  |  | 30 | 100
1407-003.3 | Final Drawings -type C casting supports | 4056 | 4056 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
451-7-2 | FDR DC transmission-Dsn | 4056 | 4056 |  | 0 | 18% | 0 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 01 | 1 |  | 45 | 18 | 100
121-035.2 | ORNL design support during MTM Contract | 4068 | 4068 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
1350-520 | Misc tools & equipt | 2847.908 | 4068.44 |  | 1220.532 | 24% | 292.9277 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 70
3101-213 | DESIGN TERMINATION | 4094 | 4094 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 00 |  |  |  | 30 | 100
1803-4.01 | Concept definition and requirements | 4094 | 4094 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 00 | 1 |  |  | 40 | 100
1803-5.001 | Concept definition and requirements | 4094 | 4094 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 4.00 | 01 | 1 |  |  | 40 | 100
S3P3-102 | Mount MC on crane; perform metr checks | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S3P3-104 | Transfer load to supt sysand recheck position | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S3P3-106 | Rotate left MC to stand-off position and check p | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S3P3-107 | Move left & right MC to final position & measure | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S3P3-109 | Bolt together at flange interface. | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S3P3-111 | Secure VV to MC's using temporary supports. | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S4P1-113 | Adjust final support base interfaces | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P1-114 | Prepare Field Period for shipment | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P2-105 | Change platforms | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P2-113 | Adjust final support base interfaces | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P2-114 | Prepare Field Period for shipment | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-101 | Mount MC/VV assembly to support frame a | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
S4P3-105 | Change platforms | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
S4P3-113 | Adjust final support base interfaces | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
S4P3-114 | Prepare Field Period for shipment | 0 | 4102.08 |  | 4102.08 | 40% | 1640.832 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
1351-905 | Cold test #1 BEFORE casting applied | 0 | 4102.4 |  | 4102.4 | 67% | 2748.608 | 1 | 13 | 131 | 9450 | 1361 | F | 13Z |  |  |  |  | 67
1351-910 | Cold test #1 again AFTER casting applied | 0 | 4102.4 |  | 4102.4 | 67% | 2748.608 | 1 | 13 | 131 | 9450 | 1361 | F | 13Z |  |  |  |  | 67
1351-901 | Build Cryostat for teststand to hold TF coil | 0 | 4113 |  | 4113 | 67% | 2755.71 | 1 | 13 | 131 | 9450 | 1361 | F | 13Z |  |  |  |  | 67
1409-136 | Valve/pump repairs&safety mods to cryo pp sys | 4113 | 4113 |  | 0 | 34% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 6 | 02 | 1 | C | 141 | 34 | 100
740.100 | Romer CMM- spare probes | 2056.5 | 4113 |  | 2056.5 | 24% | 493.56 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 24 | 1 |  | 18 | 24 | 50
1203-321 | Assemble FDR Drawing Package, Check & Promote | 4118.08 | 4118.08 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
411-2-8 | Grounding-Commission | 0 | 4122.48 |  | 4122.48 | 18% | 742.0464 | 4 | 41 | 411 | 9450 | 4101 | S | 411 |  | 1 |  | 41 | 18
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 0 | 4122.48 |  | 4122.48 | 18% | 742.0464 | 4 | 44 | 444 | 9450 | 4401 | 2 | 444 |  | 1 |  | 44 | 18
445-1-8 | Ground Fault Protection-Commission | 0 | 4122.48 |  | 4122.48 | 22% | 906.9456 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
1302-PF | Start PF Preliminary Design | 4131.25 | 4131.25 |  | 0 | 32% | 0 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 05 | 1 |  | 13 | 32 | 100
1351-130A | Assemble TF to Wedge Casting TF#5 | 0 | 4161 |  | 4161 | 67% | 2787.87 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-135A | Assemble TF to Wedge Casting TF#6 | 0 | 4161 |  | 4161 | 67% | 2787.87 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
444-4-6 | Signal Conditioning & Cabling-Install | 0 | 4181.18 |  | 4181.18 | 18% | 752.6124 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
1407-130.1 | Misc tools & equipt FY05 | 4200.8 | 4200.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  | 141 | 34 | 100
1407-130 | Misc tools & equipt FY04 | 4212 | 4212 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  | 141 | 34 | 100
452-2-6 | Diagnostics sensor cabling-Install | 0 | 4229.95 |  | 4229.95 | 26% | 1099.787 | 4 | 45 | 452 | 9450 | 4501 | F | 452 |  | 1 |  | 45 | 26
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 4233.36 |  | 4233.36 | 18% | 762.0048 | 4 | 41 | 412 | 9450 | 4101 | S | 412 |  | 1 |  | 41 | 18
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 4233.36 |  | 4233.36 | 18% | 762.0048 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
444-3-8 | DC Shunts-Commission | 0 | 4233.36 |  | 4233.36 | 18% | 762.0048 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
1406-021 | Test Coil | 4235.28 | 4235.28 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 72 | 1 | C | 141 | 30 | 100
121-141 | Fabricate Seal Template and ship to MTM | 4240.11 | 4240.11 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | 100
452-2-6 | Diagnostics sensor cabling-Install | 0 | 4249.68 |  | 4249.68 | 26% | 1104.9168 | 4 | 45 | 452 | 9450 | 4501 | F | 452 |  | 1 |  | 45 | 26
1406-103.1 | Prepare for Twisted Racetrack FDR | 4255.35 | 4255.35 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-103.1 | Prepare for Twisted Racetrack FDR | 4255.35 | 4255.35 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-103.1 | Prepare for Twisted Racetrack FDR | 4255.35 | 4255.35 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
1406-103.1 | Prepare for Twisted Racetrack FDR | 4255.35 | 4255.35 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C |  | 40 | 100
2501-014.1 | FY04 work closeout *TBD* | 4258.8 | 4258.8 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16 | LOE
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 4304.64 |  | 4304.64 | 24% | 1033.1136 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 4322.5 | 4322.5 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
2501-014 | FY04 work accomplished | 4340.16 | 4340.16 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16
1501-229 | Create Prelim Assemblies | 0 | 4351.5 |  | 4351.5 | 32% | 1392.48 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1501-233 | PDR Preparation | 0 | 4351.5 |  | 4351.5 | 32% | 1392.48 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
C1RW | C1 rework | 4362.8 | 4362.8 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 00 | 1 | C | 141 | 20 | 100
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 4383.6 |  | 4383.6 | 24% | 1052.064 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 4383.6 |  | 4383.6 | 24% | 1052.064 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 4383.6 |  | 4383.6 | 24% | 1052.064 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
1407-100.4 | Electr hookup turning fixtures 2,3&4 | 4422.6 | 4422.6 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 20 | 1 |  | 141 | 28 | 100
1406-021 | Test Coil | 4422.8 | 4422.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 72 | 1 | C | 141 | 30 | 100
1407-110 | Fabricate Winding clamp sets (125) | 4471.2 | 4471.2 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
1407-110.3 | Compl Fabr Winding clamp sets (300 of 400) | 4471.2 | 4471.2 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  |  | 28 | 100
1406-55 | Fab chill plate specimens | 4471.2 | 4471.2 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1803-1.10 | Fab / Design Review - follow-up activities | 4471.44 | 4471.44 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 60 | 1 |  |  | 20 | 100
1403-47 | Prepare failure modes assessment (FMECA) | 4504.15 | 4504.15 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW06 | 10 | 1 |  |  | 40 | 100
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 4526.82 |  | 4526.82 | 30% | 1358.046 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 21 | 1 |  | 141 | 30
1351-120A | Assemble TF to Wedge Casting TF#3 | 0 | 4577.1 |  | 4577.1 | 67% | 3066.657 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-125A | Assemble TF to Wedge Casting TF#4 | 0 | 4577.1 |  | 4577.1 | 67% | 3066.657 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1407-100.5 | Complete Fab & Instl Turning Fixt 4 | 4620.88 | 4620.88 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  | 141 | 28 | 100
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 4624.36 |  | 4624.36 | 24% | 1109.8464 | 1 | 13 | 133 | 9450 | 1354 | F | 133 | 16 | 1 |  |  | 24
1403-11 | Prepare assembly / interface drawings for ICDs | 4632.84 | 4632.84 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW08 | 10 | 1 |  |  | 40 | 100
1403-12 | Finalize and approve all ICDs | 4632.84 | 4632.84 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW08 | 10 | 1 |  |  | 40 | 100
1301-140 | Complete Draft SOW | 4635 | 4635 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1030.1 | Review & Evaluate Proposals | 4635 | 4635 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | R | DW07 | 14 |  |  |  | 40 | 100
1030.1 | Review & Evaluate Proposals | 4635 | 4635 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | R | DW07 | 14 |  |  |  | 40 | 100
1501-125 | Update drawings & models based on vendor recomm | 4635 | 4635 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 | 15B |  | 1 |  |  | 32 | 100
1403-11 | Prepare assembly / interface drawings for ICDs | 4671.45 | 4671.45 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW08 | 10 | 1 |  |  | 40 | 100
1350-610 | Setup copper delivery system | 4723.52 | 4723.52 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1350-615 | Install taping machine | 4723.52 | 4723.52 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
412-1-2 | D-site Pulsed AC Power Distr-Dsn | 0 | 4734.4 |  | 4734.4 | 18% | 852.192 | 4 | 41 | 412 | 9450 | 4101 | 2 | 412 |  | 1 |  | 41 | 18
431-250 | c-site dc sys DGS dsn documentation | 0 | 4734.4 |  | 4734.4 | 18% | 852.192 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
451-4-2 | FDR AC auxiliaries & grounding-Dsn | 0 | 4734.4 |  | 4734.4 | 18% | 852.192 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 15 | F |  | 45 | 18
3101-157 | Design & fab tooling and clamps | 4742.04 | 4742.04 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 20 |  |  |  | 30 | 100
1403-202 | G-10 Filler DwgsType C ????????????? | 4761.53 | 4761.53 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1407-125 | Fab Type C casting supports (6) sets | 4769.28 | 4769.28 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1407-125 | Fab Type C casting supports (6) sets | 4769.28 | 4769.28 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
361-001 | Design Visible Camera sys | 0 | 4804.77 |  | 4804.77 | 20% | 960.954 | 3 | 36 | 360 | 9450 | 3601 | 2 |  |  | 1 |  |  | 20
1030.1 | Review & Evaluate Proposals | 4812.6 | 4812.6 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | R | DW07 | 14 |  |  |  | 40 | 100
25-225.1 | Cabling-Design & WP Procedures | 4812.6 | 4812.6 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 2 | 2520 | 10 | 1 |  | 25 | 16
25-099 | FY04 work accomplished | 4841.2 | 4841.2 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 2510 |  | 1 |  | 25 | 16
1406-017.1 | Instl grnd wrap Side b | 4843.8 | 4843.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-017.1 | Instl grnd wrap Side b | 4843.8 | 4843.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1409-028 | System Testing (planar racetrack) | 4843.8 | 4843.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 64 | 1 | C | 141 | 34 | 100
411-3-6 | Test Cell AC Power Distr-Install | 2428.44 | 4856.88 |  | 2428.44 | 18% | 437.1192 | 4 | 41 | 411 | 9450 | 4101 | F | 411 |  | 1 |  | 41 | 18 | 50
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 4858.28 |  | 4858.28 | 30% | 1457.484 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 10 | 1 |  | 141 | 30
1350-610 | Setup copper delivery system | 4871.6 | 4871.6 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1350-615 | Install taping machine | 4871.6 | 4871.6 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1351-513 | Develop brzae techniques | 0 | 4886.4 |  | 4886.4 | 67% | 3273.888 | 1 | 13 | 131 | 9450 | 1361 | F | 13F |  |  |  |  | 67
1351-514 | Braze conductor samples | 0 | 4886.4 |  | 4886.4 | 67% | 3273.888 | 1 | 13 | 131 | 9450 | 1361 | F | 13F |  |  |  |  | 67
1203-202 | Start Port Nozzle Analysis | 4944 | 4944 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1301-175.3 | Layout New Wedge Concept | 4944 | 4944 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
3101-165 | Identify lead wires at multiple locations | 0 | 4945.4 |  | 4945.4 | 30% | 1483.62 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 30 |  |  |  | 30
1803-5.002 | TF Rotation Fixture plus dwgs start | 4957.5 | 4957.5 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 05 | 1 |  |  | 40 | 100
124-011.3 | check support analysis | 4960 | 4960 |  | 0 | 30% | 0 | 1 | 12 | 124 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 30 | 100
FY05CV-24 | FY05 unrecoverable cost variance | 5000 | 5000 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1413 | [7 empty] | 100
810.002 | Project Management Office PPPL FY04 | 5000 | 5000 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
0191-5 | LOE-FY05 WBS 191 | 5000 | 5000 |  | 0 | 10% | 0 | 1 | 19 | 191 | 9450 | 1901 | 2 | 191 | 02 | 1 |  |  | 10 | LOE
442-1-6 | Kirk Keys-Install | 0 | 5029.8 |  | 5029.8 | 18% | 905.364 | 4 | 44 | 442 | 9450 | 4401 | F | 442 |  | 1 |  | 44 | 18
25-099 | FY04 work accomplished | 5047.8 | 5047.8 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 2510 |  | 1 |  | 25 | 16
1203-820 | BOM for all VV parts | 3795.75 | 5061 |  | 1265.25 | 40% | 506.1 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 07 | 1 |  |  | 40 | 75
3101-537 | INSTALL TERMINATIONS | 0 | 5061.52 |  | 5061.52 | 30% | 1518.456 | 3 | 31 | 310 | 9450 | 3101 | F | MD5 |  |  |  |  | 30
3101-429 | INSTALL TERMINATIONS | 0 | 5078.35 |  | 5078.35 | 30% | 1523.505 | 3 | 31 | 310 | 9450 | 3101 | F | MD4 |  |  |  |  | 30
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 5086.44 | 5086.44 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1402-004 | Subcontract analysis upport for PDR | 5096 | 5096 |  | 0 | 0% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 10 | 1 |  |  | 0 | 100
1403-FY04 | Analysis fy04 | 5096 | 5096 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 00 | 1 |  |  | 40 | 100
1301FD-15 | Lead Transition Stress Analysis | 5124 | 5124 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1301FD-16 | Honeycomb InsulationStress Analysis | 5124 | 5124 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
3101-230 | Install heat shrink tubing on MI cable | 769.2 | 5128 |  | 4358.8 | 30% | 1307.64 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 12 |  |  |  | 30 | 15
1203-141 | Finalize Spec for VVSA | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1203-240 | Check Analysis of VV Supports | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1403-22 | Update thermal analysis to current WP design | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW03 |  | 1 |  |  | 40 | 100
1403-25 | Check EM loads calculation for ref scenarios | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW03 |  | 1 |  |  | 40 | 100
1403-33 | Anlyz wind pack deflect/stress fo thrml, EM lds | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-34 | Analyze and optimize clamp locations | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-42B | Modify ORNL beam test setup provide torsional ld | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-42E | Complete checking struct calculations | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-45 | Check and promote models / drawings | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1406-107 | Calculate EM Loads due to max current | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-108 | Prep MECHANICA Struct Analysis Model | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-109 | Analyze Stress/deflection due to cooldown,pulse | 5147.6 | 5147.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
2501-014.1 | FY04 work closeout *TBD* | 5147.6 | 5147.6 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16 | LOE
192-6.10 | MC interf during assly, geometry, assly trajecto | 5147.6 | 5147.6 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
192-6.11 | Range of motion reqts for Assly MC fixture. | 5147.6 | 5147.6 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 5165.4 |  | 5165.4 | 18% | 929.772 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
411-2-8 | Grounding-Commission | 0 | 5176.8 |  | 5176.8 | 18% | 931.824 | 4 | 41 | 411 | 9450 | 4101 | S | 411 |  | 1 |  | 41 | 18
1303-110 | CS Support Final Design | 0 | 5221.8 |  | 5221.8 | 32% | 1670.976 | 1 | 13 | 132 | 9450 | 1303 | 2 |  | 10 | 1 |  | 13 | 32
1501-241 | Write final purchase spec | 0 | 5221.8 |  | 5221.8 | 32% | 1670.976 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
1501-253 | Prep Final Drawings | 0 | 5221.8 |  | 5221.8 | 32% | 1670.976 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
1501-281 | Prep for FDR | 0 | 5221.8 |  | 5221.8 | 32% | 1670.976 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
21-15 | Design Gas Handling Hardware | 0 | 5240 |  | 5240 | 14% | 733.6 | 2 | 21 | 210 | 9450 | 2101 | 2 | EC16 |  | 1 |  |  | 14
431-265 | Fabricate bus components | 0 | 5258.02 |  | 5258.02 | 18% | 946.4436 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
810.009 | PDR Support | 5274.5 | 5274.5 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 03 | 1 |  |  | 17 | 100
1301FD-03 | Layout Subassembly Fixture | 5288 | 5288 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 81 | 1 | C |  | 24 | 100
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 5313 |  | 5313 | 24% | 1275.12 | 1 | 13 | 133 | 9450 | 1354 | F | 133 | 16 | 1 |  |  | 24
21-55 | Install PLC Controls | 0 | 5316.4 |  | 5316.4 | 14% | 744.296 | 2 | 21 | 210 | 9450 | 2101 | F | EC16 |  | 1 |  |  | 14
22-75 | Integrated Systems Testing/Tech Support | 0 | 5316.4 |  | 5316.4 | 14% | 744.296 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 5316.4 |  | 5316.4 | 18% | 956.952 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
S4P1-108 | Change platforms | 0 | 5326.08 |  | 5326.08 | 40% | 2130.432 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 5380.8 |  | 5380.8 | 24% | 1291.392 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-240 | Bolt on preassembled pump duct | 0 | 5380.8 |  | 5380.8 | 24% | 1291.392 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 16 |  |  |  | 24
1301-155 | Trim Coil Layouts | 5407.5 | 5407.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1501-133 | Prepare a "scope sheet" which defines all interf | 5407.5 | 5407.5 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 | 15B |  | 1 |  |  | 32 | LOE
S4P2-108 | Change platforms | 0 | 5469.44 |  | 5469.44 | 40% | 2187.776 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-108 | Change platforms | 0 | 5469.44 |  | 5469.44 | 40% | 2187.776 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
3101-146 | Procure remaining materials | 5484 | 5484 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 20 |  |  |  | 30 | 100
740.110 | Romer CMM-Laptop for 2nd arm | 5484 | 5484 |  | 0 | 24% | 0 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 24 | 1 |  | 18 | 24 | 100
1406-005 | Purchase epoxy & Insulation | 5516.42 | 5516.42 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-1 | 60 | 1 |  |  | 40 | 100
1406-104 | Prepare Draft of Coil Test Plan | 5562.95 | 5562.95 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 15 | 1 |  |  | 40 | 100
444-3-6 | DC Shunts-Install | 0 | 5569.11 |  | 5569.11 | 18% | 1002.4398 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
1403-219 | MCWF assy-Type C | 5580 | 5580 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 03 | 1 |  |  | 40 | 100
1203-201 | Update/Perform FMECA Analyses | 5640.45 | 5640.45 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1404-FR3 | Test Lot 1 specimens - 17 pcs. At $260 | 5644.07 | 5644.07 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | 2 | FRAC | 15 |  |  |  | 40 | 100
441-125 | Program Control pages | 0 | 5644.48 |  | 5644.48 | 18% | 1016.0064 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
820.005 | Proj engr FY09 | 0 | 5652 |  | 5652 | 5% | 282.6 | 8 | 82 | 820 | 9450 | 8202 | S |  | 21 | 1 |  |  | 5
7503-370 | Install Cryostat Circulation Duct | 0 | 5746 |  | 5746 | 24% | 1379.04 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
713.020 | Lab Fab/Assy/Installation | 0 | 5748.8 |  | 5748.8 | 24% | 1379.712 | 7 | 76 | 760 | 9450 | 7601 | F |  |  | 1 |  |  | 24
1351-115A | Assemble TF to Wedge Casting TF#2 | 0 | 5825.4 |  | 5825.4 | 67% | 3903.018 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
1351-905 | Cold test #1 BEFORE casting applied | 0 | 5863.68 |  | 5863.68 | 67% | 3928.6656 | 1 | 13 | 131 | 9450 | 1361 | F | 13Z |  |  |  |  | 67
1351-910 | Cold test #1 again AFTER casting applied | 0 | 5863.68 |  | 5863.68 | 67% | 3928.6656 | 1 | 13 | 131 | 9450 | 1361 | F | 13Z |  |  |  |  | 67
S1P1-103 | Establish metrology setting; align VV base | 0 | 5863.68 |  | 5863.68 | 40% | 2345.472 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 12 |  |  |  | 40
S1P2-103 | Establish metrology setting; align VV base | 0 | 5863.68 |  | 5863.68 | 40% | 2345.472 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 12 |  |  |  | 40
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 5906.88 |  | 5906.88 | 30% | 1772.064 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 10 | 1 |  | 141 | 30
1407-135 | construct cleanroom mech and electrical | 5961.6 | 5961.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1407-135 | construct cleanroom mech and electrical | 5961.6 | 5961.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1407-135 | construct cleanroom mech and electrical | 5961.6 | 5961.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1407-135 | construct cleanroom mech and electrical | 5961.6 | 5961.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 25 | 1 |  | 141 | 34 | 100
1406-010 | Keystone Test for New Conductor | 5961.6 | 5961.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-1 | 60 | 1 |  |  | 40 | 100
1406-029 | Fab New Specimen Molds | 5961.6 | 5961.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-106.3 | Winding Trials (wo/ cladding) | 5961.6 | 5961.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-106.3 | Winding Trials (wo/ cladding) | 5961.6 | 5961.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 01 | 1 | C | 141 | 40 | 100
1406-ST1 | Fab Straight Tee Specimen | 5961.6 | 5961.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-T | 80 | 1 | C | 141 | 40 | 100
1406-ST1 | Fab Straight Tee Specimen | 5961.6 | 5961.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-T | 80 | 1 | C | 141 | 40 | 100
1350-600 | Build Cleanroom | 5990.15 | 5990.15 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
S1P1-116 | Prepare and transfer completed VV to holding are | 0 | 5991.84 |  | 5991.84 | 40% | 2396.736 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 19 |  |  |  | 40
S1P2-116 | Prepare and transfer completed VV to holding are | 0 | 5991.84 |  | 5991.84 | 40% | 2396.736 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 19 |  |  |  | 40
S1P3-103 | Establish metrology setting; align VV base | 0 | 5991.84 |  | 5991.84 | 40% | 2396.736 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 13 |  |  |  | 40
S1P3-116 | Prepare and transfer completed VV to holding are | 0 | 5991.84 |  | 5991.84 | 40% | 2396.736 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 19 |  |  |  | 40
S3P1-103 | Rotate right MC to stand-off position&chk | 0 | 5991.84 |  | 5991.84 | 40% | 2396.736 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P2-103 | Rotate right MC to stand-off position&chk | 0 | 5991.84 |  | 5991.84 | 40% | 2396.736 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
S4P1-107 | Attach TF coils to MC's | 0 | 5991.84 |  | 5991.84 | 40% | 2396.736 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
151-000 | Adv Concep Design Cryostat shell & struct | 6000 | 6000 |  | 0 | 28% | 0 | 1 | 17 | 171 | 9450 | 1701 | 1 | CRYO | 01 | 1 |  |  | 28 | 100
1501-125 | Update drawings & models based on vendor recomm | 6025.5 | 6025.5 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 | 15B |  | 1 |  |  | 32 | 100
1409-032 | Design I2T Protection | 6028 | 6028 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
451-7-2 | FDR DC transmission-Dsn | 6028 | 6028 |  | 0 | 18% | 0 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 01 | 1 |  | 45 | 18 | 100
1501-209 | Prepare SRD | 0 | 6092.1 |  | 6092.1 | 32% | 1949.472 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1501-225 | Write prelim purchase spec | 0 | 6092.1 |  | 6092.1 | 32% | 1949.472 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1407-202 | Setup facility stations | 6121.8 | 6121.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-F | 20 | 1 |  |  | 34 | 100
1803-1.01 | Concept definition and requirements | 6141 | 6141 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 10 | 1 |  |  | 20 | 100
1803-2.01 | Concept definition and requirements | 6141 | 6141 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 10 | 1 |  |  | 20 | 100
7503-240.2 | Install insulation | 0 | 6153.12 |  | 6153.12 | 24% | 1476.7488 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 16 |  |  |  | 24
S3P3-103 | Rotate right MC to stand-off position&chk | 0 | 6153.12 |  | 6153.12 | 40% | 2461.248 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
S4P2-107 | Attach TF coils to MC's | 0 | 6153.12 |  | 6153.12 | 40% | 2461.248 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-107 | Attach TF coils to MC's | 0 | 6153.12 |  | 6153.12 | 40% | 2461.248 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
1350-505 | Winding Clamps | 6155.03 | 6155.03 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 03 |  |  |  | 24 | 100
1350-600 | Build Cleanroom | 6171.23 | 6171.23 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1403-40.2C | Model expected deflections under thermal/EM load | 6177.12 | 6177.12 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1301-160 | Trim Coil Leads | 6180 | 6180 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1403-23 | Update thermo-hydraulic analysis of coils | 6180 | 6180 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW03 |  | 1 |  |  | 40 | 100
1403-31 | Analyze stress in bolted connections | 6180 | 6180 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-39 | Analyze gravity, equip, seismic loading | 6180 | 6180 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-40 | Analyze combined loads and fault conditions | 6180 | 6180 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-42E | Complete checking struct calculations | 6180 | 6180 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1501-113 | Prepare PBR documentation | 6180 | 6180 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 | 15A |  | 1 |  |  | 32 | 100
192-6.07 | Time constant calcs using SPARK | 6180 | 6180 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
124-011.2 | Analysis of Lateral supports | 6200 | 6200 |  | 0 | 30% | 0 | 1 | 12 | 124 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 30 | 100
1403-40.2X | Multifilament coils file incl leads | 6200 | 6200 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 05 | 1 |  |  | 40 | 100
1403-49A | Update tech sheets for new #of turns | 6200 | 6200 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 20 | 1 | C |  | 40 | 100
1403-20.04 | Resolve FDR chits | 6200 | 6200 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | F | C | 141 | 40 | 100
1403-222 | Terminal / elec services assembly-Type C | 6200 | 6200 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1403-42A | WP beam bending results documentation | 6200 | 6200 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1403-58X1 | Check and promote cladding & terminal dwg-Type C | 6200 | 6200 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 | C |  | 40 | 100
21-10 | Eng. Work Planning and Design | 0 | 6205.5 |  | 6205.5 | 14% | 868.77 | 2 | 21 | 210 | 9450 | 2101 | 2 | EC16 |  | 1 |  |  | 14
445-1-6 | Ground Fault Protection-Install | 0 | 6212.16 |  | 6212.16 | 22% | 1366.6752 | 4 | 44 | 445 | 9450 | 4401 | F | 445 |  | 1 |  | 44 | 22
1406-021 | Test Coil | 6230.8 | 6230.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 72 | 1 | C | 141 | 30 | 100
1351-763 | VPI Coil #7 & #8 | 0 | 6241.5 |  | 6241.5 | 67% | 4181.805 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1351-767 | VPI Coil #9 & #10 | 0 | 6241.5 |  | 6241.5 | 67% | 4181.805 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1351-771 | VPI Coil #11 & #12 | 0 | 6241.5 |  | 6241.5 | 67% | 4181.805 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1351-775 | VPI Coil #13 & #14 | 0 | 6241.5 |  | 6241.5 | 67% | 4181.805 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1351-779 | VPI Coil #15 & #16 | 0 | 6241.5 |  | 6241.5 | 67% | 4181.805 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
51-10 | Preliminary Design (Title I) | 0 | 6260.4 |  | 6260.4 | 5% | 313.02 | 5 | 51 | 510 | 9450 | 5101 | 2 |  |  | P |  |  | 5
51-20 | Final Network Design (Title II) | 0 | 6260.4 |  | 6260.4 | 5% | 313.02 | 5 | 51 | 510 | 9450 | 5101 | 2 |  |  | F |  |  | 5
151-031 | Title III engr | 0 | 6266.9 |  | 6266.9 | 28% | 1754.732 | 1 | 17 | 171 | 9450 | 1751 | F | 171 | 19 | 1 |  |  | 28
1403-40.2Z | Update nonlinear winding pack analysis | 5642.271 | 6269.19 |  | 626.919 | 30% | 188.0757 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 08 | 1 |  |  | 30 | 90
1404-FR7 | Engineering coordination | 6298.82 | 6298.82 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | 2 | FRAC | 15 |  |  |  | 40 | 100
1351-783 | VPI Coil #17 & #18 | 0 | 6340.32 |  | 6340.32 | 67% | 4248.0144 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1403-59 | Type-C product specifications | 6350.79 | 6350.79 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 00 | 1 |  |  | 30 | 100
1202-330 | MT-Final MIT/QA plans for VVSA (3.3.1) | 6370 | 6370 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 40 | 100
1202-335 | MT-Firm Fixed Price Proposal for VVSA (3.3.2) | 6370 | 6370 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 40 | 100
1301-175.8 | Rerun Analysis | 6370 | 6370 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 | C |  | 24 | 100
1403-42E | Complete checking struct calculations | 6370 | 6370 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-47B | det boundary conditions single nonlinear windng | 6370 | 6370 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 06 | 1 |  |  | 40 | 100
1403-40.2Z | Update nonlinear winding pack analysis | 5733 | 6370 |  | 637 | 30% | 191.1 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 08 | 1 |  |  | 30 | 90
1350-500 | Recondition turnkng fixture | 6405 | 6405 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1408-107 | Insulation-Initial Delivery for Production | 6405 | 6405 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | INSL | 15 | 1 |  |  | 40 | 100
21-45 | Fabrication/installation | 0 | 6409.5 |  | 6409.5 | 14% | 897.33 | 2 | 21 | 210 | 9450 | 2101 | F | EC16 |  | 1 |  |  | 14
1202-845 | SOW for full size test sample *ECP6* | 6416.8 | 6416.8 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1406-100 | Single conductor torsion test | 6416.8 | 6416.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 20 | 1 |  |  | 40 | 100
1406-021 | Test Coil | 6416.8 | 6416.8 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 72 | 1 | C | 141 | 30 | 100
3101-109 | INTEGRATE LOOP AND LEAD DESIGN WITH H/C TUBES | 6416.8 | 6416.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
3101-125 | PDR PREP -VESSEL SADDLE LOOP MOUNTING | 6416.8 | 6416.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
3101-129 | DESIGN AND PROTOTYPE SADDLE LOOP TERMINATIONS | 6416.8 | 6416.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 00 |  |  |  | 30 | 100
3101-149 | PREPARE METROLOGY | 6416.8 | 6416.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 01 |  |  |  | 30 | 100
3101-409 | FINALIZE LOOP LOCATION/MOUNTING TECHNIQUE | 6416.8 | 6416.8 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD4 |  |  |  |  | 30 | 100
712.008 | Update Platform Specification | 6416.8 | 6416.8 |  | 0 | 24% | 0 | 7 | 73 | 730 | 9450 | 7301 | 2 |  | 25 | 1 |  |  | 24 | 100
1803-3.33 | Design Equivalent Test Simulation Model | 6416.8 | 6416.8 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
1803-3.36 | Design Test Track | 6416.8 | 6416.8 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
1803-3.39 | Fab Test Track | 6416.8 | 6416.8 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
431-215 | Document status | 5775.57 | 6417.3 |  | 641.73 | 18% | 115.5114 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 90
431-225 | Reactivate DF & PEI units | 5776.011 | 6417.79 |  | 641.779 | 18% | 115.5202 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 90
191-8 | LOE-FY089 WBS 191 | 0 | 6420 |  | 6420 | 10% | 642 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
0192-99 | LOE-FY09 | 0 | 6420 |  | 6420 | 10% | 642 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  | STRO | 10 | LOE
1501-213 | Approve ICD's | 0 | 6440.22 |  | 6440.22 | 32% | 2060.8704 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1403-206C | Finish Cooling, Electr Schematic Dwgs - Type C | 5804.505 | 6449.45 |  | 644.945 | 30% | 193.4835 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 28 | 1 |  |  | 30 | 90
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 6456.96 |  | 6456.96 | 24% | 1549.6704 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 6456.96 |  | 6456.96 | 24% | 1549.6704 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 6456.96 |  | 6456.96 | 24% | 1549.6704 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
1403-11.1 | Describe interfaces as part of coil FDR's | 5815.98 | 6462.2 |  | 646.22 | 40% | 258.488 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 |  |  | 40 | 90
1403-70.05 | Update MIT/QA Plans for Type C Winding Fab | 6474 | 6474 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 00 | 1 |  |  | 30 | 100
1407-003.4 | Final Drawings -casting to ring fixture | 6489.6 | 6489.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
1407-003.5 | Final Drawings -Type A casting supports | 6489.6 | 6489.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
1351-901 | Build Cryostat for teststand to hold TF coil | 0 | 6515.2 |  | 6515.2 | 67% | 4365.184 | 1 | 13 | 131 | 9450 | 1361 | F | 13Z |  |  |  |  | 67
1350-505 | Winding Clamps | 6562.23 | 6562.23 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 03 |  |  |  | 24 | 100
1350-510 | Taping Machine Conditioning | 5250.56 | 6563.2 |  | 1312.64 | 24% | 315.0336 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 80
431-230 | Load test | 5925.051 | 6583.39 |  | 658.339 | 18% | 118.501 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 90
411-3-6 | Test Cell AC Power Distr-Install | 3294.085 | 6588.17 |  | 3294.085 | 18% | 592.9353 | 4 | 41 | 411 | 9450 | 4101 | F | 411 |  | 1 |  | 41 | 18 | 50
1403-20.2 | Resolve FDR chits | 5944.167 | 6604.63 |  | 660.463 | 30% | 198.1389 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 45 | 1 |  | 141 | 30 | 90
1206-115 | Analyze | 6610 | 6610 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1206 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
1301R-11 | Design Test Fixtures | 6610 | 6610 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 80 | 1 | C |  | 24 | 100
1301R-12 | Build Test Fixture | 6610 | 6610 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1301FD-04 | Final Drawing Check | 6610 | 6610 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 80 | 1 | C |  | 24 | 100
1301FD-17 | Resolve Tolerance Issues | 6610 | 6610 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 80 | 1 | C |  | 24 | 100
1413-100 | Oversight | 6610 | 6610 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1413 | 2 |  | 30 |  |  |  | 10 | 100
1803-3.01 | Concept definition and requirements | 6610 | 6610 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 10 | 1 |  |  | 40 | 100
1803-4.01 | Concept definition and requirements | 6610 | 6610 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 00 | 1 |  |  | 40 | 100
1803-5.001 | Concept definition and requirements | 6610 | 6610 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 4.00 | 01 | 1 |  |  | 40 | 100
1803-5.01 | Finalize TFTR test cell FPA assembly layout draw | 6610 | 6610 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 6.00 | 00 | 1 |  |  | 40 | 100
1803-5.03 | Design MC assy test components | 6610 | 6610 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 6.00 | 00 | 1 |  |  | 40 | 100
3101-501 | DETERMINE NUMEBR AND LOCATION OF LOOPS | 0 | 6623.6 |  | 6623.6 | 30% | 1987.08 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
1350-515 | Winding mandrel | 1989.516 | 6631.72 |  | 4642.204 | 24% | 1114.129 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 30
1351-557 | Wind Coil #5 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-559 | Wind Coil #6 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-561 | Wind Coil #7 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-563 | Wind Coil #8 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-565 | Wind Coil #9 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-567 | Wind Coil #10 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-569 | Wind Coil #11 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-571 | Wind Coil #12 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-573 | Wind Coil #13 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-575 | Wind Coil #14 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-577 | Wind Coil #15 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-579 | Wind Coil #16 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-581 | Wind Coil #17 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1351-583 | Wind Coil #18 | 0 | 6657.6 |  | 6657.6 | 67% | 4460.592 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
S4P1-103 | Inspect Welds | 0 | 6657.6 |  | 6657.6 | 40% | 2663.04 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
1203-241 | Check FMECA Analyses | 5336.176 | 6670.22 |  | 1334.044 | 40% | 533.6176 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 01 | 1 |  |  | 40 | 80
411-2-8 | Grounding-Commission | 0 | 6706.4 |  | 6706.4 | 18% | 1207.152 | 4 | 41 | 411 | 9450 | 4101 | S | 411 |  | 1 |  | 41 | 18
1203-800 | Issue VV FP Station 1 assy dwg | 5711.6515 | 6719.59 |  | 1007.9385 | 40% | 403.1754 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 03 | 1 |  |  | 40 | 85
3101-157 | Design & fab tooling and clamps | 6722.44 | 6722.44 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 20 |  |  |  | 30 | 100
1403-47A | Update,review & approve FMECA | 672.857 | 6728.57 |  | 6055.713 | 30% | 1816.7139 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 50 | 1 |  |  | 30 | 10
1203-801 | Issue VV FP final assy dwg | 1687 | 6748 |  | 5061 | 40% | 2024.4 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 04 | 1 |  |  | 40 | 25
1203-802 | Issue spacer field machining dwgs | 5398.4 | 6748 |  | 1349.6 | 40% | 539.84 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 07 | 1 |  |  | 40 | 80
1203-806 | Establish interface reqmnts | 5735.8 | 6748 |  | 1012.2 | 40% | 404.88 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 07 | 1 |  |  | 40 | 85
1203-803 | Issue VV final assy dwg | 0 | 6748 |  | 6748 | 40% | 2699.2 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 98 | 1 |  |  | 40
1203-804 | Issue VV assy specification | 0 | 6748 |  | 6748 | 40% | 2699.2 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 98 | 1 |  |  | 40
1403-50A | Check inductance calculation | 0 | 6748 |  | 6748 | 30% | 2024.4 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 70 | 1 | C |  | 30
1416A-105 | Top level models and drawings | 2024.4 | 6748 |  | 4723.6 | 20% | 944.72 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 01 |  |  |  | 20 | 30
1416A-117 | MCWF mods-Studs, Lead Block Mount | 6748 | 6748 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 01 |  |  |  | 20 | 100
1416A-165 | Side A Coil Assy-Cond Layers, Geom Files | 6748 | 6748 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416A-177 | Side A Coil Assy-Check and Promote | 6748 | 6748 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416A-185 | Side B Coil Assy-Cond Layers, Geom Files | 6748 | 6748 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416A-197 | Side B Coil Assy-Check and Promote | 5398.4 | 6748 |  | 1349.6 | 20% | 269.92 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 80
1416A-205 | Coil Post VPI mods-Clamp Arrangement | 5398.4 | 6748 |  | 1349.6 | 20% | 269.92 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 80
1416A-225 | I&C-Rogowski Coils | 2024.4 | 6748 |  | 4723.6 | 20% | 944.72 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 30
1416A-249 | -Type-A Coil Asm Specification | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-261 | -Prepare and Conduct FDR | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416A-265 | -Resolve FDR Comments | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20
1416B-105 | Top level models and drawings | 674.8 | 6748 |  | 6073.2 | 20% | 1214.64 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 10
1416B-113 | MCWF mods-As-Built MCWF | 5398.4 | 6748 |  | 1349.6 | 20% | 269.92 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 80
1416B-117 | MCWF mods-Studs, Lead Block Mount | 3374 | 6748 |  | 3374 | 20% | 674.8 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 50
1416B-165 | Side A Coil Assy-Cond Layers, Geom Files | 2699.2 | 6748 |  | 4048.8 | 20% | 809.76 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 40
1416B-177 | Side A Coil Assy-Check and Promote | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-185 | Side B Coil Assy-Cond Layers, Geom Files | 1349.6 | 6748 |  | 5398.4 | 20% | 1079.68 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 20
1416B-197 | Side B Coil Assy-Check and Promote | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-205 | Coil Post VPI mods-Clamp Arrangement | 2024.4 | 6748 |  | 4723.6 | 20% | 944.72 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 30
1416B-225 | I&C-Rogowski Coils | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-249 | -Type-B Coil Asm Specification | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-261 | -Prepare and Conduct FDR | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
1416B-265 | -Resolve FDR Comments | 0 | 6748 |  | 6748 | 20% | 1349.6 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20
S4P1-115 | Transfer completed assy to C-site test cell | 0 | 6836.8 |  | 6836.8 | 40% | 2734.72 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P2-103 | Inspect Welds | 0 | 6836.8 |  | 6836.8 | 40% | 2734.72 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P2-115 | Transfer completed assy to C-site test cell | 0 | 6836.8 |  | 6836.8 | 40% | 2734.72 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-103 | Inspect Welds | 0 | 6836.8 |  | 6836.8 | 40% | 2734.72 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
S4P3-115 | Transfer completed assy to C-site test cell | 0 | 6836.8 |  | 6836.8 | 40% | 2734.72 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
820.002 | LOE FY04 | 6837 | 6837 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | FY04 | 10 | 1 |  |  | 17 | LOE
1409-130 | Production Cryostat Design | 6839.71 | 6839.71 |  | 0 | 34% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 6 | 01 | 1 | C | 141 | 34 | 100
3101-417 | PROCURE MATERIALS | 0 | 6855 |  | 6855 | 30% | 2056.5 | 3 | 31 | 310 | 9450 | 3101 | F | MD4 |  |  |  |  | 30
3101-529 | PROCURE MATERIALS | 0 | 6855 |  | 6855 | 30% | 2056.5 | 3 | 31 | 310 | 9450 | 3101 | F | MD5 |  |  |  |  | 30
411-2-4 | Grounding-Procure | 0 | 6855 |  | 6855 | 18% | 1233.9 | 4 | 41 | 411 | 9450 | 4101 | T | 411 |  | 1 |  | 41 | 18
412-1-4 | D-site Pulsed AC Power Distr-Procure | 0 | 6860.44 |  | 6860.44 | 18% | 1234.8792 | 4 | 41 | 412 | 9450 | 4101 | T | 412 |  | 1 |  | 41 | 18
411-2-6 | Grounding-Install | 0 | 6870.8 |  | 6870.8 | 18% | 1236.744 | 4 | 41 | 411 | 9450 | 4101 | F | 411 |  | 1 |  | 41 | 18
412-1-2 | D-site Pulsed AC Power Distr-Dsn | 0 | 6870.8 |  | 6870.8 | 18% | 1236.744 | 4 | 41 | 412 | 9450 | 4101 | 2 | 412 |  | 1 |  | 41 | 18
441-100 | PLC Specification | 0 | 6870.8 |  | 6870.8 | 18% | 1236.744 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
441-105 | Prep Block diagrams | 0 | 6870.8 |  | 6870.8 | 18% | 1236.744 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
442-1-2 | Kirk Keys-Dsn | 0 | 6870.8 |  | 6870.8 | 18% | 1236.744 | 4 | 44 | 442 | 9450 | 4401 | 2 | 442 |  | 1 |  | 44 | 18
444-3-2 | DC Shunts-Dsn | 0 | 6870.8 |  | 6870.8 | 18% | 1236.744 | 4 | 44 | 444 | 9450 | 4401 | 2 | 444 |  | 1 |  | 44 | 18
445-1-6 | Ground Fault Protection-Install | 0 | 6870.8 |  | 6870.8 | 22% | 1511.576 | 4 | 44 | 445 | 9450 | 4401 | F | 445 |  | 1 |  | 44 | 22
445-2-135 | Overload Protect-Documentation | 0 | 6870.8 |  | 6870.8 | 22% | 1511.576 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
451-4-2 | FDR AC auxiliaries & grounding-Dsn | 0 | 6870.8 |  | 6870.8 | 18% | 1236.744 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 15 | F |  | 45 | 18
452-2-2 | Diagnostics sensor cabling-Dsn | 0 | 6870.8 |  | 6870.8 | 26% | 1786.408 | 4 | 45 | 452 | 9450 | 4501 | 2 | 452 |  | 1 |  | 45 | 26
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 6887.2 |  | 6887.2 | 18% | 1239.696 | 4 | 41 | 412 | 9450 | 4101 | F | 412 |  | 1 |  | 41 | 18
3101-146 | Procure remaining materials | 6940.4 | 6940.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 20 |  |  |  | 30 | 100
3101-217 | Peer review of lead routing | 6940.4 | 6940.4 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 11 |  |  |  | 30 | 100
3101-230 | Install heat shrink tubing on MI cable | 1041.06 | 6940.4 |  | 5899.34 | 30% | 1769.802 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 12 |  |  |  | 30 | 15
3101-521 | FINALIZE LOOP LOCATION/MOUNTING TECHNIQUE | 0 | 6940.4 |  | 6940.4 | 30% | 2082.12 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
3101-525 | FDR PREP - MC SHELL SADDLE LOOPS | 0 | 6940.4 |  | 6940.4 | 30% | 2082.12 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD5 |  |  |  |  | 30
1404-66 | Proposal evaluation & contract oversight | 6949.26 | 6949.26 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 14D | 13 | 1 |  |  | 40 | 100
1301-150 | Vendor Responses | 6952.5 | 6952.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
441-110 | PLC CWD's & Cabling | 0 | 6957.76 |  | 6957.76 | 18% | 1252.3968 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
1403-47C | Perform cool-down/warmup analysis | 0 | 6962.4 |  | 6962.4 | 30% | 2088.72 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 65 | 1 | C |  | 30
1501-246 | Update Models | 0 | 6962.4 |  | 6962.4 | 32% | 2227.968 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 | 1 |  |  | 32
1501-277 | Prep Assy Dwgs | 0 | 6962.4 |  | 6962.4 | 32% | 2227.968 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
21-45 | Fabrication/installation | 0 | 7025 |  | 7025 | 14% | 983.5 | 2 | 21 | 210 | 9450 | 2101 | F | EC16 |  | 1 |  |  | 14
3101-161 | SUPT LOOP INSTL 200 LOOPS), TESTING | 0 | 7035.89 |  | 7035.89 | 30% | 2110.767 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 40 |  |  |  | 30
441-130 | Pre-commissioning tests | 0 | 7046.1 |  | 7046.1 | 18% | 1268.298 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
431-275 | Power cabling & Installation | 0 | 7055.6 |  | 7055.6 | 18% | 1270.008 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
441-120 | Program PLC Logic | 0 | 7055.6 |  | 7055.6 | 18% | 1270.008 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 7055.6 |  | 7055.6 | 26% | 1834.456 | 4 | 45 | 452 | 9450 | 4501 | S | 452 |  | 1 |  | 45 | 26
810.005 | Project Management OfficePPPL FY07 | 0 | 7084 |  | 7084 | 5% | 354.2 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 0 | 7101.6 |  | 7101.6 | 18% | 1278.288 | 4 | 44 | 444 | 9450 | 4401 | 2 | 444 |  | 1 |  | 44 | 18
3101-533 | INSTALL MC SHELL SADDLE LOOPS | 0 | 7125.99 |  | 7125.99 | 30% | 2137.797 | 3 | 31 | 310 | 9450 | 3101 | F | MD5 |  |  |  |  | 30
1803-3.49 | Run Test | 7153.92 | 7153.92 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
361-001 | Design Visible Camera sys | 0 | 7192.38 |  | 7192.38 | 20% | 1438.476 | 3 | 36 | 360 | 9450 | 3601 | 2 |  |  | 1 |  |  | 20
441-100 | PLC Specification | 0 | 7247.52 |  | 7247.52 | 18% | 1304.5536 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
22-70 | Integrated Systems Testing/Eng | 0 | 7283.2 |  | 7283.2 | 14% | 1019.648 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 7306 |  | 7306 | 24% | 1753.44 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-090 | Install local Platforms around FPA-1 | 0 | 7306 |  | 7306 | 24% | 1753.44 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-130 | Install local Platforms around FPA-2 | 0 | 7306 |  | 7306 | 24% | 1753.44 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-190 | Install local Platforms around FPA-3 | 0 | 7306 |  | 7306 | 24% | 1753.44 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 04 |  |  |  | 24
7503-210 | Fit-up all TF coils | 0 | 7306 |  | 7306 | 24% | 1753.44 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
25-099 | FY04 work accomplished | 7351.5 | 7351.5 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 2510 |  | 1 |  | 25 | 16
1409-027 | Cryo Line Installation | 7359.78 | 7359.78 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 07 | 1 |  | 141 | 34 | 100
1407-100.2 | Fabr turning fixt&coil supports **2nd line** | 7371 | 7371 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 28 | 100
3101-333 | Complete termination box design & prototyping | 7413.95 | 7413.95 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30 | 100
1403-40.2D | Confirm plasma performance & surface quality | 7416 | 7416 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1407-109 | Fab & assemble VPI delivery sys | 7452 | 7452 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | VPI | 21 | 1 |  | 141 | 34 | 100
1407-109 | Fab & assemble VPI delivery sys | 7452 | 7452 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | VPI | 21 | 1 |  | 141 | 34 | 100
1407-109 | Fab & assemble VPI delivery sys | 7452 | 7452 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | VPI | 21 | 1 |  | 141 | 34 | 100
431-210 | Organize & verify documentation | 7086.5155 | 7459.49 |  | 372.9745 | 18% | 67.1354 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 95
1351-653 | GW & Apply Mold Coil #3 | 0 | 7489.8 |  | 7489.8 | 67% | 5018.166 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1351-655 | GW & Apply Mold Coil #4 | 0 | 7489.8 |  | 7489.8 | 67% | 5018.166 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1301-180 | Update ANSYS model & structure | 7491.12 | 7491.12 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
191-042 | PDR #17,25,3 | 0 | 7514.61 |  | 7514.61 | 30% | 2254.383 | 1 | 16 | 161 | 9450 | 1601 | F | 161 |  | 1 |  |  | 30
1406-001 | Purchase 10 spools conductor (twisted racetrack) | 7644 | 7644 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-1 | 60 | 1 |  |  | 40 | 100
1406-003 | Purchase 8 spools conductor (long twisted windin | 7644 | 7644 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-1 | 60 | 1 |  |  | 40 | 100
1413-110 | Cut 3 discs from proto;cut 1 into qrts (MTM) | 7686 | 7686 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1413 | 2 |  | 30 |  |  |  | 10 | 100
1407-110.3 | Compl Fabr Winding clamp sets (300 of 400) | 7686 | 7686 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  |  | 28 | 100
810.003 | Project Management Office PPPL FY05 | 7686 | 7686 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
1203-101 | Prepare documents for PDR closeout | 7721.4 | 7721.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | PDRX | 05 | 1 |  |  | 40 | 100
1203-111 | Response to chits, prepare FY04 WP/WAF/Checklist | 7721.4 | 7721.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | PDRX | 05 | 1 |  |  | 40 | 100
1203-121 | Review, revise, and approve SRD | 7721.4 | 7721.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | PDRX | 05 | 1 |  |  | 40 | 100
1203-131 | Complete preliminary design of insulation and he | 7721.4 | 7721.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | PDRX | 05 | 1 |  |  | 40 | 100
1403-202 | G-10 Filler DwgsType C ????????????? | 7721.4 | 7721.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1406-098 | Complete Drawings of Casting | 7721.4 | 7721.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-098 | Complete Drawings of Casting | 7721.4 | 7721.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1801-001 | Apr-Sept MIE Costs PPPL | 7750 | 7750 |  | 0 | 0% | 0 | 1 | 18 | 181 | 9450 | 1801 | 1 | 0000 | 10 | 1 |  |  | 0 | 100
1351-110A | Assemble TF to Wedge Casting TF#1 | 0 | 7818.24 |  | 7818.24 | 67% | 5238.2208 | 1 | 13 | 131 | 9450 | 1361 | 1 | 13A | 70 | 1 | C |  | 67
S1P1-101 | Receive VV and inspect | 0 | 7818.24 |  | 7818.24 | 40% | 3127.296 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 10 |  |  |  | 40
S1P2-101 | Receive VV and inspect | 0 | 7818.24 |  | 7818.24 | 40% | 3127.296 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 10 |  |  |  | 40
S1P3-101 | Receive VV and inspect | 0 | 7818.24 |  | 7818.24 | 40% | 3127.296 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 11 |  |  |  | 40
3101-517A | Install termination boxes | 0 | 7989.12 |  | 7989.12 | 30% | 2396.736 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30
S4P1-104 | Assemble left TF Coil Assembly check position | 0 | 7989.12 |  | 7989.12 | 40% | 3195.648 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P1-106 | Assemble right TF Coil Assembly chk position | 0 | 7989.12 |  | 7989.12 | 40% | 3195.648 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
3101-231 | Terminate MC co-wound loops | 0 | 7993.8 |  | 7993.8 | 30% | 2398.14 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD2 | 14 |  |  |  | 30
1202-848 | Bid,eval,award full size test sample **ECP36** | 8000 | 8000 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1206 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 8024.04 |  | 8024.04 | 18% | 1444.3272 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
124-011 | Final design WBS 124 VV supports | 8077.6 | 8077.6 |  | 0 | 30% | 0 | 1 | 12 | 124 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 30 | 100
1407-003.2 | Final Drawings for winding clamps | 8112 | 8112 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
1407-003.6 | Final Drawings -Type B casting supports | 8112 | 8112 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
121-034.1 | VVSA Title III engr | 3457.2706 | 8153.94 |  | 4696.6694 | 40% | 1878.6678 | 1 | 12 | 121 | 9450 | 1250 | F |  | 07 | 1 |  |  | 40 | LOE
1803-3.04 | VV support stand - model design and drawing deta | 8188 | 8188 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 25 | 1 |  |  | 40 | 100
1803-3.05 | Platform - design and drawing details | 8188 | 8188 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 30 | 1 |  |  | 40 | 100
S4P2-104 | Assemble left TF Coil Assembly check position | 0 | 8204.16 |  | 8204.16 | 40% | 3281.664 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P2-106 | Assemble right TF Coil Assembly chk position | 0 | 8204.16 |  | 8204.16 | 40% | 3281.664 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-104 | Assemble left TF Coil Assembly check position | 0 | 8204.16 |  | 8204.16 | 40% | 3281.664 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
S4P3-106 | Assemble right TF Coil Assembly chk position | 0 | 8204.16 |  | 8204.16 | 40% | 3281.664 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
124-011 | Final design WBS 124 VV supports | 8224.47 | 8224.47 |  | 0 | 30% | 0 | 1 | 12 | 124 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 30 | 100
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 8226 |  | 8226 | 18% | 1480.68 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
444-2-4 | DC Potential Transducers (DCPTs)-Procure | 0 | 8226 |  | 8226 | 18% | 1480.68 | 4 | 44 | 444 | 9450 | 4401 | T | 444 |  | 1 |  | 44 | 18
810.004 | Project Management Office PPPL FY06 | 4014.288 | 8226 |  | 4211.712 | 5% | 210.5856 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5 | LOE
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 8244.96 |  | 8244.96 | 18% | 1484.0928 | 4 | 41 | 411 | 9450 | 4101 | S | 411 |  | 1 |  | 41 | 18
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 8260.41 |  | 8260.41 | 22% | 1817.2902 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
1501-001 | Prelim Design Structures | 8262.5 | 8262.5 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32 | 100
3101-425 | INSTALL HEAT SHRINK CABLE | 0 | 8285.47 |  | 8285.47 | 30% | 2485.641 | 3 | 31 | 310 | 9450 | 3101 | F | MD4 |  |  |  |  | 30
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 8322 |  | 8322 | 30% | 2496.6 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 46 | 1 |  | 141 | 30
METFY05 | Dimensional control FY05 ECP24 | 8325 | 8325 |  | 0 | 25% | 0 | 8 | 82 | 820 | 9450 | 8205 | 2 |  | 20 | 1 |  |  | 25 | LOE
1404-66 | Proposal evaluation & contract oversight | 8343 | 8343 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 14D | 13 | 1 |  |  | 40 | 100
1301FD-12 | Turn to Turn and Ground Wrap 2nd Sample | 8346.24 | 8346.24 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1407.011.4 | Instl insulation on autoclave | 8346.24 | 8346.24 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407.011.4 | Instl insulation on autoclave | 8346.24 | 8346.24 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1406-50 | Fab Straight Tee Specimen | 8346.24 | 8346.24 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-50 | Fab Straight Tee Specimen | 8346.24 | 8346.24 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
444-3-6 | DC Shunts-Install | 0 | 8392.37 |  | 8392.37 | 18% | 1510.6266 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
1406-016.A | fab trc lead components | 8409.56 | 8409.56 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-4 | 63 | 1 |  | 141 | 40 | 100
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 8466.72 |  | 8466.72 | 18% | 1524.0096 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 8506.24 |  | 8506.24 | 18% | 1531.1232 | 4 | 41 | 412 | 9450 | 4101 | F | 412 |  | 1 |  | 41 | 18
1403-201 | Leads start assy Dwgs (10)-Type C | 8582.11 | 8582.11 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1303-110 | CS Support Final Design | 0 | 8703 |  | 8703 | 32% | 2784.96 | 1 | 13 | 132 | 9450 | 1303 | 2 |  | 10 | 1 |  | 13 | 32
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 8718.32 |  | 8718.32 | 18% | 1569.2976 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
640.021 | Assembly/Fabrication | 0 | 8739.84 |  | 8739.84 | 20% | 1747.968 | 6 | 63 | 630 | 9450 | 6301 | F |  |  | 1 |  |  | 20
1409-029 | Oversight/Supervision | 8748.12 | 8748.12 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 14 | 1 |  | 141 | 34 | 100
1406-000.2 | Supervision & Oversight | 8821.68 | 8821.68 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
1351-533 | Coil Supplies- Lead Blocks(pe6134 for copper) | 0 | 8851.19 |  | 8851.19 | 24% | 2124.2856 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 06 |  |  |  | 24 | M&S
820.04X | Proj engr FY07 | 0 | 8855 |  | 8855 | 5% | 442.75 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5
1301-190 | FEA Analysis PF Supports,Stress Deflection | 8918 | 8918 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 45 | 1 |  |  | 24 | 100
1406-011 | Purchase add'l copper Conductor | 8918 | 8918 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-1 | 60 | 1 |  |  | 40 | 100
1407-011.1 | Autoclave assembly | 8942.4 | 8942.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407-011.1 | Autoclave assembly | 8942.4 | 8942.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407-011.2 | Rebuild vacuum pumps (2) | 8942.4 | 8942.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407-011.2 | Rebuild vacuum pumps (2) | 8942.4 | 8942.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1408-999 | 3rd winding line conductor payout sys | 8942.4 | 8942.4 |  | 0 | 40% | 0 | 1 | 14 | 144 | 9450 | 1412 | T | FIX | 00 | 1 |  |  | 40 | 100
1406-01609 | Rework Lead Blocks | 8942.4 | 8942.4 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 02 | 1 | C | 141 | 30 | 100
1409-027 | Cryo Line Installation | 8942.4 | 8942.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 07 | 1 |  | 141 | 34 | 100
820.004Z | Proj engr FY08 | 0 | 8965 |  | 8965 | 5% | 448.25 | 8 | 82 | 820 | 9450 | 8202 | F |  | 21 | 1 |  |  | 5
444-4-2 | Signal Conditioning & Cabling-Dsn | 1345.617 | 8970.78 |  | 7625.163 | 18% | 1372.5293 | 4 | 44 | 444 | 9450 | 4401 | 2 | 444 |  | 1 |  | 44 | 18 | 15
FY05CV-20 | FY05 unrecoverable cost variance | 9000 | 9000 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1415 | [7 empty] | 100
FY05CV-46 | FY05 unrecoverable cost variance | 9000 | 9000 |  | 0 | 0% | 0 | 8 | 82 | 820 | 9450 | 8204
FY05CV-31 | FY05 unrecoverable cost variance | 9000 | 9000 |  | 0 | 0% | 0 | 1 | 19 | 191 | 9450 | 1901
1803-3.10A | Issue dwgs | 9006.8 | 9006.8 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.10 | 74 | 1 |  |  | 40 | 100
C1RW | C1 rework | 9022.52 | 9022.52 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 00 | 1 | C | 141 | 20 | 100
1350-505 | Winding Clamps | 9049.52 | 9049.52 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 03 |  |  |  | 24 | 100
7502-002 | Test Cell 208v outlets | 6402.781 | 9146.83 |  | 2744.049 | 24% | 658.5718 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  | 7 | 24 | 70
1803-7.03 | Develop and maintain assembly plan document | 9254 | 9254 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
1403-40.1 | Check Structural Calculations | 9265.68 | 9265.68 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-40.1A | Prepare plate element model of coil structure | 9265.68 | 9265.68 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-40.1C | Check all struct calculkations | 9265.68 | 9265.68 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
192-6.10 | MC interf during assly, geometry, assly trajecto | 9270 | 9270 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
124-011.1 | Lateral VV supports | 9300 | 9300 |  | 0 | 30% | 0 | 1 | 12 | 124 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 30 | 100
124-011.1 | Lateral VV supports | 9300 | 9300 |  | 0 | 30% | 0 | 1 | 12 | 124 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 30 | 100
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 0 | 9321.15 |  | 9321.15 | 28% | 2609.922 | 1 | 16 | 161 | 9450 | 1601 | F | 161 |  | 1 |  |  | 28
6501-001 | Apr-Sept MIE Cost PPPL | 9380 | 9380 |  | 0 | 0% | 0 | 6 | 65 | 612 | 9450 | 6501 | 1 | 0000 |  | 1 |  | 6501 | 0 | 100
613.030 | Test Cell copper ground plane cuts | 7534.152 | 9417.69 |  | 1883.538 | 24% | 452.0491 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  | 7 | 24 | 80
1203-810 | resolve design pockets for soft x ray arrays | 9447.2 | 9447.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12SX | 07 | 1 |  |  | 40 | 100
192-6.031 | Demo Method for current center on TRC | 9462.79 | 9462.79 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 05 | 1 |  |  | 10 | 100
21-30 | Drafting | 0 | 9468.8 |  | 9468.8 | 14% | 1325.632 | 2 | 21 | 210 | 9450 | 2101 | 2 | EC16 |  | 1 |  |  | 14
442-1-2 | Kirk Keys-Dsn | 0 | 9468.8 |  | 9468.8 | 18% | 1704.384 | 4 | 44 | 442 | 9450 | 4401 | 2 | 442 |  | 1 |  | 44 | 18
444-3-2 | DC Shunts-Dsn | 0 | 9468.8 |  | 9468.8 | 18% | 1704.384 | 4 | 44 | 444 | 9450 | 4401 | 2 | 444 |  | 1 |  | 44 | 18
445-2-110 | Overload Protect-Design | 0 | 9468.8 |  | 9468.8 | 22% | 2083.136 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
1406-019.1 | Instl permanent clamps | 9538.56 | 9538.56 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 70 | 1 | C | 141 | 30 | 100
1406-021 | Test Coil | 9538.56 | 9538.56 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 72 | 1 | C | 141 | 30 | 100
1407-204.2 | Build cleanroom (1 add'l) **2nd line** | 9555 | 9555 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-F | 20 | 1 |  |  | 28 | 100
1407-110 | Fabricate Winding clamp sets (125) | 9555 | 9555 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
633-010 | Final Design | 0 | 9617.28 |  | 9617.28 | 20% | 1923.456 | 6 | 62 | 623 | 9450 | 6201 | 2 | 623 | 13 | F |  |  | 20
431-230 | Load test | 8662.113 | 9624.57 |  | 962.457 | 18% | 173.2423 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 90
1409-100 | Design Controls Modifications | 9625.2 | 9625.2 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
181.110 | PPPL EM LOE FY05 | 9625.2 | 9625.2 |  | 0 | 24% | 0 | 1 | 18 | 181 | 9450 | 1802 | F | A | 40 | 1 |  |  | 24 | LOE
1406-102 | Review/Approve Clamp& Chill Plate Dwgs | 9637.46 | 9637.46 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
623.011 | Design WBS 612 | 0 | 9724 |  | 9724 | 20% | 1944.8 | 6 | 61 | 613 | 9450 | 6101 | 2 | 613 |  | 1 |  |  | 20
MCWF-401 | A4-Receive at PPPL | 0 | 9730 |  | 9730 | 10% | 973 | 1 | 14 | 141 | 9450 | 1411 | P |  | 41 |  |  |  | 10
P3-111C | Final Clamps & Warm Test (Station1) C4 | 0 | 9772.8 |  | 9772.8 | 30% | 2931.84 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 04 | 1 |  | 141 | 30
P1-141C | Final Clamps & Warm Test (Station1) C5 | 0 | 9772.8 |  | 9772.8 | 30% | 2931.84 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 05 | 1 |  | 141 | 30
431-275 | Power cabling & Installation | 0 | 9835 |  | 9835 | 18% | 1770.3 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
1409-100 | Design Controls Modifications | 9880.8 | 9880.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1351-651 | GW & Apply Mold Coil #2 | 0 | 9894.86 |  | 9894.86 | 67% | 6629.5562 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
1403-42D | Fracture fatigue analysis for MCWF | 9915 | 9915 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 10 | 1 |  |  | 40 | 100
1803-1.01 | Concept definition and requirements | 9915 | 9915 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 10 | 1 |  |  | 20 | 100
1803-2.01 | Concept definition and requirements | 9915 | 9915 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 10 | 1 |  |  | 20 | 100
1803-7.02 | Develop and maintain concept definition document | 9915 | 9915 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
7502-011 | Cable Removal in test cell (S04335-32) | 9937.2 | 9937.2 |  | 0 | 24% | 0 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  |  | 24 | 100
1350-100.1 | Design tooling & winding facility | 8970.966 | 9967.74 |  | 996.774 | 24% | 239.2258 | 1 | 13 | 131 | 9450 | 1350 | F |  | 02 |  |  |  | 24 | 90
P2-021C | Final Clamps & Warm Test (Station1) A1 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 06 | 1 |  | 141 | 30
P3-021C | Final Clamps & Warm Test (Station1) A2 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 07 | 1 |  | 141 | 30
P3-051C | Final Clamps & Warm Test (Station1) A3 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 08 | 1 |  | 141 | 30
P1-051C | Final Clamps & Warm Test (Station1) B1 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 09 | 1 |  | 141 | 30
P3-141C | Final Clamps & Warm Test (Station1) A4 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 10 | 1 |  | 141 | 30
P2-141C | Final Clamps & Warm Test (Station1) B2 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 11 | 1 |  | 141 | 30
P2-081C | Final Clamps & Warm Test (Station1) B3 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 12 | 1 |  | 141 | 30
P3-081C | Final Clamps & Warm Test (Station1) B4 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 13 | 1 |  | 141 | 30
P3-171C | Final Clamps & Warm Test (Station1) B5 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 14 | 1 |  | 141 | 30
P2-171C | Final Clamps & Warm Test (Station1) B6 | 0 | 9986.4 |  | 9986.4 | 30% | 2995.92 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 15 | 1 |  | 141 | 30
FY05CV-12 | FY05 unrecoverable cost variance | 10000 | 10000 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1404 | [7 empty] | 100
1403-42H | calculate EM loads at leads | 6007.038 | 10011.73 |  | 4004.692 | 30% | 1201.4076 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 47 | 1 | C |  | 30 | 60
445-1-6 | Ground Fault Protection-Install | 0 | 10059.6 |  | 10059.6 | 22% | 2213.112 | 4 | 44 | 445 | 9450 | 4401 | F | 445 |  | 1 |  | 44 | 22
1350-605 | Install winding table | 10081.92 | 10081.92 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
21-45 | Fabrication/installation | 0 | 10089 |  | 10089 | 14% | 1412.46 | 2 | 21 | 210 | 9450 | 2101 | F | EC16 |  | 1 |  |  | 14
1416A-121 | MCWF mods-Seal Groove Adapter | 8097.6 | 10122 |  | 2024.4 | 20% | 404.88 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 01 |  |  |  | 20 | 80
1416A-141 | Lead Block Assy-Detail Parts, Intralink | 10122 | 10122 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416B-121 | MCWF mods-Seal Groove Adapter | 3036.6 | 10122 |  | 7085.4 | 20% | 1417.08 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 30
1416B-141 | Lead Block Assy-Detail Parts, Intralink | 7085.4 | 10122 |  | 3036.6 | 20% | 607.32 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 70
1407-003.1 | Facility Drawings | 10140 | 10140 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
1407-003.9 | Electrical design support/oversight | 10140 | 10140 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
711A.020 | LOE FY04 | 10140 | 10140 |  | 0 | 15% | 0 | 7 | 74 | 741 | 9450 | 7401 | 1 | A | 11 | 1 |  |  | 15 | LOE
1406-048 | Testing & Strain Gauge Design | 10203 | 10203 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 |  | 1 |  |  | 40 | 100
431-265 | Fabricate bus components | 0 | 10217.39 |  | 10217.39 | 18% | 1839.1302 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
P1-081C | Final Clamps & Warm Test (Station1) A5 | 0 | 10255.2 |  | 10255.2 | 30% | 3076.56 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 16 | 1 |  | 141 | 30
P1-171C | Final Clamps & Warm Test (Station1) A6 | 0 | 10255.2 |  | 10255.2 | 30% | 3076.56 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 17 | 1 |  | 141 | 30
P2-051C | Final Clamps & Warm Test (Station1) C6 | 0 | 10255.2 |  | 10255.2 | 30% | 3076.56 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 18 | 1 |  | 141 | 30
1350-510 | Taping Machine Conditioning | 8204.8 | 10256 |  | 2051.2 | 24% | 492.288 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 80
1351-512 | Prepare braze samples | 0 | 10256 |  | 10256 | 67% | 6871.52 | 1 | 13 | 131 | 9450 | 1361 | F | 13F |  |  |  |  | 67
1351-515 | Test brazed samples | 0 | 10256 |  | 10256 | 67% | 6871.52 | 1 | 13 | 131 | 9450 | 1361 | F | 13F |  |  |  |  | 67
1351-848 | Prep & setup for warm test | 0 | 10256 |  | 10256 | 67% | 6871.52 | 1 | 13 | 131 | 9450 | 1361 | F | 13L |  |  |  |  | 67
FY06CV-01 | FY06 YTD cost vari (offset by scope reductions) | 10256 | 10256 |  | 0 | 0% | 0 | 3 | 31 | 310 | 9450 | 3101
1203-237 | Perform Thermal-Hydraulic Analysis VV htg/clng | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1403-06 | Prepare documents for PDR closeout | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW01 |  | 1 |  |  | 40 | 100
1403-26 | Perform scan of EM fault load conditions | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW03 |  | 1 |  |  | 40 | 100
1403-26.1 | Check thermal & electrical calculations | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW03 |  | 1 |  |  | 40 | 100
1403-32 | Update MECHANICA model of 3 coil types | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-40.1B | Confirm global deflection/stress, re-inf of shel | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-50 | Prepare FDR documentation / presentations | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW06 | 10 | 1 |  |  | 40 | 100
1403-45 | Check and promote models / drawings | 10295.2 | 10295.2 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
192-6.08 | Indep check time constant calcs using EDDYCUFF | 10295.2 | 10295.2 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
444-3-8 | DC Shunts-Commission | 0 | 10330.8 |  | 10330.8 | 18% | 1859.544 | 4 | 44 | 444 | 9450 | 4401 | S | 444 |  | 1 |  | 44 | 18
21-20 | Design PLC Controls | 0 | 10353.6 |  | 10353.6 | 14% | 1449.504 | 2 | 21 | 210 | 9450 | 2101 | 2 | EC16 |  | 1 |  |  | 14
411-2-6 | Grounding-Install | 0 | 10353.6 |  | 10353.6 | 18% | 1863.648 | 4 | 41 | 411 | 9450 | 4101 | F | 411 |  | 1 |  | 41 | 18
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 10353.6 |  | 10353.6 | 18% | 1863.648 | 4 | 41 | 411 | 9450 | 4101 | S | 411 |  | 1 |  | 41 | 18
441-105 | Prep Block diagrams | 0 | 10353.6 |  | 10353.6 | 18% | 1863.648 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
445-2-110 | Overload Protect-Design | 0 | 10353.6 |  | 10353.6 | 22% | 2277.792 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
445-2-120 | Overload Protect-Test 4 units | 0 | 10353.6 |  | 10353.6 | 22% | 2277.792 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
1403-36 | Update EM loads for reference scenarios | 10357.62 | 10357.62 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-38 | Check nonlinear winding pack analysis | 10357.62 | 10357.62 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
713A.040 | General procurements | 0 | 10410 |  | 10410 | 40% | 4164 | 1 | 18 | 186 | 9450 | 1803 | T | TOOL | 11 | 1 |  |  | 40
713A.050 | Welding tools, materials & equipt | 0 | 10410 |  | 10410 | 40% | 4164 | 1 | 18 | 186 | 9450 | 1803 | T | TOOL | 12 | 1 |  |  | 40
3101-141 | FDR PREP- | 5205.3 | 10410.6 |  | 5205.3 | 30% | 1561.59 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 14 |  |  |  | 30 | 50
1501-253 | Prep Final Drawings | 0 | 10443.6 |  | 10443.6 | 32% | 3341.952 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
22-25 | Eng. Work Planning and Design | 0 | 10480 |  | 10480 | 14% | 1467.2 | 2 | 22 | 220 | 9450 | 2201 | 2 |  |  | 1 |  |  | 14
7502-010 | Ready Rooms (under control room) 110v outlets | 0 | 10480 |  | 10480 | 24% | 2515.2 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  | 7 | 24
7502-035 | Control room firesealing | 0 | 10480 |  | 10480 | 24% | 2515.2 | 7 | 75 | 750 | 9450 | 7502 | F |  |  | 1 |  | 7 | 24
184-100 | Assemble 3 TF coils&structure -Left-Period #1 | 0 | 10480 |  | 10480 | 40% | 4192 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-105 | Assemble 3 TF coils&structure -Right -Period #1 | 0 | 10480 |  | 10480 | 40% | 4192 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-110 | Assemble 3 TF coils&structure -Left-Period #2 | 0 | 10480 |  | 10480 | 40% | 4192 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-115 | Assemble 3 TF coils&structure -Right -Period #2 | 0 | 10480 |  | 10480 | 40% | 4192 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-120 | Assemble 3 TF coils&structure -Left -Period #3 | 0 | 10480 |  | 10480 | 40% | 4192 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
1407-115.2 | Fabr Conduct payout spool syst ** 2nd line** | 10530 | 10530 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  |  | 28 | 100
740.020 | Facility Prep | 1611.09 | 10530 |  | 8918.91 | 24% | 2140.5384 | 1 | 18 | 187 | 9450 | 1810 | F | S0P0 | 20 | 1 |  |  | 24 | LOE
380-015 | Fab & Install Beam probe | 0 | 10583.4 |  | 10583.4 | 34% | 3598.356 | 3 | 38 | 380 | 9450 | 3801 | F |  |  | 1 |  |  | 34
1202-305 | MT-Issue Draft MIT/QA plan (3.2.1) | 10599.68 | 10599.68 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 0 | 100
380-015 | Fab & Install Beam probe | 0 | 10632.8 |  | 10632.8 | 34% | 3615.152 | 3 | 38 | 380 | 9450 | 3801 | F |  |  | 1 |  |  | 34
445-2-130 | Overload Protect-Write & perform ISTP | 0 | 10632.8 |  | 10632.8 | 22% | 2339.216 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 10632.8 |  | 10632.8 | 26% | 2764.528 | 4 | 45 | 452 | 9450 | 4501 | F | 452 |  | 1 |  | 45 | 26
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 10632.8 |  | 10632.8 | 26% | 2764.528 | 4 | 45 | 452 | 9450 | 4501 | S | 452 |  | 1 |  | 45 | 26
22-50 | Perform maint. & repair of pmpg sys | 0 | 10634.88 |  | 10634.88 | 14% | 1488.8832 | 2 | 22 | 220 | 9450 | 2201 | 2 |  |  | 1 |  |  | 14
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 10649.74 |  | 10649.74 | 18% | 1916.9532 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
161-031 | Title III engr WBS 172 | 0 | 10726.43 |  | 10726.43 | 32% | 3432.4576 | 1 | 17 | 172 | 9450 | 1752 | F | 172 | 19 | 1 |  |  | 32
1350-605 | Install winding table | 10730.88 | 10730.88 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
441-135 | Install I/O Cabling | 0 | 10740.34 |  | 10740.34 | 18% | 1933.2612 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
22-55 | Repair and Calibration of vac instrumentation | 0 | 10761.6 |  | 10761.6 | 14% | 1506.624 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 10761.6 |  | 10761.6 | 24% | 2582.784 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-090 | Install local Platforms around FPA-1 | 0 | 10761.6 |  | 10761.6 | 24% | 2582.784 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-130 | Install local Platforms around FPA-2 | 0 | 10761.6 |  | 10761.6 | 24% | 2582.784 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-190 | Install local Platforms around FPA-3 | 0 | 10761.6 |  | 10761.6 | 24% | 2582.784 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 04 |  |  |  | 24
7503-260 | PTP Pumpdown & leak check VV | 0 | 10761.6 |  | 10761.6 | 24% | 2582.784 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 16 |  |  |  | 24
7503-210 | Fit-up all TF coils | 0 | 10761.6 |  | 10761.6 | 24% | 2582.784 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
184-125 | Assemble 3 TF coils&structure -Right -Period #3 | 0 | 10761.6 |  | 10761.6 | 40% | 4304.64 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
1501-205 | Update Design/models | 0 | 10791.72 |  | 10791.72 | 32% | 3453.3504 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1403-FY04 | Analysis fy04 | 10815 | 10815 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 00 | 1 |  |  | 40 | 100
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 10938.65 | 10938.65 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
192-5 | LOE-FY05 WBS 192-5 VV & Coil Services Integr | 10938.65 | 10938.65 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 10938.88 |  | 10938.88 | 24% | 2625.3312 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
7503-020 | Install & Level Support Base Plates | 0 | 10959 |  | 10959 | 24% | 2630.16 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 10959 |  | 10959 | 24% | 2630.16 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 05 |  |  |  | 24
1351-535 | Coil Supplies- Safety & PPE equipt & supplies | 0 | 10968 |  | 10968 | 24% | 2632.32 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 50 |  |  |  | 24
1351-537 | Coil Supplies- Misc supplies | 0 | 10968 |  | 10968 | 24% | 2632.32 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 50 |  |  |  | 24
1351-541 | VPI Supplies- Misc VPI supplies | 0 | 10968 |  | 10968 | 24% | 2632.32 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 50 |  |  |  | 24
740.105 | Romer CMM-Software support&warranty renewal FY06 | 5374.32 | 10968 |  | 5593.68 | 24% | 1342.4832 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 24 | 1 |  | 18 | 24 | LOE
740.106 | Romer CMM-Software support&warranty renewal FY07 | 0 | 10978.92 |  | 10978.92 | 24% | 2634.9408 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 24 | 1 |  | 18 | 24
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 10985.04 |  | 10985.04 | 30% | 3295.512 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 21 | 1 |  | 141 | 30
7503-310 | Complete LN2 connections | 0 | 11053.76 |  | 11053.76 | 24% | 2652.9024 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
192-6.02 | Check critical coil tolerance calculations. | 11098.48 | 11098.48 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 02 | 1 |  |  | 10 | 100
1301-185 | FEA Analysis Coils,Stress deflection | 11147.5 | 11147.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
1301-195 | Seismic Analysis | 11147.5 | 11147.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
2501-014 | FY04 work accomplished | 11147.5 | 11147.5 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16
1803-3.10A | Issue dwgs | 11237 | 11237 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.10 | 74 | 1 |  |  | 40 | 100
740.107 | Romer CMM-Software support&warranty renewal FY07 | 0 | 11240 |  | 11240 | 24% | 2697.6 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 24 | 1 |  | 18 | 24
441-135 | Install I/O Cabling | 0 | 11281.77 |  | 11281.77 | 18% | 2030.7186 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
1501-269 | Check Analysis | 0 | 11313.9 |  | 11313.9 | 32% | 3620.448 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
1406-110 | Finalize, Approve coil test plan | 11337.43 | 11337.43 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 15 | 1 |  |  | 40 | 100
1407-008 | Remaining Autoclave components-Deliver | 11466 | 11466 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 12 | 1 |  |  | 34 | 100
7503-340 | Install Cryostat Base, vapor barrie& port boots | 0 | 11492 |  | 11492 | 24% | 2758.08 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
7503-350 | Install Cryostat upper section,VB and port boots | 0 | 11492 |  | 11492 | 24% | 2758.08 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
730.8200 | PTP and Cooldown | 0 | 11492 |  | 11492 | 30% | 3447.6 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 91 | 1 |  | 7 | 30
1409-027 | Cryo Line Installation | 11502.07 | 11502.07 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 07 | 1 |  | 141 | 34 | 100
740.108 | Romer CMM-Software support&warranty renewal FY07 | 0 | 11520 |  | 11520 | 24% | 2764.8 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 24 | 1 |  | 18 | 24
820.003 | Proj engr FY05 | 11655 | 11655 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8202 | 2 |  | 20 | 1 |  |  | 10 | LOE
1351-089 | Fab Lift Fixture | 8795.52 | 11727.36 |  | 2931.84 | 24% | 703.6416 | 1 | 13 | 131 | 9450 | 1350 | 1 |  | 89 | 1 | C |  | 24 | 75
P3-091 | Receive C4, Prep& Instl Cladding | 2345.472 | 11727.36 |  | 9381.888 | 30% | 2814.5664 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 04 | 1 |  | 141 | 30 | 20
P1-121 | Receive C5, Prep& Instl Cladding | 0 | 11727.36 |  | 11727.36 | 30% | 3518.208 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 05 | 1 |  | 141 | 30
P2-001 | Receive A1, Prep& Instl Cladding | 0 | 11727.36 |  | 11727.36 | 30% | 3518.208 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 06 | 1 | C | 141 | 30
P3-001 | Receive A2, Prep& Instl Cladding | 0 | 11727.36 |  | 11727.36 | 30% | 3518.208 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 07 | 1 | C | 141 | 30
P3-031 | Receive A3, Prep& Instl Cladding | 0 | 11727.36 |  | 11727.36 | 30% | 3518.208 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 08 | 1 |  | 141 | 30
P1-031 | Receive B1, Prep& Instl Cladding | 0 | 11727.36 |  | 11727.36 | 30% | 3518.208 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 09 | 1 |  | 141 | 30
51-00 | FY03 | 11900 | 11900 |  | 0 | 3% | 0 | 5 | 58 | 580 | 9450 | 5801 | 1 |  |  | 1 |  |  | 3 | LOE
1407-106 | Instl electric to VPI platforms & cntrl panel | 11923.2 | 11923.2 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | VPI | 20 | 1 |  | 141 | 34 | 100
1407-106 | Instl electric to VPI platforms & cntrl panel | 11923.2 | 11923.2 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | VPI | 20 | 1 |  | 141 | 34 | 100
1409-120 | Install Control Modifications | 11923.2 | 11923.2 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1409-141 | Modify Cryostat for TRC | 11923.2 | 11923.2 |  | 0 | 34% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 50 | 1 |  | 141 | 34 | 100
1803-3.43 | Assembly of Test Article | 11923.2 | 11923.2 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
P3-121 | Receive A4, Prep& Instl Cladding | 0 | 11926.72 |  | 11926.72 | 30% | 3578.016 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 10 | 1 |  | 141 | 30
P2-121 | Receive B2, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 11 | 1 |  | 141 | 30
P2-061 | Receive B3, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 12 | 1 |  | 141 | 30
P2-151 | Receive B4, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 13 | 1 |  | 141 | 30
P3-061 | Receive B5, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 14 | 1 |  | 141 | 30
P3-151 | Receive B6, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 15 | 1 |  | 141 | 30
P1-061 | Receive A5, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 16 | 1 |  | 141 | 30
P1-151 | Receive A6, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 17 | 1 |  | 141 | 30
P2-031 | Receive C6, Prep& Instl Cladding | 0 | 11983.68 |  | 11983.68 | 30% | 3595.104 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 18 | 1 |  | 141 | 30
1408-147 | Copper Conductor -Delivery #1 PE005371 | 12002.97 | 12002.97 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | COPP | 20 | 1 |  | 141 | 40 | 100
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 12155 |  | 12155 | 34% | 4132.7 | 3 | 38 | 380 | 9450 | 3801 | 2 |  |  | 1 |  |  | 34
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 12163.2 |  | 12163.2 | 34% | 4135.488 | 3 | 38 | 380 | 9450 | 3801 | 2 |  |  | 1 |  |  | 34
1407-003.8 | Misc Drawings (ecn's etc) | 12168 | 12168 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 65 | 1 |  |  | 34 | 100
713.020 | Lab Fab/Assy/Installation | 0 | 12173.95 |  | 12173.95 | 24% | 2921.748 | 7 | 76 | 760 | 9450 | 7601 | F |  |  | 1 |  |  | 24
1701-001 | Apr-Sept MIE Costs PPPL | 12180 | 12180 |  | 0 | 0% | 0 | 1 | 17 | 171 | 9450 | 1701 | 1 | 0000 |  | 1 |  |  | 0 | 100
1501-217 | Update stress analysis | 0 | 12184.2 |  | 12184.2 | 32% | 3898.944 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32
1501-249 | Update Analysis | 0 | 12184.2 |  | 12184.2 | 32% | 3898.944 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 20 |  |  |  | 32
0191-6 | LOE-FY06 WBS 191 | 5979.96 | 12204 |  | 6224.04 | 10% | 622.404 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
0192-6 | LOE-FY06 WBS 192 | 5979.96 | 12204 |  | 6224.04 | 10% | 622.404 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
172-031.1 | Title III engr | 4279.7416 | 12262.87 |  | 7983.1284 | 20% | 1596.6257 | 1 | 14 | 141 | 9450 | 1411 | F | 14T | 10 | 1 |  |  | 20 | LOE
1803-1.02 | VV Support Fixture - model design& drawing detai | 12282 | 12282 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 15 | 1 |  |  | 20 | 100
1803-1.04 | Metrology -sightline layout metrology support | 12282 | 12282 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 25 | 1 |  |  | 20 | 100
1803-3.03 | MC Gantry Crane - model design and drawing detai | 12282 | 12282 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.00 | 20 | 1 |  |  | 40 | 100
1803-4.03 | TF HP support turning fixture - model design d | 12282 | 12282 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 01 | 1 |  |  | 40 | 100
1803-4.02 | MC Support Stand - model design and drawing deta | 12282 | 12282 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 4.00 | 00 | 1 |  |  | 40 | 100
1803-5.03 | Design MC assy test components | 12282 | 12282 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 6.00 | 00 | 1 |  |  | 40 | 100
820.004 | Proj engr FY06 | 5995.08 | 12285 |  | 6289.92 | 5% | 314.496 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5 | LOE
1202-327 | PPPL Receipt Inspection of MT PVVS | 12360 | 12360 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 40 | 100
1202-427 | PPPL Receipt Inspection of RW PVVS | 12360 | 12360 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 50 | 1 |  |  | 40 | 100
1203-238 | Check Thermal-Hydraulic Analysis VV htg/clng | 12360 | 12360 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1301-170 | New Lead Details | 12360 | 12360 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 |  |  | 24 | 100
1301R-22 | Hydraulic Analysis | 12360 | 12360 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 69 | 1 |  |  | 24 | 100
1501-109 | Prepare FY 04 WP/WAF | 12360 | 12360 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 | 15A |  | 1 |  |  | 32 | 100
192-6.11 | Range of motion reqts for Assly MC fixture. | 12360 | 12360 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
411-2-2 | Grounding-Dsn | 0 | 12367.44 |  | 12367.44 | 18% | 2226.1392 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
P1-021C | Final Clamps & Warm Test (Station1) C1 | 12378.88 | 12378.88 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 00 | 1 |  | 141 | 20 | 100
P1-111C | Final Clamps & Warm Test (Station1) C2 | 0 | 12378.88 |  | 12378.88 | 20% | 2475.776 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 02 | 1 |  | 141 | 20
P2-111C | Final Clamps & Warm Test (Station1) C3 | 0 | 12378.88 |  | 12378.88 | 20% | 2475.776 | 1 | 14 | 142 | 9450 | 1451 | F | 7 | 03 | 1 |  | 141 | 20
1403-58X2 | Check and promote lead blocks | 12400 | 12400 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 | C |  | 40 | 100
1403-219 | MCWF assy-Type C | 12400 | 12400 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 03 | 1 |  |  | 40 | 100
1403-066 | Clamp modifications Dwgs | 12400 | 12400 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C | 141 | 40 | 100
1403-068 | TRC I&C | 12400 | 12400 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C | 141 | 40 | 100
0191-6X | LOE-FY07 WBS 191 | 0 | 12408 |  | 12408 | 10% | 1240.8 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
0192-6X | LOE-FY07 WBS 192 | 0 | 12408 |  | 12408 | 10% | 1240.8 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
51-02 | FY05 LOE support | 12462.26 | 12462.26 |  | 0 | 3% | 0 | 5 | 58 | 580 | 9450 | 5801 | 2 |  |  | 1 |  |  | 3 | LOE
1350-515 | Winding mandrel | 3744.309 | 12481.03 |  | 8736.721 | 24% | 2096.813 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 30
1351-533 | Coil Supplies- Lead Blocks(pe6134 for copper) | 0 | 12493.52 |  | 12493.52 | 24% | 2998.4448 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 06 |  |  |  | 24 | M&S
55-10 | Preliminary Design (Title I) | 0 | 12520.8 |  | 12520.8 | 8% | 1001.664 | 5 | 55 | 550 | 9450 | 5501 | 2 |  |  | P |  |  | 8
55-20 | Final Design (Title II) | 0 | 12520.8 |  | 12520.8 | 8% | 1001.664 | 5 | 55 | 550 | 9450 | 5501 | 2 |  |  | F |  |  | 8
141-031 | Title III engr WBS 132 | 0 | 12573.25 |  | 12573.25 | 24% | 3017.58 | 1 | 13 | 132 | 9450 | 1352 | F | 13P | 50 | 1 |  |  | 24
1301R-14 | Build Samples | 12602.4 | 12602.4 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 80 | 1 | C |  | 24 | 100
1409-155 | Fab/Instl Closed Loop LN2 sys | 12602.4 | 12602.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 07 | 1 | C | 141 | 34 | 100
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 12613.2 |  | 12613.2 | 20% | 2522.64 | 1 | 13 | 134 | 9450 | 1355 | T | 134 |  | 1 |  |  | 20
P3-091 | Receive C4, Prep& Instl Cladding | 2524.64 | 12623.2 |  | 10098.56 | 30% | 3029.568 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 04 | 1 |  | 141 | 30 | 20
P1-121 | Receive C5, Prep& Instl Cladding | 0 | 12623.2 |  | 12623.2 | 30% | 3786.96 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 05 | 1 |  | 141 | 30
P2-001 | Receive A1, Prep& Instl Cladding | 0 | 12623.2 |  | 12623.2 | 30% | 3786.96 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 06 | 1 | C | 141 | 30
P3-001 | Receive A2, Prep& Instl Cladding | 0 | 12623.2 |  | 12623.2 | 30% | 3786.96 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 07 | 1 | C | 141 | 30
P3-031 | Receive A3, Prep& Instl Cladding | 0 | 12623.2 |  | 12623.2 | 30% | 3786.96 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 08 | 1 |  | 141 | 30
P1-031 | Receive B1, Prep& Instl Cladding | 0 | 12623.2 |  | 12623.2 | 30% | 3786.96 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 09 | 1 |  | 141 | 30
0191-7 | LOE-FY08 WBS 191 | 0 | 12624 |  | 12624 | 10% | 1262.4 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
0192-7 | LOE-FY08 WBS 192 | 0 | 12624 |  | 12624 | 10% | 1262.4 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
1409-034 | Fabricate I2T Cards | 12636 | 12636 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1203-233 | Check structural analysis | 12638.08 | 12638.08 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
722.010 | PF Coil receipt inspect/test (formerly wbs 183) | 0 | 12644.88 |  | 12644.88 | 20% | 2528.976 | 1 | 13 | 132 | 9450 | 1352 | F | 13P | 49 | 1 |  |  | 20
1407-115 | Fabricate Conductor payout spool system | 12740 | 12740 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
1409-040 | Install N2 Ejection Scheme | 12740 | 12740 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1408-999 | 3rd winding line conductor payout sys | 12810 | 12810 |  | 0 | 40% | 0 | 1 | 14 | 144 | 9450 | 1412 | T | FIX | 00 | 1 |  |  | 40 | 100
740.135 | Gary Puhl subcontract for metrology support | 12810 | 12810 |  | 0 | 24% | 0 | 8 | 82 | 820 | 9450 | 8205 | T | MEAS | 30 | 1 |  | 18 | 24
1403-76 | Structural analysis of leads | 10250.704 | 12813.38 |  | 2562.676 | 30% | 768.8028 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 19 | 1 | C |  | 30 | 80
1203-141 | Finalize Spec for VVSA | 12833.6 | 12833.6 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1406-033 | Prepare Test report | 12833.6 | 12833.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 22 | 1 |  |  | 40 | 100
1409-028 | System Testing (planar racetrack) | 12833.6 | 12833.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 64 | 1 | C | 141 | 34 | 100
1203-331 | Prepare Presentations | 12869 | 12869 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1803-2.04 | Metrology - sightline layout design details metr | 12896.1 | 12896.1 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 13 | 1 |  |  | 20 | 100
P3-121 | Receive A4, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 10 | 1 |  | 141 | 30
P2-121 | Receive B2, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 11 | 1 |  | 141 | 30
P2-061 | Receive B3, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 12 | 1 |  | 141 | 30
P2-151 | Receive B4, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 13 | 1 |  | 141 | 30
P3-061 | Receive B5, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 14 | 1 |  | 141 | 30
P3-151 | Receive B6, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 15 | 1 |  | 141 | 30
P1-061 | Receive A5, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 16 | 1 |  | 141 | 30
P1-151 | Receive A6, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 17 | 1 |  | 141 | 30
P2-031 | Receive C6, Prep& Instl Cladding | 0 | 12899.1 |  | 12899.1 | 30% | 3869.73 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 18 | 1 |  | 141 | 30
361-015 | Fab/Assy/Installation Visible Camera | 0 | 12913.92 |  | 12913.92 | 20% | 2582.784 | 3 | 36 | 360 | 9450 | 3601 | F |  |  | 1 |  |  | 20
1403-11.1 | Describe interfaces as part of coil FDR's | 11631.951 | 12924.39 |  | 1292.439 | 40% | 516.9756 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 |  |  | 40 | 90
1403-11.1 | Describe interfaces as part of coil FDR's | 11631.951 | 12924.39 |  | 1292.439 | 40% | 516.9756 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 |  |  | 40 | 90
1301-175.7 | Complete PDR Drawings | 12928.71 | 12928.71 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 23 | 1 | C |  | 24 | 100
FY05CV-42 | FY05 unrecoverable cost variance | 13000 | 13000 |  | 0 | 0% | 0 | 8 | 81 | 810 | 9450 | 8102
1403-60C | Finish Update design basis document | 7806.534 | 13010.89 |  | 5204.356 | 30% | 1561.3068 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 37 | 1 |  |  | 30 | 60
192-6.031 | Demo Method for current center on TRC | 13027.19 | 13027.19 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 05 | 1 |  |  | 10 | 100
1350-510 | Taping Machine Conditioning | 10424.32 | 13030.4 |  | 2606.08 | 24% | 625.4592 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 80
1351-649 | GW & Apply Mold Coil #1 | 0 | 13030.4 |  | 13030.4 | 67% | 8730.368 | 1 | 13 | 131 | 9450 | 1361 | F | 13J |  |  |  |  | 67
S1P1-107.1 | Loop termination & verification | 0 | 13030.4 |  | 13030.4 | 40% | 5212.16 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 15 |  |  |  | 40
S1P2-107.1 | Loop termination & verification | 0 | 13030.4 |  | 13030.4 | 40% | 5212.16 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 15 |  |  |  | 40
1403-73 | Prep struct analysis report | 10446.08 | 13057.6 |  | 2611.52 | 30% | 783.456 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 15 | 1 | C |  | 30 | 80
1303-TRIM | Trim Coil Design | 0 | 13107.32 |  | 13107.32 | 32% | 4194.3424 | 1 | 13 | 133 | 9450 | 1354 | 2 | 133 | 01 | 1 |  | 13 | 32
1303-TRIM | Trim Coil Design | 0 | 13107.32 |  | 13107.32 | 32% | 4194.3424 | 1 | 13 | 133 | 9450 | 1354 | 2 | 133 | 01 | 1 |  | 13 | 32
1416A-113 | MCWF mods-As-Built MCWF | 13153.5 | 13153.5 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 01 |  |  |  | 20 | 100
C1RW | C1 rework | 13162.5 | 13162.5 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 00 | 1 | C | 141 | 20 | 100
1301R-10 | Check or Re-Run Analysis with new data | 13220 | 13220 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 80 | 1 | C |  | 24 | 100
1501-001 | Prelim Design Structures | 13220 | 13220 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32 | 100
1803-1.04 | Metrology -sightline layout metrology support | 13220 | 13220 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 25 | 1 |  |  | 20 | 100
1803-1.05 | Structural / Seismic Analysis check | 13220 | 13220 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 30 | 1 |  |  | 20 | 100
1803-5.03 | Design MC assy test components | 13220 | 13220 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 6.00 | 00 | 1 |  |  | 40 | 100
1803-4.13 | FAB-TF Support Stands (1) | 0 | 13230.15 |  | 13230.15 | 40% | 5292.06 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 20 | 1 |  |  | 40
S1P3-107.1 | Loop termination & verification | 0 | 13315.2 |  | 13315.2 | 40% | 5326.08 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 16 |  |  |  | 40
810.003 | Project Management Office PPPL FY05 | 13320 | 13320 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
411-2-6 | Grounding-Install | 0 | 13412.8 |  | 13412.8 | 18% | 2414.304 | 4 | 41 | 411 | 9450 | 4101 | F | 411 |  | 1 |  | 41 | 18
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 13412.8 |  | 13412.8 | 18% | 2414.304 | 4 | 41 | 411 | 9450 | 4101 | S | 411 |  | 1 |  | 41 | 18
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 13455.34 |  | 13455.34 | 18% | 2421.9612 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
1416B-133 | Lead Block Assy-Lead Blocks | 12143.367 | 13492.63 |  | 1349.263 | 20% | 269.8526 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 90
1416B-137 | Lead Block Assy-Top and Side Plates | 12143.367 | 13492.63 |  | 1349.263 | 20% | 269.8526 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 90
1416A-133 | Lead Block Assy-Lead Blocks | 13496 | 13496 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
1416A-137 | Lead Block Assy-Top and Side Plates | 13496 | 13496 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
163.001 | Title I design WBS 163 Coil protection | 0 | 13536.8 |  | 13536.8 | 28% | 3790.304 | 1 | 16 | 163 | 9450 | 1601 | 1 | 163 |  | 1 |  |  | 28
163.011 | Title II design WBS 163 Coil protection | 0 | 13536.8 |  | 13536.8 | 28% | 3790.304 | 1 | 16 | 163 | 9450 | 1601 | 2 | 163 |  | 1 |  |  | 28
133-010 | Design WBS 134 Conv Coil I&C | 1354.059 | 13540.59 |  | 12186.531 | 24% | 2924.7674 | 1 | 13 | 130 | 9450 | 1302 | 1 | TFIC | 85 | 1 |  |  | 24 | 10
444-3-6 | DC Shunts-Install | 0 | 13590.05 |  | 13590.05 | 18% | 2446.209 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
172-031 | Title III engr | 13612.15 | 13612.15 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1411 | F | 14T | 10 | 1 |  |  | 40 | LOE
192-6.031 | Demo Method for current center on TRC | 13623.32 | 13623.32 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 05 | 1 |  |  | 10 | 100
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 13673.6 |  | 13673.6 | 24% | 3281.664 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-240 | Bolt on preassembled pump duct | 0 | 13673.6 |  | 13673.6 | 24% | 3281.664 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 16 |  |  |  | 24
1409-135 | Production Cryostat Fabr & Install | 10968 | 13710 |  | 2742 | 34% | 932.28 | 1 | 14 | 142 | 9450 | 1414 | R | 6 | 02 | 1 | C | 141 | 34 | 80
442-1-4 | Kirk Keys-Procure | 0 | 13710 |  | 13710 | 18% | 2467.8 | 4 | 44 | 442 | 9450 | 4401 | T | 442 |  | 1 |  | 44 | 18
7502-020 | Resurface TC floor | 0 | 13710 |  | 13710 | 24% | 3290.4 | 7 | 75 | 750 | 9450 | 7502 | F |  |  | 1 |  | 7 | 24
7502-035 | Control room firesealing | 0 | 13710 |  | 13710 | 24% | 3290.4 | 7 | 75 | 750 | 9450 | 7502 | F |  |  | 1 |  | 7 | 24
431-240 | Simulate each of 6 pwr loops in PSCAD | 0 | 13741.6 |  | 13741.6 | 18% | 2473.488 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
441-095 | Design Interlock sys | 0 | 13741.6 |  | 13741.6 | 18% | 2473.488 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
441-097 | Install Interlock sys | 0 | 13741.6 |  | 13741.6 | 18% | 2473.488 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
445-2-105 | Overload Protect-Write spec and approve | 0 | 13741.6 |  | 13741.6 | 22% | 3023.152 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
445-2-120 | Overload Protect-Test 4 units | 0 | 13741.6 |  | 13741.6 | 22% | 3023.152 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
452-1-2 | Diagnostics AC Power Distr-Dsn | 0 | 13741.6 |  | 13741.6 | 26% | 3572.816 | 4 | 45 | 452 | 9450 | 4501 | 2 | 452 |  | 1 |  | 45 | 26
452-2-6 | Diagnostics sensor cabling-Install | 0 | 13763.27 |  | 13763.27 | 26% | 3578.4502 | 4 | 45 | 452 | 9450 | 4501 | F | 452 |  | 1 |  | 45 | 26
1403-14 | Revise winding form and windings/asm models | 13769.83 | 13769.83 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW02 |  | 1 |  |  | 40 | 100
1403-14 | Revise winding form and windings/asm models | 13769.83 | 13769.83 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW02 |  | 1 |  |  | 40 | 100
1403-14 | Revise winding form and windings/asm models | 13769.83 | 13769.83 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW02 |  | 1 |  |  | 40 | 100
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 13774.4 |  | 13774.4 | 26% | 3581.344 | 4 | 45 | 452 | 9450 | 4501 | S | 452 |  | 1 |  | 45 | 26
451-6-2 | FDR C-Site -Cabling | 275.6066 | 13780.33 |  | 13504.7234 | 18% | 2430.8502 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 13 | F |  | 45 | 18 | 2
820.003 | Proj engr FY05 | 13796.12 | 13796.12 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8202 | 2 |  | 20 | 1 |  |  | 10 | LOE
443-1-2 | Develop Control Algorithms-Dsn | 0 | 13819.68 |  | 13819.68 | 18% | 2487.5424 | 4 | 44 | 443 | 9450 | 4401 | 2 | 443 |  | 1 |  | 44 | 18
810.002 | Project Management Office PPPL FY04 | 13832 | 13832 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
820.002 | LOE FY04 | 13832 | 13832 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | FY04 | 10 | 1 |  |  | 17 | LOE
181.100 | PPPL EM LOE FY04 | 13832 | 13832 |  | 0 | 24% | 0 | 1 | 18 | 181 | 9450 | 1802 | 2 | A | 39 | 1 |  |  | 24 | LOE
1406-000.2 | Supervision & Oversight | 13881 | 13881 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
1803-7.01 | Meetings Prep and Reporting | 13881 | 13881 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
441-135 | Install I/O Cabling | 0 | 13913.81 |  | 13913.81 | 18% | 2504.4858 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
1803-2.05 | Structural / Seismic Analysis | 0 | 13924.8 |  | 13924.8 | 20% | 2784.96 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 14 | 1 |  |  | 20
1803-4.07 | Structural Analysis | 0 | 13924.8 |  | 13924.8 | 40% | 5569.92 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 17 | 1 |  |  | 40
191-001 | Title I design WBS 161 LN2 manifolds&piping | 0 | 13934.15 |  | 13934.15 | 28% | 3901.562 | 1 | 16 | 161 | 9450 | 1601 | 1 | 161 |  | 1 |  | 16 | 28
1406-048 | Testing & Strain Gauge Design | 13956.54 | 13956.54 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 |  | 1 |  |  | 40 | 100
451-2-2.1 | FDR C-Site | 279.7146 | 13985.73 |  | 13706.0154 | 18% | 2467.0828 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 14 | F |  | 45 | 18 | 2
431-200 | Condition/spare parts inventory | 13287.2225 | 13986.55 |  | 699.3275 | 18% | 125.8789 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 95
FY05CV-8 | FY05 unrecoverable cost variance | 14000 | 14000 |  | 0 | 0% | 0 | 1 | 13 | 131 | 9450 | 1351 |  | 13E | 00
840.203 | Closeout cost FY04 ECP-21 | 14000 | 14000 |  | 0 | 3% | 0 | 8 | 84 | 840 | 9450 | 8401 | P | FY04 |  | 1 |  |  | 3 | LOE
1350-515 | Winding mandrel | 4201.146 | 14003.82 |  | 9802.674 | 24% | 2352.6418 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 30
810.004 | Project Management Office PPPL FY06 | 6851.52 | 14040 |  | 7188.48 | 5% | 359.424 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5 | LOE
453-1-8 | Testing PTPs, ISTPs | 0 | 14050 |  | 14050 | 18% | 2529 | 4 | 45 | 453 | 9450 | 4501 | S | 453 |  | 1 |  | 45 | 18
163.001 | Title I design WBS 163 Coil protection | 0 | 14095.8 |  | 14095.8 | 28% | 3946.824 | 1 | 16 | 163 | 9450 | 1601 | 1 | 163 |  | 1 |  |  | 28
163.011 | Title II design WBS 163 Coil protection | 0 | 14095.8 |  | 14095.8 | 28% | 3946.824 | 1 | 16 | 163 | 9450 | 1601 | 2 | 163 |  | 1 |  |  | 28
445-2-130 | Overload Protect-Write & perform ISTP | 0 | 14111.2 |  | 14111.2 | 22% | 3104.464 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 14111.2 |  | 14111.2 | 26% | 3668.912 | 4 | 45 | 452 | 9450 | 4501 | F | 452 |  | 1 |  | 45 | 26
1403-16 | Assembly bolts, nuts,washers | 8508.318 | 14180.53 |  | 5672.212 | 40% | 2268.8848 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 | C |  | 40 | 60
21-25 | Electrical Drafting for pumping system | 0 | 14203.2 |  | 14203.2 | 14% | 1988.448 | 2 | 21 | 210 | 9450 | 2101 | 2 | EC16 |  | 1 |  |  | 14
445-1-2 | Ground Fault Protection-Dsn | 0 | 14203.2 |  | 14203.2 | 22% | 3124.704 | 4 | 44 | 445 | 9450 | 4401 | 2 | 445 |  | 1 |  | 44 | 22
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 14333.44 |  | 14333.44 | 30% | 4300.032 | 1 | 14 | 142 | 9450 | 1414 | F | 6 | 10 | 1 |  | 141 | 30
810.104X | Project Management Office ORNL FY07 | 0 | 14444.32 |  | 14444.32 | 10% | 1444.432 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10
820.003 | Proj engr FY05 | 14480.1 | 14480.1 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8202 | 2 |  | 20 | 1 |  |  | 10 | LOE
1407-100.5 | Complete Fab & Instl Turning Fixt 4 | 14531.4 | 14531.4 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  | 141 | 28 | 100
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 14560.97 |  | 14560.97 | 22% | 3203.4134 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
1351-755 | VPI Coil #3 & #4 | 0 | 14563.5 |  | 14563.5 | 67% | 9757.545 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1351-759 | VPI Coil #5 & #6 | 0 | 14563.5 |  | 14563.5 | 67% | 9757.545 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
623.011 | Design WBS 612 | 0 | 14566.4 |  | 14566.4 | 20% | 2913.28 | 6 | 61 | 613 | 9450 | 6101 | 2 | 613 |  | 1 |  |  | 20
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 14566.4 |  | 14566.4 | 20% | 2913.28 | 6 | 61 | 613 | 9450 | 6101 | F | 613 |  | 1 |  |  | 20
640.011 | Design GN2, Air & Vent Systems | 0 | 14566.4 |  | 14566.4 | 20% | 2913.28 | 6 | 63 | 630 | 9450 | 6301 | 2 |  |  | 1 |  |  | 20
1202-ECP16 | ecp-16 | 14600 | 14600 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 0000 | 10 | 1 |  |  | 0 | 100
7503-370 | Install Cryostat Circulation Duct | 0 | 14601.6 |  | 14601.6 | 24% | 3504.384 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
MCWF-251 | B1-Receive at PPPL | 0 | 14660 |  | 14660 | 10% | 1466 | 1 | 14 | 141 | 9450 | 1411 | P |  | 40 |  |  |  | 10
163-015 | Title III design CS sprt struc | 0 | 14728.65 |  | 14728.65 | 32% | 4713.168 | 1 | 13 | 132 | 9450 | 1353 | F | 132A | 24 | 1 |  |  | 32
122-012 | Heater Tape System Design | 14063.762 | 14803.96 |  | 740.198 | 32% | 236.8634 | 1 | 12 | 123 | 9450 | 1203 | 2 | 124H | 09 | 1 |  |  | 32 | 80
713.020 | Lab Fab/Assy/Installation | 0 | 14821.16 |  | 14821.16 | 24% | 3557.0784 | 7 | 76 | 760 | 9450 | 7601 | F |  |  | 1 |  |  | 24
1415-100 | Straight Tee Lacing Test | 14850 | 14850 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1415 | F | 6 | 06 | 1 |  | 141 | 30 | 100
810.104 | Project Management Office ORNL FY06 | 7281.7652 | 14921.65 |  | 7639.8848 | 10% | 763.9885 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10 | LOE
191-031 | Title III engr WBS 161 | 0 | 14986.21 |  | 14986.21 | 28% | 4196.1388 | 1 | 16 | 161 | 9450 | 1601 | F | 161 |  | 1 |  |  | 28
65-03 | LOE WBS 6 | 15000 | 15000 |  | 0 | 20% | 0 | 6 | 65 | 650 | 9450 | 6163 | 1 |  |  | 1 |  |  | 20 | LOE
163.001 | Title I design WBS 163 Coil protection | 0 | 15112 |  | 15112 | 28% | 4231.36 | 1 | 16 | 163 | 9450 | 1601 | 1 | 163 |  | 1 |  |  | 28
163.011 | Title II design WBS 163 Coil protection | 0 | 15112 |  | 15112 | 28% | 4231.36 | 1 | 16 | 163 | 9450 | 1601 | 2 | 163 |  | 1 |  |  | 28
1202-435 | RW-Firm Fixed Price Proposal for VVSA (3.3.2) | 15122.38 | 15122.38 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 53 | 1 |  |  | 40 | 100
1407-115 | Fabricate Conductor payout spool system | 15163.2 | 15163.2 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
1406-54 | Complete shear modulus & cyclic testing | 15163.2 | 15163.2 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
163-001 | Title I design CS sprt struc | 15295.5 | 15295.5 |  | 0 | 32% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | 0000 | 07 | 1 |  |  | 32 | 100
1203-151 | Update VVSA Drawings incl ECP6 add'l port config | 15442.8 | 15442.8 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1203-235 | Perform Local Thermal Analysis | 15442.8 | 15442.8 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1203-236 | Checdk Local Thermal Analysis | 15442.8 | 15442.8 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1403-53 | Resolve FDR comments and recommendations | 15442.8 | 15442.8 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW07 | 10 | 1 |  | 141 | 40 | 100
1403-48 | Update design basis document | 15442.8 | 15442.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW08 | 10 | 1 |  |  | 40 | 100
1403-42C | Revise analysis incorp final modeling changes | 15442.8 | 15442.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-46 | Update build-to specification / SOW | 15442.8 | 15442.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-30 | Analyze global stress /deflect winding form asm | 15450 | 15450 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-221 | Lead ends assy-Type C | 15500 | 15500 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1406-018 | Pre-VPI Press test &Apply bag mold | 15500.16 | 15500.16 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 68 | 1 | C | 141 | 30 | 100
2501-014.1 | FY04 work closeout *TBD* | 15500.16 | 15500.16 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16 | LOE
441-097 | Install Interlock sys | 0 | 15530.4 |  | 15530.4 | 18% | 2795.472 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
730.8200 | PTP and Cooldown | 0 | 15553.6 |  | 15553.6 | 30% | 4666.08 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 91 | 1 |  | 7 | 30
810.004 | Project Management Office PPPL FY06 | 7600.6195 | 15575.04 |  | 7974.4205 | 5% | 398.721 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5 | LOE
S1P1-106 | Attach studs for coolant lines | 0 | 15636.48 |  | 15636.48 | 40% | 6254.592 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 16 |  |  |  | 40
7502-030 | TC Floor firesealing | 0 | 15720 |  | 15720 | 24% | 3772.8 | 7 | 75 | 750 | 9450 | 7502 | F |  |  | 1 |  | 7 | 24
441-110 | PLC CWD's & Cabling | 0 | 15727.48 |  | 15727.48 | 18% | 2830.9464 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
633-001 | Preliminary Design | 0 | 15779.7 |  | 15779.7 | 20% | 3155.94 | 6 | 62 | 623 | 9450 | 6201 | 2 | 623 | 10 | P |  |  | 20
1403-203C | Finish Clamp Dwgs (5)-Type C | 15791.04 | 15791.04 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 00 | 1 |  |  | 30 | 100
631-001 | Preliminary Design | 0 | 15792.79 |  | 15792.79 | 20% | 3158.558 | 6 | 62 | 621 | 9450 | 6201 | 2 | 621 | 10 | P |  |  | 20
1406-119 | Join straight sections w/2 end loops | 15795 | 15795 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-L | 63 | 1 |  |  | 40 | 100
1406-119 | Join straight sections w/2 end loops | 15795 | 15795 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-L | 63 | 1 |  |  | 40 | 100
820.04X | Proj engr FY07 | 0 | 15850.26 |  | 15850.26 | 5% | 792.513 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5
1406-000.2 | Supervision & Oversight | 15864 | 15864 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
441-130 | Pre-commissioning tests | 0 | 15927.67 |  | 15927.67 | 18% | 2866.9806 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
1303-TRIM | Trim Coil Design | 0 | 15941.33 |  | 15941.33 | 32% | 5101.2256 | 1 | 13 | 133 | 9450 | 1354 | 2 | 133 | 01 | 1 |  | 13 | 32
441-120 | Program PLC Logic | 0 | 15949.2 |  | 15949.2 | 18% | 2870.856 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
441-125 | Program Control pages | 0 | 15949.2 |  | 15949.2 | 18% | 2870.856 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
S1P2-106 | Attach studs forcoolant lines | 0 | 15978.24 |  | 15978.24 | 40% | 6391.296 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 16 |  |  |  | 40
S1P3-106 | Attach studs forcoolant lines | 0 | 15978.24 |  | 15978.24 | 40% | 6391.296 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 17 |  |  |  | 40
S4P1-109 | Position, weld two large horizontal diag ports | 0 | 15978.24 |  | 15978.24 | 40% | 6391.296 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
51-01 | FY04 LOE support | 16000 | 16000 |  | 0 | 3% | 0 | 5 | 58 | 580 | 9450 | 5801 | 1 |  |  | 1 |  |  | 3 | LOE
633-010 | Final Design | 0 | 16027.22 |  | 16027.22 | 20% | 3205.444 | 6 | 62 | 623 | 9450 | 6201 | 2 | 623 | 13 | F |  |  | 20
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 16113 |  | 16113 | 20% | 3222.6 | 1 | 13 | 134 | 9450 | 1355 | T | 134 |  | 1 |  |  | 20
7503-020 | Install & Level Support Base Plates | 0 | 16142.4 |  | 16142.4 | 24% | 3874.176 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 16142.4 |  | 16142.4 | 24% | 3874.176 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 05 |  |  |  | 24
7503-200 | Mate-up and weld all VV-to-Spool interfaces | 0 | 16142.4 |  | 16142.4 | 24% | 3874.176 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 06 |  |  |  | 24
22-45 | Eng. Work Planning and Design during fab | 0 | 16193.61 |  | 16193.61 | 14% | 2267.1054 | 2 | 22 | 220 | 9450 | 2201 | 2 |  |  | 1 |  |  | 14
631-010 | Final Design**reduced scope | 0 | 16205.12 |  | 16205.12 | 20% | 3241.024 | 6 | 62 | 621 | 9450 | 6201 | 2 | 621 | 11 | F |  |  | 20
631-015 | Fab/Assy/Installation**reduced scope | 0 | 16205.12 |  | 16205.12 | 20% | 3241.024 | 6 | 62 | 621 | 9450 | 6201 | F | 621 | 14 | 1 |  |  | 20
633-015 | Fab/Assy/Installation | 0 | 16205.12 |  | 16205.12 | 20% | 3241.024 | 6 | 62 | 623 | 9450 | 6201 | F | 623 | 13 | 1 |  |  | 20
444-4-4 | Signal Conditioning & Cabling-Procure | 2431.293 | 16208.62 |  | 13777.327 | 18% | 2479.9189 | 4 | 44 | 444 | 9450 | 4401 | T | 444 |  | 1 |  | 44 | 18 | 15
820.004Z | Proj engr FY08 | 0 | 16275.84 |  | 16275.84 | 5% | 813.792 | 8 | 82 | 820 | 9450 | 8202 | F |  | 21 | 1 |  |  | 5
1351-086 | Fab/Assemble Fixture | 0 | 16288 |  | 16288 | 24% | 3909.12 | 1 | 13 | 131 | 9450 | 1350 | 1 |  | 98 | 1 | C |  | 24
1409-136 | Valve/pump repairs&safety mods to cryo pp sys | 16288 | 16288 |  | 0 | 34% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 6 | 02 | 1 | C | 141 | 34 | 100
1350-600 | Build Cleanroom | 16351.33 | 16351.33 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1403-58C | Check and promote clamp, I&C assy dwgs -Type C | 14734.17 | 16371.3 |  | 1637.13 | 30% | 491.139 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 29 | 1 | C |  | 30 | 90
451-2-1 | CDR Power system -Dsn | 16376 | 16376 |  | 0 | 18% | 0 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 02 | 1 |  | 45 | 18 | 100
1408-138 | Misc. Supplies | 11475.702 | 16393.86 |  | 4918.158 | 30% | 1475.4474 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 25 | 1 |  | 141 | 30 | 70
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 16408.32 |  | 16408.32 | 24% | 3937.9968 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 16408.32 |  | 16408.32 | 24% | 3937.9968 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 16408.32 |  | 16408.32 | 24% | 3937.9968 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
S4P2-109 | Position, weld two large horizontal diag ports | 0 | 16408.32 |  | 16408.32 | 40% | 6563.328 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-109 | Position, weld two large horizontal diag ports | 0 | 16408.32 |  | 16408.32 | 40% | 6563.328 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
1351-553 | Wind Coil #3 | 0 | 16572.8 |  | 16572.8 | 67% | 11103.776 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
PPC-4 | Build Pattern & Pour Casting | 16610 | 16610 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | P | 14E | 15 |  | C |  | 40 | 100
1351-555 | Wind Coil #4 | 0 | 16644 |  | 16644 | 67% | 11151.48 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
1406-54 | Complete shear modulus & cyclic testing | 16683.68 | 16683.68 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
431-210 | Organize & verify documentation | 15850.731 | 16684.98 |  | 834.249 | 18% | 150.1648 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 95
1203-161 | Finalize & Sign All ICDs | 16686.55 | 16686.55 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1403-35 | Perform supporting analysis for material tests | 16727.62 | 16727.62 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-37 | Perform check og global structural analysis | 16727.62 | 16727.62 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1350-600 | Build Cleanroom | 16753.13 | 16753.13 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
1406-029 | Fab New Specimen Molds | 16848 | 16848 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-031 | Prep fixtures and test equipt | 16848 | 16848 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
7502-025 | TC Floor penetration covers | 16848 | 16848 |  | 0 | 24% | 0 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  |  | 24 | 100
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 16896.7 |  | 16896.7 | 24% | 4055.208 | 1 | 13 | 133 | 9450 | 1354 | F | 133 | 16 | 1 |  |  | 24
361-015 | Fab/Assy/Installation Visible Camera | 0 | 17028.48 |  | 17028.48 | 20% | 3405.696 | 3 | 36 | 360 | 9450 | 3601 | F |  |  | 1 |  |  | 20
125-011 | Final design WBS 125 local I&C | 15406.569 | 17118.41 |  | 1711.841 | 30% | 513.5523 | 1 | 12 | 125 | 9450 | 1203 | 2 | 125 | 52 | 1 |  |  | 30 | 90
7503-360 | Install Midplane Cryostat sections and port boot | 0 | 17238 |  | 17238 | 24% | 4137.12 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
121-035.1 | ORNL fesign support during MTM Contract | 17360 | 17360 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
631-015 | Fab/Assy/Installation**reduced scope | 0 | 17519.3 |  | 17519.3 | 20% | 3503.86 | 6 | 62 | 621 | 9450 | 6201 | F | 621 | 14 | 1 |  |  | 20
132-015 | Title III design WBS 162 Coil leads | 0 | 17542 |  | 17542 | 22% | 3859.24 | 1 | 16 | 162 | 9450 | 1601 | F | 162 | 01 | 1 |  |  | 22
22-25 | Eng. Work Planning and Design | 0 | 17730 |  | 17730 | 14% | 2482.2 | 2 | 22 | 220 | 9450 | 2201 | 2 |  |  | 1 |  |  | 14
1407-126.1 | Complete Fab Type A casting supports (6) sets | 17735.76 | 17735.76 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  | 141 | 34 | 100
1407.011.3 | Fab & Install vacuum lines | 17884.8 | 17884.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
1407-200 | Decon TFTR test Cell Crane | 17884.8 | 17884.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-F | 20 | 1 |  |  | 34 | 100
1406-120 | Wind Conductor | 17884.8 | 17884.8 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-L | 64 | 1 |  |  | 40 | 100
1803-3.39 | Fab Test Track | 17884.8 | 17884.8 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
1350-520 | Misc tools & equipt | 12536.916 | 17909.88 |  | 5372.964 | 24% | 1289.5114 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 70
8203FY05 | Design Integration FY05 LOE | 18000 | 18000 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8203 | 2 |  | 50 | 1 |  |  | 10
121-035.2 | ORNL design support during MTM Contract | 18050.9 | 18050.9 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
4501-100 | Design Drawings | 18084 | 18084 |  | 0 | 18% | 0 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 01 | 1 |  | 45 | 18 | 100
1202-303 | MT-Issue VVSA MIT/QA plans and C&S Est (3.1) | 18090.8 | 18090.8 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 0 | 100
161-001 | Revise Preliminary Design for new supt locations | 16307.883 | 18119.87 |  | 1811.987 | 32% | 579.8358 | 1 | 17 | 172 | 9450 | 1701 | 1 | BASE | 14 | 1 |  | 17 | 32 | 90
1202-866 | Engineering Oversght *ECP6* | 18127.46 | 18127.46 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 49 | 1 |  | 12 | 40 | 100
172-031.1 | Title III engr | 6334.2488 | 18149.71 |  | 11815.4612 | 20% | 2363.0922 | 1 | 14 | 141 | 9450 | 1411 | F | 14T | 10 | 1 |  |  | 20 | LOE
174-035 | Modular Coil local I&C -Procurement | 0 | 18275.43 |  | 18275.43 | 24% | 4386.1032 | 1 | 14 | 142 | 9450 | 1408 | T | I&C |  | 1 |  |  | 24
7502-001 | Test Cell 110v outlets | 12805.555 | 18293.65 |  | 5488.095 | 24% | 1317.1428 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  | 7 | 24 | 70
1403-204 | Outer Chill Plate Dwgs -Type C | 18356.25 | 18356.25 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 89 | 1 |  |  | 40 | 100
1803-2.02 | MC Holding Fixture - model design and drawing | 18423 | 18423 |  | 0 | 20% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 11 | 1 |  |  | 20 | 100
1803-4.04 | FP Assembly platform - model design drawing det | 18423 | 18423 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 4.00 | 03 | 1 |  |  | 40 | 100
1403-068 | TRC I&C | 18446.4 | 18446.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C | 141 | 40 | 100
1202-402 | Oversight and Contract Management | 18448.3 | 18448.3 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12B | 40 | 1 |  |  | 40 | 100
714.010 | LOE FY05 | 18483.52 | 18483.52 |  | 0 | 15% | 0 | 7 | 74 | 742 | 9450 | 7401 | F | P1 | 11 | 1 |  |  | 15 | LOE
1403-41 | Prepare structural analysis report | 18531.36 | 18531.36 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
1403-15 | Prepare winding form asm / detail drawings | 18531.36 | 18531.36 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW08 | 10 | 1 |  |  | 40 | 100
451-2-2 | PDR Prep Power system -Dsn | 0 | 18532.8 |  | 18532.8 | 18% | 3335.904 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 12 | P |  | 45 | 18
1301-165 | PF1-PF3 Support System Layouts | 18540 | 18540 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1301R-03 | ReEvaluate Analysis, Dahlgren | 18540 | 18540 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 69 | 1 |  |  | 24 | 100
8204.02 | Model effects local high MU regions on MCWF | 18540 | 18540 |  | 0 | 32% | 0 | 8 | 82 | 820 | 9450 | 8204 | 2 | FY04 | 11 | 1 |  |  | 32 | 100
192-6.10 | MC interf during assly, geometry, assly trajecto | 18540 | 18540 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | 100
120-100 | Magnetic Diag Interface/Install dwgs | 18600 | 18600 |  | 0 | 30% | 0 | 1 | 12 | 124 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 30 | 100
1301FD-20 | Test 1st Sample | 18600 | 18600 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 79 | 1 | C |  | 24 | 100
1301FD-21 | Test 2nd Sample | 18600 | 18600 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 80 | 1 | C |  | 24 | 100
1403-220 | Cladding assembly-Type C | 18600 | 18600 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 22 | 1 |  |  | 40 | 100
54-10 | Preliminary Design (Title I) | 0 | 18624.69 |  | 18624.69 | 14% | 2607.4566 | 5 | 54 | 540 | 9450 | 5401 | 2 |  |  | P |  |  | 14
722.010 | PF Coil receipt inspect/test (formerly wbs 183) | 0 | 18630.28 |  | 18630.28 | 20% | 3726.056 | 1 | 13 | 132 | 9450 | 1352 | F | 13P | 49 | 1 |  |  | 20
22-40 | Drafting | 0 | 18937.6 |  | 18937.6 | 14% | 2651.264 | 2 | 22 | 220 | 9450 | 2201 | 2 |  |  | 1 |  |  | 14
411-2-2 | Grounding-Dsn | 0 | 18937.6 |  | 18937.6 | 18% | 3408.768 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
441-095 | Design Interlock sys | 0 | 18937.6 |  | 18937.6 | 18% | 3408.768 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
445-2-135 | Overload Protect-Documentation | 0 | 18937.6 |  | 18937.6 | 22% | 4166.272 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
452-2-2 | Diagnostics sensor cabling-Dsn | 0 | 18937.6 |  | 18937.6 | 26% | 4923.776 | 4 | 45 | 452 | 9450 | 4501 | 2 | 452 |  | 1 |  | 45 | 26
1407-100.2 | Fabr turning fixt&coil supports **2nd line** | 19110 | 19110 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 28 | 100
1403-42C | Revise analysis incorp final modeling changes | 19110 | 19110 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1302-PFX | Complete PF Preliminary Design | 7658.64 | 19146.6 |  | 11487.96 | 32% | 3676.1472 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 07 | 1 |  | 13 | 32 | 35*
1302-PFX | Complete PF Preliminary Design | 6184.3518 | 19146.6 |  | 12962.2482 | 32% | 4147.9194 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 07 | 1 |  | 13 | 32 | 35*
1302-CSS | PF Final Design | 0 | 19146.6 |  | 19146.6 | 32% | 6126.912 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 10 | 1 |  | 13 | 32
1302-CSS | PF Final Design | 0 | 19146.6 |  | 19146.6 | 32% | 6126.912 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 10 | 1 |  | 13 | 32
1407.002.3 | Winding Facility, Tooling, Materials Oversight | 19169 | 19169 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | A | 62 | 1 |  |  | 34 | 100
1409-150 | Proc Matl's/pump f/closed LN2 | 19182.98 | 19182.98 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 07 | 1 |  | 141 | 34 | 100
713.010 | General procurements | 19215 | 19215 |  | 0 | 24% | 0 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  |  | 24 | LOE
1803-5.04 | Fab - Test Articles | 19215 | 19215 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 6.00 | 00 | 1 |  |  | 40 | 100
411-3-6 | Test Cell AC Power Distr-Install | 9627.45 | 19254.9 |  | 9627.45 | 18% | 1732.941 | 4 | 41 | 411 | 9450 | 4101 | F | 411 |  | 1 |  | 41 | 18 | 50
192-6.01 | Document coil tolerance and trim coil requiremen | 19284.37 | 19284.37 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 02 | 1 |  |  | 10 | 100
714.020 | LOE FY06 prior to assy starting | 0 | 19361.23 |  | 19361.23 | 15% | 2904.1845 | 7 | 74 | 742 | 9450 | 7401 | F | P1 | 11 | 1 |  |  | 15
1403-224C | Finish VPI mold assembly-Type C | 17427.699 | 19364.11 |  | 1936.411 | 30% | 580.9233 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 25 | 1 |  |  | 30 | 90
1803-7.01 | Meetings Prep and Reporting | 19446.5 | 19446.5 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
51-30 | Installation, Testing, Documentation (Title III) | 0 | 19448 |  | 19448 | 5% | 972.4 | 5 | 51 | 510 | 9450 | 5101 | F |  |  | 1 |  |  | 5
640.011 | Design GN2, Air & Vent Systems | 0 | 19448 |  | 19448 | 20% | 3889.6 | 6 | 63 | 630 | 9450 | 6301 | 2 |  |  | 1 |  |  | 20
714.010 | LOE FY05 | 19460.32 | 19460.32 |  | 0 | 15% | 0 | 7 | 74 | 742 | 9450 | 7401 | F | P1 | 11 | 1 |  |  | 15 | LOE
1351-752 | VPI Coil #2 | 0 | 19473.48 |  | 19473.48 | 67% | 13047.2316 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1403-203 | Start Clamp Dwgs (5)-Type C | 19530 | 19530 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
1351-088 | Setup Wedge Casting Fixture & test | 0 | 19545.6 |  | 19545.6 | 24% | 4690.944 | 1 | 13 | 131 | 9450 | 1350 | 1 |  | 99 | 1 | C |  | 24
1406-023 | Hi-pot & Dissect Coil | 19545.6 | 19545.6 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1414 | R | 14-4 | 73 | 1 | C | 141 | 30 | 100
S1P2-103.1 | Layout diagnostic&coolant paths on vessel | 0 | 19545.6 |  | 19545.6 | 40% | 7818.24 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 13 |  |  |  | 40
1408-185 | Valves and Fittings | 19644.55 | 19644.55 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 40 | 1 |  |  | 30 | 100
441-135 | Install I/O Cabling | 0 | 19644.7 |  | 19644.7 | 18% | 3536.046 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
56-30 | Installation, Testing, Documentation (Title III) | 0 | 19670 |  | 19670 | 8% | 1573.6 | 5 | 56 | 560 | 9450 | 5601 | F |  |  | 1 |  |  | 8
1407-110.2 | Compl Fabr Winding clamp sets (100 of 400) | 19796.4 | 19796.4 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 24 | 1 |  |  | 28 | 100
1301FD-01 | TF Detailed Drawings | 19830 | 19830 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 78 | 1 | C |  | 24 | 100
S1P3-103.1 | Layout diagnostic&coolant paths on vessel | 0 | 19972.8 |  | 19972.8 | 40% | 7989.12 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 14 |  |  |  | 40
S4P1-111 | Assemble external trim coils to TF Coil | 0 | 20044.48 |  | 20044.48 | 40% | 8017.792 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
121-032 | VVSA Contract oversight FY04 | 20052.5 | 20052.5 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
1403-15 | Prepare winding form asm / detail drawings | 20075.64 | 20075.64 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW08 | 10 | 1 |  |  | 40 | 100
451-6-2 | FDR C-Site -Cabling | 401.9534 | 20097.67 |  | 19695.7166 | 18% | 3545.229 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 13 | F |  | 45 | 18 | 2
C1RW | C1 rework | 20115.68 | 20115.68 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 00 | 1 | C | 141 | 20 | 100
1407-005 | Domes & cylinder Fab & Deliver (PE4226) | 20167.42 | 20167.42 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 10 | 1 |  |  | 34 | 100
1403-90 | Compile Material properties database | 18166.68 | 20185.2 |  | 2018.52 | 30% | 605.556 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 07 | 1 | C |  | 30 | 90
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 20210.69 |  | 20210.69 | 22% | 4446.3518 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
1406-032 | Test samples | 20217.6 | 20217.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1203-805 | Redo CC heating/coolinbg tube dwgs& analysis | 20244 | 20244 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 123 | 05 | 1 |  |  | 40 | 100
1407-124.5 | Electrical Installations | 20269.44 | 20269.44 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 | C | 141 | 34 | 100
451-2-2.1 | FDR C-Site | 405.9216 | 20296.08 |  | 19890.1584 | 18% | 3580.2285 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 14 | F |  | 45 | 18 | 2
2501-014.1 | FY04 work closeout *TBD* | 20406 | 20406 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16 | LOE
1202-405 | RW-Issue Draft MIT/QA plan (3.2.1) | 20409.48 | 20409.48 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 40 | 1 |  |  | 0 | 100
MCWF-371 | A3-Receive at PPPL | 0 | 20410 |  | 20410 | 10% | 2041 | 1 | 14 | 141 | 9450 | 1411 | P |  | 39 |  |  |  | 10
1408-137 | Safety & PPE equipt & supplies | 15309.4575 | 20412.61 |  | 5103.1525 | 30% | 1530.9458 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 25 | 1 |  | 141 | 30 | 75
3101-145 | Procure MI Cable | 20457.86 | 20457.86 |  | 0 | 30% | 0 | 3 | 31 | 310 | 9450 | 3101 | F | MD1 | 10 |  |  |  | 30 | 100
121-034 | VVSA Title III engr | 20460 | 20460 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 07 | 1 |  |  | 40 | LOE
1408-108 | Insulation-Delivery incl add'l f/trial winding | 20496 | 20496 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | INSL | 15 | 1 |  |  | 30 | 100
1355-100 | CS and PF 1a Pre-Assy incl coil I&C procurement | 0 | 20510.4 |  | 20510.4 | 20% | 4102.08 | 1 | 13 | 134 | 9450 | 1355 | F | 134 |  | 1 |  |  | 20
S4P2-111 | Assemble external trim coils to TF Coil | 0 | 20510.4 |  | 20510.4 | 40% | 8204.16 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-111 | Assemble external trim coils to TF Coil | 0 | 20510.4 |  | 20510.4 | 40% | 8204.16 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
123-037 | Fabricate and Deliver H/C Tubing WBS 123 | 0 | 20565 |  | 20565 | 32% | 6580.8 | 1 | 12 | 123 | 9450 | 1204 | T | 123 | 35 | 1 |  | 12 | 32
1408-117 | Epoxy -1st Delivery for Production | 20565 | 20565 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | EPOX | 10 | 1 |  |  | 30 | 100
1408-119 | Epoxy -2nd Delivery for Production | 0 | 20565 |  | 20565 | 30% | 6169.5 | 1 | 14 | 142 | 9450 | 1408 | T | EPOX | 10 | 1 |  |  | 30
1408-121 | Epoxy -3rd Delivery for Production | 0 | 20565 |  | 20565 | 30% | 6169.5 | 1 | 14 | 142 | 9450 | 1408 | T | EPOX | 10 | 1 |  |  | 30
1408-123 | Epoxy -4th Delivery for Production | 0 | 20565 |  | 20565 | 30% | 6169.5 | 1 | 14 | 142 | 9450 | 1408 | T | EPOX | 10 | 1 |  |  | 30
1408-125 | Epoxy -5th Delivery for Production | 0 | 20565 |  | 20565 | 30% | 6169.5 | 1 | 14 | 142 | 9450 | 1408 | T | EPOX | 10 | 1 |  |  | 30
1408-127 | Epoxy -6th Delivery for Production | 0 | 20565 |  | 20565 | 30% | 6169.5 | 1 | 14 | 142 | 9450 | 1408 | T | EPOX | 10 | 1 |  |  | 30
1408-905 | Fabr Clamps Type C for Coil c1 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-907 | Fabr Clamps Type C for Coil c2 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-909 | Fabr Clamps Type C for Coil c3 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-911 | Fabr Clamps Type C for Coil c4 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-913 | Fabr Clamps Type C for Coil c5 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-915 | Fabr Clamps Type C for Coil c6 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-921 | Fabr Clamps Type A for Coil a1 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-923 | Fabr Clamps Type A for Coil a2 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-925 | Fabr Clamps Type A for Coil a3 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-927 | Fabr Clamps Type A for Coil a4 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-929 | Fabr Clamps Type A for Coil a5 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-931 | Fabr Clamps Type A for Coil a6 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-937 | Fabr Clamps Type B for Coil b1 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-939 | Fabr Clamps Type B for Coil b2 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-941 | Fabr Clamps Type B for Coil b3 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-943 | Fabr Clamps Type B for Coil b4 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-945 | Fabr Clamps Type B for Coil b5 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
1408-947 | Fabr Clamps Type B for Coil b6 | 9871.2 | 20565 |  | 10693.8 | 30% | 3208.14 | 1 | 14 | 142 | 9450 | 1408 | T | CLMP | 25 | 1 | C | 141 | 30 | 48
3101-329 | FAB ROWGOWSKI COILS (2) | 0 | 20565 |  | 20565 | 30% | 6169.5 | 3 | 31 | 310 | 9450 | 3101 | F | MD3 |  |  |  |  | 30
1403-27 | Prepare thermal, electrical analysis report | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-27A | Update winding pack thermal/hydraulic analysis | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-40.3X | Modify MCWF Contract Documents & drawings | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-45 | Check and promote models / drawings | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-45 | Check and promote models / drawings | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-45 | Check and promote models / drawings | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1406-101 | Prepare Clamp & Chill Plate detail Drawings | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1406-101.1 | Winding block dwgs for prototype leads????????? | 20590.4 | 20590.4 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
445-1-2 | Ground Fault Protection-Dsn | 0 | 20612.4 |  | 20612.4 | 22% | 4534.728 | 4 | 44 | 445 | 9450 | 4401 | 2 | 445 |  | 1 |  | 44 | 22
445-2-115 | Overload Protect-Fabr 4 chassis 120 modls | 0 | 20612.4 |  | 20612.4 | 22% | 4534.728 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
1403-17 | Assembly shims | 12375.738 | 20626.23 |  | 8250.492 | 40% | 3300.1968 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 | C |  | 40 | 60
810.002 | Project Management Office PPPL FY04 | 20638.8 | 20638.8 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
1202-400 | Oversight and Contract Management | 20748 | 20748 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12B | 40 | 1 |  |  | 40 | 100
1202-401 | Oversight and Contract Management | 20748 | 20748 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12B | 40 | 1 |  |  | 40 | 100
1404-206 | JPP- July forecast ECP 11 | 20750 | 20750 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14J | 09 | 1 |  |  | 40 | 100
1406-01602 | Oversight & Supervision | 20781.84 | 20781.84 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 62 | 1 | C | 141 | 30 | 100
712.020 | Platform Parts | 0 | 20805 |  | 20805 | 10% | 2080.5 | 7 | 73 | 730 | 9450 | 7301 | F |  |  | 1 |  |  | 10
3101-139 | Develop ProE model of loops, flat dev, fiducials | 19808.678 | 20851.24 |  | 1042.562 | 30% | 312.7686 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD1 | 12 |  |  |  | 30 | 95
445-2-125 | Overload Protect-Install & Rack wiring | 0 | 20945.04 |  | 20945.04 | 22% | 4607.9088 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
7502-020 | Resurface TC floor | 0 | 20960 |  | 20960 | 24% | 5030.4 | 7 | 75 | 750 | 9450 | 7502 | F |  |  | 1 |  | 7 | 24
1407-124 | Fab casting to ring assy fixture station 1 | 21004 | 21004 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 | C | 141 | 34 | 100
1406-01609 | Rework Lead Blocks | 21004 | 21004 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 02 | 1 | C | 141 | 30 | 100
0192-99 | LOE-FY09 | 0 | 21040 |  | 21040 | 10% | 2104 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  | STRO | 10 | LOE
1407.002.2 | Winding Facility, Tooling, Materials Oversight | 21060 | 21060 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | A | 61 | 1 |  |  | 34 | 100
55-30 | Installation, Testing, Documentation (Title III) | 0 | 21075 |  | 21075 | 8% | 1686 | 5 | 55 | 550 | 9450 | 5501 | F |  |  | 1 |  |  | 8
22-65 | Fab PLC conrols | 0 | 21265.6 |  | 21265.6 | 14% | 2977.184 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
54-20 | Final Design (Title II) | 0 | 21285.36 |  | 21285.36 | 14% | 2979.9504 | 5 | 54 | 540 | 9450 | 5401 | 2 |  |  | F |  |  | 14
56-10 | Preliminary Design (Title I) | 0 | 21285.36 |  | 21285.36 | 8% | 1702.8288 | 5 | 56 | 560 | 9450 | 5601 | 2 |  |  | P |  |  | 8
56-20 | Final Design (Title II) | 0 | 21285.36 |  | 21285.36 | 8% | 1702.8288 | 5 | 56 | 560 | 9450 | 5601 | 2 |  |  | F |  |  | 8
441-135 | Install I/O Cabling | 0 | 21380.92 |  | 21380.92 | 18% | 3848.5656 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
431-210 | Organize & verify documentation | 20401.2405 | 21474.99 |  | 1073.7495 | 18% | 193.2749 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18 | 95
1406-016.0 | Oversight & Supervision | 21529.1 | 21529.1 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 00 | 1 | C | 141 | 40 | 100
740.020 | Facility Prep | 3295.2528 | 21537.6 |  | 18242.3472 | 24% | 4378.1633 | 1 | 18 | 187 | 9450 | 1810 | F | S0P0 | 20 | 1 |  |  | 24 | LOE
122-031 | Title III engr WBS 12 non vvsa | 1378.7603 | 21543.13 |  | 20164.3697 | 32% | 6452.5983 | 1 | 12 | 122 | 9450 | 1204 | F |  | 99 | 1 |  |  | 32
PPC-1 | Engr & Flow Solidification | 21570 | 21570 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | P | 14E | 15 |  | C |  | 40 | 100
1409-135 | Production Cryostat Fabr & Install | 17265.28 | 21581.6 |  | 4316.32 | 34% | 1467.5488 | 1 | 14 | 142 | 9450 | 1414 | R | 6 | 02 | 1 | C | 141 | 34 | 80
1203-181 | Start Thermal Analyses | 21630 | 21630 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
MCWF-491 | B3-Receive at PPPL | 0 | 21780 |  | 21780 | 10% | 2178 | 1 | 14 | 141 | 9450 | 1411 | P |  | 45 |  |  |  | 10
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 21849.6 |  | 21849.6 | 34% | 7428.864 | 3 | 38 | 380 | 9450 | 3801 | 2 |  |  | 1 |  |  | 34
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 21918 |  | 21918 | 24% | 5260.32 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 21936 |  | 21936 | 18% | 3948.48 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18
1351-551 | Wind Coil #2 | 0 | 21988.8 |  | 21988.8 | 67% | 14732.496 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
VVSA-491 | Receive at PPPL | 0 | 22000 |  | 22000 | 10% | 2200 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 17 |  |  |  | 10
VVSA-591 | Receive at PPPL | 0 | 22000 |  | 22000 | 10% | 2200 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 18 |  |  |  | 10
1203-239 | Perform Analysis of VV Supports | 22071.98 | 22071.98 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
52-10 | Preliminary Design (Title I) | 0 | 22288.16 |  | 22288.16 | 10% | 2228.816 | 5 | 52 | 520 | 9450 | 5201 | 2 |  |  | P |  |  | 10
1406-000.1 | Supervision & Oversight | 22302 | 22302 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
174-037 | Modular Coil local I&C -Install (from wbs 143) | 2322.9617 | 22336.17 |  | 20013.2083 | 24% | 4803.17 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 98 | 1 |  |  | 24 | LOE
1407-202 | Setup facility stations | 22356 | 22356 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-F | 20 | 1 |  |  | 34 | 100
1407-204.2 | Build cleanroom (1 add'l) **2nd line** | 22356 | 22356 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-F | 20 | 1 |  |  | 28 | 100
1408-186 | Manifolds | 22356 | 22356 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 40 | 1 |  |  | 30 | 100
714.020X | TC power instl | 22445.71 | 22445.71 |  | 0 | 15% | 0 | 7 | 74 | 742 | 9450 | 7401 | F | TCMS | 11 | 1 |  |  | 15
712.010 | Final Design | 22458.8 | 22458.8 |  | 0 | 6% | 0 | 7 | 73 | 730 | 9450 | 7301 | 2 |  | 26 | F |  |  | 6 | 100
1403-19A | Bladder Details | 4498.596 | 22492.98 |  | 17994.384 | 40% | 7197.7536 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 | C |  | 40 | 20
7503-320 | Complete Elect Pwr connections | 0 | 22545.76 |  | 22545.76 | 24% | 5410.9824 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
7503-321 | Complete mag diag & machine I&C | 0 | 22545.76 |  | 22545.76 | 24% | 5410.9824 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
VVSA-391 | Receive at PPPL | 0 | 22560 |  | 22560 | 10% | 2256 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 18 |  |  |  | 10
380-015 | Fab & Install Beam probe | 0 | 22868.4 |  | 22868.4 | 34% | 7775.256 | 3 | 38 | 380 | 9450 | 3801 | F |  |  | 1 |  |  | 34
VVSA-381 | Inspect & Pack for Shipping LI#4 | 0 | 23000 |  | 23000 | 10% | 2300 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 17 |  |  |  | 10
VVSA-481 | Inspect & pack for Shipping LI#4 | 0 | 23000 |  | 23000 | 10% | 2300 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 16 |  |  |  | 10
VVSA-581 | 5Inspect & Pack for Shipping LI#4 | 0 | 23000 |  | 23000 | 10% | 2300 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 17 |  |  |  | 10
FY05CV-16 | FY05 unrecoverable cost variance | 23000 | 23000 |  | 0 | 0% | 0 | 1 | 14 | 144 | 9450 | 1407 | [7 empty] | 100
FY06CV-01 | FY06 YTD cost vari (offset by scope reductions) | 23047.52 | 23047.52 |  | 0 | 0% | 0 | 3 | 31 | 310 | 9450 | 3101
P2-081V | VPI (Station 5) B3 | 0 | 23218.38 |  | 23218.38 | 30% | 6965.514 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 12 | 1 |  | 141 | 30
P3-081V | VPI (Station 5) B4 | 0 | 23218.38 |  | 23218.38 | 30% | 6965.514 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 13 | 1 |  | 141 | 30
P2-171V | VPI (Station 5) B5 | 0 | 23218.38 |  | 23218.38 | 30% | 6965.514 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 14 | 1 |  | 141 | 30
P3-171V | VPI (Station 5) B6 | 0 | 23218.38 |  | 23218.38 | 30% | 6965.514 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 15 | 1 |  | 141 | 30
1409-029 | Oversight/Supervision | 23260.9 | 23260.9 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 14 | 1 |  | 141 | 34 | 100
S3P1-108 | Install shims ( as reqd); ream 24 holes | 0 | 23301.6 |  | 23301.6 | 40% | 9320.64 | 1 | 18 | 185 | 9450 | 1810 | F | S3P1 |  |  |  |  | 40
S3P2-108 | Install shims ( as reqd); ream 24 holes | 0 | 23301.6 |  | 23301.6 | 40% | 9320.64 | 1 | 18 | 185 | 9450 | 1810 | F | S3P2 |  |  |  |  | 40
1803-1.12 | PPPL FAB - VV support Fixture (1st) | 23307 | 23307 |  | 0 | 100% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 1.00 | 75 | 1 |  |  | 100 | 100
1403-15 | Prepare winding form asm / detail drawings | 23421.58 | 23421.58 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW08 | 10 | 1 |  |  | 40 | 100
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 0 | 23685.78 |  | 23685.78 | 28% | 6632.0184 | 1 | 16 | 161 | 9450 | 1601 | F | 161 |  | 1 |  |  | 28
1202-430 | RW-Final MIT/QA plans for VVSA (3.3.1) | 23709.14 | 23709.14 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 52 | 1 |  |  | 40 | 100
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 23779.61 |  | 23779.61 | 22% | 5231.5142 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
444-4-6 | Signal Conditioning & Cabling-Install | 0 | 23807.41 |  | 23807.41 | 18% | 4285.3338 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
P1-171V | VPI (Station 5) A6 | 0 | 23843.34 |  | 23843.34 | 30% | 7153.002 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 17 | 1 |  | 141 | 30
P2-051V | VPI (Station 5) C6 | 0 | 23843.34 |  | 23843.34 | 30% | 7153.002 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 18 | 1 |  | 141 | 30
1406-017.J | Instl diag loops & chill plates | 23846.4 | 23846.4 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 02 | 1 | C | 141 | 30 | 100
S3P3-108 | Install shims ( as reqd); ream 24 holes | 0 | 23928.8 |  | 23928.8 | 40% | 9571.52 | 1 | 18 | 185 | 9450 | 1810 | F | S3P3 |  |  |  |  | 40
1501-001 | Prelim Design Structures | 23961.25 | 23961.25 |  | 0 | 32% | 0 | 1 | 15 | 151 | 9450 | 1501 | 1 |  | 10 |  |  |  | 32 | 100
1350-520 | Misc tools & equipt | 16862.552 | 24089.36 |  | 7226.808 | 24% | 1734.4339 | 1 | 13 | 131 | 9450 | 1350 | F |  | 05 |  |  |  | 24 | 70
1406-016.9 | fab trc clamps | 24206 | 24206 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-4 | 63 | 1 |  | 141 | 40 | 100
171-000 | Winding Preparations (LOE) FY05 | 24291.75 | 24291.75 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | LABR | 11 | 1 |  |  | 30
1406-01608 | Coil Clamps | 24339 | 24339 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 63 | 1 | C | 141 | 30 | 100
1803-7.01 | Meetings Prep and Reporting | 24359.3 | 24359.3 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
1406-019 | VPI TRC in autoclave | 24442.56 | 24442.56 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 69 | 1 | C | 141 | 30 | 100
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 24612.48 |  | 24612.48 | 20% | 4922.496 | 6 | 61 | 613 | 9450 | 6101 | F | 613 |  | 1 |  |  | 20
172-031.1 | Title III engr | 8597.4894 | 24634.64 |  | 16037.1506 | 20% | 3207.4301 | 1 | 14 | 141 | 9450 | 1411 | F | 14T | 10 | 1 |  |  | 20 | LOE
445-1-4 | Ground Fault Protection-Procure | 0 | 24678 |  | 24678 | 22% | 5429.16 | 4 | 44 | 445 | 9450 | 4401 | T | 445 |  | 1 |  | 44 | 22
1403-42 | Complete FDR Struct Analysis Report | 24720 | 24720 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1408-173 | Epoxy for Shell Mold (Hysol) | 14862.966 | 24771.61 |  | 9908.644 | 30% | 2972.5932 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 40 | 1 |  |  | 30 | 60
1403-065 | Cooling redesign and analysis | 24800 | 24800 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 | C | 141 | 40 | 100
1803-7.04 | Mike Cole's FY05 on-site involvement in assembly | 24800 | 24800 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
22-35 | Electrical Drafting for pumping system | 0 | 24855.6 |  | 24855.6 | 14% | 3479.784 | 2 | 22 | 220 | 9450 | 2201 | 2 |  |  | 1 |  |  | 14
810.002 | Project Management Office PPPL FY04 | 24866.4 | 24866.4 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
192-6.06 | Coil positions to minimize islands. | 24900.66 | 24900.66 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 02 | 1 |  |  | 10 | 100
1408-707 | Fabr Lead HW Type C for Coil c2 | 24911.7 | 24911.7 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 21 | 1 | C | 141 | 30 | 100
451-2-1 | CDR Power system -Dsn | 24923.2 | 24923.2 |  | 0 | 18% | 0 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 02 | 1 |  | 45 | 18 | 100
640.021 | Assembly/Fabrication | 0 | 25009 |  | 25009 | 20% | 5001.8 | 6 | 63 | 630 | 9450 | 6301 | F |  |  | 1 |  |  | 20
1403-220 | Cladding assembly-Type C | 25110 | 25110 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 22 | 1 |  |  | 40 | 100
445-2-125 | Overload Protect-Install & Rack wiring | 0 | 25250.69 |  | 25250.69 | 22% | 5555.1518 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
MCWF-191 | A2-Receive at PPPL | 0 | 25270 |  | 25270 | 10% | 2527 | 1 | 14 | 141 | 9450 | 1411 | P |  | 38 |  |  |  | 10
1406-031 | Prep fixtures and test equipt | 25272 | 25272 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
7502-000 | Outlet Design | 25272 | 25272 |  | 0 | 24% | 0 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  | 7 | 24 | 100
1351-751 | VPI Coil #1 | 0 | 25409.28 |  | 25409.28 | 67% | 17024.2176 | 1 | 13 | 131 | 9450 | 1361 | F | 13K |  |  |  |  | 67
1407-130 | Misc tools & equipt FY04 | 25480 | 25480 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 15 | 1 |  | 141 | 34 | 100
1407-130.1 | Misc tools & equipt FY05 | 25620 | 25620 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  | 141 | 34 | 100
1408-112.1 | Grndwrap-Delivery | 25620 | 25620 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | GRWP | 15 | 1 |  |  | 40 | 100
172-031 | Title III engr | 25654.9 | 25654.9 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1411 | F | 14T | 10 | 1 |  |  | 40 | LOE
1406-031 | Prep fixtures and test equipt | 25667.2 | 25667.2 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
2001-100 | PDR Support | 25667.2 | 25667.2 |  | 0 | 0% | 0 | 2 | 22 | 220 | 9450 | 2001 | 1 | 0000 |  | 1 |  |  | 0 | LOE
1403-204 | Outer Chill Plate Dwgs -Type C | 25698.74 | 25698.74 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 89 | 1 |  |  | 40 | 100
1203-400 | 350c Bakeout Study | 25738 | 25738 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | PDRR | 05 | 1 |  |  | 40 | 100
192-5 | LOE-FY05 WBS 192-5 VV & Coil Services Integr | 25738 | 25738 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
162-031 | Title III engr WBS 151 | 0 | 25805.27 |  | 25805.27 | 32% | 8257.6864 | 1 | 15 | 151 | 9450 | 1550 | F |  | 16 | 1 |  |  | 32
181.201 | D-Site Shift Supervisor LOE FY04 | 25920.4 | 25920.4 |  | 0 | 24% | 0 | 1 | 18 | 181 | 9450 | 1802 | F | A | 10 | 1 |  |  | 24 | LOE
1409-025 | Complete Design | 25958.4 | 25958.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
740.010 | Final Design Measurement systems | 26000 | 26000 |  | 0 | 24% | 0 | 1 | 18 | 187 | 9450 | 1804 | 2 | MEAS | 00 | 1 |  | 18 | 24 | LOE
131-033 | Winding operations field oversight | 0 | 26010.85 |  | 26010.85 | 67% | 17427.2695 | 1 | 13 | 131 | 9450 | 1361 | F | 130 | 16 | 1 | C |  | 67
1302-PFX | Complete PF Preliminary Design | 8433.207 | 26109 |  | 17675.793 | 32% | 5656.2538 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 07 | 1 |  | 13 | 32 | 35*
1302-CSS | PF Final Design | 0 | 26109 |  | 26109 | 32% | 8354.88 | 1 | 13 | 132 | 9450 | 1302 | 2 |  | 10 | 1 |  | 13 | 32
1203-261 | Startup Plan | 26136.92 | 26136.92 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1408-709 | Fabr Lead HW Type C for Coil c3 | 26186.1 | 26186.1 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 22 | 1 | C | 141 | 30 | 100
1408-711 | Fabr Lead HW Type C for Coil c4 | 26186.1 | 26186.1 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 22 | 1 | C | 141 | 30 | 100
1408-713 | Fabr Lead HW Type C for Coil c5 | 26186.1 | 26186.1 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 22 | 1 | C | 141 | 30 | 100
1408-715 | Fabr Lead HW Type C for Coil c6 | 26186.1 | 26186.1 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 22 | 1 | C | 141 | 30 | 100
1408-721 | Fabr Lead HW Type A for Coil a1 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-723 | Fabr Lead HW Type A for Coil a2 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-725 | Fabr Lead HW Type A for Coil a3 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-727 | Fabr Lead HW Type A for Coil a4 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-729 | Fabr Lead HW Type A for Coil a5 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-731 | Fabr Lead HW Type A for Coil a6 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-737 | Fabr Lead HW Type B for Coil b1 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-739 | Fabr Lead HW Type B for Coil b2 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-741 | Fabr Lead HW Type B for Coil b3 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-743 | Fabr Lead HW Type B for Coil b4 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-745 | Fabr Lead HW Type B for Coil b5 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
1408-747 | Fabr Lead HW Type B for Coil b6 | 5630.0115 | 26186.1 |  | 20556.0885 | 30% | 6166.8265 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 25 | 1 | C | 141 | 30 | 22
163-001 | Title I design CS sprt struc | 26265 | 26265 |  | 0 | 32% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | 0000 | 07 | 1 |  |  | 32 | 100
53-10 | Preliminary Design (Title I) | 0 | 26312.41 |  | 26312.41 | 16% | 4209.9856 | 5 | 53 | 530 | 9450 | 5301 | 2 |  |  | P |  |  | 16
1407-110 | Fabricate Winding clamp sets (125) | 26325 | 26325 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
1406-01602 | Oversight & Supervision | 26414.63 | 26414.63 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 62 | 1 | C | 141 | 30 | 100
184-100 | Assemble 3 TF coils&structure -Left-Period #1 | 0 | 26630.4 |  | 26630.4 | 40% | 10652.16 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-105 | Assemble 3 TF coils&structure -Right -Period #1 | 0 | 26630.4 |  | 26630.4 | 40% | 10652.16 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-110 | Assemble 3 TF coils&structure -Left-Period #2 | 0 | 26630.4 |  | 26630.4 | 40% | 10652.16 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-115 | Assemble 3 TF coils&structure -Right -Period #2 | 0 | 26630.4 |  | 26630.4 | 40% | 10652.16 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
184-120 | Assemble 3 TF coils&structure -Left -Period #3 | 0 | 26630.4 |  | 26630.4 | 40% | 10652.16 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
54-30 | Installation, Testing, Documentation (Title III) | 0 | 26695 |  | 26695 | 14% | 3737.3 | 5 | 54 | 540 | 9450 | 5401 | F |  |  | 1 |  |  | 14
P1-021V | VPI (Station 5) C1 | 26712.32 | 26712.32 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 01 | 1 | C | 141 | 30 | 100
P1-111V | VPI (Station 5) C2 | 0 | 26712.32 |  | 26712.32 | 30% | 8013.696 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 02 | 1 |  | 141 | 30
P2-111V | VPI (Station 5) C3 | 0 | 26712.32 |  | 26712.32 | 30% | 8013.696 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 03 | 1 |  | 141 | 30
P3-111V | VPI (Station 5) C4 | 0 | 26712.32 |  | 26712.32 | 30% | 8013.696 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 04 | 1 |  | 141 | 30
P1-141V | VPI (Station 5) C5 | 0 | 26712.32 |  | 26712.32 | 30% | 8013.696 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 05 | 1 |  | 141 | 30
810.103 | Project Management Office ORNL FY05 | 26755.18 | 26755.18 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8102 | P |  |  | 1 |  |  | 10 | LOE
1409-000 | FY04 Oct-Mar | 26790.14 | 26790.14 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1350-500 | Recondition turnkng fixture | 26827.2 | 26827.2 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
451-2-2 | PDR Prep Power system -Dsn | 0 | 26894.4 |  | 26894.4 | 18% | 4840.992 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 12 | P |  | 45 | 18
141TITLE2P | PDR #1,4,26 Access,Tolerance Budget,Bolting | 26896.21 | 26896.21 |  | 0 | 30% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 | 01 | 1 |  |  | 30 | 100
810.003 | Project Management Office PPPL FY05 | 26900 | 26900 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
1301-FY04 | FY04 cost variance | 27000 | 27000 |  | 0 | 0% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | 0000 | 54 | 1 |  |  | 0 | 100
PPC-6 | Oversight/Reporting | 27040 | 27040 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | P | 14E | 15 |  | C |  | 40 | 100
151-031 | Title III engr | 0 | 27070.2 |  | 27070.2 | 28% | 7579.656 | 1 | 17 | 171 | 9450 | 1751 | F | 171 | 19 | 1 |  |  | 28
1407-204 | Build cleanrooms (2) locations | 27072.5 | 27072.5 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-F | 20 | 1 |  |  | 34 | 100
1301FD-05 | Anaylsis Check | 25767.135 | 27123.3 |  | 1356.165 | 24% | 325.4796 | 1 | 13 | 130 | 9450 | 1301 | 1 | FNLC | 01 | 1 | C |  | 24 | 95
1409-100 | Design Controls Modifications | 27126 | 27126 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1403-18 | Eccentric ball assembly | 16280.682 | 27134.47 |  | 10853.788 | 40% | 4341.5152 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 | C |  | 40 | 60
390-015 | LOE Support FY05 **reduced scope | 27141.18 | 27141.18 |  | 0 | 30% | 0 | 3 | 39 | 390 | 9450 | 3901 | 2 |  |  | 1 |  |  | 30 | LOE
P2-021V | VPI (Station 5) A1 | 0 | 27296.16 |  | 27296.16 | 30% | 8188.848 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 06 | 1 |  | 141 | 30
P3-021V | VPI (Station 5) A2 | 0 | 27296.16 |  | 27296.16 | 30% | 8188.848 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 07 | 1 |  | 141 | 30
P3-051V | VPI (Station 5) A3 | 0 | 27296.16 |  | 27296.16 | 30% | 8188.848 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 08 | 1 |  | 141 | 30
P1-051V | VPI (Station 5) B1 | 0 | 27296.16 |  | 27296.16 | 30% | 8188.848 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 09 | 1 |  | 141 | 30
P3-141V | VPI (Station 5) A4 | 0 | 27296.16 |  | 27296.16 | 30% | 8188.848 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 10 | 1 |  | 141 | 30
P2-141V | VPI (Station 5) B2 | 0 | 27296.16 |  | 27296.16 | 30% | 8188.848 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 11 | 1 |  | 141 | 30
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 27347.2 |  | 27347.2 | 24% | 6563.328 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-090 | Install local Platforms around FPA-1 | 0 | 27347.2 |  | 27347.2 | 24% | 6563.328 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-130 | Install local Platforms around FPA-2 | 0 | 27347.2 |  | 27347.2 | 24% | 6563.328 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-190 | Install local Platforms around FPA-3 | 0 | 27347.2 |  | 27347.2 | 24% | 6563.328 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 04 |  |  |  | 24
7503-240.1 | Install insulation boots | 0 | 27347.2 |  | 27347.2 | 24% | 6563.328 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 16 |  |  |  | 24
184-125 | Assemble 3 TF coils&structure -Right -Period #3 | 0 | 27347.2 |  | 27347.2 | 40% | 10938.88 | 1 | 18 | 185 | 9450 | 1810 | F | S5P1 | 20 | 1 |  | 18 | 40
3101-517 | Fab termination boxes (24) | 0 | 27363.84 |  | 27363.84 | 30% | 8209.152 | 3 | 31 | 310 | 9450 | 3101 | 1 | MD6 | 20 |  |  |  | 30
1403-44 | Prepare final drawings for winding forms, asm | 27410.97 | 27410.97 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-44 | Prepare final drawings for winding forms, asm | 27410.97 | 27410.97 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1403-44 | Prepare final drawings for winding forms, asm | 27410.97 | 27410.97 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
1351-086 | Fab/Assemble Fixture | 0 | 27420 |  | 27420 | 24% | 6580.8 | 1 | 13 | 131 | 9450 | 1350 | 1 |  | 98 | 1 | C |  | 24
1403-20 | 3 coil assembly specification | 0 | 27491.2 |  | 27491.2 | 40% | 10996.48 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 | C |  | 40
P1-081V | VPI (Station 5) A5 | 0 | 27506.08 |  | 27506.08 | 30% | 8251.824 | 1 | 14 | 142 | 9450 | 1451 | F | 5 | 16 | 1 |  | 141 | 30
1803-5.002 | TF Rotation Fixture plus dwgs start | 27634.5 | 27634.5 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 5.00 | 05 | 1 |  |  | 40 | 100
1351-547 | Conductor Preparation | 0 | 27677.12 |  | 27677.12 | 67% | 18543.6704 | 1 | 13 | 131 | 9450 | 1361 | F | 13G |  |  |  |  | 67
1202-401 | Oversight and Contract Management | 27752.66 | 27752.66 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12B | 40 | 1 |  |  | 40 | 100
444-3-6 | DC Shunts-Install | 0 | 27753.33 |  | 27753.33 | 18% | 4995.5994 | 4 | 44 | 444 | 9450 | 4401 | F | 444 |  | 1 |  | 44 | 18
121-031 | VVSA Title III engr | 27753.79 | 27753.79 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 06 | 1 |  |  | 40 | LOE
380-015 | Fab & Install Beam probe | 0 | 27801.6 |  | 27801.6 | 34% | 9452.544 | 3 | 38 | 380 | 9450 | 3801 | F |  |  | 1 |  |  | 34
711A.040 | Platform nut plates | 25030.746 | 27811.94 |  | 2781.194 | 6% | 166.8716 | 7 | 73 | 730 | 9450 | 7301 | F |  | 27 | 1 |  |  | 6 | 90
1803-3.07 | Structural analysis Analysis | 0 | 27849.6 |  | 27849.6 | 40% | 11139.84 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 79 | 1 |  |  | 40
1403-42F | Perform WP beam tests at ORNL | 27900 | 27900 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 10 | 1 | C |  | 40 | 100
1203-405 | Field Weld joint design and Specific spool piece | 28000 | 28000 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12Z | 05 | 1 |  | 12 | 40 | 100
7503-310 | Complete LN2 connections | 0 | 28089.6 |  | 28089.6 | 24% | 6741.504 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
453-1-2 | New Procedures | 0 | 28406.4 |  | 28406.4 | 18% | 5113.152 | 4 | 45 | 453 | 9450 | 4501 | 2 | 453 |  | 1 |  | 45 | 18
191-011 | Title II design WBS 161 LN2 manifolds&piping | 0 | 28457.6 |  | 28457.6 | 28% | 7968.128 | 1 | 16 | 161 | 9450 | 1601 | 2 | 161 |  | 1 |  | 16 | 28
810.003 | Project Management Office PPPL FY05 | 28588.25 | 28588.25 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
7503-321 | Complete mag diag & machine I&C | 0 | 28646.4 |  | 28646.4 | 24% | 6875.136 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 28802.5 |  | 28802.5 | 20% | 5760.5 | 6 | 61 | 613 | 9450 | 6101 | F | 613 |  | 1 |  |  | 20
1406-01602 | Oversight & Supervision | 29031.12 | 29031.12 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 62 | 1 | C | 141 | 30 | 100
171-000 | Winding Preparations (LOE) FY05 | 29090.54 | 29090.54 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | LABR | 11 | 1 |  |  | 30
380-015 | Fab & Install Beam probe | 0 | 29132.8 |  | 29132.8 | 34% | 9905.152 | 3 | 38 | 380 | 9450 | 3801 | F |  |  | 1 |  |  | 34
7503-340 | Install Cryostat Base, vapor barrie& port boots | 0 | 29203.2 |  | 29203.2 | 24% | 7008.768 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
7503-350 | Install Cryostat upper section,VB and port boots | 0 | 29203.2 |  | 29203.2 | 24% | 7008.768 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
390-020 | LOE Support FY06 | 14361.6207 | 29309.43 |  | 14947.8093 | 30% | 4484.3428 | 3 | 39 | 390 | 9450 | 3901 | 2 |  |  | 1 |  |  | 30 | LOE
1351-549 | Wind Coil #1 | 0 | 29318.4 |  | 29318.4 | 67% | 19643.328 | 1 | 13 | 131 | 9450 | 1361 | F | 13H |  |  |  |  | 67
161-011 | Final Design Base Support Structure WBS 172 | 0 | 29590.2 |  | 29590.2 | 32% | 9468.864 | 1 | 17 | 172 | 9450 | 1701 | 2 | BASE | 16 | 1 |  | 17 | 32
1408-001 | Apr-Sep YTD MIE Cost PPPL | 29790 | 29790 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1408 | R | 0000 | 54 | 1 |  |  | 0 | 100
0192-5 | LOE-FY05 WBS 192 | 29850 | 29850 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 07 | 1 |  |  | 10 | LOE
MCWF-131 | A1-Receive at PPPL | 0 | 29880 |  | 29880 | 10% | 2988 | 1 | 14 | 141 | 9450 | 1411 | P |  | 36 |  |  |  | 10
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 29950 | 29950 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
TITLE2TRC | Titel III Design-TRC FAB | 29970 | 29970 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | F | TRTD | 20 | 1 |  |  | 40 | 100
PPC-5C | contract resolution setaside | 30000 | 30000 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | P | 14E | 15 |  | C |  | 40 | 100
FY05CV-32 | FY05 unrecoverable cost variance | 30000 | 30000 |  | 0 | 0% | 0 | 3 | 31 | 310 | 9450 | 3101
1901-ECP16 | ecp16 | 30000 | 30000 |  | 0 | 10% | 0 | 1 | 19 | 191 | 9450 | 1901 | 2 | 0000 | 01 | 1 |  |  | 10 | LOE
1406-101 | Prepare Clamp & Chill Plate detail Drawings | 30113.46 | 30113.46 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1408-184 | Vulcanizing tape, felt and RTV | 25034.46 | 30162 |  | 5127.54 | 30% | 1538.262 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 40 | 1 |  |  | 30 | 83
1407-011 | Fabricate Autoclave | 30326.4 | 30326.4 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
0192-6 | LOE-FY06 WBS 192 | 14875.1505 | 30357.45 |  | 15482.2995 | 10% | 1548.23 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
1406-030 | Fab & Pot samples | 30404.16 | 30404.16 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
820.04X | Proj engr FY07 | 0 | 30672.9 |  | 30672.9 | 5% | 1533.645 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5
712.010 | Final Design | 30705 | 30705 |  | 0 | 6% | 0 | 7 | 73 | 730 | 9450 | 7301 | 2 |  | 26 | F |  |  | 6 | 100
1406-032 | Test samples | 30800.64 | 30800.64 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 10 | 1 |  |  | 40 | 100
1406-111 | Write papers and present at conferences | 30885.6 | 30885.6 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | R | TRTD | 10 | 1 |  |  | 40 | 100
1403-19 | Top assembly dwgs for mod coil shell | 18563.604 | 30939.34 |  | 12375.736 | 40% | 4950.2944 | 1 | 14 | 142 | 9450 | 1421 | 2 | DW08 |  | 1 | C |  | 40 | 60
0192-6X | LOE-FY07 WBS 192 | 0 | 30968.3 |  | 30968.3 | 10% | 3096.83 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
MCWF-221 | C4-Receive at PPPL | 31190 | 31190 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 34 |  |  |  | 10
810.003 | Project Management Office PPPL FY05 | 31239.96 | 31239.96 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
1803-3.15C | Fab Crane Support & Laser screens | 0 | 31258.8 |  | 31258.8 | 40% | 12503.52 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 86 | 1 |  |  | 40
1408-146 | Add'l Copper Conductor f/trial winding PE005371 | 31382.87 | 31382.87 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | COPP | 99 | 1 |  | 141 | 0 | 100
820.004Z | Proj engr FY08 | 0 | 31499.84 |  | 31499.84 | 5% | 1574.992 | 8 | 82 | 820 | 9450 | 8202 | F |  | 21 | 1 |  |  | 5
0192-7 | LOE-FY08 WBS 192 | 0 | 31507.4 |  | 31507.4 | 10% | 3150.74 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
1407-100 | Fabricate turning fixtures and coil supports | 31590 | 31590 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
1803-2.11 | Fab MC HP Assy Fixtures (1) | 0 | 31889.46 |  | 31889.46 | 100% | 31889.46 | 1 | 18 | 186 | 9450 | 1803 | F | 2.00 | 50 | 1 |  |  | 100
431-275 | Power cabling & Installation | 0 | 31898.4 |  | 31898.4 | 18% | 5741.712 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
453-1-8 | Testing PTPs, ISTPs | 0 | 31898.4 |  | 31898.4 | 18% | 5741.712 | 4 | 45 | 453 | 9450 | 4501 | S | 453 |  | 1 |  | 45 | 18
740.020 | Facility Prep | 4884.4454 | 31924.48 |  | 27040.0346 | 24% | 6489.6083 | 1 | 18 | 187 | 9450 | 1810 | F | S0P0 | 20 | 1 |  |  | 24 | LOE
S1SP-101 | Attachdiagnostics, studs and coolant lines | 0 | 31956.48 |  | 31956.48 | 40% | 12782.592 | 1 | 18 | 185 | 9450 | 1810 | F | S1SP |  |  |  |  | 40
SSD-ST2 | Second shift cost differential | 7072 | 32000 |  | 24928 | 24% | 5982.72 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 99 | 1 |  |  | 24 | LOE
SSD-ST3 | Second shift cost differential | 3328 | 32000 |  | 28672 | 24% | 6881.28 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 99 | 1 |  |  | 24 | LOE
1351-533 | Coil Supplies- Lead Blocks(pe6134 for copper) | 32025 | 32025 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 06 |  |  |  | 24 | M&S
1803-3.39 | Fab Test Track | 32025 | 32025 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 3.20 | 00 | 1 |  |  | 40 | 100
7101-000 | Apr-Sept MIE Cost PPPL | 32150 | 32150 |  | 0 | 0% | 0 | 7 | 71 | 710 | 9450 | 7101 | 1 | 0000 |  | 1 |  |  | 0 | 100
1403-FY04 | Analysis fy04 | 32172.5 | 32172.5 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 00 | 1 |  |  | 40 | 100
S1P1-107 | Wind magnetic diagnostic sensors | 0 | 32250.24 |  | 32250.24 | 40% | 12900.096 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 14 |  |  |  | 40
S1P2-107 | Wind magnetic diagnostic sensors | 0 | 32250.24 |  | 32250.24 | 40% | 12900.096 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 14 |  |  |  | 40
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 32284.8 |  | 32284.8 | 24% | 7748.352 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
22-60 | Fabrication/installation | 0 | 32315 |  | 32315 | 14% | 4524.1 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
453-1-8 | Testing PTPs, ISTPs | 0 | 32369.84 |  | 32369.84 | 18% | 5826.5712 | 4 | 45 | 453 | 9450 | 4501 | S | 453 |  | 1 |  | 45 | 18
1351-080 | Design Assy Fixture | 0 | 32432.4 |  | 32432.4 | 24% | 7783.776 | 1 | 13 | 131 | 9450 | 1350 | 1 |  | 97 | 1 | C |  | 24
22-60 | Fabrication/installation | 0 | 32474.8 |  | 32474.8 | 14% | 4546.472 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
810.900 | Project Management Office PPPL FY08 | 0 | 32685.12 |  | 32685.12 | 5% | 1634.256 | 8 | 81 | 810 | 9450 | 8101 | S |  | 10 | 1 |  | STRO | 5
S1P3-107 | Wind magnetic diagnostic sensors | 0 | 32955.12 |  | 32955.12 | 40% | 13182.048 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 15 |  |  |  | 40
FY05CV-14 | FY05 unrecoverable cost variance | 33000 | 33000 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1406 | [7 empty] | 100
FY05CV-21 | FY05 unrecoverable cost variance | 33000 | 33000 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1408
444-4-2 | Signal Conditioning & Cabling-Dsn | 4966.2495 | 33108.33 |  | 28142.0805 | 18% | 5065.5745 | 4 | 44 | 444 | 9450 | 4401 | 2 | 444 |  | 1 |  | 44 | 18 | 15
1407-127.1 | Complete Fab Type B casting supports (6) sets | 33235.92 | 33235.92 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 25 | 1 |  | 141 | 34 | 100
161-001 | Revise Preliminary Design for new supt locations | 29950.569 | 33278.41 |  | 3327.841 | 32% | 1064.9091 | 1 | 17 | 172 | 9450 | 1701 | 1 | BASE | 14 | 1 |  | 17 | 32 | 90
124-037L | VV Lateral Supports Fab by PPPL WBS 124 | 0 | 33288 |  | 33288 | 30% | 9986.4 | 1 | 12 | 124 | 9450 | 1204 | T | 124L | 22 | 1 |  | 12 | 30
131-032 | Title III engr (completion of coils 10% ) | 0 | 33470.34 |  | 33470.34 | 67% | 22425.1278 | 1 | 13 | 131 | 9450 | 1361 | F | 130 | 16 | 1 | C |  | 67
1203-271 | Develop Assy Rqmnts spec & process | 15183 | 33740 |  | 18557 | 40% | 7422.8 | 1 | 12 | 121 | 9450 | 1203 | 2 | 12FD | 02 | 1 |  |  | 40 | 45
810.104X | Project Management Office ORNL FY07 | 0 | 34002 |  | 34002 | 10% | 3400.2 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10
714.020 | LOE FY06 prior to assy starting | 0 | 34149.75 |  | 34149.75 | 15% | 5122.4625 | 7 | 74 | 742 | 9450 | 7401 | F | P1 | 11 | 1 |  |  | 15
123-137 | Fabricate and Deliver H/C ManifoldsWBS 123 | 0 | 34275 |  | 34275 | 32% | 10968 | 1 | 12 | 123 | 9450 | 1204 | T | 123A | 35 | 1 |  | 12 | 32
184-037 | External Trim Coil Procurement/Fab*ecp16 | 0 | 34275 |  | 34275 | 24% | 8226 | 1 | 13 | 133 | 9450 | 1354 | T | 133 | 14 | 1 |  | 13 | 24
411-2-6 | Grounding-Install | 0 | 34275 |  | 34275 | 18% | 6169.5 | 4 | 41 | 411 | 9450 | 4101 | F | 411 |  | 1 |  | 41 | 18
442-1-6 | Kirk Keys-Install | 0 | 34275 |  | 34275 | 18% | 6169.5 | 4 | 44 | 442 | 9450 | 4401 | F | 442 |  | 1 |  | 44 | 18
453-1-4 | Preop Testing-Procure test equipt | 0 | 34301.56 |  | 34301.56 | 18% | 6174.2808 | 4 | 45 | 453 | 9450 | 4501 | T | 453 |  | 1 |  | 45 | 18
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 34418.37 |  | 34418.37 | 22% | 7572.0414 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
51-30 | Installation, Testing, Documentation (Title III) | 0 | 34432.2 |  | 34432.2 | 5% | 1721.61 | 5 | 51 | 510 | 9450 | 5101 | F |  |  | 1 |  |  | 5
MCWF-281 | C5-Receive at PPPL | 0 | 34480 |  | 34480 | 10% | 3448 | 1 | 14 | 141 | 9450 | 1411 | P |  | 35 |  |  |  | 10
810.105X | Project Management Office ORNL FY08 | 0 | 34560 |  | 34560 | 10% | 3456 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10
1403-201 | Leads start assy Dwgs (10)-Type C | 34757.56 | 34757.56 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DWPT | 00 | 1 |  |  | 40 | 100
P1-140 | Instl Chl Plates,Tubing, Bag C5 | 0 | 34856.32 |  | 34856.32 | 30% | 10456.896 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 03 | 1 |  | 141 | 30
P3-110 | Instl Chill Plates,Tubing, Bag C4 | 0 | 34856.32 |  | 34856.32 | 30% | 10456.896 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 02 | 1 |  | 141 | 30
631-015 | Fab/Assy/Installation**reduced scope | 0 | 35038.6 |  | 35038.6 | 20% | 7007.72 | 6 | 62 | 621 | 9450 | 6201 | F | 621 | 14 | 1 |  |  | 20
161-011 | Final Design Base Support Structure WBS 172 | 0 | 35049.02 |  | 35049.02 | 32% | 11215.6864 | 1 | 17 | 172 | 9450 | 1701 | 2 | BASE | 16 | 1 |  | 17 | 32
P2-020 | Instl Chill Plates,Tubing, Bag A1 | 0 | 35059.48 |  | 35059.48 | 30% | 10517.844 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 03 | 1 |  | 141 | 30
431-260 | Power loop design | 35452.14 | 35452.14 |  | 0 | 18% | 0 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 01 | 1 |  | 43 | 18 | 100
1351-543 | VPI Supplies- Disposable VPI HW | 0 | 35505.47 |  | 35505.47 | 24% | 8521.3128 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 50 |  |  |  | 24
P3-020 | Instl Chill Plates,Tubing, Bag A2 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 04 | 1 |  | 141 | 30
P1-050 | Instl Chl Plates,Tubing, Bag B1 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 07 | 1 |  | 141 | 30
P1-080 | Instl Chl Plates,Tubing,Bag B2 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 07 | 1 |  | 141 | 30
P2-170 | Instl Chill Plates,Tubing,Bag B4 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 08 | 1 |  | 141 | 30
P3-170 | Instl Chill Plates,Tubing,Bag B6 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 09 | 1 |  | 141 | 30
P3-050 | Instl Chl Plates,Tubing, Bag A3 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 04 | 1 |  | 141 | 30
P3-140 | Instl Chl Plates,Tubing, Bag A4 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 05 | 1 |  | 141 | 30
P2-080 | Instl Chill Plates,Tubing,Bag B3 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 06 | 1 |  | 141 | 30
P3-080 | Instl Chill Plates,Tubing,Bag B5 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 07 | 1 |  | 141 | 30
P2-140 | Instl Chl Plates,Tubing, Bag A5 | 0 | 35618.16 |  | 35618.16 | 30% | 10685.448 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 08 | 1 |  | 141 | 30
1406-017.H | complete coil winding | 35769.6 | 35769.6 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 02 | 1 | C | 141 | 30 | 100
810.009 | PDR Support | 35888.58 | 35888.58 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 03 | 1 |  |  | 17 | 100
P1-170 | Instl Chill Plates,Tubing,Bag A6 | 0 | 36193.39 |  | 36193.39 | 30% | 10858.017 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 15 | 1 |  | 141 | 30
192-6.031 | Demo Method for current center on TRC | 36360 | 36360 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 05 | 1 |  |  | 10 | 100
P2-050 | Instl Chl Plates,Tubing, Bag C6 | 0 | 36576.88 |  | 36576.88 | 30% | 10973.064 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 09 | 1 |  | 141 | 30
172-031 | Title III engr | 37006.85 | 37006.85 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1411 | F | 14T | 10 | 1 |  |  | 40 | LOE
1403-45 | Check and promote models / drawings | 37062.72 | 37062.72 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 01 | 1 |  |  | 40 | 100
8204.01 | Assess magnetic material in test cell | 37080 | 37080 |  | 0 | 32% | 0 | 8 | 82 | 820 | 9450 | 8204 | 2 | FY04 | 11 | 1 |  |  | 32 | 100
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 37080 | 37080 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
EXFAC001.2 | Complete Crane Modifications (S04354) | 37608.48 | 37608.48 |  | 0 | 24% | 0 | 7 | 74 | 740 | 9450 | 7401 | F | TCMS |  | 1 |  |  | 24 | 100
431-260 | Power loop design | 37830.13 | 37830.13 |  | 0 | 18% | 0 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 01 | 1 |  | 43 | 18 | 100
431-260 | Power loop design | 37830.13 | 37830.13 |  | 0 | 18% | 0 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 01 | 1 |  | 43 | 18 | 100
1203-234 | Perform Global Seismic Analysis | 37914.24 | 37914.24 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
132-000 | PDR #17 & 25 | 0 | 37924.98 |  | 37924.98 | 30% | 11377.494 | 1 | 16 | 162 | 9450 | 1601 | F | 162 | 01 | 1 |  |  | 30
2001-001 | Apr-May MIE Cost | 38000 | 38000 |  | 0 | 0% | 0 | 2 | 22 | 220 | 9450 | 2001 | 1 | 0000 |  | 1 |  |  | 0 | 100
1350-100 | Design tooling & winding facility | 38007.5 | 38007.5 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
820.002 | LOE FY04 | 38220 | 38220 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | FY04 | 10 | 1 |  |  | 17 | LOE
1416A-161 | Side A Coil Assy-Cladding Asm | 38319.6 | 38319.6 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
820.004 | Proj engr FY06 | 18858.0085 | 38643.46 |  | 19785.4515 | 5% | 989.2726 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5 | LOE
S1P1-103.1 | Layout diagnostic&coolant paths on vsl w/templt | 0 | 38684 |  | 38684 | 40% | 15473.6 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 13 |  |  |  | 40
1406-016.0 | Oversight & Supervision | 38833.75 | 38833.75 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 00 | 1 | C | 141 | 40 | 100
VVSA-035 | Trinos Flanges | 39000 | 39000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS1 |  |  |  |  | 10 | 100
640.021 | Assembly/Fabrication | 0 | 39140.68 |  | 39140.68 | 20% | 7828.136 | 6 | 63 | 630 | 9450 | 6301 | F |  |  | 1 |  |  | 20
PPC-3 | Materials | 39150 | 39150 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | P | 14E | 15 |  | C |  | 40 | 100
390-015 | LOE Support FY05 **reduced scope | 39216.12 | 39216.12 |  | 0 | 30% | 0 | 3 | 39 | 390 | 9450 | 3901 | 2 |  |  | 1 |  |  | 30 | LOE
920.000 | Startup Personnel | 0 | 39424.32 |  | 39424.32 | 30% | 11827.296 | 8 | 85 | 850 | 9450 | 8501 | S |  | 10 | 1 |  |  | 30
1403-74 | check analysis using simplified models | 39660 | 39660 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 09 | 1 | C |  | 40 | 100
1416A-181 | Side B Coil Assy-Cladding Asm | 39724.23 | 39724.23 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
7501-07 | Construction Support Crew during cryostat instl | 0 | 39819.78 |  | 39819.78 | 24% | 9556.7472 | 7 | 75 | 750 | 9450 | 7501 | F |  |  | 1 |  |  | 24
121-037 | Purchase seals and ship to MTM | 39967.2 | 39967.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | 100
1406-215 | 4 turn racetrack fatigue tests | 40105 | 40105 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 21 | 1 |  |  | 40 | 100
1303-100 | CS Support Preliminary Design | 33557.3755 | 40381.92 |  | 6824.5445 | 32% | 2183.8542 | 1 | 13 | 132 | 9450 | 1303 | 2 |  | 08 | 1 |  | 13 | 32 | 83*
1350-100.1 | Design tooling & winding facility | 36437.04 | 40485.6 |  | 4048.56 | 24% | 971.6544 | 1 | 13 | 131 | 9450 | 1350 | F |  | 02 |  |  |  | 24 | 90
1416A-173 | Side A Coil Assy-Chill Plates and Tubing | 40488 | 40488 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
121-035 | VVSA Contract oversight FY05 & FY06 | 40698.7 | 40698.7 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
8203FY07 | Design Integration FY07 | 0 | 40838.57 |  | 40838.57 | 5% | 2041.9285 | 8 | 82 | 820 | 9450 | 8203 | F |  | 70 | 1 |  |  | 5
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 40861.02 |  | 40861.02 | 20% | 8172.204 | 1 | 13 | 134 | 9450 | 1355 | T | 134 |  | 1 |  |  | 20
840.301 | Apr-Sept MIE Cost ORNL | 40980 | 40980 |  | 0 | 0% | 0 | 8 | 84 | 840 | 9450 | 8402 | P | 0000 |  | 1 |  | 8400 | 0 | 100
7503-020 | Install & Level Support Base Plates | 0 | 41020.8 |  | 41020.8 | 24% | 9844.992 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
7503-260 | PTP Pumpdown & leak check VV | 0 | 41020.8 |  | 41020.8 | 24% | 9844.992 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 16 |  |  |  | 24
7503-210 | Fit-up all TF coils | 0 | 41020.8 |  | 41020.8 | 24% | 9844.992 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
TITLE3W | Titel III Design ORNL- Component Fab & WINDING | 9403.3491 | 41062.66 |  | 31659.3109 | 30% | 9497.7933 | 1 | 14 | 142 | 9450 | 1451 | F | LABR | 20 | 1 |  |  | 30 | LOE
123-037 | Fabricate and Deliver H/C Tubing WBS 123 | 0 | 41130 |  | 41130 | 32% | 13161.6 | 1 | 12 | 123 | 9450 | 1204 | T | 123 | 35 | 1 |  | 12 | 32
390-020 | LOE Support FY06 | 20190.744 | 41205.6 |  | 21014.856 | 30% | 6304.4568 | 3 | 39 | 390 | 9450 | 3901 | 2 |  |  | 1 |  |  | 30 | LOE
453-1-2 | New Procedures | 0 | 41224.8 |  | 41224.8 | 18% | 7420.464 | 4 | 45 | 453 | 9450 | 4501 | 2 | 453 |  | 1 |  | 45 | 18
714.020X | TC power instl | 41227.94 | 41227.94 |  | 0 | 15% | 0 | 7 | 74 | 742 | 9450 | 7401 | F | TCMS | 11 | 1 |  |  | 15
P1-020 | Instl Chill Plates,Tubing, Bag C1>>@150% | 41371.52 | 41371.52 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 01 | 1 | C | 141 | 20 | 100
P2-110 | Instl Chill Plates,Tubing,Bag C3 | 0 | 41371.52 |  | 41371.52 | 20% | 8274.304 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 02 | 1 |  | 141 | 20
P1-110 | Instl Chill Plates,Tubing,Bag C2>>@125% | 0 | 41371.52 |  | 41371.52 | 20% | 8274.304 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 01 | 1 | C | 141 | 20
22-30 | Design PLC based control system | 0 | 41414.4 |  | 41414.4 | 14% | 5798.016 | 2 | 22 | 220 | 9450 | 2201 | 2 |  |  | 1 |  |  | 14
192-6.06 | Coil positions to minimize islands. | 41501.1 | 41501.1 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 02 | 1 |  |  | 10 | 100
1407-100.3 | Fab & Instl Turning Fixt 2,3&4 | 41698.8 | 41698.8 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 16 | 1 |  | 141 | 28 | 100
1202-400 | Oversight and Contract Management | 41709.2 | 41709.2 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 12B | 40 | 1 |  |  | 40 | 100
1416A-193 | Side B Coil Assy-Chill Plates and Tubing | 41774.4 | 41774.4 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTA | 02 |  |  |  | 20 | 100
451-3-2 | Dwgs,asbuilts -Elect Dsn | 0 | 41781.42 |  | 41781.42 | 18% | 7520.6556 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 10 | 1 |  | 45 | 18
1352-145 | Fabricate/Dlvr PF 5 lower | 0 | 41817 |  | 41817 | 24% | 10036.08 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 39 | 1 |  | 13 | 24
1352-150 | Fabricate/Dlvr PF 6 lower | 0 | 41817 |  | 41817 | 24% | 10036.08 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 40 | 1 |  | 13 | 24
1352-155 | Fabricate/Dlvr PF 4 upper | 0 | 41817 |  | 41817 | 24% | 10036.08 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 41 | 1 |  | 13 | 24
1352-160 | Fabricate/Dlvr PF 5 upper | 0 | 41817 |  | 41817 | 24% | 10036.08 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 42 | 1 |  | 13 | 24
1352-165 | Fabricate/Dlvr PF 6 upper | 0 | 41817 |  | 41817 | 24% | 10036.08 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 43 | 1 |  | 13 | 24
441-135 | Install I/O Cabling | 0 | 42306.65 |  | 42306.65 | 18% | 7615.197 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
192-6 | LOE-FY05 WBS 192-6 Integrated Analysis | 42333 | 42333 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
191-001 | Title I design WBS 161 LN2 manifolds&piping | 0 | 42368.41 |  | 42368.41 | 28% | 11863.1548 | 1 | 16 | 161 | 9450 | 1601 | 1 | 161 |  | 1 |  | 16 | 28
810.005 | Project Management OfficePPPL FY07 | 0 | 42440.32 |  | 42440.32 | 5% | 2122.016 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 42792.22 |  | 42792.22 | 22% | 9414.2884 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
MCWF-161 | C3-Receive at PPPL | 43000 | 43000 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 33 |  |  |  | 10
7503-360 | Install Midplane Cryostat sections and port boot | 0 | 43804.8 |  | 43804.8 | 24% | 10513.152 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
730.8200 | PTP and Cooldown | 0 | 43804.8 |  | 43804.8 | 30% | 13141.44 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 91 | 1 |  | 7 | 30
840.303 | Closeout cost FY04 ECP-21 | 44000 | 44000 |  | 0 | 3% | 0 | 8 | 84 | 840 | 9450 | 8402 | P | FY04 |  | 1 |  |  | 3 | LOE
P1-091 | Receive C2, Prep& Instl Cladding | 44303.36 | 44303.36 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 02 | 1 | C | 141 | 20 | 100
P2-091 | Receive C3, Prep& Instl Cladding | 44303.36 | 44303.36 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 03 | 1 | C | 141 | 20 | 100
163-015 | Title III design CS sprt struc | 0 | 44363.42 |  | 44363.42 | 32% | 14196.2944 | 1 | 13 | 132 | 9450 | 1353 | F | 132A | 24 | 1 |  |  | 32
1407.002.2 | Winding Facility, Tooling, Materials Oversight | 44496 | 44496 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | A | 61 | 1 |  |  | 34 | 100
1407.002.2 | Winding Facility, Tooling, Materials Oversight | 44496 | 44496 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | A | 61 | 1 |  |  | 34 | 100
1408-999 | 3rd winding line conductor payout sys | 44528.48 | 44528.48 |  | 0 | 40% | 0 | 1 | 14 | 144 | 9450 | 1412 | T | FIX | 00 | 1 |  |  | 40 | 100
1406-000.1 | Supervision & Oversight | 44604 | 44604 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
820.173 | Apr-Sept MIE Cost PPPL | 44620 | 44620 |  | 0 | 0% | 0 | 8 | 82 | 820 | 9450 | 8204 | 2 | 0000 |  | 1 |  |  | 0 | 100
431-275 | Power cabling & Installation | 0 | 44766.8 |  | 44766.8 | 18% | 8058.024 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
411-3-4 | Test Cell AC Power Distr-Procure(pnls & xfrmrs) | 8956.744 | 44783.72 |  | 35826.976 | 18% | 6448.8557 | 4 | 41 | 411 | 9450 | 4101 | T | 411 |  | 1 |  | 41 | 18 | 20
22-65 | Fab PLC conrols | 0 | 44960 |  | 44960 | 14% | 6294.4 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
VVSA-521 | Join two pieces | 45000 | 45000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 13 |  |  |  | 10 | 100
191-8 | LOE-FY089 WBS 191 | 0 | 45384 |  | 45384 | 10% | 4538.4 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
1406-000.1 | Supervision & Oversight | 45485.38 | 45485.38 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
712.030 | Miscs Hardware/Material | 36414.504 | 45518.13 |  | 9103.626 | 10% | 910.3626 | 7 | 73 | 730 | 9450 | 7301 | F |  |  | 1 |  |  | 10 | 80
1303-100 | CS Support Preliminary Design | 37896.6913 | 45603.72 |  | 7707.0287 | 32% | 2466.2492 | 1 | 13 | 132 | 9450 | 1303 | 2 |  | 08 | 1 |  | 13 | 32 | 83*
1408-183 | Tubing (Chem flor and Poly) | 46373.37 | 46373.37 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 40 | 1 |  |  | 30 | 100
8203FY05 | Design Integration FY05 LOE | 47096.25 | 47096.25 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8203 | 2 |  | 50 | 1 |  |  | 10
1416B-161 | Side A Coil Assy-Cladding Asm | 23615.47 | 47230.94 |  | 23615.47 | 20% | 4723.094 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 50
174-037 | Modular Coil local I&C -Install (from wbs 143) | 4941.8533 | 47517.82 |  | 42575.9667 | 24% | 10218.232 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 98 | 1 |  |  | 24 | LOE
151-001 | Title I design WBS 171 cryostat | 47565.65 | 47565.65 |  | 0 | 28% | 0 | 1 | 17 | 171 | 9450 | 1701 | 1 | CRYO | 02 | 1 |  | 17 | 28 | 100
54-30 | Installation, Testing, Documentation (Title III) | 0 | 47892.06 |  | 47892.06 | 14% | 6704.8884 | 5 | 54 | 540 | 9450 | 5401 | F |  |  | 1 |  |  | 14
1407-002 | Winding Facility, Tooling, Materials Oversight | 47911.5 | 47911.5 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | A | 60 | 1 |  |  | 34 | 100
S1P1-108 | Install cooling/htg lines to vac vsl | 0 | 47934.72 |  | 47934.72 | 40% | 19173.888 | 1 | 18 | 185 | 9450 | 1810 | F | S1P1 | 17 |  |  |  | 40
S1P2-108 | Install cooling/htg lines to vac vsl | 0 | 47934.72 |  | 47934.72 | 40% | 19173.888 | 1 | 18 | 185 | 9450 | 1810 | F | S1P2 | 17 |  |  |  | 40
S1P3-108 | Install cooling/htg lines to vac vsl | 0 | 47934.72 |  | 47934.72 | 40% | 19173.888 | 1 | 18 | 185 | 9450 | 1810 | F | S1P3 | 18 |  |  |  | 40
810.003 | Project Management Office PPPL FY05 | 47975.2 | 47975.2 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
1351-543 | VPI Supplies- Disposable VPI HW | 0 | 47985 |  | 47985 | 24% | 11516.4 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 50 |  |  |  | 24
FY05CV-18 | FY05 unrecoverable cost variance | 48000 | 48000 |  | 0 | 0% | 0 | 1 | 14 | 144 | 9450 | 1419 | [7 empty] | 100
820.003 | Proj engr FY05 | 48000 | 48000 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8202 | 2 |  | 20 | 1 |  |  | 10 | LOE
99.05P | PPPL Allocations FY05 rebaeline re-estimate | 48151.8 | 48151.8 |  | 0 | 10% | 0 | A | AA | AAA | 9450 | 8998 | A |  |  | 1 |  |  | 10 | LOE
1301-155 | Trim Coil Layouts | 48204 | 48204 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 20 | 1 |  |  | 24 | 100
1416B-181 | Side B Coil Assy-Cladding Asm | 24365.79 | 48731.58 |  | 24365.79 | 20% | 4873.158 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 50
FY05CV-36 | FY05 unrecoverable cost variance | 49000 | 49000 |  | 0 | 0% | 0 | 4 | 44 | 445 | 9450 | 4401
1301FD-50 | Engineering LOE | 49575 | 49575 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | FINL | 99 | 1 | C |  | 24 | 100
1406-000 | Supervision & Oversight | 49596.3 | 49596.3 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
TITLE2TRC | Titel III Design-TRC FAB | 49600 | 49600 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | F | TRTD | 20 | 1 |  |  | 40 | 100
445-2-115 | Overload Protect-Fabr 4 chassis 120 modls | 0 | 49697.28 |  | 49697.28 | 22% | 10933.4016 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
VVSA-321 | Join two pieces | 50000 | 50000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 10 |  |  |  | 5 | 100
VVSA-371 | Cut Off Ports | 50000 | 50000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 15 |  |  |  | 10 | 100
VVSA-351 | Final Machine | 50000 | 50000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 16 |  |  |  | 10 | 100
VVSA-471 | Cut Off Ports | 0 | 50000 |  | 50000 | 10% | 5000 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 14 |  |  |  | 10
VVSA-451 | Final Machine | 0 | 50000 |  | 50000 | 10% | 5000 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 15 |  |  |  | 10
VVSA-571 | Cut Off Ports | 0 | 50000 |  | 50000 | 10% | 5000 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 15 |  |  |  | 10
VVSA-551 | Final Machine | 0 | 50000 |  | 50000 | 10% | 5000 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 16 |  |  |  | 10
1404-65 | Fabrication oversight by Project | 50000 | 50000 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 14D | 12 | 1 |  |  | 40 | 100
8203FY06 | Design Integration FY06 | 24418.8173 | 50038.56 |  | 25619.7427 | 5% | 1280.9871 | 8 | 82 | 820 | 9450 | 8203 | F |  | 60 | 1 |  |  | 5 | LOE
122-012 | Heater Tape System Design | 47587.3145 | 50091.91 |  | 2504.5955 | 32% | 801.4706 | 1 | 12 | 123 | 9450 | 1203 | 2 | 124H | 09 | 1 |  |  | 32 | 80
FY06CV-01 | FY06 YTD cost vari (offset by scope reductions) | 50317.9 | 50317.9 |  | 0 | 0% | 0 | 3 | 31 | 310 | 9450 | 3101
130-000 | TF PDR & FDR Engineering | 51227.5 | 51227.5 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 09 | 1 |  |  | 24 | 100
631-020 | Procurement **reduced scope | 0 | 51423 |  | 51423 | 20% | 10284.6 | 6 | 62 | 621 | 9450 | 6201 | T | 621 | 13 | 1 |  |  | 20
53-20 | Final Design (Title II) | 0 | 51648.3 |  | 51648.3 | 16% | 8263.728 | 5 | 53 | 530 | 9450 | 5301 | 2 |  |  | F |  |  | 16
810.909 | Project Management Office PPPL FY09 | 0 | 52134 |  | 52134 | 5% | 2606.7 | 8 | 81 | 810 | 9450 | 8101 | S |  | 10 | 1 |  | STRO | 5
1403-223C | Finish Top level coil assembly-Type C | 46982.061 | 52202.29 |  | 5220.229 | 30% | 1566.0687 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 40 | 1 |  |  | 30 | 90
1803-5.009 | Fabricate | 0 | 52714.95 |  | 52714.95 | 40% | 21085.98 | 1 | 18 | 186 | 9450 | 1803 | F | 4.00 | 17 | 1 |  |  | 40
1801-002 | Apr-Sept MIE Costs ORNL | 53050 | 53050 |  | 0 | 0% | 0 | 1 | 18 | 181 | 9450 | 1801 | 1 | 0000 | 10 | 1 |  |  | 0 | 100
1301R-00 | Oversight,suprevision,job management | 53476 | 53476 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 69 | 1 |  |  | 24 | 100
1408-186 | Manifolds | 53494.56 | 53494.56 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | OTHE | 40 | 1 |  |  | 30 | 100
S4P1-112 | Close up VV, leak check | 0 | 54694.4 |  | 54694.4 | 40% | 21877.76 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P2-112 | Close up VV, leak check | 0 | 54694.4 |  | 54694.4 | 40% | 21877.76 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
S4P3-112 | Close up VV, leak check | 0 | 54694.4 |  | 54694.4 | 40% | 21877.76 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
P1-001 | Rec C1,Prep& Instl Cladding>>@125% 1 shift | 54727.68 | 54727.68 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 1 | 01 | 1 | C | 141 | 20 | 100
1406-000 | Supervision & Oversight | 54847.5 | 54847.5 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 60 | 1 |  |  | 40 | 100
52-20 | Final Design (Title II) | 0 | 54935.01 |  | 54935.01 | 10% | 5493.501 | 5 | 52 | 520 | 9450 | 5201 | 2 |  |  | F |  |  | 10
445-2-110 | Overload Protect-Design | 0 | 54966.4 |  | 54966.4 | 22% | 12092.608 | 4 | 44 | 445 | 9450 | 4401 | S | 445 |  | 1 |  | 44 | 22
451-1-2 | Calculations-Dsn | 0 | 54966.4 |  | 54966.4 | 18% | 9893.952 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 16 | 1 |  | 45 | 18
VVSA-421 | Join two pieces | 55000 | 55000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 10 |  |  |  | 10 | 100
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 55097.6 |  | 55097.6 | 26% | 14325.376 | 4 | 45 | 452 | 9450 | 4501 | F | 452 |  | 1 |  | 45 | 26
1352-140 | Fabricate/Dlvr PF 4 lower | 0 | 55848.75 |  | 55848.75 | 24% | 13403.7 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 38 | 1 |  | 13 | 24
1409-000 | FY04 Oct-Mar | 55972.8 | 55972.8 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
FY05CV-43 | FY05 unrecoverable cost variance | 56000 | 56000 |  | 0 | 0% | 0 | A | AA | AAA | 9450 | 8998
633-015 | Fab/Assy/Installation | 0 | 56061.76 |  | 56061.76 | 20% | 11212.352 | 6 | 62 | 623 | 9450 | 6201 | F | 623 | 13 | 1 |  |  | 20
1803-7.01 | Meetings Prep and Reporting | 56350.25 | 56350.25 |  | 0 | 40% | 0 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
713.050 | Welding tools, materials & equipt | 0 | 56561.29 |  | 56561.29 | 24% | 13574.7096 | 7 | 76 | 760 | 9450 | 7601 | T |  |  | 1 |  |  | 24
FY05CV-28 | FY05 unrecoverable cost variance | 57000 | 57000 |  | 0 | 0% | 0 | 1 | 18 | 181 | 9450 | 1802
820.005 | Proj engr FY09 | 0 | 57146.72 |  | 57146.72 | 5% | 2857.336 | 8 | 82 | 820 | 9450 | 8202 | S |  | 21 | 1 |  |  | 5
55-30 | Installation, Testing, Documentation (Title III) | 0 | 58090 |  | 58090 | 8% | 4647.2 | 5 | 55 | 550 | 9450 | 5501 | F |  |  | 1 |  |  | 8
810.101 | Apr-Sept MIE Cost ORNL | 58600 | 58600 |  | 0 | 0% | 0 | 8 | 81 | 810 | 9450 | 8102 | 1 | 0000 |  | 1 |  |  | 0 | 100
1407-002 | Winding Facility, Tooling, Materials Oversight | 58710 | 58710 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | A | 60 | 1 |  |  | 34 | 100
1407-002 | Winding Facility, Tooling, Materials Oversight | 58864.5 | 58864.5 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | A | 60 | 1 |  |  | 34 | 100
1350-100 | Design tooling & winding facility | 58953.6 | 58953.6 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1350 | F |  | 01 |  |  |  | 24 | 100
380-015 | Fab & Install Beam probe | 0 | 59010 |  | 59010 | 34% | 20063.4 | 3 | 38 | 380 | 9450 | 3801 | F |  |  | 1 |  |  | 34
1407-110.3 | Compl Fabr Winding clamp sets (300 of 400) | 59231.28 | 59231.28 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 00 | 1 |  |  | 28 | 100
VVSA-361 | Vacuum Test | 60000 | 60000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 14 |  |  |  | 10 | 100
VVSA-461 | Vacuum Test | 0 | 60000 |  | 60000 | 10% | 6000 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 13 |  |  |  | 10
VVSA-561 | Vacuum Test | 0 | 60000 |  | 60000 | 10% | 6000 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 14 |  |  |  | 10
1421-410 | Deliver - Bladders | 0 | 60000 |  | 60000 | 40% | 24000 | 1 | 14 | 142 | 9450 | 1421 | T |  | 25 | 1 | C | 141 | 40
22-60 | Fabrication/installation | 0 | 60534 |  | 60534 | 14% | 8474.76 | 2 | 22 | 220 | 9450 | 2201 | F |  |  | 1 |  |  | 14
1416B-173 | Side A Coil Assy-Chill Plates and Tubing | 24289.428 | 60723.57 |  | 36434.142 | 20% | 7286.8284 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 40
840.302 | Project Physics/Engr Analysis FY04 | 60876 | 60876 |  | 0 | 3% | 0 | 8 | 84 | 840 | 9450 | 8402 | P | FY04 |  | 1 |  |  | 3 | LOE
181.200 | HP Coverage in the TFTR TC LOE FY04 | 61119.6 | 61119.6 |  | 0 | 24% | 0 | 1 | 18 | 181 | 9450 | 1802 | F | A | 10 | 1 |  |  | 24 | LOE
191-038 | PDR#17 | 0 | 61326.15 |  | 61326.15 | 30% | 18397.845 | 1 | 16 | 161 | 9450 | 1601 | 2 | 161 |  | 1 |  |  | 30
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 61531.2 |  | 61531.2 | 24% | 14767.488 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 05 |  |  |  | 24
7503-200 | Mate-up and weld all VV-to-Spool interfaces | 0 | 61531.2 |  | 61531.2 | 24% | 14767.488 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 06 |  |  |  | 24
122-037 | Deliver Pourable Insulation | 0 | 61695 |  | 61695 | 32% | 19742.4 | 1 | 12 | 122 | 9450 | 1204 | T | 122 | 44 | 1 |  | 12 | 32
444-3-4 | DC Shunts-Procure | 0 | 61695 |  | 61695 | 18% | 11105.1 | 4 | 44 | 444 | 9450 | 4401 | T | 444 |  | 1 |  | 44 | 18
FY05CV-22 | FY05 unrecoverable cost variance | 62000 | 62000 |  | 0 | 0% | 0 | 1 | 14 | 144 | 9450 | 1409 | [7 empty] | 100
0192-5 | LOE-FY05 WBS 192 | 62000 | 62000 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 07 | 1 |  |  | 10 | LOE
124-037 | PPPL Fab VV Vert. Supports (log # M1091) | 31272.96 | 62545.92 |  | 31272.96 | 30% | 9381.888 | 1 | 12 | 124 | 9450 | 1204 | T | 124 | 14 | 1 |  | 12 | 30 | 50
1416B-193 | Side B Coil Assy-Chill Plates and Tubing | 12530.58 | 62652.9 |  | 50122.32 | 20% | 10024.464 | 1 | 14 | 142 | 9450 | 1416 | 2 | DWTB |  |  |  |  | 20 | 20
7501-07 | Construction Support Crew during cryostat instl | 0 | 63261.43 |  | 63261.43 | 24% | 15182.7432 | 7 | 75 | 750 | 9450 | 7501 | F |  |  | 1 |  |  | 24
1407-204 | Build cleanrooms (2) locations | 63342 | 63342 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-F | 20 | 1 |  |  | 34 | 100
810.103 | Project Management Office ORNL FY05 | 63613.8 | 63613.8 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8102 | P |  |  | 1 |  |  | 10 | LOE
713.040 | General procurements | 0 | 63631.45 |  | 63631.45 | 24% | 15271.548 | 7 | 76 | 760 | 9450 | 7601 | T |  |  | 1 |  |  | 24
181.100 | PPPL EM LOE FY04 | 63686.74 | 63686.74 |  | 0 | 24% | 0 | 1 | 18 | 181 | 9450 | 1802 | 2 | A | 39 | 1 |  |  | 24 | LOE
1407-100 | Fabricate turning fixtures and coil supports | 63700 | 63700 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
1407-115 | Fabricate Conductor payout spool system | 64385.28 | 64385.28 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
2501-014 | FY04 work accomplished | 64654.8 | 64654.8 |  | 0 | 16% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0004 |  | 1 |  |  | 16
1404-003 | Apr-Sept YTD MIE Cost PPPL | 64670 | 64670 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 0000 | 54 | 1 |  |  | 0 | 100
390-010 | LOE Support FY04 | 65000 | 65000 |  | 0 | 30% | 0 | 3 | 39 | 390 | 9450 | 3901 | 1 |  |  | 1 |  |  | 30 | LOE
1901-003 | Apr-Sept MIE Costs PPPL | 67070 | 67070 |  | 0 | 0% | 0 | 1 | 19 | 192 | 9450 | 1901 | 1 | 0000 | 01 | 1 |  |  | 0 | 100
131-031 | Title III engr (FDR through 1st coil test 75%) | 43387.1323 | 67476.1 |  | 24088.9677 | 67% | 16139.6084 | 1 | 13 | 131 | 9450 | 1361 | F | 130 | 16 | 1 | C |  | 67 | LOE
8202-ECP16 | ecp16 | 68000 | 68000 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | FY04 | 10 | 1 |  |  | 17 | LOE
FY05CV-30 | FY05 unrecoverable cost variance | 68000 | 68000 |  | 0 | 0% | 0 | 1 | 18 | 187 | 9450 | 1804
FY05CV-35 | FY05 unrecoverable cost variance | 69000 | 69000 |  | 0 | 0% | 0 | 4 | 43 | 431 | 9450 | 4301
151-011 | Final Design Cryostat WBS 171 | 0 | 69927.69 |  | 69927.69 | 28% | 19579.7532 | 1 | 17 | 171 | 9450 | 1701 | 2 | CRYO | 18 | 1 |  | 17 | 28
441-115 | deliver PLC | 0 | 70250 |  | 70250 | 18% | 12645 | 4 | 44 | 441 | 9450 | 4401 | F | 441 |  | 1 |  | 44 | 18
S0P0-100 | LOE Crane support, fixture setupfor TFTR TC. | 0 | 70282.72 |  | 70282.72 | 40% | 28113.088 | 1 | 18 | 182 | 9450 | 1810 | F | S0P0 |  |  |  |  | 40
740.045 | Purchase- second Faro Arm PE005330 | 70455 | 70455 |  | 0 | 24% | 0 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 02 | 1 |  |  | 24 | 100
52-30 | Installation, Testing, Documentation (Title III) | 0 | 70664.53 |  | 70664.53 | 10% | 7066.453 | 5 | 52 | 520 | 9450 | 5201 | F |  |  | 1 |  |  | 10
631-020 | Procurement **reduced scope | 0 | 71655 |  | 71655 | 20% | 14331 | 6 | 62 | 621 | 9450 | 6201 | T | 621 | 13 | 1 |  |  | 20
714.010 | LOE FY05 | 72028.58 | 72028.58 |  | 0 | 15% | 0 | 7 | 74 | 742 | 9450 | 7401 | F | P1 | 11 | 1 |  |  | 15 | LOE
920.000 | Startup Personnel | 0 | 72195.84 |  | 72195.84 | 30% | 21658.752 | 8 | 85 | 850 | 9450 | 8501 | S |  | 10 | 1 |  |  | 30
METFY06R | Metrology for FP & machine assy FY06 | 35250.6312 | 72234.9 |  | 36984.2688 | 25% | 9246.0672 | 8 | 82 | 820 | 9450 | 8205 | F | [5 empty] | 25 | LOE
191-037 | Procurement WBS 161 | 0 | 72594.45 |  | 72594.45 | 28% | 20326.446 | 1 | 16 | 161 | 9450 | 1601 | T | 161 |  | 1 |  | 16 | 28
411-3-2.04 | Test Cell AC Power fy04 | 73000 | 73000 |  | 0 | 18% | 0 | 4 | 41 | 411 | 9450 | 4101 | 2 | 411 |  | 1 |  | 41 | 18 | 100
S2P1-100 | Assemble Mod-Coils A1/A2, B1/B2 | 0 | 73233.6 |  | 73233.6 | 40% | 29293.44 | 1 | 18 | 185 | 9450 | 1810 | F | S2P1 |  |  |  |  | 40
S2P1-200 | Assemble Mod-Coils C1/C2 | 0 | 73233.6 |  | 73233.6 | 40% | 29293.44 | 1 | 18 | 185 | 9450 | 1810 | F | S2P1 |  |  |  |  | 40
S2P2-100 | Assemble Mod-Coils A3/A4, B3/B4 | 0 | 73233.6 |  | 73233.6 | 40% | 29293.44 | 1 | 18 | 185 | 9450 | 1810 | F | S2P1 |  |  |  |  | 40
S2P2-200 | Assemble Mod-Coils C3/C4 | 0 | 73233.6 |  | 73233.6 | 40% | 29293.44 | 1 | 18 | 185 | 9450 | 1810 | F | S2P1 |  |  |  |  | 40
1352-110 | Tooling for PF 4 | 0 | 73762.5 |  | 73762.5 | 24% | 17703 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 32 | 1 |  | 13 | 24
1352-115 | Tooling for PF 5 | 0 | 73762.5 |  | 73762.5 | 24% | 17703 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 33 | 1 |  | 13 | 24
1352-120 | Tooling for PF 6 | 0 | 73762.5 |  | 73762.5 | 24% | 17703 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 34 | 1 |  | 13 | 24
124-130 | VV NB port cover Fabrication | 0 | 73924.32 |  | 73924.32 | 30% | 22177.296 | 1 | 12 | 124 | 9450 | 1204 | T | 124P | 22 | 1 |  | 12 | 30
3110 | Contract balance | 74000 | 74000 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 14J | 15 |  |  |  | 40 | 100
METFY07R | Metrology for FP & machine assy FY07 | 0 | 74115.1 |  | 74115.1 | 25% | 18528.775 | 8 | 82 | 820 | 9450 | 8205 | F | [5 empty] | 25
0192-99 | LOE-FY09 | 0 | 74400 |  | 74400 | 10% | 7440 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  | STRO | 10 | LOE
121-033 | VVSA Contract oversight FY05 | 74434.88 | 74434.88 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
VVSA-341 | Weld Ports | 75000 | 75000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 14 |  |  |  | 10 | 100
VVSA-441 | Weld Ports | 75000 | 75000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 13 |  |  |  | 10 | 100
VVSA-541 | Weld Ports | 0 | 75000 |  | 75000 | 10% | 7500 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 14 |  |  |  | 10
55-30 | Installation, Testing, Documentation (Title III) | 0 | 75124.8 |  | 75124.8 | 8% | 6009.984 | 5 | 55 | 550 | 9450 | 5501 | F |  |  | 1 |  |  | 8
S2P3-100 | Assemble Mod-Coils A5/A6, B5/B6 | 0 | 75204.8 |  | 75204.8 | 40% | 30081.92 | 1 | 18 | 185 | 9450 | 1810 | F | S2P1 |  |  |  |  | 40
S2P3-200 | Assemble Mod-Coils C5/C6 | 0 | 75204.8 |  | 75204.8 | 40% | 30081.92 | 1 | 18 | 185 | 9450 | 1810 | F | S2P1 |  |  |  |  | 40
1403-40.2Z | Update nonlinear winding pack analysis | 67707.297 | 75230.33 |  | 7523.033 | 30% | 2256.9099 | 1 | 14 | 142 | 9450 | 1403 | 2 | TCCO | 08 | 1 |  |  | 30 | 90
123-050 | Fabricate& Deliver Insul Boots WBS 122 | 0 | 75405 |  | 75405 | 32% | 24129.6 | 1 | 12 | 123 | 9450 | 1204 | T | 122 | 24 | 1 |  | 12 | 32
452-1-2 | Diagnostics AC Power Distr-Dsn | 0 | 75750.4 |  | 75750.4 | 26% | 19695.104 | 4 | 45 | 452 | 9450 | 4501 | 2 | 452 |  | 1 |  | 45 | 26
METFY08R | Metrology for FP & machine assy FY08 | 0 | 75799.75 |  | 75799.75 | 25% | 18949.9375 | 8 | 82 | 820 | 9450 | 8205 | F | [5 empty] | 25
1202-403 | RW-Issue VVSA MIT/QA plans and C&S Est (3.1) | 75815.74 | 75815.74 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 40 | 1 |  |  | 0 | 100
52-30 | Installation, Testing, Documentation (Title III) | 0 | 77664.45 |  | 77664.45 | 10% | 7766.445 | 5 | 52 | 520 | 9450 | 5201 | F |  |  | 1 |  |  | 10
810.909 | Project Management Office PPPL FY09 | 0 | 78255 |  | 78255 | 5% | 3912.75 | 8 | 81 | 810 | 9450 | 8101 | S |  | 10 | 1 |  | STRO | 5
151-001 | Title I design WBS 171 cryostat | 78284.96 | 78284.96 |  | 0 | 28% | 0 | 1 | 17 | 171 | 9450 | 1701 | 1 | CRYO | 02 | 1 |  | 17 | 28 | 100
920.000 | Startup Personnel | 0 | 79427.52 |  | 79427.52 | 30% | 23828.256 | 8 | 85 | 850 | 9450 | 8501 | S |  | 10 | 1 |  |  | 30
S4P1-102 | Position and weld all ports to VV | 0 | 79891.2 |  | 79891.2 | 40% | 31956.48 | 1 | 18 | 185 | 9450 | 1810 | F | S4P1 |  |  |  |  | 40
S4P2-102 | Position and weld all ports to VV | 0 | 80894.72 |  | 80894.72 | 40% | 32357.888 | 1 | 18 | 185 | 9450 | 1810 | F | S4P2 |  |  |  |  | 40
FY05CV-25 | FY05 unrecoverable cost variance | 81000 | 81000 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1451
53-30 | Coding, Configuration, Testing (Title III) | 0 | 81220.25 |  | 81220.25 | 16% | 12995.24 | 5 | 53 | 530 | 9450 | 5301 | F |  |  | 1 |  |  | 16
122-011 | Final design WBS 122 Thermal insulation | 60942.0825 | 81256.11 |  | 20314.0275 | 32% | 6500.4888 | 1 | 12 | 122 | 9450 | 1203 | 2 | 122 | 08 | 1 |  |  | 32 | 75
54-30 | Installation, Testing, Documentation (Title III) | 0 | 81326 |  | 81326 | 14% | 11385.64 | 5 | 54 | 540 | 9450 | 5401 | F |  |  | 1 |  |  | 14
920.000 | Startup Personnel | 0 | 81367.2 |  | 81367.2 | 30% | 24410.16 | 8 | 85 | 850 | 9450 | 8501 | S |  | 10 | 1 |  |  | 30
1404-65 | Fabrication oversight by Project | 82000 | 82000 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 14D | 12 | 1 |  |  | 40 | 100
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 82041.6 |  | 82041.6 | 24% | 19689.984 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 01 |  |  |  | 24
S4P3-102 | Position and weld all ports to VV*2 shift* | 0 | 82041.6 |  | 82041.6 | 40% | 32816.64 | 1 | 18 | 185 | 9450 | 1810 | F | S4P3 |  |  |  |  | 40
1351-527 | Coil Supplies- Epoxy | 0 | 82322.96 |  | 82322.96 | 24% | 19757.5104 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 50 |  |  |  | 24
1402-002 | Apr-Sept MIE Cost ORNL | 84220 | 84220 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1402 | 1 | 0000 | 54 | 1 |  |  | 0 | 100
121-034.1 | VVSA Title III engr | 35853.9106 | 84561.11 |  | 48707.1994 | 40% | 19482.8797 | 1 | 12 | 121 | 9450 | 1250 | F |  | 07 | 1 |  |  | 40 | LOE
713.030 | Tooling,assy fixtures,misc equipt | 0 | 84841.94 |  | 84841.94 | 24% | 20362.0656 | 7 | 76 | 760 | 9450 | 7601 | T |  |  | 1 |  |  | 24
1202-325 | MT-PVVS Complete Fabrication (3.2.2) [A/ 1] | 85000 | 85000 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 40 | 100
7503-320 | Complete Elect Pwr connections | 0 | 85939.2 |  | 85939.2 | 24% | 20625.408 | 7 | 75 | 750 | 9450 | 7503 | F | 75Z | 17 |  |  |  | 24
191-011 | Title II design WBS 161 LN2 manifolds&piping | 0 | 86465.7 |  | 86465.7 | 28% | 24210.396 | 1 | 16 | 161 | 9450 | 1601 | 2 | 161 |  | 1 |  | 16 | 28
192-6.03 | Method for determining current center | 86626.35 | 86626.35 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 02 | 1 |  |  | 10 | 100
0191-7 | LOE-FY08 WBS 191 | 0 | 87352 |  | 87352 | 10% | 8735.2 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
820.200 | LOE FY04 | 87508.2 | 87508.2 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8203 | 2 | FY04 | 10 | 1 |  |  | 17 | LOE
FY05CV-19 | FY05 unrecoverable cost variance | 88000 | 88000 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1414
810.102 | Project Management Office ORNL FY04 | 88000 | 88000 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8102 | 1 | FY04 |  | 1 |  |  | 17 | LOE
METFY05 | Dimensional control FY05 ECP24 | 88323.84 | 88323.84 |  | 0 | 25% | 0 | 8 | 82 | 820 | 9450 | 8205 | 2 |  | 20 | 1 |  |  | 25 | LOE
1351-531 | Coil Supplies- G-11 fillers (PE006162) | 89115 | 89115 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 05 |  |  |  | 24 | 100
8203FY06 | Design Integration FY06 | 43999.583 | 90163.08 |  | 46163.497 | 5% | 2308.1748 | 8 | 82 | 820 | 9450 | 8203 | F |  | 60 | 1 |  |  | 5 | LOE
920.000 | Startup Personnel | 0 | 90919.5 |  | 90919.5 | 30% | 27275.85 | 8 | 85 | 850 | 9450 | 8501 | S |  | 10 | 1 |  |  | 30
1301R-99 | Chit resolution,design,analysis (ecp24 plg) | 91000 | 91000 |  | 0 | 24% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | PREL | 88 | 1 | C |  | 24 | 100
1301-0003 | Apr-Sept MIE Cost PPPL | 91660 | 91660 |  | 0 | 0% | 0 | 1 | 13 | 130 | 9450 | 1301 | 1 | 0000 | 54 | 1 |  |  | 0 | 100
8203FY07 | Design Integration FY07 | 0 | 92141.33 |  | 92141.33 | 5% | 4607.0665 | 8 | 82 | 820 | 9450 | 8203 | F |  | 70 | 1 |  |  | 5
1404-ECP16 | ecp16 | 93000 | 93000 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 0000 | 54 | 1 |  |  | 0 | 100
1408-705 | Fabr Lead HW Type C for Coil c1 | 93326.22 | 93326.22 |  | 0 | 30% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | LEAD | 20 | 1 | C | 141 | 30 | 100
1203-232 | Structural Analysis of Vac Vsl | 94239.96 | 94239.96 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
840.202 | Project Physics/Engr Analysis FY04 | 94255.2 | 94255.2 |  | 0 | 3% | 0 | 8 | 84 | 840 | 9450 | 8401 | P | FY04 |  | 1 |  |  | 3 | LOE
VVSA-331 | Machine for Ports | 95000 | 95000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 14 |  |  |  | 5 | 100
VVSA-431 | Machine for Ports | 95000 | 95000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 13 |  |  |  | 10 | 100
VVSA-531 | Machine for Ports | 52250 | 95000 |  | 42750 | 10% | 4275 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 14 |  |  |  | 10 | 55
VVSA-011 | Sect 5.1 Segmentation Scheme | 96075 | 96075 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS1 |  |  |  |  | 5 | 100
820.002 | LOE FY04 | 96893.68 | 96893.68 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | FY04 | 10 | 1 |  |  | 17 | LOE
1404-200 | JPP- cost FY03 | 97206.2 | 97206.2 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14J | 08 | 1 |  |  | 40 | 100
51-30 | Installation, Testing, Documentation (Title III) | 0 | 98353.4 |  | 98353.4 | 5% | 4917.67 | 5 | 51 | 510 | 9450 | 5101 | F |  |  | 1 |  |  | 5
P1-131 | Wind coil C5 | 0 | 99031.04 |  | 99031.04 | 30% | 29709.312 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 03 | 1 |  | 141 | 30
P3-101 | Wind coil C4 | 0 | 99031.04 |  | 99031.04 | 30% | 29709.312 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 02 | 1 |  | 141 | 30
P2-011 | Wind coil A1 | 0 | 99031.04 |  | 99031.04 | 30% | 29709.312 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 03 | 1 | C | 141 | 30
7501-06 | Construction Support Crew during e-beam mapping | 0 | 99199.62 |  | 99199.62 | 24% | 23807.9088 | 7 | 75 | 750 | 9450 | 7501 | F |  |  | 1 |  |  | 24
P3-011 | Wind coil A2 | 0 | 99227.81 |  | 99227.81 | 30% | 29768.343 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 04 | 1 |  | 141 | 30
VVSA-051 | Procure Die Materials (4 sets) | 100000 | 100000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS2 | 11 |  |  |  | 5 | 100
VVSA-221 | Procure Vessel Material | 100000 | 100000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS5 | 11 |  |  |  | 5 | 100
1404-002 | Apr-Sept YTD MIE Cost ORNL | 100220 | 100220 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1404 | R | 0000 | 54 | 1 |  |  | 0 | 100
141-031 | Title III engr WBS 132 | 0 | 100403.8 |  | 100403.8 | 24% | 24096.912 | 1 | 13 | 132 | 9450 | 1352 | F | 13P | 50 | 1 |  |  | 24
1803-8 | Metrology Support (moved from 1803) | 101133 | 101133 |  | 0 | 40% | 0 | 1 | 18 | 187 | 9450 | 1804 | F | MEAS | 17 | 1 |  |  | 40 | LOE
P1-041 | Wind coil B1 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 05 | 1 |  | 141 | 30
P1-071 | Wind coil B2 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 07 | 1 |  | 141 | 30
P2-161 | Wind coil B4 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 08 | 1 |  | 141 | 30
P3-161 | Wind coil B6 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 09 | 1 |  | 141 | 30
P1-161 | Wind coil A6 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 14 | 1 |  | 141 | 30
P3-041 | Wind coil A3 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 04 | 1 |  | 141 | 30
P3-131 | Wind coil A4 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 05 | 1 |  | 141 | 30
P2-071 | Wind coil B3 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 06 | 1 |  | 141 | 30
P3-071 | Wind coil B5 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 07 | 1 |  | 141 | 30
P2-131 | Wind coil A5 | 0 | 101195.52 |  | 101195.52 | 30% | 30358.656 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 08 | 1 |  | 141 | 30
191-4 | LOE-FY04 WBS 191-4 Management Activities | 101500 | 101500 |  | 0 | 10% | 0 | 1 | 19 | 191 | 9450 | 1901 | 2 | 191 | 01 | 1 |  |  | 10 | LOE
VVSA-081 | Inspection | 101640 | 101640 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS2 | 13 |  |  |  | 5 | 100
1407-100.2 | Fabr turning fixt&coil supports **2nd line** | 101719.8 | 101719.8 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 28 | 100
P2-041 | Wind coil C6 | 0 | 103506.66 |  | 103506.66 | 30% | 31051.998 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 09 | 1 |  | 141 | 30
56-30 | Installation, Testing, Documentation (Title III) | 0 | 103766.13 |  | 103766.13 | 8% | 8301.2904 | 5 | 56 | 560 | 9450 | 5601 | F |  |  | 1 |  |  | 8
1201-003 | Apr-MSept MIE Cost PPPL | 105370 | 105370 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1201 | 1 | 0000 | 10 | 1 |  |  | 0 | 100
8203FY05 | Design Integration FY05 LOE | 105932.25 | 105932.25 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8203 | 2 |  | 50 | 1 |  |  | 10
0192-7 | LOE-FY08 WBS 192 | 0 | 107400 |  | 107400 | 10% | 10740 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
1351-525 | Coil Supplies- Insulation (PE6299) | 91034.4 | 109680 |  | 18645.6 | 24% | 4474.944 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 06 |  |  |  | 24 | 83
820.003 | Proj engr FY05 | 110689.8 | 110689.8 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8202 | 2 |  | 20 | 1 |  |  | 10 | LOE
1407-003 | Winding Facility, Tooling, Design | 111438.6 | 111438.6 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | D | 64 | 1 |  |  | 34 | 100
99.03 | Apr-Sept MIE Cost PPPL | 112000 | 112000 |  | 0 | 0% | 0 | A | AA | AAA | 9450 | 8998 | A | 0000 |  | 1 |  |  | 0 | 100
172-031.1 | Title III engr | 39122.9733 | 112100.21 |  | 72977.2367 | 20% | 14595.4473 | 1 | 14 | 141 | 9450 | 1411 | F | 14T | 10 | 1 |  |  | 20 | LOE
633-020 | Procurement | 0 | 112329.75 |  | 112329.75 | 20% | 22465.95 | 6 | 62 | 623 | 9450 | 6201 | T | 623 | 12 | 1 |  |  | 20
4501-001 | Apr-Sept MIE Cost | 112340 | 112340 |  | 0 | 0% | 0 | 4 | 45 | 451 | 9450 | 4501 | 1 | 0000 |  | 1 |  |  | 0 | 100
0192-6X | LOE-FY07 WBS 192 | 0 | 114657.3 |  | 114657.3 | 10% | 11465.73 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
51-30 | Installation, Testing, Documentation (Title III) | 0 | 115631.5 |  | 115631.5 | 5% | 5781.575 | 5 | 51 | 510 | 9450 | 5101 | F |  |  | 1 |  |  | 5
P2-101 | Wind coil C-3 | 8146.4432 | 116377.76 |  | 108231.3168 | 20% | 21646.2634 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 02 | 1 | C | 141 | 20 | 7
P1-101 | Wind coil C-2>>@125% | 116377.76 | 116377.76 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 3 | 01 | 1 | C | 141 | 20 | 100
810.002 | Project Management Office PPPL FY04 | 116864.8 | 116864.8 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
METFY06R | Metrology for FP & machine assy FY06 | 57131.1994 | 117072.13 |  | 59940.9306 | 25% | 14985.2326 | 8 | 82 | 820 | 9450 | 8205 | F | [5 empty] | 25 | LOE
P1-011 | Wind coil C1>>@150% | 118006.56 | 118006.56 |  | 0 | 20% | 0 | 1 | 14 | 142 | 9450 | 1451 | F | 2 | 01 | 1 | C | 141 | 20 | 100
52-30 | Installation, Testing, Documentation (Title III) | 0 | 118614.8 |  | 118614.8 | 10% | 11861.48 | 5 | 52 | 520 | 9450 | 5201 | F |  |  | 1 |  |  | 10
1404-106 | contract balance ECP 11 | 119610 | 119610 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14E | 09 | 1 |  |  | 40 | 100
820.004 | Proj engr FY06 | 58424.2872 | 119721.9 |  | 61297.6128 | 5% | 3064.8806 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5 | LOE
FY05CV-5 | FY05 unrecoverable cost variance | 120000 | 120000 |  | 0 | 0% | 0 | 1 | 13 | 131 | 9450 | 1301 |  | 0000 | [5 empty] | 100
VVSA-031 | Sect 5.1.3 Proc Outline & Asc Procedures | 121675.78 | 121675.78 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS1 |  |  |  |  | 5 | 100
1203-361 | Final Design of Heating/Cooling | 121988.29 | 121988.29 |  | 0 | 32% | 0 | 1 | 12 | 123 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 32 | 100
1404-206 | JPP- July forecast ECP 11 | 122622.5 | 122622.5 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14J | 09 | 1 |  |  | 40 | 100
2501-001 | Apr-Sept MIE Cost | 123000 | 123000 |  | 0 | 0% | 0 | 2 | 25 | 250 | 9450 | 2501 | 1 | 0000 |  | 1 |  |  | 0 | 100
1350-525 | TF mold (2) | 0 | 123390 |  | 123390 | 24% | 29613.6 | 1 | 13 | 131 | 9450 | 1350 | F |  | 96 |  |  |  | 24
451-3-2 | Dwgs,asbuilts -Elect Dsn | 0 | 124759.84 |  | 124759.84 | 18% | 22456.7712 | 4 | 45 | 451 | 9450 | 4501 | 2 | 451 | 10 | 1 |  | 45 | 18
8203-ECP16 | ecp16 | 125000 | 125000 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8203 | 2 | FY04 | 10 | 1 |  |  | 17 | LOE
431-275 | Power cabling & Installation | 0 | 126450 |  | 126450 | 18% | 22761 | 4 | 43 | 431 | 9450 | 4301 | F | 431 | 10 | 1 |  | 43 | 18
1406-016 | Procure casting from EIO (new scope) | 127387.26 | 127387.26 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-4 | 64 | 1 |  | 141 | 40 | 100
1202-425 | RW-PVVS Complete Fabrication (3.2.2) | 127527.4 | 127527.4 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 46 | 1 |  |  | 40 | 100
162-031 | Title III engr WBS 151 | 0 | 128073.05 |  | 128073.05 | 32% | 40983.376 | 1 | 15 | 151 | 9450 | 1550 | F |  | 16 | 1 |  |  | 32
1202-003 | Apr-Sept MIE Cost PPPL | 128340 | 128340 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | R | 0000 | 10 | 1 |  |  | 0 | 100
1407-011 | Fabricate Autoclave | 128770.56 | 128770.56 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 14-5 | 13 | 1 |  |  | 34 | 100
MCWF-001A | EIO Project Mgt. & Reporting AMEND #11 | 0 | 129250 |  | 129250 | 10% | 12925 | 1 | 14 | 141 | 9450 | 1411 | P |  | 15 |  |  |  | 10
MCWF-011 | Pattern A complete | 130000 | 130000 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 20 |  |  |  | 10 | 100
1409-000 | FY04 Oct-Mar | 130559.52 | 130559.52 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 05 | 1 |  | 141 | 34 | 100
1407-100.3 | Fab & Instl Turning Fixt 2,3&4 | 130782.6 | 130782.6 |  | 0 | 28% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 16 | 1 |  | 141 | 28 | 100
820.174 | LOE FY04 | 133179 | 133179 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8204 | 2 | FY04 | 10 | 1 |  |  | 17 | LOE
1351-529 | Coil Supplies- Deliver Copper Conductor(PE005935 | 133864.5 | 133864.5 |  | 0 | 24% | 0 | 1 | 13 | 131 | 9450 | 1351 | F | 13E | 02 |  |  |  | 24 | 100
FY05CV-7 | FY05 unrecoverable cost variance | 135000 | 135000 |  | 0 | 0% | 0 | 1 | 13 | 131 | 9450 | 1350 |  |  | 00
453-1-8 | Testing PTPs, ISTPs | 0 | 135467.52 |  | 135467.52 | 18% | 24384.1536 | 4 | 45 | 453 | 9450 | 4501 | S | 453 |  | 1 |  | 45 | 18
181.210 | HP Coverage in the TFTR TC LOE FY05 | 136539 | 136539 |  | 0 | 24% | 0 | 1 | 18 | 181 | 9450 | 1802 | F | A | 20 | 1 |  |  | 24 | LOE
1421-210 | Deliver - Assembly shims | 0 | 138000 |  | 138000 | 40% | 55200 | 1 | 14 | 142 | 9450 | 1421 | T |  | 25 | 1 | C | 141 | 40
711A.020 | LOE FY04 | 138442.46 | 138442.46 |  | 0 | 15% | 0 | 7 | 74 | 741 | 9450 | 7401 | 1 | A | 11 | 1 |  |  | 15 | LOE
1403-ECP16 | ecp16 | 139000 | 139000 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | DW09 | 00 | 1 |  |  | 40 | 100
MCWF-111 | A1-MTK-casting | 140600 | 140600 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 36 |  |  |  | 10 | 100
MCWF-171 | A2-MTK-casting | 140600 | 140600 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 38 |  |  |  | 10 | 100
MCWF-351 | A3-MTK-casting | 140600 | 140600 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 39 |  |  |  | 10 | 100
MCWF-231 | B1-MTK-casting | 140600 | 140600 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 40 |  |  |  | 10 | 100
MCWF-321 | B2-MTK-casting | 91390 | 140600 |  | 49210 | 10% | 4921 | 1 | 14 | 141 | 9450 | 1411 | P |  | 44 |  |  |  | 10 | 65
MCWF-441 | A6-MTK-casting | 112480 | 140600 |  | 28120 | 10% | 2812 | 1 | 14 | 141 | 9450 | 1411 | P |  | 50 |  |  |  | 10 | 80
920.000 | Startup Personnel | 0 | 140633.35 |  | 140633.35 | 30% | 42190.005 | 8 | 85 | 850 | 9450 | 8501 | S |  | 10 | 1 |  |  | 30
MCWF-081 | C2-MTK-casting | 140810 | 140810 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 32 |  |  |  | 10 | 100
MCWF-141 | C3-MTK-casting | 140810 | 140810 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 33 |  |  |  | 10 | 100
MCWF-201 | C4-MTK-casting | 140810 | 140810 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 34 |  |  |  | 10 | 100
MCWF-261 | C5-MTK-casting | 140810 | 140810 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 35 |  |  |  | 10 | 100
MCWF-381 | A4-MTK-casting | 140810 | 140810 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 41 |  |  |  | 10 | 100
MCWF-471 | B3-MTK-casting | 77445.5 | 140810 |  | 63364.5 | 10% | 6336.45 | 1 | 14 | 141 | 9450 | 1411 | P |  | 45 |  |  |  | 10 | 55
MCWF-501 | B4-MTK-casting | 70405 | 140810 |  | 70405 | 10% | 7040.5 | 1 | 14 | 141 | 9450 | 1411 | P |  | 46 |  |  |  | 10 | 50
MCWF-531 | B5-MTK-casting | 21121.5 | 140810 |  | 119688.5 | 10% | 11968.85 | 1 | 14 | 141 | 9450 | 1411 | P |  | 47 |  |  |  | 10 | 15
MCWF-561 | B6-MTK-casting | 0 | 140810 |  | 140810 | 10% | 14081 | 1 | 14 | 141 | 9450 | 1411 | P |  | 48 |  |  |  | 10
MCWF-411 | A5-MTK-casting | 140810 | 140810 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 49 |  |  |  | 10 | 100
MCWF-291 | C6-MTK-casting | 140810 | 140810 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 51 |  |  |  | 10 | 100
MCWF-051 | C1-MTK-casting upgrade | 144138.12 | 144138.12 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 30 |  |  |  | 10 | 100
1407-100 | Fabricate turning fixtures and coil supports | 145314 | 145314 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | FIX | 10 | 1 |  | 141 | 34 | 100
MCWF-001B | EIO Project Mgt. & Reporting AMEND #12 | 0 | 146000 |  | 146000 | 10% | 14600 | 1 | 14 | 141 | 9450 | 1411 | P |  | 15 |  |  |  | 10
810.002E | Project Management Office PPPL FY04 ECP24 | 146000 | 146000 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
181.222 | HP Coverage in the TFTR TC LOE FY06 | 71896.4739 | 147328.84 |  | 75432.3661 | 24% | 18103.7679 | 1 | 18 | 181 | 9450 | 1802 | F | A | 21 | 1 |  |  | 24 | LOE
132-001 | Title I design WBS 162 Coil leads | 0 | 149381.1 |  | 149381.1 | 22% | 32863.842 | 1 | 16 | 162 | 9450 | 1601 | 1 | 162 | 01 | 1 |  | 16 | 22
132-011 | Title II design WBS 162 Coil leads | 0 | 149903.17 |  | 149903.17 | 22% | 32978.6974 | 1 | 16 | 162 | 9450 | 1601 | 2 | 162 | 01 | 1 |  | 16 | 22
1803-7.20 | Design Activity | 73199.9268 | 149999.85 |  | 76799.9232 | 40% | 30719.9693 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
181.220 | HP Coverage in the TFTR TC LOE FY07 | 0 | 150543.22 |  | 150543.22 | 24% | 36130.3728 | 1 | 18 | 181 | 9450 | 1802 | F | A | 30 | 1 |  |  | 24
1202-424 | RW-PVVS Begin Fabrication (3.2.2) | 151109.14 | 151109.14 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 40 | 1 |  |  | 0 | 100
192-4 | LOE-FY05 WBS 192-4 Design Integration Activities | 152368.96 | 152368.96 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 00 | 1 |  |  | 10 | LOE
1403-ECPRB | Rebaselining YTD adjustment for ytd cv | 154400 | 154400 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1403 | 2 | 0000 | 00 | 1 |  |  | 40 | 100
1403-29 | Complete ANSYS model of coil structure asm | 154500 | 154500 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW04 |  | 1 |  |  | 40 | 100
181.221 | HP Coverage in the TFTR TC LOE FY08 | 0 | 154583 |  | 154583 | 24% | 37099.92 | 1 | 18 | 181 | 9450 | 1802 | F | A | 32 | 1 |  |  | 24
1402-003 | Apr-Sept MIE Cost PPPL | 154920 | 154920 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1402 | 1 | 0000 | 54 | 1 |  |  | 0 | 100
MCWF-451 | A6-MTM - machining/inspection | 0 | 155000 |  | 155000 | 10% | 15500 | 1 | 14 | 141 | 9450 | 1411 | P |  | 50 |  |  |  | 10
TITLE3W | Titel III Design ORNL- Component Fab & WINDING | 35504.6455 | 155042.12 |  | 119537.4745 | 30% | 35861.2424 | 1 | 14 | 142 | 9450 | 1451 | F | LABR | 20 | 1 |  |  | 30 | LOE
390-001 | LOE Support FY03 | 155450 | 155450 |  | 0 | 30% | 0 | 3 | 39 | 390 | 9450 | 3901 | 1 | 0000 |  | 1 |  |  | 30 | 100
810.104 | Project Management Office ORNL FY06 | 76447.64 | 156655 |  | 80207.36 | 10% | 8020.736 | 8 | 81 | 810 | 9450 | 8102 | F |  |  | 1 |  |  | 10 | LOE
MCWF-341 | B2-Receive at PPPL | 0 | 159450 |  | 159450 | 10% | 15945 | 1 | 14 | 141 | 9450 | 1411 | P |  | 44 |  |  |  | 10
56-30 | Installation, Testing, Documentation (Title III) | 0 | 159492 |  | 159492 | 8% | 12759.36 | 5 | 56 | 560 | 9450 | 5601 | F |  |  | 1 |  |  | 8
MCWF-061 | C1-MTM - machining/inspection | 159560 | 159560 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 30 |  |  |  | 10 | 100
820.200 | LOE FY04 | 160062 | 160062 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8203 | 2 | FY04 | 10 | 1 |  |  | 17 | LOE
MCWF-011 | Pattern A complete | 160125 | 160125 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 20 |  |  |  | 10 | 100
7401-001 | Apr-Sept MIE Cost PPPL | 164000 | 164000 |  | 0 | 15% | 0 | 7 | 74 | 741 | 9450 | 7401 | 1 | 0000 |  | 1 |  |  | 15 | 100
VVSA-501 | 60 deg segment | 165000 | 165000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 13 |  |  |  | 10 | 100
VVSA-511 | 60 deg segment | 165000 | 165000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS8 | 13 |  |  |  | 10 | 100
99.08 | PPPL Allocations FY08 | 0 | 166336.61 |  | 166336.61 | 10% | 16633.661 | A | AA | AAA | 9450 | 8998 | A |  |  | 1 |  |  | 10
MCWF-151 | C3-MTM - machining/inspection | 167910 | 167910 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 33 |  |  |  | 10 | 100
MCWF-211 | C4-MTM - machining/inspection | 167910 | 167910 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 34 |  |  |  | 10 | 100
MCWF-271 | C5-MTM - machining/inspection | 142723.5 | 167910 |  | 25186.5 | 10% | 2518.65 | 1 | 14 | 141 | 9450 | 1411 | P |  | 35 |  |  |  | 10 | 85
MCWF-121 | A1-MTM - machining/inspection | 83955 | 167910 |  | 83955 | 10% | 8395.5 | 1 | 14 | 141 | 9450 | 1411 | P |  | 36 |  |  |  | 10 | 50
MCWF-181 | A2-MTM - machining/inspection | 41977.5 | 167910 |  | 125932.5 | 10% | 12593.25 | 1 | 14 | 141 | 9450 | 1411 | P |  | 38 |  |  |  | 10 | 25
MCWF-361 | A3-MTM - machining/inspection | 33582 | 167910 |  | 134328 | 10% | 13432.8 | 1 | 14 | 141 | 9450 | 1411 | P |  | 39 |  |  |  | 10 | 20
MCWF-241 | B1-MTM - machining/inspection | 8395.5 | 167910 |  | 159514.5 | 10% | 15951.45 | 1 | 14 | 141 | 9450 | 1411 | P |  | 40 |  |  |  | 10 | 5
MCWF-391 | A4-MTM - machining/inspection | 16791 | 167910 |  | 151119 | 10% | 15111.9 | 1 | 14 | 141 | 9450 | 1411 | P |  | 41 |  |  |  | 10 | 10
MCWF-331 | B2-MTM - machining/inspection | 0 | 167910 |  | 167910 | 10% | 16791 | 1 | 14 | 141 | 9450 | 1411 | P |  | 44 |  |  |  | 10
MCWF-481 | B3-MTM - machining/inspection | 0 | 167910 |  | 167910 | 10% | 16791 | 1 | 14 | 141 | 9450 | 1411 | P |  | 45 |  |  |  | 10
MCWF-511 | B4-MTM - machining/inspection | 0 | 167910 |  | 167910 | 10% | 16791 | 1 | 14 | 141 | 9450 | 1411 | P |  | 46 |  |  |  | 10
MCWF-541 | B5-MTM - machining/inspection | 0 | 167910 |  | 167910 | 10% | 16791 | 1 | 14 | 141 | 9450 | 1411 | P |  | 47 |  |  |  | 10
MCWF-571 | B6-MTM - machining/inspection | 0 | 167910 |  | 167910 | 10% | 16791 | 1 | 14 | 141 | 9450 | 1411 | P |  | 48 |  |  |  | 10
MCWF-421 | A5-MTM - machining/inspection | 0 | 167910 |  | 167910 | 10% | 16791 | 1 | 14 | 141 | 9450 | 1411 | P |  | 49 |  |  |  | 10
MCWF-301 | C6-MTM - machining/inspection | 0 | 167910 |  | 167910 | 10% | 16791 | 1 | 14 | 141 | 9450 | 1411 | P |  | 51 |  |  |  | 10
1405-003 | Apr-Sep YTD MIE Cost PPPL | 168070 | 168070 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1405 | R | 0000 | 54 | 1 |  |  | 0 | 100
MCWF-091 | C2-MTM - machining/inspection | 169040 | 169040 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 32 |  |  |  | 10 | 100
53-30 | Coding, Configuration, Testing (Title III) | 0 | 169891.87 |  | 169891.87 | 16% | 27182.6992 | 5 | 53 | 530 | 9450 | 5301 | F |  |  | 1 |  |  | 16
0191-5 | LOE-FY05 WBS 191 | 170500 | 170500 |  | 0 | 10% | 0 | 1 | 19 | 191 | 9450 | 1901 | 2 | 191 | 02 | 1 |  |  | 10 | LOE
740.030 | Deliver 3-D Scanner & Romer Arm | 171990 | 171990 |  | 0 | 24% | 0 | 1 | 18 | 187 | 9450 | 1804 | T | MEAS | 00 | 1 |  | 18 | 24 | 100
151-011 | Final Design Cryostat WBS 171 | 0 | 172404.27 |  | 172404.27 | 28% | 48273.1956 | 1 | 17 | 171 | 9450 | 1701 | 2 | CRYO | 18 | 1 |  | 17 | 28
VVSA-301 | 1st 60 deg segment | 175000 | 175000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 10 |  |  |  | 5 | 100
VVSA-311 | 2nd 60 deg segment | 175000 | 175000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS6 | 10 |  |  |  | 5 | 100
VVSA-401 | 60 deg segment | 175000 | 175000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 10 |  |  |  | 5 | 100
VVSA-411 | 60 deg segment | 175000 | 175000 |  | 0 | 10% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS7 | 10 |  |  |  | 10 | 100
FY05CV-40 | FY05 unrecoverable cost variance | 178000 | 178000 |  | 0 | 0% | 0 | 7 | 74 | 740 | 9450 | 7401
FY05CV-27 | FY05 unrecoverable cost variance | 178000 | 178000 |  | 0 | 0% | 0 | 1 | 17 | 171 | 9450 | 1701 |  | 0000
820.150 | Apr-Sept MIE Cost PPPL | 178750 | 178750 |  | 0 | 0% | 0 | 8 | 82 | 820 | 9450 | 8203 | 2 | 0000 |  | 1 |  |  | 0 | 100
1202-425 | RW-PVVS Complete Fabrication (3.2.2) | 183532.44 | 183532.44 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12R | 46 | 1 |  |  | 40 | 100
820.04X | Proj engr FY07 | 0 | 184262.96 |  | 184262.96 | 5% | 9213.148 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5
8205FY06 | Systems Engineering Support FY06 | 90122.6981 | 184677.66 |  | 94554.9619 | 5% | 4727.7481 | 8 | 82 | 820 | 9450 | 8202 | F |  | 21 | 1 |  |  | 5 | LOE
0191-6 | LOE-FY06 WBS 191 | 90929.3 | 185570 |  | 94640.7 | 10% | 9464.07 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
52-30 | Installation, Testing, Documentation (Title III) | 0 | 185945.46 |  | 185945.46 | 10% | 18594.546 | 5 | 52 | 520 | 9450 | 5201 | F |  |  | 1 |  |  | 10
0192-5 | LOE-FY05 WBS 192 | 186000 | 186000 |  | 0 | 10% | 0 | 1 | 19 | 192 | 9450 | 1901 | 2 | 192 | 07 | 1 |  |  | 10 | LOE
1203-151 | Update VVSA Drawings incl ECP6 add'l port config | 186960.83 | 186960.83 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1203 | 2 | 05FD | 00 | 1 |  |  | 40 | 100
1901-002 | Apr-Sept MIE Costs ORNL | 187090 | 187090 |  | 0 | 0% | 0 | 1 | 19 | 191 | 9450 | 1901 | 1 | 0000 | 01 | 1 |  |  | 0 | 100
0191-6X | LOE-FY07 WBS 191 | 0 | 189090 |  | 189090 | 10% | 18909 | 1 | 19 | 191 | 9450 | 1901 | F | 191 | 02 | 1 |  |  | 10 | LOE
820.004Z | Proj engr FY08 | 0 | 189225.4 |  | 189225.4 | 5% | 9461.27 | 8 | 82 | 820 | 9450 | 8202 | F |  | 21 | 1 |  |  | 5
1803-7.10 | Tom Brown Engineering | 92416.1126 | 189377.28 |  | 96961.1674 | 40% | 38784.4669 | 1 | 18 | 186 | 9450 | 1803 | F | 7.00 | 17 | 1 |  |  | 40 | LOE
810.002 | Project Management Office PPPL FY04 | 189794.8 | 189794.8 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
163-037 | CS Support Structure Procurement/Fab | 0 | 198598.28 |  | 198598.28 | 32% | 63551.4496 | 1 | 13 | 132 | 9450 | 1353 | T | 132A | 23 | 1 |  | 13 | 32
8205FY05 | System Engr Support FY05 | 199622 | 199622 |  | 0 | 5% | 0 | 8 | 82 | 820 | 9450 | 8202 | 2 |  | 21 | 1 |  |  | 5 | LOE
181.122 | PPPL EM LOE FY08 | 0 | 200288 |  | 200288 | 24% | 48069.12 | 1 | 18 | 181 | 9450 | 1802 | F | A | 43 | 1 |  |  | 24
181.120 | PPPL EM LOE FY06 | 79313.4623 | 204416.14 |  | 125102.6777 | 24% | 30024.6426 | 1 | 18 | 181 | 9450 | 1802 | F | A | 41 | 1 |  |  | 24 | LOE
920.001 | Procedure and Document Preparation | 0 | 205870.07 |  | 205870.07 | 20% | 41174.014 | 8 | 85 | 850 | 9450 | 8501 | S |  | 05 | 1 |  |  | 20
920.000 | Startup Personnel | 0 | 207251.72 |  | 207251.72 | 30% | 62175.516 | 8 | 85 | 850 | 9450 | 8501 | S |  | 10 | 1 |  |  | 30
810.003 | Project Management Office PPPL FY05 | 207624.42 | 207624.42 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
840.201 | Apr-Sept MIE Cost PPPL | 210270 | 210270 |  | 0 | 0% | 0 | 8 | 84 | 840 | 9450 | 8401 | P | 0000 |  | 1 |  | 8400 | 0 | 100
VVSA-051 | Procure Die Materials (4 sets) | 215000 | 215000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS2 | 11 |  |  |  | 5 | 100
121-035 | VVSA Contract oversight FY05 & FY06 | 215025.25 | 215025.25 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1250 | F |  | 08 | 1 |  |  | 40 | LOE
810.900 | Project Management Office PPPL FY08 | 0 | 215806.5 |  | 215806.5 | 5% | 10790.325 | 8 | 81 | 810 | 9450 | 8101 | S |  | 10 | 1 |  | STRO | 5
820.002 | LOE FY04 | 219121.5 | 219121.5 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | FY04 | 10 | 1 |  |  | 17 | LOE
VVSA-171 | Procure Materials | 220000 | 220000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS4 | 11 |  |  |  | 5 | 100
8204FY06 | Systems Analysis FY06 | 109998.9576 | 225407.7 |  | 115408.7424 | 5% | 5770.4371 | 8 | 82 | 820 | 9450 | 8204 | F |  | 20 | 1 |  |  | 5 | LOE
820.002 | LOE FY04 | 226651.5 | 226651.5 |  | 0 | 17% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | FY04 | 10 | 1 |  |  | 17 | LOE
PPC-2 | Lawton mold Assy | 227630 | 227630 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | P | 14E | 15 |  | C |  | 40 | 100
1408-145 | Copper Conductor -Delivery #2 PE005371 | 228056.43 | 228056.43 |  | 0 | 10% | 0 | 1 | 14 | 142 | 9450 | 1408 | T | COPP | 99 | 1 |  | 141 | 10 | 100
1407ECP36 | ECP36 job closeout cost variance | 230000 | 230000 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1412 | R | FIX | 25 | 1 |  | 141 | 34 | 100
171-040 | Winding Oversight (LOE) | 55201.1391 | 238965.97 |  | 183764.8309 | 30% | 55129.4493 | 1 | 14 | 142 | 9450 | 1451 | F | LABR | 11 | 1 |  |  | 30 | LOE
VVSA-081 | Inspection | 239000 | 239000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS2 | 13 |  |  |  | 5 | 100
1406-299 | Closeout cost for testing ECP-21 | 239000 | 239000 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-2 | 20 | 1 |  |  | 40 | 100
VVSA-241 | Production Panels Period #2 LOT 5 | 240000 | 240000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS5 | 15 |  |  |  | 5 | 100
VVSA-251 | Production Panels Period #3 LOT 6 | 240000 | 240000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS5 | 17 |  |  |  | 5 | 100
810.004 | Project Management Office PPPL FY06 | 120488.8006 | 246903.28 |  | 126414.4794 | 5% | 6320.724 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5 | LOE
810.005 | Project Management OfficePPPL FY07 | 0 | 252300.16 |  | 252300.16 | 5% | 12615.008 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5
MCWF-021 | Pattern B complete | 255120 | 255120 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 20 |  |  |  | 10 | 100
8204FY05 | Systems Analysis FY05 | 256633.25 | 256633.25 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8204 | 2 |  | 20 | 1 |  |  | 10 | LOE
1404-105 | EIO-FY04 Cost Through June 30,2004 ECP 11 | 258290 | 258290 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14E | 09 | 1 |  |  | 40 | 100
VVSA-231 | Production Panels Period #1 LOT 4 | 260000 | 260000 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS5 | 13 |  |  |  | 5 | 100
181.121 | PPPL EM LOE FY07 | 0 | 260099.1 |  | 260099.1 | 24% | 62423.784 | 1 | 18 | 181 | 9450 | 1802 | F | A | 42 | 1 |  |  | 24
99.04 | PPPL Allocations FY04 | 260691 | 260691 |  | 0 | 10% | 0 | A | AA | AAA | 9450 | 8998 | A | FY04 |  | 1 |  |  | 10 | LOE
1352-100 | Material & leads | 0 | 264140 |  | 264140 | 24% | 63393.6 | 1 | 13 | 132 | 9450 | 1352 | T | 13P | 30 | 1 |  | 13 | 24
1351-85D | Vendor Fab TF Castings | 0 | 264924 |  | 264924 | 24% | 63581.76 | 1 | 13 | 131 | 9450 | 1351 | 1 | 13E | 39 | 1 | C |  | 24
1407-001 | Apr-Sep YTD MIE Cost PPPL | 267550 | 267550 |  | 0 | 0% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 0000 | 54 | 1 |  |  | 0 | 100
0192-6 | LOE-FY06 WBS 192 | 132260.8 | 269920 |  | 137659.2 | 10% | 13765.92 | 1 | 19 | 192 | 9450 | 1901 | F | 192 | 07 | 1 |  |  | 10 | LOE
820.004 | Proj engr FY06 | 131913.8078 | 270315.18 |  | 138401.3722 | 5% | 6920.0686 | 8 | 82 | 820 | 9450 | 8202 | F |  | 20 | 1 |  |  | 5 | LOE
820.003 | Proj engr FY05 | 271010 | 271010 |  | 0 | 10% | 0 | 8 | 82 | 820 | 9450 | 8202 | 2 |  | 20 | 1 |  |  | 10 | LOE
FY05CV-23 | FY05 unrecoverable cost variance | 275000 | 275000 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1411 |  | 14T
920.001 | Procedure and Document Preparation | 0 | 278652.32 |  | 278652.32 | 20% | 55730.464 | 8 | 85 | 850 | 9450 | 8501 | S |  | 05 | 1 |  |  | 20
1202-325 | MT-PVVS Complete Fabrication (3.2.2) [A/ 1] | 290115.28 | 290115.28 |  | 0 | 40% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 40 | 100
1406-049 | Increased cost of FDR support ECP 11 | 292000 | 292000 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 14-0 | 59 | 1 |  |  | 40 | 100
MCWF-031 | Major Tool Tooling Complete | 293000 | 293000 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 20 |  |  |  | 10 | 100
820.110 | Apr-Sept MIE Cost PPPL | 295530 | 295530 |  | 0 | 0% | 0 | 8 | 82 | 820 | 9450 | 8202 | P | 0000 |  | 1 |  |  | 0 | 100
161-037 | Machine Base&supports Procurement [A/1] | 0 | 297136.83 |  | 297136.83 | 32% | 95083.7856 | 1 | 17 | 172 | 9450 | 1752 | T | 172 | 20 | 1 |  | 17 | 32
810.900 | Project Management Office PPPL FY08 | 0 | 302418.64 |  | 302418.64 | 5% | 15120.932 | 8 | 81 | 810 | 9450 | 8101 | S |  | 10 | 1 |  | STRO | 5
99.05 | PPPL Allocations FY05 | 302697 | 302697 |  | 0 | 10% | 0 | A | AA | AAA | 9450 | 8998 | A |  |  | 1 |  |  | 10 | LOE
1401-002 | Apr-Sept MIE Cost ORNL | 303040 | 303040 |  | 0 | 0% | 0 | 1 | 14 | 141 | 9450 | 1401 | 1 | 0000 | 54 | 1 |  |  | 0 | 100
1406-01603 | ECP-36 job closeout cost variance | 305000 | 305000 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 00 | 1 | C | 141 | 40 | 100
171-041 | Tech Supervision | 71073.8421 | 307678.97 |  | 236605.1279 | 30% | 70981.5384 | 1 | 14 | 142 | 9450 | 1451 | F | LABR | 13 | 1 |  |  | 30 | LOE
1404-105 | EIO-FY04 Cost Through June 30,2004 ECP 11 | 313047.28 | 313047.28 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14E | 09 | 1 |  |  | 40 | 100
132-037 | Coil Leads Procurement WBS 162 | 0 | 314186.1 |  | 314186.1 | 22% | 69120.942 | 1 | 16 | 162 | 9450 | 1601 | T | 162 | 01 | 1 |  | 16 | 22
810.002 | Project Management Office PPPL FY04 | 314964.9 | 314964.9 |  | 0 | 17% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | FY04 | 05 | 1 |  |  | 17 | LOE
1201-002 | Apr-Sept MIE Cost ORNL | 319050 | 319050 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1201 | 1 | 0000 | 10 | 1 |  |  | 0 | 100
1404-100 | EIO-Cost FY03 | 323952.72 | 323952.72 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14E | 09 | 1 |  |  | 40 | 100
162-037 | WBS 151Coil Support Struc Procurement [A/1] | 0 | 324678.02 |  | 324678.02 | 32% | 103896.9664 | 1 | 15 | 151 | 9450 | 1550 | T |  | 15 | 1 |  | 15 | 32
99.06 | PPPL Allocations FY06 | 160925.076 | 329764.5 |  | 168839.424 | 10% | 16883.9424 | A | AA | AAA | 9450 | 8998 | A |  |  | 1 |  |  | 10 | LOE
7501-05 | Construction Support Crew during machine assy | 0 | 332651.29 |  | 332651.29 | 24% | 79836.3096 | 7 | 75 | 750 | 9450 | 7501 | F |  |  | 1 |  |  | 24
810.003 | Project Management Office PPPL FY05 | 332783.12 | 332783.12 |  | 0 | 10% | 0 | 8 | 81 | 810 | 9450 | 8101 | P |  | 05 | 1 |  |  | 10 | LOE
99.07 | PPPL Allocations FY07 | 0 | 332787.3 |  | 332787.3 | 10% | 33278.73 | A | AA | AAA | 9450 | 8998 | A |  |  | 1 |  |  | 10
MCWF-031 | Major Tool Tooling Complete | 335622 | 335622 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 20 |  |  |  | 10 | 100
810.004 | Project Management Office PPPL FY06 | 170750.4192 | 349898.4 |  | 179147.9808 | 5% | 8957.399 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5 | LOE
1403-03 | Increase for actual cost of Final Design ECP 11 | 357000 | 357000 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1403 | 2 | DW06 | 01 | 1 |  |  | 40 | 100
810.005 | Project Management OfficePPPL FY07 | 0 | 357533.64 |  | 357533.64 | 5% | 17876.682 | 8 | 81 | 810 | 9450 | 8101 | F |  | 05 | 1 |  |  | 5
VVSA-221 | Procure Vessel Material | 371490 | 371490 |  | 0 | 5% | 0 | 1 | 12 | 121 | 9450 | 1250 | T | VVS5 | 11 |  |  |  | 5 | 100
714.030 | LOE FY07 thru first plasma | 0 | 372900.52 |  | 372900.52 | 15% | 55935.078 | 7 | 74 | 742 | 9450 | 7401 | F | P1 | 11 | 1 |  |  | 15
810.001 | Apr-Sept MIE Cost PPPL | 387340 | 387340 |  | 0 | 0% | 0 | 8 | 81 | 810 | 9450 | 8101 | P | 0000 |  | 1 |  |  | 0 | 100
1202-324 | MT-PVVS Begin Fabrication (3.2.2) | 388595.48 | 388595.48 |  | 0 | 0% | 0 | 1 | 12 | 121 | 9450 | 1202 | T | 12M | 40 | 1 |  |  | 0 | 100
1406-01601 | ECP-29 | 400000 | 400000 |  | 0 | 40% | 0 | 1 | 14 | 142 | 9450 | 1410 | R | 14-4 | 00 | 1 | C | 141 | 40 | 100
1409-ECP36 | ECP36 job closeout cost variance | 406000 | 406000 |  | 0 | 34% | 0 | 1 | 14 | 144 | 9450 | 1409 | R | 14-9 | 99 | 1 | C | 141 | 34 | 100
FY05CV-11 | FY05 unrecoverable cost variance | 410000 | 410000 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1403 |  | 0000 | [5 empty] | 100
1404-205 | JPP-FY04 Cost Through June 30,2004 ECP 11 | 417120.34 | 417120.34 |  | 0 | 40% | 0 | 1 | 14 | 141 | 9450 | 1404 | T | 14J | 09 | 1 |  |  | 40 | 100
171-040 | Winding Oversight (LOE) | 96498.2334 | 417741.27 |  | 321243.0366 | 30% | 96372.911 | 1 | 14 | 142 | 9450 | 1451 | F | LABR | 11 | 1 |  |  | 30 | LOE
1421-110 | Deliver - Assy bolts,nuts,washers | 0 | 449000 |  | 449000 | 40% | 179600 | 1 | 14 | 142 | 9450 | 1421 | T |  | 25 | 1 | C | 141 | 40
VVSA-611 | PPPL Receive Tooling | 0 | 486000 |  | 486000 | 10% | 48600 | 1 | 12 | 121 | 9450 | 1250 | T | VVS9 | 11 |  |  |  | 10
151-037 | Cryostat Procurement [A/1] | 0 | 503650.35 |  | 503650.35 | 28% | 141022.098 | 1 | 17 | 171 | 9450 | 1751 | T | 171 | 20 | 1 |  | 17 | 28
714.030 | LOE FY07 thru first plasma | 0 | 504720.43 |  | 504720.43 | 15% | 75708.0645 | 7 | 74 | 742 | 9450 | 7401 | F | P1 | 11 | 1 |  |  | 15
1407-ECP16 | ecp16 | 507000 | 507000 |  | 0 | 0% | 0 | 1 | 14 | 144 | 9450 | 1407 | R | 0000 | 54 | 1 |  |  | 0 | 100
7501-05 | Construction Support Crew during machine assy | 0 | 528482.4 |  | 528482.4 | 24% | 126835.776 | 7 | 75 | 750 | 9450 | 7501 | F |  |  | 1 |  |  | 24
162-037 | WBS 151Coil Support Struc Procurement [A/1] | 0 | 685568.27 |  | 685568.27 | 32% | 219381.8464 | 1 | 15 | 151 | 9450 | 1550 | T |  | 15 | 1 |  | 15 | 32
MCWF-041 | Materials (MetalTek) | 744750 | 744750 |  | 0 | 10% | 0 | 1 | 14 | 141 | 9450 | 1411 | P |  | 20 |  |  |  | 10 | 100
1406-0003 | Apr-Sep YTD MIE Cost PPPL | 831120 | 831120 |  | 0 | 0% | 0 | 1 | 14 | 142 | 9450 | 1406 | R | 0000 | 54 | 1 |  |  | 0 | 100
MCWF-001 | EIO Project Mgt. & Reporting | 682500 | 910000 |  | 227500 | 10% | 22750 | 1 | 14 | 141 | 9450 | 1411 | P |  | 15 |  |  |  | 10 | LOE
|  |  | 0 | 424495 |  | 0% | 0 | 1 | 12 |  |  | 1201
|  |  |  | 1770580 |  | 0% | 0 | 1 | 12 |  |  | 1202
|  |  |  | 1119389 |  | 0% | 0 | 1 | 12 |  |  | 1203
|  |  |  | 95398 |  | 0% | 0 | 1 | 12 |  |  | 1204
|  |  |  | 15954 |  | 0% | 0 | 1 | 12 |  |  | 1206
|  |  |  | 4614203 |  | 0% | 0 | 1 | 12 |  |  | 1250
|  |  |  | 964415 |  | 0% | 0 | 1 | 13 |  |  | 1301
|  |  |  | 2328 |  | 0% | 0 | 1 | 13 |  |  | 1302
|  |  |  | 81499 |  | 0% | 0 | 1 | 13 |  |  | 1303
|  |  |  | 545444 |  | 0% | 0 | 1 | 13 |  |  | 1350
|  |  |  | 424000 |  | 0% | 0 | 1 | 13 |  |  | 1351
|  |  |  | 80609 |  | 0% | 0 | 1 | 13 |  |  | 1361
|  |  |  | 304356 |  | 0% | 0 | 1 | 14 |  |  | 1401
|  |  |  | 239140 |  | 0% | 0 | 1 | 14 |  |  | 1402
|  |  |  | 3431690 |  | 0% | 0 | 1 | 14 |  |  | 1403
|  |  |  | 2543679 |  | 0% | 0 | 1 | 14 |  |  | 1404
|  |  |  | 168000 |  | 0% | 0 | 1 | 14 |  |  | 1405
|  |  |  | 2263565 |  | 0% | 0 | 1 | 14 |  |  | 1406
|  |  |  | 2571368 |  | 0% | 0 | 1 | 14 |  |  | 1407
|  |  |  | 1156321 |  | 0% | 0 | 1 | 14 |  |  | 1408
|  |  |  | 861721 |  | 0% | 0 | 1 | 14 |  |  | 1409
|  |  |  | 1049967 |  | 0% | 0 | 1 | 14 |  |  | 1410
|  |  |  | 6164980 |  | 0% | 0 | 1 | 14 |  |  | 1411
|  |  |  | 540987 |  | 0% | 0 | 1 | 14 |  |  | 1412
|  |  |  | 27819 |  | 0% | 0 | 1 | 14 |  |  | 1413
|  |  |  | 345839 |  | 0% | 0 | 1 | 14 |  |  | 1414
|  |  |  | 24038 |  | 0% | 0 | 1 | 14 |  |  | 1415
|  |  |  | 208505 |  | 0% | 0 | 1 | 14 |  |  | 1416
|  |  |  | 55216 |  | 0% | 0 | 1 | 14 |  |  | 1419
|  |  |  | 1328037 |  | 0% | 0 | 1 | 14 |  |  | 1451
|  |  |  | 102096 |  | 0% | 0 | 1 | 14 |  |  | 1459
|  |  |  | 82401 |  | 0% | 0 | 1 | 15 |  |  | 1501
|  |  |  | 2792 |  | 0% | 0 | 1 | 16 |  |  | 1601
|  |  |  | 414775 |  | 0% | 0 | 1 | 17 |  |  | 1701
|  |  |  | 64685 |  | 0% | 0 | 1 | 18 |  |  | 1801
|  |  |  | 504658 |  | 0% | 0 | 1 | 18 |  |  | 1802
|  |  |  | 663923 |  | 0% | 0 | 1 | 18 |  |  | 1803
|  |  |  | 532184 |  | 0% | 0 | 1 | 18 |  |  | 1804
|  |  |  | 10198 |  | 0% | 0 | 1 | 18 |  |  | 1810
|  |  |  | 1746366 |  | 0% | 0 | 1 | 19 |  |  | 1901
|  |  |  | 62893 |  | 0% | 0 | 2 | 20 |  |  | 2001
|  |  |  | 285016 |  | 0% | 0 | 2 | 25 |  |  | 2501
|  |  |  | 375656 |  | 0% | 0 | 3 | 31 |  |  | 3101
|  |  |  | 302859 |  | 0% | 0 | 3 | 39 |  |  | 3901
|  |  |  | 107351 |  | 0% | 0 | 4 | 41 |  |  | 4101
|  |  |  | 384666 |  | 0% | 0 | 4 | 43 |  |  | 4301
|  |  |  | 81687 |  | 0% | 0 | 4 | 44 |  |  | 4401
|  |  |  | 138294 |  | 0% | 0 | 4 | 45 |  |  | 4501
|  |  |  | 1300 |  | 0% | 0 | 4 | 46 |  |  | 4601
|  |  |  | 33022 |  | 0% | 0 | 5 | 58 |  |  | 5801
|  |  |  | 14873 |  | 0% | 0 | 6 | 61 |  |  | 6163
|  |  |  | 9370 |  | 0% | 0 | 6 | 65 |  |  | 6501
|  |  |  | 32635 |  | 0% | 0 | 7 | 71 |  |  | 7101
|  |  |  | 75940 |  | 0% | 0 | 7 | 73 |  |  | 7301
|  |  |  | 833041 |  | 0% | 0 | 7 | 74 |  |  | 7401
|  |  |  | 2292540 |  | 0% | 0 | 8 | 81 |  |  | 8101
|  |  |  | 345795 |  | 0% | 0 | 8 | 81 |  |  | 8102
|  |  |  | 988459 |  | 0% | 0 | 8 | 81 |  |  | 8998
|  |  |  | 1965095 |  | 0% | 0 | 8 | 82 |  |  | 8202
|  |  |  | 750990 |  | 0% | 0 | 8 | 82 |  |  | 8203
|  |  |  | 750967 |  | 0% | 0 | 8 | 82 |  |  | 8204
|  |  |  | 181945 |  | 0% | 0 | 8 | 82 |  |  | 8205
|  |  |  | 323549 |  | 0% | 0 | 8 | 84 |  |  | 8401
|  |  |  | 146467 |  | 0% | 0 | 8 | 84 |  |  | 8402
|  |  |  | 75000 |  | 0% | 0 | dcma | dcma |  |  | dcma
|  | 46350558.4652 | 83605438.46 | 48107030 | 37254879.9948 |  | 8355856.4142
8720000
75000
92400438.46
48107030