## RiskOpportunities
| Risk |  | Opportunity
Modular Coil Winding Operations | 661 | Re-evaluate in 3rd quarter with experience gained winding first 3 coils. | -445 | Process improvement studies challenge to reduce hours by 10%.
TF Coil Winding Operations | 448.1 | Winding Operations in FY07 & FY08 to be re-evaluated after first coil is fabricated. | -82 | Process improvement studies challenge to reduce hours by 10%.
TF,PF Coil and Structure |  |  | ~($1,000) | Chinese Fusion Laboratory
Field Period & Machine Assembly |  |  | -404 | Two shift field period assy and final machine assy. Accelerates first plasma by 2 months.
| 1109.1 |  | -1931

## Budget Reconciliation
Proposed PMB Updates
| wbs 12 | 1203 | Vacuum Vessel Design incl Title III | 204.3 | Redesign of insulation scheme and cooling tubes
| wbs 12 | 1204 | VV Hardware | -97.8 | Cheaper tubes and insulation
| wbs 131 | 135x | TF Coil fabrication | 432.3 | Facility, Material and winding operation
| wbs 132 | 1352 | PF Coil design/fab | -466 | Use NSTX PF1a coil for central solenoid
| wbs 133 | 1354 | Trim Coils | -154 | Simplify design of trim coils
| wbs 14 | 1416 | Modular Coil Design for Type A & B incl interface hardware | 520.4 | re-estimated based on Type C experience
| wbs 14 | 1451 | Modular Coil Winding -Operations | -16.5 | Increased time for ground wrap, interlacing and shift differential offset by supervision and oversight reduction due to shorten schedule.
| wbs 14 | 1421 | Modular coil-to-coil interface hardware | 655.1 | Underestimated cost of shims and high strength bolts
| wbs 14 | 1411 | MCWF Title III | 68.5 | Req'd oversight of contract
| wbs 18 | 1803 | Eliminated 350C bakeout of field period assy | -40
| wbs 18 | 1803 | Field Period Tooling and Fixturing | -50 | Only 1 set of fixtures req'd
| wbs 31 | 3101 | Magnetic Diagnostics | 61.7 | Saddle loops and termination box design/fab
| wbs 38 | 3801 | E-beam mapping | -103.9 | Simplified application
| wbs 81 | 8101 | Project Management | -53.9 | Revised FY09 ETC Reqmnt
| wbs 82 | 8205 | Dimensional control | 84 | Coordination of metrology and design integration
| wbs 5x | 5x01 | Plasma Control | -100 | Simplified Plasma Control
| Other |  | re-scheduling and laboratory rate changes | -180
764.2
Unrecoverable Cost Variances
| wbs 13 | 1301 | TF Design | 119 | TF Design iterations
| wbs 13 | 1350/1351 | TF Fabrication facilities | 149 | Design time plus materials. Electrical sys debugging.
| wbs 14 | 1403 | Modular Coil Type C detail design | 409 | Iterative process in conjunction with TRC fabrication.
| wbs 14 | 1414/1409 | Coil test facility fabrication and TRC testing | 150 | Cryogenic systems debugging and design. Safety design safeguards.
| wbs 14 | 1411 | MCWF 1st production casting | 137 | (part of prototype contract)
| wbs 14 | 1411 | MCWF contract oversight | 110 | Working with EIO addressing technical reqmnts and schedule.
| wbs 17 | 1701 | Cryostat & base support structure prel dsn | 178 | Designer and engineering time underestimated
| wbs 74 | 7401 | Test cell electrical power supply | 178 | House power for test cell.
| wbs 4 | 4x01 | Electrical pwr sys DC sys & coil protection | 68 | DC systems engineering.
| Other |  |  | 95
1593
2357.2

## EC36 vs EC38 job comparision
ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 |  | ecp36 | ecp36 | ecp38 - 36
JJJJ | ACT CODE | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL
| 1101 | 0.1 | [6 empty] | 0.1 | 1101 | 1101 | 0.06 | 0.04
| 1201 | 424.4 | [6 empty] | 424.4 | 1201 | 1201 | 424.42 | -0.02 | 204.34 | vv dsn | 6
| 1202 | 793 | 998.2 | [5 empty] | 1791.2 | 1202 | 1202 | 1791.18 | 0.02
| 1203 |  | 624.8 | 315.1 | 155.3 |  |  |  | 1095.2 | 1203 | 1203 | 943.53 | 151.67
| 1204 |  |  |  | 187.4 | 182.6 | 89.4 |  | 459.4 | 1204 | 1204 | 557.24 | -97.84 | vv hw |  | 8
| 1206 |  | 3.4 | 14.2 |  |  |  |  | 17.6 | 1206 | 1206 | 17.64 | -0.04
| 1250 |  | 36.9 | 3041.9 | 2627.7 | 12.2 |  |  | 5718.7 | 1250 | 1250 | 5665.99 | 52.71
| 1301 | 91.7 | 333.9 | 397.9 |  |  |  |  | 823.5 | 1301 | 1301 | 837.4 | -13.9
| 1302 |  |  | 20.5 | 12.5 | 219.1 |  |  | 252.1 | 1302 | 1302 | 253.18 | -1.08
| 1350 |  |  | 256 | 377.9 |  |  |  | 633.9 | 1350 | 1350 | 399.59 | 234.31
| 1351 |  |  | 165.9 | 631.3 | 53.3 | 5.9 |  | 856.4 | 1351 | 1351 | 1318.24 | -461.84
| 1352 |  |  |  | 1.3 | 10.1 | 884.5 |  | 895.9 | 1352 | 1352 | 1361.87 | -465.97 | pf1a |  | 23
| 1353 |  |  |  |  | 82.4 | 183.4 |  | 265.8 | 1353 | 1353 | 270.3 | -4.5
| 1354 |  |  |  |  | 103.4 |  |  | 103.4 | 1354 | 1354 | 257.67 | -154.27 | trim coils |  | 24
| 1355 |  |  |  |  | 70.7 | 20.5 |  | 91.2 | 1355 | 1355 | 91.87 | -0.67
| 1361 |  |  |  | 254.9 | 378 | 26.9 |  | 659.8 | 1361 |  |  | 659.8 | 432.27 | tf | 10
| 1401 | 303 | [6 empty] | 303 | 1401 | 1401 | 303.04 | -0.04
| 1402 | 239.1 | [6 empty] | 239.1 | 1402 | 1402 | 239.14 | -0.04
| 1403 |  | 1798.7 | 863.1 | 84.4 |  |  |  | 2746.2 | 1403 | 1403 | 3148.64 | -402.44 | 520.36 | mc dsn | 5
| 1404 | 586 | 1625.8 | 321.6 |  |  |  |  | 2533.4 | 1404 | 1404 | 2533.52 | -0.12
| 1405 | 168.1 | [6 empty] | 168.1 | 1405 | 1405 | 168.07 | 0.03
| 1406 | 831.1 | 1266.5 | 116 |  |  |  |  | 2213.6 | 1406 | 1406 | 2213.59 | 0.01
| 1407 | 267.6 | 2236.3 | 19.2 |  |  |  |  | 2523.1 | 1407 | 1407 | 2522.99 | 0.11
| 1408 | 29.8 | 2.5 | 506.9 | 1065.6 | 166.8 | 6.8 |  | 1778.4 | 1408 | 1408 | 1852.61 | -74.21
| 1409 |  | 363.8 | 490.1 |  |  |  |  | 853.9 | 1409 | 1409 | 853.95 | -0.05
| 1410 |  |  | 1080.2 |  |  |  |  | 1080.2 | 1410 | 1410 | 1080.21 | -0.01
| 1411 |  | 20.4 | 3748.7 | 4102.5 | 564 |  |  | 8435.6 | 1411 | 1411 | 8367.06 | 68.54 | mcwf title iii |  | 18
| 1412 |  |  | 540.4 |  |  |  |  | 540.4 | 1412 | 1412 | 540.44 | -0.04
| 1413 |  |  | 23.2 |  |  |  |  | 23.2 | 1413 | 1413 | 23.17 | 0.03
| 1414 |  |  | 46 | 129.8 | 31 |  |  | 206.8 | 1414 | 1414 | 169.94 | 36.86
| 1415 |  |  | 14.8 |  |  |  |  | 14.8 | 1415 | 1415 | 14.85 | -0.05
| 1416 |  |  | 65.1 | 684.4 |  |  |  | 749.5 | 1416 |  |  | 749.5
| 1421d |  |  | 65.8 | 107.5 |  |  |  | 173.3 |  |  |  | 173.3
| 1421h |  |  |  |  | 655.097 |  |  | 655.097 | 1421 |  |  | 655.097 |  | interface hw | 15
| 1451 |  |  | 56.9 | 2393.7 | 2536.8 | 80.3 |  | 5067.7 | 1451 | 1451 | 5082.4 | -14.7 |  | winding | 7
| 1501 |  | 34.6 | 44.3 | 130.6 |  |  |  | 209.5 | 1501 | 1501 | 221.48 | -11.98
| 1550 |  |  |  |  | 1173 | 4.7 |  | 1177.7 | 1550 | 1550 | 1191.47 | -13.77
| 1601 |  |  |  |  | 660 | 475 |  | 1135 | 1601 | 1601 | 1139.98 | -4.98
| 1701 | 12.2 | 80.9 | 100.1 | 5.5 | 304.4 |  |  | 503.1 | 1701 | 1701 | 504.49 | -1.39
| 1751 |  |  |  |  | 5.6 | 527.8 | 7.1 | 540.5 | 1751 | 1751 | 541.48 | -0.98
| 1752 |  |  |  |  | 308.1 | 3.3 |  | 311.4 | 1752 | 1752 | 314.97 | -3.57
| 1801 | 60.8 | [6 empty] | 60.8 | 1801 | 1801 | 60.8 | 0
| 1802 |  | 164.6 | 146.2 | 350.2 | 411.6 | 355.5 |  | 1428.1 | 1802 | 1802 | 1444.46 | -16.36
| 1803 |  |  | 615.9 | 464.2 | 107.6 | 10.4 |  | 1198.1 | 1803 | 1803 | 1219.66 | -21.56 | -50 | I set of fixture | 16
| 1804 |  | 198 | 171.6 | 79.1 | 11 | 11.1 | 11.6 | 482.4 | 1804 | 1804 | 501.77 | -19.37 | -40 | 350c bakeout | 9
| 1810 |  |  |  | 282.4 | 1174.1 | 676.5 |  | 2133 | 1810 | 1810 | 2203.28 | -70.28
| 1901 | 254.2 | 640.7 | 580.8 | 515.7 | 361.6 | 251.5 | 153.7 | 2758.2 | 1901 | 1901 | 2738.1 | 20.1
| 2001 | 63.7 | [6 empty] | 63.7 | 2001 | 2001 | 63.67 | 0.03
| 2101 |  |  |  |  | 52.7 | 35.4 |  | 88.1 | 2101 | 2101 | 86.54 | 1.56
| 2201 |  |  |  |  | 125.5 | 229.7 |  | 355.2 | 2201 | 2201 | 348.88 | 6.32
| 2501 | 123 | 161.4 | [5 empty] | 284.4 | 2501 | 2501 | 284.37 | 0.03
| 3101 |  |  | 100.2 | 307 | 65.7 | 15.2 |  | 488.1 | 3101 | 3101 | 426.36 | 61.74 | saddleloops and term boxes |  | 17
| 3601 |  |  |  |  | 5.7 | 39.9 |  | 45.6 | 3601 | 3601 | 45.96 | -0.36
| 3801 | [5 empty] | 206.2 |  | 206.2 | 3801 | 3801 | 310.09 | -103.89 | ebeam |  | 22
| 3901 | 155.5 | 65 | 66.4 | 70.5 |  |  |  | 357.4 | 3901 | 3901 | 360.52 | -3.12
| 4101 |  | 85.8 | 18.7 | 0.1 | 288 | 29.3 |  | 421.9 | 4101 | 4101 | 430.17 | -8.27
| 4301 |  |  | 156.9 | 38.4 | 214.5 |  |  | 409.8 | 4301 | 4301 | 453.94 | -44.14
| 4401 |  | 1.1 | 4.4 |  | 842.5 | 431.3 | 17.8 | 1297.1 | 4401 | 4401 | 1308.88 | -11.78
| 4501 | 112.3 | 29.9 | 47.5 | 129.2 | 350.4 | 437.7 |  | 1107 | 4501 | 4501 | 1106.78 | 0.22
| 4601 | 1.3 | [6 empty] | 1.3 | 4601 | 4601 | 1.3 | 0
| 5101 | [5 empty] | 280.4 |  | 280.4 | 5101 | 5101 | 282.69 | -2.29
| 5201 |  |  |  |  | 9.4 | 429.1 | 91.6 | 530.1 | 5201 | 5201 | 610.92 | -80.82 | -100 | plasama control | 20
| 5301 |  |  |  |  | 11.1 | 299.1 | 18.9 | 329.1 | 5301 | 5301 | 351.01 | -21.91
| 5401 | [5 empty] | 195.8 |  | 195.8 | 5401 | 5401 | 220.96 | -25.16
| 5501 | [5 empty] | 179.3 |  | 179.3 | 5501 | 5501 | 161.65 | 17.65
| 5601 | [5 empty] | 325.5 |  | 325.5 | 5601 | 5601 | 381.94 | -56.44
| 5801 | 11.9 | 16 | 12.5 |  |  |  |  | 40.4 | 5801 | 5801 | 40.36 | 0.04
| 6101 | [5 empty] | 92.3 |  | 92.3 | 6101 | 6101 | 94.51 | -2.21
| 6163 |  | 15 | [5 empty] | 15 | 6163 | 6163 | 15 | 0
| 6201 |  |  |  |  | 41.8 | 413.2 |  | 455 | 6201 | 6201 | 463.26 | -8.26
| 6301 | [5 empty] | 106.9 |  | 106.9 | 6301 | 6301 | 109.3 | -2.4
| 6501 | 9.4 | [6 empty] | 9.4 | 6501 | 6501 | 9.38 | 0.02
| 7101 | 32.2 | [6 empty] | 32.2 | 7101 | 7101 | 32.15 | 0.05
| 7201 |  |  |  |  | 9.1 |  |  | 9.1 | 7201 | 7201 | 8.02 | 1.08
| 7301 |  |  | 120.7 |  | 38.3 |  |  | 159 | 7301 | 7301 | 164.42 | -5.42
| 7401 | 164 | 238.2 | 213.6 | 17.6 | 188.5 | 496.1 | 257 | 1575 | 7401 | 7401 | 1564.76 | 10.24
| 7501 | [5 empty] | 831.3 | 232.1 | 1063.4 | 7501 | 7501 | 1054.34 | 9.06
| 7502 |  |  |  |  | 74.6 |  |  | 74.6 | 7502 | 7502 | 57.17 | 17.43
| 7503 | [5 empty] | 833.1 | 451.4 | 1284.5 | 7503 | 7503 | 1254.04 | 30.46
| 7601 | [5 empty] | 176.4 | 61.4 | 237.8 | 7601 | 7601 | 238.25 | -0.45
| 8101 | 387.3 | 873.1 | 696.1 | 634.6 | 662.1 | 554.5 | 132.3 | 3940 | 8101 | 8101 | 4110.21 | -170.21 | -53.91 | project mgmt
| 8102 | 58.6 | 88 | 95.4 | 173.6 | 50.5 | 36.7 |  | 502.8 | 8102 | 8102 | 386.5 | 116.3
| 8202 | 295.5 | 669.6 | 669.3 | 625.6 | 239.6 | 246 | 62.8 | 2808.4 | 8202 | 8202 | 2834.97 | -26.57 | 84.01 |  | 19
| 8203 | 178.8 | 372.6 | 171 | 140.2 | 132.5 | 0.5 |  | 995.6 | 8203 | 8203 | 1116.34 | -120.74 | wbs 82
| 8204 | 44.6 | 188.8 | 256.6 | 225.4 |  |  |  | 715.4 | 8204 | 8204 | 600.93 | 114.47
| 8205 |  |  | 109.5 | 189.3 | 73.8 | 76.1 |  | 448.7 | 8205 | 8205 | 331.85 | 116.85
| 8401 | 210.3 | 113.8 | [5 empty] | 324.1 | 8401 | 8401 | 324.5 | -0.4
| 8402 | 41 | 104.9 | [5 empty] | 145.9 | 8402 | 8402 | 145.86 | 0.04
| 8501 | [5 empty] | 365.1 | 834.2 | 1199.3 | 8501 | 8501 | 1189.18 | 10.12
| 8998 | 112 | 260.7 | 350.8 | 329.8 | 331.5 | 167.7 |  | 1552.5 | 8998 | 8998 | 1576.89 | -24.39
|  | 6062.5 | 13713.9 | 16918 | 17525.2 | 13390.297 | 11143.3 | 2331.9 | 81085.097 |  | CCCP | 11984 |  | 945.777
[11 empty] | DCMA | 75 |  | -205.24 | other
| cont |  |  |  | 1295.7 | 2518.3 | 4756.7 | 1051 | 9621.7 |  |  |  | 740.537 |  | o
| cv |  |  | 1593
|  | 6062.5 | 13713.9 | 18511 | 18820.9 | 15908.597 | 15900 | 3382.9 | 92299.797
| ba |  |  |  | 18830 | 15900 | 15900 | 3383
| cum plan | 6062.5 | 19776.4 | 38287.4 | 57108.3 | 73016.897 | 88916.897 | 92299.797 | 74 | 92373.797
| ba cum |  |  | 41243 | 57143 | 73043 | 88943 | 92326 | 75 | 92401
|  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL
[5 empty] | 42 | 44 | 38 | 11 | 135
[5 empty] | 1253.7 | 2474.3 | 4718.7 | 1040
[5 empty] | 57108.3 | 73016.897 | 88916.897 | 92299.797
[5 empty] | 9621.7 | 21.68%
|  |  |  | 38312.887 | 44390.697 |  |  |  | 82703.584
[8 empty] | dcma | 75
92400.284

## Contingency Analysis
| Proposed PMB | BCWR | Contingency | % | wayne | before | ECP36 %
12 - Vacuum Vessel Systems (wo/VVSA) | 4304.7 | 863 | 209 | 24.22% | 25.64% | 33.16% | 36% | 12 | 3245017.8509 | 525152.663 | 16.18%
VVSA Contract | 5134 | 2392 | 240 | 10.03% | 10% | 10%
13 - Conventional Coils | 4827.2 | 3316 | 1268.4 | 38.25% | 38.31% | 33.63% | 43% | 13 | 3309741.3526 | 1115143.3807 | 33.69%
14 - Modular Coils (wo/MCWF) | 23158.9 | 8086 | 2323.4 | 28.73% | 28.68% | 28.93% | 42% | 14 | 12601589.3299 | 2799408.4942 | 22.21%
MCWF Contract | 8192 | 4499 | 449.99 | 10% | 10% | 10%
15 - Structures | 1386.2 | 1308 | 391.108 | 29.9% | 29.92% | 31.88% |  | 15 | 1307049.946 | 417047.5191 | 31.91%
16 - Coil Services | 1135 | 1135 | 340.504 | 30% | 30% | 24.82% |  | 16 | 1135012.25 | 281714.5902 | 24.82%
17 - Cryostat and Base Support Struct | 1533.1 | 1162 | 346.769 | 29.84% | 30% | 29.17% |  | 17 | 1155896.5262 | 338949.1774 | 29.32%
18 - Field Period Assembly | 5280.3 | 3945 | 1178.6 | 29.88% | 29.87% | 35.79% | 42% | 18 | 3945762.16 | 1411742.832 | 35.78%
19 - Stellarator Core Mgt & Integr | 2767.2 | 1283 | 128.3 | 10% | 10% | 9.993% |  | 19 | 1282096.445 | 128209.6445 | 10%
1 Stellarator Core Systems | 57718.6 | 27989 | 6876.071 | 24.57% | 24.58% | 25.04% | 29% | 1 | 27982165.8607 | 7017368.3012 | 25.08%
2 Heating, Fueling & Vac Sys | 791.4 | 443.2497 | 62.055 | 14% | 14% | 14% |  | 21 | 88092.99 | 12333.0186
3 Diagnostics | 1149.3 | 744 | 175.716 | 23.62% | 25.84% | 27.92% | 31%
4 Electrical Power Sys | 3305.1 | 2779 | 548.806 | 19.75% | 19.47% | 19.75% |  | 22 | 355156.69 | 49721.9366
5 Central I&C Sys | 1873.6 | 1840 | 187.484 | 10.19% | 10.19% | 10.19% |  | 2 | 443249.68 | 62054.9552 | 14%
6 Facility Sys | 678.6 | 654 | 130.842 | 20.01% | 20% | 20.01% |  | 25 | 0 | 0
7 Test Cell Prep & MachAssy | 4563.1 | 3667 | 793.147 | 21.63% | 21.65% | 21.63%
8 Project Oversight & Support | 12634.3 | 6285 | 837.7 | 13.33% | 11.13% | 10.73% | 15% | 31 | 357766.5088 | 107329.9527
subtotal | 82714 | 44401.2497 | 9611.821 | 21.65% | 21.36% | 21.65% | 25%
Contingency | 9612 | [6 empty] | 36 | 45581.15 | 9116.23
TEC = | 92326
DCMA | 75 | [6 empty] | 38 | 206196.8 | 70106.912
92401
[8 empty] | 39 | 70515.03 | 21154.509
[8 empty] | 3 | 680059.4888 | 207707.6037 | 30.54%
[8 empty] | 41 | 314949.46 | 56690.9028
[8 empty] | 43 | 298006.764 | 53641.2175
[8 empty] | 44 | 1289552.6376 | 252769.5932
[8 empty] | 45 | 916464.64 | 185703.9856
[8 empty] | 46 | 0 | 0
[8 empty] | 4 | 2818973.5016 | 548805.6991 | 19.47%
[8 empty] | 51 | 280385.9 | 14019.295
[8 empty] | 52 | 530112.41 | 53011.241
[8 empty] | 53 | 329072.83 | 52651.6528
[8 empty] | 54 | 195823.11 | 27415.2354
[8 empty] | 55 | 179331.4 | 14346.512
[8 empty] | 56 | 325498.85 | 26039.908
[8 empty] | 57 | 0 | 0
[8 empty] | 58 | 0 | 0
VVSA Contract | 5134 | 2392 | 240 | 10.03% |  |  |  | 5 | 1840224.5 | 187483.8442 | 10.19%
|  |  |  | #DIV/0! |  |  |  | 61 | 92271.78 | 18454.356
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 62 | 455033.04 | 91006.608
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 63 | 106903.92 | 21380.784
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 64 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 65 | 0 | 0
MCWF Contract | 8192 | 4499 | 449.99 | 10% |  |  |  |  | 654208.74 | 130841.748 | 20%
|  |  |  | #DIV/0! |  |  |  | 71 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 72 | 9097.92 | 909.792
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 73 | 37599.901 | 3643.5385
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 74 | 956980.383 | 145873.4182
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 75 | 2422508.16 | 585652.9824
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 76 | 237778.59 | 57066.8616
WBS 12-18 | 41625.4 | 19815 | 6057.781 | 30.57% |  |  |  | 7 | 3663964.954 | 793146.5927 | 21.65%
|  |  |  | #DIV/0! |  |  |  | 81 | 2244301.07 | 112320.2535
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 82 | 2011860.24 | 168437.388
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 84 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | 85 | 1199387.27 | 310999.399
#DIV/0!
|  |  |  | #DIV/0! |  |  |  | AA | 828888.41 | 82888.841
WBS 2-7 & 85 (BOP) | 13560.1 | 11326.2497 | 2209.05 | 19.5% |  |  |  | 8 | 6284436.99 | 674645.8815 | 10.74%
WBS 19,81 & 82 | 14202.5 | 6369 | 655 | 10.28% |  |  |  | Total Sum of Contingency $ | 44367283.7151 | 9622054.6255 | 21.69%
| 82714 | 44401.2497 | 9611.821 | 21.65%

## LEHMAN WORKSHEET
WBS | WBS Title | Project Estimate | [5 empty] | DOE Assessment |  |  |  |  | Variance ($K) | Comments | Comment
|  | Base Cost ($K) | Base To Date | Base To Go | Contingency |  | Total ($K) | To Date | To Go | Contingency |  | Total ($K)
|  |  | Cost | Cost | % | $ |  | Cost | Cost | $ | %
1 | Stellarator Core Systems | 57728100 | 29727000 | 28001100 | 24.56% | 6878349 | 64606449
11 | In Vessel Components |  | 0 | 0 |  |  | 0
12 | Vacuum Vessel Systems | 9439300 | 6191000 | 3248300 | 13.91% | 451892 | 9891192
13 | Conventional Coils | 4831000 | 1515000 | 3316000 | 38.24% | 1267951 | 6098951
14 | Mod Coils | 31355900 | 18753000 | 12602900 | 22.01% | 2773324 | 34129224
15 | Coil Support Structures | 1386200 | 75000 | 1311200 | 29.83% | 391108 | 1777308
16 | Coil Services | 1135000 | 0 | 1135000 | 30% | 340504 | 1475504
17 | Cryostat & Base Support Structure | 1532900 | 372000 | 1160900 | 29.87% | 346769 | 1879669
18 | Field Period Assembly | 5280800 | 1336000 | 3944800 | 29.88% | 1178591 | 6459391
19 | Stellarator Core Mgmt. & Integration | 2767000 | 1485000 | 1282000 | 10% | 128210 | 2895210
2 | Plasma Heating Fueling & Vac Systems | 791300 | 347400 | 443900 | 13.98% | 62054.9552 | 853354.9552
21 | Fueling Systems | 88100 |  | 88100 | 14% | 12333.0186 | 100433.0186
22 | Torus Vacuum Pump | 418800 | 63000 | 355800 | 13.97% | 49721.9366 | 468521.9366
23 | Wall Conditioning System |  |  | 0 |  |  | 0
25 | Neutral Beam Injection System | 284400 | 284400 | 0 |  |  | 284400
3 | Diagnostics | 1148700 | 405000 | 743700 | 23.63% | 175717.142 | 1324417.142
31 | Magnetic Diagnostics | 551600 | 131000 | 420600 | 21.27% | 89442 | 641042
35 | Profile Diagnostics |  |  | 0 |  |  | 0
36 | Edge & Divertor Diagnostics | 45600 |  | 45600 | 19.99% | 9116.23 | 54716.23
38 | Electron Beam (EB) Mapping | 206200 |  | 206200 | 34% | 70106.912 | 276306.912
39 | Diagnostics Integration | 345300 | 274000 | 71300 | 9.891% | 7052 | 352352
4 | Electrical Power Systems | 3305100 | 527000 | 2778100 | 19.75% | 548805.6991 | 3853905.6991
41 | AC Power | 423900 | 107000 | 316900 | 17.89% | 56690.9028 | 480590.9028
42 | AC/DC Converter |  |  | 0 |  |  | 0
43 | DC Systems | 478800 | 226000 | 252800 | 21.22% | 53641.2175 | 532441.2175
44 | Control & protection system | 1346000 | 55000 | 1291000 | 19.58% | 252769.5932 | 1598769.5932
45 | Power System Design & Integration | 1055100 | 138000 | 917100 | 20.25% | 185703.9856 | 1240803.9856
46 | FCPC Building Modification | 1300 | 1000 | 300 | 0% |  | 1300
5 | Central I&C Systems | 1873585 | 33400 | 1840185 | 10.19% | 187483.8442 | 2061068.8442
51 | TCP/IP Infrastructure System | 280385 |  | 280385 | 5% | 14019.295 | 294404.295
52 | Central Instrumentation & Controls System | 530100 |  | 530100 | 10% | 53011.241 | 583111.241
53 | Data Acquisition & Facility Computing | 329100 |  | 329100 | 16% | 52651.6528 | 381751.6528
54 | Facility Timing & Synchronization System | 195800 |  | 195800 | 14% | 27415.2354 | 223215.2354
55 | Real Time Plasma & Power Control Systems | 179300 |  | 179300 | 8.001% | 14346.512 | 193646.512
56 | Central Safety Interlock System | 325500 |  | 325500 | 8% | 26039.908 | 351539.908
57 | Control Room Facility |  |  | 0 |  |  | 0
58 | Central I&C management and Integration | 33400 | 33400 | 0 |  |  | 33400
6 | Facility Systems | 678200 | 24000 | 654200 | 20% | 130841.748 | 809041.748
61 | Water Cooling Systems | 92300 | 15000 | 77300 | 23.87% | 18454.356 | 110754.356
62 | Cryogenic System | 455000 |  | 455000 | 20% | 91006.608 | 546006.608
63 | Utility Systems | 106900 | 9000 | 97900 | 21.84% | 21380.784 | 128280.784
64 | Bakeout System |  |  | 0 |  |  | 0
65 | Facility System | 24000 |  | 24000 | 0% |  | 24000
7 | Test Cell Preparation & Machine Assy | 4555200 | 900200 | 3655000 | 21.7% | 793146.5927 | 5348346.5927
71 | Shield Wall Reconfiguration | 32200 | 32200 | 0 |  | 0 | 32200
72 | Control Room Refurbishment | 9100 | 0 | 9100 | 9.998% | 909.792 | 10009.792
73 | Platform Design | 109100 | 73000 | 36100 | 10.09% | 3643.5385 | 112743.5385
74 | Planning/Oversight | 1753200 | 795000 | 958200 | 15.22% | 145873.4182 | 1899073.4182
75 | Machine Assembly Planning & Oversight | 2413800 |  | 2413800 | 24.26% | 585652.9824 | 2999452.9824
76 | Tooling Design & Fabrication | 237800 |  | 237800 | 24% | 57066.8616 | 294866.8616
8 | Project Oversight & Support | 12633000 | 6349900 | 6283100 | 13.31% | 836075.4935 | 13469075.4935
81 | Project Management & Control | 4452900 | 2209000 | 2243900 | 11.09% | 248820.2535 | 4701720.2535
82 | Project Engineering | 4904100 | 2891000 | 2013100 | 9.605% | 193367 | 5097467
83 | Environmental & Safety/QA/QC in overhead |  |  | 0 |  |  | 0
84 | Project Physics | 469900 | 469900 | 0 |  |  | 469900
85 | Integrated System Testing | 1197700 | 0 | 1197700 | 25.97% | 310999.399 | 1508699.399
A | Allocations | 1608400 | 780000 | 828400 | 10.01% | 82888.841 | 1691288.841
| TOTAL | 82713185 | 38313900 | 44399285 | 21.65% | 9612474.4747 | 92325659.4747 |  |  |  |  | 0 | -92325659.4747
| DCMA | 75000 |  |  |  |  | 75000
|  | 82788185 |  |  |  |  | 92400659.4747
ECP-38
[16 empty] | 12 - Vacuum Vessel Systems | 9439.3 | 9439300
[16 empty] | 13 - Conventional Coils | 4831 | 4831000
[16 empty] | 14 - Modular Coils | 31355.9 | 31355900
[16 empty] | 15 - Structures | 1386.2 | 1386200
[16 empty] | 16 - Coil Services | 1135 | 1135000
[16 empty] | 17 - Cryostat and Base Support Structure | 1532.9 | 1532900
[16 empty] | 18 - Field Period Assembly | 5280.8 | 5280800
[16 empty] | 19 - Stellarator Core Management and Integration | 2767 | 2767000
[16 empty] | 21 - Fueling Systems | 88.1 | 88100
[16 empty] | 22 - Torus Vacuum Pumping Systems | 418.8 | 418800
[16 empty] | 25 - Neutral Beam Injection System | 284.4 | 284400
[16 empty] | 31 - Magnetic Diagnostics | 551.6 | 551600
[16 empty] | 36 - Edge and Divertor Diagnostics | 45.6 | 45600
[16 empty] | 38 - Electron Beam (EB) Mapping | 206.2 | 206200
[16 empty] | 39 - Diagnostics Integration | 345.3 | 345300
[16 empty] | 41 - AC Power | 423.9 | 423900
[16 empty] | 43 - DC Systems | 478.8 | 478800
[16 empty] | 44 - Control and protection Systems | 1346 | 1346000
[16 empty] | 45 - Power System Design and Integration | 1055.1 | 1055100
[16 empty] | 46 - FCPC Building Modifications | 1.3 | 1300
[16 empty] | 51 - TCP/IP Infrastructure Systems | 308.3 | 308300
[16 empty] | 52 - Central Instrumentation & Control | 530.1 | 530100
[16 empty] | 53 - Data Acquisition & Facility Computing | 329.1 | 329100
[16 empty] | 54 - Facility Timing & Synchronization | 195.8 | 195800
[16 empty] | 55 - Real Time Plasma & Power Supply Control Sys | 179.3 | 179300
[16 empty] | 56 - Central Safety Interlock Systems | 325.5 | 325500
[16 empty] | 58 - Central I&C management and Integration | 5.5 | 5500
[16 empty] | 61 - Water Systems | 92.3 | 92300
[16 empty] | 62 - Cryogenic Systems | 455 | 455000
[16 empty] | 63 - Utility Systems | 106.9 | 106900
[16 empty] | 65 - Facility Systems Integration | 24 | 24000
[16 empty] | 71 - Shield Wall Seismic Modifications | 32.2 | 32200
[16 empty] | 72 - Control Room Refurbishment | 9.1 | 9100
[16 empty] | 73 - Platform Design & Fabrication | 109.1 | 109100
[16 empty] | 74 - Machine Assembly Planning and Oversight | 1753.2 | 1753200
[16 empty] | 75 - Test Cell and Basement Assembly Operations | 2413.8 | 2413800
[16 empty] | 76 - Tooling Design & Fabrication | 237.8 | 237800
[16 empty] | 81 - Project Management and Control | 4452.9 | 4452900
[16 empty] | 82 - Project Engineering | 4904.1 | 4904100
[16 empty] | 84 - Project Physics | 469.9 | 469900
[16 empty] | 85 - Integrated Systems Testing | 1197.7 | 1197700
[16 empty] | PPPL Allocations | 1608.4 | 1608400
[17 empty] | 82713.2 | 82713200
Note on O4: SC: The committee believes that the NCSX Team has made a credible estimate of the base costs and applied an appropriate level of contingency made on the basis of technical and schedule risk. The base costs estimates have benefited significantly from preliminary manufacturing feasibility studies performed by potential vendors of both the Modular Coil forms and the Vacuum Vessel. The NCSX Team has performed significant analysis of the components deemed to be the most technically risky (modular coils and VV). They have included an appropriate level of manufacturing R&D to mitigate these risks.
Note on O14: SC: Refurbishment of existing systems.
Note on O19: SC: Viable budget estimate for planned effort using new hardware.
Note on O25: SC: All technology and costing data drawn from NSTX.
Note on O32: SC: Install computers & networks & connect existing software systems for controls and data acquisition.
Note on O33: SC: Layout and install standard computer networks.
Note on O34: SC: EPICS control configuration and testing for 5 systems--lots of experience.
Note on O35: SC: Install computer hardware and configure MDS Plus data acquisition--lots of experience
Note on O36: SC: Design and deploy timing and synchronization system based on NSTX.
Note on O37: SC: Clone NSTX real-time control systems
Note on O38: SC: Layout and install safety interlock systems
Note on O39: SC: Computers for first plasma and PA system in control room
Note on O41: SC: Extensive use of existing systems with refurbishing. Recent experience with NSTX for cost estimates
Note on O54: SC: Cost reasonable based on review

## ECP38 reconciliation
NCSX rebaseline reconciliation
|  | ECP-036 | ECP-39 | Changes
111 - Limiters
12 - Vacuum Vessel Systems | [6 empty] | etc | ETC/rates | cv
| 121 - Vacuum Vessel Assembly | 8548.22 | 8630 | 81.78 | 121 | 8630 | 8698 | 149.78 | -68
| 122 - Vacuum Vessel Thermal Insulation | 191.89 | 172.3 | -19.59 | 122 | 172.3 | 172.3 | -19.59
| 123 - Vacuum Vessel Heating and Cooling Distrib | 535.98 | 364.9 | -171.08 | 123 | 364.9 | 364.9 | -171.08
| 124 - Vacuum Vessel Supports | 106.1 | 247.5 | 141.4 | 124 | 247.5 | 247.5 | 141.4
| 125 - Vacuum Vessel Local I&C | 17.64 | 24.6 | 6.96 | 125 | 24.6 | 24.6 | 6.96
| subtotal | 9399.83 | 9439.3 | 39.47 |  | -68 |  | 107.47 | -68
13 - Conventional Coils | [5 empty] | 0 |  | 0
| 130 - Conventional Coil Design | 837.4 | 837.4 | 0 | 130 | 837.4 | 837.4 | 0
| 131 - TF Coils | 1717.83 | 2399 | 681.17 | 131 | 2399 | 2153 | 435.17 | 246
| 132 - PF Coils | 1885.36 | 1400 | -485.36 | 132 | 1400 | 1400 | -485.36
| 133 - External Trim Coils | 257.67 | 103.4 | -154.27 | 133 | 103.4 | 103.4 | -154.27
| 134 - Conventional Coil Local | 91.87 | 91.2 | -0.67 | 134 | 91.2 | 91.2 | -0.67
| subtotal | 4790.13 | 4831 | 40.87 |  | 246 |  | -205.13 | 246
14 - Modular Coils | [5 empty] | 0 |  | 0
| 141 - Modular Coil Winding Form | 13271.57 | 12727 | -544.57 | 141 | 12727 | 12437 | -834.57 | 290
| 142 - Modular Coil Windings and Assembly | 11978.769 | 14580.5 | 2601.731 | 142 | 14580.5 | 13956.5 | 1977.731 | 624
| 143 - Modular Coil Local I&C | 0 | 0 | 0 |  | 0 |  | 0
| 144 - Modular Coil Winding Facility & Fixtures | 3863.201 | 4048.4 | 185.199 | 144 | 4048.4 | 3918.4 | 55.199 | 130 | 1044
| subtotal | 29113.54 | 31355.9 | 2242.36 |  | 1044 |  | 1198.36 | 1044
15 - Structures | [5 empty] | 0 |  | 0
| 151 - Coil Support Structure | 1412.96 | 1386.2 | -26.76 | 151 | 1386.2 | 1387.2 | -25.76 | -1
16 - Coil Services | [5 empty] | 0 |  | 0
| 161 - LN2 Distribution | 372.04 | 368.5 | -3.54 | 161 | 368.5 | 368.5 | -3.54
| 162 - Electrical Leads | 681.64 | 681 | -0.64 | 162 | 681 | 681 | -0.64
| 163 - Coil Protection System | 86.3 | 85.5 | -0.8 | 163 | 85.5 | 85.5 | -0.8
| subtotal | 1139.98 | 1135 | -4.98 |  | -1 |  | -4.98 | -1
17 - Cryostat and Base Support Structure | [5 empty] | 0 |  | 0
| 171 -Cryostat | 934.01 | 1105.2 | 171.19 | 171 | 1105.2 | 927.2 | -6.81 | 178
| 172 - Base Support Structure | 426.93 | 427.7 | 0.77 | 172 | 427.7 | 427.7 | 0.77
| 173-Spacer manipulator | 0 | 0 | 0 |  | 0 |  | 0
| subtotal | 1360.94 | 1532.9 | 171.96 |  | 178 |  | -6.04 | 178
18 - Field Period Assembly | [5 empty] | 0 |  | 0
| 181 - Field Period Assembly Planning/Oversight | 1505.26 | 1545.8 | 40.54 | 181 | 1545.8 | 1488.8 | -16.46 | 57
| 182 - TFTR Test Cell Area preparations | 0 | 70.3 | 70.3 | 182 | 70.3 | 70.3 | 70.3
| 183 - Receive Inspect and Test Coils | 0 | 0 | 0 |  | 0 |  | 0
| 184 - Receive Inspect and Test VV | 0 | 0 | 0 |  | 0 |  | 0
| 185 - Assemble Field Periods | 2203.28 | 2063.2 | -140.08 | 185 | 2063.2 | 2063.2 | -140.08
| 186 - Tooling Design and Fabrication | 1219.66 | 1051.1 | -168.56 | 186 | 1051.1 | 1199.1 | -20.56 | -148
| 187 - Measurement Systems | 501.77 | 550.4 | 48.63 | 187 | 550.4 | 482.4 | -19.37 | 68 | -23
| subtotal | 5429.97 | 5280.8 | -149.17 |  | -23 |  | -126.17 | -23
19 - Stellarator Core Management and Integration | [5 empty] | 0 |  | 0
| 191 - Stellarator Core Management & Oversight | 1041.61 | 1054.2 | 12.59 | 191 | 1054.2 | 1045.2 | 3.59 | 9
| 192 - Stellarator Core Integration & Analysis | 1696.49 | 1712.9 | 16.41 | 192 | 1712.9 | 1712.9 | 16.41
| subtotal | 2738.1 | 2767.1 | 29 |  | 9 |  | 20 | 9
| SUBTOTAL WBS 1 | 55385.45 | 57728.2 | 2342.75 |  | 1384 |  | 957.75 | 1384
[6 empty] | 0 |  | 0
21 - Fueling Systems |  | 86.54 | 88.1 | 1.56 | 210 | 88.1 | 88.1 | 1.56
22 - Torus Vacuum Pumping Systems |  | 412.55 | 418.8 | 6.25 | 220 | 418.8 | 418.8 | 6.25
25 - Neutral Beam Injection System |  | 284.37 | 284.4 | 0.03 | 250 | 284.4 | 284.4 | 0.03
| SUBTOTAL WBS 2 | 783.46 | 791.3 | 7.84 |  | 0 |  | 7.84 | 0
31 - Magnetic Diagnostics |  | 426.35 | 551.6 | 125.25 | 310 | 551.6 | 521.6 | 95.25 | 30
36 - Edge and Divertor Diagnostics |  | 45.96 | 45.6 | -0.36 | 360 | 45.6 | 45.6 | -0.36
38 - Electron Beam (EB) Mapping |  | 310.09 | 206.2 | -103.89 | 380 | 206.2 | 206.2 | -103.89
39 - Diagnostics Integration |  | 360.52 | 345.3 | -15.22 | 390 | 345.3 | 357.3 | -3.22 | -12
| SUBTOTAL WBS 3 | 1142.92 | 1148.7 | 5.78 |  | 18 |  | -12.22 | 18
41 - AC Power | [5 empty] | 0 |  | 0
| 411 - Auxliary AC Power Systems | 382.03 | 376.4 | -5.63 | 411 | 376.4 | 374.4 | -7.63 | 2
| 412 - Experimental AC Power Systems | 48.14 | 47.5 | -0.64 | 412 | 47.5 | 47.5 | -0.64
43 - DC Systems | [5 empty] | 0 |  | 0
| 431 - C-Site DC Systems | 453.94 | 478.8 | 24.86 | 431 | 478.8 | 409.8 | -44.14 | 69
| 432 - D-to-C Site DC Systems | 0 | 0 | 0 |  | 0 |  | 0
| 433 - D-Site DC Systems | 0 | 0 | 0 |  | 0 |  | 0
44 - Control and protection Systems | [5 empty] | 0 |  | 0
| 441 - Electrical Interlocks | 377.66 | 377 | -0.66 | 441 | 377 | 377 | -0.66
| 442 - Kirk Key Interlocks | 82.18 | 81.4 | -0.78 | 442 | 81.4 | 81.4 | -0.78
| 443 - Real Time Control Systems | 14.27 | 13.8 | -0.47 | 443 | 13.8 | 13.8 | -0.47
| 444 - Instrument Systems | 312.65 | 307.5 | -5.15 | 444 | 307.5 | 307.5 | -5.15
| 445 - Coil protection Systems | 522.1 | 566.3 | 44.2 | 445 | 566.3 | 517.3 | -4.8 | 49
45 - Power System Design and Integration | [5 empty] | 0 |  | 0
| 451 - System Design and Interfaces | 520.33 | 478.1 | -42.23 | 451 | 478.1 | 530.1 | 9.77 | -52
| 452 - Electrical Systems Support | 261.74 | 259.3 | -2.44 | 452 | 259.3 | 259.3 | -2.44
| 453 - System Testing (PTP's) | 324.72 | 317.7 | -7.02 | 453 | 317.7 | 317.7 | -7.02
[6 empty] | 0 |  | 0
46 - FCPC Building Modifications |  | 1.3 | 1.3 |  | 460 | 1.3 | 1.3 | 0
| SUBTOTAL WBS 4 | 3301.06 | 3305.1 | 4.04 |  | 68 |  | -63.96 | 68
[6 empty] | 0 |  | 0
51 - TCP/IP Infrastructure Systems |  | 282.69 | 280.4 | -2.29 | 510 | 280.4 | 280.4 | -2.29
52 - Central Instrumentation & Control |  | 610.92 | 530.1 | -80.82 | 520 | 530.1 | 530.1 | -80.82
53 - Data Acquisition & Facility Computing |  | 351.01 | 329.1 | -21.91 | 530 | 329.1 | 329.1 | -21.91
54 - Facility Timing & Synchronization |  | 220.96 | 195.8 | -25.16 | 540 | 195.8 | 195.8 | -25.16
55 - Real Time Plasma & Power Supply Control Sys |  | 161.65 | 179.3 | 17.65 | 550 | 179.3 | 179.3 | 17.65
56 - Central Safety Interlock Systems |  | 381.94 | 325.5 | -56.44 | 560 | 325.5 | 325.5 | -56.44
58 - Central I&C management and Integration |  | 40.36 | 33.4 | -6.96 | 580 | 33.4 | 40.4 | 0.04 | -7
| SUBTOTAL WBS 5 | 2049.53 | 1873.6 | -175.93 |  | -7 |  | -168.93 | -7
61 - Water Systems | [5 empty] | 0 |  | 0
| 611 - C-Site Cooling System | 0 | 0 | 0 |  | 0 |  | 0
| 612 - NB Water Cooling Systems | 0 | 0 | 0 |  | 0 |  | 0
| 613 - Vacuum Pumping System | 94.51 | 92.3 | -2.21 | 613 | 92.3 | 92.3 | -2.21
| 614 - Bakeout Water System | 0 | 0 | 0 |  | 0 |  | 0
62 - Cryogenic Systems | [5 empty] | 0 |  | 0
| 621 - LN2-LHe Supply System | 233.04 | 229 | -4.04 | 621 | 229 | 229 | -4.04
| 622 - LN2 Coil Cooling Supply | 0 | 0 | 0 | 622 | 0 |  | 0
| 623 - GN2 Cryostat Cooling System | 230.22 | 226 | -4.22 | 623 | 226 | 226 | -4.22
[6 empty] | 0 |  | 0
63 - Utility Systems |  | 109.3 | 106.9 | -2.4 | 630 | 106.9 | 106.9 | -2.4
65 - Facility Systems Integration | [5 empty] | 0 |  | 0
| 612 - NB Water Cooling Systems | 9.38 | 9.4 | 0.02 | 612 | 9.4 | 9.4 | 0.02
| 650 - Facility Systems Integration | 15 | 15 | 0 | 650 | 15 | 15 | 0
| SUBTOTAL WBS 6 | 691.45 | 678.6 | -12.85 |  | 0 |  | -12.85 | 0
71 - Shield Wall Seismic Modifications |  | 32.15 | 32.2 | 0.05 | 710 | 32.2 | 32.2 | 0.05
72 - Control Room Refurbishment |  | 8.09 | 9.1 | 1.01 | 720 | 9.1 | 9.1 | 1.01
73 - Platform Design & Fabrication |  | 164.42 | 109.1 | -55.32 | 730 | 109.1 | 159.1 | -5.32 | -50
74 - Machine Assembly Planning and Oversight |  |  |  | 0 |  | 0 |  | 0
| 740 - Machine Assembly Planning and Oversight | 152.71 | 335.8 | 183.09 | 740 | 335.8 | 157.8 | 5.09 | 178
| 741 - Planning Prior to Machine Assembly | 312.58 | 312.6 | 0.02 | 741 | 312.6 | 312.6 | 0.02
| 742 - Construction Management | 1099.47 | 1104.8 | 5.33 | 742 | 1104.8 | 1104.8 | 5.33
75 - Test Cell and Basement Assembly Operations |  |  |  | 0 |  | 0 |  | 0
| 750 - Test Cell & Basement Assembly Operations | 2365.55 | 2413.8 | 48.25 | 750 | 2413.8 | 2413.8 | 48.25
76 - Tooling Design & Fabrication |  | 238.25 | 237.8 | -0.45 | 760 | 237.8 | 237.8 | -0.45
| SUBTOTAL WBS 7 | 4373.22 | 4555.2 | 181.98 |  | 128 |  | 53.98 | 128
81 - Project Management and Control |  | 4508.81 | 4452.9 | -55.91 | 810 | 4452.9 | 4442.9 | -65.91 | 10
82 - Project Engineering |  | 4885.08 | 4904.1 | 19.02 | 820 | 4904.1 | 4969.1 | 84.02 | -65
84 - Project Physics |  | 469.93 | 469.9 | -0.03 | 840 | 469.9 | 469.9 | -0.03
85 - Integrated Systems Testing |  | 1189.18 | 1197.7 | 8.52 | 850 | 1197.7 | 1197.7 | 8.52
| SUBTOTAL WBS 8 | 11053 | 11024.6 | -28.4 |  | -55 |  | 26.6 | -55 |  | 12633
PPPL Allocations |  | 1576.89 | 1608.4 | 31.51 | AAA | 1608.4 | 1552.4 | -24.49 | 56
[6 empty] | 0 |  | 0
Contingency |  | 11969.1 | 9612 | -2357.1 | CCC | 9612
0
DCMA Support |  | 75 | 75 | 0 | DDD | 75 | 75
|  | 92401.39 | 92400.7 | -0.38 |  | 95321.7 | 81195.7 | 763.72 | 1592 | 2355.72
82713.7

## Budget Summary
| Current Baseline | Unrecoverable Cost Variances | ETC Updates & Design Changes | Total Proposed Change |  | New PMB
12 - Vacuum Vessel Systems | 9400 | -68 | 107 | 39 |  | 9439
13 - Conventional Coils | 4790 | 246 | -205 | 41 |  | 4831
14 - Modular Coils | 29114 | 1043.5 | 1198 | 2241.5 |  | 31355.5
15 - Structures | 1413 | -1 | -26 | -27 |  | 1386
16 - Coil Services | 1140 |  | -5 | -5 |  | 1135
17 - Cryostat and Base Support Struct | 1361 | 178 | -6 | 172 |  | 1533
18 - Field Period Assembly | 5430 | -23 | -126 | -149 |  | 5281
19 - Stellarator Core Mgt & Integr | 2738 | 9 | 20 | 29 |  | 2767
1 Stellarator Core Systems | 55386 | 1384.5 | 957 | 2341.5 |  | 57727.5
2 Heating, Fueling & Vac Sys | 783 |  | 8 | 8 |  | 791
3 Diagnostics | 1143 | 18 | -12 | 6 |  | 1149
4 Electrical Power Sys | 3301 | 68 | -64 | 4 |  | 3305
5 Central I&C Sys | 2050 | -7 | -169 | -176 |  | 1874
6 Facility Sys | 691 |  | -13 | -13 |  | 678
7 Test Cell Prep & MachAssy | 4373 | 128.5 | 54 | 182.5 |  | 4555.5
8 Project Oversight & Support | 12630 | 1 | 3 | 4 |  | 12634
subtotal | 80357 | 1593 | 764 | 2357 |  | 82714
Contingency | 11969 | -1593 | -764 | -2357 |  | 9612
TEC = | 92326 |  |  |  |  | 92326
DCMA | 75 |  |  |  |  | 75
| 92401 |  |  |  |  | 92401
|  |  |  | BCWR |  | 44400
|  |  |  | Contingency balance |  | 9612
21.65%
|  |  |  | BCWP | 36720
|  |  |  | ACWP | 38313
|  |  |  | CPI | 0.95842 |  | 92400
|  |  |  | CV | 1593

## Mpwr job
| JJJJ | ACT CODE | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09 | OCT FY10 | NOV FY10 | DEC FY10
| 6.3 | 1408 | 0.3 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2
| 273.2 | 1451 | 8.7 | 11.4 | 9.5 | 11.9 | 14.7 | 9.9 | 13.2 | 15.2 | 14.4 | 16 | 13.5 | 13.3 | 11.2 | 12.4 | 7.1 | 13.2 | 8.5 | 9.4 | 9.5 | 7.9 | 8.1 | 9.3 | 9 | 6.6 | 5.5 | 3.1 | 0.7
53.3 | 52.9992 | risk |  |  |  |  | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083
| 0.5 | 1204 | 0.5 | 0
| 0.5 | 1350 | 0.5 | 0
| 34.8 | 1351 | 0.7 | 1.4 | 2.6 | 2.7 | 2.5 | 0.4 | 1.5 |  | 0.5 |  |  |  | 1.7 | 3.6 | 1.8 | 3.8 | 2.3 | 4.3 | 1.9 | 2.8 | 0.3
| 36 | risk | [12 empty] | 2.4 | 2.2 | 1.7 | 2.4 | 2.2 | 2.4 | 2.3 | 2.4 | 2.3 | 2.3 | 2.5 | 2.1 | 2.5 | 2.2 | 1.6 | 2.5
| 1.4 | 1352 | [28 empty] | 0.1 | 0.2 | 0.3 | 0.2 | 0.2 | 0.3 | 0.1
| 5 | 1355 | [12 empty] | 0.6 | 0.5 | 0.4 | 0.6 | 0.5 | 0.6 | 0.2 | [15 empty] | 1 | 0.6
| 3.6 | 1414 |  | 1.2 |  |  |  | 1.2 |  |  |  | 0.2 | 1
| 2.5 | 1601 | [24 empty] | 0.7 | 0.8 | 0.6 | 0.4
| 1.6 | 1803 | [12 empty] | 0.5 | 0.5 | 0.4 | 0.2
| 2.7 | 1804 | 0.6 | 0.6 | 0.5 | 0.6 | 0.4
| 165.6 | 1810 | 0.5 | 0.5 | 0.5 | 3.3 | 3.1 | 3.6 | 3 | 2.5 | 4 | 1.4 | 0.5 | 0.5 | 2.9 | 3.7 | 3 | 8.4 | 9.3 | 7.2 | 11.9 | 13.1 | 9.7 | 2.7 | 9.8 | 4.5 | 8.7 | 9.1 | 7.6 | 9.7 | 8.9 | 4.4 | 6.7 | 6.2 | 1.8
| 0.6 | 2101 | [24 empty] | 0.2 | 0.2 | 0.1 | 0.1
| 2.5 | 2201 | [24 empty] | 0 | 0.6 | 0.5 | 0.7 | 0.7 | 0
| 2.7 | 3101 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.6 | 0.5 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| 2 | 6101 | [28 empty] | 1 | 1
| 8.5 | 6201 | [27 empty] | 0.3 | 1 | 2.1 | 2.5 | 2.2 | 0.4
| 3.1 | 6301 | [27 empty] | 1.7 | 1.4
| 3.4 | 7301 | 0.8 | 0.7 | 0.1 | [9 empty] | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.1
| 52.9 | 7501 | [24 empty] | 3.6 | 3.2 | 2.4 | 3.6 | 3.3 | 3.3 | 3.5 | 3.3 | 3.3 | 3.5 | 3.3 | 3.3 | 1.4 | 2 | 2.7 | 2.1 | 3.5 | 1.6
| 63.6 | 7503 | [24 empty] | 4.9 | 4.3 | 3.2 | 1.5 |  | 3.2 | 0.2 |  | 0.6 | 5.1 | 6.7 | 10.2 | 10.7 | 4.9 | 4.9 | 3.2
| 1.5 | 7601 | [24 empty] | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| 2.9 | 8501 | [37 empty] | 0.2 | 0.9 | 0.9 | 0.8 | 0.1
| 440.5411 |  | 12.1 | 15.9 | 12.9 | 15.5 | 20.0083 | 14.0083 | 20.0083 | 21.6083 | 21.5083 | 23.3083 | 19.1083 | 15.9083 | 22.3083 | 25.6083 | 17.1083 | 31.4083 | 25.5083 | 26.7083 | 28.4083 | 28.7083 | 22.9083
jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar
|  | Modular Coil | 9 | 11.6 | 9.7 | 12.2 | 17.1083 | 12.4083 | 15.6083 | 17.7083 | 16.9083 | 18.4083 | 16.0083 | 15.8083 | 13.7083 | 14.8083 | 9.5083 | 15.7083 | 10.9083 | 11.9083 | 12.0083 | 10.4083 | 10.6083 | 11.8083 | 11.5083 | 9.0083 | 7.7083 | 5.3083 | 2.9083 | 2.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TF Coil | 1.2 | 1.4 | 2.6 | 2.7 | 2.5 | 0.4 | 1.5 | 0 | 0.5 | 0 | 0 | 0 | 4.1 | 5.8 | 3.5 | 6.2 | 4.5 | 6.7 | 4.2 | 5.2 | 2.6 | 2.3 | 2.5 | 2.1 | 2.5 | 2.2 | 1.6 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Field Period Assy | 0.6 | 0.6 | 0.5 | 0.6 | 0.4 | 0 | 2.9 | 3.9 | 3.6 | 4.1 | 1.6 | 0 | 3.6 | 4.2 | 3.4 | 8.6 | 9.3 | 7.2 | 11.9 | 13.1 | 9.7 | 2.7 | 9.8 | 4.5 | 8.7 | 9.1 | 7.6 | 9.7 | 8.9 | 4.4 | 6.7 | 6.2 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machine Assy | 0.8 | 0.7 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0 | 8.6 | 7.6 | 5.6 | 5.2 | 3.4 | 6.6 | 3.8 | 3.4 | 4 | 8.7 | 10.1 | 13.6 | 12.2 | 7 | 7.7 | 5.4 | 3.5 | 1.6
|  | Other | 0.5 | 1.6 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0.5 | 0.8 | 1.5 | 0.1 | 0.6 | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.2 | 0 | 0 | 0 | 0.1 | 0.1 | 1 | 1.7 | 1.3 | 3.2 | 4.2 | 3.3 | 2.8 | 2.4 | 0.6 | 0.3 | 1.1 | 0.6 | 0 | 0.2 | 0.9 | 0.9 | 0.8 | 0.1
| 730.3992 |  | 12.1 | 15.9 | 12.9 | 15.5 | 20.0083 | 14.0083 | 20.0083 | 21.6083 | 21.5083 | 23.3083 | 19.1083 | 15.9083 | 22.3083 | 25.6083 | 17.1083 | 31.4083 | 25.5083 | 26.7083 | 28.4083 | 28.7083 | 22.9083 | 16.8083 | 23.9083 | 15.7083 | 28.5083 | 25.9083 | 19.0083 | 22.8083 | 16.5 | 14.3 | 13.3 | 12 | 6.4 | 9 | 11.2 | 14.2 | 12.2 | 7.2 | 8.6 | 6.3 | 4.3 | 1.7
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| 9 | Mod Coil | 9 | 9.8667 | 10.1 | 10.625 | 12.6521 | 12.8542 | 14.3312 | 15.7083 | 15.6583 | 17.1583 | 17.2583 | 16.7833 | 15.9833 | 15.0833 | 13.4583 | 13.4333 | 12.7333 | 12.0083 | 12.6333 | 11.3083 | 11.2333 | 11.2083 | 11.0833 | 10.7333 | 10.0083 | 8.3833 | 6.2333 | 4.5333 | 2.6062 | 1.2792 | 0.55207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | TF Coil | 1.2 | 1.2667 | 1.7333 | 1.975 | 2.3 | 2.05 | 1.775 | 1.1 | 0.6 | 0.5 | 0.125 | 0.125 | 1.025 | 2.475 | 3.35 | 4.9 | 5 | 5.225 | 5.4 | 5.15 | 4.675 | 3.575 | 3.15 | 2.375 | 2.35 | 2.325 | 2.1 | 2.2 | 1.575 | 1.025 | 0.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0.6 | FP Assy | 1.1 | 1.1 | 1 | 3.9 | 3.5 | 3.6 | 3 | 2.5 | 4 | 1.4 | 0.5 | 0.5 | 2.325 | 2.35 | 2.8 | 4.95 | 6.375 | 7.125 | 9.25 | 10.375 | 10.475 | 9.35 | 8.825 | 6.675 | 6.425 | 8.025 | 7.475 | 8.775 | 8.825 | 7.65 | 7.425 | 6.55 | 4.775 | 3.675 | 2 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0
| 0.8 | Mach Assy | 0.8 | 0.76667 | 0.53333 | 0.4 | 0.2 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075 | 0.15 | 0.2 | 0.275 | 0.275 | 0.275 | 0.25 | 0.175 | 0.1 | 0.025 | 0 | 0 | 2.15 | 4.05 | 5.45 | 6.75 | 5.45 | 5.2 | 4.75 | 4.3 | 4.45 | 4.975 | 6.55 | 9.1 | 11.15 | 10.725 | 10.125 | 8.075 | 5.9 | 3.5
| 0.5 | Other | 0.5 | 0.86667 | 0.7 | 0.525 | 0.4 | 0.3 | 0.3 | 0.3 | 0.425 | 0.325 | 0.7 | 0.725 | 0.75 | 0.675 | 0.425 | 0.55 | 0.525 | 0.55 | 0.475 | 0.325 | 0.2 | 0.05 | 0.025 | 0.05 | 0.3 | 0.725 | 1.025 | 1.8 | 2.6 | 3 | 3.375 | 3.175 | 2.275 | 1.525 | 1.1 | 0.65 | 0.5 | 0.475 | 0.425 | 0.5 | 0.7 | 0.6
26.1
|  | 26.1 | O: 0.6; N: 0.6; D: 0.56667; J: 0.575; F: 0.525; M: 0.375; A: 0.975; M: 1.8; J: 2.6; J: 3.625; A: 3.3; S: 2.325

## Mpwr smry
RES | RESOURCE | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09
ecp38 | EA//EM | 6.1 | 5.5 | 4.1 | 5.6 | 6.5 | 7.2 | 5.8 | 6.6 | 6.1 | 3.8 | 4.4 | 3.9 | 5.1 | 4.7 | 3.4 | 5.3 | 4.8 | 5 | 3.7 | 3 | 2.9 | 2.9 | 3.1 | 2.8 | 3.1 | 1.8 | 1.3 | 1.6 | 1.7 | 1.3 | 1.4 | 1.3 | 1.5 | 1.8 | 1.3 | 1.4 | 0.3 | 0.2 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
incl cont risk | EA//SM | 3.1 | 1.3 | 0.9 | 3 | 1 | 1.1 | 1 | 1.1 | 1.1 | 1 | 1.1 | 1 | 4.4 | 4.2 | 3.2 | 3.9 | 2.2 | 1.8 | 1.9 | 1.8 | 1.8 | 2.2 | 2.3 | 1.1 | 1.4 | 1.5 | 0.9 | 0.9 | 0.7 | 0.6 | 0.7 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1
| EC//EM | [23 empty] | 0.9 | 2.1 | 2.1 | 1.8 | 2.9 | 2.8 | 3.2 | 3.8 | 3.8 | 3.8 | 3.1 | 3 | 2.5 | 1.6 | 0.8 | 0.9 | 0.9 | 0.8
| EC//SM | [27 empty] | 0.4 | 0.6 | 1.2 | 1.9 | 1.8 | 1.8 | 1.3 | 1.2 | 1 | 0.5 | 0.3
| EE//AM | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| EE//EM | 1.7 | 0.7 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.3 | 1.9 | 1.8 | 1.8 | 2.5 | 1.7 | 1.2 | 1.2 | 1 | 1.2 | 1.4 | 1.6 | 1.5 | 2.2 | 2.2 | 1.5 | 1.9 | 1.5 | 1 | 0.4 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.3 | 0.9 | 0.9 | 0.8
| EE//SM | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0 | 0 |  |  | 0.1 | 0.5 | 0.6 | 0.4 | 0.8 | 0.6 | 0.7 | 0.9 | 1.7 | 2 | 2.7 | 2.8 | 1.8 | 2.4 | 2 | 1.5 | 2.5 | 2.2 | 2 | 2.5 | 2.7 | 2.5 | 1.7 | 1.6 | 0.9 | 0 | 0
| EE//TB | 0.6 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.4 | 0.1 | 0.1 |  |  | 0.5 | 0.8 | 0.7 | 0.7 | 1.4 | 0.8 | 0.9 | 0.3 | 0.7 | 1.1 | 1.6 | 2.4 | 2 | 3.2 | 3.4 | 1.8 | 1.9 | 1.6 | 1 | 0.7 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.6 | 1.8 | 1.8 | 1.6
| EM//EM | 2.8 | 2.7 | 2.4 | 2.7 | 1.5 | 1.7 | 1.5 | 1.3 | 1.4 | 1.3 | 1.5 | 1.5 | 2.8 | 2.5 | 1.6 | 2.3 | 2 | 2.1 | 2 | 2.3 | 2 | 2.5 | 2.7 | 2.6 | 3.6 | 3 | 2.1 | 3.6 | 3.5 | 3.8 | 3.4 | 3.1 | 2.7 | 1.9 | 1.9 | 1.8 | 1.9 | 2.4 | 4.2 | 3.5 | 2.8 | 0.9
| EM//SM | 4 | 3 | 1.6 | 1.7 | 1 | 0.9 | 0.7 | 1.3 | 1.3 | 0.7 | 0.8 | 0.7 | 1.3 | 1 | 0.8 | 1.4 | 1.4 | 1.4 | 1.7 | 2.2 | 1.9 | 2.3 | 1.8 | 1.8 | 5.6 | 5 | 3.7 | 5.1 | 5 | 3.6 | 3.8 | 3.3 | 3.7 | 4.5 | 4.5 | 4.4 | 5.3 | 4.3 | 6 | 3.3 | 2.6 | 0.9
| EM//TB | 9 | 13.9 | 12.3 | 18.2 | 16.9 | 26.7 | 23.9 | 24.6 | 24.5 | 18.9 | 22.5 | 19 | 30.9 | 28.8 | 20.5 | 34.3 | 26.4 | 25.3 | 29.4 | 29.6 | 31.2 | 34.4 | 35.5 | 17.9 | 25.9 | 22.2 | 16.4 | 17.1 | 14.1 | 12 | 12.6 | 9.1 | 6.9 | 10.4 | 12.7 | 13.1 | 12.8 | 6.9 | 8.5 | 5.8 | 4.3 | 1.1
| ORNLEM | 10.7 | 8.5 | 6.1 | 6.8 | 5.8 | 4.7 | 4.1 | 3.1 | 2.5 | 2.2 | 3 | 2.4 | 3.4 | 3 | 2.3 | 3.6 | 3.5 | 3.6 | 2.4 | 2.3 | 2.2 | 2.2 | 2.5 | 1.9 | 1.7 | 1 | 0.7 | 1 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.7 | 0.6 | 0.5 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0
 | time axis 2005-10-01 to 2009-09-01
| PPPL Engr | 10.6 | 8.9 | 6.8 | 8.5 | 8.2 | 9.1 | 7.5 | 8.1 | 7.7 | 5.2 | 6.1 | 5.7 | 9.8 | 9 | 6.8 | 10.1 | 8.5 | 8.3 | 6.9 | 6.3 | 6.1 | 6.8 | 7.4 | 7.8 | 11 | 9.1 | 6.7 | 10 | 9.5 | 9.3 | 9 | 8.4 | 8.2 | 7 | 6.3 | 5.8 | 3.9 | 3.7 | 6.3 | 5.5 | 4.6 | 1.1 | 0.2 | 0.2 | 0 | 0 | 0 | 0
| PPPL Tecnicians | 13.6 | 17 | 14 | 20 | 18 | 27.9 | 25.1 | 26 | 25.9 | 19.6 | 23.3 | 20.3 | 33.5 | 31.1 | 22.4 | 37.9 | 29.2 | 28.3 | 32.3 | 34.2 | 36.2 | 41 | 42.5 | 23.5 | 37.1 | 32.6 | 23.4 | 27 | 23.5 | 19.8 | 21.5 | 17.2 | 15 | 18 | 20.1 | 19.5 | 18.7 | 12.1 | 16.3 | 10.9 | 8.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| ORNL Engrs | 10.7 | 8.5 | 6.1 | 6.8 | 5.8 | 4.7 | 4.1 | 3.1 | 2.5 | 2.2 | 3 | 2.4 | 3.4 | 3 | 2.3 | 3.6 | 3.5 | 3.6 | 2.4 | 2.3 | 2.2 | 2.2 | 2.5 | 1.9 | 1.7 | 1 | 0.7 | 1 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.7 | 0.6 | 0.5 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0
|  | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul
| Techs ecp36 | 16 | 19.1 | 14.3 | 19.1 | 19.5 | 15.3 | 20.3 | 21.3 | 22.5 | 22.7 | 20.6 | 15.8 | 23.5 | 25.7 | 16.8 | 30.2 | 24.7 | 25.8 | 26.9 | 29.3 | 23.4 | 16.8 | 25.7 | 16.2 | 34.9 | 31.8 | 22.3 | 28.5 | 25.5 | 22.8 | 22.1 | 20.1 | 14.2 | 16.4 | 18.3 | 21.3 | 17.9 | 11.8 | 16.6 | 11.5 | 8.5 | 3.1 | 0 | 0 | 0 | 0

## Milestones may06
|  |  | CD-2 | CD-2
|  |  | Baseline |  | Baseline | float | Forecast | Actual | master schedule | Milestone float
| Level I | CD-1 | 2003-05-01 | 0 | 2003-05-01 |  |  | 2003-05-01
M-0110 |  | CD-2 | 2004-02-01 | 0 | 2004-02-01 |  |  | 2004-02-01
M-0115 |  | CD-3 | 2004-09-30 | 0 | 2004-09-30 |  |  | 2004-09-30
M-0120 |  | CD-4 | 2008-05-30 | 14.2333 | 2009-07-31 | 1900-01-05 18:24 | 2009-01-09 |  | 2009-02-27 | 5.1333
0
1201-500 | Level II | Vacuum Vessel & Modular Coil Prel Dsn Rvw | 2003-10-07 | 0 | 2003-10-07 |  |  | 2003-10-07
1403-08 |  | Performance Baseline Review | 2003-11-18 | 0 | 2003-11-18 |  |  | 2003-11-18
1203-341 |  | Conduct VVSA FDR | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1403-51 |  | Mod Coil Winding Form Final Design Review | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1408-143.1 |  | Award MC Conductor Contract |  |  | 2004-12-19 |  |  | 2004-10-15
121-6-9 |  | Award VV Production Vendor | 2004-12-01 | -2 | 2004-10-15 |  |  | 2004-09-15
C-081 |  | Award MCWF Mfg Contract | 2004-11-01 | -1 | 2004-10-01 |  |  | 2004-09-15
C-121.1 |  | First MCWF Delivered | 2005-03-01 | 4 | 2005-07-15 | 1284.9333 |  | 2005-09-30
131-035 |  | Begin TF Coil fabrication activities | 2005-04-01 | 3 | 2005-09-30 | 1287.5 |  | 2005-06-30
P1-021.1 |  | Complete First Mod Coil Fabrication | 2005-08-31 | 6 | 2006-03-29 | 2006-04-15 |  | 2006-03-01 | 2006-03-29 | 0
121-038.1 |  | Vacuum Vessel Sectors Delivered | 2006-02-01 | 0 | 2006-09-15 | 1.5 | 2006-08-01 |  | 2006-03-21 | 1.5
C-501B1 |  | Last MCWF Delivered | 2006-08-01 | 4 | 2007-09-01 | 1.0333 | 2007-08-01 |  | 2007-02-28 | 1.0333
141-036 |  | PF Coils Awarded | 2006-06-01 | 7 | 2008-03-30 | 5.1667 | 2007-10-27 |  | 2007-10-27 | 5.1667
S3P1-101 |  | Begin Assembly of First Field Period | 2006-09-01 | 6 | 2007-07-01 | 4.0667 | 2007-03-01 |  | 2007-01-12 | 4.0667
1351-195x |  | All TF Coils Delivered | 2007-01-01 | 4 | 2008-08-15 | 10.6333 | 2007-10-01 |  | 2007-11-19 | 10.6333
S4P3-115 |  | Last Field Period Assembled | 2007-06-01 | 3 | 2008-11-15 | 6.6 | 2008-05-01 |  | 2008-06-12 | 6.6
7503-250 |  | Begin Vac Vsl Pumpdown | 2007-09-01 | 2 | 2009-02-11 | 6.4667 | 2008-08-01 |  | 2008-09-11 | 6.4667
7503-330 |  | Begin Cryostat Installation | 2007-11-01 | 2 | 2009-04-07 | 7.2667 | 2008-09-01 |  | 2008-11-07 | 7.2667
730.1250 |  | Operational Readiness | 2007-11-01 | 4 | 2009-06-01 | 7.0667 | 2008-11-01 |  | 2008-12-28 | 7.0667
920.004 |  | Begin Start-up Testing | 2008-03-31 | 0 | 2009-06-16 | 6.5667 | 2008-12-01 |  | 2008-12-01 | 6.5667
0
1404-109.J | Joule | FY04 JOULE #1-Authorize Prototype Fab | 2003-12-20 | 0.33333 | 2003-12-30 |  |  | 2003-10-20
1406-040 |  | FY04 JOULE #2-Begin winding on 3D surface | 2004-03-01 | 1 | 2004-03-31 |  |  | 2004-01-30
1404-110.J |  | FY04 JOULE #3-Prototype Casting Ready for Machining | 2004-06-01 | 0.96667 | 2004-06-30 |  |  | 2004-05-26
C-081.1 |  | FY04 JOULE #4 - CD-3 Readiness | 2004-09-01 | 0.96667 | 2004-09-30 |  |  | 2004-09-15
1408-143.1 |  | FY05 JOULE #1- VVSA, MCWF and MC Copper Conductor Awarded |  | 1278.3667 | 2004-12-30 | 2.5333 |  | 2004-10-15
1406-017.3 |  | FY05 JOULE #2- Cmplt Assy of twisted racetrack |  | 1281.4 | 2005-03-31 | 1281.4 |  | 2005-03-30
1403-20 |  | FY05 JOULE #3- Mod Coil Winding Type C FDR |  | 1284.4333 | 2005-06-30 | 1284.4333 |  | 2005-06-30
P1-011J |  | FY05 JOULE #4- Complete Winding First MC |  | 1287.5 | 2005-09-30 | 2005-10-31 |  | 2005-12-01 | 2005-12-15 | -2.5333
mcwf-311 |  | FY06 JOULE Complete Fabr. of one VVSA and two Mod Coils |  |  | 2006-09-30 |  | 2006-05-01 |  | 2006-03-22 | 6.4
P2-041joul |  | FY07 JOULE Complete Winding of 1/2 of Modular Coils |  |  | 2007-09-30 |  | 2006-12-01 |  | 2006-11-06 | 10.9333
NCSX Milestone Status
Formulas:
Actual = +[Baseline]
float = (+[Baseline]-[Forecast])/30
Forecast = SUM([master schedule])

## EIO IMPACT
Modular Coil Winding Form Delivery Schedule
[9 empty] | EIO Forecast |  |  | Project Forecast |  |  |  |  | Free Float |  | 3 winding lines 2 shifts |  |  |  |  | 2 shfits for field period |  |  |  |  | 2 shifts Machine Assembly
[19 empty] | for coil winding |  |  |  |  | assembly
|  |  | Machine Time (wks) | [10 empty] | 2006 | [11 empty] | 2007
2005-01-01 | 2005-02-01 | MWF# | EIO | Proj Forecast | 2005-04-01 | 2005-05-01 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | Sep | Oct
|  | C1 | 26 (A) | 26 (A)
|  | C2 | 20 | 22
|  | C3 | 14 | 16
|  | C4 |  | 15
|  | C5 |  | 14
|  | C6 |  | 14
|  | A1 |  | 16
|  | A2 |  | 14
|  | A3 |  | 14
|  | B1 |  | 16
|  | A4 |  | 14
|  | A5 |  | 14
|  | A6 |  | 14
|  | B2 |  | 15
|  | B3 |  | 14
|  | B4 |  | 14
|  | B5 |  | 14
|  | B6 |  | 14
|  | 2005 | [11 empty] | 2006 | [11 empty] | 2007
2005-01-01 | 2005-02-01 | 2005-03-01 |  |  | 2005-04-01 | 2005-05-01 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | Sep | Oct | Nov
|  | 2) |  |  | Winding plan basis;
a) first coil taking 50% longer.
b) 2 winding stations with 3 winding teams. 3rd team dedicated to 2nd shift for winding only. Chill plate ,bagging VPI pre done on 1st shift only.
c) 2nd shift utilized for first 10 coils only.
d) all shifts based 5 days/week 70% of winding ops utilize 10hr/days. Some overtime and all Saturday's held back as contingency.
E
E
E
E
E
E
E
E
E
E
E
E
E

## Summary Schedule may06
NCSX Critical Path Summary Schedule
FY02 |  |  |  |  | FY03 | [11 empty] | FY04 | [11 empty] | FY05 | [11 empty] | FY06 | [12 empty] | FY07 | [11 empty] | FY08 | [11 empty] | FY09
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| CDR |  |  |  | DOE Milestones
FY02 J: CD-1; FY03 S: MC/VV PDR; FY04 M: CD-2 | [10 empty] | Joule FY06-Complt fab one VVSA and two modular coils
FY04 D: EIR; FY05 O: CD-3 Start of Fab | [32 empty] | Pumpdown Vac Vsl
[12 empty] | Start of Preliminary Design | [10 empty] | Vac Vsl FDR
Modular Coil FDR
FY04 D: Joule #1 Authorize Protype Fab; FY05 J: Joule #1 Award VVSA,MWCF,Cond | [40 empty] | ORA
[22 empty] | Joule #2 Demonstarte Winding Process on 3-D Surface | [12 empty] | Joule #2 Cmplt Assy TRC
FY04 J: Joule #3 First Prototype Casting Produced for Machining; FY05 J: Joule #3 Mod Coil Winding Type C FDR | [43 empty] | CD-4 Completion of MIE Project
[28 empty] | Joule #4 CD-3 Prereq Complete | [13 empty] | Joule #4 Cmplt Winding First MC
VACUUM VESSEL
[10 empty] | Title I & II Design | [16 empty] | Vessel Award
Manuf Devel
FY04 S: Vessel Fab | 1 |  | 2 | 3
MODULAR COILS
Title I & II MCWF
Twisted Racetrack Fabrication
FY04 D: Title II Design for Winding; FY05 N: Type C; FY05 M: Type C | Type A |  |  |  | Type B
Component Fabrication
MCWF Manufacturing Development
[16 empty] | Fabricate Prototype Type "C" | [12 empty] | Award Winding Form Contract
[43 empty] | C2 |  | C3 | C4 |  | C5 | A1 | A2 | A3 | B1 |  | A4 | B2 |  | B3 | B4 | B5 | B6 | A5 | A6 |  | C6 | bar: FY04 J to FY04 A; FY05 S
Fab Winding Forms
Station 2-Wind
Station 3-Wind
VPI,Clamps,& Test
FY04 O: FIELD PERIOD ASSEMBLY |  |  |  | Stage 1: Attach Cooling,Diag, Insulation
Stage 2: Pre-Assemble Mod Coils
Stage 3: MC Installation
Stage 4: Assemble 1st Period
Stage 4: Assemble 2nd Period
Stage 4: Assemble 3rd Period
FY04 A: MACHINE ASSEMBLY | [21 empty] | Install Supports and Lower PF Coils
Install,align, connect Field Period Assemblies
FY03 O: Legend: | [34 empty] | Pump Down
FY03 O: Completed Task | [33 empty] | Connect to Ancilliary Systems
FY03 O: Critical Paths | [33 empty] | Install Cryostat & PTP
FY03 O: Off critical path | [36 empty] | Startup Testing and E-Beam Mapping
FY03 M: 2 shift operation | [8 empty] | Ancilliary Systems Installation | [34 empty] | First Plasma
FY02 M: FY02; FY03 O: FY03; FY04 O: FY04; FY05 O: FY05; FY06 O: FY06 | [11 empty] | FY07 | [11 empty] | FY08
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A |  | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1
Total Float 6 mo.

## Funding may06
Total
| Original BA | 7.9 | 15.83 | 15.84 | 22.14 | 19.42 | 5.2 |  | 86.33
| New BA | 7.9 | 15.83 | 17.5 | 15.9 | 15.9 | 15.9 | 5.199 | 94.129
| PMB | 6.062 | 13.658 | 18.238 | 15.425 | 13.289 | 12.748 | 2.466 | 81.886
| Contingency |  |  | 0.8 | 3 | 2.6 | 3.1 | 2.742 | 12.242
| BA cum old | 7.9 | 23.73 | 39.57 | 61.71 | 81.13 | 86.33 | 86.33
| BA cum new | 7.9 | 23.73 | 41.23 | 57.13 | 73.03 | 88.93 | 94.129
| PMB cum | 6.062 | 19.72 | 37.958 | 53.383 | 66.672 | 79.42 | 81.886
%
24.8%
|  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total
| 22.01% |  | BA | 7.897 | 15.921 | 17.5 | 17 | 15.9 | 15.9 | 2.3 | 92.418
|  |  | EAC | 5.9419 | 14.2393 | 18.162 | 19.8 | 15.1 | 9.8 | 1.6 | 84.6432
| 5% |  | Contingency |  |  |  |  | 1 | 6.1 | 0.7 | 7.8
| 10% |  | BO (EAC + Cont) | 5.9419 | 14.2393 | 18.162 | 19.8 | 16.1 | 15.9 | 2.3 | 92.4432
33.49%
| 19.58% |  | Cum BA | 7.897 | 23.818 | 41.318 | 58.318 | 74.218 | 90.118 | 92.418
| 11.24% |  | Cum PMB | 5.9419 | 20.1812 | 38.3432 | 58.1432 | 73.2432 | 83.0432 | 84.6432
22.01%
|  |  | Cum BO | 5.9419 | 20.1812 | 38.3432 | 58.1432 | 74.2432 | 90.1432 | 92.4432
[5 empty] | 23.8 | 41.3 | 58.3 | 74.2 | 90.1 | 92.4
|  |  | pmb puts and takes |  |  | -0.415 | -1.047 | -0.712 | 0.151 | 0.121
|  |  | contingency puts and takes |  | 0 | 0.415 | 1.047 | 0.712 | -0.151 | -0.121
|  |  |  | wbs1 | -0.24 | -0.12 | -0.12
|  |  |  | wbs13 | -0.6 | -0.2 | -0.2 | -0.2
|  |  |  | wbs 141 | -0.64 |  | -0.32 | -0.32
|  |  |  | wbs142 | -0.095 | -0.095
|  |  |  | wbs142 | -0.097 |  | -0.097
|  |  |  | wbs18 | -0.3 |  | -0.15 | -0.15
|  |  |  | wbs82 | -0.32 |  | -0.16 | -0.16
|  |  |  | red | 0.48 |  |  | 0.118 | 0.151 | 0.121
0.09
FY04 FY05 FY06 FY07 FY08 FY09
$23.8
$74.2
$58.3
$41.3
$92.4
$90.1

## wbs2 budgets by fy
| WBS2 |  |  | ACT CODE | DESCRIPTION | FY2003 | FY2004 | FY2005 | FY05 CV | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL | ACT CODE
| 0.1 |  | 0 | 11 | 11 - In-Vessel Components | 0.1 | [7 empty] | 0.1 | 11
| 6252 |  | 3254.7 | 12 | 12 - Vacuum Vessel Systems | 1217.4 | 1663.3 | 3371.3 | -68 | 2970.4 | 194.9 | 89.4 |  | 9438.7 | 12
| 1265.9 |  | 3316.3 | 13 | 13 - Conventional Coils | 91.7 | 333.9 | 840.3 | 245 | 1277.9 | 917.1 | 1121.3 |  | 4827.2 | 13
| 17722.9 |  | 12584.5 | 14 | 14 - Modular Coils | 2424.8 | 7314.1 | 7984 | 1043.5 | 8551.7 | 3945.6 | 87.2 |  | 31350.9 | 14
| 78.9 |  | 1308.3 | 15 | 15 - Structures |  | 34.6 | 44.3 | -1 | 130.6 | 1173 | 4.7 |  | 1386.2 | 15 | 3945.4
| 0 |  | 1135 | 16 | 16 - Coil Services |  |  |  | 0 |  | 660 | 475 |  | 1135 | 16
| 193.2 |  | 1161.9 | 17 | 17 - Cryostat and Base Support Structure | 12.2 | 80.9 | 100.1 | 178 | 5.5 | 618.1 | 531.2 | 7.1 | 1533.1 | 17
| 1356.9 |  | 3945.4 | 18 | 18 - Field Period Assembly | 60.8 | 362.5 | 933.6 | -22 | 1175.9 | 1704.4 | 1053.5 | 11.6 | 5280.3 | 18
28345.6 | 1475.7 |  | 1282.5 | 19 | 19 - Stellarator Core Management and Integration | 254.2 | 640.7 | 580.8 | 9 | 515.7 | 361.6 | 251.5 | 153.7 | 2767.2 | 19 | 57718.7
| 0 |  | 88.1 | 21 | 21 - Fueling Systems | [5 empty] | 52.7 | 35.4 |  | 88.1 | 21 | 791.4
| 63.7 | 443.3 | 355.2 | 22 | 22 - Torus Vacuum Pumping Systems | 63.7 |  |  |  |  | 125.5 | 229.7 |  | 418.9 | 22
| 284.4 |  | 0 | 25 | 25 - Neutral Beam Injection System | 123 | 161.4 | [6 empty] | 284.4 | 25
| 100.2 | 744.2 | 421.9 | 31 | 31 - Magnetic Diagnostics |  |  | 100.2 | 30 | 314.2 | 92.5 | 15.2 |  | 552.1 | 31 | 1149.3
| 0 |  | 45.6 | 36 | 36 - Edge and Divertor Diagnostics | [5 empty] | 5.7 | 39.9 |  | 45.6 | 36
| 0 |  | 206.2 | 38 | 38 - Electron Beam (EB) Mapping | [6 empty] | 206.2 |  | 206.2 | 38
| 286.9 |  | 70.5 | 39 | 39 - Diagnostics Integration | 155.5 | 65 | 66.4 | -12 | 70.5 |  |  |  | 345.4 | 39
| 104.5 | 2779.2 | 317.4 | 41 | 41 - AC Power |  | 85.8 | 18.7 | 2 | 0.1 | 288 | 29.3 |  | 423.9 | 41 | 3305.1
| 156.9 |  | 252.9 | 43 | 43 - DC Systems |  |  | 156.9 | 69 | 38.4 | 214.5 |  |  | 478.8 | 43
| 5.5 |  | 1291.6 | 44 | 44 - Control and protection Systems |  | 1.1 | 4.4 | 49 |  | 842.5 | 431.3 | 17.8 | 1346.1 | 44
| 189.7 |  | 917.3 | 45 | 45 - Power System Design and Integration | 112.3 | 29.9 | 47.5 | -52 | 129.2 | 350.4 | 437.7 |  | 1055 | 45
| 1.3 |  | 0 | 46 | 46 - FCPC Building Modifications | 1.3 | [7 empty] | 1.3 | 46
| 27.9 | 1840.2 | 280.4 | 51 | 51 - TCP/IP Infrastructure Systems | 11.9 | 16 |  |  |  |  | 280.4 |  | 308.3 | 51 | 1873.6
| 0 |  | 530.1 | 52 | 52 - Central Instrumentation & Control | [5 empty] | 9.4 | 429.1 | 91.6 | 530.1 | 52
| 0 |  | 329.1 | 53 | 53 - Data Acquisition & Facility Computing | [5 empty] | 11.1 | 299.1 | 18.9 | 329.1 | 53
| 0 |  | 195.8 | 54 | 54 - Facility Timing & Synchronization | [6 empty] | 195.8 |  | 195.8 | 54
| 0 |  | 179.3 | 55 | 55 - Real Time Plasma & Power | [6 empty] | 179.3 |  | 179.3 | 55
| 0 |  | 325.5 | 56 | 56 - Central Safety Interlock | [6 empty] | 325.5 |  | 325.5 | 56
| 12.5 |  | 0 | 58 | 58 - Central I&C management and Integration |  |  | 12.5 | -7 |  |  |  |  | 5.5 | 58
| 0 | 654.2 | 92.3 | 61 | 61 - Water Systems | [6 empty] | 92.3 |  | 92.3 | 61 | 678.6
| 0 |  | 455 | 62 | 62 - Cryogenic Systems | [5 empty] | 41.8 | 413.2 |  | 455 | 62
| 0 |  | 106.9 | 63 | 63 - Utility Systems | [6 empty] | 106.9 |  | 106.9 | 63
| 24.4 |  | 0 | 65 | 65 - Facility Systems Integration | 9.4 | 15 | [6 empty] | 24.4 | 65
768.7 | 32.2 | 3666.9 | 0 | 71 | 71 - Shield Wall Seismic Modifications | 32.2 | [7 empty] | 32.2 | 71 | 4563.1
| 0 |  | 9.1 | 72 | 72 - Control Room Refurbishment | [5 empty] | 9.1 |  |  | 9.1 | 72
| 120.7 |  | 38.3 | 73 | 73 - Platform Design & Fabrication |  |  | 120.7 | -50 |  | 38.3 |  |  | 109 | 73
| 615.8 |  | 959.2 | 74 | 74 - Machine Assembly Planning and Oversight | 164 | 238.2 | 213.6 | 177.5 | 17.6 | 188.5 | 496.1 | 257 | 1752.5 | 74
| 0 |  | 2422.5 | 75 | 75 - Test Cell and Basement Assembly Operations | [5 empty] | 74.6 | 1664.4 | 683.5 | 2422.5 | 75
| 0 |  | 237.8 | 76 | 76 - Tooling Design & Fabrication | [6 empty] | 176.4 | 61.4 | 237.8 | 76
| 2921.5 | 6284.6 | 3073.4 | 81 | 81 - Project Management and Control | 557.9 | 1221.8 | 1141.8 | 67 | 1138.1 | 1044.1 | 758.9 | 132.3 | 6061.9 | 81 | 12634.3
| 2956.2 |  | 2011.9 | 82 | 82 - Project Engineering | 518.9 | 1230.9 | 1206.4 | -65 | 1180.6 | 445.9 | 322.6 | 62.8 | 4903.1 | 82
| 470 |  | 0 | 84 | 84 - Project Physics | 251.3 | 218.7 | [6 empty] | 470 | 84
|  |  | 1199.3 | 85 | 85 - Integrated Systems Testing | [6 empty] | 365.1 | 834.2 | 1199.3 | 85
[6 empty] | 6062.6 | 13713.8 | 16943.5 | 1593 | 17516.4 | 13409.3 | 11143.6 | 2331.9 | 82714.1 | 82714.1 | 86659.5
[8 empty] | 36719.9 |  | 44401.2
|  |  |  | CC | Contingency |  |  | 1582 | 1593 | 1295 | 2518 | 4750 | 1049 | 9612 | CC
[6 empty] | 6062.6 | 13713.8 | 18536.5 |  | 18811.4 | 15927.3 | 15893.6 | 3380.9 | 92326.1 | 92326.1
[8 empty] | 38313 | 38312.9
|  |  |  | DD | DCMA |  | 75 | [6 empty] | 75 | 75
[10 empty] | 57124.3 | 73051.6 |  |  | 92401.1
2921.5
2956.2
[6 empty] | 557.9 | 1221.8 | 1141.8 | 67 | 1138.1 | 1044.1 | 758.9 | 132.3
92401.1