## RiskOpportunities may06
| Risk | Opportunity
Modular Coil Winding Operations | 509 |  | Re-evaluate at year end
MCWF Deliveries ahead of schedule | 410
Project Engineering oversight (FY08/09) | 339 |  | Re-evaluate at year end
Design Integration (FY08/09) | 333 |  | Re-evaluate at year end
Systems Analysis (FY08/09) | 304 |  | Re-evaluate at year end
Dimensional Control (FY08/09) | 207 |  | Re-evaluate at year end
Fabricate PF coils at ASIPP |  | -375
Simpler Cryostat Design |  | -350
Aggressive machine assembly schedule using 2 shifts. Saves two months and LOE cost |  | -400
| 2102 | -1125

## Budget Reconciliation may06
Unrecoverable Cost Variances
|  | WBS 12 | Vac Vsl hardware design | 154 | Design of heater tape, cooling tubes and associated hardware
|  | WBS 12 | VVSA Contract oversight | 57 | Contract oversight, Support of MTM leak testing of the VVSA, and NCR reconciliation
WBS | WBS WBS 13 | WBS 13 | TF Fab Facility | 64 | TF Coil Hardware fabrication
WBS | WBS WBS 13 | WBS 13 | TF coil -PPPL oversight/title III | 101 | TF outsourcing efforts (documentation, travel, evaluation)
WBS | WBS WBS 14 | WBS 14 | Cryogenic test facility (job 1414) | 130 | Design , testing and modifications in support of the upcoming mod. coil cold test
WBS | WBS WBS 14 | WBS 14 | MC winding (job 1451 & 1459) | 492 | Unplanned work, extensive overtime to makeup schedule, and initial learning curve/efficiencies.
WBS | WBS WBS 14 | WBS 14 | Modular Coil Design | 33
WBS | WBS WBS 17 | WBS 17 | WBS 17 cryostat and base support | 47 | Updates to the cryosat design
WBS | WBS WBS 18 | WBS 18 | WBS 18 Field period assy fuxtures & prep | 79 | Purchase of a third Romer arm and computer
WBS | WBS WBS 3 | WBS 3 | Magnetic Diagmnostics | 70 | Engineering and fabrication of vacuum vessel saddle loops.
WBS | WBS WBS 4 | WBS 4 | Electrical Power Systems | 141 | Revisions to the C-site power systems and cabling design
WBS | WBS WBS 7 | WBS 7 | Test Cell Preparations | 37 | NCSX test cell electrical power upgrades
WBS | WBS WBS 81 | WBS 81 | Project management office | 83 | Project management team (PPPL & ORNL) and overhead allocations
WBS | WBS WBS 82 | WBS 82 | Proj Engr (Reierson,Dudek, Simmons) | 44 | RLM oversight
|  | WBS 82 | Systems Analysis (Brooks) | 142 | Integrated stellarator modeling and analysis (ie mod coil coil-to-coil and machine support)
|  |  | other cost variances | 8
|  |  | rate variance | -107
1575
ETC Updates
|  | WBS 12 | Vac Vsl hardware design | 70 | Completion of thermal insulation, heater tape and assembly drawings
|  | WBS 12 | Vac Vsl hardware fabrication | 36 | Port insulation
|  | WBS 13 | TF coil- fabrication | 345 | Increase in fabrication cost ($1,473 contract award)
|  | WBS 13 | TF coil -PPPL oversight/title III | 165 | Increase to oversee outsourcing of fabrication (average of 1 trip/week). Risk mitigation due to vendor history. | 510
|  | WBS 13 | PF coil procurement & design | -90 | Estimate reduced in recognition of TF cost.
|  | WBS 13,15 | Bbase ,& coil support struct | -63 | combine base ,& coil support struct into one procurement
|  | WBS 13 | Central solenoid support structure fabrication | -144 | Simpler design to be fabricated by PPPL
|  | WBS 14 | Cryogenic test facility (job 1414) | 66 | Completion of test facility and testing of modular coil
|  | WBS 14 | MC winding (job 1451 & 1459) | 448.83 | Estimate growth (including overtime and second shift differential) into mid-FY07.
|  | WBS 14 | Completion of Type A & B modular coil design | -97 | Elimination of redundant assembly and hardware drawings.
|  | WBS 14 | Mod Coil interface design | 125 | Additional analysis of joint and resultant design modifications
|  | WBS 14 | Mod Coil interface hardware | 70 | Shims, bolts, washers and bladder hardware.
|  | WBS 18 | FP assy stage 1 | 163 | Additional assembly steps and includes hands-on senior field supervisor.
|  | WBS 18 | FP assy tooling & fixtures | 112 | Fixtures re-estimate plus add'l stage 5 fixture. | 657
|  | WBS 18 | FP assy tooling & fixtures -engr& design increase | 140
|  | WBS 18 | Metrology H/W maint and support (job 1804) | 74 |  |  | 494
|  | WBS 18 | Metrology engr supervision (raftopolous) stage 1 FP assy | 168
ETC Updates (continued)
|  | WBS 2 | Fueling and Vacuum Pumping | -306 | Simplified systems design using existing pumping system (tested on VVSA).
|  | WBS 3 | Magnetic Diagnostic design and fabrication | -7.379 | Anticipated FY06 rate variance
|  | WBS 3 | E-beam mapping diagnostic hardware | -176 | Use of borrowed equipt for e-beam mapping
|  | WBS 3 | Edge & diverter diagnostics | -36 | Use borrowed camera from NSTX
|  | WBS 4 | Controls and protection | -339.734 | eliminate DC shunts and simplify overload protection | -1031.362
|  | WBS 4 | AC power | -67.977 | Minimal ex-test cell AC power and grounding
|  | WBS 4 | DC power | 70 | Power loop design and C-site rectifier maintenance\
|  | WBS 51 | TCP/IP network | -106.486 | Local TCP/IP network infrastructure
|  | WBS 52 | Central Facilities I&C | -383.452 | No central contrl. Integrated control will be implemented administratively.
|  | WBS 53 | Diagnostic Data Acquisition & computing | -176.857 | The NSTX infrastructure will be used where possible.
|  | WBS 54 | Facility timing & synchronization | -102.971 | Use timing device designs in use on NSTX
|  | WBS 55 | Real time plasma control | -85.716 | PC based "LabVIEW" will produce open-loop power supply commands.
|  | WBS 56 | Central Safety & Interlokcs | -200.08 | Administrative controls;ie locked test cell, limited kirk keys.
|  | WBS 58 | Central I&C Integr and oversight | 24.2 | Oversight
|  | WBS 61 | Water systems | -78.4 | Once through potable water system for vacuum pumps only
|  | WBS 75 | Machine assy preparations | -19.578 | Eliminate TC floor resurface and completion of control rm floors
|  | WBS 75 | Machine assembly | -135 | 2 shift ops on select tasks (reduced support crews | -209.781
|  | WBS 81 | Project management office | -88.8 | Anticipated FY06 rate variance and allocations
|  | WBS 82 | Proj Engr (Reierson,Dudek, Simmons) | 77.911 | Increased RLM oversight and Project engineering
|  | WBS 82 | Design Integration (brown, Designer) | 58.672 | Increase designer and engineer time for global design interface.
|  | WBS 82 | Systems Analysis (Brooks) | 72.87 | Global machine modeling and analysis
|  | WBS 82 | Dimensional Control (Stratton, Raftopolous) | 66.166 | Dimensional control supervision.
|  | WBS 85 | wbs 85 PTP & ISTP startup | -396.6 | Reduced operational and startup procdures plus allocation of startup staff
-748.381
* includes anticipated rates variances

## EC36 vs EC38 job comparision
ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 |  | ecp36 | ecp36 | ecp38 - 36
JJJJ | ACT CODE | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL
| 1101 | 0.1 | [6 empty] | 0.1 | 1101 | 1101 | 0.06 | 0.04
| 1201 | 424.4 | [6 empty] | 424.4 | 1201 | 1201 | 424.42 | -0.02 | 204.34 | vv dsn | 6
| 1202 | 793 | 998.2 | [5 empty] | 1791.2 | 1202 | 1202 | 1791.18 | 0.02
| 1203 |  | 624.8 | 315.1 | 155.3 |  |  |  | 1095.2 | 1203 | 1203 | 943.53 | 151.67
| 1204 |  |  |  | 187.4 | 182.6 | 89.4 |  | 459.4 | 1204 | 1204 | 557.24 | -97.84 | vv hw |  | 8
| 1206 |  | 3.4 | 14.2 |  |  |  |  | 17.6 | 1206 | 1206 | 17.64 | -0.04
| 1250 |  | 36.9 | 3041.9 | 2627.7 | 12.2 |  |  | 5718.7 | 1250 | 1250 | 5665.99 | 52.71
| 1301 | 91.7 | 333.9 | 397.9 |  |  |  |  | 823.5 | 1301 | 1301 | 837.4 | -13.9
| 1302 |  |  | 20.5 | 12.5 | 219.1 |  |  | 252.1 | 1302 | 1302 | 253.18 | -1.08
| 1350 |  |  | 256 | 377.9 |  |  |  | 633.9 | 1350 | 1350 | 399.59 | 234.31
| 1351 |  |  | 165.9 | 631.3 | 53.3 | 5.9 |  | 856.4 | 1351 | 1351 | 1318.24 | -461.84
| 1352 |  |  |  | 1.3 | 10.1 | 884.5 |  | 895.9 | 1352 | 1352 | 1361.87 | -465.97 | pf1a |  | 23
| 1353 |  |  |  |  | 82.4 | 183.4 |  | 265.8 | 1353 | 1353 | 270.3 | -4.5
| 1354 |  |  |  |  | 103.4 |  |  | 103.4 | 1354 | 1354 | 257.67 | -154.27 | trim coils |  | 24
| 1355 |  |  |  |  | 70.7 | 20.5 |  | 91.2 | 1355 | 1355 | 91.87 | -0.67
| 1361 |  |  |  | 254.9 | 378 | 26.9 |  | 659.8 | 1361 |  |  | 659.8 | 432.27 | tf | 10
| 1401 | 303 | [6 empty] | 303 | 1401 | 1401 | 303.04 | -0.04
| 1402 | 239.1 | [6 empty] | 239.1 | 1402 | 1402 | 239.14 | -0.04
| 1403 |  | 1798.7 | 863.1 | 84.4 |  |  |  | 2746.2 | 1403 | 1403 | 3148.64 | -402.44 | 520.36 | mc dsn | 5
| 1404 | 586 | 1625.8 | 321.6 |  |  |  |  | 2533.4 | 1404 | 1404 | 2533.52 | -0.12
| 1405 | 168.1 | [6 empty] | 168.1 | 1405 | 1405 | 168.07 | 0.03
| 1406 | 831.1 | 1266.5 | 116 |  |  |  |  | 2213.6 | 1406 | 1406 | 2213.59 | 0.01
| 1407 | 267.6 | 2236.3 | 19.2 |  |  |  |  | 2523.1 | 1407 | 1407 | 2522.99 | 0.11
| 1408 | 29.8 | 2.5 | 506.9 | 1065.6 | 166.8 | 6.8 |  | 1778.4 | 1408 | 1408 | 1852.61 | -74.21
| 1409 |  | 363.8 | 490.1 |  |  |  |  | 853.9 | 1409 | 1409 | 853.95 | -0.05
| 1410 |  |  | 1080.2 |  |  |  |  | 1080.2 | 1410 | 1410 | 1080.21 | -0.01
| 1411 |  | 20.4 | 3748.7 | 4102.5 | 564 |  |  | 8435.6 | 1411 | 1411 | 8367.06 | 68.54 | mcwf title iii |  | 18
| 1412 |  |  | 540.4 |  |  |  |  | 540.4 | 1412 | 1412 | 540.44 | -0.04
| 1413 |  |  | 23.2 |  |  |  |  | 23.2 | 1413 | 1413 | 23.17 | 0.03
| 1414 |  |  | 46 | 129.8 | 31 |  |  | 206.8 | 1414 | 1414 | 169.94 | 36.86
| 1415 |  |  | 14.8 |  |  |  |  | 14.8 | 1415 | 1415 | 14.85 | -0.05
| 1416 |  |  | 65.1 | 684.4 |  |  |  | 749.5 | 1416 |  |  | 749.5
| 1421d |  |  | 65.8 | 107.5 |  |  |  | 173.3 |  |  |  | 173.3
| 1421h |  |  |  |  | 655.097 |  |  | 655.097 | 1421 |  |  | 655.097 |  | interface hw | 15
| 1451 |  |  | 56.9 | 2393.7 | 2536.8 | 80.3 |  | 5067.7 | 1451 | 1451 | 5082.4 | -14.7 |  | winding | 7
| 1501 |  | 34.6 | 44.3 | 130.6 |  |  |  | 209.5 | 1501 | 1501 | 221.48 | -11.98
| 1550 |  |  |  |  | 1173 | 4.7 |  | 1177.7 | 1550 | 1550 | 1191.47 | -13.77
| 1601 |  |  |  |  | 660 | 475 |  | 1135 | 1601 | 1601 | 1139.98 | -4.98
| 1701 | 12.2 | 80.9 | 100.1 | 5.5 | 304.4 |  |  | 503.1 | 1701 | 1701 | 504.49 | -1.39
| 1751 |  |  |  |  | 5.6 | 527.8 | 7.1 | 540.5 | 1751 | 1751 | 541.48 | -0.98
| 1752 |  |  |  |  | 308.1 | 3.3 |  | 311.4 | 1752 | 1752 | 314.97 | -3.57
| 1801 | 60.8 | [6 empty] | 60.8 | 1801 | 1801 | 60.8 | 0
| 1802 |  | 164.6 | 146.2 | 350.2 | 411.6 | 355.5 |  | 1428.1 | 1802 | 1802 | 1444.46 | -16.36
| 1803 |  |  | 615.9 | 464.2 | 107.6 | 10.4 |  | 1198.1 | 1803 | 1803 | 1219.66 | -21.56 | -50 | I set of fixture | 16
| 1804 |  | 198 | 171.6 | 79.1 | 11 | 11.1 | 11.6 | 482.4 | 1804 | 1804 | 501.77 | -19.37 | -40 | 350c bakeout | 9
| 1810 |  |  |  | 282.4 | 1174.1 | 676.5 |  | 2133 | 1810 | 1810 | 2203.28 | -70.28
| 1901 | 254.2 | 640.7 | 580.8 | 515.7 | 361.6 | 251.5 | 153.7 | 2758.2 | 1901 | 1901 | 2738.1 | 20.1
| 2001 | 63.7 | [6 empty] | 63.7 | 2001 | 2001 | 63.67 | 0.03
| 2101 |  |  |  |  | 52.7 | 35.4 |  | 88.1 | 2101 | 2101 | 86.54 | 1.56
| 2201 |  |  |  |  | 125.5 | 229.7 |  | 355.2 | 2201 | 2201 | 348.88 | 6.32
| 2501 | 123 | 161.4 | [5 empty] | 284.4 | 2501 | 2501 | 284.37 | 0.03
| 3101 |  |  | 100.2 | 307 | 65.7 | 15.2 |  | 488.1 | 3101 | 3101 | 426.36 | 61.74 | saddleloops and term boxes |  | 17
| 3601 |  |  |  |  | 5.7 | 39.9 |  | 45.6 | 3601 | 3601 | 45.96 | -0.36
| 3801 | [5 empty] | 206.2 |  | 206.2 | 3801 | 3801 | 310.09 | -103.89 | ebeam |  | 22
| 3901 | 155.5 | 65 | 66.4 | 70.5 |  |  |  | 357.4 | 3901 | 3901 | 360.52 | -3.12
| 4101 |  | 85.8 | 18.7 | 0.1 | 288 | 29.3 |  | 421.9 | 4101 | 4101 | 430.17 | -8.27
| 4301 |  |  | 156.9 | 38.4 | 214.5 |  |  | 409.8 | 4301 | 4301 | 453.94 | -44.14
| 4401 |  | 1.1 | 4.4 |  | 842.5 | 431.3 | 17.8 | 1297.1 | 4401 | 4401 | 1308.88 | -11.78
| 4501 | 112.3 | 29.9 | 47.5 | 129.2 | 350.4 | 437.7 |  | 1107 | 4501 | 4501 | 1106.78 | 0.22
| 4601 | 1.3 | [6 empty] | 1.3 | 4601 | 4601 | 1.3 | 0
| 5101 | [5 empty] | 280.4 |  | 280.4 | 5101 | 5101 | 282.69 | -2.29
| 5201 |  |  |  |  | 9.4 | 429.1 | 91.6 | 530.1 | 5201 | 5201 | 610.92 | -80.82 | -100 | plasama control | 20
| 5301 |  |  |  |  | 11.1 | 299.1 | 18.9 | 329.1 | 5301 | 5301 | 351.01 | -21.91
| 5401 | [5 empty] | 195.8 |  | 195.8 | 5401 | 5401 | 220.96 | -25.16
| 5501 | [5 empty] | 179.3 |  | 179.3 | 5501 | 5501 | 161.65 | 17.65
| 5601 | [5 empty] | 325.5 |  | 325.5 | 5601 | 5601 | 381.94 | -56.44
| 5801 | 11.9 | 16 | 12.5 |  |  |  |  | 40.4 | 5801 | 5801 | 40.36 | 0.04
| 6101 | [5 empty] | 92.3 |  | 92.3 | 6101 | 6101 | 94.51 | -2.21
| 6163 |  | 15 | [5 empty] | 15 | 6163 | 6163 | 15 | 0
| 6201 |  |  |  |  | 41.8 | 413.2 |  | 455 | 6201 | 6201 | 463.26 | -8.26
| 6301 | [5 empty] | 106.9 |  | 106.9 | 6301 | 6301 | 109.3 | -2.4
| 6501 | 9.4 | [6 empty] | 9.4 | 6501 | 6501 | 9.38 | 0.02
| 7101 | 32.2 | [6 empty] | 32.2 | 7101 | 7101 | 32.15 | 0.05
| 7201 |  |  |  |  | 9.1 |  |  | 9.1 | 7201 | 7201 | 8.02 | 1.08
| 7301 |  |  | 120.7 |  | 38.3 |  |  | 159 | 7301 | 7301 | 164.42 | -5.42
| 7401 | 164 | 238.2 | 213.6 | 17.6 | 188.5 | 496.1 | 257 | 1575 | 7401 | 7401 | 1564.76 | 10.24
| 7501 | [5 empty] | 831.3 | 232.1 | 1063.4 | 7501 | 7501 | 1054.34 | 9.06
| 7502 |  |  |  |  | 74.6 |  |  | 74.6 | 7502 | 7502 | 57.17 | 17.43
| 7503 | [5 empty] | 833.1 | 451.4 | 1284.5 | 7503 | 7503 | 1254.04 | 30.46
| 7601 | [5 empty] | 176.4 | 61.4 | 237.8 | 7601 | 7601 | 238.25 | -0.45
| 8101 | 387.3 | 873.1 | 696.1 | 634.6 | 662.1 | 554.5 | 132.3 | 3940 | 8101 | 8101 | 4110.21 | -170.21 | -53.91 | project mgmt
| 8102 | 58.6 | 88 | 95.4 | 173.6 | 50.5 | 36.7 |  | 502.8 | 8102 | 8102 | 386.5 | 116.3
| 8202 | 295.5 | 669.6 | 669.3 | 625.6 | 239.6 | 246 | 62.8 | 2808.4 | 8202 | 8202 | 2834.97 | -26.57 | 84.01 |  | 19
| 8203 | 178.8 | 372.6 | 171 | 140.2 | 132.5 | 0.5 |  | 995.6 | 8203 | 8203 | 1116.34 | -120.74 | wbs 82
| 8204 | 44.6 | 188.8 | 256.6 | 225.4 |  |  |  | 715.4 | 8204 | 8204 | 600.93 | 114.47
| 8205 |  |  | 109.5 | 189.3 | 73.8 | 76.1 |  | 448.7 | 8205 | 8205 | 331.85 | 116.85
| 8401 | 210.3 | 113.8 | [5 empty] | 324.1 | 8401 | 8401 | 324.5 | -0.4
| 8402 | 41 | 104.9 | [5 empty] | 145.9 | 8402 | 8402 | 145.86 | 0.04
| 8501 | [5 empty] | 365.1 | 834.2 | 1199.3 | 8501 | 8501 | 1189.18 | 10.12
| 8998 | 112 | 260.7 | 350.8 | 329.8 | 331.5 | 167.7 |  | 1552.5 | 8998 | 8998 | 1576.89 | -24.39
|  | 6062.5 | 13713.9 | 16918 | 17525.2 | 13390.297 | 11143.3 | 2331.9 | 81085.097 |  | CCCP | 11984 |  | 945.777
[11 empty] | DCMA | 75 |  | -205.24 | other
| cont |  |  |  | 1295.7 | 2518.3 | 4756.7 | 1051 | 9621.7 |  |  |  | 740.537 |  | o
| cv |  |  | 1593
|  | 6062.5 | 13713.9 | 18511 | 18820.9 | 15908.597 | 15900 | 3382.9 | 92299.797
| ba |  |  |  | 18830 | 15900 | 15900 | 3383
| cum plan | 6062.5 | 19776.4 | 38287.4 | 57108.3 | 73016.897 | 88916.897 | 92299.797 | 74 | 92373.797
| ba cum |  |  | 41243 | 57143 | 73043 | 88943 | 92326 | 75 | 92401
|  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL
[5 empty] | 42 | 44 | 38 | 11 | 135
[5 empty] | 1253.7 | 2474.3 | 4718.7 | 1040
[5 empty] | 57108.3 | 73016.897 | 88916.897 | 92299.797
[5 empty] | 9621.7 | 21.68%
|  |  |  | 38312.887 | 44390.697 |  |  |  | 82703.584
[8 empty] | dcma | 75
92400.284

## Contingency Analysis may06
| Proposed PMB | ETC | Contingency | % | Nov05 lehman | ECP36 %
12 - Vacuum Vessel Systems (wo/VVSA) | 4618.83 | 627.947 | 103.608 | 16.5% | 24% | 36% | 12 | 3245017.8509 | 525152.663 | 16.18%
VVSA Contract | 5135.441 | 1059.311 | 52.95 | 4.999% | 10%
13 - Conventional Coils | 5252.023 | 3154.943 | 512.905 | 16.26% | 38% | 43% | 13 | 3309741.3526 | 1115143.3807 | 33.69%
14 - Modular Coils (wo/MCWF) | 24392.233 | 6830.118 | 1477.603 | 21.63% | 29% | 42% | 14 | 12601589.3299 | 2799408.4942 | 22.21%
MCWF Contract | 9079.115 | 3316.002 | 410 | 12.36% | 10%
15 - Structures | 1325.349 | 1247.719 | 398.126 | 31.91% | 30% |  | 15 | 1307049.946 | 417047.5191 | 31.91%
16 - Coil Services | 1137.792 | 1131.648 | 280.748 | 24.81% | 30% |  | 16 | 1135012.25 | 281714.5902 | 24.82%
17 - Cryostat and Base Support Struct | 1578.486 | 1164.09 | 344.644 | 29.61% | 30% |  | 17 | 1155896.5262 | 338949.1774 | 29.32%
18 - Field Period Assembly | 6006.76 | 4233.121 | 1987.101 | 46.94% | 30% | 42% | 18 | 3945762.16 | 1411742.832 | 35.78%
19 - Stellarator Core Mgt & Integr | 2769.538 | 1024.933 | 102.493 | 10% | 10% |  | 19 | 1282096.445 | 128209.6445 | 10%
1 Stellarator Core Systems | 61295.567 | 23789.832 | 5670.178 | 23.83% | 25.04% | 29% | 1 | 27982165.8607 | 7017368.3012 | 25.08%
2 Heating, Fueling & Vac Sys | 484.874 | 137.25 | 19.215 | 14% | 14% |  | 21 | 88092.99 | 12333.0186
3 Diagnostics | 994.53 | 292.843 | 87.807 | 29.98% | 24% | 31%
4 Electrical Power Sys | 3104.307 | 2452.585 | 477.399 | 19.47% | 20% |  | 22 | 355156.69 | 49721.9366
5 Central I&C Sys | 842.315 | 808.879 | 78.238 | 9.672% | 10% |  | 2 | 443249.68 | 62054.9552 | 14%
6 Facility Sys | 600.863 | 576.209 | 115.242 | 20% | 20% |  | 25 | 0 | 0
7 Test Cell Prep & MachAssy | 4436.766 | 3498.828 | 1008.48 | 28.82% | 22%
8 Project Oversight & Support | 12662.936 | 4939.142 | 446.48 | 9.04% | 13% | 15% | 31 | 357766.5088 | 107329.9527
subtotal | 84422.158 | 36495.568 | 7903.039 | 21.65% | 21.65% | 25%
Contingency | 7903.842 | [5 empty] | 36 | 45581.15 | 9116.23
TEC = | 92326
DCMA | 75 | [5 empty] | 38 | 206196.8 | 70106.912
92401
[7 empty] | 39 | 70515.03 | 21154.509
[7 empty] | 3 | 680059.4888 | 207707.6037 | 30.54%
[7 empty] | 41 | 314949.46 | 56690.9028
[7 empty] | 43 | 298006.764 | 53641.2175
[7 empty] | 44 | 1289552.6376 | 252769.5932
[7 empty] | 45 | 916464.64 | 185703.9856
[7 empty] | 46 | 0 | 0
[7 empty] | 4 | 2818973.5016 | 548805.6991 | 19.47%
[7 empty] | 51 | 280385.9 | 14019.295
[7 empty] | 52 | 530112.41 | 53011.241
[7 empty] | 53 | 329072.83 | 52651.6528
[7 empty] | 54 | 195823.11 | 27415.2354
[7 empty] | 55 | 179331.4 | 14346.512
[7 empty] | 56 | 325498.85 | 26039.908
[7 empty] | 57 | 0 | 0
[7 empty] | 58 | 0 | 0
VVSA Contract | 5135.441 | 1059.311 | 52.95 | 4.999% |  |  | 5 | 1840224.5 | 187483.8442 | 10.19%
|  |  |  | #DIV/0! |  |  | 61 | 92271.78 | 18454.356
#DIV/0!
|  |  |  | #DIV/0! |  |  | 62 | 455033.04 | 91006.608
#DIV/0!
|  |  |  | #DIV/0! |  |  | 63 | 106903.92 | 21380.784
#DIV/0!
|  |  |  | #DIV/0! |  |  | 64 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! |  |  | 65 | 0 | 0
MCWF Contract | 9079.115 | 3316.002 | 410 | 12.36% |  |  |  | 654208.74 | 130841.748 | 20%
|  |  |  | #DIV/0! |  |  | 71 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! |  |  | 72 | 9097.92 | 909.792
#DIV/0!
|  |  |  | #DIV/0! |  |  | 73 | 37599.901 | 3643.5385
#DIV/0!
|  |  |  | #DIV/0! |  |  | 74 | 956980.383 | 145873.4182
#DIV/0!
|  |  |  | #DIV/0! |  |  | 75 | 2422508.16 | 585652.9824
#DIV/0!
|  |  |  | #DIV/0! |  |  | 76 | 237778.59 | 57066.8616
WBS 12-18 | 44311.473 | 18389.586 | 5104.735 | 27.76% |  |  | 7 | 3663964.954 | 793146.5927 | 21.65%
|  |  |  | #DIV/0! |  |  | 81 | 2244301.07 | 112320.2535
#DIV/0!
|  |  |  | #DIV/0! |  |  | 82 | 2011860.24 | 168437.388
#DIV/0!
|  |  |  | #DIV/0! |  |  | 84 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! |  |  | 85 | 1199387.27 | 310999.399
#DIV/0!
|  |  |  | #DIV/0! |  |  | AA | 828888.41 | 82888.841
WBS 2-7 & 85 (BOP) | 11662.655 | 8965.594 | 2097.381 | 23.39% |  |  | 8 | 6284436.99 | 674645.8815 | 10.74%
WBS 19,81 & 82 | 14233.474 | 4765.075 | 237.973 | 4.994% |  |  | Total Sum of Contingency $ | 44367283.7151 | 9622054.6255 | 21.69%
| 84422.158 | 36495.568 | 7903.039 | 21.65%
VVSA,MCWF,&TF Contract | 15837.556 | 5998.313 | 624.95 | 10.42%
Balance of Project | 68584.602 | 30497.255 | 7278.089 | 23.86%

## LEHMAN WORKSHEET
WBS | WBS Title | Project Estimate | [5 empty] | DOE Assessment |  |  |  |  | Variance ($K) | Comments | Comment
|  | Base Cost ($K) | Base To Date | Base To Go | Contingency |  | Total ($K) | To Date | To Go | Contingency |  | Total ($K)
|  |  | Cost | Cost | % | $ |  | Cost | Cost | $ | %
1 | Stellarator Core Systems | 57728100 | 29727000 | 28001100 | 24.56% | 6878349 | 64606449
11 | In Vessel Components |  | 0 | 0 |  |  | 0
12 | Vacuum Vessel Systems | 9439300 | 6191000 | 3248300 | 13.91% | 451892 | 9891192
13 | Conventional Coils | 4831000 | 1515000 | 3316000 | 38.24% | 1267951 | 6098951
14 | Mod Coils | 31355900 | 18753000 | 12602900 | 22.01% | 2773324 | 34129224
15 | Coil Support Structures | 1386200 | 75000 | 1311200 | 29.83% | 391108 | 1777308
16 | Coil Services | 1135000 | 0 | 1135000 | 30% | 340504 | 1475504
17 | Cryostat & Base Support Structure | 1532900 | 372000 | 1160900 | 29.87% | 346769 | 1879669
18 | Field Period Assembly | 5280800 | 1336000 | 3944800 | 29.88% | 1178591 | 6459391
19 | Stellarator Core Mgmt. & Integration | 2767000 | 1485000 | 1282000 | 10% | 128210 | 2895210
2 | Plasma Heating Fueling & Vac Systems | 791300 | 347400 | 443900 | 13.98% | 62054.9552 | 853354.9552
21 | Fueling Systems | 88100 |  | 88100 | 14% | 12333.0186 | 100433.0186
22 | Torus Vacuum Pump | 418800 | 63000 | 355800 | 13.97% | 49721.9366 | 468521.9366
23 | Wall Conditioning System |  |  | 0 |  |  | 0
25 | Neutral Beam Injection System | 284400 | 284400 | 0 |  |  | 284400
3 | Diagnostics | 1148700 | 405000 | 743700 | 23.63% | 175717.142 | 1324417.142
31 | Magnetic Diagnostics | 551600 | 131000 | 420600 | 21.27% | 89442 | 641042
35 | Profile Diagnostics |  |  | 0 |  |  | 0
36 | Edge & Divertor Diagnostics | 45600 |  | 45600 | 19.99% | 9116.23 | 54716.23
38 | Electron Beam (EB) Mapping | 206200 |  | 206200 | 34% | 70106.912 | 276306.912
39 | Diagnostics Integration | 345300 | 274000 | 71300 | 9.891% | 7052 | 352352
4 | Electrical Power Systems | 3305100 | 527000 | 2778100 | 19.75% | 548805.6991 | 3853905.6991
41 | AC Power | 423900 | 107000 | 316900 | 17.89% | 56690.9028 | 480590.9028
42 | AC/DC Converter |  |  | 0 |  |  | 0
43 | DC Systems | 478800 | 226000 | 252800 | 21.22% | 53641.2175 | 532441.2175
44 | Control & protection system | 1346000 | 55000 | 1291000 | 19.58% | 252769.5932 | 1598769.5932
45 | Power System Design & Integration | 1055100 | 138000 | 917100 | 20.25% | 185703.9856 | 1240803.9856
46 | FCPC Building Modification | 1300 | 1000 | 300 | 0% |  | 1300
5 | Central I&C Systems | 1873585 | 33400 | 1840185 | 10.19% | 187483.8442 | 2061068.8442
51 | TCP/IP Infrastructure System | 280385 |  | 280385 | 5% | 14019.295 | 294404.295
52 | Central Instrumentation & Controls System | 530100 |  | 530100 | 10% | 53011.241 | 583111.241
53 | Data Acquisition & Facility Computing | 329100 |  | 329100 | 16% | 52651.6528 | 381751.6528
54 | Facility Timing & Synchronization System | 195800 |  | 195800 | 14% | 27415.2354 | 223215.2354
55 | Real Time Plasma & Power Control Systems | 179300 |  | 179300 | 8.001% | 14346.512 | 193646.512
56 | Central Safety Interlock System | 325500 |  | 325500 | 8% | 26039.908 | 351539.908
57 | Control Room Facility |  |  | 0 |  |  | 0
58 | Central I&C management and Integration | 33400 | 33400 | 0 |  |  | 33400
6 | Facility Systems | 678200 | 24000 | 654200 | 20% | 130841.748 | 809041.748
61 | Water Cooling Systems | 92300 | 15000 | 77300 | 23.87% | 18454.356 | 110754.356
62 | Cryogenic System | 455000 |  | 455000 | 20% | 91006.608 | 546006.608
63 | Utility Systems | 106900 | 9000 | 97900 | 21.84% | 21380.784 | 128280.784
64 | Bakeout System |  |  | 0 |  |  | 0
65 | Facility System | 24000 |  | 24000 | 0% |  | 24000
7 | Test Cell Preparation & Machine Assy | 4555200 | 900200 | 3655000 | 21.7% | 793146.5927 | 5348346.5927
71 | Shield Wall Reconfiguration | 32200 | 32200 | 0 |  | 0 | 32200
72 | Control Room Refurbishment | 9100 | 0 | 9100 | 9.998% | 909.792 | 10009.792
73 | Platform Design | 109100 | 73000 | 36100 | 10.09% | 3643.5385 | 112743.5385
74 | Planning/Oversight | 1753200 | 795000 | 958200 | 15.22% | 145873.4182 | 1899073.4182
75 | Machine Assembly Planning & Oversight | 2413800 |  | 2413800 | 24.26% | 585652.9824 | 2999452.9824
76 | Tooling Design & Fabrication | 237800 |  | 237800 | 24% | 57066.8616 | 294866.8616
8 | Project Oversight & Support | 12633000 | 6349900 | 6283100 | 13.31% | 836075.4935 | 13469075.4935
81 | Project Management & Control | 4452900 | 2209000 | 2243900 | 11.09% | 248820.2535 | 4701720.2535
82 | Project Engineering | 4904100 | 2891000 | 2013100 | 9.605% | 193367 | 5097467
83 | Environmental & Safety/QA/QC in overhead |  |  | 0 |  |  | 0
84 | Project Physics | 469900 | 469900 | 0 |  |  | 469900
85 | Integrated System Testing | 1197700 | 0 | 1197700 | 25.97% | 310999.399 | 1508699.399
A | Allocations | 1608400 | 780000 | 828400 | 10.01% | 82888.841 | 1691288.841
| TOTAL | 82713185 | 38313900 | 44399285 | 21.65% | 9612474.4747 | 92325659.4747 |  |  |  |  | 0 | -92325659.4747
| DCMA | 75000 |  |  |  |  | 75000
|  | 82788185 |  |  |  |  | 92400659.4747
ECP-38
[16 empty] | 12 - Vacuum Vessel Systems | 9439.3 | 9439300
[16 empty] | 13 - Conventional Coils | 4831 | 4831000
[16 empty] | 14 - Modular Coils | 31355.9 | 31355900
[16 empty] | 15 - Structures | 1386.2 | 1386200
[16 empty] | 16 - Coil Services | 1135 | 1135000
[16 empty] | 17 - Cryostat and Base Support Structure | 1532.9 | 1532900
[16 empty] | 18 - Field Period Assembly | 5280.8 | 5280800
[16 empty] | 19 - Stellarator Core Management and Integration | 2767 | 2767000
[16 empty] | 21 - Fueling Systems | 88.1 | 88100
[16 empty] | 22 - Torus Vacuum Pumping Systems | 418.8 | 418800
[16 empty] | 25 - Neutral Beam Injection System | 284.4 | 284400
[16 empty] | 31 - Magnetic Diagnostics | 551.6 | 551600
[16 empty] | 36 - Edge and Divertor Diagnostics | 45.6 | 45600
[16 empty] | 38 - Electron Beam (EB) Mapping | 206.2 | 206200
[16 empty] | 39 - Diagnostics Integration | 345.3 | 345300
[16 empty] | 41 - AC Power | 423.9 | 423900
[16 empty] | 43 - DC Systems | 478.8 | 478800
[16 empty] | 44 - Control and protection Systems | 1346 | 1346000
[16 empty] | 45 - Power System Design and Integration | 1055.1 | 1055100
[16 empty] | 46 - FCPC Building Modifications | 1.3 | 1300
[16 empty] | 51 - TCP/IP Infrastructure Systems | 308.3 | 308300
[16 empty] | 52 - Central Instrumentation & Control | 530.1 | 530100
[16 empty] | 53 - Data Acquisition & Facility Computing | 329.1 | 329100
[16 empty] | 54 - Facility Timing & Synchronization | 195.8 | 195800
[16 empty] | 55 - Real Time Plasma & Power Supply Control Sys | 179.3 | 179300
[16 empty] | 56 - Central Safety Interlock Systems | 325.5 | 325500
[16 empty] | 58 - Central I&C management and Integration | 5.5 | 5500
[16 empty] | 61 - Water Systems | 92.3 | 92300
[16 empty] | 62 - Cryogenic Systems | 455 | 455000
[16 empty] | 63 - Utility Systems | 106.9 | 106900
[16 empty] | 65 - Facility Systems Integration | 24 | 24000
[16 empty] | 71 - Shield Wall Seismic Modifications | 32.2 | 32200
[16 empty] | 72 - Control Room Refurbishment | 9.1 | 9100
[16 empty] | 73 - Platform Design & Fabrication | 109.1 | 109100
[16 empty] | 74 - Machine Assembly Planning and Oversight | 1753.2 | 1753200
[16 empty] | 75 - Test Cell and Basement Assembly Operations | 2413.8 | 2413800
[16 empty] | 76 - Tooling Design & Fabrication | 237.8 | 237800
[16 empty] | 81 - Project Management and Control | 4452.9 | 4452900
[16 empty] | 82 - Project Engineering | 4904.1 | 4904100
[16 empty] | 84 - Project Physics | 469.9 | 469900
[16 empty] | 85 - Integrated Systems Testing | 1197.7 | 1197700
[16 empty] | PPPL Allocations | 1608.4 | 1608400
[17 empty] | 82713.2 | 82713200
Note on O4: SC: The committee believes that the NCSX Team has made a credible estimate of the base costs and applied an appropriate level of contingency made on the basis of technical and schedule risk. The base costs estimates have benefited significantly from preliminary manufacturing feasibility studies performed by potential vendors of both the Modular Coil forms and the Vacuum Vessel. The NCSX Team has performed significant analysis of the components deemed to be the most technically risky (modular coils and VV). They have included an appropriate level of manufacturing R&D to mitigate these risks.
Note on O14: SC: Refurbishment of existing systems.
Note on O19: SC: Viable budget estimate for planned effort using new hardware.
Note on O25: SC: All technology and costing data drawn from NSTX.
Note on O32: SC: Install computers & networks & connect existing software systems for controls and data acquisition.
Note on O33: SC: Layout and install standard computer networks.
Note on O34: SC: EPICS control configuration and testing for 5 systems--lots of experience.
Note on O35: SC: Install computer hardware and configure MDS Plus data acquisition--lots of experience
Note on O36: SC: Design and deploy timing and synchronization system based on NSTX.
Note on O37: SC: Clone NSTX real-time control systems
Note on O38: SC: Layout and install safety interlock systems
Note on O39: SC: Computers for first plasma and PA system in control room
Note on O41: SC: Extensive use of existing systems with refurbishing. Recent experience with NSTX for cost estimates
Note on O54: SC: Cost reasonable based on review

## ECP38 reconciliation
NCSX rebaseline reconciliation
|  | ECP-036 | ECP-39 | Changes
111 - Limiters
12 - Vacuum Vessel Systems | [6 empty] | etc | ETC/rates | cv
| 121 - Vacuum Vessel Assembly | 8548.22 | 8630 | 81.78 | 121 | 8630 | 8698 | 149.78 | -68
| 122 - Vacuum Vessel Thermal Insulation | 191.89 | 172.3 | -19.59 | 122 | 172.3 | 172.3 | -19.59
| 123 - Vacuum Vessel Heating and Cooling Distrib | 535.98 | 364.9 | -171.08 | 123 | 364.9 | 364.9 | -171.08
| 124 - Vacuum Vessel Supports | 106.1 | 247.5 | 141.4 | 124 | 247.5 | 247.5 | 141.4
| 125 - Vacuum Vessel Local I&C | 17.64 | 24.6 | 6.96 | 125 | 24.6 | 24.6 | 6.96
| subtotal | 9399.83 | 9439.3 | 39.47 |  | -68 |  | 107.47 | -68
13 - Conventional Coils | [5 empty] | 0 |  | 0
| 130 - Conventional Coil Design | 837.4 | 837.4 | 0 | 130 | 837.4 | 837.4 | 0
| 131 - TF Coils | 1717.83 | 2399 | 681.17 | 131 | 2399 | 2153 | 435.17 | 246
| 132 - PF Coils | 1885.36 | 1400 | -485.36 | 132 | 1400 | 1400 | -485.36
| 133 - External Trim Coils | 257.67 | 103.4 | -154.27 | 133 | 103.4 | 103.4 | -154.27
| 134 - Conventional Coil Local | 91.87 | 91.2 | -0.67 | 134 | 91.2 | 91.2 | -0.67
| subtotal | 4790.13 | 4831 | 40.87 |  | 246 |  | -205.13 | 246
14 - Modular Coils | [5 empty] | 0 |  | 0
| 141 - Modular Coil Winding Form | 13271.57 | 12727 | -544.57 | 141 | 12727 | 12437 | -834.57 | 290
| 142 - Modular Coil Windings and Assembly | 11978.769 | 14580.5 | 2601.731 | 142 | 14580.5 | 13956.5 | 1977.731 | 624
| 143 - Modular Coil Local I&C | 0 | 0 | 0 |  | 0 |  | 0
| 144 - Modular Coil Winding Facility & Fixtures | 3863.201 | 4048.4 | 185.199 | 144 | 4048.4 | 3918.4 | 55.199 | 130 | 1044
| subtotal | 29113.54 | 31355.9 | 2242.36 |  | 1044 |  | 1198.36 | 1044
15 - Structures | [5 empty] | 0 |  | 0
| 151 - Coil Support Structure | 1412.96 | 1386.2 | -26.76 | 151 | 1386.2 | 1387.2 | -25.76 | -1
16 - Coil Services | [5 empty] | 0 |  | 0
| 161 - LN2 Distribution | 372.04 | 368.5 | -3.54 | 161 | 368.5 | 368.5 | -3.54
| 162 - Electrical Leads | 681.64 | 681 | -0.64 | 162 | 681 | 681 | -0.64
| 163 - Coil Protection System | 86.3 | 85.5 | -0.8 | 163 | 85.5 | 85.5 | -0.8
| subtotal | 1139.98 | 1135 | -4.98 |  | -1 |  | -4.98 | -1
17 - Cryostat and Base Support Structure | [5 empty] | 0 |  | 0
| 171 -Cryostat | 934.01 | 1105.2 | 171.19 | 171 | 1105.2 | 927.2 | -6.81 | 178
| 172 - Base Support Structure | 426.93 | 427.7 | 0.77 | 172 | 427.7 | 427.7 | 0.77
| 173-Spacer manipulator | 0 | 0 | 0 |  | 0 |  | 0
| subtotal | 1360.94 | 1532.9 | 171.96 |  | 178 |  | -6.04 | 178
18 - Field Period Assembly | [5 empty] | 0 |  | 0
| 181 - Field Period Assembly Planning/Oversight | 1505.26 | 1545.8 | 40.54 | 181 | 1545.8 | 1488.8 | -16.46 | 57
| 182 - TFTR Test Cell Area preparations | 0 | 70.3 | 70.3 | 182 | 70.3 | 70.3 | 70.3
| 183 - Receive Inspect and Test Coils | 0 | 0 | 0 |  | 0 |  | 0
| 184 - Receive Inspect and Test VV | 0 | 0 | 0 |  | 0 |  | 0
| 185 - Assemble Field Periods | 2203.28 | 2063.2 | -140.08 | 185 | 2063.2 | 2063.2 | -140.08
| 186 - Tooling Design and Fabrication | 1219.66 | 1051.1 | -168.56 | 186 | 1051.1 | 1199.1 | -20.56 | -148
| 187 - Measurement Systems | 501.77 | 550.4 | 48.63 | 187 | 550.4 | 482.4 | -19.37 | 68 | -23
| subtotal | 5429.97 | 5280.8 | -149.17 |  | -23 |  | -126.17 | -23
19 - Stellarator Core Management and Integration | [5 empty] | 0 |  | 0
| 191 - Stellarator Core Management & Oversight | 1041.61 | 1054.2 | 12.59 | 191 | 1054.2 | 1045.2 | 3.59 | 9
| 192 - Stellarator Core Integration & Analysis | 1696.49 | 1712.9 | 16.41 | 192 | 1712.9 | 1712.9 | 16.41
| subtotal | 2738.1 | 2767.1 | 29 |  | 9 |  | 20 | 9
| SUBTOTAL WBS 1 | 55385.45 | 57728.2 | 2342.75 |  | 1384 |  | 957.75 | 1384
[6 empty] | 0 |  | 0
21 - Fueling Systems |  | 86.54 | 88.1 | 1.56 | 210 | 88.1 | 88.1 | 1.56
22 - Torus Vacuum Pumping Systems |  | 412.55 | 418.8 | 6.25 | 220 | 418.8 | 418.8 | 6.25
25 - Neutral Beam Injection System |  | 284.37 | 284.4 | 0.03 | 250 | 284.4 | 284.4 | 0.03
| SUBTOTAL WBS 2 | 783.46 | 791.3 | 7.84 |  | 0 |  | 7.84 | 0
31 - Magnetic Diagnostics |  | 426.35 | 551.6 | 125.25 | 310 | 551.6 | 521.6 | 95.25 | 30
36 - Edge and Divertor Diagnostics |  | 45.96 | 45.6 | -0.36 | 360 | 45.6 | 45.6 | -0.36
38 - Electron Beam (EB) Mapping |  | 310.09 | 206.2 | -103.89 | 380 | 206.2 | 206.2 | -103.89
39 - Diagnostics Integration |  | 360.52 | 345.3 | -15.22 | 390 | 345.3 | 357.3 | -3.22 | -12
| SUBTOTAL WBS 3 | 1142.92 | 1148.7 | 5.78 |  | 18 |  | -12.22 | 18
41 - AC Power | [5 empty] | 0 |  | 0
| 411 - Auxliary AC Power Systems | 382.03 | 376.4 | -5.63 | 411 | 376.4 | 374.4 | -7.63 | 2
| 412 - Experimental AC Power Systems | 48.14 | 47.5 | -0.64 | 412 | 47.5 | 47.5 | -0.64
43 - DC Systems | [5 empty] | 0 |  | 0
| 431 - C-Site DC Systems | 453.94 | 478.8 | 24.86 | 431 | 478.8 | 409.8 | -44.14 | 69
| 432 - D-to-C Site DC Systems | 0 | 0 | 0 |  | 0 |  | 0
| 433 - D-Site DC Systems | 0 | 0 | 0 |  | 0 |  | 0
44 - Control and protection Systems | [5 empty] | 0 |  | 0
| 441 - Electrical Interlocks | 377.66 | 377 | -0.66 | 441 | 377 | 377 | -0.66
| 442 - Kirk Key Interlocks | 82.18 | 81.4 | -0.78 | 442 | 81.4 | 81.4 | -0.78
| 443 - Real Time Control Systems | 14.27 | 13.8 | -0.47 | 443 | 13.8 | 13.8 | -0.47
| 444 - Instrument Systems | 312.65 | 307.5 | -5.15 | 444 | 307.5 | 307.5 | -5.15
| 445 - Coil protection Systems | 522.1 | 566.3 | 44.2 | 445 | 566.3 | 517.3 | -4.8 | 49
45 - Power System Design and Integration | [5 empty] | 0 |  | 0
| 451 - System Design and Interfaces | 520.33 | 478.1 | -42.23 | 451 | 478.1 | 530.1 | 9.77 | -52
| 452 - Electrical Systems Support | 261.74 | 259.3 | -2.44 | 452 | 259.3 | 259.3 | -2.44
| 453 - System Testing (PTP's) | 324.72 | 317.7 | -7.02 | 453 | 317.7 | 317.7 | -7.02
[6 empty] | 0 |  | 0
46 - FCPC Building Modifications |  | 1.3 | 1.3 |  | 460 | 1.3 | 1.3 | 0
| SUBTOTAL WBS 4 | 3301.06 | 3305.1 | 4.04 |  | 68 |  | -63.96 | 68
[6 empty] | 0 |  | 0
51 - TCP/IP Infrastructure Systems |  | 282.69 | 280.4 | -2.29 | 510 | 280.4 | 280.4 | -2.29
52 - Central Instrumentation & Control |  | 610.92 | 530.1 | -80.82 | 520 | 530.1 | 530.1 | -80.82
53 - Data Acquisition & Facility Computing |  | 351.01 | 329.1 | -21.91 | 530 | 329.1 | 329.1 | -21.91
54 - Facility Timing & Synchronization |  | 220.96 | 195.8 | -25.16 | 540 | 195.8 | 195.8 | -25.16
55 - Real Time Plasma & Power Supply Control Sys |  | 161.65 | 179.3 | 17.65 | 550 | 179.3 | 179.3 | 17.65
56 - Central Safety Interlock Systems |  | 381.94 | 325.5 | -56.44 | 560 | 325.5 | 325.5 | -56.44
58 - Central I&C management and Integration |  | 40.36 | 33.4 | -6.96 | 580 | 33.4 | 40.4 | 0.04 | -7
| SUBTOTAL WBS 5 | 2049.53 | 1873.6 | -175.93 |  | -7 |  | -168.93 | -7
61 - Water Systems | [5 empty] | 0 |  | 0
| 611 - C-Site Cooling System | 0 | 0 | 0 |  | 0 |  | 0
| 612 - NB Water Cooling Systems | 0 | 0 | 0 |  | 0 |  | 0
| 613 - Vacuum Pumping System | 94.51 | 92.3 | -2.21 | 613 | 92.3 | 92.3 | -2.21
| 614 - Bakeout Water System | 0 | 0 | 0 |  | 0 |  | 0
62 - Cryogenic Systems | [5 empty] | 0 |  | 0
| 621 - LN2-LHe Supply System | 233.04 | 229 | -4.04 | 621 | 229 | 229 | -4.04
| 622 - LN2 Coil Cooling Supply | 0 | 0 | 0 | 622 | 0 |  | 0
| 623 - GN2 Cryostat Cooling System | 230.22 | 226 | -4.22 | 623 | 226 | 226 | -4.22
[6 empty] | 0 |  | 0
63 - Utility Systems |  | 109.3 | 106.9 | -2.4 | 630 | 106.9 | 106.9 | -2.4
65 - Facility Systems Integration | [5 empty] | 0 |  | 0
| 612 - NB Water Cooling Systems | 9.38 | 9.4 | 0.02 | 612 | 9.4 | 9.4 | 0.02
| 650 - Facility Systems Integration | 15 | 15 | 0 | 650 | 15 | 15 | 0
| SUBTOTAL WBS 6 | 691.45 | 678.6 | -12.85 |  | 0 |  | -12.85 | 0
71 - Shield Wall Seismic Modifications |  | 32.15 | 32.2 | 0.05 | 710 | 32.2 | 32.2 | 0.05
72 - Control Room Refurbishment |  | 8.09 | 9.1 | 1.01 | 720 | 9.1 | 9.1 | 1.01
73 - Platform Design & Fabrication |  | 164.42 | 109.1 | -55.32 | 730 | 109.1 | 159.1 | -5.32 | -50
74 - Machine Assembly Planning and Oversight |  |  |  | 0 |  | 0 |  | 0
| 740 - Machine Assembly Planning and Oversight | 152.71 | 335.8 | 183.09 | 740 | 335.8 | 157.8 | 5.09 | 178
| 741 - Planning Prior to Machine Assembly | 312.58 | 312.6 | 0.02 | 741 | 312.6 | 312.6 | 0.02
| 742 - Construction Management | 1099.47 | 1104.8 | 5.33 | 742 | 1104.8 | 1104.8 | 5.33
75 - Test Cell and Basement Assembly Operations |  |  |  | 0 |  | 0 |  | 0
| 750 - Test Cell & Basement Assembly Operations | 2365.55 | 2413.8 | 48.25 | 750 | 2413.8 | 2413.8 | 48.25
76 - Tooling Design & Fabrication |  | 238.25 | 237.8 | -0.45 | 760 | 237.8 | 237.8 | -0.45
| SUBTOTAL WBS 7 | 4373.22 | 4555.2 | 181.98 |  | 128 |  | 53.98 | 128
81 - Project Management and Control |  | 4508.81 | 4452.9 | -55.91 | 810 | 4452.9 | 4442.9 | -65.91 | 10
82 - Project Engineering |  | 4885.08 | 4904.1 | 19.02 | 820 | 4904.1 | 4969.1 | 84.02 | -65
84 - Project Physics |  | 469.93 | 469.9 | -0.03 | 840 | 469.9 | 469.9 | -0.03
85 - Integrated Systems Testing |  | 1189.18 | 1197.7 | 8.52 | 850 | 1197.7 | 1197.7 | 8.52
| SUBTOTAL WBS 8 | 11053 | 11024.6 | -28.4 |  | -55 |  | 26.6 | -55 |  | 12633
PPPL Allocations |  | 1576.89 | 1608.4 | 31.51 | AAA | 1608.4 | 1552.4 | -24.49 | 56
[6 empty] | 0 |  | 0
Contingency |  | 11969.1 | 9612 | -2357.1 | CCC | 9612
0
DCMA Support |  | 75 | 75 | 0 | DDD | 75 | 75
|  | 92401.39 | 92400.7 | -0.38 |  | 95321.7 | 81195.7 | 763.72 | 1592 | 2355.72
82713.7

## Budget Summary may06
| Current Baseline (ECP-43) | Unrecoverable Cost Variances | ETC Updates & Design Changes | Total Proposed Change |  | New PMB (ECP-44)
12 - Vacuum Vessel Systems | 9439 | 209.271 | 106 | 315.271 |  | 9754.271
13 - Conventional Coils | 4831 | 155.969 | 265.054 | 421.023 |  | 5252.023
14 - Modular Coils | 32247 | 611.518 | 612.83 | 1224.348 |  | 33471.348
15 - Structures | 1386 | 2.349 | -63 | -60.651 |  | 1325.349
16 - Coil Services | 1135 | 2.792 | 0 | 2.792 |  | 1137.792
17 - Cryostat and Base Support Struct | 1533 | 45.486 | 0 | 45.486 |  | 1578.486
18 - Field Period Assembly | 5281 | 68.76 | 657 | 725.76 |  | 6006.76
19 - Stellarator Core Mgt & Integr | 2767 | 2.538 | 0 | 2.538 |  | 2769.538
1 Stellarator Core Systems | 58619 | 1098.683 | 1577.884 | 2676.567 |  | 61295.567
2 Heating, Fueling & Vac Sys | 791 | -0.126 | -306 | -306.126 |  | 484.874
3 Diagnostics | 1149 | 64.909 | -219.379 | -154.47 |  | 994.53
4 Electrical Power Sys | 3305 | 137.018 | -337.711 | -200.693 |  | 3104.307
5 Central I&C Sys | 1874 | -0.34 | -1031.345 | -1031.685 |  | 842.315
6 Facility Sys | 679 | -0.137 | -78 | -78.137 |  | 600.863
7 Test Cell Prep & MachAssy | 4555 | 36.344 | -154.578 | -118.234 |  | 4436.766
8 Project Oversight & Support | 12634 | 239.12 | -210.184 | 28.936 |  | 12662.936
subtotal | 83606 | 1575.471 | -759.313 | 816.158 |  | 84422.158
Contingency | 8720 | -1575.471 | 759.313 | -816.158 |  | 7903.842
TEC = | 92326 | 0 | 0 | 0 |  | 92326
DCMA | 75 |  |  |  |  | 75
| 92401 |  |  |  |  | 92401
[5 empty] | ETC | 36495.567
[5 empty] | Contingency balance | 7903.842
21.66%
|  |  |  | BCWP | 36720
|  |  |  | ACWP | 38313
|  |  |  | CPI | 0.95842 |  | 82787.409
|  |  |  | CV | 1593

## Mpwr job
| JJJJ | ACT CODE | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09 | OCT FY10 | NOV FY10 | DEC FY10
| 6.3 | 1408 | 0.3 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2
| 273.2 | 1451 | 8.7 | 11.4 | 9.5 | 11.9 | 14.7 | 9.9 | 13.2 | 15.2 | 14.4 | 16 | 13.5 | 13.3 | 11.2 | 12.4 | 7.1 | 13.2 | 8.5 | 9.4 | 9.5 | 7.9 | 8.1 | 9.3 | 9 | 6.6 | 5.5 | 3.1 | 0.7
53.3 | 52.9992 | risk |  |  |  |  | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083
| 0.5 | 1204 | 0.5 | 0
| 0.5 | 1350 | 0.5 | 0
| 34.8 | 1351 | 0.7 | 1.4 | 2.6 | 2.7 | 2.5 | 0.4 | 1.5 |  | 0.5 |  |  |  | 1.7 | 3.6 | 1.8 | 3.8 | 2.3 | 4.3 | 1.9 | 2.8 | 0.3
| 36 | risk | [12 empty] | 2.4 | 2.2 | 1.7 | 2.4 | 2.2 | 2.4 | 2.3 | 2.4 | 2.3 | 2.3 | 2.5 | 2.1 | 2.5 | 2.2 | 1.6 | 2.5
| 1.4 | 1352 | [28 empty] | 0.1 | 0.2 | 0.3 | 0.2 | 0.2 | 0.3 | 0.1
| 5 | 1355 | [12 empty] | 0.6 | 0.5 | 0.4 | 0.6 | 0.5 | 0.6 | 0.2 | [15 empty] | 1 | 0.6
| 3.6 | 1414 |  | 1.2 |  |  |  | 1.2 |  |  |  | 0.2 | 1
| 2.5 | 1601 | [24 empty] | 0.7 | 0.8 | 0.6 | 0.4
| 1.6 | 1803 | [12 empty] | 0.5 | 0.5 | 0.4 | 0.2
| 2.7 | 1804 | 0.6 | 0.6 | 0.5 | 0.6 | 0.4
| 165.6 | 1810 | 0.5 | 0.5 | 0.5 | 3.3 | 3.1 | 3.6 | 3 | 2.5 | 4 | 1.4 | 0.5 | 0.5 | 2.9 | 3.7 | 3 | 8.4 | 9.3 | 7.2 | 11.9 | 13.1 | 9.7 | 2.7 | 9.8 | 4.5 | 8.7 | 9.1 | 7.6 | 9.7 | 8.9 | 4.4 | 6.7 | 6.2 | 1.8
| 0.6 | 2101 | [24 empty] | 0.2 | 0.2 | 0.1 | 0.1
| 2.5 | 2201 | [24 empty] | 0 | 0.6 | 0.5 | 0.7 | 0.7 | 0
| 2.7 | 3101 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.6 | 0.5 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| 2 | 6101 | [28 empty] | 1 | 1
| 8.5 | 6201 | [27 empty] | 0.3 | 1 | 2.1 | 2.5 | 2.2 | 0.4
| 3.1 | 6301 | [27 empty] | 1.7 | 1.4
| 3.4 | 7301 | 0.8 | 0.7 | 0.1 | [9 empty] | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.1
| 52.9 | 7501 | [24 empty] | 3.6 | 3.2 | 2.4 | 3.6 | 3.3 | 3.3 | 3.5 | 3.3 | 3.3 | 3.5 | 3.3 | 3.3 | 1.4 | 2 | 2.7 | 2.1 | 3.5 | 1.6
| 63.6 | 7503 | [24 empty] | 4.9 | 4.3 | 3.2 | 1.5 |  | 3.2 | 0.2 |  | 0.6 | 5.1 | 6.7 | 10.2 | 10.7 | 4.9 | 4.9 | 3.2
| 1.5 | 7601 | [24 empty] | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| 2.9 | 8501 | [37 empty] | 0.2 | 0.9 | 0.9 | 0.8 | 0.1
| 440.5411 |  | 12.1 | 15.9 | 12.9 | 15.5 | 20.0083 | 14.0083 | 20.0083 | 21.6083 | 21.5083 | 23.3083 | 19.1083 | 15.9083 | 22.3083 | 25.6083 | 17.1083 | 31.4083 | 25.5083 | 26.7083 | 28.4083 | 28.7083 | 22.9083
jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar
|  | Modular Coil | 9 | 11.6 | 9.7 | 12.2 | 17.1083 | 12.4083 | 15.6083 | 17.7083 | 16.9083 | 18.4083 | 16.0083 | 15.8083 | 13.7083 | 14.8083 | 9.5083 | 15.7083 | 10.9083 | 11.9083 | 12.0083 | 10.4083 | 10.6083 | 11.8083 | 11.5083 | 9.0083 | 7.7083 | 5.3083 | 2.9083 | 2.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TF Coil | 1.2 | 1.4 | 2.6 | 2.7 | 2.5 | 0.4 | 1.5 | 0 | 0.5 | 0 | 0 | 0 | 4.1 | 5.8 | 3.5 | 6.2 | 4.5 | 6.7 | 4.2 | 5.2 | 2.6 | 2.3 | 2.5 | 2.1 | 2.5 | 2.2 | 1.6 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Field Period Assy | 0.6 | 0.6 | 0.5 | 0.6 | 0.4 | 0 | 2.9 | 3.9 | 3.6 | 4.1 | 1.6 | 0 | 3.6 | 4.2 | 3.4 | 8.6 | 9.3 | 7.2 | 11.9 | 13.1 | 9.7 | 2.7 | 9.8 | 4.5 | 8.7 | 9.1 | 7.6 | 9.7 | 8.9 | 4.4 | 6.7 | 6.2 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machine Assy | 0.8 | 0.7 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0 | 8.6 | 7.6 | 5.6 | 5.2 | 3.4 | 6.6 | 3.8 | 3.4 | 4 | 8.7 | 10.1 | 13.6 | 12.2 | 7 | 7.7 | 5.4 | 3.5 | 1.6
|  | Other | 0.5 | 1.6 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0.5 | 0.8 | 1.5 | 0.1 | 0.6 | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.2 | 0 | 0 | 0 | 0.1 | 0.1 | 1 | 1.7 | 1.3 | 3.2 | 4.2 | 3.3 | 2.8 | 2.4 | 0.6 | 0.3 | 1.1 | 0.6 | 0 | 0.2 | 0.9 | 0.9 | 0.8 | 0.1
| 730.3992 |  | 12.1 | 15.9 | 12.9 | 15.5 | 20.0083 | 14.0083 | 20.0083 | 21.6083 | 21.5083 | 23.3083 | 19.1083 | 15.9083 | 22.3083 | 25.6083 | 17.1083 | 31.4083 | 25.5083 | 26.7083 | 28.4083 | 28.7083 | 22.9083 | 16.8083 | 23.9083 | 15.7083 | 28.5083 | 25.9083 | 19.0083 | 22.8083 | 16.5 | 14.3 | 13.3 | 12 | 6.4 | 9 | 11.2 | 14.2 | 12.2 | 7.2 | 8.6 | 6.3 | 4.3 | 1.7
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| 9 | Mod Coil | 9 | 9.8667 | 10.1 | 10.625 | 12.6521 | 12.8542 | 14.3312 | 15.7083 | 15.6583 | 17.1583 | 17.2583 | 16.7833 | 15.9833 | 15.0833 | 13.4583 | 13.4333 | 12.7333 | 12.0083 | 12.6333 | 11.3083 | 11.2333 | 11.2083 | 11.0833 | 10.7333 | 10.0083 | 8.3833 | 6.2333 | 4.5333 | 2.6062 | 1.2792 | 0.55207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | TF Coil | 1.2 | 1.2667 | 1.7333 | 1.975 | 2.3 | 2.05 | 1.775 | 1.1 | 0.6 | 0.5 | 0.125 | 0.125 | 1.025 | 2.475 | 3.35 | 4.9 | 5 | 5.225 | 5.4 | 5.15 | 4.675 | 3.575 | 3.15 | 2.375 | 2.35 | 2.325 | 2.1 | 2.2 | 1.575 | 1.025 | 0.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0.6 | FP Assy | 1.1 | 1.1 | 1 | 3.9 | 3.5 | 3.6 | 3 | 2.5 | 4 | 1.4 | 0.5 | 0.5 | 2.325 | 2.35 | 2.8 | 4.95 | 6.375 | 7.125 | 9.25 | 10.375 | 10.475 | 9.35 | 8.825 | 6.675 | 6.425 | 8.025 | 7.475 | 8.775 | 8.825 | 7.65 | 7.425 | 6.55 | 4.775 | 3.675 | 2 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0
| 0.8 | Mach Assy | 0.8 | 0.76667 | 0.53333 | 0.4 | 0.2 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075 | 0.15 | 0.2 | 0.275 | 0.275 | 0.275 | 0.25 | 0.175 | 0.1 | 0.025 | 0 | 0 | 2.15 | 4.05 | 5.45 | 6.75 | 5.45 | 5.2 | 4.75 | 4.3 | 4.45 | 4.975 | 6.55 | 9.1 | 11.15 | 10.725 | 10.125 | 8.075 | 5.9 | 3.5
| 0.5 | Other | 0.5 | 0.86667 | 0.7 | 0.525 | 0.4 | 0.3 | 0.3 | 0.3 | 0.425 | 0.325 | 0.7 | 0.725 | 0.75 | 0.675 | 0.425 | 0.55 | 0.525 | 0.55 | 0.475 | 0.325 | 0.2 | 0.05 | 0.025 | 0.05 | 0.3 | 0.725 | 1.025 | 1.8 | 2.6 | 3 | 3.375 | 3.175 | 2.275 | 1.525 | 1.1 | 0.65 | 0.5 | 0.475 | 0.425 | 0.5 | 0.7 | 0.6
26.1
|  | 26.1 | O: 0.6; N: 0.6; D: 0.56667; J: 0.575; F: 0.525; M: 0.375; A: 0.975; M: 1.8; J: 2.6; J: 3.625; A: 3.3; S: 2.325

## Mpwr smry
RES | RESOURCE | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09
ecp38 | EA//EM | 6.1 | 5.5 | 4.1 | 5.6 | 6.5 | 7.2 | 5.8 | 6.6 | 6.1 | 3.8 | 4.4 | 3.9 | 5.1 | 4.7 | 3.4 | 5.3 | 4.8 | 5 | 3.7 | 3 | 2.9 | 2.9 | 3.1 | 2.8 | 3.1 | 1.8 | 1.3 | 1.6 | 1.7 | 1.3 | 1.4 | 1.3 | 1.5 | 1.8 | 1.3 | 1.4 | 0.3 | 0.2 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
incl cont risk | EA//SM | 3.1 | 1.3 | 0.9 | 3 | 1 | 1.1 | 1 | 1.1 | 1.1 | 1 | 1.1 | 1 | 4.4 | 4.2 | 3.2 | 3.9 | 2.2 | 1.8 | 1.9 | 1.8 | 1.8 | 2.2 | 2.3 | 1.1 | 1.4 | 1.5 | 0.9 | 0.9 | 0.7 | 0.6 | 0.7 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1
| EC//EM | [23 empty] | 0.9 | 2.1 | 2.1 | 1.8 | 2.9 | 2.8 | 3.2 | 3.8 | 3.8 | 3.8 | 3.1 | 3 | 2.5 | 1.6 | 0.8 | 0.9 | 0.9 | 0.8
| EC//SM | [27 empty] | 0.4 | 0.6 | 1.2 | 1.9 | 1.8 | 1.8 | 1.3 | 1.2 | 1 | 0.5 | 0.3
| EE//AM | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| EE//EM | 1.7 | 0.7 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.3 | 1.9 | 1.8 | 1.8 | 2.5 | 1.7 | 1.2 | 1.2 | 1 | 1.2 | 1.4 | 1.6 | 1.5 | 2.2 | 2.2 | 1.5 | 1.9 | 1.5 | 1 | 0.4 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.3 | 0.9 | 0.9 | 0.8
| EE//SM | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0 | 0 |  |  | 0.1 | 0.5 | 0.6 | 0.4 | 0.8 | 0.6 | 0.7 | 0.9 | 1.7 | 2 | 2.7 | 2.8 | 1.8 | 2.4 | 2 | 1.5 | 2.5 | 2.2 | 2 | 2.5 | 2.7 | 2.5 | 1.7 | 1.6 | 0.9 | 0 | 0
| EE//TB | 0.6 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.4 | 0.1 | 0.1 |  |  | 0.5 | 0.8 | 0.7 | 0.7 | 1.4 | 0.8 | 0.9 | 0.3 | 0.7 | 1.1 | 1.6 | 2.4 | 2 | 3.2 | 3.4 | 1.8 | 1.9 | 1.6 | 1 | 0.7 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.6 | 1.8 | 1.8 | 1.6
| EM//EM | 2.8 | 2.7 | 2.4 | 2.7 | 1.5 | 1.7 | 1.5 | 1.3 | 1.4 | 1.3 | 1.5 | 1.5 | 2.8 | 2.5 | 1.6 | 2.3 | 2 | 2.1 | 2 | 2.3 | 2 | 2.5 | 2.7 | 2.6 | 3.6 | 3 | 2.1 | 3.6 | 3.5 | 3.8 | 3.4 | 3.1 | 2.7 | 1.9 | 1.9 | 1.8 | 1.9 | 2.4 | 4.2 | 3.5 | 2.8 | 0.9
| EM//SM | 4 | 3 | 1.6 | 1.7 | 1 | 0.9 | 0.7 | 1.3 | 1.3 | 0.7 | 0.8 | 0.7 | 1.3 | 1 | 0.8 | 1.4 | 1.4 | 1.4 | 1.7 | 2.2 | 1.9 | 2.3 | 1.8 | 1.8 | 5.6 | 5 | 3.7 | 5.1 | 5 | 3.6 | 3.8 | 3.3 | 3.7 | 4.5 | 4.5 | 4.4 | 5.3 | 4.3 | 6 | 3.3 | 2.6 | 0.9
| EM//TB | 9 | 13.9 | 12.3 | 18.2 | 16.9 | 26.7 | 23.9 | 24.6 | 24.5 | 18.9 | 22.5 | 19 | 30.9 | 28.8 | 20.5 | 34.3 | 26.4 | 25.3 | 29.4 | 29.6 | 31.2 | 34.4 | 35.5 | 17.9 | 25.9 | 22.2 | 16.4 | 17.1 | 14.1 | 12 | 12.6 | 9.1 | 6.9 | 10.4 | 12.7 | 13.1 | 12.8 | 6.9 | 8.5 | 5.8 | 4.3 | 1.1
| ORNLEM | 10.7 | 8.5 | 6.1 | 6.8 | 5.8 | 4.7 | 4.1 | 3.1 | 2.5 | 2.2 | 3 | 2.4 | 3.4 | 3 | 2.3 | 3.6 | 3.5 | 3.6 | 2.4 | 2.3 | 2.2 | 2.2 | 2.5 | 1.9 | 1.7 | 1 | 0.7 | 1 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.7 | 0.6 | 0.5 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0
 | time axis 2005-10-01 to 2009-09-01
| PPPL Engr | 10.6 | 8.9 | 6.8 | 8.5 | 8.2 | 9.1 | 7.5 | 8.1 | 7.7 | 5.2 | 6.1 | 5.7 | 9.8 | 9 | 6.8 | 10.1 | 8.5 | 8.3 | 6.9 | 6.3 | 6.1 | 6.8 | 7.4 | 7.8 | 11 | 9.1 | 6.7 | 10 | 9.5 | 9.3 | 9 | 8.4 | 8.2 | 7 | 6.3 | 5.8 | 3.9 | 3.7 | 6.3 | 5.5 | 4.6 | 1.1 | 0.2 | 0.2 | 0 | 0 | 0 | 0
| PPPL Tecnicians | 13.6 | 17 | 14 | 20 | 18 | 27.9 | 25.1 | 26 | 25.9 | 19.6 | 23.3 | 20.3 | 33.5 | 31.1 | 22.4 | 37.9 | 29.2 | 28.3 | 32.3 | 34.2 | 36.2 | 41 | 42.5 | 23.5 | 37.1 | 32.6 | 23.4 | 27 | 23.5 | 19.8 | 21.5 | 17.2 | 15 | 18 | 20.1 | 19.5 | 18.7 | 12.1 | 16.3 | 10.9 | 8.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| ORNL Engrs | 10.7 | 8.5 | 6.1 | 6.8 | 5.8 | 4.7 | 4.1 | 3.1 | 2.5 | 2.2 | 3 | 2.4 | 3.4 | 3 | 2.3 | 3.6 | 3.5 | 3.6 | 2.4 | 2.3 | 2.2 | 2.2 | 2.5 | 1.9 | 1.7 | 1 | 0.7 | 1 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.7 | 0.6 | 0.5 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0
|  | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul
| Techs ecp36 | 16 | 19.1 | 14.3 | 19.1 | 19.5 | 15.3 | 20.3 | 21.3 | 22.5 | 22.7 | 20.6 | 15.8 | 23.5 | 25.7 | 16.8 | 30.2 | 24.7 | 25.8 | 26.9 | 29.3 | 23.4 | 16.8 | 25.7 | 16.2 | 34.9 | 31.8 | 22.3 | 28.5 | 25.5 | 22.8 | 22.1 | 20.1 | 14.2 | 16.4 | 18.3 | 21.3 | 17.9 | 11.8 | 16.6 | 11.5 | 8.5 | 3.1 | 0 | 0 | 0 | 0

## Milestones may06
|  |  | CD-2 | CD-2
|  |  | Baseline |  | Baseline | float | Forecast | Actual | master schedule | Milestone float
| Level I | CD-1 | 2003-05-01 | 0 | 2003-05-01 |  |  | 2003-05-01
M-0110 |  | CD-2 | 2004-02-01 | 0 | 2004-02-01 |  |  | 2004-02-01
M-0115 |  | CD-3 | 2004-09-30 | 0 | 2004-09-30 |  |  | 2004-09-30
M-0120 |  | CD-4 | 2008-05-30 | 14.2333 | 2009-07-31 | 1900-01-05 18:24 | 2009-01-09 |  | 2009-02-27 | 5.1333
0
1201-500 | Level II | Vacuum Vessel & Modular Coil Prel Dsn Rvw | 2003-10-07 | 0 | 2003-10-07 |  |  | 2003-10-07
1403-08 |  | Performance Baseline Review | 2003-11-18 | 0 | 2003-11-18 |  |  | 2003-11-18
1203-341 |  | Conduct VVSA FDR | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1403-51 |  | Mod Coil Winding Form Final Design Review | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1408-143.1 |  | Award MC Conductor Contract |  |  | 2004-12-19 |  |  | 2004-10-15
121-6-9 |  | Award VV Production Vendor | 2004-12-01 | -2 | 2004-10-15 |  |  | 2004-09-15
C-081 |  | Award MCWF Mfg Contract | 2004-11-01 | -1 | 2004-10-01 |  |  | 2004-09-15
C-121.1 |  | First MCWF Delivered | 2005-03-01 | 4 | 2005-07-15 | 1284.9333 |  | 2005-09-30
131-035 |  | Begin TF Coil fabrication activities | 2005-04-01 | 3 | 2005-09-30 | 1287.5 |  | 2005-06-30
P1-021.1 |  | Complete First Mod Coil Fabrication | 2005-08-31 | 6 | 2006-03-29 | 2006-04-15 |  | 2006-03-01 | 2006-03-29 | 0
121-038.1 |  | Vacuum Vessel Sectors Delivered | 2006-02-01 | 0 | 2006-09-15 | 1.5 | 2006-08-01 |  | 2006-03-21 | 1.5
C-501B1 |  | Last MCWF Delivered | 2006-08-01 | 4 | 2007-09-01 | 1.0333 | 2007-08-01 |  | 2007-02-28 | 1.0333
141-036 |  | PF Coils Awarded | 2006-06-01 | 7 | 2008-03-30 | 5.1667 | 2007-10-27 |  | 2007-10-27 | 5.1667
S3P1-101 |  | Begin Assembly of First Field Period | 2006-09-01 | 6 | 2007-07-01 | 4.0667 | 2007-03-01 |  | 2007-01-12 | 4.0667
1351-195x |  | All TF Coils Delivered | 2007-01-01 | 4 | 2008-08-15 | 10.6333 | 2007-10-01 |  | 2007-11-19 | 10.6333
S4P3-115 |  | Last Field Period Assembled | 2007-06-01 | 3 | 2008-11-15 | 6.6 | 2008-05-01 |  | 2008-06-12 | 6.6
7503-250 |  | Begin Vac Vsl Pumpdown | 2007-09-01 | 2 | 2009-02-11 | 6.4667 | 2008-08-01 |  | 2008-09-11 | 6.4667
7503-330 |  | Begin Cryostat Installation | 2007-11-01 | 2 | 2009-04-07 | 7.2667 | 2008-09-01 |  | 2008-11-07 | 7.2667
730.1250 |  | Operational Readiness | 2007-11-01 | 4 | 2009-06-01 | 7.0667 | 2008-11-01 |  | 2008-12-28 | 7.0667
920.004 |  | Begin Start-up Testing | 2008-03-31 | 0 | 2009-06-16 | 6.5667 | 2008-12-01 |  | 2008-12-01 | 6.5667
0
1404-109.J | Joule | FY04 JOULE #1-Authorize Prototype Fab | 2003-12-20 | 0.33333 | 2003-12-30 |  |  | 2003-10-20
1406-040 |  | FY04 JOULE #2-Begin winding on 3D surface | 2004-03-01 | 1 | 2004-03-31 |  |  | 2004-01-30
1404-110.J |  | FY04 JOULE #3-Prototype Casting Ready for Machining | 2004-06-01 | 0.96667 | 2004-06-30 |  |  | 2004-05-26
C-081.1 |  | FY04 JOULE #4 - CD-3 Readiness | 2004-09-01 | 0.96667 | 2004-09-30 |  |  | 2004-09-15
1408-143.1 |  | FY05 JOULE #1- VVSA, MCWF and MC Copper Conductor Awarded |  | 1278.3667 | 2004-12-30 | 2.5333 |  | 2004-10-15
1406-017.3 |  | FY05 JOULE #2- Cmplt Assy of twisted racetrack |  | 1281.4 | 2005-03-31 | 1281.4 |  | 2005-03-30
1403-20 |  | FY05 JOULE #3- Mod Coil Winding Type C FDR |  | 1284.4333 | 2005-06-30 | 1284.4333 |  | 2005-06-30
P1-011J |  | FY05 JOULE #4- Complete Winding First MC |  | 1287.5 | 2005-09-30 | 2005-10-31 |  | 2005-12-01 | 2005-12-15 | -2.5333
mcwf-311 |  | FY06 JOULE Complete Fabr. of one VVSA and two Mod Coils |  |  | 2006-09-30 |  | 2006-05-01 |  | 2006-03-22 | 6.4
P2-041joul |  | FY07 JOULE Complete Winding of 1/2 of Modular Coils |  |  | 2007-09-30 |  | 2006-12-01 |  | 2006-11-06 | 10.9333
NCSX Milestone Status
Formulas:
Actual = +[Baseline]
float = (+[Baseline]-[Forecast])/30
Forecast = SUM([master schedule])

## EIO IMPACT
Modular Coil Winding Form Delivery Schedule
[9 empty] | EIO Forecast |  |  | Project Forecast |  |  |  |  | Free Float |  | 3 winding lines 2 shifts |  |  |  |  | 2 shfits for field period |  |  |  |  | 2 shifts Machine Assembly
[19 empty] | for coil winding |  |  |  |  | assembly
|  |  | Machine Time (wks) | [10 empty] | 2006 | [11 empty] | 2007
2005-01-01 | 2005-02-01 | MWF# | EIO | Proj Forecast | 2005-04-01 | 2005-05-01 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | Sep | Oct
|  | C1 | 26 (A) | 26 (A)
|  | C2 | 20 | 22
|  | C3 | 14 | 16
|  | C4 |  | 15
|  | C5 |  | 14
|  | C6 |  | 14
|  | A1 |  | 16
|  | A2 |  | 14
|  | A3 |  | 14
|  | B1 |  | 16
|  | A4 |  | 14
|  | A5 |  | 14
|  | A6 |  | 14
|  | B2 |  | 15
|  | B3 |  | 14
|  | B4 |  | 14
|  | B5 |  | 14
|  | B6 |  | 14
|  | 2005 | [11 empty] | 2006 | [11 empty] | 2007
2005-01-01 | 2005-02-01 | 2005-03-01 |  |  | 2005-04-01 | 2005-05-01 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | Sep | Oct | Nov
|  | 2) |  |  | Winding plan basis;
a) first coil taking 50% longer.
b) 2 winding stations with 3 winding teams. 3rd team dedicated to 2nd shift for winding only. Chill plate ,bagging VPI pre done on 1st shift only.
c) 2nd shift utilized for first 10 coils only.
d) all shifts based 5 days/week 70% of winding ops utilize 10hr/days. Some overtime and all Saturday's held back as contingency.
E
E
E
E
E
E
E
E
E
E
E
E
E

## Summary Schedule may06
NCSX Critical Path Summary Schedule
FY02 |  |  |  |  | FY03 | [11 empty] | FY04 | [11 empty] | FY05 | [11 empty] | FY06 | [12 empty] | FY07 | [11 empty] | FY08 | [11 empty] | FY09
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| CDR |  |  |  | DOE Milestones
FY02 J: CD-1; FY03 S: MC/VV PDR; FY04 M: CD-2 | [10 empty] | Joule FY06-Complt fab one VVSA and two modular coils
FY04 D: EIR; FY05 O: CD-3 Start of Fab | [32 empty] | Pumpdown Vac Vsl
[12 empty] | Start of Preliminary Design | [10 empty] | Vac Vsl FDR
Modular Coil FDR
FY04 D: Joule #1 Authorize Protype Fab; FY05 J: Joule #1 Award VVSA,MWCF,Cond | [40 empty] | ORA
[22 empty] | Joule #2 Demonstarte Winding Process on 3-D Surface | [12 empty] | Joule #2 Cmplt Assy TRC
FY04 J: Joule #3 First Prototype Casting Produced for Machining; FY05 J: Joule #3 Mod Coil Winding Type C FDR | [43 empty] | CD-4 Completion of MIE Project
[28 empty] | Joule #4 CD-3 Prereq Complete | [13 empty] | Joule #4 Cmplt Winding First MC
VACUUM VESSEL
[10 empty] | Title I & II Design | [16 empty] | Vessel Award
Manuf Devel
FY04 S: Vessel Fab | 1 |  | 2 | 3
MODULAR COILS
Title I & II MCWF
Twisted Racetrack Fabrication
FY04 D: Title II Design for Winding; FY05 N: Type C; FY05 M: Type C | Type A |  |  |  | Type B
Component Fabrication
MCWF Manufacturing Development
[16 empty] | Fabricate Prototype Type "C" | [12 empty] | Award Winding Form Contract
[43 empty] | C2 |  | C3 | C4 |  | C5 | A1 | A2 | A3 | B1 |  | A4 | B2 |  | B3 | B4 | B5 | B6 | A5 | A6 |  | C6 | bar: FY04 J to FY04 A; FY05 S
Fab Winding Forms
Station 2-Wind
Station 3-Wind
VPI,Clamps,& Test
FY04 O: FIELD PERIOD ASSEMBLY |  |  |  | Stage 1: Attach Cooling,Diag, Insulation
Stage 2: Pre-Assemble Mod Coils
Stage 3: MC Installation
Stage 4: Assemble 1st Period
Stage 4: Assemble 2nd Period
Stage 4: Assemble 3rd Period
FY04 A: MACHINE ASSEMBLY | [21 empty] | Install Supports and Lower PF Coils
Install,align, connect Field Period Assemblies
FY03 O: Legend: | [34 empty] | Pump Down
FY03 O: Completed Task | [33 empty] | Connect to Ancilliary Systems
FY03 O: Critical Paths | [33 empty] | Install Cryostat & PTP
FY03 O: Off critical path | [36 empty] | Startup Testing and E-Beam Mapping
FY03 M: 2 shift operation | [8 empty] | Ancilliary Systems Installation | [34 empty] | First Plasma
FY02 M: FY02; FY03 O: FY03; FY04 O: FY04; FY05 O: FY05; FY06 O: FY06 | [11 empty] | FY07 | [11 empty] | FY08
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A |  | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1
Total Float 6 mo.

## Funding may06
Total
| Original BA | 7.9 | 15.83 | 15.84 | 22.14 | 19.42 | 5.2 |  | 86.33
| New BA | 7.9 | 15.83 | 17.5 | 15.9 | 15.9 | 15.9 | 5.199 | 94.129
| PMB | 6.062 | 13.658 | 18.238 | 15.425 | 13.289 | 12.748 | 2.466 | 81.886
| Contingency |  |  | 0.8 | 3 | 2.6 | 3.1 | 2.742 | 12.242
| BA cum old | 7.9 | 23.73 | 39.57 | 61.71 | 81.13 | 86.33 | 86.33
| BA cum new | 7.9 | 23.73 | 41.23 | 57.13 | 73.03 | 88.93 | 94.129
| PMB cum | 6.062 | 19.72 | 37.958 | 53.383 | 66.672 | 79.42 | 81.886
%
24.8%
|  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total
| 22.01% |  | BA | 7.897 | 15.921 | 17.5 | 17 | 15.9 | 15.9 | 2.3 | 92.418
|  |  | EAC | 5.9419 | 14.2393 | 18.162 | 19.8 | 15.1 | 9.8 | 1.6 | 84.6432
| 5% |  | Contingency |  |  |  |  | 1 | 6.1 | 0.7 | 7.8
| 10% |  | BO (EAC + Cont) | 5.9419 | 14.2393 | 18.162 | 19.8 | 16.1 | 15.9 | 2.3 | 92.4432
33.49%
| 19.58% |  | Cum BA | 7.897 | 23.818 | 41.318 | 58.318 | 74.218 | 90.118 | 92.418
| 11.24% |  | Cum PMB | 5.9419 | 20.1812 | 38.3432 | 58.1432 | 73.2432 | 83.0432 | 84.6432
22.01%
|  |  | Cum BO | 5.9419 | 20.1812 | 38.3432 | 58.1432 | 74.2432 | 90.1432 | 92.4432
[5 empty] | 23.8 | 41.3 | 58.3 | 74.2 | 90.1 | 92.4
|  |  | pmb puts and takes |  |  | -0.415 | -1.047 | -0.712 | 0.151 | 0.121
|  |  | contingency puts and takes |  | 0 | 0.415 | 1.047 | 0.712 | -0.151 | -0.121
|  |  |  | wbs1 | -0.24 | -0.12 | -0.12
|  |  |  | wbs13 | -0.6 | -0.2 | -0.2 | -0.2
|  |  |  | wbs 141 | -0.64 |  | -0.32 | -0.32
|  |  |  | wbs142 | -0.095 | -0.095
|  |  |  | wbs142 | -0.097 |  | -0.097
|  |  |  | wbs18 | -0.3 |  | -0.15 | -0.15
|  |  |  | wbs82 | -0.32 |  | -0.16 | -0.16
|  |  |  | red | 0.48 |  |  | 0.118 | 0.151 | 0.121
0.09
FY04 FY05 FY06 FY07 FY08 FY09
$23.8
$74.2
$58.3
$41.3
$92.4
$90.1

## financial status may06
BCWS | BCWP | ACWP | Budget
48.2 | 46.35 | 48 | 83.65
|  |  | 8.74 | contingency | 23.4%
| 55.41% | 51.95% | 92.39 | TEC | on remaining scope
| complete | spent
FY06
| Budget (BA plus c/o)= | 19.949
| EAC (FY06)= | 19.8 | +/-