## Sheet2
0.95
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 16
3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | 0.95 | 0.9025 | 0.85737 | 0.81451 | 0.77378 | 0.73509 | 0.69834 | 0.66342 | 0.63025 | 0.59874 | 0.5688 | 0.54036 | 0.51334 | 0.48767 | 0.46329 | 11.1975
0.69984
-30.02%

## Sheet1
"SWEET Lemon" proposal | -1432
WSBS 81 Jim Lyon FY07 & 08 | -87
WBS 81 Hutch & Ron FY09 (only9% consistent with total Program funding plan) | -65
Eliminate the Installation of the cryogenic systems for first plasma=installation cost | -161 | system still to be designed and procured. First plasma accelerated by ~ 2 mo.
Eliminate the Installation of the cryogenic systems for first plasma=construc crew support | -103
Eliminate the Installation of the cryogenic systems for first plasma=construc suppervision | -79
Vacuum Pumping sys design, fab and installation | -300 | use pump cart plis $50k allowance for mods/additions
WBS 19 in fy09 | -152 | Core machine assembled by end of fy08
WBS 411 auxiliary AC power reduce by 50% | -180
WBS 441 electr interlocks reduce by 50% | -180
WBS 452 diag elect systems support | -125