## Sheet1
JJJJ | JOB | BUDGET (BAC) | BCWP | CV | etc increases | COST TO DATE (BCWP plus cost variance) | REMAINING SCOPE (BCWR) | ETC Increases | FY06 | ETC total | Total Contingency Balance %$ | Total Contingency Balance % |  | CONTINGENCY $ calculated based on risk % assigned | Previous % | Nov--> May change | Ron---> Hutch changes
1350 | Job: 1350 TF Coil Fab Preparation-CHRZANOWSKI | 771023.91 | 500724.713 | 44719.287 | -260299 | 545444 | 270299.197 | -260299 |  | 10000.197 | 2000.0394 | 20% | 20% | 64871.8073 | 24% | -4% | #REF!
1351 | Job: 1351 - TF Coil Fabr Supplies-KALISH | 863670.64 | 360038.9 | 63961.1 | -464000 | 424000 | 503631.74 | -464000 |  | 39631.74 | 7926.348 | 20% | 20% | 120871.6176 | 24% | -4% | #REF!
1361 | Job: 1361 - TF Fabrication-KALISH | 659135.39 | 43387.1323 | 37221.8677 | 1237000 | 80609 | 615748.2577 | 1237000 | 91000 | 1852748.2577 | 185274.8258 | 10% | 10% | 412551.3327 | 67% | -57% | #REF!
1902380.1947
[5 empty] | TF Coil Cost and Schedule Summary | [5 empty] | 195201.2132
Budget
[5 empty] | Nov 05 |  | May 06
Budgeted Scope
[5 empty] | 2293829.94 |  | 2293829.94 | Facility prep, Hardware Fabrication,Engineering/Design, Title III'
[7 empty] | 145000 | Cost Variance attributed to facilties prep,hardware fab, and engineering
[7 empty] | 345000 | Increased fabrication estimate (Everson-Tesla)
[7 empty] | 165000 | Increase Title III for oversight
[5 empty] | 2293829.94 |  | 2948829.94
Unbudgeted Risk
|  |  |  | Fabrication | 448000 |  | 0 | Risk retired with fixed price contract
|  |  |  | Wedge Casting Fabrication | 135000 |  | 0 | Risk retired with fixed price contract
|  |  |  | contingency balance | 208000 |  | 195000
|  |  |  | Total Expectation and risk | 3084829.94 |  | 3143829.94
Schedule
|  |  |  | Delivery 1st coil | 2006-06-06 |  | 2006-11-07
|  |  |  | Delivery Last coil | 2006-12-06 |  | 2006-09-07