## etc_from_1mar
ETC from Mar-1-06
Summary
March | Issue Type-A part drawings for procurement
April | Issue Type-A subasm drawings, Type-C top level asm drawings
May | Issue Type-ABC term splice plates, Type-ABC analysis reports
June | Conduct Type-A FDR, Issue Type-B part and subasm drawings, Conduct Type-C final design closeout
July | Issue Type-A top level asm drawings, Conduct Type-B FDR
Aug | Issue Type-B top level asm drawings
Sep | Issue coil-coil interface hdw drawings
Oct
[8 empty] | $k |  |  | Total |  | Labor Hours | [5 empty] | Total | Old Total
Job Title | WBS | ACT | TITLE | Deliverable | Start | Finish | NEW FINISH | Travel | M&S | Other |  | Old Total | EA//EM | EM//SM | EM//TB | ORNLEM | ORNLRM | R///RM2
Job: 1403 - Modular Coil Final Design-WILLIAMSON 152 | Type C Design Closeout | 1403-20.0 | Final Design Close-out for Type C |  |  | 2006-04-24 | 2006-06-02
|  | 1403-20.2 | Resolve FDR chits |  | 2005-08-01 | 2006-03-24 | 2006-03-31 | [8 empty] | 4 |  |  | 4
|  | 1403-200 | Side A/B winding pack assy-Type C | Included in Top-Level Asm DRW | 2004-01-01 | 2006-03-30 | [12 empty] | 0
|  | 1403-206.1 | Cooling tubes/services assy- Type C | Included in Post-VPI DRW | 2005-04-25 | 2006-03-30 | [12 empty] | 0
|  | 1403-206C | Finish Cooling, Electr Schematic Dwgs - Type C | DRW3 - | 2005-03-01 | 2006-03-30 | 2006-03-31 | [8 empty] | 16 |  |  | 16
|  | 1403-208C | Finish I&C Dwgs -Type C | Included in Post-VPI DRW | 2005-03-01 | 2006-03-30 | [12 empty] | 0
|  | 1403-223C | Finish Top level coil assembly-Type C | DRW1 -BOM | 2005-03-01 | 2006-03-30 | 2006-04-28 | [8 empty] | 56 |  |  | 56
|  | 1403-224C | Finish VPI mold assembly-Type C | DRW2 -Studs, clamps, bushings, etc | 2005-03-01 | 2006-03-30 | 2006-04-14 | [8 empty] | 40 |  |  | 40
|  | 1403-40.2Z | Update nonlinear winding pack analysis | DAC, Kevin - checks HM report | 2004-08-01 | 2006-04-21 | 2006-04-21 | [8 empty] | 80 |  |  | 80
|  | 1403-42A1 | Document analysis of MCWF eddy currents | DAC, David | 2006-03-01 | 2006-03-24 | 2006-03-31 | [8 empty] | 4 |  |  | 4
|  | 1403-42H | calculate EM loads at leads | incl DAC for task -76, Kevin | 2005-09-01 | 2006-04-21 | 2006-04-28 | [8 empty] | 16 |  |  | 16
|  | 1403-47A | Update,review & approve FMECA |  | 2005-09-26 | 2006-03-24 | 2006-04-20 | [8 empty] | 16 |  |  | 16
|  | 1403-47C | Perform cool-down/warmup analysis |  | 2006-03-01 | 2006-03-24 | 2006-05-12 | [8 empty] | 8 |  |  | 8
|  | 1403-50A | Check inductance calculation |  | 2006-03-01 | 2006-03-24 | 2006-05-12 | [8 empty] | 4 |  |  | 4
|  | 1403-58C | Check and promote clamp, I&C assy dwgs -Type C | Catch-all for remaining drawings | 2005-06-01 | 2006-03-30 | 2006-05-12 | [8 empty] | 60 |  |  | 60
|  | 1403-60C | Finish Update design basis document |  | 2005-05-02 | 2006-03-30 | 2006-04-20 | [8 empty] | 8 |  |  | 8
|  | 1403-73 | Prep struct analysis report | DAC, HM (draft issued) | 2005-05-01 | 2006-04-21 | 2006-05-26 | [5 empty] | 20 | [5 empty] | 20
|  | 1403-76 | Structural analysis of leads | DAC, Kevin | 2004-10-01 | 2006-03-10 | 2006-05-12 | [8 empty] | 40 |  |  | 40
|  | 1403-90 | Compile Material properties database | DAC, HM (draft issued) | 2004-10-01 | 2006-04-21 | 2006-04-07 | [5 empty] | 20 | [5 empty] | 20
| Type C Design Closeout Total | [11 empty] | 40 |  |  | 352 |  |  | 392 | 331 | +61hrs
Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON 153 | Winding and Assembly Design-Type A | 1416A-105 | Top Level Models and Drawings | renamed task | 2006-03-01 | 2006-03-07 | 2006-07-07 | [8 empty] | 80 |  |  | 80
|  | 1416A-109 | Check and Promote Top Level Drawings | drw rel by start of A1 coil testing (11/7/06) | 2006-03-08 | 2006-03-14 | 2006-07-21 | [8 empty] | 80 |  |  | 80
|  | 1416A-121 | MCWF mods-Seal Groove Adapter |  | 2005-10-01 | 2006-03-10 | 2006-04-03 | [8 empty] | 16 |  |  | 16
|  | 1416A-125 | MCWF mods-Metrology Data Files | delete task | 2005-10-03 | 2006-03-10 | [9 empty] | 0 |  |  | 0
|  | 1416A-129 | MCWF mods-Check and Promote | drw rel 8wks before A1 arrives (5/30) | 2005-11-30 | 2006-03-10 | 2006-04-14 | [8 empty] | 24 |  |  | 24
|  | 1416A-141 | Lead Block Assy-Detail Parts, Intralink |  | 2005-11-28 | 2006-03-10 | 2006-03-10 | [8 empty] | 24 |  |  | 24
|  | 1416A-145 | Lead Block Assy-Filament Data Files | delete task | 2005-11-28 | 2006-03-10 | [9 empty] | 0 |  |  | 0
|  | 1416A-149 | Lead Block Assy-Check and Promote | drw rel 8wks before A1 arrives (5/30) | 2006-03-01 | 2006-03-10 | 2006-03-31 | [8 empty] | 48 |  |  | 48
|  | 1416A-153 | Lead Terminals-Splice Plates |  | 2006-04-03 | 2006-04-07 | 2006-05-09 | [8 empty] | 24 |  |  | 24
|  | 1416A-157 | Lead Terminals-Check and Promote | drw rel for proc with fpa parts (5/23) | 2006-04-10 | 2006-04-14 | 2006-05-16 | [8 empty] | 24 |  |  | 24
| Type-A | 1416A-161 | Side A Coil Assy-Cladding Asm |  | 2005-09-01 | 2006-03-15 | 2006-03-17 | [8 empty] | 32 |  |  | 32
|  | 1416A-165 | Side A Coil Assy-Cond Layers, Geom Files |  | 2005-11-28 | 2006-03-22 | 2006-03-17 | [8 empty] | 4 |  |  | 4
|  | 1416A-169 | Side A Coil Assy-Magnetic Loops |  | 2005-11-28 | 2006-03-15 | 2006-03-17 | [8 empty] | 4 |  |  | 4
|  | 1416A-173 | Side A Coil Assy-Chill Plates and Tubing |  | 2005-11-28 | 2006-03-15 | 2006-03-17 | [8 empty] | 48 |  |  | 48
|  | 1416A-177 | Side A Coil Assy-Check and Promote | drw rel 8wks before A1 arrives (5/30) | 2006-03-01 | 2006-03-15 | 2006-03-31 | [8 empty] | 16 |  |  | 16
| Type-A | 1416A-181 | Side B Coil Assy-Cladding Asm |  | 2005-09-01 | 2006-03-15 | 2006-03-17 | [8 empty] | 32 |  |  | 32
|  | 1416A-185 | Side B Coil Assy-Cond Layers, Geom Files |  | 2005-11-28 | 2006-03-15 | 2006-03-17 | [8 empty] | 4 |  |  | 4
|  | 1416A-189 | Side B Coil Assy-Magnetic Loops |  | 2005-11-28 | 2006-03-15 | 2006-03-17 | [8 empty] | 4 |  |  | 4
|  | 1416A-193 | Side B Coil Assy-Chill Plates and Tubing |  | 2005-11-28 | 2006-03-15 | 2006-03-17 | [8 empty] | 48 |  |  | 48
|  | 1416A-197 | Side B Coil Assy-Check and Promote | drw rel 8wks before A1 arrives (5/30) | 2006-03-01 | 2006-03-15 | 2006-03-31 | [8 empty] | 16 |  |  | 16
|  | 1416A-201 | Coil Post VPI mods-Studs Removed |  | 2005-12-03 | 2006-04-28 | 2006-08-18 | [8 empty] | 24 |  |  | 24
|  | 1416A-205 | Coil Post VPI mods-Clamp Arrangement |  | 2005-12-03 | 2006-04-28 | 2006-08-18 | [8 empty] | 16 |  |  | 16
|  | 1416A-209 | Coil Post VPI mods-Check and Promote | drw rel 4wks before A1 post-vpi (10/24) | 2006-05-01 | 2006-05-05 | 2006-09-29 | [8 empty] | 20 |  |  | 20
|  | 1416A-221 | I&C-Strain Gages and T/C |  | 2006-03-01 | 2006-03-03 | 2006-09-08 | [8 empty] | 20 |  |  | 20
|  | 1416A-225 | I&C-Rogowski Coils |  | 2006-03-01 | 2006-03-07 | 2006-09-08 | [8 empty] | 40 |  |  | 40
|  | 1416A-229 | I&C-Check and Promote | drw rel 4wks before A1 post-vpi (10/24) | 2006-03-08 | 2006-03-14 | 2006-09-29 | [8 empty] | 20 |  |  | 20
|  | 1416A-233 | Coil-to-Coil -Current Feed Insul, Covers |  | 2006-03-01 | 2006-03-07 | 2006-09-22 | [8 empty] | 20 |  |  | 20
|  | 1416A-237 | Coil-to-Coil -Windings Insul Blanket |  | 2006-03-01 | 2006-03-07 | 2006-09-22 | [8 empty] | 20 |  |  | 20
|  | 1416A-241 | Coil-to-Coil -Bushing Installation |  | 2006-03-01 | 2006-03-07 | 2006-09-22 | [8 empty] | 20 |  |  | 20
|  | 1416A-245 | Coil-to-Coil -Check and Promote | drw rel 4wks before A1 post-vpi (10/24) | 2006-03-08 | 2006-03-14 | 2006-09-29 | [8 empty] | 20 |  |  | 20
|  | 1416A-249 | -Type-A Coil Asm Specification | draft by 5/5 | 2006-03-07 | 2006-03-13 | 2006-05-05 | [8 empty] | 40 |  |  | 40
|  | 1416A-253 | -Review and Approve Type-A Spec |  | 2006-03-14 | 2006-03-20 | 2006-05-30 | [8 empty] | 24 |  |  | 24
|  | 1416A-257 | -Update Coil Fab Procedures | draft by 5/19 | 2006-03-21 | 2006-03-27 | 2006-05-19 | [8 empty] | 24 |  |  | 24
|  | 1416A-261 | -Prepare and Conduct FDR |  | 2006-05-08 | 2006-05-12 | 2006-05-25 | [8 empty] | 24 |  |  | 24
|  | 1416A-262 | TYPE A FDR | need by start of A1 prep (5/30) |  | 2006-05-12 | 2006-05-25 | [8 empty] | 0 |  |  | 0
|  | 1416A-265 | -Resolve FDR Comments |  | 2006-05-15 | 2006-05-26 | 2006-06-09 | [8 empty] | 40 |  |  | 40
| Winding and Assembly Design-Type A Total | [14 empty] | 900 |  |  | 900 | 772 | +128hrs
| Winding and Assembly Design-Type B | 1416B-105 | Top Level Models and Drawings | renamed task | 2006-04-11 | 2006-04-17 | 2006-08-25 | [8 empty] | 80 |  |  | 80
|  | 1416B-109 | Check and Promote Top Level Drawings | drw rel by start of B1 coil testing (2/8/07) | 2006-04-18 | 2006-04-24 | 2006-08-25 | [8 empty] | 80 |  |  | 80
|  | 1416B-113 | MCWF mods-As-Built MCWF |  | 2005-12-01 | 2006-03-09 | 2006-04-28 | [8 empty] | 28 |  |  | 28
|  | 1416B-117 | MCWF mods-Studs, Lead Block Mount |  | 2006-03-01 | 2006-03-07 | 2006-05-12 | [8 empty] | 32 |  |  | 32
|  | 1416B-121 | MCWF mods-Seal Groove Adapter |  | 2006-03-01 | 2006-03-07 | 2006-05-26 | [8 empty] | 40 |  |  | 40
|  | 1416B-125 | MCWF mods-Metrology Data Files | delete task | 2006-03-01 | 2006-03-03 | [9 empty] | 0 |  |  | 0
|  | 1416B-129 | MCWF mods-Check and Promote | drw rel 8wks before B1 arrives (8/9/06) | 2006-03-10 | 2006-03-16 | 2006-06-09 | [8 empty] | 40 |  |  | 40
|  | 1416B-133 | Lead Block Assy-Lead Blocks |  | 2005-11-28 | 2006-03-09 | 2006-04-14 | [8 empty] | 7.998 |  |  | 7.998
|  | 1416B-137 | Lead Block Assy-Top and Side Plates |  | 2005-11-28 | 2006-03-09 | 2006-04-14 | [8 empty] | 7.998 |  |  | 7.998
|  | 1416B-141 | Lead Block Assy-Detail Parts, Intralink |  | 2006-02-10 | 2006-03-07 | 2006-04-28 | [8 empty] | 24 |  |  | 24
|  | 1416B-145 | Lead Block Assy-Filament Data Files | delete task | 2006-02-06 | 2006-03-07 | [9 empty] | 0 |  |  | 0
|  | 1416B-149 | Lead Block Assy-Check and Promote | drw rel 8wks before B1 arrives (8/9/06) | 2006-03-10 | 2006-03-16 | 2006-06-09 | [8 empty] | 80 |  |  | 80
|  | 1416B-153 | Lead Terminals-Splice Plates |  | 2006-03-01 | 2006-03-07 | 2006-05-09 | [8 empty] | 24 |  |  | 24
|  | 1416B-157 | Lead Terminals-Check and Promote | drw rel for proc with fpa parts (5/23) | 2006-03-08 | 2006-03-14 | 2006-05-16 | [8 empty] | 24 |  |  | 24
| Type-B | 1416B-161 | Side A Coil Assy-Cladding Asm |  | 2005-12-03 | 2006-04-18 | 2006-05-12 | [8 empty] | 40 |  |  | 40
|  | 1416B-165 | Side A Coil Assy-Cond Layers, Geom Files |  | 2006-03-01 | 2006-03-07 | 2006-05-12 | [8 empty] | 4 |  |  | 4
|  | 1416B-169 | Side A Coil Assy-Magnetic Loops |  | 2006-03-03 | 2006-03-09 | 2006-05-12 | [8 empty] | 4 |  |  | 4
|  | 1416B-173 | Side A Coil Assy-Chill Plates and Tubing |  | 2006-03-07 | 2006-05-08 | 2006-05-12 | [8 empty] | 56 |  |  | 56
|  | 1416B-177 | Side A Coil Assy-Check and Promote | drw rel 8wks before B1 arrives (8/9/06) | 2006-05-09 | 2006-05-22 | 2006-06-09 | [8 empty] | 20 |  |  | 20
| Type-B | 1416B-181 | Side B Coil Assy-Cladding Asm |  | 2005-12-03 | 2006-04-18 | 2006-05-12 | [8 empty] | 40 |  |  | 40
|  | 1416B-185 | Side B Coil Assy-Cond Layers, Geom Files |  | 2006-03-01 | 2006-03-07 | 2006-05-12 | [8 empty] | 4 |  |  | 4
|  | 1416B-189 | Side B Coil Assy-Magnetic Loops |  | 2006-03-03 | 2006-03-09 | 2006-05-12 | [8 empty] | 4 |  |  | 4
|  | 1416B-193 | Side B Coil Assy-Chill Plates and Tubing |  | 2006-03-07 | 2006-05-08 | 2006-05-12 | [8 empty] | 56 |  |  | 56
|  | 1416B-197 | Side B Coil Assy-Check and Promote | drw rel 8wks before B1 arrives (8/9/06) | 2006-05-09 | 2006-05-22 | 2006-06-09 | [8 empty] | 20 |  |  | 20
|  | 1416B-201 | Coil Post VPI mods-Studs Removed |  | 2006-03-01 | 2006-03-07 | 2006-08-11 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-205 | Coil Post VPI mods-Clamp Arrangement |  | 2006-03-03 | 2006-03-09 | 2006-08-11 | [8 empty] | 40 |  |  | 40
|  | NEW | Coil Post VPI mods-Cooling/Electrical |  |  |  | 2006-08-11 | [8 empty] | 40 |  |  | 40
|  | 1416B-209 | Coil Post VPI mods-Check and Promote | drw rel 4wks before B1 post-vpi (1/25/07) | 2006-03-10 | 2006-03-16 | 2006-08-25 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-213 | Clamp Assy-Clamp Hardware | delete task | 2006-03-01 | 2006-03-01 | [9 empty] | 0 |  |  | 0
|  | 1416B-217 | Clamp Assy-Check and Promote | delete task | 2006-03-02 | 2006-03-02 | [9 empty] | 0 |  |  | 0
|  | 1416B-221 | I&C-Strain Gages and T/C |  | 2006-04-03 | 2006-04-07 | 2006-08-11 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-225 | I&C-Rogowski Coils |  | 2006-04-10 | 2006-04-14 | 2006-08-11 | [8 empty] | 40 |  |  | 40
|  | 1416B-229 | I&C-Check and Promote | drw rel 4wks before B1 post-vpi (1/25/07) | 2006-04-17 | 2006-04-21 | 2006-08-25 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-233 | Coil-to-Coil -Current Feed Insul, Covers |  | 2006-03-23 | 2006-03-29 | 2006-08-11 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-237 | Coil-to-Coil -Windings Insul Blanket |  | 2006-03-20 | 2006-03-24 | 2006-08-11 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-241 | Coil-to-Coil -Bushing Installation |  | 2006-03-28 | 2006-04-03 | 2006-08-11 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-245 | Coil-to-Coil -Check and Promote | drw rel 4wks before B1 post-vpi (1/25/07) | 2006-04-04 | 2006-04-10 | 2006-08-25 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-249 | -Type-B Coil Asm Specification | draft by 7/21 | 2006-05-11 | 2006-05-17 | 2006-07-21 | [8 empty] | 40 |  |  | 40
|  | 1416B-253 | -Review and Approve Type-B Spec |  | 2006-05-18 | 2006-05-24 | 2006-08-09 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-257 | -Update Coil Fab Procedures | draft by 7/31 | 2006-05-25 | 2006-06-01 | 2006-07-31 | [8 empty] | 19.99 |  |  | 19.99
|  | 1416B-261 | -Prepare and Conduct FDR |  | 2006-06-02 | 2006-06-08 | 2006-08-07 | [8 empty] | 40 |  |  | 40
|  | 1416B-262 | TYPE B FDR | need by start of B1 prep (8/9/06) |  | 2006-06-08 | 2006-08-07 | [8 empty] | 0 |  |  | 0
|  | 1416B-265 | -Resolve FDR Comments |  | 2006-06-09 | 2006-06-22 | 2006-08-25 | [8 empty] | 40 |  |  | 40
| Winding and Assembly Design-Type B Total | [14 empty] | 1155.896 |  |  | 1155.896 | 1922 | -766hrs
Job: 1421-Mod Coil Interface Hardware-WILLIAMSON 158 | Coil-to-coil Interface Design | 1403-11.1 | Describe interfaces as part of coil FDRs | renamed task | 2004-11-01 | 2006-06-30 | 2006-08-07 | [8 empty] | 60 |  |  | 60
|  | NEW | additional analysis of coil to coil joints/friction |  |  |  | 2006-05-30 | [8 empty] | 80 |  |  | 80
|  | NEW | develop design fix for issue |  |  |  | 2006-06-30 | [8 empty] | 80 |  |  | 80
|  | NEW | rework type A, B, C design, as required for fix | if needed, other tasks accelerate |  |  | 2006-04-10 | [8 empty] | 80 |  |  | 80
|  | NEW | detailed design of additional hardware |  |  |  | 2006-08-15 | [8 empty] | 80 |  |  | 80
|  | 1403-16 | Assembly bolts, nuts,washers |  | 2004-10-01 | 2006-06-30 | 2006-09-15 | [8 empty] | 80 |  |  | 80
|  | 1403-17 | Assembly shims |  | 2004-10-01 | 2006-06-30 | 2006-09-15 |  | needs | [6 empty] | 80 |  |  | 80
|  | 1403-18 | Eccentric ball assembly |  | 2004-11-08 | 2006-06-30 | 2006-09-15 |  | review | [6 empty] | 80 |  |  | 80
|  | 1403-19 | Top assembly dwgs for 3 coil asm | renamed task | 2004-10-01 | 2006-06-30 | 2006-09-15 | [8 empty] | 160 |  |  | 160
|  | 1403-19A | Bladder Details |  | 2005-07-01 | 2006-06-30 | 2006-09-15 | [8 empty] | 160 |  |  | 160
|  | 1403-20 | 3 coil assembly specification | need 8wks before start of fpa | 2006-08-01 | 2006-09-25 | 2006-09-15 | [8 empty] | 160 |  |  | 160
|  | NEW | Check and promote 3-coil drws |  |  |  | 2006-09-25 | [8 empty] | 160 |  |  | 160
| Coil-to-coil Interface Design Total | [14 empty] | 1260 |  |  | 1260 | 519 | +741hrs
TOTAL
+164hrs
Job: 1601 - Coil Services Design-WILLIAMSON | 161 - LN2 Distribution | 191-001 | Title I design WBS 161 LN2 manifolds&piping |  | 2006-07-03 | 2006-10-03 | [6 empty] | 80 |  |  | 251 |  |  | 331
|  | 191-011 | Title II design WBS 161 LN2 manifolds&piping |  | 2006-10-04 | 2007-01-05 | [6 empty] | 160 |  |  | 503 |  |  | 663
|  | 191-031 | Title III engr WBS 161 |  | 2007-01-08 | 2008-02-18 | [6 empty] | 8 |  |  | 86 |  |  | 94
|  | 191-037 | Procurement WBS 161 |  | 2007-01-08 | 2007-07-10 |  |  | 52.95 |  | 52.95
|  | 191-038 | PDR#17 |  | 2007-07-11 | 2007-11-08 |  |  | 44.36 |  | 44.36
|  | 191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 |  | 2007-07-11 | 2007-10-05 | [7 empty] | 71 | 284 |  |  |  | 355
|  | 191-042 | PDR #17,25,3 |  | 2007-07-11 | 2007-10-10 | [7 empty] | 23 | 90 |  |  |  | 113
| 161 - LN2 Distribution Total | [7 empty] | 97.31 |  | 97.31 |  | 248 | 94 | 374 | 840 |  |  | 1556
| 162 - Electrical Leads | 132-000 | PDR #17 & 25 |  | 2006-10-02 | 2008-01-24 | [9 empty] | 20 | 200 |  | 220
|  | 132-001 | Title I design WBS 162 Coil leads |  | 2006-10-02 | 2007-04-11 | [9 empty] | 869 | 20 |  | 889
|  | 132-011 | Title II design WBS 162 Coil leads |  | 2007-04-12 | 2007-10-15 | [9 empty] | 869 | 20 |  | 889
|  | 132-015 | Title III design WBS 162 Coil leads |  | 2007-10-16 | 2008-01-17 | [7 empty] | 8 |  | 98 |  |  | 106
|  | 132-037 | Coil Leads Procurement WBS 162 |  | 2007-10-16 | 2008-01-17 |  |  | 223.62 |  | 223.62
| 162 - Electrical Leads Total | [7 empty] | 223.62 |  | 223.62 |  |  | 8 |  | 1856 | 240 |  | 2104
| 163 - Coil Protection System | 163.001 | Title I design WBS 163 Coil protection |  | 2006-10-02 | 2007-01-10 | [9 empty] | 82 | 80 | 80 | 242
|  | 163.011 | Title II design WBS 163 Coil protection |  | 2007-01-11 | 2007-03-07 | [9 empty] | 82 | 80 | 80 | 242
| 163 - Coil Protection System Total | [14 empty] | 164 | 160 | 160 | 484
Job: 1601 - Coil Services Design-WILLIAMSON Total | Coil Services Design & Procurement Total | [7 empty] | 320.93 |  | 320.93 | 321 | 248 | 102 | 374 | 2860 | 400 | 160 | 4144 | 4144