Report Date:  September, 2005		U. S. DOE Project Manager’s Progress Report	Office of Science

Project Number:  MIE-02	Title: National Compact Stellarator Experiment		Program: FE

Report Period:4th Quarter FY2005	Location: Princeton Plasma Physics Laboratory		Project Office: PSO

SUMMARY ASSESSMENT	PROJECT MANAGEMENT

### Current	Previous

Quarter	Quarter

Cost:	Satisfactory		Satisfactory		DOE Program Manager:	Barry Sullivan

Schedule: 	Satisfactory		Satisfactory	 	Phone:				301-903-8438

Technical:	Satisfactory 	Satisfactory		DOE Project Director:		Greg Pitonak

Overall:	Satisfactory	Satisfactory		Phone:				609-243-3713

### Contractor Project Manager: 	G. H. Neilson

Phone:				609-243-2726

#### COST/FUNDING ($K)	CRITICAL DECISIONS

### Baseline	Current Estimate	Funding Received	Number         	Baseline	         Actual/Forecast

### DOE TEC:	92,401	92,401	41,349

### DOE TPC:	N/A	N/A	N/A	1	                Aug, 2002      	Nov, 2002 (A)

NON DOE: 	0	0	0	2	                Jan, 2004	        Feb, 2004 (A)

3	                Oct, 2004        Sep, 2004 (A)

4   	             July, 2009      July, 2009 (F)

#### FUNDING PROFILES

#### Per Latest Approved Budget  in $M (as-spent)				Cumulative Costing through end of June, 2005

FY03     FY04     FY05     FY06     FY07    FY08   FY09  Total	TEC ($K)	TPC ($K)

### TEC:     7.9	       15.9	       17.5	       15.9      15.9        15.9	      3.4    92.4         Costs Accrued:                    $ 38,314	N/A

OPC:    N/A					     	 Uncosted Commitments:       $ 2,900		N/A

TPC:    N/A						 Remaining Uncommitted     $51,187		                       N/A

# SCHEDULE SUMMARY

Start Date	Completion Date 	Percent Complete

### Baseline	Forecast (9) /Actual	Baseline	Forecast (9) /Actual	Baseline	Actual

### Title I & II Design:                          10/02        	       04/03 (A)                 06/06 (2)	          6/07 (F)                                   84%              	  82%

### Procurement:                            	       08/03 (3)           08/03 (A)                04/07	(4)                  4/08  (F)                                  47%                45%

### Fab & Assembly 	                            01/05 (5)           12/04(A)                 12/07 (6)                 12/08 (F)                                             13%                  10%

### Start-up & Operation                      06/09	 (7)           06/09 (F)                  07/09 (8)                  7/09  (F)                                  0%	               0%

(2) Last WBS 1 FDR

(3)  VV Prototype Fabrication Release

(4) Delivery of Cryostat

(5) 1st Casting poured

(6) Complete Installation of Cryostat

(7) Begin Startup testing WBS 85

(8) First Plasma

(9) Forecast dates reflect revised baseline resulting from new DOE budget guidance.

Revised baseline was submitted for approval in April, 2005 and has not yet been approved by DOE.

Key Milestones          Completed Since Last Report				Baseline Date (PEP)	Actual Date

(LEVEL)

DOE			Approve Directed Baseline Change					July 2005         July 2005

Level II		First MCWF delivered						July 2005	Sep 2005

Key Milestones         Upcoming (Next Three Months)				Baseline Date(PEP) 	Forecast Date

(LEVEL)

Joule #4		Complete winding first modular coil					Sept 2005	Dec 2005

NARRATIVE HIGHLIGHTS (April thru June, 2005)

Modular Coil Winding Forms

- 9 total castings have been poured (6C, 3A).

- Machining of MCWF#C2 is progressing at an improved pace.

- C2 delivery expected in November.

- Machining of MCWF#3 has started. EIO delivery forecast: December.

Vacuum Vessel

  - Ports are being welded onto the first 120-degree segment.

  - The second 120-degree segment is being welded.

  - All 60 panels have been formed.

Coil Winding Preparations

- “Ready to wind” the C1 coil.

- Coil test facility completed& operational.

- Type C coil assembly Final Design Review completed.

- Parts procurement continues.

- Manufacturing procedures will continue to be optimized.

Other Work Packages

- WBS 13 TF Coil: Copper expected delivery October. Nose castings out for procurement. Winding facility nearing completion.

- Successful design reviews held for the following during the period;

        - WBS 13 Wedge Casting FDR

        - WBS 13 Comprehensive TF FDR

        - WBS 14 Mod Coil Type C FDR

        - WBS 4 Power Systems CDR

Management

Lehman review November 2-3 at PPPL.

- DOE directed rebaseline approved on July 27, 2005.

- The project maintains reports documenting its responses to the recommendations of all reviews and these are reviewed and updated regularly. The project also maintains a “critical issues” list as a primary risk management tool, which is reviewed at regularly scheduled IPT meetings.

- Performance metrics as of  9/30/2005

SPI =	.95

CPI=   .96

# WBS Cost Summary Plan (BO $k)

# Scope Item			FY03	          FY04	      FY05		FY06		FY07		FY08		 FY09	         Total

Actual	          Actual	      Plan       Actual(1)	Plan		Plan		Plan                      Plan

WBS-1   Core Systems	             $4,005	         $10,481      $15,535       $15,240	$11,908		$8,837		$4,448		$ 172	 $55,386

WBS-2   Heating, Fueling		$   207                $141       						   $175		   $260			      $783

WBS-3   Diagnostics		$   155	               $75	   $263         $   176 	      $212		    $82		   $355			   $1,142

WBS-4   Power Systems		$   115               $127	  $  373	      $   286   	      $252		$1,505		   $911		   $18	   $3,301

WBS-5   Central I&C		$     10                 $21      	      $ 9 	             $2         			     $25	              $1,861		$124	   $2,050

WBS-6   Facilities		$       9                 $15	      	        			                  $ 43		  $624			      $691

WBS-7   Assembly    		$   164               $197	     $324 	        $539	   $ 149		$251		$2,289		$999	  $4,373

WBS-8   Project Mgmt   		$1,277            $2,820(1)	  $2313 	     $2,328	 $2,119		$1,539		$1,483		$1,154	$12,705(1)

Total	Plan (BO)		$5,942	       $13,877	$18,817     $18,570          $14,640               $12,457               $12,231                  $2,467	$80,432

MR/Contingency	                                  -          		   	                             $3,840                  $3,472                  $3,041	              $1,616    $11,969

Total	Plan (BO)(ECP-36)        $5,942       $13,877                 $18,817                           $18,480           $15,929               $15,272          $4,083	$92,401

Total   Plan (BA)                         $7,897        $15,921                 $17,500                           $15,900           $15,900                $15,900          $3,383              $92,401

(1) includes $75K to DCMA for inspection services