## Budget Reconciliation
Proposed PMB Updates
| wbs 12 | 1203 | Vacuum Vessel Design incl Title III | 204.3 | Redesign of insulation scheme and cooling tubes
| wbs 12 | 1204 | VV Hardware | -97.8 | Cheaper tubes and insulation
| wbs 131 | 135x | TF Coil fabrication | 432.3 | Facility, Material and winding operation
| wbs 132 | 1352 | PF Coil design/fab | -466 | Use NSTX PF1a coil for central solenoid
| wbs 133 | 1354 | Trim Coils | -154 | Simplify design of trim coils
| wbs 14 | 1416 | Modular Coil Design for Type A & B incl interface hardware | 520.4 | re-estimated based on Type C experience
| wbs 14 | 1451 | Modular Coil Winding -Operations | -16.5 | Increased time for ground wrap, interlacing and shift differential offset by supervision and oversight reduction due to shorten schedule.
| wbs 14 | 1421 | Modular coil-to-coil interface hardware | 655.1 | Underestimated cost of shims and high strength bolts
| wbs 14 | 1411 | MCWF Title III | 68.5 | Req'd oversight of contract
| wbs 18 | 1803 | Eliminated 350C bakeout of field period assy | -40
| wbs 18 | 1803 | Field Period Tooling and Fixturing | -50 | Only 1 set of fixtures req'd
| wbs 31 | 3101 | Magnetic Diagnostics | 61.7 | Saddle loops and termination box design/fab
| wbs 38 | 3801 | E-beam mapping | -103.9 | Simplified application
| wbs 81 | 8101 | Project Management | -53.9 | Revised FY09 ETC Reqmnt
| wbs 82 | 8205 | Dimensional control | 84 | Coordination of metrology and design integration
| wbs 5x | 5x01 | Plasma Control | -100 | Simplified Plasma Control
| Other |  | re-scheduling and laboratory rate changes | -180
764.2
Unrecoverable Cost Variances
| wbs 13 | 1301 | TF Design | 119 | TF Design iterations
| wbs 13 | 1350/1351 | TF Fabrication facilities | 149 | Design time plus materials. Electrical sys debugging.
| wbs 14 | 1403 | Modular Coil Type C detail design | 409 | Iterative process in conjunction with TRC fabrication.
| wbs 14 | 1414/1409 | Coil test facility fabrication and TRC testing | 150 | Cryogenic systems debugging and design. Safety design safeguards.
| wbs 14 | 1411 | MCWF 1st production casting | 137 | (part of prototype contract)
| wbs 14 | 1411 | MCWF contract oversight | 110 | Working with EIO addressing technical reqmnts and schedule.
| wbs 17 | 1701 | Cryostat & base support structure prel dsn | 178 | Designer and engineering time underestimated
| wbs 74 | 7401 | Test cell electrical power supply | 178 | House power for test cell.
| wbs 4 | 4x01 | Electrical pwr sys DC sys & coil protection | 68 | DC systems engineering.
| Other |  |  | 95
1593
2357.2

## ECP38 reconciliation
NCSX rebaseline reconciliation
|  | ECP-036 | ECP-39 | Changes
111 - Limiters
12 - Vacuum Vessel Systems | [6 empty] | etc | ETC/rates | cv
| 121 - Vacuum Vessel Assembly | 8548.22 | 8630 | 81.78 | 121 | 8630 | 8698 | 149.78 | -68
| 122 - Vacuum Vessel Thermal Insulation | 191.89 | 172.3 | -19.59 | 122 | 172.3 | 172.3 | -19.59
| 123 - Vacuum Vessel Heating and Cooling Distrib | 535.98 | 364.9 | -171.08 | 123 | 364.9 | 364.9 | -171.08
| 124 - Vacuum Vessel Supports | 106.1 | 247.5 | 141.4 | 124 | 247.5 | 247.5 | 141.4
| 125 - Vacuum Vessel Local I&C | 17.64 | 24.6 | 6.96 | 125 | 24.6 | 24.6 | 6.96
| subtotal | 9399.83 | 9439.3 | 39.47 |  | -68 |  | 107.47 | -68
13 - Conventional Coils | [5 empty] | 0 |  | 0
| 130 - Conventional Coil Design | 837.4 | 837.4 | 0 | 130 | 837.4 | 837.4 | 0
| 131 - TF Coils | 1717.83 | 2399 | 681.17 | 131 | 2399 | 2153 | 435.17 | 246
| 132 - PF Coils | 1885.36 | 1400 | -485.36 | 132 | 1400 | 1400 | -485.36
| 133 - External Trim Coils | 257.67 | 103.4 | -154.27 | 133 | 103.4 | 103.4 | -154.27
| 134 - Conventional Coil Local | 91.87 | 91.2 | -0.67 | 134 | 91.2 | 91.2 | -0.67
| subtotal | 4790.13 | 4831 | 40.87 |  | 246 |  | -205.13 | 246
14 - Modular Coils | [5 empty] | 0 |  | 0
| 141 - Modular Coil Winding Form | 13271.57 | 12727 | -544.57 | 141 | 12727 | 12437 | -834.57 | 290
| 142 - Modular Coil Windings and Assembly | 11978.769 | 14580.5 | 2601.731 | 142 | 14580.5 | 13956.5 | 1977.731 | 624
| 143 - Modular Coil Local I&C | 0 | 0 | 0 |  | 0 |  | 0
| 144 - Modular Coil Winding Facility & Fixtures | 3863.201 | 4048.4 | 185.199 | 144 | 4048.4 | 3918.4 | 55.199 | 130 | 1044
| subtotal | 29113.54 | 31355.9 | 2242.36 |  | 1044 |  | 1198.36 | 1044
15 - Structures | [5 empty] | 0 |  | 0
| 151 - Coil Support Structure | 1412.96 | 1386.2 | -26.76 | 151 | 1386.2 | 1387.2 | -25.76 | -1
16 - Coil Services | [5 empty] | 0 |  | 0
| 161 - LN2 Distribution | 372.04 | 368.5 | -3.54 | 161 | 368.5 | 368.5 | -3.54
| 162 - Electrical Leads | 681.64 | 681 | -0.64 | 162 | 681 | 681 | -0.64
| 163 - Coil Protection System | 86.3 | 85.5 | -0.8 | 163 | 85.5 | 85.5 | -0.8
| subtotal | 1139.98 | 1135 | -4.98 |  | -1 |  | -4.98 | -1
17 - Cryostat and Base Support Structure | [5 empty] | 0 |  | 0
| 171 -Cryostat | 934.01 | 1105.2 | 171.19 | 171 | 1105.2 | 927.2 | -6.81 | 178
| 172 - Base Support Structure | 426.93 | 427.7 | 0.77 | 172 | 427.7 | 427.7 | 0.77
| 173-Spacer manipulator | 0 | 0 | 0 |  | 0 |  | 0
| subtotal | 1360.94 | 1532.9 | 171.96 |  | 178 |  | -6.04 | 178
18 - Field Period Assembly | [5 empty] | 0 |  | 0
| 181 - Field Period Assembly Planning/Oversight | 1505.26 | 1545.8 | 40.54 | 181 | 1545.8 | 1488.8 | -16.46 | 57
| 182 - TFTR Test Cell Area preparations | 0 | 70.3 | 70.3 | 182 | 70.3 | 70.3 | 70.3
| 183 - Receive Inspect and Test Coils | 0 | 0 | 0 |  | 0 |  | 0
| 184 - Receive Inspect and Test VV | 0 | 0 | 0 |  | 0 |  | 0
| 185 - Assemble Field Periods | 2203.28 | 2063.2 | -140.08 | 185 | 2063.2 | 2063.2 | -140.08
| 186 - Tooling Design and Fabrication | 1219.66 | 1051.1 | -168.56 | 186 | 1051.1 | 1199.1 | -20.56 | -148
| 187 - Measurement Systems | 501.77 | 550.4 | 48.63 | 187 | 550.4 | 482.4 | -19.37 | 68 | -23
| subtotal | 5429.97 | 5280.8 | -149.17 |  | -23 |  | -126.17 | -23
19 - Stellarator Core Management and Integration | [5 empty] | 0 |  | 0
| 191 - Stellarator Core Management & Oversight | 1041.61 | 1054.2 | 12.59 | 191 | 1054.2 | 1045.2 | 3.59 | 9
| 192 - Stellarator Core Integration & Analysis | 1696.49 | 1712.9 | 16.41 | 192 | 1712.9 | 1712.9 | 16.41
| subtotal | 2738.1 | 2767.1 | 29 |  | 9 |  | 20 | 9
| SUBTOTAL WBS 1 | 55385.45 | 57728.2 | 2342.75 |  | 1384 |  | 957.75 | 1384
[6 empty] | 0 |  | 0
21 - Fueling Systems |  | 86.54 | 88.1 | 1.56 | 210 | 88.1 | 88.1 | 1.56
22 - Torus Vacuum Pumping Systems |  | 412.55 | 418.8 | 6.25 | 220 | 418.8 | 418.8 | 6.25
25 - Neutral Beam Injection System |  | 284.37 | 284.4 | 0.03 | 250 | 284.4 | 284.4 | 0.03
| SUBTOTAL WBS 2 | 783.46 | 791.3 | 7.84 |  | 0 |  | 7.84 | 0
31 - Magnetic Diagnostics |  | 426.35 | 551.6 | 125.25 | 310 | 551.6 | 521.6 | 95.25 | 30
36 - Edge and Divertor Diagnostics |  | 45.96 | 45.6 | -0.36 | 360 | 45.6 | 45.6 | -0.36
38 - Electron Beam (EB) Mapping |  | 310.09 | 206.2 | -103.89 | 380 | 206.2 | 206.2 | -103.89
39 - Diagnostics Integration |  | 360.52 | 345.3 | -15.22 | 390 | 345.3 | 357.3 | -3.22 | -12
| SUBTOTAL WBS 3 | 1142.92 | 1148.7 | 5.78 |  | 18 |  | -12.22 | 18
41 - AC Power | [5 empty] | 0 |  | 0
| 411 - Auxliary AC Power Systems | 382.03 | 376.4 | -5.63 | 411 | 376.4 | 374.4 | -7.63 | 2
| 412 - Experimental AC Power Systems | 48.14 | 47.5 | -0.64 | 412 | 47.5 | 47.5 | -0.64
43 - DC Systems | [5 empty] | 0 |  | 0
| 431 - C-Site DC Systems | 453.94 | 478.8 | 24.86 | 431 | 478.8 | 409.8 | -44.14 | 69
| 432 - D-to-C Site DC Systems | 0 | 0 | 0 |  | 0 |  | 0
| 433 - D-Site DC Systems | 0 | 0 | 0 |  | 0 |  | 0
44 - Control and protection Systems | [5 empty] | 0 |  | 0
| 441 - Electrical Interlocks | 377.66 | 377 | -0.66 | 441 | 377 | 377 | -0.66
| 442 - Kirk Key Interlocks | 82.18 | 81.4 | -0.78 | 442 | 81.4 | 81.4 | -0.78
| 443 - Real Time Control Systems | 14.27 | 13.8 | -0.47 | 443 | 13.8 | 13.8 | -0.47
| 444 - Instrument Systems | 312.65 | 307.5 | -5.15 | 444 | 307.5 | 307.5 | -5.15
| 445 - Coil protection Systems | 522.1 | 566.3 | 44.2 | 445 | 566.3 | 517.3 | -4.8 | 49
45 - Power System Design and Integration | [5 empty] | 0 |  | 0
| 451 - System Design and Interfaces | 520.33 | 478.1 | -42.23 | 451 | 478.1 | 530.1 | 9.77 | -52
| 452 - Electrical Systems Support | 261.74 | 259.3 | -2.44 | 452 | 259.3 | 259.3 | -2.44
| 453 - System Testing (PTP's) | 324.72 | 317.7 | -7.02 | 453 | 317.7 | 317.7 | -7.02
[6 empty] | 0 |  | 0
46 - FCPC Building Modifications |  | 1.3 | 1.3 |  | 460 | 1.3 | 1.3 | 0
| SUBTOTAL WBS 4 | 3301.06 | 3305.1 | 4.04 |  | 68 |  | -63.96 | 68
[6 empty] | 0 |  | 0
51 - TCP/IP Infrastructure Systems |  | 282.69 | 280.4 | -2.29 | 510 | 280.4 | 280.4 | -2.29
52 - Central Instrumentation & Control |  | 610.92 | 530.1 | -80.82 | 520 | 530.1 | 530.1 | -80.82
53 - Data Acquisition & Facility Computing |  | 351.01 | 329.1 | -21.91 | 530 | 329.1 | 329.1 | -21.91
54 - Facility Timing & Synchronization |  | 220.96 | 195.8 | -25.16 | 540 | 195.8 | 195.8 | -25.16
55 - Real Time Plasma & Power Supply Control Sys |  | 161.65 | 179.3 | 17.65 | 550 | 179.3 | 179.3 | 17.65
56 - Central Safety Interlock Systems |  | 381.94 | 325.5 | -56.44 | 560 | 325.5 | 325.5 | -56.44
58 - Central I&C management and Integration |  | 40.36 | 33.4 | -6.96 | 580 | 33.4 | 40.4 | 0.04 | -7
| SUBTOTAL WBS 5 | 2049.53 | 1873.6 | -175.93 |  | -7 |  | -168.93 | -7
61 - Water Systems | [5 empty] | 0 |  | 0
| 611 - C-Site Cooling System | 0 | 0 | 0 |  | 0 |  | 0
| 612 - NB Water Cooling Systems | 0 | 0 | 0 |  | 0 |  | 0
| 613 - Vacuum Pumping System | 94.51 | 92.3 | -2.21 | 613 | 92.3 | 92.3 | -2.21
| 614 - Bakeout Water System | 0 | 0 | 0 |  | 0 |  | 0
62 - Cryogenic Systems | [5 empty] | 0 |  | 0
| 621 - LN2-LHe Supply System | 233.04 | 229 | -4.04 | 621 | 229 | 229 | -4.04
| 622 - LN2 Coil Cooling Supply | 0 | 0 | 0 | 622 | 0 |  | 0
| 623 - GN2 Cryostat Cooling System | 230.22 | 226 | -4.22 | 623 | 226 | 226 | -4.22
[6 empty] | 0 |  | 0
63 - Utility Systems |  | 109.3 | 106.9 | -2.4 | 630 | 106.9 | 106.9 | -2.4
65 - Facility Systems Integration | [5 empty] | 0 |  | 0
| 612 - NB Water Cooling Systems | 9.38 | 9.4 | 0.02 | 612 | 9.4 | 9.4 | 0.02
| 650 - Facility Systems Integration | 15 | 15 | 0 | 650 | 15 | 15 | 0
| SUBTOTAL WBS 6 | 691.45 | 678.6 | -12.85 |  | 0 |  | -12.85 | 0
71 - Shield Wall Seismic Modifications |  | 32.15 | 32.2 | 0.05 | 710 | 32.2 | 32.2 | 0.05
72 - Control Room Refurbishment |  | 8.09 | 9.1 | 1.01 | 720 | 9.1 | 9.1 | 1.01
73 - Platform Design & Fabrication |  | 164.42 | 109.1 | -55.32 | 730 | 109.1 | 159.1 | -5.32 | -50
74 - Machine Assembly Planning and Oversight |  |  |  | 0 |  | 0 |  | 0
| 740 - Machine Assembly Planning and Oversight | 152.71 | 335.8 | 183.09 | 740 | 335.8 | 157.8 | 5.09 | 178
| 741 - Planning Prior to Machine Assembly | 312.58 | 312.6 | 0.02 | 741 | 312.6 | 312.6 | 0.02
| 742 - Construction Management | 1099.47 | 1104.8 | 5.33 | 742 | 1104.8 | 1104.8 | 5.33
75 - Test Cell and Basement Assembly Operations |  |  |  | 0 |  | 0 |  | 0
| 750 - Test Cell & Basement Assembly Operations | 2365.55 | 2413.8 | 48.25 | 750 | 2413.8 | 2413.8 | 48.25
76 - Tooling Design & Fabrication |  | 238.25 | 237.8 | -0.45 | 760 | 237.8 | 237.8 | -0.45
| SUBTOTAL WBS 7 | 4373.22 | 4555.2 | 181.98 |  | 128 |  | 53.98 | 128
81 - Project Management and Control |  | 4508.81 | 4452.9 | -55.91 | 810 | 4452.9 | 4442.9 | -65.91 | 10
82 - Project Engineering |  | 4885.08 | 4904.1 | 19.02 | 820 | 4904.1 | 4969.1 | 84.02 | -65
84 - Project Physics |  | 469.93 | 469.9 | -0.03 | 840 | 469.9 | 469.9 | -0.03
85 - Integrated Systems Testing |  | 1189.18 | 1197.7 | 8.52 | 850 | 1197.7 | 1197.7 | 8.52
| SUBTOTAL WBS 8 | 11053 | 11024.6 | -28.4 |  | -55 |  | 26.6 | -55 |  | 12633
PPPL Allocations |  | 1576.89 | 1608.4 | 31.51 | AAA | 1608.4 | 1552.4 | -24.49 | 56
[6 empty] | 0 |  | 0
Contingency |  | 11969.1 | 9612 | -2357.1 | CCC | 9612
0
DCMA Support |  | 75 | 75 | 0 | DDD | 75 | 75
|  | 92401.39 | 92400.7 | -0.38 |  | 95321.7 | 81195.7 | 763.72 | 1592 | 2355.72
82713.7

## Budget Summary
| Current Baseline | Unrecoverable Cost Variances | ETC Updates & Design Changes | Total Budget Change |  | Proposed PMB
12 - Vacuum Vessel Systems | 9400 | -68 | 107 | 39 |  | 9439
13 - Conventional Coils | 4790 | 246 | -205 | 41 |  | 4831
14 - Modular Coils | 29114 | 1043.5 | 1198 | 2241.5 |  | 31355.5
15 - Structures | 1413 | -1 | -26 | -27 |  | 1386
16 - Coil Services | 1140 |  | -5 | -5 |  | 1135
17 - Cryostat and Base Support Struct | 1361 | 178 | -6 | 172 |  | 1533
18 - Field Period Assembly | 5430 | -23 | -126 | -149 |  | 5281
19 - Stellarator Core Mgt & Integr | 2738 | 9 | 20 | 29 |  | 2767
1 Stellarator Core Systems | 55386 | 1384.5 | 957 | 2341.5 |  | 57727.5
2 Heating, Fueling & Vac Sys | 783 |  | 8 | 8 |  | 791
3 Diagnostics | 1143 | 18 | -12 | 6 |  | 1149
4 Electrical Power Sys | 3301 | 68 | -64 | 4 |  | 3305
5 Central I&C Sys | 2050 | -7 | -169 | -176 |  | 1874
6 Facility Sys | 691 |  | -13 | -13 |  | 678
7 Test Cell Prep & MachAssy | 4373 | 128.5 | 54 | 182.5 |  | 4555.5
8 Project Oversight & Support | 12630 | 1 | 3 | 4 |  | 12634
subtotal | 80357 | 1593 | 764 | 2357 |  | 82714
Contingency | 11969 | -1593 | -764 | -2357 |  | 9612
TEC = | 92326 |  |  |  |  | 92326
DCMA | 75 |  |  |  |  | 75
| 92401 |  |  |  |  | 92401
|  |  |  | BCWR |  | 44400
|  |  |  | Contingency balance |  | 9612
21.65%
|  |  |  | BCWP | 36720
|  |  |  | ACWP | 38313
|  |  |  | CPI | 0.95842 |  | 92400
|  |  |  | CV | 1593

## Milestones
|  |  | CD-2 | CD-2
|  |  | Baseline |  | Baseline | float | Forecast | Actual | master schedule | Milestone float
| Level I | CD-1 | 2003-05-01 | 0 | 2003-05-01 |  |  | 2003-05-01
M-0110 |  | CD-2 | 2004-02-01 | 0 | 2004-02-01 |  |  | 2004-02-01
M-0115 |  | CD-3 | 2004-09-30 | 0 | 2004-09-30 |  |  | 2004-09-30
M-0120 |  | CD-4 | 2008-05-30 | 14.2333 | 2009-07-31 | 1900-01-04 03:12 | 2009-02-27 |  | 2009-02-27 | 5.1333
0
1201-500 | Level II | Vacuum Vessel & Modular Coil Prel Dsn Rvw | 2003-10-07 | 0 | 2003-10-07 |  |  | 2003-10-07
1403-08 |  | Performance Baseline Review | 2003-11-18 | 0 | 2003-11-18 |  |  | 2003-11-18
1203-341 |  | Conduct VVSA FDR | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1403-51 |  | Mod Coil Winding Form Final Design Review | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1408-143.1 |  | Award MC Conductor Contract |  |  | 2004-12-19 |  |  | 2004-10-15
121-6-9 |  | Award VV Production Vendor | 2004-12-01 | -2 | 2004-10-15 |  |  | 2004-09-15
C-081 |  | Award MCWF Mfg Contract | 2004-11-01 | -1 | 2004-10-01 |  |  | 2004-09-15
C-121.1 |  | First MCWF Delivered | 2005-03-01 | 4 | 2005-07-15 | 1284.9333 |  | 2005-09-30
131-035 |  | Begin TF Coil fabrication activities | 2005-04-01 | 3 | 2005-09-30 | 1287.5 |  | 2005-06-30
P1-021.1 |  | Complete First Mod Coil Fabrication | 2005-08-31 | 6 | 2006-03-29 | 2006-04-15 | 2006-02-28 |  | 2006-03-29 | 0
121-038.1 |  | Vacuum Vessel Sectors Delivered | 2006-02-01 | 0 | 2006-09-15 | 5.9333 | 2006-03-21 |  | 2006-03-21 | 5.9333
C-501B1 |  | Last MCWF Delivered | 2006-08-01 | 4 | 2007-06-15 | 3.5667 | 2007-02-28 |  | 2007-02-28 | 3.5667
141-036 |  | PF Coils Awarded | 2006-06-01 | 7 | 2008-03-30 | 5.1667 | 2007-10-27 |  | 2007-10-27 | 5.1667
S3P1-101 |  | Begin Assembly of First Field Period | 2006-09-01 | 6 | 2007-07-01 | 5.6667 | 2007-01-12 |  | 2007-01-12 | 5.6667
1351-195x |  | All TF Coils Delivered | 2007-01-01 | 4 | 2008-08-15 | 9 | 2007-11-19 |  | 2007-11-19 | 9
S4P3-115 |  | Last Field Period Assembled | 2007-06-01 | 3 | 2008-11-15 | 5.2 | 2008-06-12 |  | 2008-06-12 | 5.2
7503-250 |  | Begin Vac Vsl Pumpdown | 2007-09-01 | 2 | 2009-02-11 | 5.1 | 2008-09-11 |  | 2008-09-11 | 5.1
7503-330 |  | Begin Cryostat Installation | 2007-11-01 | 2 | 2009-04-07 | 5.0333 | 2008-11-07 |  | 2008-11-07 | 5.0333
730.1250 |  | Operational Readiness | 2007-11-01 | 4 | 2009-06-01 | 5.1667 | 2008-12-28 |  | 2008-12-28 | 5.1667
920.004 |  | Begin Start-up Testing | 2008-03-31 | 0 | 2009-06-16 | 5.0333 | 2009-01-16 |  | 2009-01-16 | 5.0333
0
1404-109.J | Joule | FY04 JOULE #1-Authorize Prototype Fab | 2003-12-20 | 0.33333 | 2003-12-30 |  |  | 2003-10-20
1406-040 |  | FY04 JOULE #2-Begin winding on 3D surface | 2004-03-01 | 1 | 2004-03-31 |  |  | 2004-01-30
1404-110.J |  | FY04 JOULE #3-Prototype Casting Ready for Machining | 2004-06-01 | 0.96667 | 2004-06-30 |  |  | 2004-05-26
C-081.1 |  | FY04 JOULE #4 - CD-3 Readiness | 2004-09-01 | 0.96667 | 2004-09-30 |  |  | 2004-09-15
1408-143.1 |  | FY05 JOULE #1- VVSA, MCWF and MC Copper Conductor Awarded |  | 1278.3667 | 2004-12-30 | 2.5333 |  | 2004-10-15
1406-017.3 |  | FY05 JOULE #2- Cmplt Assy of twisted racetrack |  | 1281.4 | 2005-03-31 | 1281.4 |  | 2005-03-30
1403-20 |  | FY05 JOULE #3- Mod Coil Winding Type C FDR |  | 1284.4333 | 2005-06-30 | 1284.4333 |  | 2005-06-30
P1-011J |  | FY05 JOULE #4- Complete Winding First MC |  | 1287.5 | 2005-09-30 | 2005-10-31 | 2005-12-30 |  | 2005-12-15 | -2.5333
mcwf-311 |  | FY06 JOULE Receive all VVSA and 1/3 of MCWF's |  |  | 2006-09-30 |  | 2006-03-22 |  | 2006-03-22 | 6.4
P2-041joul |  | FY07 JOULE Complete Winding of 1/2 of Modular Coils |  |  | 2007-09-30 |  | 2006-11-06 |  | 2006-11-06 | 10.9333
NCSX Milestone Status
Formulas:
Actual = +[Baseline]
float = (+[Baseline]-[Forecast])/30
Forecast = SUM([master schedule])
Forecast = +[master schedule]

## Funding
Total
| Original BA | 7.9 | 15.83 | 15.84 | 22.14 | 19.42 | 5.2 |  | 86.33
| New BA | 7.9 | 15.83 | 17.5 | 15.9 | 15.9 | 15.9 | 5.199 | 94.129
| PMB | 6.062 | 13.658 | 18.238 | 15.425 | 13.289 | 12.748 | 2.466 | 81.886
| Contingency |  |  | 0.8 | 3 | 2.6 | 3.1 | 2.742 | 12.242
| BA cum old | 7.9 | 23.73 | 39.57 | 61.71 | 81.13 | 86.33 | 86.33
| BA cum new | 7.9 | 23.73 | 41.23 | 57.13 | 73.03 | 88.93 | 94.129
| PMB cum | 6.062 | 19.72 | 37.958 | 53.383 | 66.672 | 79.42 | 81.886
%
24.8%
|  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total
| 22.01% |  | BA | 7.897 | 15.921 | 17.5 | 15.9 | 15.9 | 15.9 | 3.383 | 92.401
|  |  | PMB | 5.9419 | 14.2393 | 18.162 | 17.515 | 13.409 | 11.14 | 2.331 | 82.7382
| 5% |  | Contingency |  |  |  | 1.295 | 2.518 | 4.75 | 1.049 | 9.612
| 10% |  | BO (PMB + Cont) | 5.9419 | 14.2393 | 18.162 | 18.81 | 15.927 | 15.89 | 3.38 | 92.3502
33.49%
| 19.58% |  | Cum BA | 7.897 | 23.818 | 41.318 | 57.218 | 73.118 | 89.018 | 92.401
| 11.24% |  | Cum PMB | 5.9419 | 20.1812 | 38.3432 | 55.8582 | 69.2672 | 80.4072 | 82.7382
22.01%
|  |  | Cum BO | 5.9419 | 20.1812 | 38.3432 | 57.1532 | 73.0802 | 88.9702 | 92.3502
|  |  | pmb puts and takes |  |  | -0.415 | -1.047 | -0.712 | 0.151 | 0.121
|  |  | contingency puts and takes |  | 0 | 0.415 | 1.047 | 0.712 | -0.151 | -0.121
|  |  |  | wbs1 | -0.24 | -0.12 | -0.12
|  |  |  | wbs13 | -0.6 | -0.2 | -0.2 | -0.2
|  |  |  | wbs 141 | -0.64 |  | -0.32 | -0.32
|  |  |  | wbs142 | -0.095 | -0.095
|  |  |  | wbs142 | -0.097 |  | -0.097
|  |  |  | wbs18 | -0.3 |  | -0.15 | -0.15
|  |  |  | wbs82 | -0.32 |  | -0.16 | -0.16
|  |  |  | red | 0.48 |  |  | 0.118 | 0.151 | 0.121
0.09
FY04 FY05 FY06 FY07 FY08 FY09
$23.8
$73.1
$57.2
41.3
$92.4
$89.0

## wbs2 budgets by fy
| WBS2 |  |  | ACT CODE | DESCRIPTION | FY2003 | FY2004 | FY2005 | FY05 CV | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL | ACT CODE
| 0.1 |  | 0 | 11 | 11 - In-Vessel Components | 0.1 | [7 empty] | 0.1 | 11
| 6252 |  | 3254.7 | 12 | 12 - Vacuum Vessel Systems | 1217.4 | 1663.3 | 3371.3 | -68 | 2970.4 | 194.9 | 89.4 |  | 9438.7 | 12
| 1265.9 |  | 3316.3 | 13 | 13 - Conventional Coils | 91.7 | 333.9 | 840.3 | 245 | 1277.9 | 917.1 | 1121.3 |  | 4827.2 | 13
| 17722.9 |  | 12584.5 | 14 | 14 - Modular Coils | 2424.8 | 7314.1 | 7984 | 1043.5 | 8551.7 | 3945.6 | 87.2 |  | 31350.9 | 14
| 78.9 |  | 1308.3 | 15 | 15 - Structures |  | 34.6 | 44.3 | -1 | 130.6 | 1173 | 4.7 |  | 1386.2 | 15 | 3945.4
| 0 |  | 1135 | 16 | 16 - Coil Services |  |  |  | 0 |  | 660 | 475 |  | 1135 | 16
| 193.2 |  | 1161.9 | 17 | 17 - Cryostat and Base Support Structure | 12.2 | 80.9 | 100.1 | 178 | 5.5 | 618.1 | 531.2 | 7.1 | 1533.1 | 17
| 1356.9 |  | 3945.4 | 18 | 18 - Field Period Assembly | 60.8 | 362.5 | 933.6 | -22 | 1175.9 | 1704.4 | 1053.5 | 11.6 | 5280.3 | 18
28345.6 | 1475.7 |  | 1282.5 | 19 | 19 - Stellarator Core Management and Integration | 254.2 | 640.7 | 580.8 | 9 | 515.7 | 361.6 | 251.5 | 153.7 | 2767.2 | 19 | 57718.7
| 0 |  | 88.1 | 21 | 21 - Fueling Systems | [5 empty] | 52.7 | 35.4 |  | 88.1 | 21 | 791.4
| 63.7 | 443.3 | 355.2 | 22 | 22 - Torus Vacuum Pumping Systems | 63.7 |  |  |  |  | 125.5 | 229.7 |  | 418.9 | 22
| 284.4 |  | 0 | 25 | 25 - Neutral Beam Injection System | 123 | 161.4 | [6 empty] | 284.4 | 25
| 100.2 | 744.2 | 421.9 | 31 | 31 - Magnetic Diagnostics |  |  | 100.2 | 30 | 314.2 | 92.5 | 15.2 |  | 552.1 | 31 | 1149.3
| 0 |  | 45.6 | 36 | 36 - Edge and Divertor Diagnostics | [5 empty] | 5.7 | 39.9 |  | 45.6 | 36
| 0 |  | 206.2 | 38 | 38 - Electron Beam (EB) Mapping | [6 empty] | 206.2 |  | 206.2 | 38
| 286.9 |  | 70.5 | 39 | 39 - Diagnostics Integration | 155.5 | 65 | 66.4 | -12 | 70.5 |  |  |  | 345.4 | 39
| 104.5 | 2779.2 | 317.4 | 41 | 41 - AC Power |  | 85.8 | 18.7 | 2 | 0.1 | 288 | 29.3 |  | 423.9 | 41 | 3305.1
| 156.9 |  | 252.9 | 43 | 43 - DC Systems |  |  | 156.9 | 69 | 38.4 | 214.5 |  |  | 478.8 | 43
| 5.5 |  | 1291.6 | 44 | 44 - Control and protection Systems |  | 1.1 | 4.4 | 49 |  | 842.5 | 431.3 | 17.8 | 1346.1 | 44
| 189.7 |  | 917.3 | 45 | 45 - Power System Design and Integration | 112.3 | 29.9 | 47.5 | -52 | 129.2 | 350.4 | 437.7 |  | 1055 | 45
| 1.3 |  | 0 | 46 | 46 - FCPC Building Modifications | 1.3 | [7 empty] | 1.3 | 46
| 27.9 | 1840.2 | 280.4 | 51 | 51 - TCP/IP Infrastructure Systems | 11.9 | 16 |  |  |  |  | 280.4 |  | 308.3 | 51 | 1873.6
| 0 |  | 530.1 | 52 | 52 - Central Instrumentation & Control | [5 empty] | 9.4 | 429.1 | 91.6 | 530.1 | 52
| 0 |  | 329.1 | 53 | 53 - Data Acquisition & Facility Computing | [5 empty] | 11.1 | 299.1 | 18.9 | 329.1 | 53
| 0 |  | 195.8 | 54 | 54 - Facility Timing & Synchronization | [6 empty] | 195.8 |  | 195.8 | 54
| 0 |  | 179.3 | 55 | 55 - Real Time Plasma & Power | [6 empty] | 179.3 |  | 179.3 | 55
| 0 |  | 325.5 | 56 | 56 - Central Safety Interlock | [6 empty] | 325.5 |  | 325.5 | 56
| 12.5 |  | 0 | 58 | 58 - Central I&C management and Integration |  |  | 12.5 | -7 |  |  |  |  | 5.5 | 58
| 0 | 654.2 | 92.3 | 61 | 61 - Water Systems | [6 empty] | 92.3 |  | 92.3 | 61 | 678.6
| 0 |  | 455 | 62 | 62 - Cryogenic Systems | [5 empty] | 41.8 | 413.2 |  | 455 | 62
| 0 |  | 106.9 | 63 | 63 - Utility Systems | [6 empty] | 106.9 |  | 106.9 | 63
| 24.4 |  | 0 | 65 | 65 - Facility Systems Integration | 9.4 | 15 | [6 empty] | 24.4 | 65
768.7 | 32.2 | 3666.9 | 0 | 71 | 71 - Shield Wall Seismic Modifications | 32.2 | [7 empty] | 32.2 | 71 | 4563.1
| 0 |  | 9.1 | 72 | 72 - Control Room Refurbishment | [5 empty] | 9.1 |  |  | 9.1 | 72
| 120.7 |  | 38.3 | 73 | 73 - Platform Design & Fabrication |  |  | 120.7 | -50 |  | 38.3 |  |  | 109 | 73
| 615.8 |  | 959.2 | 74 | 74 - Machine Assembly Planning and Oversight | 164 | 238.2 | 213.6 | 177.5 | 17.6 | 188.5 | 496.1 | 257 | 1752.5 | 74
| 0 |  | 2422.5 | 75 | 75 - Test Cell and Basement Assembly Operations | [5 empty] | 74.6 | 1664.4 | 683.5 | 2422.5 | 75
| 0 |  | 237.8 | 76 | 76 - Tooling Design & Fabrication | [6 empty] | 176.4 | 61.4 | 237.8 | 76
| 2921.5 | 6284.6 | 3073.4 | 81 | 81 - Project Management and Control | 557.9 | 1221.8 | 1141.8 | 67 | 1138.1 | 1044.1 | 758.9 | 132.3 | 6061.9 | 81 | 12634.3
| 2956.2 |  | 2011.9 | 82 | 82 - Project Engineering | 518.9 | 1230.9 | 1206.4 | -65 | 1180.6 | 445.9 | 322.6 | 62.8 | 4903.1 | 82
| 470 |  | 0 | 84 | 84 - Project Physics | 251.3 | 218.7 | [6 empty] | 470 | 84
|  |  | 1199.3 | 85 | 85 - Integrated Systems Testing | [6 empty] | 365.1 | 834.2 | 1199.3 | 85
[6 empty] | 6062.6 | 13713.8 | 16943.5 | 1593 | 17516.4 | 13409.3 | 11143.6 | 2331.9 | 82714.1 | 82714.1 | 86659.5
[8 empty] | 36719.9 |  | 44401.2
|  |  |  | CC | Contingency |  |  | 1582 | 1593 | 1295 | 2518 | 4750 | 1049 | 9612 | CC
[6 empty] | 6062.6 | 13713.8 | 18536.5 |  | 18811.4 | 15927.3 | 15893.6 | 3380.9 | 92326.1 | 92326.1
[8 empty] | 38313 | 38312.9
|  |  |  | DD | DCMA |  | 75 | [6 empty] | 75 | 75
[10 empty] | 57124.3 | 73051.6 |  |  | 92401.1
2921.5
2956.2
[6 empty] | 557.9 | 1221.8 | 1141.8 | 67 | 1138.1 | 1044.1 | 758.9 | 132.3
92401.1