## RiskOpportunities
| Risk |  | Opportunity
Modular Coil Winding Operations | 661 | Re-evaluate after 3 coils are fabricated | -445 | Process improvement studies challenge to reduce hours by 10%.
TF Coil Winding Operations | 448.1 | Accept facility, material and 1st coil fabrication increase only. | -82 | Process improvement studies challenge to reduce hours by 10%.
Field Period & Machine Assembly |  |  | -404 | Two shift field period assy and final machine assy. Accelerates first plasma by 2 months.
| 1109.1 |  | -931

## Budget Reconciliation
ETC Update
| wbs 12 | 1203 | Vacuum Vessel Design incl Title III | 204.3 | Redesign of insulation scheme and cooling tubes
| wbs 12 | 1204 | VV Hardware | -97.8 | Cheaper tubes and insulation
| wbs 131 | 135x | TF Coil fabrication | 432.3 | Facility, Material and winding operation
| wbs 132 | 1352 | PF Coil design/fab | -466 | Use NSTX PF1a coil for central solenoid
| wbs 133 | 1354 | Trim Coils | -154 | Simplify design of trim coils
| wbs 14 | 1416 | Modular Coil Design for Type A & B incl interface hardware | 520.4 | re-estimated based on Type C experience
| wbs 14 | 1451 | Modular Coil Winding -Operations | 241.5 | Increased time for ground wrap and interlacing and shift differential
| wbs 14 | 1451 | Modular Coil Winding -Supervision/Oversight | -258 | overall duration shortened due to two shift ops
| wbs 14 | 1421 | Modular coil-to-coil interface hardware | 655.1 | Underestimated cost of shims and high strength bolts
| wbs 14 | 1411 | MCWF Title III | 68.5 | Req'd oversight of contract
| wbs 18 | 1803 | Eliminated 350C bakeout of field period assy | -40
| wbs 18 | 1803 | Field Period Tooling and Fixturing | -50 | Only 1 set of fixtures req'd
| wbs 31 | 3101 | Magnetic Diagnostics | 61.7 | Saddle loops and termination box design/fab
| wbs 38 | 3801 | E-beam mapping | -103.9 | Simplified application
| wbs 81 | 8101 | Project Management | -53.9 | Revised FY09 ETC Reqmnt
| wbs 82 | 8205 | Dimensional control | 84 | Coordination of metrology application and design integration
| wbs 5x | 5x01 | Plasma Control | -100 | Simplified Plasma Control
| Other |  | re-scheduling and laboratory rate changes | -180
764.2
Unrecoverable Cost Variances
| wbs 13 | 1301 | TF Design | 119 | TF Design iterations
| wbs 13 | 1350/1351 | TF Fabrication facilities | 149
| wbs 14 | 1403 | Modular Coil Type C detail design | 409
| wbs 14 | 1414/1409 | Coil test facility fabrication and TRC testing | 150
| wbs 14 | 1411 | MCWF 1st production casting | 137 | (part of prototype contract)
| wbs 14 | 1411 | MCWF contract oversight | 110
| wbs 17 | 1701 | Cryostat & base support structure prel dsn | 178
| wbs 74 | 7401 | Test cell electrical power supply | 178
| wbs 4 | 4x01 | Electrical pwr sys DC sys & coil protection | 68
| Other |  |  | 95
1593
2357.2

## EC36 vs EC38 job comparision
ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 | ecp38 |  | ecp36 | ecp36 | ecp38 - 36
JJJJ | ACT CODE | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL
| 1101 | 0.1 | [6 empty] | 0.1 | 1101 | 1101 | 0.06 | 0.04
| 1201 | 424.4 | [6 empty] | 424.4 | 1201 | 1201 | 424.42 | -0.02 | 204.34 | vv dsn | 6
| 1202 | 793 | 998.2 | [5 empty] | 1791.2 | 1202 | 1202 | 1791.18 | 0.02
| 1203 |  | 624.8 | 315.1 | 155.3 |  |  |  | 1095.2 | 1203 | 1203 | 943.53 | 151.67
| 1204 |  |  |  | 187.4 | 182.6 | 89.4 |  | 459.4 | 1204 | 1204 | 557.24 | -97.84 | vv hw |  | 8
| 1206 |  | 3.4 | 14.2 |  |  |  |  | 17.6 | 1206 | 1206 | 17.64 | -0.04
| 1250 |  | 36.9 | 3041.9 | 2627.7 | 12.2 |  |  | 5718.7 | 1250 | 1250 | 5665.99 | 52.71
| 1301 | 91.7 | 333.9 | 397.9 |  |  |  |  | 823.5 | 1301 | 1301 | 837.4 | -13.9
| 1302 |  |  | 20.5 | 12.5 | 219.1 |  |  | 252.1 | 1302 | 1302 | 253.18 | -1.08
| 1350 |  |  | 256 | 377.9 |  |  |  | 633.9 | 1350 | 1350 | 399.59 | 234.31
| 1351 |  |  | 165.9 | 631.3 | 53.3 | 5.9 |  | 856.4 | 1351 | 1351 | 1318.24 | -461.84
| 1352 |  |  |  | 1.3 | 10.1 | 884.5 |  | 895.9 | 1352 | 1352 | 1361.87 | -465.97 | pf1a |  | 23
| 1353 |  |  |  |  | 82.4 | 183.4 |  | 265.8 | 1353 | 1353 | 270.3 | -4.5
| 1354 |  |  |  |  | 103.4 |  |  | 103.4 | 1354 | 1354 | 257.67 | -154.27 | trim coils |  | 24
| 1355 |  |  |  |  | 70.7 | 20.5 |  | 91.2 | 1355 | 1355 | 91.87 | -0.67
| 1361 |  |  |  | 254.9 | 378 | 26.9 |  | 659.8 | 1361 |  |  | 659.8 | 432.27 | tf | 10
| 1401 | 303 | [6 empty] | 303 | 1401 | 1401 | 303.04 | -0.04
| 1402 | 239.1 | [6 empty] | 239.1 | 1402 | 1402 | 239.14 | -0.04
| 1403 |  | 1798.7 | 863.1 | 84.4 |  |  |  | 2746.2 | 1403 | 1403 | 3148.64 | -402.44 | 520.36 | mc dsn | 5
| 1404 | 586 | 1625.8 | 321.6 |  |  |  |  | 2533.4 | 1404 | 1404 | 2533.52 | -0.12
| 1405 | 168.1 | [6 empty] | 168.1 | 1405 | 1405 | 168.07 | 0.03
| 1406 | 831.1 | 1266.5 | 116 |  |  |  |  | 2213.6 | 1406 | 1406 | 2213.59 | 0.01
| 1407 | 267.6 | 2236.3 | 19.2 |  |  |  |  | 2523.1 | 1407 | 1407 | 2522.99 | 0.11
| 1408 | 29.8 | 2.5 | 506.9 | 1065.6 | 166.8 | 6.8 |  | 1778.4 | 1408 | 1408 | 1852.61 | -74.21
| 1409 |  | 363.8 | 490.1 |  |  |  |  | 853.9 | 1409 | 1409 | 853.95 | -0.05
| 1410 |  |  | 1080.2 |  |  |  |  | 1080.2 | 1410 | 1410 | 1080.21 | -0.01
| 1411 |  | 20.4 | 3748.7 | 4102.5 | 564 |  |  | 8435.6 | 1411 | 1411 | 8367.06 | 68.54 | mcwf title iii |  | 18
| 1412 |  |  | 540.4 |  |  |  |  | 540.4 | 1412 | 1412 | 540.44 | -0.04
| 1413 |  |  | 23.2 |  |  |  |  | 23.2 | 1413 | 1413 | 23.17 | 0.03
| 1414 |  |  | 46 | 129.8 | 31 |  |  | 206.8 | 1414 | 1414 | 169.94 | 36.86
| 1415 |  |  | 14.8 |  |  |  |  | 14.8 | 1415 | 1415 | 14.85 | -0.05
| 1416 |  |  | 65.1 | 684.4 |  |  |  | 749.5 | 1416 |  |  | 749.5
| 1421d |  |  | 65.8 | 107.5 |  |  |  | 173.3 |  |  |  | 173.3
| 1421h |  |  |  |  | 655.097 |  |  | 655.097 | 1421 |  |  | 655.097 |  | interface hw | 15
| 1451 |  |  | 56.9 | 2393.7 | 2536.8 | 80.3 |  | 5067.7 | 1451 | 1451 | 5082.4 | -14.7 |  | winding | 7
| 1501 |  | 34.6 | 44.3 | 130.6 |  |  |  | 209.5 | 1501 | 1501 | 221.48 | -11.98
| 1550 |  |  |  |  | 1173 | 4.7 |  | 1177.7 | 1550 | 1550 | 1191.47 | -13.77
| 1601 |  |  |  |  | 660 | 475 |  | 1135 | 1601 | 1601 | 1139.98 | -4.98
| 1701 | 12.2 | 80.9 | 100.1 | 5.5 | 304.4 |  |  | 503.1 | 1701 | 1701 | 504.49 | -1.39
| 1751 |  |  |  |  | 5.6 | 527.8 | 7.1 | 540.5 | 1751 | 1751 | 541.48 | -0.98
| 1752 |  |  |  |  | 308.1 | 3.3 |  | 311.4 | 1752 | 1752 | 314.97 | -3.57
| 1801 | 60.8 | [6 empty] | 60.8 | 1801 | 1801 | 60.8 | 0
| 1802 |  | 164.6 | 146.2 | 350.2 | 411.6 | 355.5 |  | 1428.1 | 1802 | 1802 | 1444.46 | -16.36
| 1803 |  |  | 615.9 | 464.2 | 107.6 | 10.4 |  | 1198.1 | 1803 | 1803 | 1219.66 | -21.56 | -50 | I set of fixture | 16
| 1804 |  | 198 | 171.6 | 79.1 | 11 | 11.1 | 11.6 | 482.4 | 1804 | 1804 | 501.77 | -19.37 | -40 | 350c bakeout | 9
| 1810 |  |  |  | 282.4 | 1174.1 | 676.5 |  | 2133 | 1810 | 1810 | 2203.28 | -70.28
| 1901 | 254.2 | 640.7 | 580.8 | 515.7 | 361.6 | 251.5 | 153.7 | 2758.2 | 1901 | 1901 | 2738.1 | 20.1
| 2001 | 63.7 | [6 empty] | 63.7 | 2001 | 2001 | 63.67 | 0.03
| 2101 |  |  |  |  | 52.7 | 35.4 |  | 88.1 | 2101 | 2101 | 86.54 | 1.56
| 2201 |  |  |  |  | 125.5 | 229.7 |  | 355.2 | 2201 | 2201 | 348.88 | 6.32
| 2501 | 123 | 161.4 | [5 empty] | 284.4 | 2501 | 2501 | 284.37 | 0.03
| 3101 |  |  | 100.2 | 307 | 65.7 | 15.2 |  | 488.1 | 3101 | 3101 | 426.36 | 61.74 | saddleloops and term boxes |  | 17
| 3601 |  |  |  |  | 5.7 | 39.9 |  | 45.6 | 3601 | 3601 | 45.96 | -0.36
| 3801 | [5 empty] | 206.2 |  | 206.2 | 3801 | 3801 | 310.09 | -103.89 | ebeam |  | 22
| 3901 | 155.5 | 65 | 66.4 | 70.5 |  |  |  | 357.4 | 3901 | 3901 | 360.52 | -3.12
| 4101 |  | 85.8 | 18.7 | 0.1 | 288 | 29.3 |  | 421.9 | 4101 | 4101 | 430.17 | -8.27
| 4301 |  |  | 156.9 | 38.4 | 214.5 |  |  | 409.8 | 4301 | 4301 | 453.94 | -44.14
| 4401 |  | 1.1 | 4.4 |  | 842.5 | 431.3 | 17.8 | 1297.1 | 4401 | 4401 | 1308.88 | -11.78
| 4501 | 112.3 | 29.9 | 47.5 | 129.2 | 350.4 | 437.7 |  | 1107 | 4501 | 4501 | 1106.78 | 0.22
| 4601 | 1.3 | [6 empty] | 1.3 | 4601 | 4601 | 1.3 | 0
| 5101 | [5 empty] | 280.4 |  | 280.4 | 5101 | 5101 | 282.69 | -2.29
| 5201 |  |  |  |  | 9.4 | 429.1 | 91.6 | 530.1 | 5201 | 5201 | 610.92 | -80.82 | -100 | plasama control | 20
| 5301 |  |  |  |  | 11.1 | 299.1 | 18.9 | 329.1 | 5301 | 5301 | 351.01 | -21.91
| 5401 | [5 empty] | 195.8 |  | 195.8 | 5401 | 5401 | 220.96 | -25.16
| 5501 | [5 empty] | 179.3 |  | 179.3 | 5501 | 5501 | 161.65 | 17.65
| 5601 | [5 empty] | 325.5 |  | 325.5 | 5601 | 5601 | 381.94 | -56.44
| 5801 | 11.9 | 16 | 12.5 |  |  |  |  | 40.4 | 5801 | 5801 | 40.36 | 0.04
| 6101 | [5 empty] | 92.3 |  | 92.3 | 6101 | 6101 | 94.51 | -2.21
| 6163 |  | 15 | [5 empty] | 15 | 6163 | 6163 | 15 | 0
| 6201 |  |  |  |  | 41.8 | 413.2 |  | 455 | 6201 | 6201 | 463.26 | -8.26
| 6301 | [5 empty] | 106.9 |  | 106.9 | 6301 | 6301 | 109.3 | -2.4
| 6501 | 9.4 | [6 empty] | 9.4 | 6501 | 6501 | 9.38 | 0.02
| 7101 | 32.2 | [6 empty] | 32.2 | 7101 | 7101 | 32.15 | 0.05
| 7201 |  |  |  |  | 9.1 |  |  | 9.1 | 7201 | 7201 | 8.02 | 1.08
| 7301 |  |  | 120.7 |  | 38.3 |  |  | 159 | 7301 | 7301 | 164.42 | -5.42
| 7401 | 164 | 238.2 | 213.6 | 17.6 | 188.5 | 496.1 | 257 | 1575 | 7401 | 7401 | 1564.76 | 10.24
| 7501 | [5 empty] | 831.3 | 232.1 | 1063.4 | 7501 | 7501 | 1054.34 | 9.06
| 7502 |  |  |  |  | 74.6 |  |  | 74.6 | 7502 | 7502 | 57.17 | 17.43
| 7503 | [5 empty] | 833.1 | 451.4 | 1284.5 | 7503 | 7503 | 1254.04 | 30.46
| 7601 | [5 empty] | 176.4 | 61.4 | 237.8 | 7601 | 7601 | 238.25 | -0.45
| 8101 | 387.3 | 873.1 | 696.1 | 634.6 | 662.1 | 554.5 | 132.3 | 3940 | 8101 | 8101 | 4110.21 | -170.21 | -53.91 | project mgmt
| 8102 | 58.6 | 88 | 95.4 | 173.6 | 50.5 | 36.7 |  | 502.8 | 8102 | 8102 | 386.5 | 116.3
| 8202 | 295.5 | 669.6 | 669.3 | 625.6 | 239.6 | 246 | 62.8 | 2808.4 | 8202 | 8202 | 2834.97 | -26.57 | 84.01 |  | 19
| 8203 | 178.8 | 372.6 | 171 | 140.2 | 132.5 | 0.5 |  | 995.6 | 8203 | 8203 | 1116.34 | -120.74 | wbs 82
| 8204 | 44.6 | 188.8 | 256.6 | 225.4 |  |  |  | 715.4 | 8204 | 8204 | 600.93 | 114.47
| 8205 |  |  | 109.5 | 189.3 | 73.8 | 76.1 |  | 448.7 | 8205 | 8205 | 331.85 | 116.85
| 8401 | 210.3 | 113.8 | [5 empty] | 324.1 | 8401 | 8401 | 324.5 | -0.4
| 8402 | 41 | 104.9 | [5 empty] | 145.9 | 8402 | 8402 | 145.86 | 0.04
| 8501 | [5 empty] | 365.1 | 834.2 | 1199.3 | 8501 | 8501 | 1189.18 | 10.12
| 8998 | 112 | 260.7 | 350.8 | 329.8 | 331.5 | 167.7 |  | 1552.5 | 8998 | 8998 | 1576.89 | -24.39
|  | 6062.5 | 13713.9 | 16918 | 17525.2 | 13390.297 | 11143.3 | 2331.9 | 81085.097 |  | CCCP | 11984 |  | 945.777
[11 empty] | DCMA | 75 |  | -205.24 | other
| cont |  |  |  | 1295.7 | 2518.3 | 4756.7 | 1051 | 9621.7 |  |  |  | 740.537 |  | o
| cv |  |  | 1593
|  | 6062.5 | 13713.9 | 18511 | 18820.9 | 15908.597 | 15900 | 3382.9 | 92299.797
| ba |  |  |  | 18830 | 15900 | 15900 | 3383
| cum plan | 6062.5 | 19776.4 | 38287.4 | 57108.3 | 73016.897 | 88916.897 | 92299.797 | 74 | 92373.797
| ba cum |  |  | 41243 | 57143 | 73043 | 88943 | 92326 | 75 | 92401
|  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL
[5 empty] | 42 | 44 | 38 | 11 | 135
[5 empty] | 1253.7 | 2474.3 | 4718.7 | 1040
[5 empty] | 57108.3 | 73016.897 | 88916.897 | 92299.797
[5 empty] | 9621.7 | 21.68%
|  |  |  | 38312.887 | 44390.697 |  |  |  | 82703.584
[8 empty] | dcma | 75
92400.284

## Contingency Analysis
| ECP-38 | BCWR | Contingency | %
12 - Vacuum Vessel Systems | 4304.7 | 863 | 286.1527 | 33.16% | 12 | 3245017.8509 | 525152.663 | 16.18%
VVSA Contract | 5134 | 2392 | 239.2 | 10%
13 - Conventional Coils | 4827.2 | 3316 | 1115.1434 | 33.63% | 13 | 3309741.3526 | 1115143.3807 | 33.69%
14 - Modular Coils | 23158.9 | 8086 | 2339.4085 | 28.93% | 14 | 12601589.3299 | 2799408.4942 | 22.21%
MCWF Contract | 8192 | 4499 | 449.9 | 10%
15 - Structures | 1386.2 | 1308 | 417.0475 | 31.88% | 15 | 1307049.946 | 417047.5191 | 31.91%
16 - Coil Services | 1135 | 1135 | 281.7146 | 24.82% | 16 | 1135012.25 | 281714.5902 | 24.82%
17 - Cryostat and Base Support Struct | 1533.1 | 1162 | 338.9492 | 29.17% | 17 | 1155896.5262 | 338949.1774 | 29.32%
18 - Field Period Assembly | 5280.3 | 3945 | 1411.7428 | 35.79% | 18 | 3945762.16 | 1411742.832 | 35.78%
19 - Stellarator Core Mgt & Integr | 2767.2 | 1283 | 128.2096 | 9.993% | 19 | 1282096.445 | 128209.6445 | 10%
1 Stellarator Core Systems | 57718.6 | 27989 | 7007.4683 | 25.04% | 1 | 27982165.8607 | 7017368.3012 | 25.08%
2 Heating, Fueling & Vac Sys | 791.4 | 443.2497 | 62.055 | 14% | 21 | 88092.99 | 12333.0186
3 Diagnostics | 1149.3 | 744 | 207.7076 | 27.92%
4 Electrical Power Sys | 3305.1 | 2779 | 548.8057 | 19.75% | 22 | 355156.69 | 49721.9366
5 Central I&C Sys | 1873.6 | 1840 | 187.4838 | 10.19% | 2 | 443249.68 | 62054.9552 | 14%
6 Facility Sys | 678.6 | 654 | 130.8417 | 20.01% | 25 | 0 | 0
7 Test Cell Prep & MachAssy | 4563.1 | 3667 | 793.1466 | 21.63%
8 Project Oversight & Support | 12634.3 | 6285 | 674.6459 | 10.73% | 31 | 357766.5088 | 107329.9527
subtotal | 82714 | 44401.2497 | 9612.1546 | 21.65%
Contingency | 9612 |  |  |  | 36 | 45581.15 | 9116.23
TEC = | 92326
DCMA | 75 |  |  |  | 38 | 206196.8 | 70106.912
92401
[5 empty] | 39 | 70515.03 | 21154.509
[5 empty] | 3 | 680059.4888 | 207707.6037 | 30.54%
[5 empty] | 41 | 314949.46 | 56690.9028
[5 empty] | 43 | 298006.764 | 53641.2175
[5 empty] | 44 | 1289552.6376 | 252769.5932
[5 empty] | 45 | 916464.64 | 185703.9856
[5 empty] | 46 | 0 | 0
[5 empty] | 4 | 2818973.5016 | 548805.6991 | 19.47%
[5 empty] | 51 | 280385.9 | 14019.295
[5 empty] | 52 | 530112.41 | 53011.241
[5 empty] | 53 | 329072.83 | 52651.6528
[5 empty] | 54 | 195823.11 | 27415.2354
[5 empty] | 55 | 179331.4 | 14346.512
[5 empty] | 56 | 325498.85 | 26039.908
[5 empty] | 57 | 0 | 0
[5 empty] | 58 | 0 | 0
VVSA Contract | 5134 | 2392 | 239.2 | 10% | 5 | 1840224.5 | 187483.8442 | 10.19%
|  |  |  | #DIV/0! | 61 | 92271.78 | 18454.356
#DIV/0!
|  |  |  | #DIV/0! | 62 | 455033.04 | 91006.608
#DIV/0!
|  |  |  | #DIV/0! | 63 | 106903.92 | 21380.784
#DIV/0!
|  |  |  | #DIV/0! | 64 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! | 65 | 0 | 0
MCWF Contract | 8192 | 4499 | 449.9 | 10% |  | 654208.74 | 130841.748 | 20%
|  |  |  | #DIV/0! | 71 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! | 72 | 9097.92 | 909.792
#DIV/0!
|  |  |  | #DIV/0! | 73 | 37599.901 | 3643.5385
#DIV/0!
|  |  |  | #DIV/0! | 74 | 956980.383 | 145873.4182
#DIV/0!
|  |  |  | #DIV/0! | 75 | 2422508.16 | 585652.9824
#DIV/0!
|  |  |  | #DIV/0! | 76 | 237778.59 | 57066.8616
WBS 12-18 | 41625.4 | 19815 | 6190.1587 | 31.24% | 7 | 3663964.954 | 793146.5927 | 21.65%
|  |  |  | #DIV/0! | 81 | 2244301.07 | 112320.2535
#DIV/0!
|  |  |  | #DIV/0! | 82 | 2011860.24 | 168437.388
#DIV/0!
|  |  |  | #DIV/0! | 84 | 0 | 0
#DIV/0!
|  |  |  | #DIV/0! | 85 | 1199387.27 | 310999.399
#DIV/0!
|  |  |  | #DIV/0! | AA | 828888.41 | 82888.841
WBS 2-7 & 85 (BOP) | 13560.1 | 11326.2497 | 2241.0404 | 19.79% | 8 | 6284436.99 | 674645.8815 | 10.74%
WBS 19,81 & 82 | 14202.5 | 6369 | 491.8555 | 7.723% | Total Sum of Contingency $ | 44367283.7151 | 9622054.6255 | 21.69%
| 82714 | 44401.2497 | 9612.1546 | 21.65%

## Budget Summary
| ECP-36 | Change |  | ECP-38
12 - Vacuum Vessel Systems | 9400 | 38.7 |  | 9438.7
13 - Conventional Coils | 4790 | 37.2 |  | 4827.2
14 - Modular Coils | 29114 | 2236.9 |  | 31350.9
15 - Structures | 1413 | -26.8 |  | 1386.2
16 - Coil Services | 1140 | -5 |  | 1135
17 - Cryostat and Base Support Struct | 1361 | 172.1 |  | 1533.1
18 - Field Period Assembly | 5430 | -149.7 |  | 5280.3
19 - Stellarator Core Mgt & Integr | 2738 | 29.2 |  | 2767.2
1 Stellarator Core Systems | 55386 | 2332.6 |  | 57718.6
2 Heating, Fueling & Vac Sys | 783 | 8.4 |  | 791.4
3 Diagnostics | 1143 | 6.3 |  | 1149.3
4 Electrical Power Sys | 3301 | 4.1 |  | 3305.1
5 Central I&C Sys | 2050 | -176.4 |  | 1873.6
6 Facility Sys | 691 | -12.4 |  | 678.6
7 Test Cell Prep & MachAssy | 4373 | 190.1 |  | 4563.1
8 Project Oversight & Support | 12630 | 4.3 |  | 12634.3
subtotal | 80357 | 2357 |  | 82714
Contingency | 11969 | -2357 |  | 9612 | 21.65%
TEC = | 92326 |  |  | 92326
DCMA | 75 |  |  | 75
| 92401 |  |  | 92401
PARS thru SEP 30th against ECP-29
|  | BCWP | 36720
|  | ACWP | 38313
|  | SPI | 0.95842 |  |  | 92401.2
|  | CV | 1593
|  | BCWR |  | 44401.2
|  | Contingency balance |  | 9612 | 21.65%

## Mpwr job
| JJJJ | ACT CODE | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09 | OCT FY10 | NOV FY10 | DEC FY10
| 6.3 | 1408 | 0.3 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2
| 273.2 | 1451 | 8.7 | 11.4 | 9.5 | 11.9 | 14.7 | 9.9 | 13.2 | 15.2 | 14.4 | 16 | 13.5 | 13.3 | 11.2 | 12.4 | 7.1 | 13.2 | 8.5 | 9.4 | 9.5 | 7.9 | 8.1 | 9.3 | 9 | 6.6 | 5.5 | 3.1 | 0.7
53.3 | 52.9992 | risk |  |  |  |  | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083 | 2.2083
| 0.5 | 1204 | 0.5 | 0
| 0.5 | 1350 | 0.5 | 0
| 34.8 | 1351 | 0.7 | 1.4 | 2.6 | 2.7 | 2.5 | 0.4 | 1.5 |  | 0.5 |  |  |  | 1.7 | 3.6 | 1.8 | 3.8 | 2.3 | 4.3 | 1.9 | 2.8 | 0.3
| 36 | risk | [12 empty] | 2.4 | 2.2 | 1.7 | 2.4 | 2.2 | 2.4 | 2.3 | 2.4 | 2.3 | 2.3 | 2.5 | 2.1 | 2.5 | 2.2 | 1.6 | 2.5
| 1.4 | 1352 | [28 empty] | 0.1 | 0.2 | 0.3 | 0.2 | 0.2 | 0.3 | 0.1
| 5 | 1355 | [12 empty] | 0.6 | 0.5 | 0.4 | 0.6 | 0.5 | 0.6 | 0.2 | [15 empty] | 1 | 0.6
| 3.6 | 1414 |  | 1.2 |  |  |  | 1.2 |  |  |  | 0.2 | 1
| 2.5 | 1601 | [24 empty] | 0.7 | 0.8 | 0.6 | 0.4
| 1.6 | 1803 | [12 empty] | 0.5 | 0.5 | 0.4 | 0.2
| 2.7 | 1804 | 0.6 | 0.6 | 0.5 | 0.6 | 0.4
| 165.6 | 1810 | [6 empty] | 2.9 | 3.9 | 3.6 | 4.1 | 1.6 |  | 3.1 | 3.7 | 3 | 8.4 | 9.3 | 7.2 | 11.9 | 13.1 | 9.7 | 2.7 | 9.8 | 4.5 | 8.7 | 9.1 | 7.6 | 9.7 | 8.9 | 4.4 | 6.7 | 6.2 | 1.8
| 0.6 | 2101 | [24 empty] | 0.2 | 0.2 | 0.1 | 0.1
| 2.5 | 2201 | [24 empty] | 0 | 0.6 | 0.5 | 0.7 | 0.7 | 0
| 2.7 | 3101 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.6 | 0.5 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
| 2 | 6101 | [28 empty] | 1 | 1
| 8.5 | 6201 | [27 empty] | 0.3 | 1 | 2.1 | 2.5 | 2.2 | 0.4
| 3.1 | 6301 | [27 empty] | 1.7 | 1.4
| 3.4 | 7301 | 0.8 | 0.7 | 0.1 | [9 empty] | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.1
| 52.9 | 7501 | [24 empty] | 3.6 | 3.2 | 2.4 | 3.6 | 3.3 | 3.3 | 3.5 | 3.3 | 3.3 | 3.5 | 3.3 | 3.3 | 1.4 | 2 | 2.7 | 2.1 | 3.5 | 1.6
| 63.6 | 7503 | [24 empty] | 4.9 | 4.3 | 3.2 | 1.5 |  | 3.2 | 0.2 |  | 0.6 | 5.1 | 6.7 | 10.2 | 10.7 | 4.9 | 4.9 | 3.2
| 1.5 | 7601 | [24 empty] | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| 2.9 | 8501 | [37 empty] | 0.2 | 0.9 | 0.9 | 0.8 | 0.1
| 440.5411 |  | 12.1 | 15.9 | 12.9 | 15.5 | 20.0083 | 14.0083 | 20.0083 | 21.6083 | 21.5083 | 23.3083 | 19.1083 | 15.9083 | 22.3083 | 25.6083 | 17.1083 | 31.4083 | 25.5083 | 26.7083 | 28.4083 | 28.7083 | 22.9083
jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar
|  | Modular Coil | 9 | 11.6 | 9.7 | 12.2 | 17.1083 | 12.4083 | 15.6083 | 17.7083 | 16.9083 | 18.4083 | 16.0083 | 15.8083 | 13.7083 | 14.8083 | 9.5083 | 15.7083 | 10.9083 | 11.9083 | 12.0083 | 10.4083 | 10.6083 | 11.8083 | 11.5083 | 9.0083 | 7.7083 | 5.3083 | 2.9083 | 2.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TF Coil | 1.2 | 1.4 | 2.6 | 2.7 | 2.5 | 0.4 | 1.5 | 0 | 0.5 | 0 | 0 | 0 | 4.1 | 5.8 | 3.5 | 6.2 | 4.5 | 6.7 | 4.2 | 5.2 | 2.6 | 2.3 | 2.5 | 2.1 | 2.5 | 2.2 | 1.6 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Field Period Assy | 0.6 | 0.6 | 0.5 | 0.6 | 0.4 | 0 | 2.9 | 3.9 | 3.6 | 4.1 | 1.6 | 0 | 3.6 | 4.2 | 3.4 | 8.6 | 9.3 | 7.2 | 11.9 | 13.1 | 9.7 | 2.7 | 9.8 | 4.5 | 8.7 | 9.1 | 7.6 | 9.7 | 8.9 | 4.4 | 6.7 | 6.2 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Machine Assy | 0.8 | 0.7 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0 | 8.6 | 7.6 | 5.6 | 5.2 | 3.4 | 6.6 | 3.8 | 3.4 | 4 | 8.7 | 10.1 | 13.6 | 12.2 | 7 | 7.7 | 5.4 | 3.5 | 1.6
|  | Other | 0.5 | 1.6 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0.5 | 0.8 | 1.5 | 0.1 | 0.6 | 0.5 | 0.5 | 0.6 | 0.5 | 0.6 | 0.2 | 0 | 0 | 0 | 0.1 | 0.1 | 1 | 1.7 | 1.3 | 3.2 | 4.2 | 3.3 | 2.8 | 2.4 | 0.6 | 0.3 | 1.1 | 0.6 | 0 | 0.2 | 0.9 | 0.9 | 0.8 | 0.1
| 730.3992 |  | 12.1 | 15.9 | 12.9 | 15.5 | 20.0083 | 14.0083 | 20.0083 | 21.6083 | 21.5083 | 23.3083 | 19.1083 | 15.9083 | 22.3083 | 25.6083 | 17.1083 | 31.4083 | 25.5083 | 26.7083 | 28.4083 | 28.7083 | 22.9083 | 16.8083 | 23.9083 | 15.7083 | 28.5083 | 25.9083 | 19.0083 | 22.8083 | 16.5 | 14.3 | 13.3 | 12 | 6.4 | 9 | 11.2 | 14.2 | 12.2 | 7.2 | 8.6 | 6.3 | 4.3 | 1.7
|  |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| 9 | Mod Coil | 9 | 9.8667 | 10.1 | 10.625 | 12.6521 | 12.8542 | 14.3312 | 15.7083 | 15.6583 | 17.1583 | 17.2583 | 16.7833 | 15.9833 | 15.0833 | 13.4583 | 13.4333 | 12.7333 | 12.0083 | 12.6333 | 11.3083 | 11.2333 | 11.2083 | 11.0833 | 10.7333 | 10.0083 | 8.3833 | 6.2333 | 4.5333 | 2.6062 | 1.2792 | 0.55207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2 | TF Coil | 1.2 | 1.2667 | 1.7333 | 1.975 | 2.3 | 2.05 | 1.775 | 1.1 | 0.6 | 0.5 | 0.125 | 0.125 | 1.025 | 2.475 | 3.35 | 4.9 | 5 | 5.225 | 5.4 | 5.15 | 4.675 | 3.575 | 3.15 | 2.375 | 2.35 | 2.325 | 2.1 | 2.2 | 1.575 | 1.025 | 0.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0.6 | FP Assy | 0.6 | 0.6 | 0.56667 | 0.575 | 0.525 | 0.375 | 0.975 | 1.8 | 2.6 | 3.625 | 3.3 | 2.325 | 2.325 | 2.35 | 2.8 | 4.95 | 6.375 | 7.125 | 9.25 | 10.375 | 10.475 | 9.35 | 8.825 | 6.675 | 6.425 | 8.025 | 7.475 | 8.775 | 8.825 | 7.65 | 7.425 | 6.55 | 4.775 | 3.675 | 2 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0
| 0.8 | Mach Assy | 0.8 | 0.76667 | 0.53333 | 0.4 | 0.2 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075 | 0.15 | 0.2 | 0.275 | 0.275 | 0.275 | 0.25 | 0.175 | 0.1 | 0.025 | 0 | 0 | 2.15 | 4.05 | 5.45 | 6.75 | 5.45 | 5.2 | 4.75 | 4.3 | 4.45 | 4.975 | 6.55 | 9.1 | 11.15 | 10.725 | 10.125 | 8.075 | 5.9 | 3.5
| 0.5 | Other | 0.5 | 0.86667 | 0.7 | 0.525 | 0.4 | 0.3 | 0.3 | 0.3 | 0.425 | 0.325 | 0.7 | 0.725 | 0.75 | 0.675 | 0.425 | 0.55 | 0.525 | 0.55 | 0.475 | 0.325 | 0.2 | 0.05 | 0.025 | 0.05 | 0.3 | 0.725 | 1.025 | 1.8 | 2.6 | 3 | 3.375 | 3.175 | 2.275 | 1.525 | 1.1 | 0.65 | 0.5 | 0.475 | 0.425 | 0.5 | 0.7 | 0.6

## Mpwr smry
RES | RESOURCE | OCT FY06 | NOV FY06 | DEC FY06 | JAN FY06 | FEB FY06 | MAR FY06 | APR FY06 | MAY FY06 | JUN FY06 | JUL FY06 | AUG FY06 | SEP FY06 | OCT FY07 | NOV FY07 | DEC FY07 | JAN FY07 | FEB FY07 | MAR FY07 | APR FY07 | MAY FY07 | JUN FY07 | JUL FY07 | AUG FY07 | SEP FY07 | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09
ecp38 | EA//EM | 6.1 | 5.5 | 4.1 | 5.6 | 6.5 | 7.2 | 5.8 | 6.6 | 6.1 | 3.8 | 4.4 | 3.9 | 5.1 | 4.7 | 3.4 | 5.3 | 4.8 | 5 | 3.7 | 3 | 2.9 | 2.9 | 3.1 | 2.8 | 3.1 | 1.8 | 1.3 | 1.6 | 1.7 | 1.3 | 1.4 | 1.3 | 1.5 | 1.8 | 1.3 | 1.4 | 0.3 | 0.2 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
incl cont risk | EA//SM | 3.1 | 1.3 | 0.9 | 3 | 1 | 1.1 | 1 | 1.1 | 1.1 | 1 | 1.1 | 1 | 4.4 | 4.2 | 3.2 | 3.9 | 2.2 | 1.8 | 1.9 | 1.8 | 1.8 | 2.2 | 2.3 | 1.1 | 1.4 | 1.5 | 0.9 | 0.9 | 0.7 | 0.6 | 0.7 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1
| EC//EM | [23 empty] | 0.9 | 2.1 | 2.1 | 1.8 | 2.9 | 2.8 | 3.2 | 3.8 | 3.8 | 3.8 | 3.1 | 3 | 2.5 | 1.6 | 0.8 | 0.9 | 0.9 | 0.8
| EC//SM | [27 empty] | 0.4 | 0.6 | 1.2 | 1.9 | 1.8 | 1.8 | 1.3 | 1.2 | 1 | 0.5 | 0.3
| EE//AM | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| EE//EM | 1.7 | 0.7 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.3 | 1.9 | 1.8 | 1.8 | 2.5 | 1.7 | 1.2 | 1.2 | 1 | 1.2 | 1.4 | 1.6 | 1.5 | 2.2 | 2.2 | 1.5 | 1.9 | 1.5 | 1 | 0.4 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.3 | 0.9 | 0.9 | 0.8
| EE//SM | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0 | 0 |  |  | 0.1 | 0.5 | 0.6 | 0.4 | 0.8 | 0.6 | 0.7 | 0.9 | 1.7 | 2 | 2.7 | 2.8 | 1.8 | 2.4 | 2 | 1.5 | 2.5 | 2.2 | 2 | 2.5 | 2.7 | 2.5 | 1.7 | 1.6 | 0.9 | 0 | 0
| EE//TB | 0.6 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.4 | 0.1 | 0.1 |  |  | 0.5 | 0.8 | 0.7 | 0.7 | 1.4 | 0.8 | 0.9 | 0.3 | 0.7 | 1.1 | 1.6 | 2.4 | 2 | 3.2 | 3.4 | 1.8 | 1.9 | 1.6 | 1 | 0.7 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.6 | 1.8 | 1.8 | 1.6
| EM//EM | 2.8 | 2.7 | 2.4 | 2.7 | 1.5 | 1.7 | 1.5 | 1.3 | 1.4 | 1.3 | 1.5 | 1.5 | 2.8 | 2.5 | 1.6 | 2.3 | 2 | 2.1 | 2 | 2.3 | 2 | 2.5 | 2.7 | 2.6 | 3.6 | 3 | 2.1 | 3.6 | 3.5 | 3.8 | 3.4 | 3.1 | 2.7 | 1.9 | 1.9 | 1.8 | 1.9 | 2.4 | 4.2 | 3.5 | 2.8 | 0.9
| EM//SM | 4 | 3 | 1.6 | 1.7 | 1 | 0.9 | 0.7 | 1.3 | 1.3 | 0.7 | 0.8 | 0.7 | 1.3 | 1 | 0.8 | 1.4 | 1.4 | 1.4 | 1.7 | 2.2 | 1.9 | 2.3 | 1.8 | 1.8 | 5.6 | 5 | 3.7 | 5.1 | 5 | 3.6 | 3.8 | 3.3 | 3.7 | 4.5 | 4.5 | 4.4 | 5.3 | 4.3 | 6 | 3.3 | 2.6 | 0.9
| EM//TB | 9 | 13.9 | 12.3 | 18.2 | 16.9 | 26.7 | 23.9 | 24.6 | 24.5 | 18.9 | 22.5 | 19 | 30.9 | 28.8 | 20.5 | 34.3 | 26.4 | 25.3 | 29.4 | 29.6 | 31.2 | 34.4 | 35.5 | 17.9 | 25.9 | 22.2 | 16.4 | 17.1 | 14.1 | 12 | 12.6 | 9.1 | 6.9 | 10.4 | 12.7 | 13.1 | 12.8 | 6.9 | 8.5 | 5.8 | 4.3 | 1.1
| ORNLEM | 10.7 | 8.5 | 6.1 | 6.8 | 5.8 | 4.7 | 4.1 | 3.1 | 2.5 | 2.2 | 3 | 2.4 | 3.4 | 3 | 2.3 | 3.6 | 3.5 | 3.6 | 2.4 | 2.3 | 2.2 | 2.2 | 2.5 | 1.9 | 1.7 | 1 | 0.7 | 1 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.7 | 0.6 | 0.5 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0
 | time axis 2005-10-01 to 2009-09-01
| PPPL Engr | 10.6 | 8.9 | 6.8 | 8.5 | 8.2 | 9.1 | 7.5 | 8.1 | 7.7 | 5.2 | 6.1 | 5.7 | 9.8 | 9 | 6.8 | 10.1 | 8.5 | 8.3 | 6.9 | 6.3 | 6.1 | 6.8 | 7.4 | 7.8 | 11 | 9.1 | 6.7 | 10 | 9.5 | 9.3 | 9 | 8.4 | 8.2 | 7 | 6.3 | 5.8 | 3.9 | 3.7 | 6.3 | 5.5 | 4.6 | 1.1 | 0.2 | 0.2 | 0 | 0 | 0 | 0
| PPPL Tecnicians | 13.6 | 17 | 14 | 20 | 18 | 27.9 | 25.1 | 26 | 25.9 | 19.6 | 23.3 | 20.3 | 33.5 | 31.1 | 22.4 | 37.9 | 29.2 | 28.3 | 32.3 | 34.2 | 36.2 | 41 | 42.5 | 23.5 | 37.1 | 32.6 | 23.4 | 27 | 23.5 | 19.8 | 21.5 | 17.2 | 15 | 18 | 20.1 | 19.5 | 18.7 | 12.1 | 16.3 | 10.9 | 8.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| ORNL Engrs | 10.7 | 8.5 | 6.1 | 6.8 | 5.8 | 4.7 | 4.1 | 3.1 | 2.5 | 2.2 | 3 | 2.4 | 3.4 | 3 | 2.3 | 3.6 | 3.5 | 3.6 | 2.4 | 2.3 | 2.2 | 2.2 | 2.5 | 1.9 | 1.7 | 1 | 0.7 | 1 | 0.8 | 0.8 | 0.8 | 0.6 | 0.6 | 0.7 | 0.6 | 0.5 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0
|  | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul
| Techs ecp36 | 16 | 19.1 | 14.3 | 19.1 | 19.5 | 15.3 | 20.3 | 21.3 | 22.5 | 22.7 | 20.6 | 15.8 | 23.5 | 25.7 | 16.8 | 30.2 | 24.7 | 25.8 | 26.9 | 29.3 | 23.4 | 16.8 | 25.7 | 16.2 | 34.9 | 31.8 | 22.3 | 28.5 | 25.5 | 22.8 | 22.1 | 20.1 | 14.2 | 16.4 | 18.3 | 21.3 | 17.9 | 11.8 | 16.6 | 11.5 | 8.5 | 3.1 | 0 | 0 | 0 | 0

## Milestones
NCSX Milestone Status
|  |  | CD-2 | CD-2
|  |  | Baseline |  | Baseline | float | Forecast | Actual | master schedule | Milestone float
| Level I | CD-1 | 2003-05-01 | 0 | 2003-05-01 |  |  | 2003-05-01
M-0110 |  | CD-2 | 2004-02-01 | 0 | 2004-02-01 |  |  | 2004-02-01
M-0115 |  | CD-3 | 2004-09-30 | 0 | 2004-09-30 |  |  | 2004-10-30
M-0120 |  | CD-4 | 2008-05-30 | 14.2333 | 2009-07-31 | 1900-01-04 03:12 | 2009-02-27 |  | 2009-02-27 | 5.1333
0
1201-500 | Level II | Vacuum Vessel & Modular Coil Prel Dsn Rvw | 2003-10-07 | 0 | 2003-10-07 |  |  | 2003-10-07
1403-08 |  | Performance Baseline Review | 2003-11-18 | 0 | 2003-11-18 |  |  | 2003-11-18
1203-341 |  | Conduct VVSA FDR | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1403-51 |  | Mod Coil Winding Form Final Design Review | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1408-143.1 |  | Award MC Conductor Contract |  |  | 2004-12-19 |  |  | 2004-10-15
121-6-9 |  | Award VV Production Vendor | 2004-12-01 | -2 | 2004-10-15 |  |  | 2004-09-15
C-081 |  | Award MCWF Mfg Contract | 2004-11-01 | -1 | 2004-10-01 |  |  | 2004-09-15
C-121.1 |  | First MCWF Delivered | 2005-03-01 | 4 | 2005-07-15 | 1284.9333 |  | 2005-09-30
131-035 |  | Begin TF Coil fabrication activities | 2005-04-01 | 3 | 2005-09-30 | 1287.5 |  | 2005-06-30
P1-021.1 |  | Complete First Mod Coil Fabrication | 2005-08-31 | 6 | 2006-03-29 | 2006-04-15 | 2006-02-28 |  | 2006-03-29 | 0
121-038.1 |  | Vacuum Vessel Sectors Delivered | 2006-02-01 | 0 | 2006-05-15 | 1.8333 | 2006-03-21 |  | 2006-03-21 | 1.8333
C-501B1 |  | Last MCWF Delivered | 2006-08-01 | 4 | 2007-06-15 | 4.5 | 2007-01-31 |  | 2007-01-31 | 4.5
141-036 |  | PF Coils Awarded | 2006-06-01 | 7 | 2008-03-30 | 5.1667 | 2007-10-27 |  | 2007-10-27 | 5.1667
S3P1-101 |  | Begin Assembly of First Field Period | 2006-09-01 | 6 | 2007-07-01 | 5.6667 | 2007-01-12 |  | 2007-01-12 | 5.6667
1351-195x |  | All TF Coils Delivered | 2007-01-01 | 4 | 2008-08-15 | 9 | 2007-11-19 |  | 2007-11-19 | 9
S4P3-115 |  | Last Field Period Assembled | 2007-06-01 | 3 | 2008-11-15 | 5.2 | 2008-06-12 |  | 2008-06-12 | 5.2
7503-250 |  | Begin Vac Vsl Pumpdown | 2007-09-01 | 2 | 2009-02-11 | 5.1 | 2008-09-11 |  | 2008-09-11 | 5.1
7503-330 |  | Begin Cryostat Installation | 2007-11-01 | 2 | 2009-04-07 | 5.0333 | 2008-11-07 |  | 2008-11-07 | 5.0333
730.1250 |  | Operational Readiness | 2007-11-01 | 4 | 2009-06-01 | 5.1667 | 2008-12-28 |  | 2008-12-28 | 5.1667
920.004 |  | Begin Start-up Testing | 2008-03-31 | 0 | 2009-06-16 | 5.0333 | 2009-01-16 |  | 2009-01-16 | 5.0333
0
1404-109.J | Joule | FY04 JOULE #1-Authorize Prototype Fab | 2003-12-20 | 0.33333 | 2003-12-30 |  |  | 2003-10-20
1406-040 |  | FY04 JOULE #2-Begin winding on 3D surface | 2004-03-01 | 1 | 2004-03-31 |  |  | 2004-01-30
1404-110.J |  | FY04 JOULE #3-Prototype Casting Ready for Machining | 2004-06-01 | 0.96667 | 2004-06-30 |  |  | 2004-05-26
C-081.1 |  | FY04 JOULE #4 - CD-3 Readiness | 2004-09-01 | 0.96667 | 2004-09-30 |  |  | 2004-09-15
1408-143.1 |  | FY05 JOULE #1- VVSA, MCWF and MC Copper Conductor Awarded |  | 1278.3667 | 2004-12-30 | 2.5333 |  | 2004-10-15
1406-017.3 |  | FY05 JOULE #2- Cmplt Assy of twisted racetrack |  | 1281.4 | 2005-03-31 | 1281.4 |  | 2005-03-30
1403-20 |  | FY05 JOULE #3- Mod Coil Winding Type C FDR |  | 1284.4333 | 2005-06-30 | 1284.4333 |  | 2005-06-30
P1-011J |  | FY05 JOULE #4- Complete Winding First MC |  | 1287.5 | 2005-09-30 | 2005-10-31 | 2005-12-30 |  | 2005-12-15 | -2.5333
mcwf-311 |  | FY06 JOULE Receive all VVSA and 1/3 of MCWF's |  |  | 2006-09-30 |  | 2006-02-22 |  | 2006-02-22 | 7.3333
P2-041joul |  | FY07 JOULE Complete Winding of 1/2 of Modular Coils |  |  | 2007-09-30 |  | 2006-11-06 |  | 2006-11-06 | 10.9333
Formulas:
Actual = +[Baseline]
float = (+[Baseline]-[Forecast])/30
Forecast = SUM([master schedule])
Forecast = +[master schedule]

## EIO IMPACT
Modular Coil Winding Form Delivery Schedule
[6 empty] | EIO Forecast |  |  |  | Project Plan |  |  |  | Free Float |  |  | 3 winding lines 2 shifts |  |  |  |  | 2 shfits for field period |  |  |  |  | 2 shifts Machine Assembly
[17 empty] | for coil winding |  |  |  |  | assembly
|  | 2005 | [9 empty] | 2006 | [11 empty] | 2007
2005-01-01 | 2005-02-01 | 2005-03-01 | 2005-04-01 | 2005-05-01 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | Sep | Oct | Nov
Casting Number
C1
C2
C3
C4
C5
C6
A1
A2
A3
B1
A4
A5
A6
B2
B3
B4
B5
B6
|  | 2) | Winding plan basis;
a) first coil taking 50% longer.
b) 2 winding stations with 3 winding teams. 3rd team dedicated to 2nd shift for winding only. Chill plate ,bagging VPI pre done on 1st shift only.
c) 2nd shift utilized for first 10 coils only.
d) all shifts based 5 days/week 70% of winding ops utilize 10hr/days. Some overtime and all Saturday's held back as contingency.
E
E
E
E
E
E
E
E
E
E
E
E
E
E
E
E
E
E

## Summary Schedule
NCSX Critical Path Summary Schedule
FY02 |  |  |  |  | FY03 | [11 empty] | FY04 | [11 empty] | FY05 | [11 empty] | FY06 | [12 empty] | FY07 | [11 empty] | FY08 | [11 empty] | FY09
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| CDR |  |  |  | DOE Milestones
|  | CD-1 | [13 empty] | MC/VV PDR | [5 empty] | CD-2
FY04 D: EIR; FY05 O: CD-3 Start of Fab | [32 empty] | Pumpdown Vac Vsl
[12 empty] | Start of Preliminary Design | [10 empty] | Vac Vsl FDR
Modular Coil FDR
FY04 D: Joule #1 Authorize Protype Fab; FY05 J: Joule #1 Award VVSA,MWCF,Cond | [40 empty] | ORA
[22 empty] | Joule #2 Demonstarte Winding Process on 3-D Surface | [12 empty] | Joule #2 Cmplt Assy TRC
FY04 J: Joule #3 First Prototype Casting Produced for Machining; FY05 J: Joule #3 Mod Coil Winding Type C FDR | [43 empty] | CD-4 Completion of MIE Project
[28 empty] | Joule #4 CD-3 Prereq Complete | [12 empty] | Joule #4 Cmplt Winding First MC
VACUUM VESSEL
[10 empty] | Title I & II Design | [16 empty] | Vessel Award
Manuf Devel
Vessel Fab
MODULAR COILS
Title I & II MCWF
Twisted Racetrack Fabrication
[19 empty] | Title II Design for Winding | [10 empty] | Type C |  |  |  | Type C |  |  |  | Type B | Type A
Component Fabrication
MCWF Manufacturing Development
[16 empty] | Fabricate Prototype Type "C" | [12 empty] | Award Winding Form Contract
[37 empty] | C1 |  |  | C2
Fab Winding Forms
Station 2-Wind & VPI
Station 3-Wind & VPI
VPI,Clamps,& Test
FY04 O: FIELD PERIOD ASSEMBLY |  |  | Attach Cooling,Diag, Insulation
Pre-Assemble Mod Coils
MC Installation
Assemble 1st Period
Assemble 2nd Period
Assemble 3rd Period
FY04 A: MACHINE ASSEMBLY | [21 empty] | Install Supports and Lower PF Coils
Install,align, connect Field Period Assemblies
FY03 O: Legend: | [35 empty] | Pump Down
FY03 O: Completed Task | [34 empty] | Connect to Ancilliary Systems
FY03 O: Critical Paths | [34 empty] | Install Cryostat & PTP
FY03 O: Off critical path | [37 empty] | Startup Testing and E-Beam Mapping
[51 empty] | Ancilliary Systems Installation | [34 empty] | First Plasma
FY02 M: FY02; FY03 O: FY03; FY04 O: FY04; FY05 O: FY05; FY06 O: FY06 | [11 empty] | FY07 | [11 empty] | FY08
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A |  | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1
Total Float 5 mo.
C3 C4 C5 C6 A1 A2 A3 B1 A4 A5 A6 B2 B3 B4 B5 B6

## Funding
Total
| Original BA | 7.9 | 15.83 | 15.84 | 22.14 | 19.42 | 5.2 |  | 86.33
| New BA | 7.9 | 15.83 | 17.5 | 15.9 | 15.9 | 15.9 | 5.199 | 94.129
| PMB | 6.062 | 13.658 | 18.238 | 15.425 | 13.289 | 12.748 | 2.466 | 81.886
| Contingency |  |  | 0.8 | 3 | 2.6 | 3.1 | 2.742 | 12.242
| BA cum old | 7.9 | 23.73 | 39.57 | 61.71 | 81.13 | 86.33 | 86.33
| BA cum new | 7.9 | 23.73 | 41.23 | 57.13 | 73.03 | 88.93 | 94.129
| PMB cum | 6.062 | 19.72 | 37.958 | 53.383 | 66.672 | 79.42 | 81.886
%
24.8%
|  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total
| 22.01% |  | BA | 7.897 | 15.921 | 17.5 | 15.9 | 15.9 | 15.9 | 3.383 | 92.401
|  |  | PMB | 5.9419 | 14.2393 | 18.162 | 17.515 | 13.409 | 11.14 | 2.331 | 82.7382
| 5% |  | Contingency |  |  |  | 1.295 | 2.518 | 4.75 | 1.049 | 9.612
| 10% |  | BO (PMB + Cont) | 5.9419 | 14.2393 | 18.162 | 18.81 | 15.927 | 15.89 | 3.38 | 92.3502
33.49%
| 19.58% |  | Cum BA | 7.897 | 23.818 | 41.318 | 57.218 | 73.118 | 89.018 | 92.401
| 11.24% |  | Cum PMB | 5.9419 | 20.1812 | 38.3432 | 55.8582 | 69.2672 | 80.4072 | 82.7382
22.01%
|  |  | Cum BO | 5.9419 | 20.1812 | 38.3432 | 57.1532 | 73.0802 | 88.9702 | 92.3502
|  |  | pmb puts and takes |  |  | -0.415 | -1.047 | -0.712 | 0.151 | 0.121
|  |  | contingency puts and takes |  | 0 | 0.415 | 1.047 | 0.712 | -0.151 | -0.121
|  |  |  | wbs1 | -0.24 | -0.12 | -0.12
|  |  |  | wbs13 | -0.6 | -0.2 | -0.2 | -0.2
|  |  |  | wbs 141 | -0.64 |  | -0.32 | -0.32
|  |  |  | wbs142 | -0.095 | -0.095
|  |  |  | wbs142 | -0.097 |  | -0.097
|  |  |  | wbs18 | -0.3 |  | -0.15 | -0.15
|  |  |  | wbs82 | -0.32 |  | -0.16 | -0.16
|  |  |  | red | 0.48 |  |  | 0.118 | 0.151 | 0.121
0.09
FY04 FY05 FY06 FY07 FY08 FY09
$23.8
$73.1
$57.2
41.3
$92.4
$89.0

## wbs2 budgets by fy
| WBS2 |  |  | ACT CODE | DESCRIPTION | FY2003 | FY2004 | FY2005 | FY05 CV | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL | ACT CODE
| 0.1 |  | 0 | 11 | 11 - In-Vessel Components | 0.1 | [7 empty] | 0.1 | 11
| 6252 |  | 3254.7 | 12 | 12 - Vacuum Vessel Systems | 1217.4 | 1663.3 | 3371.3 | -68 | 2970.4 | 194.9 | 89.4 |  | 9438.7 | 12
| 1265.9 |  | 3316.3 | 13 | 13 - Conventional Coils | 91.7 | 333.9 | 840.3 | 245 | 1277.9 | 917.1 | 1121.3 |  | 4827.2 | 13
| 17722.9 |  | 12584.5 | 14 | 14 - Modular Coils | 2424.8 | 7314.1 | 7984 | 1043.5 | 8551.7 | 3945.6 | 87.2 |  | 31350.9 | 14
| 78.9 |  | 1308.3 | 15 | 15 - Structures |  | 34.6 | 44.3 | -1 | 130.6 | 1173 | 4.7 |  | 1386.2 | 15 | 3945.4
| 0 |  | 1135 | 16 | 16 - Coil Services |  |  |  | 0 |  | 660 | 475 |  | 1135 | 16
| 193.2 |  | 1161.9 | 17 | 17 - Cryostat and Base Support Structure | 12.2 | 80.9 | 100.1 | 178 | 5.5 | 618.1 | 531.2 | 7.1 | 1533.1 | 17
| 1356.9 |  | 3945.4 | 18 | 18 - Field Period Assembly | 60.8 | 362.5 | 933.6 | -22 | 1175.9 | 1704.4 | 1053.5 | 11.6 | 5280.3 | 18
28345.6 | 1475.7 |  | 1282.5 | 19 | 19 - Stellarator Core Management and Integration | 254.2 | 640.7 | 580.8 | 9 | 515.7 | 361.6 | 251.5 | 153.7 | 2767.2 | 19 | 57718.7
| 0 |  | 88.1 | 21 | 21 - Fueling Systems | [5 empty] | 52.7 | 35.4 |  | 88.1 | 21 | 791.4
| 63.7 | 443.3 | 355.2 | 22 | 22 - Torus Vacuum Pumping Systems | 63.7 |  |  |  |  | 125.5 | 229.7 |  | 418.9 | 22
| 284.4 |  | 0 | 25 | 25 - Neutral Beam Injection System | 123 | 161.4 | [6 empty] | 284.4 | 25
| 100.2 | 744.2 | 421.9 | 31 | 31 - Magnetic Diagnostics |  |  | 100.2 | 30 | 314.2 | 92.5 | 15.2 |  | 552.1 | 31 | 1149.3
| 0 |  | 45.6 | 36 | 36 - Edge and Divertor Diagnostics | [5 empty] | 5.7 | 39.9 |  | 45.6 | 36
| 0 |  | 206.2 | 38 | 38 - Electron Beam (EB) Mapping | [6 empty] | 206.2 |  | 206.2 | 38
| 286.9 |  | 70.5 | 39 | 39 - Diagnostics Integration | 155.5 | 65 | 66.4 | -12 | 70.5 |  |  |  | 345.4 | 39
| 104.5 | 2779.2 | 317.4 | 41 | 41 - AC Power |  | 85.8 | 18.7 | 2 | 0.1 | 288 | 29.3 |  | 423.9 | 41 | 3305.1
| 156.9 |  | 252.9 | 43 | 43 - DC Systems |  |  | 156.9 | 69 | 38.4 | 214.5 |  |  | 478.8 | 43
| 5.5 |  | 1291.6 | 44 | 44 - Control and protection Systems |  | 1.1 | 4.4 | 49 |  | 842.5 | 431.3 | 17.8 | 1346.1 | 44
| 189.7 |  | 917.3 | 45 | 45 - Power System Design and Integration | 112.3 | 29.9 | 47.5 | -52 | 129.2 | 350.4 | 437.7 |  | 1055 | 45
| 1.3 |  | 0 | 46 | 46 - FCPC Building Modifications | 1.3 | [7 empty] | 1.3 | 46
| 27.9 | 1840.2 | 280.4 | 51 | 51 - TCP/IP Infrastructure Systems | 11.9 | 16 |  |  |  |  | 280.4 |  | 308.3 | 51 | 1873.6
| 0 |  | 530.1 | 52 | 52 - Central Instrumentation & Control | [5 empty] | 9.4 | 429.1 | 91.6 | 530.1 | 52
| 0 |  | 329.1 | 53 | 53 - Data Acquisition & Facility Computing | [5 empty] | 11.1 | 299.1 | 18.9 | 329.1 | 53
| 0 |  | 195.8 | 54 | 54 - Facility Timing & Synchronization | [6 empty] | 195.8 |  | 195.8 | 54
| 0 |  | 179.3 | 55 | 55 - Real Time Plasma & Power | [6 empty] | 179.3 |  | 179.3 | 55
| 0 |  | 325.5 | 56 | 56 - Central Safety Interlock | [6 empty] | 325.5 |  | 325.5 | 56
| 12.5 |  | 0 | 58 | 58 - Central I&C management and Integration |  |  | 12.5 | -7 |  |  |  |  | 5.5 | 58
| 0 | 654.2 | 92.3 | 61 | 61 - Water Systems | [6 empty] | 92.3 |  | 92.3 | 61 | 678.6
| 0 |  | 455 | 62 | 62 - Cryogenic Systems | [5 empty] | 41.8 | 413.2 |  | 455 | 62
| 0 |  | 106.9 | 63 | 63 - Utility Systems | [6 empty] | 106.9 |  | 106.9 | 63
| 24.4 |  | 0 | 65 | 65 - Facility Systems Integration | 9.4 | 15 | [6 empty] | 24.4 | 65
768.7 | 32.2 | 3666.9 | 0 | 71 | 71 - Shield Wall Seismic Modifications | 32.2 | [7 empty] | 32.2 | 71 | 4563.1
| 0 |  | 9.1 | 72 | 72 - Control Room Refurbishment | [5 empty] | 9.1 |  |  | 9.1 | 72
| 120.7 |  | 38.3 | 73 | 73 - Platform Design & Fabrication |  |  | 120.7 | -50 |  | 38.3 |  |  | 109 | 73
| 615.8 |  | 959.2 | 74 | 74 - Machine Assembly Planning and Oversight | 164 | 238.2 | 213.6 | 177.5 | 17.6 | 188.5 | 496.1 | 257 | 1752.5 | 74
| 0 |  | 2422.5 | 75 | 75 - Test Cell and Basement Assembly Operations | [5 empty] | 74.6 | 1664.4 | 683.5 | 2422.5 | 75
| 0 |  | 237.8 | 76 | 76 - Tooling Design & Fabrication | [6 empty] | 176.4 | 61.4 | 237.8 | 76
| 2921.5 | 6284.6 | 3073.4 | 81 | 81 - Project Management and Control | 557.9 | 1221.8 | 1141.8 | 67 | 1138.1 | 1044.1 | 758.9 | 132.3 | 6061.9 | 81 | 12634.3
| 2956.2 |  | 2011.9 | 82 | 82 - Project Engineering | 518.9 | 1230.9 | 1206.4 | -65 | 1180.6 | 445.9 | 322.6 | 62.8 | 4903.1 | 82
| 470 |  | 0 | 84 | 84 - Project Physics | 251.3 | 218.7 | [6 empty] | 470 | 84
|  |  | 1199.3 | 85 | 85 - Integrated Systems Testing | [6 empty] | 365.1 | 834.2 | 1199.3 | 85
[6 empty] | 6062.6 | 13713.8 | 16943.5 | 1593 | 17516.4 | 13409.3 | 11143.6 | 2331.9 | 82714.1 | 82714.1 | 86659.5
[8 empty] | 36719.9 |  | 44401.2
|  |  |  | CC | Contingency |  |  | 1582 | 1593 | 1295 | 2518 | 4750 | 1049 | 9612 | CC
[6 empty] | 6062.6 | 13713.8 | 18536.5 |  | 18811.4 | 15927.3 | 15893.6 | 3380.9 | 92326.1 | 92326.1
[8 empty] | 38313 | 38312.9
|  |  |  | DD | DCMA |  | 75 | [6 empty] | 75 | 75
[10 empty] | 57124.3 | 73051.6 |  |  | 92401.1
2921.5
2956.2
[6 empty] | 557.9 | 1221.8 | 1141.8 | 67 | 1138.1 | 1044.1 | 758.9 | 132.3
92401.1