## Key staff loading metric
Key staff metrics
| Planned First plasma= |  | Feb-09 | CD-4 = | July-09 | 5 mo float
| FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | Thru
BROOKS | 96.41% | 50% | 0.01% | 0.01%
BROWN | 106.1% | 66.92% | 31.02%
CHRZANOWSKI | 87.49% | 72.89% | 70.57% | 16.44%
DUDEK | 34.58% | 30.01% | 10.02% | 10.02%
GETTLEFINGE | 44.63% | 2.874% | 58.63% | 2.914%
HEITZENROED | 18.97% | 17.17% | 2.903%
KALISH | 75.9% | 57.26% | 112.6% | 49.77%
MEIGHAN | 70.63% | 73.58% | 65.24% | 26.85%
NEILSON | 87.02% | 87.08% | 87.08% | 71.73% | 29.97% | thru May09
PERRY | 36.44% | 14.86% | 34.17% | 92.76% | 94.95% | thru Mar 09
RAFTOPOLOUS | 78.12% | 100.1% | 80.1% | 49.34%
RAKI | 62.34% | 26.61% | 107.6% | 90.09%
REIERSEN | 95.02% | 95.02% | 60.02% | 60.02% | 43.97% | thru May09
SIMMONS | 86.33% | 50% | 34.86%
STRATTON | 53.01% | 51.59% | 5% | 1%
STRYKOWSKY | 87.08% | 92.24% | 92.24% | 76.83% | 50% | thru May09
VIOLA | 85.17% | 85.11% | 85.34% | 84.99%
WILLIAMSON |  | 25% | 133% | 51%
GORANSON |  | 22% | 2% | 0%
COLE | 96.23% | 92.29% | 39.02% | 34.76% | 46.35% | thru Mar 09
LYON | 20.51% | 15.35% | 10.43% | 10.43%
NELSON | 82.33% | 63.44% | 63.96% | 28.27% | 28.27% | thru Mar 09

## Stretchout calculation
NCSX Stretchout Impact analysis
Stretchout applied after re-estimating scope to complete
WBS 121
VVSA oversight Mike Viola
| increase contract by 43 days |  |  | 43x5.65h/dx$171= | 28544.45
NCSX Stretchout Impact Analysis
WBS 131 TF fab oversight
| 308 days added |  |  |  |  | Management |  |  | Contingency
| Mike Kalish |  | 1374 total hours x 308/714=593 add'l hrs * 183$/h= |  | 108465 | WBS 191 | Stellarator core managemnt | 66.451 | 10% | 6.6451
[6 empty] | WBS 192 | Stellarator core Integration | 81.9562 | 10% | 8.1956
| Tom Meighan |  | 280 total hours x 308/714 *118$/h= |  | 14252 | WBS 81 | Project Management | 824.1801 | 17% | 140.1106
[6 empty] | WBS 82 | Project Engineering and Intrgration | 241.7252 | 17% | 41.0933
WBS 142 MC winding | [9 empty] | 0
| Duratilon duration from 391 days to 663 days added 272 days Raftopolous and Chrzanowski |  |  |  |  | Field Oversight & Supervision |  |  |  | 0
|  | total hours=5087 =7.67h/d X 272days x 180$/h= |  |  | 375655 | WBS 131 TF fab oversight |  | 122.717 | 24% | 29.4521
[6 empty] | WBS 142 MC winding |  | 596.736 | 40% | 238.6944
[6 empty] | WBS 181 FP assy oversight |  | 475.6607 | 24% | 114.1586
| Duration 391 to 707 added 316 days Tom Meighan | [8 empty] | 0
|  | total hours =2920 =4.13h/d x 316 * $118$/h= |  |  | 153999 | Overhead & Escalation |  |  |  | 0 | 2409.4263 | 578.3497 | 0.24004
[6 empty] | Labor and Overhead Rates |  | 1598 | 24% | 383.52
| Title III Dave Williamson added 360 days @ 1.21h/d * $154$/h= |  |  |  | 67082 | Direct Allocations (overhead) |  | 345 | 24% | 82.8
[6 empty] | Escalation |  | 432 | 24% | 103.68
WBS 181 FP assy oversight | [8 empty] | contingency
| Health Physics support added 1 year at (75%fte=1300hrs) x $121$/h |  |  |  | 157300 |  | Total = | 4784.4263 | 25% | 1196.1066
| Mike Viola filed supervision added 14 months @ 85% coverage @ $186$/h= |  |  |  | 318360.7 |  | TOTAL IMPACT = | 5980.5328
WBS 191 | Brad Nelson
| added 10 months @ 30% coverage = 10/12*1726 *.3*$154$/h= |  |  |  | 66451
WBS 192 | Mike Cole
| added 10 months @ 37% = 10/12*1726*.37*$154$/h= |  |  |  | 81956.2333
WBS 81
14 month stretch
|  | Strykowsky $$154$/h *1768*14/12 *90%$= |  |  | 285885.6
|  | Neilson @ $242$/h *1768*14/12*85%= |  |  | 424290.5333
|  | Pam Hampton @ $51$/h*2080*14/12 *40% |  |  | 49504
|  | Lyon 12 months @10% |  |  | 36000
WBS 82
| Wayne Reiersen @ 12 months @ 60%= |  |  |  | 192621.6
| Larry Dudek @ 12 months @ 10%= |  |  |  | 32103.6
| Cheryl Such @ 12 months @ 10%= |  |  |  | 17000
| Art Brooks extended into FY06 260 hrs |  |  |  | 0
Dimensional control
|  | Steve Raftopolous Extended into FY08 @ 40% |  |  | 0.4
Allocations added 12 months @ $187.9/yr unloaded = |  |  |  |  | 345000
Escalation due to Annual BA limitations = |  |  |  |  | 432000
Rates differential. (old rates applied to new estimates delta to new rates)= |  |  |  |  | 1598000
4784471.1167

## Escalation impact
ECP 24 | None | RESOURCE | RESOURCE DESCRIPTION | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | TOTAL
| 35 - PPPL Travel | 35 | PPPL Travel |  | 110.47 | 183 | 119.74 | 46.44 | 13.76 |  | 473.41
| 40 - M&S no escalation | 40 | M&S no escalation |  |  | 394.33 | 440.83 |  |  |  | 835.16
| 41 - PPPL M&S | 41 | PPPL M&S | 1029.53 | 2399.22 | 3361.83 | 4113.5 | 4713.71 | 566.8 |  | 16184.6
| 41MYATT - $k myatt at 125 hr | 41MYATT | $k myatt at 125 hr |  | 127.59 | 15.29 |  |  |  |  | 142.88
| 41TITUS - $k ritus at 124 hr | 41TITUS | $k ritus at 124 hr |  | 66.8 | [5 empty] | 66.8
| 48 - | 48 | 48 |  | 543.09 | 6720.96 | 6657.11 | 985.43 |  |  | 14906.58
| 4E - PPPL M&S exempt | 4E | PPPL M&S exempt |  | 85 |  | 258.04 | 549.71 |  |  | 892.75
| 54 - Allocations | 54 | Allocations |  | 265.92 | 314.33 | 320.75 | 166.89 |  |  | 1067.89
| 81 - no G&A cost | 81 | no G&A cost | 3741.48 | 1899.33 | 241 |  |  |  |  | 5881.81
| B///CB - PPPL Project Clerical | B///CB | PPPL Project Clerical |  | 28.29 | 49.09 | 49.98 | 41.99 | 10.5 |  | 179.85
| EA//EM - PPPL Analysis engineer | EA//EM | PPPL Analysis engineer |  | 1988.23 | 2349.77 | 2293.57 | 1142.08 | 253.37 |  | 8027.01
| EA//SM - PPPL Designer | EA//SM | PPPL Designer |  | 413.27 | 765.39 | 825.17 | 443.75 | 34.26 |  | 2481.84
| EC//EM - PPPL Comuter Engineer | EC//EM | PPPL Comuter Engineer |  | 12.36 | 12.9 | 55.24 | 923.1 | 75.66 |  | 1079.26
| EC//SM - PPPL Computer Senior Tech | EC//SM | PPPL Computer Senior Tech |  |  |  |  | 171.74 | 3.72 |  | 175.46
| EE//AM - | EE//AM | EE//AM |  | 6.84 | 14.29 | 14.84 | 15.41 |  |  | 51.38
| EE//EM - PPPL Electrical engineer | EE//EM | PPPL Electrical engineer |  | 101.93 | 323.17 | 536.18 | 483.02 | 185.24 |  | 1629.55
| EE//SM - PPPL Electrical Senior Tech | EE//SM | PPPL Electrical Senior Tech |  | 124.88 | 59.33 | 457.12 | 672.61 | 100.39 |  | 1414.32
| EE//TB - PPPL Electrical Technician | EE//TB | PPPL Electrical Technician |  | 7.33 | 51.72 | 168.43 | 299.73 | 65.37 |  | 592.59
| EM//EM - PPPL FO&M Engineer | EM//EM | PPPL FO&M Engineer | 24.9 | 728.17 | 576.31 | 649.59 | 1732.89 | 547.35 |  | 4259.2
| EM//SM - PPPL FO&M Senior Tech | EM//SM | PPPL FO&M Senior Tech |  | 573.41 | 505.43 | 694.09 | 1559.58 | 732.9 |  | 4065.41
| EM//TB - PPPL FO&M Technician | EM//TB | PPPL FO&M Technician |  | 1051.29 | 1357.46 | 3232.11 | 3766.68 | 563.5 |  | 9971.04
| FC//AM - PPPL P&CO am | FC//AM | PPPL P&CO am |  | 116.86 | 216.69 | 220.82 | 204.71 | 70.55 |  | 829.64
| FC//EM - PPPL P&CO em | FC//EM | PPPL P&CO em |  | 234.57 | 222.31 | 161.96 | 118.55 | 0.48 |  | 737.86
| ORNL35 - ORNL Travel | ORNL35 | ORNL Travel |  | 4.16 | 3.18 | 2.16 | 2.21 | 4.42 |  | 16.13
| ORNL41 - ORNL M&S | ORNL41 | ORNL M&S |  | 34.28 | 33.8 | 32.06 | 33.33 |  |  | 133.46
| ORNL81 - ORNL cost | ORNL81 | ORNL cost | 1146.37 | 483 | [5 empty] | 1629.37
| ORNLAM - ORNL Admin | ORNLAM | ORNL Admin |  | 51.49 | 26.76 | 13.98 |  |  |  | 92.23
| ORNLEM - ORNL Engineer | ORNLEM | ORNL Engineer |  | 1942.97 | 1468.98 | 975.13 | 373.51 | 117.54 |  | 4878.12
| ORNLRM - ORNL Scientist | ORNLRM | ORNL Scientist |  | 122.57 | 63.6 | 92.37 | 48.92 |  |  | 327.46
| R///RM2 - PPPL Scientist pdg2 | R///RM2 | PPPL Scientist pdg2 |  | 126.12 | 96.62 | 53.13 | 69.57 | 73.29 |  | 418.72
| R///RM3 - PPPL Scientist pdg3 | R///RM3 | PPPL Scientist pdg3 |  | 550.92 | 410.66 | 345.84 | 257.07 | 44.34 |  | 1608.84
| SH//TB - HP Techs | SH//TB | HP Techs |  | 115.32 | 142.13 | 144.38 | 0.58 |  |  | 402.42
| XORNL - contingency-ornl | XORNL | contingency-ornl |  |  |  |  | 780 | 100 |  | 880
|  | ecp24 | NL | 4771.01 | 5231.5 | 10916.41 | 11589.22 | 6295.29 | 580.56 | 0 | 39383.99
|  |  | L | 1171.27 | 9084.18 | 9063.92 | 11338.9 | 13307.92 | 2982.88 | 0 | 46949.05
|  |  |  | 5942.28 | 14315.68 | 19980.33 | 22928.12 | 19603.21 | 3563.44 | 0 | 86333.04
[5 empty] | 20257.96 | 41255
ECRB | None | RESOURCE | RESOURCE DESCRIPTION | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | TOTAL
| 35 - PPPL Travel | 35 | PPPL Travel |  | 99.78 | 142.45 | 103.29 | 75.65 | 44.77 | 16.92 | 482.86
| 40 - M&S no escalation | 40 | M&S no escalation |  |  | 118.45 | 161.84 |  |  |  | 280.28
| 41 - PPPL M&S | 41 | PPPL M&S | 1085.78 | 2400.4 | 2683.3 | 2652.81 | 3303.04 | 3871.79 | 2276 | 18273.12
| 41MYATT - $k myatt at 125 hr | 41MYATT | $k myatt at 125 hr |  | 123.4 | 19.48 |  |  |  |  | 142.88
| 41TITUS - $k ritus at 124 hr | 41TITUS | $k ritus at 124 hr |  | 66.8 | [5 empty] | 66.8
| 48 - | 48 | 48 |  | 522.08 | 6226.83 | 5846.36 | 1105.61 |  |  | 13700.89
| 4E - PPPL M&S exempt | 4E | PPPL M&S exempt |  | 85 |  |  | 323.37 | 461.29 |  | 869.67
| 54 - Allocations | 54 | Allocations |  | 260.69 | 350.85 | 340.47 | 340.08 | 172.79 |  | 1464.89
| 81 - no G&A cost | 81 | no G&A cost | 3804.52 | 2053.1 | 1128.2 |  |  |  | 1000 | 7985.82
| B///CB - PPPL Project Clerical | B///CB | PPPL Project Clerical |  | 24.87 | 47.98 | 42.63 | 43.62 | 33.89 |  | 192.98
| EA//EM - PPPL Analysis engineer | EA//EM | PPPL Analysis engineer |  | 1744.85 | 2317.77 | 1934.84 | 1762.44 | 1035.3 | 802.01 | 9597.21
| EA//SM - PPPL Designer | EA//SM | PPPL Designer |  | 392.02 | 796.9 | 410.28 | 613.54 | 166.73 | 8.87 | 2388.34
| EC//EM - PPPL Comuter Engineer | EC//EM | PPPL Comuter Engineer |  |  | 12.46 |  | 23.43 | 967.74 | 135.52 | 1139.15
| EC//SM - PPPL Computer Senior Tech | EC//SM | PPPL Computer Senior Tech | [5 empty] | 176.45 | 12.83 | 189.28
| EE//AM - | EE//AM | EE//AM |  | 6.84 | 14.48 | 16.09 | 16.46 | 17.05 |  | 70.91
| EE//EM - PPPL Electrical engineer | EE//EM | PPPL Electrical engineer |  | 97.86 | 191.18 | 101.36 | 611.77 | 431.09 | 733.32 | 2166.58
| EE//SM - PPPL Electrical Senior Tech | EE//SM | PPPL Electrical Senior Tech |  | 124.19 | 58.6 | 149.78 | 394.72 | 584.03 | 465.52 | 1776.83
| EE//TB - PPPL Electrical Technician | EE//TB | PPPL Electrical Technician |  | 7.33 | 56.11 | 71.85 | 204.19 | 203.41 | 81.85 | 624.73
| EM//EM - PPPL FO&M Engineer | EM//EM | PPPL FO&M Engineer | 25.67 | 659.73 | 735.42 | 523.78 | 927.33 | 1229 | 1156.93 | 5257.86
| EM//SM - PPPL FO&M Senior Tech | EM//SM | PPPL FO&M Senior Tech |  | 562.49 | 627.94 | 534.36 | 601.89 | 1488.6 | 885.53 | 4700.82
| EM//TB - PPPL FO&M Technician | EM//TB | PPPL FO&M Technician |  | 1019.14 | 968.21 | 2849.35 | 3219.08 | 2927.43 | 855.72 | 11838.94
| FC//AM - PPPL P&CO am | FC//AM | PPPL P&CO am |  | 116.86 | 207.62 | 244.29 | 249.94 | 215.69 | 99.25 | 1133.67
| FC//EM - PPPL P&CO em | FC//EM | PPPL P&CO em |  | 219.12 | 199.62 | 158.42 | 113.01 | 0.45 |  | 690.62
| ORNL35 - ORNL Travel | ORNL35 | ORNL Travel |  |  | 3 | 2.03 | 2.07 | 2.1 | 3.21 | 12.42
| ORNL41 - ORNL M&S | ORNL41 | ORNL M&S |  | 29.95 | 31.85 | 30.24 | 31.09 | 31.51 | 21.04 | 175.68
| ORNL81 - ORNL cost | ORNL81 | ORNL cost | 1146.37 | 599 | [5 empty] | 1745.37
| ORNLAM - ORNL Admin | ORNLAM | ORNL Admin |  |  | 26.76 | 22.15 | 14.44 |  |  | 63.35
| ORNLEM - ORNL Engineer | ORNLEM | ORNL Engineer |  | 1721.8 | 2005.31 | 670.84 | 723.71 | 366.27 | 121.27 | 5609.21
| ORNLRM - ORNL Scientist | ORNLRM | ORNL Scientist |  | 60.88 | 63.61 | 48.84 | 88.95 | 55.51 |  | 317.79
| R///RM2 - PPPL Scientist pdg2 | R///RM2 | PPPL Scientist pdg2 |  | 94.26 | 140.31 | 181.84 | 196.51 | 222.05 | 91.65 | 926.61
| R///RM3 - PPPL Scientist pdg3 | R///RM3 | PPPL Scientist pdg3 |  | 504.76 | 403.24 | 435.12 | 378.47 | 322.96 | 95.4 | 2139.95
| SH//TB - HP Techs | SH//TB | HP Techs |  | 61.12 | 136.54 | 151.09 | 155.19 | 161.39 |  | 665.33
| XORNL - contingency-ornl | XORNL | contingency-ornl |  |  |  |  | 486 | 100 | 100 | 686
|  | ecrb | NL | 4890.3 | 5350.56 | 10318.71 | 8764.3 | 4807.67 | 4377.85 | 3292.92 | 41802.32 | 1.7 | 71063.944
|  |  | L | 1172.04 | 8307.76 | 9395.76 | 8919.65 | 11197.93 | 10911.44 | 5669.92 | 55574.52 | 3.5 | 194510.82
|  |  |  | 6062.34 | 13658.32 | 19714.47 | 17683.95 | 16005.6 | 15289.29 | 8962.84 | 97376.84 | 5.2 | 265574.764 | 2.7273
[5 empty] | 19720.66 | 39435.13
|  |  | NL |  | -119.06 | 597.7 | 2824.92 | 1487.62 | -3797.29 | -3292.92
|  |  | L |  | 776.42 | -331.84 | 2419.25 | 2109.99 | -7928.56 | -5669.92
|  |  |  | 1.7% | -2.024 | 10.1609 | 48.0236 | 25.2895 | -64.5539 | -55.9796
|  |  |  | 3.5% | 27.1747 | -11.6144 | 84.6737 | 73.8496 | -277.4996 | -198.4472
2.72%
[6 empty] | 1819.87 | 5244.17 | 8841.78
[7 empty] | 15905.82 | 432.6383

## Rate impact
|  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | TOTAL
| non labor | 56.25 | -6.45 | -220.1 | 380.8511 | 163.8233 | 131.5514 | 119.4264 | 625.3522 | non labor
| PPPL labor | 0.77 | -139.14 | -201.56 | 381.2003 | 222.421 | 241.8016 | 303.1541 | 808.647 | PPPL labor
| ORNL labor | 0 | -6.09 | 89.23 | 73.4193 | 73.7297 | 46.5406 | 13.8613 | 290.6909 | ORNL labor
|  | 57.02 | -151.68 | -332.43 | 835.4707 | 459.974 | 419.8936 | 436.4418 | 1642
|  |  |  | Rebaseline using new rates = | 94.129
|  |  |  | Repriced rebaseline using ECP 24 rates = | 92.486
|  |  |  | Increase due to rates = | 1.643
|  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | TOTAL
MHX Rate comparision | NEW |  |  | 25% | 40% | 30% | 30% | 30%
| ECP24 |  |  | 32% | 21.4% | 22% | 22% | 22%
Site G&A | NEW |  |  | 48% | 57% | 55.5% | 55.5% | 55.5%
| ECP24 |  |  | 50% | 48.9% | 50% | 50% | 50%
G&A | NEW |  |  | 12.5% | 13.5% | 13% | 13% | 13%
| ECP24 |  |  | 13% | 12.1% | 13% | 13% | 13%
ORNL Labor (loaded engr/dsnr rate) | NEW |  |  | 155.01 | 168.72 | 171.93 | 178.61 | 185.58
| ECP24 |  |  | 140.87 | 144.91 | 154.66 | 154.66
includes escalation component

## Contingency Summary
NCSX Contingency Analysis
as of Februaruy 28th
WBS3 | Data | BCWR | CONTINGENCY $
120 |  | 4350517.4575 | 217525.8729 | 5%
121 | BCWR | 542941.9939 | 217176.7976 | 40%
122 | BCWR | 181449.8433 | 58063.9499 | 32%
123 | BCWR | 550882.2012 | 176282.3044 | 32%
124 | BCWR | 83892.2475 | 25167.6743 | 30%
125 | BCWR | 14823.4 | 4447.02 | 30%
130 | BCWR | 200408.52 | 48098.0448 | 24% |  | 200408.52 | 48098.0448 | 24%
131 | BCWR | 2275245.6 | 608761.3072 | 26.76% |  | 1675245.6 | 1208761.3072 | 72.15%
132 | BCWR | 1885357.48 | 493123.1176 | 26.16% |  | 1885357.48 | 493123.1176 | 26.16%
133 | BCWR | 257668.32 | 94352.48 | 36.62% |  | 257668.32 | 94352.48 | 36.62%
134 | BCWR | 91872.17 | 18374.434 | 20% |  | 91872.17 | 18374.434 | 20%
140 | BCWR | 6635395.932 | 663539.5932 | 10% |  | 4110552.09 | 1862709.3836 | 45.32%
141 | BCWR | 978280.8065 | 391312.3226 | 40%
142 | BCWR | 7990328.155 | 2541172.4865 | 31.8% |  |  | BCWR ETC Feb 28th | Contingency
143 | BCWR | 86111.5 | 20666.76 | 24% |  | VVSA contract | 4350517.4575 | 217525.8729 | 5%
144 | BCWR | 102051.679 | 34697.5708 | 34% |  | MCWF contract | 6635395.932 | 663539.5932 | 10%
151 | BCWR | 1378349 | 439871.3524 | 31.91% |  | WBS 1-18 | 23980227.6095 | 8029972.1653 | 33.49%
161 | BCWR | 373539.5 | 106057.0264 | 28.39% |  | WBS 2-7 & 85(BOP) | 12125449.4399 | 2373989.5974 | 19.58%
162 | BCWR | 685661.49 | 154172.2286 | 22.49% |  | WBS 19 & 81 & 82 | 8521552.2134 | 957821.7642 | 11.24%
163 | BCWR | 86298.8 | 24163.664 | 28% |  |  | 55613142.6524 | 12242848.993 | 22.01%
171 | BCWR | 821482.145 | 230015.0006 | 28%
172 | BCWR | 384744.605 | 123118.2736 | 32%
181 | BCWR | 1222312.9552 | 293355.1092 | 24% |  | 1222312.9552 | 293355.1092 | 0.24
182 | BCWR | 35469.1 | 14187.64 | 40% |  | 35469.1 | 14187.64 | 0.4
185 | BCWR | 2134720.93 | 950076.0865 | 44.51% | 40% | 2252720.93 | 832076.0865 | 0.36936
186 | BCWR | 1407311.225 | 902397.942 | 64.12% | 20% | 1110311.225 | 1199397.942 | 1.0802
187 | BCWR | 209023.943 | 60861.5724 | 29.12% |  | 209023.943 | 60861.5724 | 0.29117
191 | BCWR | 652563.13 | 65256.313 | 10%
192 | BCWR | 962570.723 | 96257.0723 | 10% |  | 4829838.1532 | 2399878.3502 | 0.49689
210 | BCWR | 86539.94 | 12115.5916 | 14%
220 | BCWR | 348883.85 | 48843.739 | 14%
310 | BCWR | 412611.46 | 123783.438 | 30%
360 | BCWR | 45955.29 | 9191.058 | 20% |  | 14
380 | BCWR | 310093.7 | 105431.858 | 34%
390 | BCWR | 113922.4038 | 34176.7211 | 30% |  | 338280.8065 | 1031312.3226 | 304.9%
411 | BCWR | 300587.88 | 54105.8184 | 18% |  | 7990328.155 | 2541172.4865 | 31.8%
412 | BCWR | 48142.6 | 8665.668 | 18% |  | 86111.5 | 20666.76 | 24%
431 | BCWR | 390585.37 | 70305.3666 | 18% |  | 102051.679 | 34697.5708 | 34%
441 | BCWR | 377663.74 | 67979.4732 | 18%
442 | BCWR | 82183.16 | 14792.9688 | 18% |  | 8516772.1404 | 3627849.1399 | 42.6%
443 | BCWR | 14270.86 | 2568.7548 | 18%
444 | BCWR | 312654.01 | 56277.7218 | 18%
445 | BCWR | 521048.66 | 114630.7052 | 22%
451 | BCWR | 367771.12 | 66198.8016 | 18%
452 | BCWR | 261735.63 | 68051.2638 | 26%
453 | BCWR | 324719.05 | 58449.429 | 18%
510 | BCWR | 282691.2 | 14134.56 | 5%
520 | BCWR | 610917.78 | 61091.778 | 10%
530 | BCWR | 351013.72 | 56162.1952 | 16%
540 | BCWR | 220964.2 | 30934.988 | 14%
550 | BCWR | 543590.2 | 32615.412 | 6%
580 | BCWR | 7552.1296 | 226.5639 | 3%
613 | BCWR | 94505.6 | 18901.12 | 20%
621 | BCWR | 233043.05 | 46608.61 | 20%
622 | BCWR | 0 | 0
623 | BCWR | 230215.87 | 46043.174 | 20%
630 | BCWR | 592042.19 | 118408.438 | 20%
720 | BCWR | 47592.72 | 4759.272 | 10%
730 | BCWR | 162300.23 | 13871.1346 | 8.547%
740 | BCWR | 63044.8 | 15130.752 | 24%
742 | BCWR | 1056141.6465 | 158421.247 | 15%
750 | BCWR | 2365713.76 | 571981.4784 | 24.18%
760 | BCWR | 238249.81 | 57179.9544 | 24%
810 | BCWR | 2758235.3878 | 275823.5388 | 10%
820 | BCWR | 3082217.4298 | 413888.2859 | 13.43%
850 | BCWR | 706501.81 | 211950.543 | 30%
AAA | BCWR | 1065965.5428 | 106596.5543 | 10%
|  | 55613142.6524 | 12242848.993 | 22.01%

## Contingency detail
ACT | TITLE | EVC | BC | BCWR | WBS1 | WBS2 | WBS3 | JJJJ | WBS4 | ORDR | CCXX | % risk | CONTINGENCY $
21-10 | Eng. Work Planning and Design | 0 | 6439.3 | 6439.3 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 901.502
21-15 | Design Gas Handling Hardware | 0 | 4817.6 | 4817.6 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 674.464
21-20 | Design PLC Controls | 0 | 10052.8 | 10052.8 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 1407.392
21-25 | Electrical Drafting for pumping system | 0 | 13959.6 | 13959.6 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 1954.344
21-30 | Drafting | 0 | 9306.4 | 9306.4 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 1302.896
21-35 | Eng. Work Planning and Design during fab | 0 | 3683.68 | 3683.68 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 515.7152
21-40 | Fabrication/Install Hardware | 0 | 3617.21 | 3617.21 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 506.4094
21-45 | Fabrication/installation | 0 | 9358.5 | 9358.5 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 1310.19
21-45 | Fabrication/installation | 0 | 6641.25 | 6641.25 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 929.775
21-45 | Fabrication/installation | 0 | 7040 | 7040 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 985.6
21-55 | Install PLC Controls | 0 | 5207.6 | 5207.6 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 729.064
21-60 | Integrated Systems Testing/Eng | 0 | 3812.2 | 3812.2 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 533.708
21-65 | Integrated Systems Testing/Tech Support | 0 | 2603.8 | 2603.8 | 2 | 21 | 210 |  | EC16 |  | 14 | 14% | 364.532
22-25 | Eng. Work Planning and Design | 0 | 18398 | 18398 | 2 | 22 | 220 |  |  |  | 14 | 14% | 2575.72
22-25 | Eng. Work Planning and Design | 0 | 9635.2 | 9635.2 | 2 | 22 | 220 |  |  |  | 14 | 14% | 1348.928
22-30 | Design PLC based control system | 0 | 40211.2 | 40211.2 | 2 | 22 | 220 |  |  |  | 14 | 14% | 5629.568
22-35 | Electrical Drafting for pumping system | 0 | 24429.3 | 24429.3 | 2 | 22 | 220 |  |  |  | 14 | 14% | 3420.102
22-40 | Drafting | 0 | 18612.8 | 18612.8 | 2 | 22 | 220 |  |  |  | 14 | 14% | 2605.792
22-45 | Eng. Work Planning and Design during fab | 0 | 16886.39 | 16886.39 | 2 | 22 | 220 |  |  |  | 14 | 14% | 2364.0946
22-50 | Perform maint. & repair of pmpg sys | 0 | 9826.16 | 9826.16 | 2 | 22 | 220 |  |  |  | 14 | 14% | 1375.6624
22-55 | Repair and Calibration of vac instrumentation | 0 | 9982.4 | 9982.4 | 2 | 22 | 220 |  |  |  | 14 | 14% | 1397.536
22-60 | Fabrication/installation | 0 | 56151 | 56151 | 2 | 22 | 220 |  |  |  | 14 | 14% | 7861.14
22-60 | Fabrication/installation | 0 | 33649 | 33649 | 2 | 22 | 220 |  |  |  | 14 | 14% | 4710.86
22-60 | Fabrication/installation | 0 | 32384 | 32384 | 2 | 22 | 220 |  |  |  | 14 | 14% | 4533.76
22-65 | Fab PLC conrols | 0 | 20830.4 | 20830.4 | 2 | 22 | 220 |  |  |  | 14 | 14% | 2916.256
22-65 | Fab PLC conrols | 0 | 45056 | 45056 | 2 | 22 | 220 |  |  |  | 14 | 14% | 6307.84
22-70 | Integrated Systems Testing/Eng | 0 | 7624.4 | 7624.4 | 2 | 22 | 220 |  |  |  | 14 | 14% | 1067.416
22-75 | Integrated Systems Testing/Tech Support | 0 | 5207.6 | 5207.6 | 2 | 22 | 220 |  |  |  | 14 | 14% | 729.064
361-001 | Design Visible Camera sys | 0 | 4971.88 | 4971.88 | 3 | 36 | 360 |  |  |  | 20 | 20% | 994.376
361-001 | Design Visible Camera sys | 0 | 7498.43 | 7498.43 | 3 | 36 | 360 |  |  |  | 20 | 20% | 1499.686
361-015 | Fab/Assy/Installation Visible Camera | 0 | 17693.9 | 17693.9 | 3 | 36 | 360 |  |  |  | 20 | 20% | 3538.78
361-015 | Fab/Assy/Installation Visible Camera | 0 | 3812.2 | 3812.2 | 3 | 36 | 360 |  |  |  | 20 | 20% | 762.44
361-015 | Fab/Assy/Installation Visible Camera | 0 | 11978.88 | 11978.88 | 3 | 36 | 360 |  |  |  | 20 | 20% | 2395.776
361-015 | Fab/Assy/Installation Visible Camera | 0 | 0 | 0 | 3 | 36 | 360 |  |  |  | 20 | 20% | 0
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 12638.5 | 12638.5 | 3 | 38 | 380 |  |  |  | 34 | 34% | 4297.09
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 22873.2 | 22873.2 | 3 | 38 | 380 |  |  |  | 34 | 34% | 7776.888
380-010 | Designe-Beam Probe,Fluor. Screen | 0 | 12052 | 12052 | 3 | 38 | 380 |  |  |  | 34 | 34% | 4097.68
380-015 | Fab & Install Beam probe | 0 | 28888 | 28888 | 3 | 38 | 380 |  |  |  | 34 | 34% | 9821.92
380-015 | Fab & Install Beam probe | 0 | 11004.6 | 11004.6 | 3 | 38 | 380 |  |  |  | 34 | 34% | 3741.564
380-015 | Fab & Install Beam probe | 0 | 30497.6 | 30497.6 | 3 | 38 | 380 |  |  |  | 34 | 34% | 10369.184
380-015 | Fab & Install Beam probe | 0 | 10415.2 | 10415.2 | 3 | 38 | 380 |  |  |  | 34 | 34% | 3541.168
380-015 | Fab & Install Beam probe | 0 | 21212.6 | 21212.6 | 3 | 38 | 380 |  |  |  | 34 | 34% | 7212.284
380-015 | Fab & Install Beam probe | 0 | 160512 | 160512 | 3 | 38 | 380 |  |  |  | 34 | 34% | 54574.08
390-020 | LOE Support FY06 | 0 | 30148.41 | 30148.41 | 3 | 39 | 390 |  |  |  | 30 | 30% | 9044.523
390-020 | LOE Support FY06 | 0 | 0 | 0 | 3 | 39 | 390 |  |  |  | 30 | 30% | 0
390-020 | LOE Support FY06 | 0 | 0 | 0 | 3 | 39 | 390 |  |  |  | 30 | 30% | 0
390-020 | LOE Support FY06 | 0 | 43561.47 | 43561.47 | 3 | 39 | 390 |  |  |  | 30 | 30% | 13068.441
51-10 | Preliminary Design (Title I) | 0 | 6825.2 | 6825.2 | 5 | 51 | 510 |  |  |  | 5 | 5% | 341.26
51-20 | Final Network Design (Title II) | 0 | 6825.2 | 6825.2 | 5 | 51 | 510 |  |  |  | 5 | 5% | 341.26
51-30 | Installation, Testing, Documentation (Title III) | 0 | 19283.2 | 19283.2 | 5 | 51 | 510 |  |  |  | 5 | 5% | 964.16
51-30 | Installation, Testing, Documentation (Title III) | 0 | 37538.6 | 37538.6 | 5 | 51 | 510 |  |  |  | 5 | 5% | 1876.93
51-30 | Installation, Testing, Documentation (Title III) | 0 | 96340.6 | 96340.6 | 5 | 51 | 510 |  |  |  | 5 | 5% | 4817.03
51-30 | Installation, Testing, Documentation (Title III) | 0 | 115878.4 | 115878.4 | 5 | 51 | 510 |  |  |  | 5 | 5% | 5793.92
52-10 | Preliminary Design (Title I) | 0 | 26900.2 | 26900.2 | 5 | 52 | 520 |  |  |  | 10 | 10% | 2690.02
52-20 | Final Design (Title II) | 0 | 66545.7 | 66545.7 | 5 | 52 | 520 |  |  |  | 10 | 10% | 6654.57
52-30 | Installation, Testing, Documentation (Title III) | 0 | 63398.84 | 63398.84 | 5 | 52 | 520 |  |  |  | 10 | 10% | 6339.884
52-30 | Installation, Testing, Documentation (Title III) | 0 | 223777.6 | 223777.6 | 5 | 52 | 520 |  |  |  | 10 | 10% | 22377.76
52-30 | Installation, Testing, Documentation (Title III) | 0 | 152588.39 | 152588.39 | 5 | 52 | 520 |  |  |  | 10 | 10% | 15258.839
52-30 | Installation, Testing, Documentation (Title III) | 0 | 77707.05 | 77707.05 | 5 | 52 | 520 |  |  |  | 10 | 10% | 7770.705
53-10 | Preliminary Design (Title I) | 0 | 28581.46 | 28581.46 | 5 | 53 | 530 |  |  |  | 16 | 16% | 4573.0336
53-20 | Final Design (Title II) | 0 | 56307.9 | 56307.9 | 5 | 53 | 530 |  |  |  | 16 | 16% | 9009.264
53-30 | Coding, Configuration, Testing (Title III) | 0 | 184778.7 | 184778.7 | 5 | 53 | 530 |  |  |  | 16 | 16% | 29564.592
53-30 | Coding, Configuration, Testing (Title III) | 0 | 81345.66 | 81345.66 | 5 | 53 | 530 |  |  |  | 16 | 16% | 13015.3056
54-10 | Preliminary Design (Title I) | 0 | 23888.2 | 23888.2 | 5 | 54 | 540 |  |  |  | 14 | 14% | 3344.348
54-20 | Final Design (Title II) | 0 | 27300.8 | 27300.8 | 5 | 54 | 540 |  |  |  | 14 | 14% | 3822.112
54-30 | Installation, Testing, Documentation (Title III) | 0 | 73430 | 73430 | 5 | 54 | 540 |  |  |  | 14 | 14% | 10280.2
54-30 | Installation, Testing, Documentation (Title III) | 0 | 61426.8 | 61426.8 | 5 | 54 | 540 |  |  |  | 14 | 14% | 8599.752
54-30 | Installation, Testing, Documentation (Title III) | 0 | 34918.4 | 34918.4 | 5 | 54 | 540 |  |  |  | 14 | 14% | 4888.576
55-10 | Preliminary Design (Title I) | 0 | 13650.4 | 13650.4 | 5 | 55 | 550 |  |  |  | 8 | 6% | 819.024
55-20 | Final Design (Title II) | 0 | 13650.4 | 13650.4 | 5 | 55 | 550 |  |  |  | 8 | 6% | 819.024
55-30 | Installation, Testing, Documentation (Title III) | 0 | 81902.4 | 81902.4 | 5 | 55 | 550 |  |  |  | 8 | 6% | 4914.144
55-30 | Installation, Testing, Documentation (Title III) | 0 | 52450 | 52450 | 5 | 55 | 550 |  |  |  | 8 | 6% | 3147
55-30 | Installation, Testing, Documentation (Title III) | 0 | 0 | 0 | 5 | 55 | 550 |  |  |  | 8 | 6% | 0
56-10 | Preliminary Design (Title I) | 0 | 27300.8 | 27300.8 | 5 | 56 | 550 |  |  |  | 8 | 6% | 1638.048
56-20 | Final Design (Title II) | 0 | 27300.8 | 27300.8 | 5 | 56 | 550 |  |  |  | 8 | 6% | 1638.048
56-30 | Installation, Testing, Documentation (Title III) | 0 | 133091.4 | 133091.4 | 5 | 56 | 550 |  |  |  | 8 | 6% | 7985.484
56-30 | Installation, Testing, Documentation (Title III) | 0 | 156228 | 156228 | 5 | 56 | 550 |  |  |  | 8 | 6% | 9373.68
56-30 | Installation, Testing, Documentation (Title III) | 0 | 38016 | 38016 | 5 | 56 | 550 |  |  |  | 8 | 6% | 2280.96
640.011 | Design GN2, Air & Vent Systems | 0 | 15248.8 | 15248.8 | 6 | 63 | 630 |  |  |  | 20 | 20% | 3049.76
640.011 | Design GN2, Air & Vent Systems | 0 | 19283.2 | 19283.2 | 6 | 63 | 630 |  |  |  | 20 | 20% | 3856.64
640.021 | Assembly/Fabrication | 0 | 9149.28 | 9149.28 | 6 | 63 | 630 |  |  |  | 20 | 20% | 1829.856
640.021 | Assembly/Fabrication | 0 | 40555.9 | 40555.9 | 6 | 63 | 630 |  |  |  | 20 | 20% | 8111.18
640.021 | Assembly/Fabrication | 0 | 25062.4 | 25062.4 | 6 | 63 | 630 |  |  |  | 20 | 20% | 5012.48
920.001 | Procedure & Doc Prep f/ first plasma(20%into ops | 0 | 291751.9 | 291751.9 | 8 | 85 | 630 |  |  | 05 | 20 | 20% | 58350.38
920.001 | Procedure & Doc Prep f/ first plasma(20%into ops | 0 | 190990.71 | 190990.71 | 8 | 85 | 630 |  |  | 05 | 20 | 20% | 38198.142
920.000 | Startup Personnel | 0 | 210503.02 | 210503.02 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 63150.906
920.000 | Startup Personnel | 0 | 82084.32 | 82084.32 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 24625.296
920.000 | Startup Personnel | 0 | 76364.64 | 76364.64 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 22909.392
920.000 | Startup Personnel | 0 | 126555.33 | 126555.33 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 37966.599
920.000 | Startup Personnel | 0 | 0 | 0 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 0
920.000 | Startup Personnel | 0 | 39627.36 | 39627.36 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 11888.208
920.000 | Startup Personnel | 0 | 91654.5 | 91654.5 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 27496.35
920.000 | Startup Personnel | 0 | 79712.64 | 79712.64 | 8 | 85 | 850 |  |  | 10 | 30 | 30% | 23913.792
191-001 | Title I design WBS 161 LN2 manifolds&piping | 0 | 15025.6 | 15025.6 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 4207.168
191-001 | Title I design WBS 161 LN2 manifolds&piping | 0 | 43146.9 | 43146.9 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 12081.132
191-011 | Title II design WBS 161 LN2 manifolds&piping | 0 | 30051.2 | 30051.2 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 8414.336
191-011 | Title II design WBS 161 LN2 manifolds&piping | 0 | 86465.7 | 86465.7 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 24210.396
191-031 | Title III engr WBS 161 | 0 | 1561.65 | 1561.65 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 437.262
191-031 | Title III engr WBS 161 | 0 | 15447.69 | 15447.69 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 4325.3532
191-037 | Procurement WBS 161 | 0 | 74534.86 | 74534.86 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 20869.7608
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 0 | 8859.38 | 8859.38 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 2480.6264
191-041 | LN2 Manifolds & ppg Fab/assy/instl WBS 161 | 0 | 25148.2 | 25148.2 | 1 | 16 | 161 |  | 161 |  | 28 | 28% | 7041.496
191-038 | PDR#17 | 0 | 62458.88 | 62458.88 | 1 | 16 | 161 |  | 161 |  | 30 | 30% | 18737.664
191-042 | PDR #17,25,3 | 0 | 2869.94 | 2869.94 | 1 | 16 | 161 |  | 161 |  | 30 | 30% | 860.982
191-042 | PDR #17,25,3 | 0 | 7969.5 | 7969.5 | 1 | 16 | 161 |  | 161 |  | 30 | 30% | 2390.85
132-001 | Title I design WBS 162 Coil leads | 0 | 149381.1 | 149381.1 | 1 | 16 | 162 |  | 162 |  | 22 | 22% | 32863.842
132-001 | Title I design WBS 162 Coil leads | 0 | 3778 | 3778 | 1 | 16 | 162 |  | 162 |  | 22 | 22% | 831.16
132-011 | Title II design WBS 162 Coil leads | 0 | 153700.03 | 153700.03 | 1 | 16 | 162 |  | 162 |  | 22 | 22% | 33814.0066
132-011 | Title II design WBS 162 Coil leads | 0 | 3821.4 | 3821.4 | 1 | 16 | 162 |  | 162 |  | 22 | 22% | 840.708
132-015 | Title III design WBS 162 Coil leads | 0 | 17542 | 17542 | 1 | 16 | 162 |  | 162 |  | 22 | 22% | 3859.24
132-015 | Title III design WBS 162 Coil leads | 0 | 998.24 | 998.24 | 1 | 16 | 162 |  | 162 |  | 22 | 22% | 219.6128
132-037 | Coil Leads Procurement WBS 162 | 0 | 314856.96 | 314856.96 | 1 | 16 | 162 |  | 162 |  | 22 | 22% | 69268.5312
132-000 | PDR #17 & 25 | 0 | 3506.16 | 3506.16 | 1 | 16 | 162 |  | 162 |  | 30 | 30% | 1051.848
132-000 | PDR #17 & 25 | 0 | 38077.6 | 38077.6 | 1 | 16 | 162 |  | 162 |  | 30 | 30% | 11423.28
163.001 | Title I design WBS 163 Coil protection | 0 | 14095.8 | 14095.8 | 1 | 16 | 163 |  | 163 |  | 28 | 28% | 3946.824
163.001 | Title I design WBS 163 Coil protection | 0 | 15112 | 15112 | 1 | 16 | 163 |  | 163 |  | 28 | 28% | 4231.36
163.001 | Title I design WBS 163 Coil protection | 0 | 13941.6 | 13941.6 | 1 | 16 | 163 |  | 163 |  | 28 | 28% | 3903.648
163.011 | Title II design WBS 163 Coil protection | 0 | 14095.8 | 14095.8 | 1 | 16 | 163 |  | 163 |  | 28 | 28% | 3946.824
163.011 | Title II design WBS 163 Coil protection | 0 | 15112 | 15112 | 1 | 16 | 163 |  | 163 |  | 28 | 28% | 4231.36
163.011 | Title II design WBS 163 Coil protection | 0 | 13941.6 | 13941.6 | 1 | 16 | 163 |  | 163 |  | 28 | 28% | 3903.648
623.011 | Design WBS 612 | 0 | 15248.8 | 15248.8 | 6 | 61 | 613 |  | 613 |  | 20 | 20% | 3049.76
623.011 | Design WBS 612 | 0 | 9641.6 | 9641.6 | 6 | 61 | 613 |  | 613 |  | 20 | 20% | 1928.32
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 15248.8 | 15248.8 | 6 | 61 | 613 |  | 613 |  | 20 | 20% | 3049.76
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 25502.4 | 25502.4 | 6 | 61 | 613 |  | 613 |  | 20 | 20% | 5100.48
632.021 | WBS 612 Assembly/Fabrication/Installation | 0 | 28864 | 28864 | 6 | 61 | 613 |  | 613 |  | 20 | 20% | 5772.8
631-001 | Preliminary Design | 0 | 16392.38 | 16392.38 | 6 | 62 | 621 |  | 621 | 10 | 20 | 20% | 3278.476
631-010 | Final Design**reduced scope | 0 | 16964.29 | 16964.29 | 6 | 62 | 621 |  | 621 | 11 | 20 | 20% | 3392.858
631-010 | Final Design**reduced scope | 0 | 1928.32 | 1928.32 | 6 | 62 | 621 |  | 621 | 11 | 20 | 20% | 385.664
631-020 | Procurement **reduced scope | 0 | 51532.8 | 51532.8 | 6 | 62 | 621 |  | 621 | 13 | 20 | 20% | 10306.56
631-020 | Procurement **reduced scope | 0 | 71808 | 71808 | 6 | 62 | 621 |  | 621 | 13 | 20 | 20% | 14361.6
631-015 | Fab/Assy/Installation**reduced scope | 0 | 16964.29 | 16964.29 | 6 | 62 | 621 |  | 621 | 14 | 20 | 20% | 3392.858
631-015 | Fab/Assy/Installation**reduced scope | 0 | 2994.72 | 2994.72 | 6 | 62 | 621 |  | 621 | 14 | 20 | 20% | 598.944
631-015 | Fab/Assy/Installation**reduced scope | 0 | 36305.5 | 36305.5 | 6 | 62 | 621 |  | 621 | 14 | 20 | 20% | 7261.1
631-015 | Fab/Assy/Installation**reduced scope | 0 | 18152.75 | 18152.75 | 6 | 62 | 621 |  | 621 | 14 | 20 | 20% | 3630.55
632-001 | **deleted scope | 0 | 0 | 0 | 6 | 62 | 622 |  | 622 |  | 20 | 20% | 0
633-001 | Preliminary Design | 0 | 16374.22 | 16374.22 | 6 | 62 | 623 |  | 623 | 10 | 20 | 20% | 3274.844
633-020 | Procurement | 0 | 112569.6 | 112569.6 | 6 | 62 | 623 |  | 623 | 12 | 20 | 20% | 22513.92
633-010 | Final Design | 0 | 16717.53 | 16717.53 | 6 | 62 | 623 |  | 623 | 13 | 20 | 20% | 3343.506
633-010 | Final Design | 0 | 9501.43 | 9501.43 | 6 | 62 | 623 |  | 623 | 13 | 20 | 20% | 1900.286
633-015 | Fab/Assy/Installation | 0 | 16964.29 | 16964.29 | 6 | 62 | 623 |  | 623 | 13 | 20 | 20% | 3392.858
633-015 | Fab/Assy/Installation | 0 | 58088.8 | 58088.8 | 6 | 62 | 623 |  | 623 | 13 | 20 | 20% | 11617.76
1203-161 | Finalize & Sign All ICDs | 15768.404 | 16598.32 | 829.916 | 1 | 12 | 121 | 1203 | 12FD | 23 | 40 | 40% | 331.9664
1203-201 | Update/Perform FMECA Analyses | 5334.972 | 5615.76 | 280.788 | 1 | 12 | 121 | 1203 | 12FD | 23 | 40 | 40% | 112.3152
1203-232 | Structural Analysis of Vac Vsl | 74899.2546 | 93976.48 | 19077.2254 | 1 | 12 | 121 | 1203 | 12FD | 23 | 40 | 40% | 7630.8902
1203-239 | Perform Analysis of VV Supports | 10689.9666 | 21950.65 | 11260.6835 | 1 | 12 | 121 | 1203 | 12FD | 23 | 40 | 40% | 4504.2734
1203-271 | Develop/Confirm & Installation Process | 3080.329 | 30803.29 | 27722.961 | 1 | 12 | 121 | 1203 | 12FD | 70 | 40 | 40% | 11089.1844
122-011 | Final design WBS 122 Thermal insulation | 802.1 | 3208.4 | 2406.3 | 1 | 12 | 122 | 1203 | 12FD | 60 | 32 | 32% | 770.016
122-011 | Final design WBS 122 Thermal insulation | 12561.7667 | 42582.26 | 30020.4933 | 1 | 12 | 122 | 1203 | 12FD | 60 | 32 | 32% | 9606.5579
1203-361 | Final Design of Heating/Cooling | 6565.3988 | 121581.46 | 115016.0612 | 1 | 12 | 123 | 1203 | 12FD | 24 | 32 | 32% | 36805.1396
122-012 | Heater Tape Design | 0 | 23796 | 23796 | 1 | 12 | 123 | 1203 | 12FD | 60 | 32 | 32% | 7614.72
122-012 | Heater Tape Design | 0 | 23560 | 23560 | 1 | 12 | 123 | 1203 | 12FD | 60 | 32 | 32% | 7539.2
124-011 | Final design WBS 124 VV supports | 7581.2185 | 7980.23 | 399.0115 | 1 | 12 | 124 | 1203 | 12FD | 30 | 30 | 30% | 119.7034
124-011 | Final design WBS 124 VV supports | 7719.054 | 8125.32 | 406.266 | 1 | 12 | 124 | 1203 | 12FD | 30 | 30 | 30% | 121.8798
124-011.1 | Lateral VV supports | 0 | 9300 | 9300 | 1 | 12 | 124 | 1203 | 12FD | 33 | 30 | 30% | 2790
124-011.1 | Lateral VV supports | 0 | 9300 | 9300 | 1 | 12 | 124 | 1203 | 12FD | 33 | 30 | 30% | 2790
124-011.2 | Analysis of Lateral supports | 3100 | 6200 | 3100 | 1 | 12 | 124 | 1203 | 12FD | 33 | 30 | 30% | 930
124-011.3 | check support analysis | 0 | 4960 | 4960 | 1 | 12 | 124 | 1203 | 12FD | 33 | 30 | 30% | 1488
120-100 | Magnetic Diag Interface/Install dwgs | 8463 | 18600 | 10137 | 1 | 12 | 124 | 1203 | 12FD | 34 | 30 | 30% | 3041.1
125-001 | Prelim design WBS 125 local I&C | 2821 | 4030 | 1209 | 1 | 12 | 125 | 1203 | 12FD | 31 | 30 | 30% | 362.7
125-011 | Final design WBS 125 local I&C | 0 | 7750 | 7750 | 1 | 12 | 125 | 1203 | 12FD | 32 | 30 | 30% | 2325
122-037 | VV Insulation Procurement WBS 122 | 0 | 121292.79 | 121292.79 | 1 | 12 | 122 | 1204 |  | 24 | 32 | 32% | 38813.6928
122-037 | VV Insulation Procurement WBS 122 | 0 | 3624 | 3624 | 1 | 12 | 122 | 1204 |  | 24 | 32 | 32% | 1159.68
122-031 | Title III engr WBS 122 | 0 | 3801.72 | 3801.72 | 1 | 12 | 122 | 1204 |  | 25 | 32 | 32% | 1216.5504
122-031 | Title III engr WBS 122 | 0 | 20304.54 | 20304.54 | 1 | 12 | 122 | 1204 |  | 25 | 32 | 32% | 6497.4528
123-037 | VV Heating/Cooling Distr Procurement WBS 123 | 0 | 364662.24 | 364662.24 | 1 | 12 | 123 | 1204 |  | 35 | 32 | 32% | 116691.9168
123-041 | VV Heating/Cooling Fab/Assy WBS 123 | 0 | 3808.17 | 3808.17 | 1 | 12 | 123 | 1204 |  | 36 | 32 | 32% | 1218.6144
123-041 | VV Heating/Cooling Fab/Assy WBS 123 | 0 | 10888.9 | 10888.9 | 1 | 12 | 123 | 1204 |  | 36 | 32 | 32% | 3484.448
123-031 | Title III engr WBS 123 | 0 | 1364.98 | 1364.98 | 1 | 12 | 123 | 1204 |  | 37 | 32 | 32% | 436.7936
123-031 | Title III engr WBS 123 | 0 | 7785.85 | 7785.85 | 1 | 12 | 123 | 1204 |  | 37 | 32 | 32% | 2491.472
124-037 | VV Supports Procurement WBS 124 | 0 | 35643.9 | 35643.9 | 1 | 12 | 124 | 1204 |  | 12 | 30 | 30% | 10693.17
124-041 | VV Supports Fab/assy WBS 124 | 0 | 722.64 | 722.64 | 1 | 12 | 124 | 1204 |  | 13 | 30 | 30% | 216.792
124-031 | Title III engr WBS 124 | 0 | 334.48 | 334.48 | 1 | 12 | 124 | 1204 |  | 14 | 30 | 30% | 100.344
124-031 | Title III engr WBS 124 | 0 | 9588.95 | 9588.95 | 1 | 12 | 124 | 1204 |  | 14 | 30 | 30% | 2876.685
125-015 | Title III design Local I&C | 0 | 2790 | 2790 | 1 | 12 | 125 | 1204 |  | 90 | 30 | 30% | 837
125-037 | Procurement Local I&C | 0 | 3074.4 | 3074.4 | 1 | 12 | 125 | 1204 |  | 91 | 30 | 30% | 922.32
1202-848 | Bid,eval,award full size test sample *ECP6* | 1604.2 | 1604.2 | 0 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 0
1202-851 | vendor fab & deliver full size sample *ECP6* | 0 | 32025 | 32025 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 12810
1202-851 | vendor fab & deliver full size sample *ECP6* | 0 | 1604.2 | 1604.2 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 641.68
1202-854 | Instrument sample *ECP6* | 0 | 2566.72 | 2566.72 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 1026.688
1202-854 | Instrument sample *ECP6* | 0 | 2520.48 | 2520.48 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 1008.192
1202-854 | Instrument sample *ECP6* | 0 | 640.5 | 640.5 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 256.2
1202-857 | Perform welds on sample *ECP6* | 0 | 8401.6 | 8401.6 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 3360.64
1202-860 | Measure Results *ECP6* | 0 | 3850.08 | 3850.08 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 1540.032
1202-863 | Report Results *ECP6* | 0 | 3850.08 | 3850.08 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 1540.032
1206-100 | Prep Sample | 1260.24 | 2520.48 | 1260.24 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 504.096
1206-110 | Weld | 298.08 | 596.16 | 298.08 | 1 | 12 | 121 | 1206 | 12Z | 49 | 40 | 40% | 119.232
VVSA-021 | Sect 5.1.2 Fiducials | 69045.9 | 70455 | 1409.1 | 1 | 12v | 120 | 1250 | VVS1 |  | 5 | 5% | 70.455
VVSA-031 | Sect 5.1.3 Proc Outline & Asc Procedures | 103415.2925 | 121665.05 | 18249.7575 | 1 | 12v | 120 | 1250 | VVS1 |  | 5 | 5% | 912.4879
VVSA-051 | Procure Die Materials (4 sets) | 102125 | 215000 | 112875 | 1 | 12v | 120 | 1250 | VVS2 | 11 | 5 | 5% | 5643.75
VVSA-051 | Procure Die Materials (4 sets) | 102514.5 | 215820 | 113305.5 | 1 | 12v | 120 | 1250 | VVS2 | 11 | 5 | 5% | 5665.275
VVSA-081 | Inspection | 5258 | 239000 | 233742 | 1 | 12v | 120 | 1250 | VVS2 | 13 | 5 | 5% | 11687.1
VVSA-081 | Inspection | 4316.4 | 215820 | 211503.6 | 1 | 12v | 120 | 1250 | VVS2 | 13 | 5 | 5% | 10575.18
VVSA-171 | Procure Materials | 0 | 220000 | 220000 | 1 | 12v | 120 | 1250 | VVS4 | 11 | 5 | 5% | 11000
VVSA-221 | Procure Vessel Material | 278617.5 | 371490 | 92872.5 | 1 | 12v | 120 | 1250 | VVS5 | 11 | 5 | 5% | 4643.625
VVSA-231 | Production Panels Period #1 | 0 | 260000 | 260000 | 1 | 12v | 120 | 1250 | VVS5 | 13 | 5 | 5% | 13000
VVSA-241 | Production Panels Period #2 | 0 | 200000 | 200000 | 1 | 12v | 120 | 1250 | VVS5 | 15 | 5 | 5% | 10000
VVSA-251 | Production Panels Period #3 | 0 | 200000 | 200000 | 1 | 12v | 120 | 1250 | VVS5 | 17 | 5 | 5% | 10000
VVSA-321 | Join two pieces | 0 | 375000 | 375000 | 1 | 12v | 120 | 1250 | VVS6 | 10 | 5 | 5% | 18750
VVSA-391 | Receive at PPPL | 0 | 375560 | 375560 | 1 | 12v | 120 | 1250 | VVS6 | 14 | 5 | 5% | 18778
VVSA-421 | Join two pieces | 0 | 350000 | 350000 | 1 | 12v | 120 | 1250 | VVS7 | 10 | 5 | 5% | 17500
VVSA-491 | Receive at PPPL | 0 | 375000 | 375000 | 1 | 12v | 120 | 1250 | VVS7 | 13 | 5 | 5% | 18750
VVSA-521 | Join two pieces | 0 | 350000 | 350000 | 1 | 12v | 120 | 1250 | VVS8 | 13 | 5 | 5% | 17500
VVSA-591 | Receive at PPPL | 0 | 375000 | 375000 | 1 | 12v | 120 | 1250 | VVS8 | 14 | 5 | 5% | 18750
VVSA-611 | PPPL Receive Tooling | 0 | 486000 | 486000 | 1 | 12v | 120 | 1250 | VVS9 | 11 | 5 | 5% | 24300
121-034 | VVSA Title III engr | 0 | 73581.15 | 73581.15 | 1 | 12 | 121 | 1250 |  | 07 | 40 | 40% | 29432.46
121-035 | VVSA Contract oversight FY05 & FY06 | 0 | 217839.24 | 217839.24 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 87135.696
121-035 | VVSA Contract oversight FY05 & FY06 | 0 | 41166.55 | 41166.55 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 16466.62
121-035.1 | ORNL fesign support during MTM Contract | 0 | 31937.06 | 31937.06 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 12774.824
121-036 | Ship vac equipt from PPPL to MTM for vac testing | 0 | 2799.6 | 2799.6 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 1119.84
121-037 | Purchase seals and ship to MTM | 0 | 31273.44 | 31273.44 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 12509.376
121-037 | Purchase seals and ship to MTM | 0 | 2510.35 | 2510.35 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 1004.14
121-038 | assist MTM testing of VVSA | 0 | 18835.2 | 18835.2 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 7534.08
121-039 | Design Seal Template | 0 | 2480 | 2480 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 992
121-141 | Fabricate Seal Template and ship to MTM | 0 | 4330.85 | 4330.85 | 1 | 12 | 121 | 1250 |  | 08 | 40 | 40% | 1732.34
133-010 | Design WBS 134 Conv Coil I&C | 0 | 13220 | 13220 | 1 | 13 | 130 | 1301 | FINL | 09 | 24 | 24% | 3172.8
1301FD-01 | TF Detailed Drawings | 0 | 19830 | 19830 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 4759.2
1301FD-03 | Layout Subassembly Fixture | 0 | 5288 | 5288 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 1269.12
1301FD-04 | Final Drawing Check | 0 | 6610 | 6610 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 1586.4
1301FD-05 | Anaylsis Check | 0 | 26440 | 26440 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 6345.6
1301FD-09 | Electrical Test 1st Sample | 0 | 596.16 | 596.16 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 143.0784
1301FD-11 | Machine Copper Bars 2nd Sample | 0 | 596.16 | 596.16 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 143.0784
1301FD-12 | Turn to Turn and Ground Wrap 2nd Sample | 0 | 8346.24 | 8346.24 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 2003.0976
1301FD-13 | Impregnate and Complete Sample 2nd Sample | 0 | 3576.96 | 3576.96 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 858.4704
1301FD-14 | Update Analysis for Front Puller | 0 | 3843 | 3843 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 922.32
1301FD-15 | Lead Transition Stress Analysis | 0 | 5124 | 5124 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 1229.76
1301FD-16 | Honeycomb InsulationStress Analysis | 0 | 5124 | 5124 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 1229.76
1301FD-17 | Resolve Tolerance Issues | 0 | 6610 | 6610 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 1586.4
1301FD-20 | Test 1st Sample | 0 | 18600 | 18600 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 4464
1301FD-20 | Test 1st Sample | 0 | 2562 | 2562 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 614.88
1301FD-21 | Test 2nd Sample | 0 | 18600 | 18600 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 4464
1301FD-21 | Test 2nd Sample | 0 | 2562 | 2562 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 614.88
1301FD-50 | Engineering | 0 | 49575 | 49575 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 11898
1301R-12 | Build Test Fixture | 3305 | 6610 | 3305 | 1 | 13 | 130 | 1301 | FINL | 80 | 24 | 24% | 793.2
1302-PF | PF& CS Support Preliminary Design | 0 | 41320.4 | 41320.4 | 1 | 13 | 132 | 1302 |  | 08 | 32 | 32% | 13222.528
1302-PF | PF& CS Support Preliminary Design | 0 | 24792.24 | 24792.24 | 1 | 13 | 132 | 1302 |  | 08 | 32 | 32% | 7933.5168
1302-PF | PF& CS Support Preliminary Design | 0 | 21035.84 | 21035.84 | 1 | 13 | 132 | 1302 |  | 08 | 32 | 32% | 6731.4688
1302-CSS | PF & CS Support Final Design | 0 | 41320.4 | 41320.4 | 1 | 13 | 132 | 1302 |  | 10 | 32 | 32% | 13222.528
1302-CSS | PF & CS Support Final Design | 0 | 87899.76 | 87899.76 | 1 | 13 | 132 | 1302 |  | 10 | 32 | 32% | 28127.9232
1302-CSS | PF & CS Support Final Design | 0 | 36812.72 | 36812.72 | 1 | 13 | 132 | 1302 |  | 10 | 32 | 32% | 11780.0704
1350-100 | Design tooling & winding facility | 0 | 73692 | 73692 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 17686.08
1350-100 | Design tooling & winding facility | 0 | 47592 | 47592 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 11422.08
1350-500 | Recondition turnkng fixture | 0 | 26827.2 | 26827.2 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 6438.528
1350-500 | Recondition turnkng fixture | 0 | 6405 | 6405 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1537.2
1350-505 | Winding Clamps | 0 | 5961.6 | 5961.6 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1430.784
1350-505 | Winding Clamps | 0 | 8401.6 | 8401.6 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 2016.384
1350-505 | Winding Clamps | 0 | 6405 | 6405 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1537.2
1350-510 | Taping Machine Conditioning | 0 | 11923.2 | 11923.2 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 2861.568
1350-510 | Taping Machine Conditioning | 0 | 8401.6 | 8401.6 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 2016.384
1350-510 | Taping Machine Conditioning | 0 | 6050.4 | 6050.4 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1452.096
1350-510 | Taping Machine Conditioning | 0 | 1281 | 1281 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 307.44
1350-515 | Winding mandrel | 0 | 11923.2 | 11923.2 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 2861.568
1350-515 | Winding mandrel | 0 | 12602.4 | 12602.4 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 3024.576
1350-515 | Winding mandrel | 0 | 6405 | 6405 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1537.2
1350-520 | Misc tools & equipt | 0 | 3843 | 3843 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 922.32
1350-525 | TF mold (2) | 0 | 27571.35 | 27571.35 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 6617.124
1350-525 | TF mold (2) | 0 | 38854.95 | 38854.95 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 9325.188
1350-525 | TF mold (2) | 0 | 13263.75 | 13263.75 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 3183.3
1350-600 | Build Cleanroom | 0 | 16394.4 | 16394.4 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 3934.656
1350-600 | Build Cleanroom | 0 | 15542.96 | 15542.96 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 3730.3104
1350-600 | Build Cleanroom | 0 | 5892.6 | 5892.6 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1414.224
1350-605 | Install winding table | 0 | 10730.88 | 10730.88 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 2575.4112
1350-605 | Install winding table | 0 | 10081.92 | 10081.92 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 2419.6608
1350-605 | Install winding table | 0 | 3843 | 3843 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 922.32
1350-610 | Setup copper delivery system | 0 | 4322.16 | 4322.16 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1037.3184
1350-610 | Setup copper delivery system | 0 | 3990.76 | 3990.76 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 957.7824
1350-610 | Setup copper delivery system | 0 | 1537.2 | 1537.2 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 368.928
1350-615 | Install taping machine | 0 | 4322.16 | 4322.16 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 1037.3184
1350-615 | Install taping machine | 0 | 3990.76 | 3990.76 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 957.7824
1350-615 | Install taping machine | 0 | 1537.2 | 1537.2 | 1 | 13 | 131 | 1350 |  |  | 24 | 24% | 368.928
131-031 | Title III engr (FDR through 1st coil test 75%) | 0 | 180590.26 | 180590.26 | 1 | 13 | 131 | 1351 | 130 | 16 | 24 | 24% | 43341.6624 | 1871888.31 | 512859.6472 | 27.4%
131-032 | Title III engr (completion of coils 10% ) | 0 | 62942.22 | 62942.22 | 1 | 13 | 131 | 1351 | 130 | 16 | 24 | 24% | 15106.1328
131-033 | Winding operations field oversight | 0 | 32995.66 | 32995.66 | 1 | 13 | 131 | 1351 | 130 | 16 | 24 | 24% | 7918.9584
1351-080 | Design Assy Fixture | 0 | 12282 | 12282 | 1 | 13 | 131 | 1351 | 13A | 60 | 24 | 24% | 2947.68
1351-086 | Fab/Assemble Fixture | 0 | 14904 | 14904 | 1 | 13 | 131 | 1351 | 13A | 60 | 24 | 24% | 3576.96
1351-086 | Fab/Assemble Fixture | 0 | 6405 | 6405 | 1 | 13 | 131 | 1351 | 13A | 60 | 24 | 24% | 1537.2
1351-088 | Setup Wedge Casting Fixture & test | 0 | 20049.6 | 20049.6 | 1 | 13 | 131 | 1351 | 13A | 60 | 24 | 24% | 4811.904
1351-110A | Assemble TF to Wedge Casting TF#1 | 0 | 8019.84 | 8019.84 | 1 | 13 | 131 | 1351 | 13A | 70 | 24 | 24% | 1924.7616
1351-115A | Assemble TF to Wedge Casting TF#2 | 0 | 4009.92 | 4009.92 | 1 | 13 | 131 | 1351 | 13A | 70 | 24 | 24% | 962.3808
1351-120A | Assemble TF to Wedge Casting TF#3 | 0 | 4009.92 | 4009.92 | 1 | 13 | 131 | 1351 | 13A | 70 | 24 | 24% | 962.3808
1351-125A | Assemble TF to Wedge Casting TF#4 | 0 | 4009.92 | 4009.92 | 1 | 13 | 131 | 1351 | 13A | 70 | 24 | 24% | 962.3808
1351-130A | Assemble TF to Wedge Casting TF#5 | 0 | 4102.56 | 4102.56 | 1 | 13 | 131 | 1351 | 13A | 70 | 24 | 24% | 984.6144
1351-135A | Assemble TF to Wedge Casting TF#6 | 0 | 4102.56 | 4102.56 | 1 | 13 | 131 | 1351 | 13A | 70 | 24 | 24% | 984.6144
1351-140A | Assemble TF to Wedge Casting TF#7(w/15% learnin | 0 | 3504.27 | 3504.27 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1401.708
1351-145A | Assemble TF to Wedge Casting TF#8(w/15% learnin | 0 | 3504.27 | 3504.27 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1401.708
1351-150A | Assemble TF to Wedge Casting TF#9(w/15% learnin | 0 | 3504.27 | 3504.27 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1401.708
1351-155A | Assemble TF to Wedge Casting TF#10(w/15% learnin | 0 | 3504.27 | 3504.27 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1401.708
1351-160A | Assemble TF to Wedge Casting TF#11(w/15% learnin | 0 | 3504.27 | 3504.27 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1401.708
1351-165A | Assemble TF to Wedge Casting TF#12(w/15% learnin | 0 | 3504.27 | 3504.27 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1401.708
1351-170A | Assemble TF to Wedge Casting TF#13(w/15% learnin | 0 | 3630.55 | 3630.55 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1452.22
1351-175A | Assemble TF to Wedge Casting TF#14(w/15% learnin | 0 | 3630.55 | 3630.55 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1452.22
1351-180A | Assemble TF to Wedge Casting TF#15(w/15% learnin | 0 | 3630.55 | 3630.55 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1452.22
1351-185A | Assemble TF to Wedge Casting TF#16(w/15% learnin | 0 | 3630.55 | 3630.55 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1452.22
1351-190A | Assemble TF to Wedge Casting TF#17(w/15% learnin | 0 | 3630.55 | 3630.55 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1452.22
1351-195A | Assemble TF to Wedge Casting TF#18(w/15% learnin | 0 | 3630.55 | 3630.55 | 1 | 13 | 131 | 1351 | 13A | 70 | 40 | 40% | 1452.22
1351-85D | Vendor Fab TF Castings | 0 | 273879 | 273879 | 1 | 13 | 131 | 1351 | 13C | 50 | 24 | 24% | 65730.96
1351-525 | Coil Supplies- Insulation | 0 | 102480 | 102480 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 24595.2
1351-527 | Coil Supplies- Epoxy | 0 | 85394.89 | 85394.89 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 20494.7736
1351-529 | Coil Supplies- Copper Conductor | 0 | 131468.31 | 131468.31 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 31552.3944
1351-531 | Coil Supplies- G-11 fillers | 0 | 5264.12 | 5264.12 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 1263.3888
1351-531 | Coil Supplies- G-11 fillers | 0 | 6089.27 | 6089.27 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 1461.4248
1351-531 | Coil Supplies- G-11 fillers | 0 | 51488.12 | 51488.12 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 12357.1488
1351-533 | Coil Supplies- Lead Blocks | 0 | 6159.02 | 6159.02 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 1478.1648
1351-533 | Coil Supplies- Lead Blocks | 0 | 3044.63 | 3044.63 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 730.7112
1351-533 | Coil Supplies- Lead Blocks | 0 | 15446.44 | 15446.44 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 3707.1456
1351-535 | Coil Supplies- Safety & PPE equipt & supplies | 0 | 10248 | 10248 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 2459.52
1351-537 | Coil Supplies- Misc supplies | 0 | 10248 | 10248 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 2459.52
1351-539 | Coil Supplies- Primer | 0 | 10248 | 10248 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 2459.52
1351-541 | VPI Supplies- Misc VPI supplies | 0 | 11310 | 11310 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 2714.4
1351-543 | VPI Supplies- Disposable VPI HW | 0 | 48656.21 | 48656.21 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 11677.4904
1351-543 | VPI Supplies- Disposable VPI HW | 0 | 34341.25 | 34341.25 | 1 | 13 | 131 | 1351 | 13E |  | 24 | 24% | 8241.9
1351-512 | Prepare braze samples | 0 | 8401.6 | 8401.6 | 1 | 13 | 131 | 1351 | 13F |  | 24 | 24% | 2016.384
1351-513 | Develop brzae techniques | 0 | 4471.2 | 4471.2 | 1 | 13 | 131 | 1351 | 13F |  | 24 | 24% | 1073.088
1351-514 | Braze conductor samples | 0 | 4471.2 | 4471.2 | 1 | 13 | 131 | 1351 | 13F |  | 24 | 24% | 1073.088
1351-515 | Test brazed samples | 0 | 8401.6 | 8401.6 | 1 | 13 | 131 | 1351 | 13F |  | 24 | 24% | 2016.384
1351-547 | Conductor Preparation | 0 | 28069.44 | 28069.44 | 1 | 13 | 131 | 1351 | 13G |  | 24 | 24% | 6736.6656
1351-549 | Wind Coil #1 | 0 | 24727.84 | 24727.84 | 1 | 13 | 131 | 1351 | 13H |  | 24 | 24% | 5934.6816
1351-551 | Wind Coil #2 | 0 | 12029.76 | 12029.76 | 1 | 13 | 131 | 1351 | 13H |  | 24 | 24% | 2887.1424
1351-553 | Wind Coil #3 | 0 | 12029.76 | 12029.76 | 1 | 13 | 131 | 1351 | 13H |  | 24 | 24% | 2887.1424
1351-555 | Wind Coil #4 | 0 | 12029.76 | 12029.76 | 1 | 13 | 131 | 1351 | 13H |  | 24 | 24% | 2887.1424
1351-557 | Wind Coil #5 | 0 | 12307.68 | 12307.68 | 1 | 13 | 131 | 1351 | 13H |  | 24 | 24% | 2953.8432
1351-559 | Wind Coil #6 | 0 | 13675.2 | 13675.2 | 1 | 13 | 131 | 1351 | 13H |  | 24 | 24% | 3282.048
1351-561 | Wind Coil #7(w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-563 | Wind Coil #8(w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-565 | Wind Coil #9(w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-567 | Wind Coil #10(w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-569 | Wind Coil #11(w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-571 | Wind Coil #12(w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-573 | Wind Coil #13 (w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-575 | Wind Coil #14 (w/15% learning curve) | 0 | 10427.34 | 10427.34 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4170.936
1351-577 | Wind Coil #15 (w/15% learning curve) | 0 | 10803.1 | 10803.1 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4321.24
1351-579 | Wind Coil #16 (w/15% learning curve) | 0 | 10803.1 | 10803.1 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4321.24
1351-581 | Wind Coil #17 (w/15% learning curve) | 0 | 10803.1 | 10803.1 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4321.24
1351-583 | Wind Coil #18 (w/15% learning curve) | 0 | 10803.1 | 10803.1 | 1 | 13 | 131 | 1351 | 13H |  | 40 | 40% | 4321.24
1351-649 | GW & Apply Mold Coil #1 | 0 | 13366.4 | 13366.4 | 1 | 13 | 131 | 1351 | 13J |  | 24 | 24% | 3207.936
1351-651 | GW & Apply Mold Coil #2 | 0 | 6683.2 | 6683.2 | 1 | 13 | 131 | 1351 | 13J |  | 24 | 24% | 1603.968
1351-653 | GW & Apply Mold Coil #3 | 0 | 6683.2 | 6683.2 | 1 | 13 | 131 | 1351 | 13J |  | 24 | 24% | 1603.968
1351-655 | GW & Apply Mold Coil #4 | 0 | 6683.2 | 6683.2 | 1 | 13 | 131 | 1351 | 13J |  | 24 | 24% | 1603.968
1351-657 | GW & Apply Mold Coil #5 | 0 | 6837.6 | 6837.6 | 1 | 13 | 131 | 1351 | 13J |  | 24 | 24% | 1641.024
1351-659 | GW & Apply Mold Coil #6 | 0 | 6837.6 | 6837.6 | 1 | 13 | 131 | 1351 | 13J |  | 24 | 24% | 1641.024
1351-661 | GW & Apply Mold Coil #7(w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-663 | GW & Apply Mold Coil #8(w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-665 | GW & Apply Mold Coil #9(w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-667 | GW & Apply Mold Coil #10(w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-669 | GW & Apply Mold Coil #11(w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-671 | GW & Apply Mold Coil #12(w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-673 | GW & Apply Mold Coil #13 (w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-675 | GW & Apply Mold Coil #14(w/15% learning curve) | 0 | 5811.96 | 5811.96 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2324.784
1351-677 | GW & Apply Mold Coil #15(w/15% learning curve) | 0 | 6021.4 | 6021.4 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2408.56
1351-679 | GW & Apply Mold Coil #16(w/15% learning curve) | 0 | 6021.4 | 6021.4 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2408.56
1351-681 | GW & Apply Mold Coil #17(w/15% learning curve) | 0 | 6021.4 | 6021.4 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2408.56
1351-683 | GW & Apply Mold Coil #18(w/15% learning curve) | 0 | 6021.4 | 6021.4 | 1 | 13 | 131 | 1351 | 13J |  | 40 | 40% | 2408.56
1351-751 | VPI Coil #1 | 0 | 13032.24 | 13032.24 | 1 | 13 | 131 | 1351 | 13K |  | 24 | 24% | 3127.7376
1351-752 | VPI Coil #2 | 0 | 13032.24 | 13032.24 | 1 | 13 | 131 | 1351 | 13K |  | 24 | 24% | 3127.7376
1351-755 | VPI Coil #3 & #4 | 0 | 26064.48 | 26064.48 | 1 | 13 | 131 | 1351 | 13K |  | 24 | 24% | 6255.4752
1351-759 | VPI Coil #5 & #6 | 0 | 26666.64 | 26666.64 | 1 | 13 | 131 | 1351 | 13K |  | 24 | 24% | 6399.9936
1351-763 | VPI Coil #7 & #8(w/15% learning curve) | 0 | 22649.55 | 22649.55 | 1 | 13 | 131 | 1351 | 13K |  | 40 | 40% | 9059.82
1351-767 | VPI Coil #9 & #10(w/15% learning curve) | 0 | 22649.55 | 22649.55 | 1 | 13 | 131 | 1351 | 13K |  | 40 | 40% | 9059.82
1351-771 | VPI Coil #11 & #12(w/15% learning curve) | 0 | 22649.55 | 22649.55 | 1 | 13 | 131 | 1351 | 13K |  | 40 | 40% | 9059.82
1351-775 | VPI Coil #13 & #14 (w/15% learning curve) | 0 | 23414.74 | 23414.74 | 1 | 13 | 131 | 1351 | 13K |  | 40 | 40% | 9365.896
1351-779 | VPI Coil #15 & #16 (w/15% learning curve) | 0 | 23465.75 | 23465.75 | 1 | 13 | 131 | 1351 | 13K |  | 40 | 40% | 9386.3
1351-783 | VPI Coil #17 & #18 (w/15% learning curve) | 0 | 23465.75 | 23465.75 | 1 | 13 | 131 | 1351 | 13K |  | 40 | 40% | 9386.3
1351-848 | Prep & setup for warm test | 0 | 9417.6 | 9417.6 | 1 | 13 | 131 | 1351 | 13L |  | 24 | 24% | 2260.224
1351-849 | Warm Test Coil #1 | 0 | 1336.64 | 1336.64 | 1 | 13 | 131 | 1351 | 13L |  | 24 | 24% | 320.7936
1351-851 | Warm Test Coil #2 | 0 | 1336.64 | 1336.64 | 1 | 13 | 131 | 1351 | 13L |  | 24 | 24% | 320.7936
1351-853 | Warm Test Coil #3 | 0 | 1336.64 | 1336.64 | 1 | 13 | 131 | 1351 | 13L |  | 24 | 24% | 320.7936
1351-855 | Warm Test Coil #4 | 0 | 1336.64 | 1336.64 | 1 | 13 | 131 | 1351 | 13L |  | 24 | 24% | 320.7936
1351-857 | Warm Test Coil #5 | 0 | 1367.52 | 1367.52 | 1 | 13 | 131 | 1351 | 13L |  | 24 | 24% | 328.2048
1351-859 | Warm Test Coil #6 | 0 | 1367.52 | 1367.52 | 1 | 13 | 131 | 1351 | 13L |  | 24 | 24% | 328.2048
1351-861 | Warm Test Coil #7(w/15% learning curve) | 0 | 1111.11 | 1111.11 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 444.444
1351-863 | Warm Test Coil #8(w/15% learning curve) | 0 | 1111.11 | 1111.11 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 444.444
1351-865 | Warm Test Coil #9(w/15% learning curve) | 0 | 1111.11 | 1111.11 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 444.444
1351-867 | Warm Test Coil #10(w/15% learning curve) | 0 | 1111.11 | 1111.11 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 444.444
1351-869 | Warm Test Coil #11(w/15% learning curve) | 0 | 1111.11 | 1111.11 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 444.444
1351-871 | Warm Test Coil #12(w/15% learning curve) | 0 | 1111.11 | 1111.11 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 444.444
1351-873 | Warm Test Coil #13 (w/15% learning curve) | 0 | 1151.15 | 1151.15 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 460.46
1351-875 | Warm Test Coil #14 (w/15% learning curve) | 0 | 1151.15 | 1151.15 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 460.46
1351-877 | Warm Test Coil #15 (w/15% learning curve) | 0 | 1151.15 | 1151.15 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 460.46
1351-879 | Warm Test Coil #16 (w/15% learning curve) | 0 | 1151.15 | 1151.15 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 460.46
1351-881 | Warm Test Coil #17 (w/15% learning curve) | 0 | 1151.15 | 1151.15 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 460.46
1351-883 | Warm Test Coil #18 (w/15% learning curve) | 0 | 1151.15 | 1151.15 | 1 | 13 | 131 | 1351 | 13L |  | 40 | 40% | 460.46
1351-901 | Build Cryostat for teststand to hold TF coil | 0 | 6683.2 | 6683.2 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 1603.968
1351-901 | Build Cryostat for teststand to hold TF coil | 0 | 4437 | 4437 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 1064.88
1351-902 | Build lifting fixture | 0 | 2673.28 | 2673.28 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 641.5872
1351-902 | Build lifting fixture | 0 | 2218.5 | 2218.5 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 532.44
1351-905 | Cold test #1 BEFORE casting applied | 0 | 6014.88 | 6014.88 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 1443.5712
1351-905 | Cold test #1 BEFORE casting applied | 0 | 3767.04 | 3767.04 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 904.0896
1351-910 | Cold test #1 again AFTER casting applied | 0 | 6014.88 | 6014.88 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 1443.5712
1351-910 | Cold test #1 again AFTER casting applied | 0 | 3767.04 | 3767.04 | 1 | 13 | 131 | 1351 | 13Z |  | 24 | 24% | 904.0896
722.010 | PF Coil receipt inspect/test (formerly wbs 183) | 0 | 11729.32 | 11729.32 | 1 | 13 | 132 | 1352 | 13P | 49 | 20 | 20% | 2345.864
722.010 | PF Coil receipt inspect/test (formerly wbs 183) | 0 | 19303.9 | 19303.9 | 1 | 13 | 132 | 1352 | 13P | 49 | 20 | 20% | 3860.78
1352-100 | Material & leads | 0 | 352000 | 352000 | 1 | 13 | 132 | 1352 | 13P | 30 | 24 | 24% | 84480
1352-110 | Tooling for PF 4 | 0 | 73920 | 73920 | 1 | 13 | 132 | 1352 | 13P | 32 | 24 | 24% | 17740.8
1352-115 | Tooling for PF 5 | 0 | 73920 | 73920 | 1 | 13 | 132 | 1352 | 13P | 33 | 24 | 24% | 17740.8
1352-120 | Tooling for PF 6 | 0 | 73920 | 73920 | 1 | 13 | 132 | 1352 | 13P | 34 | 24 | 24% | 17740.8
1352-105 | Tooling for PF 1,2 and 3 | 0 | 73920 | 73920 | 1 | 13 | 132 | 1352 | 13P | 35 | 24 | 24% | 17740.8
1352-140 | Fabricate/Dlvr PF 4 lower | 0 | 55968 | 55968 | 1 | 13 | 132 | 1352 | 13P | 38 | 24 | 24% | 13432.32
1352-145 | Fabricate/Dlvr PF 5 lower | 0 | 41817 | 41817 | 1 | 13 | 132 | 1352 | 13P | 39 | 24 | 24% | 10036.08
1352-150 | Fabricate/Dlvr PF 6 lower | 0 | 41817 | 41817 | 1 | 13 | 132 | 1352 | 13P | 40 | 24 | 24% | 10036.08
1352-155 | Fabricate/Dlvr PF 4 upper | 0 | 41817 | 41817 | 1 | 13 | 132 | 1352 | 13P | 41 | 24 | 24% | 10036.08
1352-160 | Fabricate/Dlvr PF 5 upper | 0 | 41817 | 41817 | 1 | 13 | 132 | 1352 | 13P | 42 | 24 | 24% | 10036.08
1352-165 | Fabricate/Dlvr PF 6 upper | 0 | 41817 | 41817 | 1 | 13 | 132 | 1352 | 13P | 43 | 24 | 24% | 10036.08
1352-125 | Fabricate/Dlvr PF 1 upper & lower | 0 | 83634 | 83634 | 1 | 13 | 132 | 1352 | 13P | 46 | 24 | 24% | 20072.16
1352-130 | Fabricate/Dlvr PF 2 upper & lower | 0 | 83634 | 83634 | 1 | 13 | 132 | 1352 | 13P | 47 | 24 | 24% | 20072.16
1352-135 | Fabricate/Dlvr PF 3 upper & lower | 0 | 83634 | 83634 | 1 | 13 | 132 | 1352 | 13P | 48 | 24 | 24% | 20072.16
141-031 | Title III engr WBS 132 | 0 | 148584.56 | 148584.56 | 1 | 13 | 132 | 1352 | 13P | 50 | 24 | 24% | 35660.2944
141-031 | Title III engr WBS 132 | 0 | 18621.56 | 18621.56 | 1 | 13 | 132 | 1352 | 13P | 50 | 24 | 24% | 4469.1744
163-037 | CS Support Structure Procurement/Fab | 0 | 202779.75 | 202779.75 | 1 | 13 | 132 | 1353 | 132A | 23 | 32 | 32% | 64889.52
163-037 | CS Support Structure Procurement/Fab | 0 | 3676.33 | 3676.33 | 1 | 13 | 132 | 1353 | 132A | 23 | 32 | 32% | 1176.4256
163-015 | Title III design CS sprt struc | 0 | 47932.21 | 47932.21 | 1 | 13 | 132 | 1353 | 132A | 24 | 32 | 32% | 15338.3072
163-015 | Title III design CS sprt struc | 0 | 15913.49 | 15913.49 | 1 | 13 | 132 | 1353 | 132A | 24 | 32 | 32% | 5092.3168
1303-TRIM | Trim Coil Design | 0 | 41320.4 | 41320.4 | 1 | 13 | 133 | 1354 | 133 | 51 | 32 | 32% | 13222.528
1303-TRIM | Trim Coil Design | 0 | 33807.6 | 33807.6 | 1 | 13 | 133 | 1354 | 133 | 51 | 32 | 32% | 10818.432
1303-TRIM | Trim Coil Design | 0 | 33807.6 | 33807.6 | 1 | 13 | 133 | 1354 | 133 | 51 | 32 | 32% | 10818.432
184-037 | External Trim Coil Procurement/Fab*ecp16 | 0 | 85870 | 85870 | 1 | 13 | 133 | 1354 | 133 | 14 | 40 | 40% | 34348
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 12020.48 | 12020.48 | 1 | 13 | 133 | 1354 | 133 | 16 | 40 | 40% | 4808.192
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 43574.24 | 43574.24 | 1 | 13 | 133 | 1354 | 133 | 16 | 40 | 40% | 17429.696
184-015 | Title III WBS 133 Rxt Trim Coils | 0 | 7268 | 7268 | 1 | 13 | 133 | 1354 | 133 | 16 | 40 | 40% | 2907.2
133-015 | Title III WBS 134 Conv Coil I&C | 0 | 375.64 | 375.64 | 1 | 13 | 134 | 1355 | 134 |  | 20 | 20% | 75.128
133-015 | Title III WBS 134 Conv Coil I&C | 0 | 722.64 | 722.64 | 1 | 13 | 134 | 1355 | 134 |  | 20 | 20% | 144.528
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 12742 | 12742 | 1 | 13 | 134 | 1355 | 134 |  | 20 | 20% | 2548.4
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 14814.12 | 14814.12 | 1 | 13 | 134 | 1355 | 134 |  | 20 | 20% | 2962.824
133-037 | Conv Coil I&C WBS 134 Proc & Install | 0 | 41965.77 | 41965.77 | 1 | 13 | 134 | 1355 | 134 |  | 20 | 20% | 8393.154
1355-100 | CS and PF 1-3 Pre-Assy incl coil I&C procurement | 0 | 21252 | 21252 | 1 | 13 | 134 | 1355 | 134 |  | 20 | 20% | 4250.4
1403-11.1 | Compl assembly / interface drawings for ICDs | 6200 | 12400 | 6200 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 2480
1403-11.1 | Compl assembly / interface drawings for ICDs | 6200 | 12400 | 6200 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 2480
1403-11.1 | Compl assembly / interface drawings for ICDs | 3100 | 6200 | 3100 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 1240
1403-16 | Assembly bolts, nuts,washers | 6200 | 12400 | 6200 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 2480
1403-17 | Assembly shims | 6200 | 12400 | 6200 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 2480
1403-18 | Eccentric ball assembly | 6200 | 12400 | 6200 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 2480
1403-19 | Top assembly dwgs for mod coil shell | 9300 | 18600 | 9300 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 3720
1403-19A | Bladder Details | 0 | 12400 | 12400 | 1 | 14 | 141 | 1403 | DW08 |  | 40 | 40% | 4960
1403-90 | Compile Material properties database | 17847 | 19830 | 1983 | 1 | 14 | 141 | 1403 | DW09 | 07 | 40 | 40% | 793.2
1403-40.2Z | Update nonlinear winding pack analysis | 56661.904 | 70827.38 | 14165.476 | 1 | 14 | 141 | 1403 | DW09 | 08 | 40 | 40% | 5666.1904
1403-40.2Z | Update nonlinear winding pack analysis | 4721.824 | 5902.28 | 1180.456 | 1 | 14 | 141 | 1403 | DW09 | 08 | 40 | 40% | 472.1824
1403-40.2Z | Update nonlinear winding pack analysis | 472.184 | 590.23 | 118.046 | 1 | 14 | 141 | 1403 | DW09 | 08 | 40 | 40% | 47.2184
1403-40.2Z | Update nonlinear winding pack analysis | 5096 | 6370 | 1274 | 1 | 14 | 141 | 1403 | DW09 | 08 | 40 | 40% | 509.6
1403-42H | calculate EM loads at leads | 5580 | 9300 | 3720 | 1 | 14 | 141 | 1403 | DW09 | 09 | 40 | 40% | 1488
1403-74 | check analysis using simplified models | 35694 | 39660 | 3966 | 1 | 14 | 141 | 1403 | DW09 | 09 | 40 | 40% | 1586.4
1403-42D | Fracture fatigue analysis for MCWF | 4957.5 | 9915 | 4957.5 | 1 | 14 | 141 | 1403 | DW09 | 10 | 40 | 40% | 1983
1403-42D.0 | Determine Fatigue properties | 1652.5 | 3305 | 1652.5 | 1 | 14 | 141 | 1403 | DW09 | 10 | 40 | 40% | 661
1403-42F | Perform WP beam tests at ORNL | 11160 | 27900 | 16740 | 1 | 14 | 141 | 1403 | DW09 | 10 | 40 | 40% | 6696
1403-47A | Update,review & approve FMECA | 620 | 6200 | 5580 | 1 | 14 | 141 | 1403 | DW09 | 11 | 40 | 40% | 2232
1403-42A | WP beam bending results documentation | 0 | 6200 | 6200 | 1 | 14 | 141 | 1403 | DW09 | 12 | 40 | 40% | 2480
1403-73 | Prep struct analysis report | 0 | 12400 | 12400 | 1 | 14 | 141 | 1403 | DW09 | 15 | 40 | 40% | 4960
1403-76 | Structural analysis of leads | 6200 | 12400 | 6200 | 1 | 14 | 141 | 1403 | DW09 | 19 | 40 | 40% | 2480
1403-47C | Perform cool-down/warmup analysis | 0 | 6610 | 6610 | 1 | 14 | 141 | 1403 | DW09 | 20 | 40 | 40% | 2644
1403-49A | Update tech sheets for new #of turns | 0 | 6200 | 6200 | 1 | 14 | 141 | 1403 | DW09 | 20 | 40 | 40% | 2480
1403-50A | Check inductance calculation | 0 | 6200 | 6200 | 1 | 14 | 141 | 1403 | DW09 | 20 | 40 | 40% | 2480
1403-20.00 | Resolve FDR chits | 0 | 3100 | 3100 | 1 | 14 | 141 | 1403 | DWPT | 09 | 40 | 40% | 1240
1403-20.04 | Resolve FDR chits | 0 | 6200 | 6200 | 1 | 14 | 141 | 1403 | DWPT | 09 | 40 | 40% | 2480
1403-49 | Update cost / schedule estimates | 0 | 3100 | 3100 | 1 | 14 | 141 | 1403 | DWPT | 39 | 40 | 40% | 1240
1403-20.2 | Resolve FDR chits | 0 | 6200 | 6200 | 1 | 14 | 141 | 1403 | DWPT | 42 | 40 | 40% | 2480
TITLE2TRC | Titel III Design-TRC FAB | 14185.6 | 49600 | 35414.4 | 1 | 14 | 142 | 1403 |  | 20 | 40 | 40% | 14165.76
TITLE2TRC | Titel III Design-TRC FAB | 8571.42 | 29970 | 21398.58 | 1 | 14 | 142 | 1403 |  | 20 | 40 | 40% | 8559.432
1403-219 | MCWF assy-Type C | 5580 | 5580 | 0 | 1 | 14 | 142 | 1403 | DWPT | 04 | 40 | 40% | 0
1403-219 | MCWF assy-Type C | 0 | 12400 | 12400 | 1 | 14 | 142 | 1403 | DWPT | 04 | 40 | 40% | 4960
1403-220 | Cladding assembly-Type C | 25110 | 25110 | 0 | 1 | 14 | 142 | 1403 | DWPT | 05 | 40 | 40% | 0
1403-220 | Cladding assembly-Type C | 0 | 18600 | 18600 | 1 | 14 | 142 | 1403 | DWPT | 05 | 40 | 40% | 7440
1403-201 | Leads start assy Dwgs (10)-Type C | 33454.22 | 33454.22 | 0 | 1 | 14 | 142 | 1403 | DWPT | 06 | 40 | 40% | 0
1403-201 | Leads start assy Dwgs (10)-Type C | 0 | 8304.91 | 8304.91 | 1 | 14 | 142 | 1403 | DWPT | 06 | 40 | 40% | 3321.964
1403-222 | Terminal / elec services assembly-Type C | 3720 | 3720 | 0 | 1 | 14 | 142 | 1403 | DWPT | 07 | 40 | 40% | 0
1403-222 | Terminal / elec services assembly-Type C | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWPT | 07 | 40 | 40% | 2480
1403-200 | Side A/B winding pack assy-Type C | 25193.92 | 25193.92 | 0 | 1 | 14 | 142 | 1403 | DWPT | 10 | 40 | 40% | 0
1403-200 | Side A/B winding pack assy-Type C | 0 | 8397.27 | 8397.27 | 1 | 14 | 142 | 1403 | DWPT | 10 | 40 | 40% | 3358.908
1403-221 | Lead ends assy-Type C | 3720 | 3720 | 0 | 1 | 14 | 142 | 1403 | DWPT | 11 | 40 | 40% | 0
1403-221 | Lead ends assy-Type C | 0 | 15500 | 15500 | 1 | 14 | 142 | 1403 | DWPT | 11 | 40 | 40% | 6200
1403-204 | Outer Chill Plate Dwgs -Type C | 25266.49 | 25266.49 | 0 | 1 | 14 | 142 | 1403 | DWPT | 12 | 40 | 40% | 0
1403-204 | Outer Chill Plate Dwgs -Type C | 0 | 18174.99 | 18174.99 | 1 | 14 | 142 | 1403 | DWPT | 12 | 40 | 40% | 7269.996
1403-206.1 | Cooling tubes/services assy- Type C | 0 | 9300 | 9300 | 1 | 14 | 142 | 1403 | DWPT | 20 | 40 | 40% | 3720
1403-203C | Finish Clamp Dwgs (5)-Type C | 0 | 15500 | 15500 | 1 | 14 | 142 | 1403 | DWPT | 31 | 40 | 40% | 6200
1403-224C | Finish VPI mold assembly-Type C | 0 | 3100 | 3100 | 1 | 14 | 142 | 1403 | DWPT | 32 | 40 | 40% | 1240
1403-208C | Finish I&C Dwgs -Type C | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWPT | 33 | 40 | 40% | 2480
1403-206C | Finish Cooling, Electr Schematic Dwgs - Type C | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWPT | 34 | 40 | 40% | 2480
1403-223C | Finish Top level coil assembly-Type C | 0 | 12400 | 12400 | 1 | 14 | 142 | 1403 | DWPT | 35 | 40 | 40% | 4960
1403-58C | Check and promote clamp, I&C assy dwgs -Type C | 0 | 15500 | 15500 | 1 | 14 | 142 | 1403 | DWPT | 36 | 40 | 40% | 6200
1403-58X1 | Check and promote cladding & terminal dwg-Type C | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWPT | 36 | 40 | 40% | 2480
1403-58X2 | Check and promote lead blocks, chill plt-Type C | 0 | 12400 | 12400 | 1 | 14 | 142 | 1403 | DWPT | 36 | 40 | 40% | 4960
1403-60C | Finish Update design basis document | 0 | 12400 | 12400 | 1 | 14 | 142 | 1403 | DWPT | 37 | 40 | 40% | 4960
1403-59 | Type-C product specifications | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWPT | 38 | 40 | 40% | 2480
1403-62 | Prepare FDR documentation / presentations | 0 | 3100 | 3100 | 1 | 14 | 142 | 1403 | DWPT | 40 | 40 | 40% | 1240
1403-70.05 | Update MIT/QA Plans for Type C Winding Fab | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWPT | 44 | 40 | 40% | 2480
1403-319 | MCWF studs,modifications-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 11 | 40 | 40% | 2480
1403-320 | Cladding assembly-Type A | 0 | 31000 | 31000 | 1 | 14 | 142 | 1403 | DWTA | 12 | 40 | 40% | 12400
1403-301 | Leads & crossover Dwgs (10)-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 13 | 40 | 40% | 2480
1403-300 | Winding pack assy Dwgs (8)-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 14 | 40 | 40% | 2480
1403-321 | Lead ends & closure-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 15 | 40 | 40% | 2480
1403-322 | Terminal assembly-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 16 | 40 | 40% | 2480
1403-304 | Chill Plate Dwgs (66)-Type A | 0 | 31000 | 31000 | 1 | 14 | 142 | 1403 | DWTA | 17 | 40 | 40% | 12400
1403-324 | VPI mold assembly0-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 18 | 40 | 40% | 2480
1403-303 | Clamp Dwgs (5)-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 19 | 40 | 40% | 2480
1403-306 | Cooling, Electr Schematic Dwgs (1)-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 20 | 40 | 40% | 2480
1403-308 | I&C Dwgs (1) -Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 21 | 40 | 40% | 2480
1403-323 | Top level coil assembly-Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 22 | 40 | 40% | 2480
1403-58A | Check and promote models / drawings -Type A | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 23 | 40 | 40% | 2480
1403-904 | Update cost/sched estimates&Design Basis doc. | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTA | 24 | 40 | 40% | 2480
1403-900 | Prep FDR Documentation | 0 | 3100 | 3100 | 1 | 14 | 142 | 1403 | DWTA | 25 | 40 | 40% | 1240
1403-901 | Resolve FDR comments | 0 | 3100 | 3100 | 1 | 14 | 142 | 1403 | DWTA | 27 | 40 | 40% | 1240
1403-902 | Type A product specification | 0 | 3100 | 3100 | 1 | 14 | 142 | 1403 | DWTA | 28 | 40 | 40% | 1240
1403-71.05 | Update MIT/QA Plans for Type A Winding Fab | 0 | 3100 | 3100 | 1 | 14 | 142 | 1403 | DWTA | 29 | 40 | 40% | 1240
1403-419 | MCWF studs,modifications-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 11 | 40 | 40% | 2480
1403-420 | Cladding assembly-Type B | 0 | 31000 | 31000 | 1 | 14 | 142 | 1403 | DWTB | 12 | 40 | 40% | 12400
1403-401 | Leads & crossover Dwgs (10)-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 13 | 40 | 40% | 2480
1403-400 | Winding pack assy Dwgs (8)-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 14 | 40 | 40% | 2480
1403-421 | Lead ends & closure-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 15 | 40 | 40% | 2480
1403-422 | Terminal assembly-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 16 | 40 | 40% | 2480
1403-404 | Chill Plate Dwgs (66)-TypeB | 0 | 31000 | 31000 | 1 | 14 | 142 | 1403 | DWTB | 17 | 40 | 40% | 12400
1403-424 | VPI mold assembly0-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 18 | 40 | 40% | 2480
1403-403 | Clamp Dwgs (5)-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 19 | 40 | 40% | 2480
1403-406 | Cooling, Electr Schematic Dwgs (1)-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 20 | 40 | 40% | 2480
1403-408 | I&C Dwgs (1) -Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 22 | 40 | 40% | 2480
1403-423 | Top level coil assembly-Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 23 | 40 | 40% | 2480
1403-58B | Check and promote models / drawings -Type B | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 24 | 40 | 40% | 2480
1403-80 | Update design basis doc & cost sched est | 0 | 6200 | 6200 | 1 | 14 | 142 | 1403 | DWTB | 24 | 40 | 40% | 2480
1403-72.06 | Update build-to spec | 0 | 3305 | 3305 | 1 | 14 | 142 | 1403 | DWTB | 25 | 40 | 40% | 1322
1403-81 | Prepare FDR doc | 0 | 3100 | 3100 | 1 | 14 | 142 | 1403 | DWTB | 26 | 40 | 40% | 1240
1403-72.05 | Update MIT/QA Plans for Type C Winding Fab | 0 | 3671.4 | 3671.4 | 1 | 14 | 142 | 1403 | DWTB | 28 | 40 | 40% | 1468.56
1403-72.07 | Resolve FDR comments | 0 | 3671.4 | 3671.4 | 1 | 14 | 142 | 1403 | DWTB | 29 | 40 | 40% | 1468.56
1406-104 | Prepare Draft of Coil Test Plan | 4098.81 | 5465.08 | 1366.27 | 1 | 14 | 142 | 1403 | TRTD | 15 | 40 | 40% | 546.508
1406-110 | Finalize, Approve coil test plan | 8228.805 | 10971.74 | 2742.935 | 1 | 14 | 142 | 1403 | TRTD | 15 | 40 | 40% | 1097.174
1406-103.3 | Resolve TRC FDR Issues | 1860 | 2480 | 620 | 1 | 14 | 142 | 1403 | TRTD | 16 | 40 | 40% | 248
1403-065 | Cooling redesign and analysis | 0 | 24800 | 24800 | 1 | 14 | 142 | 1403 | TRTD | 17 | 40 | 40% | 9920
1403-066 | Clamp modifications Dwgs | 0 | 12400 | 12400 | 1 | 14 | 142 | 1403 | TRTD | 17 | 40 | 40% | 4960
1403-067 | New coil clamp fab | 0 | 12810 | 12810 | 1 | 14 | 142 | 1403 | TRTD | 17 | 40 | 40% | 5124
1403-068 | TRC I&C | 0 | 18446.4 | 18446.4 | 1 | 14 | 142 | 1403 | TRTD | 17 | 40 | 40% | 7378.56
1403-068 | TRC I&C | 0 | 12400 | 12400 | 1 | 14 | 142 | 1403 | TRTD | 17 | 40 | 40% | 4960
1406-215 | 4 turn racetrack fatigue tests | 36094.5 | 40105 | 4010.5 | 1 | 14 | 142 | 1406 | 14-2 | 21 | 40 | 40% | 1604.2
1406-033 | Prepare Test report | 0 | 12833.6 | 12833.6 | 1 | 14 | 142 | 1406 | 14-2 | 22 | 40 | 40% | 5133.44
1408-605 | Fabr Chill Plts Type C for Coil c1 | 0 | 3586.8 | 3586.8 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1076.04
1408-607 | Fabr Chill Plts Type C for Coil c2 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1242.36
1408-609 | Fabr Chill Plts Type C for Coil c3 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1242.36
1408-611 | Fabr Chill Plts Type C for Coil c4 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1242.36
1408-613 | Fabr Chill Plts Type C for Coil c5 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1242.36
1408-615 | Fabr Chill Plts Type C for Coil c6 | 0 | 4114.88 | 4114.88 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1234.464
1408-621 | Fabr Chill Plts Type A for Coil a1 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1242.36
1408-623 | Fabr Chill Plts Type A for Coil a2 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1242.36
1408-625 | Fabr Chill Plts Type A for Coil a3 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1163.4
1408-627 | Fabr Chill Plts Type A for Coil a4 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1163.4
1408-629 | Fabr Chill Plts Type A for Coil a5 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1163.4
1408-631 | Fabr Chill Plts Type A for Coil a6 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1163.4
1408-637 | Fabr Chill Plts Type B for Coil b1 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1242.36
1408-639 | Fabr Chill Plts Type B for Coil b2 | 0 | 4062.24 | 4062.24 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1218.672
1408-641 | Fabr Chill Plts Type B for Coil b3 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1163.4
1408-643 | Fabr Chill Plts Type B for Coil b4 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1163.4
1408-645 | Fabr Chill Plts Type B for Coil b5 | 0 | 3887.66 | 3887.66 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1166.298
1408-647 | Fabr Chill Plts Type B for Coil b6 | 0 | 3942.4 | 3942.4 | 1 | 14 | 142 | 1408 | CHLP | 25 | 30 | 30% | 1182.72
1408-505 | PPPL Fabr Cladding Type C for Coil c1 | 0 | 3586.8 | 3586.8 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1076.04
1408-507 | Fabr Cladding Type C for Coil c2 | 0 | 3586.8 | 3586.8 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1076.04
1408-509 | Fabr Cladding Type C for Coil c3 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-511 | Fabr Cladding Type C for Coil c4 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-513 | Fabr Cladding Type C for Coil c5 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-515 | Fabr Cladding Type C for Coil c6 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-521 | Fabr Cladding Type A for Coil a1 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-523 | Fabr Cladding Type A for Coil a2 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-525 | Fabr Cladding Type A for Coil a3 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-527 | Fabr Cladding Type A for Coil a4 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-529 | Fabr Cladding Type A for Coil a5 | 0 | 4018.37 | 4018.37 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1205.511
1408-531 | Fabr Cladding Type A for Coil a6 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1163.4
1408-537 | Fabr Cladding Type B for Coil b1 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-539 | Fabr Cladding Type B for Coil b2 | 0 | 4141.2 | 4141.2 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1242.36
1408-541 | Fabr Cladding Type B for Coil b3 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1163.4
1408-543 | Fabr Cladding Type B for Coil b4 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1163.4
1408-545 | Fabr Cladding Type B for Coil b5 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1163.4
1408-547 | Fabr Cladding Type B for Coil b6 | 0 | 3878 | 3878 | 1 | 14 | 142 | 1408 | CLAD | 25 | 30 | 30% | 1163.4
1408-905 | Fabr Clamps Type C for Coil c1 | 0 | 20898 | 20898 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6269.4
1408-907 | Fabr Clamps Type C for Coil c2 | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6655.5
1408-909 | Fabr Clamps Type C for Coil c3 | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6655.5
1408-911 | Fabr Clamps Type C for Coil c4 | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6655.5
1408-913 | Fabr Clamps Type C for Coil c5 | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6655.5
1408-915 | Fabr Clamps Type C for Coil c6 | 0 | 20822 | 20822 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6246.6
1408-921 | Fabr Clamps Type A for Coil a1 | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6655.5
1408-923 | Fabr Clamps Type A for Coil a2 | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6655.5
1408-925 | Fabr Clamps Type A for Coil a3 | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6232.5
1408-927 | Fabr Clamps Type A for Coil a4 | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6232.5
1408-929 | Fabr Clamps Type A for Coil a5 | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6232.5
1408-931 | Fabr Clamps Type A for Coil a6 | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6232.5
1408-937 | Fabr Clamps Type B for Coil b1 | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6655.5
1408-939 | Fabr Clamps Type B for Coil b2 | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6232.5
1408-941 | Fabr Clamps Type B for Coil b3 | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6232.5
1408-943 | Fabr Clamps Type B for Coil b4 | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6232.5
1408-945 | Fabr Clamps Type B for Coil b5 | 0 | 21120 | 21120 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6336
1408-947 | Fabr Clamps Type B for Coil b6 | 0 | 21120 | 21120 | 1 | 14 | 142 | 1408 | CLMP | 25 | 30 | 30% | 6336
1408-145 | Copper Conductor -Delivery #2 PE005371 | 0 | 228056.43 | 228056.43 | 1 | 14 | 142 | 1408 | COPP | 99 | 10 | 10% | 22805.643
1408-146 | Add'l Copper Conductor f/trial winding PE005371 | 0 | 30744 | 30744 | 1 | 14 | 142 | 1408 | COPP | 99 | 10 | 10% | 3074.4
1408-117 | Epoxy -1st Delivery for Production | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | EPOX | 10 | 30 | 30% | 6655.5
1408-119 | Epoxy -2nd Delivery for Production | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | EPOX | 10 | 30 | 30% | 6655.5
1408-121 | Epoxy -3rd Delivery for Production | 0 | 22185 | 22185 | 1 | 14 | 142 | 1408 | EPOX | 10 | 30 | 30% | 6655.5
1408-123 | Epoxy -4th Delivery for Production | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | EPOX | 10 | 30 | 30% | 6232.5
1408-125 | Epoxy -5th Delivery for Production | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | EPOX | 10 | 30 | 30% | 6232.5
1408-127 | Epoxy -6th Delivery for Production | 0 | 20775 | 20775 | 1 | 14 | 142 | 1408 | EPOX | 10 | 30 | 30% | 6232.5
1408-108 | Insulation-Delivery incl add'l f/trial winding | 0 | 20496 | 20496 | 1 | 14 | 142 | 1408 | INSL | 15 | 30 | 30% | 6148.8
1408-705 | Fabr Lead HW Type C for Coil c1 | 0 | 25204.8 | 25204.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 7561.44
1408-705 | Fabr Lead HW Type C for Coil c1 | 0 | 69174 | 69174 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 20752.2
1408-707 | Fabr Lead HW Type C for Coil c2 | 0 | 26728.8 | 26728.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8018.64
1408-709 | Fabr Lead HW Type C for Coil c3 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-711 | Fabr Lead HW Type C for Coil c4 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-713 | Fabr Lead HW Type C for Coil c5 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-715 | Fabr Lead HW Type C for Coil c6 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-721 | Fabr Lead HW Type A for Coil a1 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-723 | Fabr Lead HW Type A for Coil a2 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-725 | Fabr Lead HW Type A for Coil a3 | 0 | 28807.68 | 28807.68 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8642.304
1408-727 | Fabr Lead HW Type A for Coil a4 | 0 | 28905.6 | 28905.6 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8671.68
1408-729 | Fabr Lead HW Type A for Coil a5 | 0 | 28905.6 | 28905.6 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8671.68
1408-731 | Fabr Lead HW Type A for Coil a6 | 0 | 28905.6 | 28905.6 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8671.68
1408-737 | Fabr Lead HW Type B for Coil b1 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-739 | Fabr Lead HW Type B for Coil b2 | 0 | 28252.8 | 28252.8 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8475.84
1408-741 | Fabr Lead HW Type B for Coil b3 | 0 | 28905.6 | 28905.6 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8671.68
1408-743 | Fabr Lead HW Type B for Coil b4 | 0 | 28905.6 | 28905.6 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8671.68
1408-745 | Fabr Lead HW Type B for Coil b5 | 0 | 28905.6 | 28905.6 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8671.68
1408-747 | Fabr Lead HW Type B for Coil b6 | 0 | 28905.6 | 28905.6 | 1 | 14 | 142 | 1408 | LEAD | 25 | 30 | 30% | 8671.68
1408-137 | Safety & PPE equipt & supplies | 0 | 21026.92 | 21026.92 | 1 | 14 | 142 | 1408 | OTHE | 25 | 30 | 30% | 6308.076
1408-138 | Misc. Supplies | 0 | 16821.53 | 16821.53 | 1 | 14 | 142 | 1408 | OTHE | 25 | 30 | 30% | 5046.459
1408-173 | Epoxy for Shell Mold (Hysol) | 0 | 25524.06 | 25524.06 | 1 | 14 | 142 | 1408 | OTHE | 40 | 30 | 30% | 7657.218
1408-183 | Tubing (Chem flor and Poly) | 0 | 49630.11 | 49630.11 | 1 | 14 | 142 | 1408 | OTHE | 40 | 30 | 30% | 14889.033
1408-184 | Vulcanizing tape, felt and RTV | 0 | 31196.07 | 31196.07 | 1 | 14 | 142 | 1408 | OTHE | 40 | 30 | 30% | 9358.821
1408-185 | Valves and Fittings | 0 | 21270.05 | 21270.05 | 1 | 14 | 142 | 1408 | OTHE | 40 | 30 | 30% | 6381.015
1408-186 | Manifolds | 0 | 1419.47 | 1419.47 | 1 | 14 | 142 | 1408 | OTHE | 40 | 30 | 30% | 425.841
1408-186 | Manifolds | 0 | 83683.83 | 83683.83 | 1 | 14 | 142 | 1408 | OTHE | 40 | 30 | 30% | 25105.149
1408-765 | Deliver Tubing | 0 | 2562 | 2562 | 1 | 14 | 142 | 1408 | TUBE | 25 | 30 | 30% | 768.6
1409-155 | Fab/Instl Closed Loop LN2 sys | 11342.16 | 12602.4 | 1260.24 | 1 | 14 | 144 | 1409 | 14-9 | 07 | 34 | 34% | 428.4816
1409-029 | Oversight/Supervision | 2694.5451 | 3051.58 | 357.0349 | 1 | 14 | 144 | 1409 | 14-9 | 14 | 34 | 34% | 121.3919
1409-029 | Oversight/Supervision | 7698.7004 | 8718.8 | 1020.0996 | 1 | 14 | 144 | 1409 | 14-9 | 14 | 34 | 34% | 346.8339
1409-029 | Oversight/Supervision | 20539.3747 | 23260.9 | 2721.5253 | 1 | 14 | 144 | 1409 | 14-9 | 14 | 34 | 34% | 925.3186
1409-027 | Cryo Line Installation | 3576.96 | 8942.4 | 5365.44 | 1 | 14 | 144 | 1409 | 14-9 | 28 | 34 | 34% | 1824.2496
1409-027 | Cryo Line Installation | 2944.204 | 7360.51 | 4416.306 | 1 | 14 | 144 | 1409 | 14-9 | 28 | 34 | 34% | 1501.544
1409-027 | Cryo Line Installation | 4599.884 | 11499.71 | 6899.826 | 1 | 14 | 144 | 1409 | 14-9 | 28 | 34 | 34% | 2345.9408
1409-130 | Cryostat (specimen shroud) dsn | 0 | 6416.8 | 6416.8 | 1 | 14 | 144 | 1409 | 14-9 | 52 | 34 | 34% | 2181.712
1409-135 | Cryostat (specimen shroud) Fabr & Install | 0 | 12810 | 12810 | 1 | 14 | 144 | 1409 | 14-9 | 60 | 34 | 34% | 4355.4
1409-135 | Cryostat (specimen shroud) Fabr & Install | 0 | 8942.4 | 8942.4 | 1 | 14 | 144 | 1409 | 14-9 | 60 | 34 | 34% | 3040.416
1409-028 | System Testing (planar racetrack) | 0 | 12833.6 | 12833.6 | 1 | 14 | 144 | 1409 | 14-9 | 64 | 34 | 34% | 4363.424
1409-028 | System Testing (planar racetrack) | 0 | 4843.8 | 4843.8 | 1 | 14 | 144 | 1409 | 14-9 | 64 | 34 | 34% | 1646.892
1409-160 | Test Closed Loop Cooling | 0 | 2980.8 | 2980.8 | 1 | 14 | 144 | 1409 | 14-9 | 65 | 34 | 34% | 1013.472
1406-01602 | Oversight & Supervision | 0 | 49905.5 | 49905.5 | 1 | 14 | 142 | 1410 | 14-4 | 62 | 30 | 30% | 14971.65
1406-01602 | Oversight & Supervision | 0 | 45368.64 | 45368.64 | 1 | 14 | 142 | 1410 | 14-4 | 62 | 30 | 30% | 13610.592
1406-01602 | Oversight & Supervision | 0 | 35694 | 35694 | 1 | 14 | 142 | 1410 | 14-4 | 62 | 30 | 30% | 10708.2
1406-016.7 | Finish TRC Chill plates | 0 | 2980.8 | 2980.8 | 1 | 14 | 142 | 1410 | 14-4 | 63 | 30 | 30% | 894.24
1406-016.7 | Finish TRC Chill plates | 0 | 1281 | 1281 | 1 | 14 | 142 | 1410 | 14-4 | 63 | 30 | 30% | 384.3
1406-01608 | Coil Clamps | 0 | 11529 | 11529 | 1 | 14 | 142 | 1410 | 14-4 | 63 | 30 | 30% | 3458.7
1406-01609 | Rework Lead Blocks | 0 | 21004 | 21004 | 1 | 14 | 142 | 1410 | 14-4 | 63 | 30 | 30% | 6301.2
1406-01609 | Rework Lead Blocks | 0 | 8942.4 | 8942.4 | 1 | 14 | 142 | 1410 | 14-4 | 63 | 30 | 30% | 2682.72
1406-017.H | complete coil winding | 0 | 35769.6 | 35769.6 | 1 | 14 | 142 | 1410 | 14-4 | 66 | 30 | 30% | 10730.88
1406-017.J | Instl diag loops & chill plates | 0 | 23846.4 | 23846.4 | 1 | 14 | 142 | 1410 | 14-4 | 66 | 30 | 30% | 7153.92
1406-018 | Pre-VPI Press test &Apply bag mold | 0 | 15500.16 | 15500.16 | 1 | 14 | 142 | 1410 | 14-4 | 68 | 30 | 30% | 4650.048
1406-019 | VPI TRC in autoclave | 0 | 24442.56 | 24442.56 | 1 | 14 | 142 | 1410 | 14-4 | 69 | 30 | 30% | 7332.768
1406-019.1 | Instl permanent clamps | 0 | 9538.56 | 9538.56 | 1 | 14 | 142 | 1410 | 14-4 | 70 | 30 | 30% | 2861.568
1406-019.2 | Electrical & Pressure tests | 0 | 1192.32 | 1192.32 | 1 | 14 | 142 | 1410 | 14-4 | 70 | 30 | 30% | 357.696
1406-021 | Test Coil | 0 | 9538.56 | 9538.56 | 1 | 14 | 142 | 1410 | 14-4 | 72 | 30 | 30% | 2861.568
1406-021 | Test Coil | 0 | 4235.28 | 4235.28 | 1 | 14 | 142 | 1410 | 14-4 | 72 | 30 | 30% | 1270.584
1406-021 | Test Coil | 0 | 4422.8 | 4422.8 | 1 | 14 | 142 | 1410 | 14-4 | 72 | 30 | 30% | 1326.84
1406-021 | Test Coil | 0 | 6230.8 | 6230.8 | 1 | 14 | 142 | 1410 | 14-4 | 72 | 30 | 30% | 1869.24
1406-021 | Test Coil | 0 | 6416.8 | 6416.8 | 1 | 14 | 142 | 1410 | 14-4 | 72 | 30 | 30% | 1925.04
1406-023 | Dissect Coil | 0 | 2980.8 | 2980.8 | 1 | 14 | 142 | 1410 | 14-4 | 73 | 30 | 30% | 894.24
1406-023 | Dissect Coil | 0 | 2980.8 | 2980.8 | 1 | 14 | 142 | 1410 | 14-4 | 73 | 30 | 30% | 894.24
MCWF-001 | EIO Project Mgt. & Reporting | 123600.88 | 908830 | 785229.12 | 1 | 14m | 140 | 1411 |  | 15 | 10 | 10% | 78522.912
MCWF-011 | Pattern A complete | 0 | 130000 | 130000 | 1 | 14m | 140 | 1411 |  | 20 | 10 | 10% | 13000
MCWF-011 | Pattern A complete | 112087.5 | 160125 | 48037.5 | 1 | 14m | 140 | 1411 |  | 20 | 10 | 10% | 4803.75
MCWF-021 | Pattern B complete | 25512 | 255120 | 229608 | 1 | 14m | 140 | 1411 |  | 20 | 10 | 10% | 22960.8
MCWF-041 | Materials (MetalTek) | 498982.5 | 744750 | 245767.5 | 1 | 14m | 140 | 1411 |  | 20 | 10 | 10% | 24576.75
MCWF-051 | C1-MTK-casting upgrade | 129724.308 | 144138.12 | 14413.812 | 1 | 14m | 140 | 1411 |  | 20 | 10 | 10% | 1441.3812
MCWF-061 | C1-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 20 | 10 | 10% | 15491
MCWF-071 | C1-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 20 | 10 | 10% | 0
MCWF-081 | C2-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-091 | C2-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-101 | C2-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-111 | A1-MTK-casting | 0 | 141000 | 141000 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14100
MCWF-121 | A1-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-131 | A1-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-141 | C3-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-151 | C3-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-161 | C3-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-171 | A2-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-181 | A2-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-191 | A2-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-201 | C4-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-211 | C4-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-221 | C4-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-231 | B1-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-241 | B1-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-251 | B1-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-261 | C5-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-271 | C5-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-281 | C5-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-291 | C6-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-301 | C6-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-311 | C6-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-321 | B2-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-331 | B2-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-341 | B2-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-351 | A3-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-361 | A3-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-371 | A3-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-381 | A4-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-391 | A4-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-401 | A4-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-411 | A5-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-421 | A5-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-431 | A5-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-441 | A6-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-451 | A6-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-461 | A6-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-471 | B3-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-481 | B3-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-491 | B3-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-501 | B4-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-511 | B4-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-521 | B4-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-531 | B5-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-541 | B5-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-551 | B5-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
MCWF-561 | B6-MTK-casting | 0 | 140810 | 140810 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 14081
MCWF-571 | B6-MTM - machining/inspection | 0 | 154910 | 154910 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 15491
MCWF-581 | B6-Receive at PPPL | 0 | 0 | 0 | 1 | 14m | 140 | 1411 |  | 30 | 10 | 10% | 0
172-031 | Title III engr | 16281.4937 | 59421.51 | 43140.0163 | 1 | 14 | 141 | 1411 |  | 10 | 40 | 40% | 17256.0065
172-031 | Title III engr | 8710.3394 | 31789.56 | 23079.2206 | 1 | 14 | 141 | 1411 |  | 10 | 40 | 40% | 9231.6882
172-031 | Title III engr | 22999.3983 | 83939.41 | 60940.0117 | 1 | 14 | 141 | 1411 |  | 10 | 40 | 40% | 24376.0047
1407-130.1 | Misc tools & equipt FY05 | 19317.48 | 25620 | 6302.52 | 1 | 14 | 144 | 1412 | FIX | 20 | 34 | 34% | 2142.8568
1407-130.1 | Misc tools & equipt FY05 | 3167.4032 | 4200.8 | 1033.3968 | 1 | 14 | 144 | 1412 | FIX | 20 | 34 | 34% | 351.3549
1407-126.1 | Complete Fab Type A casting supports (6) sets | 5852.8008 | 17735.76 | 11882.9592 | 1 | 14 | 144 | 1412 | FIX | 25 | 34 | 34% | 4040.2061
1407-127.1 | Complete Fab Type B casting supports (6) sets | 21270.9888 | 33235.92 | 11964.9312 | 1 | 14 | 144 | 1412 | FIX | 25 | 34 | 34% | 4068.0766
1413-100 | Oversight | 0 | 0 | 0 | 1 | 14 | 141 | 1413 |  | 30 | 10 | 10% | 0
1413-110 | Cut 3 discs from proto;cut 1 into qrts (MTM) | 0 | 0 | 0 | 1 | 14 | 141 | 1413 |  | 30 | 10 | 10% | 0
1413-120 | Weld quartered discs (Metal Tek) | 0 | 0 | 0 | 1 | 14 | 141 | 1413 |  | 30 | 10 | 10% | 0
1413-130 | Machine test blanks (PPPL) | 0 | 0 | 0 | 1 | 14 | 141 | 1413 |  | 30 | 10 | 10% | 0
1413-140 | Wire EDM 12 specimens (Crystal) | 0 | 0 | 0 | 1 | 14 | 141 | 1413 |  | 30 | 10 | 10% | 0
1413-150 | Perform fracture tests (NHMFL) | 0 | 0 | 0 | 1 | 14 | 141 | 1413 |  | 30 | 10 | 10% | 0
1421-100 | Submet Requisition for - Assy bolts,nuts,washers | 0 | 2699.2 | 2699.2 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 1079.68
1421-110 | Deliver - Assy bolts,nuts,washers | 0 | 184156.25 | 184156.25 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 73662.5
1421-200 | Submet Requisition for - Assembly shims | 0 | 2699.2 | 2699.2 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 1079.68
1421-210 | Deliver - Assembly shims | 0 | 192526.98 | 192526.98 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 77010.792
1421-300 | Submet Requisition for - Eccentric ball assy | 0 | 2699.2 | 2699.2 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 1079.68
1421-310 | Deliver - Eccentric ball assy | 0 | 59990.29 | 59990.29 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 23996.116
1421-400 | Submet Requisition for - Bladders | 0 | 2699.2 | 2699.2 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 1079.68
1421-410 | Deliver - Bladders | 0 | 83707.38 | 83707.38 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 33482.952
1421-500 | Submet Requisition for-Tooling plates&reaming HW | 0 | 2699.2 | 2699.2 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 1079.68
1421-510 | Deliver-Tooling plates&reaming HW | 0 | 143697.68 | 143697.68 | 1 | 14 | 141 | 1421 |  | 25 | 40 | 40% | 57479.072
174-035 | Modular Coil local I&C -Procurement | 0 | 17075.73 | 17075.73 | 1 | 14 | 143 | 1431 |  |  | 24 | 24% | 4098.1752
174-037 | Modular Coil local I&C -Install | 0 | 20446 | 20446 | 1 | 14 | 143 | 1431 |  |  | 24 | 24% | 4907.04
174-037 | Modular Coil local I&C -Install | 0 | 48589.77 | 48589.77 | 1 | 14 | 143 | 1431 |  |  | 24 | 24% | 11661.5448
P1-001 | Receive C1, Prep& Instl Cladding(Station 1) | 0 | 10730.88 | 10730.88 | 1 | 14 | 142 | 1451 | 1 | 01 | 30 | 30% | 3219.264 | 5237948.02 | 1701171.7665 | 32.48%
P1-001 | Receive C1, Prep& Instl Cladding(Station 1) | 0 | 14307.84 | 14307.84 | 1 | 14 | 142 | 1451 | 1 | 01 | 30 | 30% | 4292.352
P1-091 | Receive C2, Prep& Instl Cladding(Station 1) | 0 | 11308.16 | 11308.16 | 1 | 14 | 142 | 1451 | 1 | 02 | 30 | 30% | 3392.448
P1-091 | Receive C2, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 02 | 30 | 30% | 4811.904
P2-001 | Receive A1, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 03 | 30 | 30% | 3608.928
P2-001 | Receive A1, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 03 | 30 | 30% | 4811.904
P2-091 | Receive C3, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 04 | 30 | 30% | 3608.928
P2-091 | Receive C3, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 04 | 30 | 30% | 4811.904
P3-001 | Receive A2, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 05 | 30 | 30% | 3608.928
P3-001 | Receive A2, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 05 | 30 | 30% | 4811.904
P3-091 | Receive C4, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 06 | 30 | 30% | 3608.928
P3-091 | Receive C4, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 06 | 30 | 30% | 4811.904
P1-031 | Receive B1, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 10 | 30 | 30% | 3608.928
P1-031 | Receive B1, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 10 | 30 | 30% | 4811.904
P1-121 | Receive C5, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 11 | 30 | 30% | 3608.928
P1-121 | Receive C5, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 11 | 30 | 30% | 4811.904
P2-031 | Receive C6, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 12 | 30 | 30% | 3608.928
P2-031 | Receive C6, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 12 | 30 | 30% | 4811.904
P2-121 | Receive B2, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 13 | 30 | 30% | 3608.928
P2-121 | Receive B2, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 13 | 30 | 30% | 4811.904
P3-031 | Receive A3, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 14 | 30 | 30% | 3608.928
P3-031 | Receive A3, Prep& Instl Cladding(Station 1) | 0 | 16039.68 | 16039.68 | 1 | 14 | 142 | 1451 | 1 | 14 | 30 | 30% | 4811.904
P3-121 | Receive A4, Prep& Instl Cladding(Station 1) | 0 | 12029.76 | 12029.76 | 1 | 14 | 142 | 1451 | 1 | 15 | 30 | 30% | 3608.928
P3-121 | Receive A4, Prep& Instl Cladding(Station 1) | 0 | 16163.2 | 16163.2 | 1 | 14 | 142 | 1451 | 1 | 15 | 30 | 30% | 4848.96
P1-061 | Receive A5, Prep& Instl Cladding(Station 1) | 0 | 12307.68 | 12307.68 | 1 | 14 | 142 | 1451 | 1 | 16 | 30 | 30% | 3692.304
P1-061 | Receive A5, Prep& Instl Cladding(Station 1) | 0 | 16410.24 | 16410.24 | 1 | 14 | 142 | 1451 | 1 | 16 | 30 | 30% | 4923.072
P1-151 | Receive A6, Prep& Instl Cladding(Station 1) | 0 | 12307.68 | 12307.68 | 1 | 14 | 142 | 1451 | 1 | 17 | 30 | 30% | 3692.304
P1-151 | Receive A6, Prep& Instl Cladding(Station 1) | 0 | 16410.24 | 16410.24 | 1 | 14 | 142 | 1451 | 1 | 17 | 30 | 30% | 4923.072
P2-061 | Receive B3, Prep& Instl Cladding(Station 1) | 0 | 12307.68 | 12307.68 | 1 | 14 | 142 | 1451 | 1 | 18 | 30 | 30% | 3692.304
P2-061 | Receive B3, Prep& Instl Cladding(Station 1) | 0 | 16410.24 | 16410.24 | 1 | 14 | 142 | 1451 | 1 | 18 | 30 | 30% | 4923.072
P2-151 | Receive B4, Prep& Instl Cladding(Station 1) | 0 | 12307.68 | 12307.68 | 1 | 14 | 142 | 1451 | 1 | 19 | 30 | 30% | 3692.304
P2-151 | Receive B4, Prep& Instl Cladding(Station 1) | 0 | 16410.24 | 16410.24 | 1 | 14 | 142 | 1451 | 1 | 19 | 30 | 30% | 4923.072
P3-061 | Receive B5, Prep& Instl Cladding(Station 1) | 0 | 12307.68 | 12307.68 | 1 | 14 | 142 | 1451 | 1 | 20 | 30 | 30% | 3692.304
P3-061 | Receive B5, Prep& Instl Cladding(Station 1) | 0 | 16410.24 | 16410.24 | 1 | 14 | 142 | 1451 | 1 | 20 | 30 | 30% | 4923.072
P3-151 | Receive B6, Prep& Instl Cladding(Station 1) | 0 | 12307.68 | 12307.68 | 1 | 14 | 142 | 1451 | 1 | 21 | 30 | 30% | 3692.304
P3-151 | Receive B6, Prep& Instl Cladding(Station 1) | 0 | 16410.24 | 16410.24 | 1 | 14 | 142 | 1451 | 1 | 21 | 30 | 30% | 4923.072
P1-011 | Wind coil C1 ------>incl trial winding | 0 | 90616.32 | 90616.32 | 1 | 14 | 142 | 1451 | 2 | 02 | 30 | 30% | 27184.896
P1-011 | Wind coil C1 ------>incl trial winding | 0 | 44712 | 44712 | 1 | 14 | 142 | 1451 | 2 | 02 | 30 | 30% | 13413.6
P1-020 | Instl Chill Plates,Tubing, Bag C1 (Station 2) | 0 | 32771.96 | 32771.96 | 1 | 14 | 142 | 1451 | 2 | 03 | 30 | 30% | 9831.588
P2-011 | Wind coil A1 ------>incl trial winding | 0 | 101584.64 | 101584.64 | 1 | 14 | 142 | 1451 | 2 | 17 | 30 | 30% | 30475.392
P2-011 | Wind coil A1 ------>incl trial winding | 0 | 50124 | 50124 | 1 | 14 | 142 | 1451 | 2 | 17 | 30 | 30% | 15037.2
P2-020 | Instl Chill Plates,Tubing, Bag A1 (Station 2) | 0 | 35755.12 | 35755.12 | 1 | 14 | 142 | 1451 | 2 | 18 | 30 | 30% | 10726.536
P3-011 | Wind coil A2 | 0 | 101584.64 | 101584.64 | 1 | 14 | 142 | 1451 | 2 | 30 | 30 | 30% | 30475.392
P3-020 | Instl Chill Plates,Tubing, Bag A2 (Station 2) | 0 | 35755.12 | 35755.12 | 1 | 14 | 142 | 1451 | 2 | 31 | 30 | 30% | 10726.536
P1-041 | Wind coil B1----------->incl trial winding | 0 | 101584.64 | 101584.64 | 1 | 14 | 142 | 1451 | 2 | 42 | 30 | 30% | 30475.392
P1-041 | Wind coil B1----------->incl trial winding | 0 | 50124 | 50124 | 1 | 14 | 142 | 1451 | 2 | 42 | 30 | 30% | 15037.2
P1-050 | Instl Chl Plates,Tubing, Bag B1 (Station 2) | 0 | 35755.12 | 35755.12 | 1 | 14 | 142 | 1451 | 2 | 43 | 30 | 30% | 10726.536
P2-041 | Wind coil C6 (station 2) | 0 | 101726.88 | 101726.88 | 1 | 14 | 142 | 1451 | 2 | 54 | 30 | 30% | 30518.064
P2-050 | Instl Chl Plates,Tubing, Bag C6 (Station 2) | 0 | 36581.16 | 36581.16 | 1 | 14 | 142 | 1451 | 2 | 55 | 30 | 30% | 10974.348
P3-041 | Wind coil A3 (station 2) | 0 | 103931.52 | 103931.52 | 1 | 14 | 142 | 1451 | 2 | 67 | 30 | 30% | 31179.456
P3-050 | Instl Chl Plates,Tubing, Bag A3 Station 2) | 0 | 36581.16 | 36581.16 | 1 | 14 | 142 | 1451 | 2 | 68 | 30 | 30% | 10974.348
P1-071 | Wind coil A5 (station 2)@15% | 0 | 88375.98 | 88375.98 | 1 | 14 | 142 | 1451 | 2 | 75 | 45 | 45% | 39769.191
P1-080 | Instl Chl Plates,Tubing,Bag A5(Station 2)@15% | 0 | 31111.08 | 31111.08 | 1 | 14 | 142 | 1451 | 2 | 76 | 45 | 45% | 13999.986
P2-071 | Wind coil B3 (station 2)@15% | 0 | 88375.98 | 88375.98 | 1 | 14 | 142 | 1451 | 2 | 77 | 45 | 45% | 39769.191
P2-080 | Instl Chill Plates,Tubing,Bag B3 (Station 2)@15% | 0 | 31111.08 | 31111.08 | 1 | 14 | 142 | 1451 | 2 | 78 | 45 | 45% | 13999.986
P3-071 | Wind coil B5 (station 2)@15% | 0 | 88603.46 | 88603.46 | 1 | 14 | 142 | 1451 | 2 | 87 | 45 | 45% | 39871.557
P3-080 | Instl Chill Plates,Tubing,Bag B5 Station 2)@15% | 0 | 32232.2 | 32232.2 | 1 | 14 | 142 | 1451 | 2 | 88 | 45 | 45% | 14504.49
P1-101 | Wind coil C-2(station 3) | 0 | 101584.64 | 101584.64 | 1 | 14 | 142 | 1451 | 3 | 11 | 30 | 30% | 30475.392
P1-110 | Instl Chill Plates,Tubing, Bag C2 (Station 3) | 0 | 35755.12 | 35755.12 | 1 | 14 | 142 | 1451 | 3 | 12 | 30 | 30% | 10726.536
P2-101 | Wind coil C-3 (station3) | 0 | 101584.64 | 101584.64 | 1 | 14 | 142 | 1451 | 3 | 23 | 30 | 30% | 30475.392
P2-110 | Instl Chill Plates,Tubing, Bag C3(Station 3) | 0 | 35755.12 | 35755.12 | 1 | 14 | 142 | 1451 | 3 | 24 | 30 | 30% | 10726.536
P3-101 | Wind coil C4 (station 3) | 0 | 101584.64 | 101584.64 | 1 | 14 | 142 | 1451 | 3 | 36 | 30 | 30% | 30475.392
P3-110 | Instl Chill Plates,Tubing, Bag C4 (Station 3) | 0 | 35755.12 | 35755.12 | 1 | 14 | 142 | 1451 | 3 | 37 | 30 | 30% | 10726.536
P1-131 | Wind coil C5 (station 3 | 0 | 101584.64 | 101584.64 | 1 | 14 | 142 | 1451 | 3 | 48 | 30 | 30% | 30475.392
P1-140 | Instl Chl Plates,Tubing, Bag C5 Station 3) | 0 | 35755.12 | 35755.12 | 1 | 14 | 142 | 1451 | 3 | 49 | 30 | 30% | 10726.536
P2-131 | Wind coil B2 (station3) | 0 | 102011.35 | 102011.35 | 1 | 14 | 142 | 1451 | 3 | 61 | 30 | 30% | 30603.405
P2-140 | Instl Chl Plates,Tubing, Bag B2 (Station 3) | 0 | 36581.16 | 36581.16 | 1 | 14 | 142 | 1451 | 3 | 62 | 30 | 30% | 10974.348
P3-131 | Wind coil A4 (station 3) | 0 | 103931.52 | 103931.52 | 1 | 14 | 142 | 1451 | 3 | 73 | 30 | 30% | 31179.456
P3-140 | Instl Chl Plates,Tubing, Bag A4 (Station 3) | 0 | 36581.16 | 36581.16 | 1 | 14 | 142 | 1451 | 3 | 74 | 30 | 30% | 10974.348
P1-161 | Wind coil A6 (station 3)@15% | 0 | 88375.98 | 88375.98 | 1 | 14 | 142 | 1451 | 3 | 75 | 45 | 45% | 39769.191
P1-170 | Instl Chill Plates,Tubing,Bag A6Station 3)@15% | 0 | 31111.08 | 31111.08 | 1 | 14 | 142 | 1451 | 3 | 76 | 45 | 45% | 13999.986
P2-161 | Wind coil B4 (station 3)@15% | 0 | 88375.98 | 88375.98 | 1 | 14 | 142 | 1451 | 3 | 77 | 45 | 45% | 39769.191
P2-170 | Instl Chill Plates,Tubing,Bag B4Station3)@15% | 0 | 31111.08 | 31111.08 | 1 | 14 | 142 | 1451 | 3 | 78 | 45 | 45% | 13999.986
P3-161 | Wind coil B6 (station 3)@15% | 0 | 89437.55 | 89437.55 | 1 | 14 | 142 | 1451 | 3 | 80 | 45 | 45% | 40246.8975
P3-170 | Instl Chill Plates,Tubing,Bag B6Station3)@15% | 0 | 32232.2 | 32232.2 | 1 | 14 | 142 | 1451 | 3 | 81 | 45 | 45% | 14504.49
P1-021V | VPI (Station 5) C1 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 04 | 30 | 30% | 8220.336
P1-111V | VPI (Station 5) C2 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 13 | 30 | 30% | 8220.336
P2-021V | VPI (Station 5) A1 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 19 | 30 | 30% | 8220.336
P2-111V | VPI (Station 5) C3 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 25 | 30 | 30% | 8220.336
P3-021V | VPI (Station 5) A2 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 32 | 30 | 30% | 8220.336
P3-111V | VPI (Station 5) C4 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 38 | 30 | 30% | 8220.336
P1-051V | VPI (Station 5) B1 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 44 | 30 | 30% | 8220.336
P1-141V | VPI (Station 5) C5 | 0 | 27401.12 | 27401.12 | 1 | 14 | 142 | 1451 | 5 | 50 | 30 | 30% | 8220.336
P2-051V | VPI (Station 5) C6 | 0 | 28034.16 | 28034.16 | 1 | 14 | 142 | 1451 | 5 | 56 | 30 | 30% | 8410.248
P2-141V | VPI (Station 5) B2 | 0 | 28034.16 | 28034.16 | 1 | 14 | 142 | 1451 | 5 | 63 | 30 | 30% | 8410.248
P3-051V | VPI (Station 5) A3 | 0 | 28034.16 | 28034.16 | 1 | 14 | 142 | 1451 | 5 | 69 | 30 | 30% | 8410.248
P3-141V | VPI (Station 5) A4 | 0 | 28034.16 | 28034.16 | 1 | 14 | 142 | 1451 | 5 | 75 | 30 | 30% | 8410.248
P1-081V | VPI (Station 5) A5 @15% learning curve | 0 | 23846.13 | 23846.13 | 1 | 14 | 142 | 1451 | 5 | 77 | 45 | 45% | 10730.7585
P1-171V | VPI (Station 5) A6 @15% learning curve | 0 | 23846.13 | 23846.13 | 1 | 14 | 142 | 1451 | 5 | 78 | 45 | 45% | 10730.7585
P2-081V | VPI (Station 5) B3 @15% learning curve | 0 | 23846.13 | 23846.13 | 1 | 14 | 142 | 1451 | 5 | 79 | 45 | 45% | 10730.7585
P3-081V | VPI (Station 5) B4 @15% learning curve | 0 | 23846.13 | 23846.13 | 1 | 14 | 142 | 1451 | 5 | 80 | 45 | 45% | 10730.7585
P2-171V | VPI (Station 5) B5 @15% learning curve | 0 | 24705.45 | 24705.45 | 1 | 14 | 142 | 1451 | 5 | 81 | 45 | 45% | 11117.4525
P3-171V | VPI (Station 5) B6 @15% learning curve | 0 | 24705.45 | 24705.45 | 1 | 14 | 142 | 1451 | 5 | 82 | 45 | 45% | 11117.4525
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 14703.04 | 14703.04 | 1 | 14 | 142 | 1451 | 6 | 06 | 30 | 30% | 4410.912
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 6049.44 | 6049.44 | 1 | 14 | 142 | 1451 | 6 | 06 | 30 | 30% | 1814.832
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 2456.4 | 2456.4 | 1 | 14 | 142 | 1451 | 6 | 06 | 30 | 30% | 736.92
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 2768.64 | 2768.64 | 1 | 14 | 142 | 1451 | 6 | 06 | 30 | 30% | 830.592
P1-021 | Test Coil (Coil Test Stand) C1 | 0 | 5034.96 | 5034.96 | 1 | 14 | 142 | 1451 | 6 | 06 | 30 | 30% | 1510.488
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 14703.04 | 14703.04 | 1 | 14 | 142 | 1451 | 6 | 21 | 30 | 30% | 4410.912
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 6049.44 | 6049.44 | 1 | 14 | 142 | 1451 | 6 | 21 | 30 | 30% | 1814.832
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 2456.4 | 2456.4 | 1 | 14 | 142 | 1451 | 6 | 21 | 30 | 30% | 736.92
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 2768.64 | 2768.64 | 1 | 14 | 142 | 1451 | 6 | 21 | 30 | 30% | 830.592
P2-021 | Test Coil (Coil Test Stand) A1 | 0 | 5034.96 | 5034.96 | 1 | 14 | 142 | 1451 | 6 | 21 | 30 | 30% | 1510.488
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 14703.04 | 14703.04 | 1 | 14 | 142 | 1451 | 6 | 46 | 30 | 30% | 4410.912
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 6049.44 | 6049.44 | 1 | 14 | 142 | 1451 | 6 | 46 | 30 | 30% | 1814.832
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 2456.4 | 2456.4 | 1 | 14 | 142 | 1451 | 6 | 46 | 30 | 30% | 736.92
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 2768.64 | 2768.64 | 1 | 14 | 142 | 1451 | 6 | 46 | 30 | 30% | 830.592
P1-051 | Test Coil (Coil Test Stand) B1 | 0 | 5034.96 | 5034.96 | 1 | 14 | 142 | 1451 | 6 | 46 | 30 | 30% | 1510.488
P1-021C | Final Clamps & Warm Test (Station1) C1 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 05 | 30 | 30% | 3007.44
P1-111C | Final Clamps & Warm Test (Station1) C2 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 14 | 30 | 30% | 3007.44
P2-021C | Final Clamps & Warm Test (Station1) A1 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 20 | 30 | 30% | 3007.44
P2-111C | Final Clamps & Warm Test (Station1) C3 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 26 | 30 | 30% | 3007.44
P3-021C | Final Clamps & Warm Test (Station1) A2 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 33 | 30 | 30% | 3007.44
P3-111C | Final Clamps & Warm Test (Station1) C4 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 39 | 30 | 30% | 3007.44
P1-051C | Final Clamps & Warm Test (Station1) B1 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 45 | 30 | 30% | 3007.44
P1-141C | Final Clamps & Warm Test (Station1) C5 | 0 | 10024.8 | 10024.8 | 1 | 14 | 142 | 1451 | 7 | 51 | 30 | 30% | 3007.44
P2-051C | Final Clamps & Warm Test (Station1) C6 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 57 | 30 | 30% | 3076.92
P2-141C | Final Clamps & Warm Test (Station1) B2 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 64 | 30 | 30% | 3076.92
P3-051C | Final Clamps & Warm Test (Station1) A3 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 70 | 30 | 30% | 3076.92
P3-141C | Final Clamps & Warm Test (Station1) A4 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 76 | 30 | 30% | 3076.92
P1-081C | Final Clamps & Warm Test (Station1) A5 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 77 | 30 | 30% | 3076.92
P1-171C | Final Clamps & Warm Test (Station1) A6 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 78 | 30 | 30% | 3076.92
P2-081C | Final Clamps & Warm Test (Station1) B3 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 79 | 30 | 30% | 3076.92
P3-081C | Final Clamps & Warm Test (Station1) B4 | 0 | 10256.4 | 10256.4 | 1 | 14 | 142 | 1451 | 7 | 80 | 30 | 30% | 3076.92
P3-171C | Final Clamps & Warm Test (Station1) B5 | 0 | 10626 | 10626 | 1 | 14 | 142 | 1451 | 7 | 81 | 30 | 30% | 3187.8
P2-171C | Final Clamps & Warm Test (Station1) B6 | 0 | 10626 | 10626 | 1 | 14 | 142 | 1451 | 7 | 82 | 30 | 30% | 3187.8
171-040 | Winding Oversight (LOE) | 0 | 594212.24 | 594212.24 | 1 | 14 | 142 | 1451 | LABR | 11 | 30 | 30% | 178263.672
171-040 | Winding Oversight (LOE) | 0 | 337587.29 | 337587.29 | 1 | 14 | 142 | 1451 | LABR | 11 | 30 | 30% | 101276.187
171-041 | Tech Supervision | 0 | 343901.41 | 343901.41 | 1 | 14 | 142 | 1451 | LABR | 13 | 30 | 30% | 103170.423
TITLE3W | Titel III Design-CASTING FAB & WINDING | 0 | 153013.08 | 153013.08 | 1 | 14 | 142 | 1451 | LABR | 20 | 30 | 30% | 45903.924
TITLE3W | Titel III Design-CASTING FAB & WINDING | 0 | 42935.78 | 42935.78 | 1 | 14 | 142 | 1451 | LABR | 20 | 30 | 30% | 12880.734
1501-FY05 | Prelim Design Structures | 0 | 34511.16 | 34511.16 | 1 | 15 | 151 | 1501 |  | 01 | 32 | 32% | 11043.5712
1501-FY05 | Prelim Design Structures | 0 | 34511.16 | 34511.16 | 1 | 15 | 151 | 1501 |  | 01 | 32 | 32% | 11043.5712
1501-FY05 | Prelim Design Structures | 0 | 24414.81 | 24414.81 | 1 | 15 | 151 | 1501 |  | 01 | 32 | 32% | 7812.7392
1501-FD | Final Design Structures | 0 | 34511.16 | 34511.16 | 1 | 15 | 151 | 1501 |  | 03 | 32 | 32% | 11043.5712
1501-FD | Final Design Structures | 0 | 34511.16 | 34511.16 | 1 | 15 | 151 | 1501 |  | 03 | 32 | 32% | 11043.5712
1501-FD | Final Design Structures | 0 | 24414.81 | 24414.81 | 1 | 15 | 151 | 1501 |  | 03 | 32 | 32% | 7812.7392
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 3490.43 | 3490.43 | 1 | 15 | 151 | 1550 |  | 17 | 20 | 20% | 698.086
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 1445.49 | 1445.49 | 1 | 15 | 151 | 1550 |  | 17 | 20 | 20% | 289.098
153.037 | WBS 153 Support Structure I&C Procurement/Fab | 0 | 4103.15 | 4103.15 | 1 | 15 | 151 | 1550 |  | 17 | 20 | 20% | 820.63
153.015 | Title III design WBS 153 localI&C | 0 | 963.66 | 963.66 | 1 | 15 | 151 | 1550 |  | 18 | 20 | 20% | 192.732
162-037 | WBS 151Coil Support Assy Procurement [A/1] | 0 | 692546.18 | 692546.18 | 1 | 15 | 151 | 1550 |  | 15 | 32 | 32% | 221614.7776
162-037 | WBS 151Coil Support Assy Procurement [A/1] | 0 | 3634.25 | 3634.25 | 1 | 15 | 151 | 1550 |  | 15 | 32 | 32% | 1162.96
162-037 | WBS 151Coil Support Assy Procurement [A/1] | 0 | 324678.02 | 324678.02 | 1 | 15 | 151 | 1550 |  | 15 | 32 | 32% | 103896.9664
162-031 | Title III engr WBS 151 | 0 | 135249.95 | 135249.95 | 1 | 15 | 151 | 1550 |  | 16 | 32 | 32% | 43279.984
162-031 | Title III engr WBS 151 | 0 | 25363.61 | 25363.61 | 1 | 15 | 151 | 1550 |  | 16 | 32 | 32% | 8116.3552
151-001 | Title I design WBS 171 cryostat | 58713.72 | 78284.96 | 19571.24 | 1 | 17 | 171 | 1701 |  | 12 | 28 | 28% | 5479.9472
151-001 | Title I design WBS 171 cryostat | 35573.535 | 47431.38 | 11857.845 | 1 | 17 | 171 | 1701 |  | 12 | 28 | 28% | 3320.1966
151-011 | Final Design Cryostat WBS 171 | 0 | 179564.48 | 179564.48 | 1 | 17 | 171 | 1701 |  | 18 | 28 | 28% | 50278.0544
151-011 | Final Design Cryostat WBS 171 | 0 | 68983.69 | 68983.69 | 1 | 17 | 171 | 1701 |  | 18 | 28 | 28% | 19315.4332
161-001 | Title I design WBS 172 base support struct | 14729.191 | 17328.46 | 2599.269 | 1 | 17 | 172 | 1701 |  | 14 | 32 | 32% | 831.7661
161-001 | Title I design WBS 172 base support struct | 27544.114 | 32404.84 | 4860.726 | 1 | 17 | 172 | 1701 |  | 14 | 32 | 32% | 1555.4323
161-011 | Final Design Base Support Structure WBS 172 | 0 | 28857.44 | 28857.44 | 1 | 17 | 172 | 1701 |  | 16 | 32 | 32% | 9234.3808
161-011 | Final Design Base Support Structure WBS 172 | 0 | 33367.35 | 33367.35 | 1 | 17 | 172 | 1701 |  | 16 | 32 | 32% | 10677.552
151-031 | Title III engr | 0 | 6498.08 | 6498.08 | 1 | 17 | 171 | 1751 | 171 | 19 | 28 | 28% | 1819.4624
151-031 | Title III engr | 0 | 26585.05 | 26585.05 | 1 | 17 | 171 | 1751 | 171 | 19 | 28 | 28% | 7443.814
151-037 | Cryostat Procurement [A/1] | 0 | 504725.76 | 504725.76 | 1 | 17 | 171 | 1751 | 171 | 20 | 28 | 28% | 141323.2128
151-037 | Cryostat Procurement [A/1] | 0 | 3696 | 3696 | 1 | 17 | 171 | 1751 | 171 | 20 | 28 | 28% | 1034.88
161-031 | Title III engr WBS 172 | 0 | 11232.73 | 11232.73 | 1 | 17 | 172 | 1752 | 172 | 19 | 32 | 32% | 3594.4736
161-037 | Machine Base&supports Procurement [A/1] | 0 | 300171.05 | 300171.05 | 1 | 17 | 172 | 1752 | 172 | 20 | 32 | 32% | 96054.736
161-037 | Machine Base&supports Procurement [A/1] | 0 | 3656.04 | 3656.04 | 1 | 17 | 172 | 1752 | 172 | 20 | 32 | 32% | 1169.9328
181.210 | HP Coverage in the TFTR TC LOE FY05 | 53796.366 | 136539 | 82742.634 | 1 | 18 | 181 | 1802 | A | 20 | 24 | 24% | 19858.2322
181.222 | HP Coverage in the TFTR TC LOE FY06 | 0 | 151697.99 | 151697.99 | 1 | 18 | 181 | 1802 | A | 21 | 24 | 24% | 36407.5176
181.220 | HP Coverage in the TFTR TC LOE FY07 | 0 | 155203.36 | 155203.36 | 1 | 18 | 181 | 1802 | A | 30 | 24 | 24% | 37248.8064
181.221 | HP Coverage in the TFTR TC LOE FY08 | 0 | 160771 | 160771 | 1 | 18 | 181 | 1802 | A | 32 | 24 | 24% | 38585.04
181.110 | PPPL EM LOE FY05 | 3792.3288 | 9625.2 | 5832.8712 | 1 | 18 | 181 | 1802 | A | 40 | 24 | 24% | 1399.8891
181.120 | PPPL EM LOE FY06 | 0 | 116541.57 | 116541.57 | 1 | 18 | 181 | 1802 | A | 41 | 24 | 24% | 27969.9768
181.121 | PPPL EM LOE FY07 | 0 | 269898.66 | 269898.66 | 1 | 18 | 181 | 1802 | A | 42 | 24 | 24% | 64775.6784
181.122 | PPPL EM LOE FY08 | 0 | 279624.87 | 279624.87 | 1 | 18 | 181 | 1802 | A | 43 | 24 | 24% | 67109.9688
1803-1.02 | VV Support Fixture - model design& drawing detai | 661 | 1322 | 661 | 1 | 18 | 186 | 1803 | 1.00 | 15 | 20 | 20% | 132.2
1803-1.02 | VV Support Fixture - model design& drawing detai | 6141 | 12282 | 6141 | 1 | 18 | 186 | 1803 | 1.00 | 15 | 20 | 20% | 1228.2
1803-1.04 | Metrology -sightline layout metrology support | 0 | 13220 | 13220 | 1 | 18 | 186 | 1803 | 1.00 | 25 | 20 | 20% | 2644
1803-1.04 | Metrology -sightline layout metrology support | 0 | 12282 | 12282 | 1 | 18 | 186 | 1803 | 1.00 | 25 | 20 | 20% | 2456.4
1803-1.05 | Structural / Seismic Analysis check | 2644 | 13220 | 10576 | 1 | 18 | 186 | 1803 | 1.00 | 30 | 20 | 20% | 2115.2
1803-1.06 | Design review PDR VV Prep Station | 0 | 1983 | 1983 | 1 | 18 | 186 | 1803 | 1.00 | 40 | 20 | 20% | 396.6
1803-1.09 | Safety Review documentation / presentation | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 1.00 | 45 | 20 | 20% | 528.8
1803-1.061 | Design review FDR VV Prep Station | 0 | 1983 | 1983 | 1 | 18 | 186 | 1803 | 1.00 | 50 | 20 | 20% | 396.6
1803-1.07 | Design check and sign-off | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 1.00 | 55 | 20 | 20% | 528.8
1803-1.07 | Design check and sign-off | 0 | 818.8 | 818.8 | 1 | 18 | 186 | 1803 | 1.00 | 55 | 20 | 20% | 163.76
1803-1.10 | Fab / Design Review - follow-up activities | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 1.00 | 60 | 20 | 20% | 528.8
1803-1.10 | Fab / Design Review - follow-up activities | 0 | 4094 | 4094 | 1 | 18 | 186 | 1803 | 1.00 | 60 | 20 | 20% | 818.8
1803-1.08 | Prep & Issue Spec,dwgs,and requisition | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 1.00 | 65 | 20 | 20% | 528.8
1803-1.12 | FAB - VV support Fixture | 0 | 14790 | 14790 | 1 | 18 | 186 | 1803 | 1.00 | 75 | 20 | 20% | 2958
1803-1.13 | FAB VV Prep Station Platform | 0 | 7395 | 7395 | 1 | 18 | 186 | 1803 | 1.00 | 80 | 20 | 20% | 1479
1803-1.14 | FAB VV Prep Station metrology stands | 0 | 7395 | 7395 | 1 | 18 | 186 | 1803 | 1.00 | 80 | 20 | 20% | 1479
1803-2.02 | MC Holding Fixture 1 - model design and drawing | 661 | 1322 | 661 | 1 | 18 | 186 | 1803 | 2.00 | 11 | 20 | 20% | 132.2
1803-2.02 | MC Holding Fixture 1 - model design and drawing | 3070.5 | 6141 | 3070.5 | 1 | 18 | 186 | 1803 | 2.00 | 11 | 20 | 20% | 614.1
1803-2.03 | MC Assembly Fixture 2- design & drawing details | 0 | 1983 | 1983 | 1 | 18 | 186 | 1803 | 2.00 | 12 | 20 | 20% | 396.6
1803-2.03 | MC Assembly Fixture 2- design & drawing details | 0 | 12282 | 12282 | 1 | 18 | 186 | 1803 | 2.00 | 12 | 20 | 20% | 2456.4
1803-2.04 | Metrology - sightline layout design details metr | 0 | 9915 | 9915 | 1 | 18 | 186 | 1803 | 2.00 | 13 | 20 | 20% | 1983
1803-2.04 | Metrology - sightline layout design details metr | 0 | 8188 | 8188 | 1 | 18 | 186 | 1803 | 2.00 | 13 | 20 | 20% | 1637.6
1803-2.05 | Structural / Seismic Analysis check | 0 | 0 | 0 | 1 | 18 | 186 | 1803 | 2.00 | 14 | 20 | 20% | 0
1803-2.05 | Structural / Seismic Analysis check | 0 | 13220 | 13220 | 1 | 18 | 186 | 1803 | 2.00 | 14 | 20 | 20% | 2644
1803-2.06 | PDR Half Period Assy | 0 | 1983 | 1983 | 1 | 18 | 186 | 1803 | 2.00 | 20 | 20 | 20% | 396.6
1803-2.09 | Safety Review documentation / presentation | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 2.00 | 25 | 20 | 20% | 528.8
1803-2.061 | FDR Half Period Assy | 0 | 1983 | 1983 | 1 | 18 | 186 | 1803 | 2.00 | 30 | 20 | 20% | 396.6
1803-2.10 | Fab / Design Review - follow-up activities | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 2.00 | 35 | 20 | 20% | 528.8
1803-2.10 | Fab / Design Review - follow-up activities | 0 | 4094 | 4094 | 1 | 18 | 186 | 1803 | 2.00 | 35 | 20 | 20% | 818.8
1803-2.07 | Design check and sign-off | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 2.00 | 40 | 20 | 20% | 528.8
1803-2.07 | Design check and sign-off | 0 | 818.8 | 818.8 | 1 | 18 | 186 | 1803 | 2.00 | 40 | 20 | 20% | 163.76
1803-2.08 | Procurement Lead Time and Award | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 2.00 | 45 | 20 | 20% | 528.8
1803-2.11 | Fab MC HP Assy Fixtures (2) | 0 | 29580 | 29580 | 1 | 18 | 186 | 1803 | 2.00 | 50 | 20 | 20% | 5916
1803-2.12 | Fab MC MC HP Assy Metrology support stands (2) | 0 | 14790 | 14790 | 1 | 18 | 186 | 1803 | 2.00 | 50 | 20 | 20% | 2958
1803-3.15 | Vendor Design MC Turning fixture & Base | 0 | 68314.62 | 68314.62 | 1 | 18 | 186 | 1803 | 3.00 | 80 | 100 | 100% | 68314.62
1803-3.15C | Fabricate - MC Turning fixture & Base | 0 | 295800 | 295800 | 1 | 18 | 186 | 1803 | 3.00 | 83 | 100 | 100% | 295800
1803-3.15A | Fabricate - MC Gantry Crane | 0 | 73950 | 73950 | 1 | 18 | 186 | 1803 | 3.00 | 84 | 100 | 100% | 73950
1803-3.16 | FAB - VV suprt stand & misc crane fixtures | 0 | 22185 | 22185 | 1 | 18 | 186 | 1803 | 3.00 | 89 | 100 | 100% | 22185
1803-3.16A | FAB -Platform | 0 | 14790 | 14790 | 1 | 18 | 186 | 1803 | 3.00 | 90 | 100 | 100% | 14790
1803-3.16B | FAB -MC Installation Metrology sprt stands | 0 | 7395 | 7395 | 1 | 18 | 186 | 1803 | 3.00 | 90 | 100 | 100% | 7395
1803-3.04 | VV support stand - model design and drawing deta | 561.85 | 661 | 99.15 | 1 | 18 | 186 | 1803 | 3.00 | 25 | 40 | 40% | 39.66
1803-3.04 | VV support stand - model design and drawing deta | 6959.8 | 8188 | 1228.2 | 1 | 18 | 186 | 1803 | 3.00 | 25 | 40 | 40% | 491.28
1803-3.05 | Platform - design and drawing details | 0 | 991.5 | 991.5 | 1 | 18 | 186 | 1803 | 3.00 | 30 | 40 | 40% | 396.6
1803-3.05 | Platform - design and drawing details | 0 | 8188 | 8188 | 1 | 18 | 186 | 1803 | 3.00 | 30 | 40 | 40% | 3275.2
1803-3.06 | Metrology - sightline layout design details metr | 0 | 6610 | 6610 | 1 | 18 | 186 | 1803 | 3.00 | 35 | 40 | 40% | 2644
1803-3.06 | Metrology - sightline layout design details metr | 0 | 8188 | 8188 | 1 | 18 | 186 | 1803 | 3.00 | 35 | 40 | 40% | 3275.2
1803-3.082 | * PDR * Turning Fixture,base&gantry crane | 0 | 991.5 | 991.5 | 1 | 18 | 186 | 1803 | 3.00 | 60 | 40 | 40% | 396.6
1803-3.083 | * FDR * Turning Fixture,base&gantry crane | 0 | 991.5 | 991.5 | 1 | 18 | 186 | 1803 | 3.00 | 65 | 40 | 40% | 396.6
1803-3.09 | Design check and sign-off | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 3.00 | 70 | 40 | 40% | 1057.6
1803-3.09 | Design check and sign-off | 0 | 818.8 | 818.8 | 1 | 18 | 186 | 1803 | 3.00 | 70 | 40 | 40% | 327.52
1803-3.10 | Procurement lead time turning fixt,base&gantry | 0 | 9915 | 9915 | 1 | 18 | 186 | 1803 | 3.00 | 75 | 40 | 40% | 3966
1803-3.07 | Structural / Seismic Analysis check | 0 | 29371.2 | 29371.2 | 1 | 18 | 186 | 1803 | 3.00 | 82 | 40 | 40% | 11748.48
1803-3.08 | ** PDR ** Platform & Support Stands | 0 | 991.5 | 991.5 | 1 | 18 | 186 | 1803 | 3.00 | 85 | 40 | 40% | 396.6
1803-3.12 | Safety Review documentation / presentation | 0 | 2644 | 2644 | 1 | 18 | 186 | 1803 | 3.00 | 85 | 40 | 40% | 1057.6
1803-3.081 | ** FDR ** Platform & Support Stands | 0 | 991.5 | 991.5 | 1 | 18 | 186 | 1803 | 3.00 | 86 | 40 | 40% | 396.6
1803-3.101 | Procurement lead time platforms & supports | 0 | 9915 | 9915 | 1 | 18 | 186 | 1803 | 3.00 | 88 | 40 | 40% | 3966
1803-3.11 | Procurement Technical Rep | 0 | 26629.66 | 26629.66 | 1 | 18 | 186 | 1803 | 3.00 | 95 | 40 | 40% | 10651.864
1803-3.13 | Fabrication - follow-up activities | 0 | 7007.81 | 7007.81 | 1 | 18 | 186 | 1803 | 3.00 | 98 | 40 | 40% | 2803.124
1803-3.13 | Fabrication - follow-up activities | 0 | 4340.46 | 4340.46 | 1 | 18 | 186 | 1803 | 3.00 | 98 | 40 | 40% | 1736.184
1803-4.13 | FAB-MC Support Stands (2) | 0 | 13850 | 13850 | 1 | 18 | 186 | 1803 | 4.00 | 20 | 100 | 100% | 13850
1803-4.14 | Fab -TF HP support and turning fixture (2) | 0 | 10387.5 | 10387.5 | 1 | 18 | 186 | 1803 | 4.00 | 20 | 100 | 100% | 10387.5
1803-4.15 | FAB-FP Assy platforms (2) | 0 | 41550 | 41550 | 1 | 18 | 186 | 1803 | 4.00 | 20 | 100 | 100% | 41550
1803-4.16 | FAB-MC Temporary End Supports (2) | 0 | 13850 | 13850 | 1 | 18 | 186 | 1803 | 4.00 | 20 | 100 | 100% | 13850
1803-4.17 | FAB-Final FP Assy Metrology suprt stands (2) | 0 | 13850 | 13850 | 1 | 18 | 186 | 1803 | 4.00 | 20 | 100 | 100% | 13850
1803-4.18 | FAB-VV Port alignment/weldment fixtures (2) | 0 | 13850 | 13850 | 1 | 18 | 186 | 1803 | 4.00 | 20 | 100 | 100% | 13850
1803-4.01 | Concept definition and requirements | 0 | 7342.8 | 7342.8 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 2937.12
1803-4.01 | Concept definition and requirements | 0 | 4548 | 4548 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 1819.2
1803-4.02 | MC Support Stand - model design and drawing deta | 0 | 2202.84 | 2202.84 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 881.136
1803-4.02 | MC Support Stand - model design and drawing deta | 0 | 13644 | 13644 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 5457.6
1803-4.03 | TF HP support turning fixture - model design d | 0 | 2202.84 | 2202.84 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 881.136
1803-4.03 | TF HP support turning fixture - model design d | 0 | 13644 | 13644 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 5457.6
1803-4.04 | FP Assembly platform - model design drawing det | 0 | 2202.84 | 2202.84 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 881.136
1803-4.04 | FP Assembly platform - model design drawing det | 0 | 13644 | 13644 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 5457.6
1803-4.05 | VV Port Alignment/Weldment Fixture - design and | 0 | 2202.84 | 2202.84 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 881.136
1803-4.05 | VV Port Alignment/Weldment Fixture - design and | 0 | 13644 | 13644 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 5457.6
1803-4.06 | Metrology - sightline layout design details metr | 0 | 1468.56 | 1468.56 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 587.424
1803-4.06 | Metrology - sightline layout design details metr | 0 | 9096 | 9096 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 3638.4
1803-4.07 | Structural / Seismic Analysis check | 0 | 14685.6 | 14685.6 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 5874.24
1803-4.08 | PDR Final FP Assy | 0 | 1468.56 | 1468.56 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 587.424
1803-4.081 | FDR Final FP Assy | 0 | 1468.56 | 1468.56 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 587.424
1803-4.09 | Design check and sign-off | 0 | 2937.12 | 2937.12 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 1174.848
1803-4.09 | Design check and sign-off | 0 | 909.6 | 909.6 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 363.84
1803-4.11 | Safety Review documentation / presentation | 0 | 2937.12 | 2937.12 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 1174.848
1803-4.12 | Fabrication - follow-up activities | 0 | 3005.12 | 3005.12 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 1202.048
1803-4.12 | Fabrication - follow-up activities | 0 | 4653.2 | 4653.2 | 1 | 18 | 186 | 1803 | 4.00 | 17 | 40 | 40% | 1861.28
1803-4.10 | Procurement lead time | 0 | 4420.52 | 4420.52 | 1 | 18 | 186 | 1803 | 4.00 | 19 | 40 | 40% | 1768.208
1803-5.009 | Fabricate TF HP Assembly (1) | 0 | 44370 | 44370 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 100 | 100% | 44370
1803-5.001 | Concept definition and requirements | 0 | 6610 | 6610 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 2644
1803-5.001 | Concept definition and requirements | 0 | 4094 | 4094 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 1637.6
1803-5.002 | TF Rotation Fixture plus dwgs | 0 | 6610 | 6610 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 2644
1803-5.002 | TF Rotation Fixture plus dwgs | 0 | 36846 | 36846 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 14738.4
1803-5.003 | Metrology layout/support stand dwgs | 0 | 1322 | 1322 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 528.8
1803-5.003 | Metrology layout/support stand dwgs | 0 | 8188 | 8188 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 3275.2
1803-5.004 | Structural Analysis | 0 | 13220 | 13220 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 5288
1803-5.005 | PDR | 0 | 1322 | 1322 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 528.8
1803-5.006 | FDR | 0 | 1322 | 1322 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 528.8
1803-5.008 | Procurement Lead Time | 0 | 4405.68 | 4405.68 | 1 | 18 | 186 | 1803 | 5.00 | 17 | 40 | 40% | 1762.272
1803-5.01 | Finalize TFTR test cell FPA assembly layout draw | 0 | 6610 | 6610 | 1 | 18 | 186 | 1803 | 6.00 | 17 | 40 | 40% | 2644
1803-5.01 | Finalize TFTR test cell FPA assembly layout draw | 0 | 2456.4 | 2456.4 | 1 | 18 | 186 | 1803 | 6.00 | 17 | 40 | 40% | 982.56
1803-5.02 | Establish an assembly interface requirements doc | 0 | 6610 | 6610 | 1 | 18 | 186 | 1803 | 6.00 | 17 | 40 | 40% | 2644
1803-5.03 | Develop test components as needed to qualify ass | 0 | 6610 | 6610 | 1 | 18 | 186 | 1803 | 6.00 | 17 | 40 | 40% | 2644
1803-5.03 | Develop test components as needed to qualify ass | 0 | 13220 | 13220 | 1 | 18 | 186 | 1803 | 6.00 | 17 | 40 | 40% | 5288
1803-5.03 | Develop test components as needed to qualify ass | 0 | 12282 | 12282 | 1 | 18 | 186 | 1803 | 6.00 | 17 | 40 | 40% | 4912.8
1803-5.03 | Develop test components as needed to qualify ass | 0 | 19215 | 19215 | 1 | 18 | 186 | 1803 | 6.00 | 17 | 40 | 40% | 7686
1803-7.01 | Meetings Prep and Reporting | 19102.7347 | 56350.25 | 37247.5152 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 14899.0061
1803-7.01 | Meetings Prep and Reporting | 8257.8027 | 24359.3 | 16101.4973 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 6440.5989
1803-7.01 | Meetings Prep and Reporting | 6592.3635 | 19446.5 | 12854.1365 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 5141.6546
1803-7.01 | Meetings Prep and Reporting | 4705.659 | 13881 | 9175.341 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 3670.1364
1803-7.02 | Develop and maintain concept definition document | 3361.185 | 9915 | 6553.815 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 2621.526
1803-7.03 | Develop and maintain assembly plan document | 4481.58 | 13220 | 8738.42 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 3495.368
1803-7.04 | Mike Cole's FY05 on-site involvement in assembly | 0 | 0 | 0 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 0
1803-7.04 | Mike Cole's FY05 on-site involvement in assembly | 8407.2 | 24800 | 16392.8 | 1 | 18 | 186 | 1803 | 7.00 | 17 | 40 | 40% | 6557.12
713A.040 | General procurements | 0 | 10473.75 | 10473.75 | 1 | 18 | 186 | 1803 | TOOL | 11 | 40 | 40% | 4189.5
713A.050 | Welding tools, materials & equipt | 0 | 10473.75 | 10473.75 | 1 | 18 | 186 | 1803 | TOOL | 12 | 40 | 40% | 4189.5
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 1878.2 | 1878.2 | 1 | 18 | 186 | 1803 | TOOL | 14 | 40 | 40% | 751.28
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 4817.6 | 4817.6 | 1 | 18 | 186 | 1803 | TOOL | 14 | 40 | 40% | 1927.04
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 20512.8 | 20512.8 | 1 | 18 | 186 | 1803 | TOOL | 14 | 40 | 40% | 8205.12
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 9306.4 | 9306.4 | 1 | 18 | 186 | 1803 | TOOL | 14 | 40 | 40% | 3722.56
713A.060 | Instl He gas piping from NSTX to D-site tc | 0 | 7756 | 7756 | 1 | 18 | 186 | 1803 | TOOL | 14 | 40 | 40% | 3102.4
740.020 | Facility Prep | 0 | 19776.96 | 19776.96 | 1 | 18 | 187 | 1804 | MEAS | 20 | 24 | 24% | 4746.4704
740.020 | Facility Prep | 0 | 32747.68 | 32747.68 | 1 | 18 | 187 | 1804 | MEAS | 20 | 24 | 24% | 7859.4432
740.020 | Facility Prep | 0 | 10872 | 10872 | 1 | 18 | 187 | 1804 | MEAS | 20 | 24 | 24% | 2609.28
740.100 | Romer CMM- spare probes | 0 | 4437 | 4437 | 1 | 18 | 187 | 1804 | MEAS | 24 | 24 | 24% | 1064.88
740.105 | Romer CMM-Software support & warranty renewal | 0 | 45633.14 | 45633.14 | 1 | 18 | 187 | 1804 | MEAS | 24 | 24 | 24% | 10951.9536
740.110 | Romer CMM-Laptop for 2nd arm | 0 | 5916 | 5916 | 1 | 18 | 187 | 1804 | MEAS | 24 | 24 | 24% | 1419.84
740.130 | Misc hand tools calibration and spare laptop | 0 | 9982.25 | 9982.25 | 1 | 18 | 187 | 1804 | MEAS | 30 | 24 | 24% | 2395.74
740.135 | Gary Puhl subcontract for TRC analysis | 0 | 12810 | 12810 | 1 | 18 | 187 | 1804 | MEAS | 30 | 24 | 24% | 3074.4
1803-8 | Metrology Support (moved from 1803) | 34284.087 | 101133 | 66848.913 | 1 | 18 | 187 | 1804 | MEAS | 17 | 40 | 40% | 26739.5652
S0P0-100 | Clearout realestate&setup fixturing crane supprt | 0 | 35469.1 | 35469.1 | 1 | 18 | 182 | 1810 | S0P0 |  | 40 | 40% | 14187.64 | 2170190.03 | 964263.7265 | 44.43%
S1P1-101 | Receive VV and inspect | 0 | 8019.84 | 8019.84 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 3207.936
S1P1-102 | Mount VV on VV Prep fixture (top side up) | 0 | 1002.48 | 1002.48 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 400.992
S1P1-103 | Establish metrology setting; align VV base | 0 | 6014.88 | 6014.88 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 2405.952
S1P1-106 | Attach studs for coolant lines,insulation on top | 0 | 16039.68 | 16039.68 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 6415.872
S1P1-107 | Wind magnetic diagnostic sensors to top surface | 0 | 16039.68 | 16039.68 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 6415.872
S1P1-108 | Install cooling/htg lines to vac vsl top surface | 0 | 21386.24 | 21386.24 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 8554.496
S1P1-109 | Install insulation to vac vsl to top surface | 0 | 33416 | 33416 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 13366.4
S1P1-110 | Flip VV to expose lower surface | 0 | 2004.96 | 2004.96 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 801.984
S1P1-112 | Attach studs for coolant lines, insulation bott | 0 | 16039.68 | 16039.68 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 6415.872
S1P1-113 | Wind magnetic diagnostic sensors to bot surface | 0 | 16039.68 | 16039.68 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 6415.872
S1P1-114 | Install cooling/htg lines to vac vsl bot surface | 0 | 21386.24 | 21386.24 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 8554.496
S1P1-115 | Install insulation to vac vsl to bot surface | 0 | 33416 | 33416 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 13366.4
S1P1-116 | Prepare and transfer completed VV to holding are | 0 | 6014.88 | 6014.88 | 1 | 18 | 185 | 1810 | S1P1 |  | 40 | 40% | 2405.952
S1P2-101 | Receive VV and inspect | 0 | 8205.12 | 8205.12 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 3282.048
S1P2-102 | Mount VV on VV Prep fixture (top side up) | 0 | 1025.64 | 1025.64 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 410.256
S1P2-103 | Establish metrology setting; align VV base | 0 | 6153.84 | 6153.84 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 2461.536
S1P2-106 | Attach studs forcoolant lines,insulation on top | 0 | 16410.24 | 16410.24 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 6564.096
S1P2-107 | Wind magnetic diagnostic sensors to top surface | 0 | 16410.24 | 16410.24 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 6564.096
S1P2-108 | Install cooling/htg lines to vac vsl top surface | 0 | 21880.32 | 21880.32 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 8752.128
S1P2-109 | Install insulation to vac vsl to top surface | 0 | 34188 | 34188 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 13675.2
S1P2-110 | Flip VV to expose lower surface | 0 | 2051.28 | 2051.28 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 820.512
S1P2-112 | Attach studs for coolant lines, insulation bott | 0 | 16410.24 | 16410.24 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 6564.096
S1P2-113 | Wind magnetic diagnostic sensors to bot surface | 0 | 16410.24 | 16410.24 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 6564.096
S1P2-114 | Install cooling/htg lines to vac vsl bot surface | 0 | 21880.32 | 21880.32 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 8752.128
S1P2-115 | Install insulation to vac vsl to bot surface | 0 | 34188 | 34188 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 13675.2
S1P2-116 | Prepare and transfer completed VV to holding are | 0 | 6153.84 | 6153.84 | 1 | 18 | 185 | 1810 | S1P2 |  | 40 | 40% | 2461.536
S1P3-101 | Receive VV and inspect(15% LC) | 0 | 6923.07 | 6923.07 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 3807.6885
S1P3-102 | Mount VV on VV Prep fixture (top side up)(15% LC | 0 | 854.7 | 854.7 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 470.085
S1P3-103 | Establish metrology setting;align VV base(15% LC | 0 | 5213.67 | 5213.67 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 2867.5185
S1P3-106 | Attach studs f/coolant lines,insul on top(15% LC | 0 | 12136.74 | 12136.74 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 6675.207
S1P3-107 | Wind magnetic diagn sensors to top (15% LC) | 0 | 13931.61 | 13931.61 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 7662.3855
S1P3-108 | Install cooling/htg lines to vac vsl top (15% LC | 0 | 13931.61 | 13931.61 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 7662.3855
S1P3-109 | Install insulation to vac vsl to top (15% LC) | 0 | 29059.8 | 29059.8 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 15982.89
S1P3-110 | Flip VV to expose lower surface(15% LC) | 0 | 1709.4 | 1709.4 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 940.17
S1P3-112 | Attach studs f/ coolant lines insul bott(15% LC) | 0 | 13931.61 | 13931.61 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 7662.3855
S1P3-113 | Wind magnetic diagn sensors to bottom(15% LC) | 0 | 13931.61 | 13931.61 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 7662.3855
S1P3-114 | Install cooling/htg lines to vv bottom(15% LC) | 0 | 18632.46 | 18632.46 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 10247.853
S1P3-115 | Install insulation to vac vsl to bottom(15% LC) | 0 | 29059.8 | 29059.8 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 15982.89
S1P3-116 | Prepare and transfer completed VV (15% LC) | 0 | 5213.67 | 5213.67 | 1 | 18 | 185 | 1810 | S1P3 |  | 55 | 55% | 2867.5185
S2P1-100 | Assemble Mod-Coils a1.b1,c1 FP 1 left | 0 | 75213.6 | 75213.6 | 1 | 18 | 185 | 1810 | S2P1 |  | 40 | 40% | 30085.44
S2P1-200 | Assemble Mod-Coils a2.b2,c2 FP 1 right | 0 | 75213.6 | 75213.6 | 1 | 18 | 185 | 1810 | S2P1 |  | 40 | 40% | 30085.44
S2P2-100 | Assemble Mod-Coils a3.b3,c3 FP 2 left | 0 | 75615.14 | 75615.14 | 1 | 18 | 185 | 1810 | S2P1 |  | 40 | 40% | 30246.056
S2P2-200 | Assemble Mod-Coils a4.b4,c4 FP 2 right | 0 | 76819.76 | 76819.76 | 1 | 18 | 185 | 1810 | S2P1 |  | 40 | 40% | 30727.904
S2P3-100 | Assemble Mod-Coils a5.b5,c5 FP 3 left(15% LC) | 0 | 66235.4 | 66235.4 | 1 | 18 | 185 | 1810 | S2P1 |  | 55 | 55% | 36429.47
S2P3-200 | Assemble Mod-Coils a6.b6,c6 FP 3 right(15% LC) | 0 | 66235.4 | 66235.4 | 1 | 18 | 185 | 1810 | S2P1 |  | 55 | 55% | 36429.47
S3P1-101 | Mount VV to MC turning fixt base; metr check | 0 | 4009.92 | 4009.92 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1603.968
S3P1-102 | Mount MC on turning fixt; perform metr checks | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1641.024
S3P1-103 | Rotate right MC to stand-off position&chk | 0 | 6153.84 | 6153.84 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 2461.536
S3P1-104 | Transfer load to crane and recheck position | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1641.024
S3P1-105 | Move MC turning fixt; mount MC on turning fixt | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1641.024
S3P1-106 | Rotate left MC to stand-off position and check p | 0 | 6153.84 | 6153.84 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 2461.536
S3P1-107 | Move left & right MC to final position & measure | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1641.024
S3P1-108 | Install shims ( as reqd); ream 24 holes | 0 | 23931.6 | 23931.6 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 9572.64
S3P1-109 | Bolt together at flange interface. | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1641.024
S3P1-110 | Perform final metrology position check | 0 | 2735.04 | 2735.04 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1094.016
S3P1-111 | Secure VV to MC's using temporary supports. | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 1641.024
S3P1-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 2051.28 | 2051.28 | 1 | 18 | 185 | 1810 | S3P1 |  | 40 | 40% | 820.512
S3P2-101 | Mount VV to MC turning fixt base; metr check | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1700.16
S3P2-102 | Mount MC on turning fixt; perform metr checks | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1700.16
S3P2-103 | Rotate right MC to stand-off position&chk | 0 | 6375.6 | 6375.6 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 2550.24
S3P2-104 | Transfer load to crane and recheck position | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1700.16
S3P2-105 | Move MC turning fixt; mount MC on turning fixt | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1700.16
S3P2-106 | Rotate left MC to stand-off position and check p | 0 | 6375.6 | 6375.6 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 2550.24
S3P2-107 | Move left & right MC to final position & measure | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1700.16
S3P2-108 | Install shims ( as reqd); ream 24 holes | 0 | 24794 | 24794 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 9917.6
S3P2-109 | Bolt together at flange interface. | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1700.16
S3P2-110 | Perform final metrology position check | 0 | 2833.6 | 2833.6 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1133.44
S3P2-111 | Secure VV to MC's using temporary supports. | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 1700.16
S3P2-112 | Prep& xfr completed assembly to Stage 4 area | 0 | 2125.2 | 2125.2 | 1 | 18 | 185 | 1810 | S3P2 |  | 40 | 40% | 850.08
S3P3-101 | Mount VV to MC turn fixt base,metr check(15% LC) | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1996.8025
S3P3-102 | Mount MC on turning fixt; perf met check(15% LC) | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1996.8025
S3P3-103 | Rotate right MC to stand-off position&chk(15% LC | 0 | 5401.55 | 5401.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 2970.8525
S3P3-104 | Transfer load to crane recheck position(15% LC | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1996.8025
S3P3-105 | Move MC turning fixt; mount MC turning fixt(15% | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1996.8025
S3P3-106 | Rotate left MC to stand-off position check (15% | 0 | 5401.55 | 5401.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 2970.8525
S3P3-107 | Move left & right MC to final position meas(15% | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1996.8025
S3P3-108 | Install shims ( as reqd); ream 24 holes(15% LC) | 0 | 21074.9 | 21074.9 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 11591.195
S3P3-109 | Bolt together at flange interface.(15% LC) | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1996.8025
S3P3-110 | Perform final metrology position check(15% LC) | 0 | 2390.85 | 2390.85 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1314.9675
S3P3-111 | Secure VV to MC's using temporary suppt(15% LC) | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 1996.8025
S3P3-112 | Prep& xfr completed assy to Stage 4 area(15% LC) | 0 | 1771 | 1771 | 1 | 18 | 185 | 1810 | S3P3 |  | 55 | 55% | 974.05
S4P1-101 | Mount MC/VV assembly to support frame a | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 1641.024
S4P1-102 | Position and weld all ports to VV | 0 | 82051.2 | 82051.2 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 32820.48
S4P1-103 | Inspect Welds | 0 | 6837.6 | 6837.6 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 2735.04
S4P1-104 | Assemble left TF Coil Assembly check position | 0 | 8205.12 | 8205.12 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 3282.048
S4P1-105 | Change platforms | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 1641.024
S4P1-106 | Assemble right TF Coil Assembly chk position | 0 | 8205.12 | 8205.12 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 3282.048
S4P1-107 | Attach TF coils to MC's | 0 | 6153.84 | 6153.84 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 2461.536
S4P1-108 | Change platforms | 0 | 5470.08 | 5470.08 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 2188.032
S4P1-109 | Position, weld two large horizontal diag ports | 0 | 16410.24 | 16410.24 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 6564.096
S4P1-110 | Inspect Welds | 0 | 1367.52 | 1367.52 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 547.008
S4P1-111 | Assemble external trim coils to TF Coil | 0 | 20512.8 | 20512.8 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 8205.12
S4P1-112 | Close up VV, bakeout 350 deg C, leak check | 0 | 54700.8 | 54700.8 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 21880.32
S4P1-113 | Adjust final support base interfaces | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 1641.024
S4P1-113.5 | Final metrology outside & inside | 0 | 13675.2 | 13675.2 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 5470.08
S4P1-114 | Prepare Field Period for shipment | 0 | 4102.56 | 4102.56 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 1641.024
S4P1-115 | Transfer completed assy to C-site test cell | 0 | 6837.6 | 6837.6 | 1 | 18 | 185 | 1810 | S4P1 |  | 40 | 40% | 2735.04
S4P2-101 | Mount MC/VV assembly to support frame a | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 1700.16
S4P2-102 | Position and weld all ports to VV | 0 | 85008 | 85008 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 34003.2
S4P2-103 | Inspect Welds | 0 | 7084 | 7084 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 2833.6
S4P2-104 | Assemble left TF Coil Assembly check position | 0 | 8500.8 | 8500.8 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 3400.32
S4P2-105 | Change platforms | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 1700.16
S4P2-106 | Assemble right TF Coil Assembly chk position | 0 | 8500.8 | 8500.8 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 3400.32
S4P2-107 | Attach TF coils to MC's | 0 | 6375.6 | 6375.6 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 2550.24
S4P2-108 | Change platforms | 0 | 5667.2 | 5667.2 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 2266.88
S4P2-109 | Position, weld two large horizontal diag ports | 0 | 17001.6 | 17001.6 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 6800.64
S4P2-110 | Inspect Welds | 0 | 1416.8 | 1416.8 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 566.72
S4P2-111 | Assemble external trim coils to TF Coil | 0 | 21252 | 21252 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 8500.8
S4P2-112 | Close up VV, bakeout 350 deg C, leak check | 0 | 56672 | 56672 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 22668.8
S4P2-113 | Adjust final support base interfaces | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 1700.16
S4P2-113.5 | Final metrology outside & inside | 0 | 14168 | 14168 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 5667.2
S4P2-114 | Prepare Field Period for shipment | 0 | 4250.4 | 4250.4 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 1700.16
S4P2-115 | Transfer completed assy to C-site test cell | 0 | 7084 | 7084 | 1 | 18 | 185 | 1810 | S4P2 |  | 40 | 40% | 2833.6
S4P3-101 | Mount MC/VV assembly to support frame a(15%LC | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 1996.8025
S4P3-102 | Position and weld all ports to VV*2 shift*(15%LC | 0 | 72256.8 | 72256.8 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 39741.24
S4P3-103 | Inspect Welds (15%LC | 0 | 6021.4 | 6021.4 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 3311.77
S4P3-104 | Assemble left TF Coil Assy chk position(15%LC | 0 | 7261.1 | 7261.1 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 3993.605
S4P3-105 | Change platforms(15%LC | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 1996.8025
S4P3-106 | Assemble right TF Coil Assy chk position(15%LC | 0 | 7261.1 | 7261.1 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 3993.605
S4P3-107 | Attach TF coils to MC's(15%LC | 0 | 5401.55 | 5401.55 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 2970.8525
S4P3-108 | Change platforms(15%LC | 0 | 4781.7 | 4781.7 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 2629.935
S4P3-109 | Position, weld two large horiz diag ports(15%LC | 0 | 14433.65 | 14433.65 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 7938.5075
S4P3-110 | Inspect Welds | 0 | 1416.8 | 1416.8 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 779.24
S4P3-111 | Assemble external trim coils to TF Coil(15%LC | 0 | 18064.2 | 18064.2 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 9935.31
S4P3-112 | Close up VV, bakeout 350 deg C, leak check(15%LC | 0 | 48171.2 | 48171.2 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 26494.16
S4P3-113 | Adjust final support base interfaces(15%LC | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 1996.8025
S4P3-113.5 | Final metrology outside & inside(15%LC | 0 | 12042.8 | 12042.8 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 6623.54
S4P3-114 | Prepare Field Period for shipment(15%LC | 0 | 3630.55 | 3630.55 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 1996.8025
S4P3-115 | Transfer assy to C-site test cell(15%LC | 0 | 6021.4 | 6021.4 | 1 | 18 | 185 | 1810 | S4P3 |  | 55 | 55% | 3311.77
184-100 | Assemble 3 TF coils&structure -Left-Period #1 | 0 | 9635.2 | 9635.2 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 3854.08
184-100 | Assemble 3 TF coils&structure -Left-Period #1 | 0 | 27350.4 | 27350.4 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 10940.16
184-105 | Assemble 3 TF coils&structure -Right -Period #1 | 0 | 9635.2 | 9635.2 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 3854.08
184-105 | Assemble 3 TF coils&structure -Right -Period #1 | 0 | 27350.4 | 27350.4 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 10940.16
184-110 | Assemble 3 TF coils&structure -Left-Period #2 | 0 | 9635.2 | 9635.2 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 3854.08
184-110 | Assemble 3 TF coils&structure -Left-Period #2 | 0 | 27350.4 | 27350.4 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 10940.16
184-115 | Assemble 3 TF coils&structure -Right -Period #2 | 0 | 9635.2 | 9635.2 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 3854.08
184-115 | Assemble 3 TF coils&structure -Right -Period #2 | 0 | 27350.4 | 27350.4 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 40 | 40% | 10940.16
184-120 | Assemble 3 TF coils&struc -Left -Period #3(15%LC | 0 | 8485.04 | 8485.04 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 55 | 55% | 4666.772
184-120 | Assemble 3 TF coils&struc -Left -Period #3(15%LC | 0 | 24085.6 | 24085.6 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 55 | 55% | 13247.08
184-125 | Assemble 3 TF coils&struc-Right -Period #3(15%LC | 0 | 8485.04 | 8485.04 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 55 | 55% | 4666.772
184-125 | Assemble 3 TF coils&struc-Right -Period #3(15%LC | 0 | 24085.6 | 24085.6 | 1 | 18 | 185 | 1810 | S5P1 | 20 | 55 | 55% | 13247.08
0191-5 | LOE-FY05 WBS 191 | 67177 | 170500 | 103323 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 10332.3
0191-5 | LOE-FY05 WBS 191 | 3280.05 | 8325 | 5044.95 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 504.495
0191-6 | LOE-FY06 WBS 191 | 0 | 185584.08 | 185584.08 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 18558.408
0191-6 | LOE-FY06 WBS 191 | 0 | 9060.1 | 9060.1 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 906.01
0191-6X | LOE-FY07 WBS 191 | 0 | 189090 | 189090 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 18909
0191-6X | LOE-FY07 WBS 191 | 0 | 9085 | 9085 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 908.5
0191-7 | LOE-FY08 WBS 191 | 0 | 87352 | 87352 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 8735.2
0191-7 | LOE-FY08 WBS 191 | 0 | 9240 | 9240 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 924
191-8 | LOE-FY089 WBS 191 | 0 | 45384 | 45384 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 4538.4
191-8 | LOE-FY089 WBS 191 | 0 | 9400 | 9400 | 1 | 19 | 191 | 1901 | 191 | 02 | 10 | 10% | 940
192-6.01 | Document coil tolerance and trim coil requiremen | 18153.132 | 19108.56 | 955.428 | 1 | 19 | 192 | 1901 | 192 | 02 | 10 | 10% | 95.5428
192-6.031 | Demo Method for current center on TRC | 0 | 13220 | 13220 | 1 | 19 | 192 | 1901 | 192 | 05 | 10 | 10% | 1322
192-6.031 | Demo Method for current center on TRC | 0 | 50356.11 | 50356.11 | 1 | 19 | 192 | 1901 | 192 | 05 | 10 | 10% | 5035.611
192-6.031 | Demo Method for current center on TRC | 0 | 12400 | 12400 | 1 | 19 | 192 | 1901 | 192 | 05 | 10 | 10% | 1240
192-6.031 | Demo Method for current center on TRC | 0 | 8401.6 | 8401.6 | 1 | 19 | 192 | 1901 | 192 | 05 | 10 | 10% | 840.16
0192-5 | LOE-FY05 WBS 192 | 1640.025 | 4162.5 | 2522.475 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 252.2475
0192-5 | LOE-FY05 WBS 192 | 73284 | 186000 | 112716 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 11271.6
0192-5 | LOE-FY05 WBS 192 | 11760.9 | 29850 | 18089.1 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 1808.91
0192-5 | LOE-FY05 WBS 192 | 24428 | 62000 | 37572 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 3757.2
0192-6 | LOE-FY06 WBS 192 | 0 | 4530.05 | 4530.05 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 453.005
0192-6 | LOE-FY06 WBS 192 | 0 | 269940.48 | 269940.48 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 26994.048
0192-6 | LOE-FY06 WBS 192 | 0 | 30359.48 | 30359.48 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 3035.948
0192-6X | LOE-FY07 WBS 192 | 0 | 9085 | 9085 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 908.5
0192-6X | LOE-FY07 WBS 192 | 0 | 114657.3 | 114657.3 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 11465.73
0192-6X | LOE-FY07 WBS 192 | 0 | 30968.3 | 30968.3 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 3096.83
0192-7 | LOE-FY08 WBS 192 | 0 | 9240 | 9240 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 924
0192-7 | LOE-FY08 WBS 192 | 0 | 107400 | 107400 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 10740
0192-7 | LOE-FY08 WBS 192 | 0 | 31507.4 | 31507.4 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 3150.74
0192-99 | LOE-FY09 | 0 | 3210 | 3210 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 321
0192-99 | LOE-FY09 | 0 | 74400 | 74400 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 7440
0192-99 | LOE-FY09 | 0 | 21040 | 21040 | 1 | 19 | 192 | 1901 | 192 | 07 | 10 | 10% | 2104
3101-125 | PDR PREP -VESSEL SADDLE LOOP MOUNTING | 0 | 3066.8 | 3066.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 920.04
3101-125 | PDR PREP -VESSEL SADDLE LOOP MOUNTING | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 1925.04
3101-129 | DESIGN AND PROTOTYPE SADDLE LOOP TERMINATIONS | 0 | 1226.72 | 1226.72 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 368.016
3101-129 | DESIGN AND PROTOTYPE SADDLE LOOP TERMINATIONS | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 1925.04
3101-133 | Prototype loops on vsl proto segment using ARI | 0 | 3208.4 | 3208.4 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 962.52
3101-133 | Prototype loops on vsl proto segment using ARI | 0 | 2980.8 | 2980.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 894.24
3101-141 | FDR PREP- VESSEL SADDLE LOOPS | 0 | 3066.8 | 3066.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 920.04
3101-141 | FDR PREP- VESSEL SADDLE LOOPS | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 1925.04
3101-145 | PROCURE MATERIALS | 0 | 24467.1 | 24467.1 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 7340.13
3101-145 | PROCURE MATERIALS | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 1925.04
3101-149 | PREPARE METROLOGY | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 1925.04
3101-153 | FAB TERMINATION BOXES & CLAMPS | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 1925.04
3101-153 | FAB TERMINATION BOXES & CLAMPS | 0 | 8401.6 | 8401.6 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 2520.48
3101-153 | FAB TERMINATION BOXES & CLAMPS | 0 | 16767 | 16767 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 5030.1
3101-157 | Design Tooling | 0 | 1490.4 | 1490.4 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 447.12
3101-157 | Design Tooling | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 1925.04
3101-157 | Design Tooling | 0 | 12602.4 | 12602.4 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 3780.72
3101-161 | SUPT LOOP INSTL 200 LOOPS), TERMINATION,TESTING | 0 | 14580.35 | 14580.35 | 3 | 31 | 310 | 3101 | MD1 |  | 30 | 30% | 4374.105
3101-209 | PROTOTYPE ON TWISTED RACETRACK | 0 | 1533.4 | 1533.4 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 460.02
3101-209 | PROTOTYPE ON TWISTED RACETRACK | 0 | 3208.4 | 3208.4 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 962.52
3101-213 | DESIGN TERMINATION | 0 | 3208.4 | 3208.4 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 962.52
3101-213 | DESIGN TERMINATION | 0 | 4094 | 4094 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 1228.2
3101-217 | FDR PREP- MC CO-WOUND LOOP | 0 | 1533.4 | 1533.4 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 460.02
3101-217 | FDR PREP- MC CO-WOUND LOOP | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 1925.04
3101-217 | FDR PREP- MC CO-WOUND LOOP | 0 | 4094 | 4094 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 1228.2
3101-221 | PROCURE MATERIALS | 0 | 3202.5 | 3202.5 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 960.75
3101-221 | PROCURE MATERIALS | 0 | 3208.4 | 3208.4 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 962.52
3101-225 | FAB TERMINATION BOXES | 0 | 1604.2 | 1604.2 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 481.26
3101-225 | FAB TERMINATION BOXES | 0 | 2980.8 | 2980.8 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 894.24
3101-229 | SUPPORT NSTALLATION, TERMINATION, TESTING | 0 | 7193.48 | 7193.48 | 3 | 31 | 310 | 3101 | MD2 |  | 30 | 30% | 2158.044
3101-301 | LAYOUT LOCATION ROWGOSKI COIL &EST COIL DIMEN | 0 | 1533.4 | 1533.4 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 460.02
3101-301 | LAYOUT LOCATION ROWGOSKI COIL &EST COIL DIMEN | 0 | 3208.4 | 3208.4 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 962.52
3101-305 | ROWGOWSKI COIL DESIGN | 0 | 7192.8 | 7192.8 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 2157.84
3101-309 | DESIGN COIL MOUNTING TECHNIQUE | 0 | 7192.8 | 7192.8 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 2157.84
3101-313 | DESIGN LEAD ROUTING AND TERMINATION | 0 | 7192.8 | 7192.8 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 2157.84
3101-317 | PDR PREP- ROWGOWSKI COIL | 0 | 1703.3 | 1703.3 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 510.99
3101-317 | PDR PREP- ROWGOWSKI COIL | 0 | 3596.4 | 3596.4 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 1078.92
3101-321 | DETAILED DESIGN OF ROWGOWSKI COILS, TERMINATIONS | 0 | 2274 | 2274 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 682.2
3101-321 | DETAILED DESIGN OF ROWGOWSKI COILS, TERMINATIONS | 0 | 8991 | 8991 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 2697.3
3101-325 | FDR PREP ROWGOSKI COIL | 0 | 7192.8 | 7192.8 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 2157.84
3101-329 | FAB ROWGOWSKI COILS (2) | 0 | 22185 | 22185 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 6655.5
3101-329 | FAB ROWGOWSKI COILS (2) | 0 | 14385.6 | 14385.6 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 4315.68
3101-329 | FAB ROWGOWSKI COILS (2) | 0 | 16708 | 16708 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 5012.4
3101-333 | FAB TERMINATIONS | 0 | 3596.4 | 3596.4 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 1078.92
3101-333 | FAB TERMINATIONS | 0 | 3341.6 | 3341.6 | 3 | 31 | 310 | 3101 | MD3 |  | 30 | 30% | 1002.48
3101-401 | MOUNTING/LOCATING TECHNIQUE TF CO-WOUND LOOPS | 0 | 3066.8 | 3066.8 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 920.04
3101-401 | MOUNTING/LOCATING TECHNIQUE TF CO-WOUND LOOPS | 0 | 3208.4 | 3208.4 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 962.52
3101-405 | DESIGN TERMINATION | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1925.04
3101-405 | DESIGN TERMINATION | 0 | 4094 | 4094 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1228.2
3101-409 | FINALIZE LOOP LOCATION/MOUNTING TECHNIQUE | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1925.04
3101-413 | FDR PREP- TF CO-WOUND LOOPS | 0 | 6416.8 | 6416.8 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1925.04
3101-417 | PROCURE MATERIALS | 0 | 7395 | 7395 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 2218.5
3101-417 | PROCURE MATERIALS | 0 | 3596.4 | 3596.4 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1078.92
3101-421 | FAB TERMINATIONS | 0 | 3596.4 | 3596.4 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1078.92
3101-421 | FAB TERMINATIONS | 0 | 5012.4 | 5012.4 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1503.72
3101-429 | INSTALL TERMINATIONS | 0 | 3668.92 | 3668.92 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1100.676
3101-429 | INSTALL TERMINATIONS | 0 | 5113.37 | 5113.37 | 3 | 31 | 310 | 3101 | MD4 |  | 30 | 30% | 1534.011
3101-501 | DETERMINE NUMEBR AND LOCATION OF LOOPS | 0 | 6970.8 | 6970.8 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 2091.24
3101-505 | MOUNTING/LOCATING TECHN MC SHELL SADDLE LOOPS | 0 | 3485.4 | 3485.4 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1045.62
3101-505 | MOUNTING/LOCATING TECHN MC SHELL SADDLE LOOPS | 0 | 3679.6 | 3679.6 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1103.88
3101-509 | PROTOTYPE MC SHELL SADDLE LOOPS | 0 | 3679.6 | 3679.6 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1103.88
3101-509 | PROTOTYPE MC SHELL SADDLE LOOPS | 0 | 1709.4 | 1709.4 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 512.82
3101-513 | PDR PREP -MC SHELL SADDLE LOOPS | 0 | 1742.7 | 1742.7 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 522.81
3101-513 | PDR PREP -MC SHELL SADDLE LOOPS | 0 | 3679.6 | 3679.6 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1103.88
3101-517 | DESIGN TERMINATION | 0 | 3679.6 | 3679.6 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1103.88
3101-517 | DESIGN TERMINATION | 0 | 2326.6 | 2326.6 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 697.98
3101-521 | FINALIZE LOOP LOCATION/MOUNTING TECHNIQUE | 0 | 7359.2 | 7359.2 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 2207.76
3101-525 | FDR PREP - MC SHELL SADDLE LOOPS | 0 | 7359.2 | 7359.2 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 2207.76
3101-529 | PROCURE MATERIALS | 0 | 6925 | 6925 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 2077.5
3101-529 | PROCURE MATERIALS | 0 | 3679.6 | 3679.6 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1103.88
3101-537 | INSTALL TERMINATIONS | 0 | 3753.64 | 3753.64 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1126.092
3101-537 | INSTALL TERMINATIONS | 0 | 5231.38 | 5231.38 | 3 | 31 | 310 | 3101 | MD5 |  | 30 | 30% | 1569.414
390-015 | LOE Support FY05 **reduced scope | 10693.6249 | 27141.18 | 16447.5551 | 3 | 39 | 390 | 3901 |  |  | 30 | 30% | 4934.2665
390-015 | LOE Support FY05 **reduced scope | 0 | 0 | 0 | 3 | 39 | 390 | 3901 |  |  | 30 | 30% | 0
390-015 | LOE Support FY05 **reduced scope | 0 | 0 | 0 | 3 | 39 | 390 | 3901 |  |  | 30 | 30% | 0
390-015 | LOE Support FY05 **reduced scope | 15451.1513 | 39216.12 | 23764.9687 | 3 | 39 | 390 | 3901 |  |  | 30 | 30% | 7129.4906
4101-100.1 | Prepare Preliminary One line diagram | 0 | 181.92 | 181.92 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 32.7456
4101-100.1 | Prepare Preliminary One line diagram | 0 | 415.3 | 415.3 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 74.754
4101-100.1 | Prepare Preliminary One line diagram | 0 | 196.51 | 196.51 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 35.3718
4101-100.1 | Prepare Preliminary One line diagram | 0 | 268.86 | 268.86 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 48.3948
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 2956.2 | 2956.2 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 532.116
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 10728.48 | 10728.48 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1931.1264
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 7614.84 | 7614.84 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1370.6712
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 8738.08 | 8738.08 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1572.8544
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 8874 | 8874 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1597.32
411-1-100 | Ex-Test cell AC pwr-Reactivate& new instl | 0 | 23664 | 23664 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 4259.52
411-2-2 | Grounding-Dsn | 0 | 18192 | 18192 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 3274.56
411-2-2 | Grounding-Dsn | 0 | 12458.88 | 12458.88 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 2242.5984
411-2-4 | Grounding-Procure | 0 | 7395 | 7395 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1331.1
411-2-6 | Grounding-Install | 0 | 7081.6 | 7081.6 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1274.688
411-2-6 | Grounding-Install | 0 | 10052.8 | 10052.8 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1809.504
411-2-6 | Grounding-Install | 0 | 13753.6 | 13753.6 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 2475.648
411-2-6 | Grounding-Install | 0 | 34625 | 34625 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 6232.5
411-2-8 | Grounding-Commission | 0 | 4248.96 | 4248.96 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 764.8128
411-2-8 | Grounding-Commission | 0 | 5026.4 | 5026.4 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 904.752
411-2-8 | Grounding-Commission | 0 | 6876.8 | 6876.8 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1237.824
411-3-2 | Test Cell AC Power Distr-Dsn | 0 | 2274 | 2274 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 409.32
411-3-2 | Test Cell AC Power Distr-Dsn | 0 | 1384.32 | 1384.32 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 249.1776
411-3-4 | Test Cell AC Power Distr-Procure(pnls & xfrmrs) | 0 | 48956.97 | 48956.97 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 8812.2546
411-3-6 | Test Cell AC Power Distr-Install | 0 | 6990.83 | 6990.83 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1258.3494
411-3-6 | Test Cell AC Power Distr-Install | 0 | 4961.95 | 4961.95 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 893.151
411-3-6 | Test Cell AC Power Distr-Install | 0 | 20366.26 | 20366.26 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 3665.9268
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 8497.92 | 8497.92 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1529.6256
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 10052.8 | 10052.8 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 1809.504
411-3-8 | Test Cell AC Power Distr-Commission | 0 | 13753.6 | 13753.6 | 4 | 41 | 411 | 4101 | 411 |  | 18 | 18% | 2475.648
412-1-2 | D-site Pulsed AC Power Distr-Dsn | 0 | 4653.2 | 4653.2 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 837.576
412-1-2 | D-site Pulsed AC Power Distr-Dsn | 0 | 7081.6 | 7081.6 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 1274.688
412-1-4 | D-site Pulsed AC Power Distr-Procure | 0 | 6928.68 | 6928.68 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 1247.1624
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 2934.56 | 2934.56 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 528.2208
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 8332.16 | 8332.16 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 1499.7888
412-1-6 | D-site Pulsed AC Power Distr-Install | 0 | 7124 | 7124 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 1282.32
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 4401.84 | 4401.84 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 792.3312
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 3124.56 | 3124.56 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 562.4208
412-1-8 | D-site Pulsed AC Power Distr-Commission | 0 | 3562 | 3562 | 4 | 41 | 412 | 4101 | 412 |  | 18 | 18% | 641.16
431-200 | Condition/spare parts inventory | 3177.708 | 3738.48 | 560.772 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 100.939
431-200 | Condition/spare parts inventory | 11278.14 | 13268.4 | 1990.26 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 358.2468
431-210 | Organize & verify documentation | 9720.048 | 16200.08 | 6480.032 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1166.4058
431-210 | Organize & verify documentation | 4245.888 | 7076.48 | 2830.592 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 509.5066
431-210 | Organize & verify documentation | 12282 | 20470 | 8188 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1473.84
431-215 | Document status | 934.62 | 6230.8 | 5296.18 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 953.3124
431-225 | Reactivate DF & PEI units | 0 | 2492.32 | 2492.32 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 448.6176
431-225 | Reactivate DF & PEI units | 0 | 2653.68 | 2653.68 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 477.6624
431-225 | Reactivate DF & PEI units | 0 | 6050.4 | 6050.4 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1089.072
431-230 | Load test | 0 | 6230.8 | 6230.8 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1121.544
431-230 | Load test | 0 | 9075.6 | 9075.6 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1633.608
431-240 | Simulate each of 6 pwr loops in PSCAD | 0 | 12461.6 | 12461.6 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 2243.088
431-250 | c-site dc sys DGS dsn documentation | 0 | 2492.32 | 2492.32 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 448.6176
431-250 | c-site dc sys DGS dsn documentation | 0 | 4094 | 4094 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 736.92
431-260 | Power loop design | 6978.496 | 34892.48 | 27913.984 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 5024.5171
431-260 | Power loop design | 7369.2 | 36846 | 29476.8 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 5305.824
431-260 | Power loop design | 7369.2 | 36846 | 29476.8 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 5305.824
431-265 | Fabricate bus components | 0 | 2577.46 | 2577.46 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 463.9428
431-265 | Fabricate bus components | 0 | 4573.77 | 4573.77 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 823.2786
431-265 | Fabricate bus components | 0 | 9385.8 | 9385.8 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1689.444
431-275 | Power cabling & Installation | 0 | 7081.6 | 7081.6 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1274.688
431-275 | Power cabling & Installation | 0 | 30158.4 | 30158.4 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 5428.512
431-275 | Power cabling & Installation | 0 | 44699.2 | 44699.2 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 8045.856
431-275 | Power cabling & Installation | 0 | 124650 | 124650 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 22437
431-275 | Power cabling & Installation | 0 | 9695 | 9695 | 4 | 43 | 431 | 4301 | 431 |  | 18 | 18% | 1745.1
441-095 | Design Interlock sys | 0 | 14163.2 | 14163.2 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2549.376
441-095 | Design Interlock sys | 0 | 18612.8 | 18612.8 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 3350.304
441-097 | Install Interlock sys | 0 | 14163.2 | 14163.2 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2549.376
441-097 | Install Interlock sys | 0 | 15079.2 | 15079.2 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2714.256
441-100 | PLC Specification | 0 | 7081.6 | 7081.6 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1274.688
441-100 | PLC Specification | 0 | 7036.96 | 7036.96 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1266.6528
441-105 | Prep Block diagrams | 0 | 7081.6 | 7081.6 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1274.688
441-105 | Prep Block diagrams | 0 | 10052.8 | 10052.8 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1809.504
441-110 | PLC CWD's & Cabling | 0 | 7201.51 | 7201.51 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1296.2718
441-110 | PLC CWD's & Cabling | 0 | 15335.01 | 15335.01 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2760.3018
441-115 | deliver PLC | 0 | 70400 | 70400 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 12672
441-120 | Program PLC Logic | 0 | 7336.4 | 7336.4 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1320.552
441-120 | Program PLC Logic | 0 | 15622.8 | 15622.8 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2812.104
441-125 | Program Control pages | 0 | 5869.12 | 5869.12 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1056.4416
441-125 | Program Control pages | 0 | 15622.8 | 15622.8 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2812.104
441-125 | Program Control pages | 0 | 2730.08 | 2730.08 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 491.4144
441-130 | Pre-commissioning tests | 0 | 7323.3 | 7323.3 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1318.194
441-130 | Pre-commissioning tests | 0 | 15594.86 | 15594.86 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2807.0748
441-130 | Pre-commissioning tests | 0 | 1406.82 | 1406.82 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 253.2276
441-135 | Install I/O Cabling | 0 | 22127.36 | 22127.36 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 3982.9248
441-135 | Install I/O Cabling | 0 | 10471.06 | 10471.06 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 1884.7908
441-135 | Install I/O Cabling | 0 | 42347.42 | 42347.42 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 7622.5356
441-135 | Install I/O Cabling | 0 | 19386.56 | 19386.56 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 3489.5808
441-135 | Install I/O Cabling | 0 | 14324.63 | 14324.63 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2578.4334
441-135 | Install I/O Cabling | 0 | 11292.65 | 11292.65 | 4 | 44 | 441 | 4401 | 441 |  | 18 | 18% | 2032.677
442-1-2 | Kirk Keys-Dsn | 0 | 9306.4 | 9306.4 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 1675.152
442-1-2 | Kirk Keys-Dsn | 0 | 7081.6 | 7081.6 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 1274.688
442-1-4 | Kirk Keys-Procure | 0 | 13850 | 13850 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 2493
442-1-6 | Kirk Keys-Install | 0 | 2832.64 | 2832.64 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 509.8752
442-1-6 | Kirk Keys-Install | 0 | 2010.56 | 2010.56 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 361.9008
442-1-6 | Kirk Keys-Install | 0 | 5157.6 | 5157.6 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 928.368
442-1-6 | Kirk Keys-Install | 0 | 34625 | 34625 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 6232.5
442-1-8 | Kirk Keys-Commission | 0 | 2934.56 | 2934.56 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 528.2208
442-1-8 | Kirk Keys-Commission | 0 | 2603.8 | 2603.8 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 468.684
442-1-8 | Kirk Keys-Commission | 0 | 1781 | 1781 | 4 | 44 | 442 | 4401 | 442 |  | 18 | 18% | 320.58
443-1-2 | Develop Control Algorithms-Dsn | 0 | 14270.86 | 14270.86 | 4 | 44 | 443 | 4401 | 443 |  | 18 | 18% | 2568.7548
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 0 | 6979.8 | 6979.8 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1256.364
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 0 | 4248.96 | 4248.96 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 764.8128
444-2-4 | DC Potential Transducers (DCPTs)-Procure | 0 | 8310 | 8310 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1495.8
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 2844.63 | 2844.63 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 512.0334
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 3028.63 | 3028.63 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 545.1534
444-2-6 | DC Potential Transducers (DCPTs)-Install | 0 | 13811.76 | 13811.76 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 2486.1168
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 4401.84 | 4401.84 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 792.3312
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 3124.56 | 3124.56 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 562.4208
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 0 | 5343 | 5343 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 961.74
444-3-2 | DC Shunts-Dsn | 0 | 9306.4 | 9306.4 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1675.152
444-3-2 | DC Shunts-Dsn | 0 | 7081.6 | 7081.6 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1274.688
444-3-4 | DC Shunts-Procure | 0 | 62325 | 62325 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 11218.5
444-3-6 | DC Shunts-Install | 0 | 5765.2 | 5765.2 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1037.736
444-3-6 | DC Shunts-Install | 0 | 8184.36 | 8184.36 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1473.1848
444-3-6 | DC Shunts-Install | 0 | 13995.95 | 13995.95 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 2519.271
444-3-6 | DC Shunts-Install | 0 | 27925.49 | 27925.49 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 5026.5882
444-3-8 | DC Shunts-Commission | 0 | 4401.84 | 4401.84 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 792.3312
444-3-8 | DC Shunts-Commission | 0 | 3124.56 | 3124.56 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 562.4208
444-3-8 | DC Shunts-Commission | 0 | 10686 | 10686 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1923.48
444-4-2 | Signal Conditioning & Cabling-Dsn | 0 | 9306.4 | 9306.4 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1675.152
444-4-2 | Signal Conditioning & Cabling-Dsn | 0 | 35408 | 35408 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 6373.44
444-4-4 | Signal Conditioning & Cabling-Procure | 0 | 16620 | 16620 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 2991.6
444-4-6 | Signal Conditioning & Cabling-Install | 0 | 4329.9 | 4329.9 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 779.382
444-4-6 | Signal Conditioning & Cabling-Install | 0 | 24526.85 | 24526.85 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 4414.833
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 8803.68 | 8803.68 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 1584.6624
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 5207.6 | 5207.6 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 937.368
444-4-8 | Signal Conditioning & Cabling-Commission | 0 | 3562 | 3562 | 4 | 44 | 444 | 4401 | 444 |  | 18 | 18% | 641.16
445-1-2 | Ground Fault Protection-Dsn | 0 | 13644 | 13644 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 3001.68
445-1-2 | Ground Fault Protection-Dsn | 0 | 20764.8 | 20764.8 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 4568.256
445-1-4 | Ground Fault Protection-Procure | 0 | 26622 | 26622 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 5856.84
445-1-6 | Ground Fault Protection-Install | 0 | 7081.6 | 7081.6 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 1557.952
445-1-6 | Ground Fault Protection-Install | 0 | 6031.68 | 6031.68 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 1326.9696
445-1-6 | Ground Fault Protection-Install | 0 | 10315.2 | 10315.2 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 2269.344
445-1-8 | Ground Fault Protection-Commission | 0 | 4248.96 | 4248.96 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 934.7712
445-1-8 | Ground Fault Protection-Commission | 0 | 3015.84 | 3015.84 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 663.4848
445-1-8 | Ground Fault Protection-Commission | 0 | 2750.72 | 2750.72 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 605.1584
445-2-105 | Overload Protect-Write spec and approve | 0 | 14163.2 | 14163.2 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 3115.904
445-2-110 | Overload Protect-Design | 0 | 56652.8 | 56652.8 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 12463.616
445-2-110 | Overload Protect-Design | 0 | 9306.4 | 9306.4 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 2047.408
445-2-110 | Overload Protect-Design | 0 | 10052.8 | 10052.8 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 2211.616
445-2-115 | Overload Protect-Fabr 4 chassis 120 modls | 0 | 21244.8 | 21244.8 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 4673.856
445-2-115 | Overload Protect-Fabr 4 chassis 120 modls | 0 | 48253.44 | 48253.44 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 10615.7568
445-2-120 | Overload Protect-Test 4 units | 0 | 14163.2 | 14163.2 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 3115.904
445-2-120 | Overload Protect-Test 4 units | 0 | 10052.8 | 10052.8 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 2211.616
445-2-125 | Overload Protect-Install & Rack wiring | 0 | 21703.44 | 21703.44 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 4774.7568
445-2-125 | Overload Protect-Install & Rack wiring | 0 | 24648.58 | 24648.58 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 5422.6876
445-2-130 | Overload Protect-Write & perform ISTP | 0 | 14672.8 | 14672.8 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 3228.016
445-2-130 | Overload Protect-Write & perform ISTP | 0 | 10415.2 | 10415.2 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 2291.344
445-2-135 | Overload Protect-Documentation | 0 | 7081.6 | 7081.6 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 1557.952
445-2-135 | Overload Protect-Documentation | 0 | 18612.8 | 18612.8 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 4094.816
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 44172.39 | 44172.39 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 9717.9258
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 23407.35 | 23407.35 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 5149.617
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 14159.5 | 14159.5 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 3115.09
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 20755.49 | 20755.49 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 4566.2078
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 8333.28 | 8333.28 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 1833.3216
445-2-140 | Overload Protection&cabling design,procure instl | 0 | 34721.99 | 34721.99 | 4 | 44 | 445 | 4401 | 445 |  | 22 | 22% | 7638.8378
451-3-2 | Dwgs,asbuilts -Elect Dsn | 0 | 123170.72 | 123170.72 | 4 | 45 | 451 | 4501 | 451 | 10 | 18 | 18% | 22170.7296
451-3-2 | Dwgs,asbuilts -Elect Dsn | 0 | 43257.06 | 43257.06 | 4 | 45 | 451 | 4501 | 451 | 10 | 18 | 18% | 7786.2708
451-2-1 | CDR Power system -Dsn | 4094 | 16376 | 12282 | 4 | 45 | 451 | 4501 | 451 | 11 | 18 | 18% | 2210.76
451-2-1 | CDR Power system -Dsn | 6230.8 | 24923.2 | 18692.4 | 4 | 45 | 451 | 4501 | 451 | 11 | 18 | 18% | 3364.632
451-2-2 | PDR Power system -Dsn | 0 | 16376 | 16376 | 4 | 45 | 451 | 4501 | 451 | 12 | 18 | 18% | 2947.68
451-2-2 | PDR Power system -Dsn | 0 | 24923.2 | 24923.2 | 4 | 45 | 451 | 4501 | 451 | 12 | 18 | 18% | 4486.176
451-2-2.1 | FDR C-Site | 0 | 12282 | 12282 | 4 | 45 | 451 | 4501 | 451 | 13 | 18 | 18% | 2210.76
451-2-2.1 | FDR C-Site | 0 | 18692.4 | 18692.4 | 4 | 45 | 451 | 4501 | 451 | 13 | 18 | 18% | 3364.632
451-6-2 | FDR C-Site -Cabling | 0 | 12282 | 12282 | 4 | 45 | 451 | 4501 | 451 | 14 | 18 | 18% | 2210.76
451-6-2 | FDR C-Site -Cabling | 0 | 18692.4 | 18692.4 | 4 | 45 | 451 | 4501 | 451 | 14 | 18 | 18% | 3364.632
451-4-2 | FDR AC auxiliaries & grounding-Dsn | 0 | 4548 | 4548 | 4 | 45 | 451 | 4501 | 451 | 15 | 18 | 18% | 818.64
451-4-2 | FDR AC auxiliaries & grounding-Dsn | 0 | 6921.6 | 6921.6 | 4 | 45 | 451 | 4501 | 451 | 15 | 18 | 18% | 1245.888
451-1-2 | Calculations-Dsn | 0 | 899.4 | 899.4 | 4 | 45 | 451 | 4501 | 451 | 16 | 18 | 18% | 161.892
451-1-2 | Calculations-Dsn | 0 | 54751.94 | 54751.94 | 4 | 45 | 451 | 4501 | 451 | 16 | 18 | 18% | 9855.3492
452-1-2 | Diagnostics AC Power Distr-Dsn | 0 | 74451.2 | 74451.2 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 19357.312
452-1-2 | Diagnostics AC Power Distr-Dsn | 0 | 14163.2 | 14163.2 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 3682.432
452-1-4 | Diagnostics AC Power Distr-Procure | 0 | 1385.76 | 1385.76 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 360.2976
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 14672.8 | 14672.8 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 3814.928
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 10415.2 | 10415.2 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 2707.952
452-1-6 | Diagnostics AC Power Distr-Install | 0 | 56992 | 56992 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 14817.92
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 7336.4 | 7336.4 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 1907.464
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 10415.2 | 10415.2 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 2707.952
452-1-8 | Diagnostics AC Power Distr-Commission | 0 | 14248 | 14248 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 3704.48
452-2-2 | Diagnostics sensor cabling-Dsn | 0 | 18612.8 | 18612.8 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 4839.328
452-2-2 | Diagnostics sensor cabling-Dsn | 0 | 7081.6 | 7081.6 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 1841.216
452-2-4 | Diagnostics sensor cabling-Procure | 0 | 2770 | 2770 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 720.2
452-2-6 | Diagnostics sensor cabling-Install | 0 | 4397.14 | 4397.14 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 1143.2564
452-2-6 | Diagnostics sensor cabling-Install | 0 | 4161.62 | 4161.62 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 1082.0212
452-2-6 | Diagnostics sensor cabling-Install | 0 | 14232.79 | 14232.79 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 3700.5254
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 1467.28 | 1467.28 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 381.4928
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 2083.04 | 2083.04 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 541.5904
452-2-8 | Diagnostics sensor cabling-Commission | 0 | 2849.6 | 2849.6 | 4 | 45 | 452 | 4501 | 452 |  | 26 | 26% | 740.896
453-1-2 | New Procedures | 0 | 27919.2 | 27919.2 | 4 | 45 | 453 | 4501 | 453 |  | 18 | 18% | 5025.456
453-1-2 | New Procedures | 0 | 42489.6 | 42489.6 | 4 | 45 | 453 | 4501 | 453 |  | 18 | 18% | 7648.128
453-1-4 | Preop Testing-Procure test equipt | 0 | 34642.97 | 34642.97 | 4 | 45 | 453 | 4501 | 453 |  | 18 | 18% | 6235.7346
453-1-8 | Testing PTPs, ISTPs | 0 | 31245.6 | 31245.6 | 4 | 45 | 453 | 4501 | 453 |  | 18 | 18% | 5624.208
453-1-8 | Testing PTPs, ISTPs | 0 | 33482.8 | 33482.8 | 4 | 45 | 453 | 4501 | 453 |  | 18 | 18% | 6026.904
453-1-8 | Testing PTPs, ISTPs | 0 | 140858.88 | 140858.88 | 4 | 45 | 453 | 4501 | 453 |  | 18 | 18% | 25354.5984
453-1-8 | Testing PTPs, ISTPs | 0 | 14080 | 14080 | 4 | 45 | 453 | 4501 | 453 |  | 18 | 18% | 2534.4
51-02 | FY05 LOE support | 4910.1304 | 12462.26 | 7552.1296 | 5 | 58 | 580 | 5801 |  |  | 3 | 3% | 226.5639
710.001 | Block Wall east side control room | 0 | 24201.6 | 24201.6 | 7 | 72 | 720 | 7201 |  | 10 | 10 | 10% | 2420.16
710.001 | Block Wall east side control room | 0 | 15372 | 15372 | 7 | 72 | 720 | 7201 |  | 10 | 10 | 10% | 1537.2
711B.050 | Complete Control Room Flooring | 0 | 2653.68 | 2653.68 | 7 | 72 | 720 | 7201 |  | 11 | 10 | 10% | 265.368
711B.050 | Complete Control Room Flooring | 0 | 2682.72 | 2682.72 | 7 | 72 | 720 | 7201 |  | 11 | 10 | 10% | 268.272
711B.050 | Complete Control Room Flooring | 0 | 2682.72 | 2682.72 | 7 | 72 | 720 | 7201 |  | 11 | 10 | 10% | 268.272
712.020 | Platform Parts | 0 | 1839.8 | 1839.8 | 7 | 73 | 730 | 7301 |  |  | 10 | 10% | 183.98
712.020 | Platform Parts | 0 | 2770.12 | 2770.12 | 7 | 73 | 730 | 7301 |  |  | 10 | 10% | 277.012
712.020 | Platform Parts | 0 | 21367.5 | 21367.5 | 7 | 73 | 730 | 7301 |  |  | 10 | 10% | 2136.75
712.030 | Miscs Hardware/Material | 0 | 48475 | 48475 | 7 | 73 | 730 | 7301 |  |  | 10 | 10% | 4847.5
712.008 | Update Platform Specification | 0 | 6416.8 | 6416.8 | 7 | 73 | 730 | 7301 |  | 25 | 24 | 24% | 1540.032
712.010 | Final Design | 0 | 22458.8 | 22458.8 | 7 | 73 | 730 | 7301 |  | 26 | 6 | 6% | 1347.528
712.010 | Final Design | 0 | 30705 | 30705 | 7 | 73 | 730 | 7301 |  | 26 | 6 | 6% | 1842.3
711A.040 | Platform nut plates | 0 | 26977.07 | 26977.07 | 7 | 73 | 730 | 7301 |  | 27 | 6 | 6% | 1618.6242
711A.040 | Platform nut plates | 0 | 1290.14 | 1290.14 | 7 | 73 | 730 | 7301 |  | 27 | 6 | 6% | 77.4084
613.030 | Test Cell copper ground plane cuts | 0 | 4471.2 | 4471.2 | 7 | 74 | 740 | 7401 | TCMS |  | 24 | 24% | 1073.088
613.030 | Test Cell copper ground plane cuts | 0 | 1281 | 1281 | 7 | 74 | 740 | 7401 | TCMS |  | 24 | 24% | 307.44
613.030 | Test Cell copper ground plane cuts | 0 | 4471.2 | 4471.2 | 7 | 74 | 740 | 7401 | TCMS |  | 24 | 24% | 1073.088
713.010 | General procurements | 0 | 19215 | 19215 | 7 | 74 | 740 | 7401 | TCMS |  | 24 | 24% | 4611.6
7502-001 | Test Cell 110v outlets | 0 | 16803.2 | 16803.2 | 7 | 74 | 740 | 7401 | TCMS |  | 24 | 24% | 4032.768
7502-002 | Test Cell 208v outlets | 0 | 8401.6 | 8401.6 | 7 | 74 | 740 | 7401 | TCMS |  | 24 | 24% | 2016.384
7502-010 | Ready Rooms (under control room) 110v outlets | 0 | 8401.6 | 8401.6 | 7 | 74 | 740 | 7401 | TCMS |  | 24 | 24% | 2016.384
714.010 | LOE FY05 | 28379.2605 | 72028.58 | 43649.3195 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 6547.3979
714.010 | LOE FY05 | 7282.5069 | 18483.52 | 11201.0131 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 1680.152
714.010 | LOE FY05 | 7667.3661 | 19460.32 | 11792.9539 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 1768.9431
714.020 | LOE FY06 prior to assy starting | 0 | 81540.29 | 81540.29 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 12231.0435
714.020 | LOE FY06 prior to assy starting | 0 | 20924.04 | 20924.04 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 3138.606
714.020 | LOE FY06 prior to assy starting | 0 | 21830.7 | 21830.7 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 3274.605
714.030 | LOE FY07 thru first plasma | 0 | 522897.08 | 522897.08 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 78434.562
714.030 | LOE FY07 thru first plasma | 0 | 342306.25 | 342306.25 | 7 | 74 | 742 | 7401 | P1 | 11 | 15 | 15% | 51345.9375
7501-05 | Construction Support Crew during machine assy | 0 | 308225.68 | 308225.68 | 7 | 75 | 750 | 7501 |  |  | 24 | 24% | 73974.1632
7501-05 | Construction Support Crew during machine assy | 0 | 546986.57 | 546986.57 | 7 | 75 | 750 | 7501 |  |  | 24 | 24% | 131276.7768
7501-06 | Construction Support Crew during e-beam mapping | 0 | 99710.51 | 99710.51 | 7 | 75 | 750 | 7501 |  |  | 24 | 24% | 23930.5224
7501-07 | Construction Support Crew during cryostat instl | 0 | 35833.64 | 35833.64 | 7 | 75 | 750 | 7501 |  |  | 24 | 24% | 8600.0736
7501-07 | Construction Support Crew during cryostat instl | 0 | 63587.24 | 63587.24 | 7 | 75 | 750 | 7501 |  |  | 24 | 24% | 15260.9376
7502-020 | Resurface TC floor | 0 | 18835.2 | 18835.2 | 7 | 75 | 750 | 7502 |  |  | 24 | 24% | 4520.448
7502-020 | Resurface TC floor | 0 | 14790 | 14790 | 7 | 75 | 750 | 7502 |  |  | 24 | 24% | 3549.6
7502-030 | TC Floor firesealing | 0 | 14126.4 | 14126.4 | 7 | 75 | 750 | 7502 |  |  | 24 | 24% | 3390.336
7502-035 | Control room firesealing | 0 | 9417.6 | 9417.6 | 7 | 75 | 750 | 7502 |  |  | 24 | 24% | 2260.224
7503-020 | Install & Level Support Base Plates | 0 | 11674.8 | 11674.8 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 2801.952
7503-020 | Install & Level Support Base Plates | 0 | 42504 | 42504 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 10200.96
7503-020 | Install & Level Support Base Plates | 0 | 14973.6 | 14973.6 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 3593.664
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 23349.6 | 23349.6 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 5603.904
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 85008 | 85008 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 20401.92
7503-030 | Install/Level FPA's and Spool Piece supports | 0 | 29947.2 | 29947.2 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 7187.328
7503-060 | Install Lower PF 4,5&6 into prelim position | 0 | 1996.48 | 1996.48 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 479.1552
7503-060 | Install Lower PF 4,5&6 into prelim position | 0 | 2833.6 | 2833.6 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 680.064
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 7783.2 | 7783.2 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 1867.968
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 28336 | 28336 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 6800.64
7503-070 | Install 3 Spool Pieces on fixt & test movement | 0 | 9982.4 | 9982.4 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 2395.776
7503-090 | Install local Platforms around FPA-1 | 0 | 7783.2 | 7783.2 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 1867.968
7503-090 | Install local Platforms around FPA-1 | 0 | 28336 | 28336 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 6800.64
7503-090 | Install local Platforms around FPA-1 | 0 | 9982.4 | 9982.4 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 2395.776
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 3891.6 | 3891.6 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 933.984
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 14168 | 14168 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 3400.32
7503-120 | Test movement of FPA-1& -2 & position checks. | 0 | 4991.2 | 4991.2 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 1197.888
7503-130 | Install local Platforms around FPA-2 | 0 | 7783.2 | 7783.2 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 1867.968
7503-130 | Install local Platforms around FPA-2 | 0 | 28336 | 28336 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 6800.64
7503-130 | Install local Platforms around FPA-2 | 0 | 9982.4 | 9982.4 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 2395.776
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 4669.92 | 4669.92 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 1120.7808
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 17001.6 | 17001.6 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 4080.384
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | 5989.44 | 5989.44 | 7 | 75 | 750 | 7503 | 75Z | 01 | 24 | 24% | 1437.4656
7503-170 | FPA Metrology Checks to Assure Alignment | 0 | 2334.96 | 2334.96 | 7 | 75 | 750 | 7503 | 75Z | 03 | 24 | 24% | 560.3904
7503-170 | FPA Metrology Checks to Assure Alignment | 0 | 1062.6 | 1062.6 | 7 | 75 | 750 | 7503 | 75Z | 03 | 24 | 24% | 255.024
7503-190 | Install local Platforms around FPA-3 | 0 | 7783.2 | 7783.2 | 7 | 75 | 750 | 7503 | 75Z | 04 | 24 | 24% | 1867.968
7503-190 | Install local Platforms around FPA-3 | 0 | 28336 | 28336 | 7 | 75 | 750 | 7503 | 75Z | 04 | 24 | 24% | 6800.64
7503-190 | Install local Platforms around FPA-3 | 0 | 9982.4 | 9982.4 | 7 | 75 | 750 | 7503 | 75Z | 04 | 24 | 24% | 2395.776
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 11674.8 | 11674.8 | 7 | 75 | 750 | 7503 | 75Z | 05 | 24 | 24% | 2801.952
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 63756 | 63756 | 7 | 75 | 750 | 7503 | 75Z | 05 | 24 | 24% | 15301.44
7503-180 | MC Interfaces: shim, ream holes ,bolt together | 0 | 14973.6 | 14973.6 | 7 | 75 | 750 | 7503 | 75Z | 05 | 24 | 24% | 3593.664
7503-200 | Mate-up and weld all VV-to-Spool interfaces | 0 | 14973.6 | 14973.6 | 7 | 75 | 750 | 7503 | 75Z | 06 | 24 | 24% | 3593.664
7503-200 | Mate-up and weld all VV-to-Spool interfaces | 0 | 63756 | 63756 | 7 | 75 | 750 | 7503 | 75Z | 06 | 24 | 24% | 15301.44
7503-240 | Bolt on preassembled pump duct | 0 | 4991.2 | 4991.2 | 7 | 75 | 750 | 7503 | 75Z | 16 | 24 | 24% | 1197.888
7503-240 | Bolt on preassembled pump duct | 0 | 14168 | 14168 | 7 | 75 | 750 | 7503 | 75Z | 16 | 24 | 24% | 3400.32
7503-260 | PTP Pumpdown & leak check VV | 0 | 9982.4 | 9982.4 | 7 | 75 | 750 | 7503 | 75Z | 16 | 24 | 24% | 2395.776
7503-260 | PTP Pumpdown & leak check VV | 0 | 42504 | 42504 | 7 | 75 | 750 | 7503 | 75Z | 16 | 24 | 24% | 10200.96
7503-210 | Fit-up all TF coils | 0 | 7783.2 | 7783.2 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 1867.968
7503-210 | Fit-up all TF coils | 0 | 42504 | 42504 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 10200.96
7503-210 | Fit-up all TF coils | 0 | 9982.4 | 9982.4 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 2395.776
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 4669.92 | 4669.92 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 1120.7808
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 17001.6 | 17001.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 4080.384
7503-270 | Raise lower PF 4,5&6 coils into final position | 0 | 5989.44 | 5989.44 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 1437.4656
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 4753.92 | 4753.92 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 1140.9408
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 17306.88 | 17306.88 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 4153.6512
7503-280 | Install Upper PF 4,5 & 6 coils | 0 | 6097.2 | 6097.2 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 1463.328
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 3225.28 | 3225.28 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 774.0672
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 11741.44 | 11741.44 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 2817.9456
7503-290 | Install PF Solenoid into position (U/L PF1,2,3) | 0 | 4136.64 | 4136.64 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 992.7936
7503-310 | Complete LN2 connections | 0 | 10341.6 | 10341.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 2481.984
7503-310 | Complete LN2 connections | 0 | 29353.6 | 29353.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 7044.864
7503-320 | Complete Elect Pwr connections | 0 | 20683.2 | 20683.2 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 4963.968
7503-320 | Complete Elect Pwr connections | 0 | 88060.8 | 88060.8 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 21134.592
7503-321 | Complete mag diag & machine I&C | 0 | 20683.2 | 20683.2 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 4963.968
7503-321 | Complete mag diag & machine I&C | 0 | 29353.6 | 29353.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 7044.864
7503-340 | Install Cryostat Base, vapor barrie& port boots | 0 | 10341.6 | 10341.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 2481.984
7503-340 | Install Cryostat Base, vapor barrie& port boots | 0 | 29353.6 | 29353.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 7044.864
7503-350 | Install Cryostat upper section,VB and port boots | 0 | 10341.6 | 10341.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 2481.984
7503-350 | Install Cryostat upper section,VB and port boots | 0 | 29353.6 | 29353.6 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 7044.864
7503-360 | Install Midplane Cryostat sections and port boot | 0 | 15512.4 | 15512.4 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 3722.976
7503-360 | Install Midplane Cryostat sections and port boot | 0 | 44030.4 | 44030.4 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 10567.296
7503-370 | Install Cryostat Circulation Duct | 0 | 5170.8 | 5170.8 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 1240.992
7503-370 | Install Cryostat Circulation Duct | 0 | 14676.8 | 14676.8 | 7 | 75 | 750 | 7503 | 75Z | 17 | 24 | 24% | 3522.432
730.8200 | PTP and Cooldown | 0 | 15797.6 | 15797.6 | 7 | 75 | 750 | 7503 | 75Z | 91 | 30 | 30% | 4739.28
730.8200 | PTP and Cooldown | 0 | 10341.6 | 10341.6 | 7 | 75 | 750 | 7503 | 75Z | 91 | 30 | 30% | 3102.48
730.8200 | PTP and Cooldown | 0 | 44030.4 | 44030.4 | 7 | 75 | 750 | 7503 | 75Z | 91 | 30 | 30% | 13209.12
713.020 | Lab Fab/Assy/Installation | 0 | 15390.43 | 15390.43 | 7 | 76 | 760 | 7601 |  |  | 24 | 24% | 3693.7032
713.020 | Lab Fab/Assy/Installation | 0 | 5289.43 | 5289.43 | 7 | 76 | 760 | 7601 |  |  | 24 | 24% | 1269.4632
713.020 | Lab Fab/Assy/Installation | 0 | 12511.89 | 12511.89 | 7 | 76 | 760 | 7601 |  |  | 24 | 24% | 3002.8536
713.030 | Tooling,assy fixtures,misc equipt | 0 | 84851.61 | 84851.61 | 7 | 76 | 760 | 7601 |  |  | 24 | 24% | 20364.3864
713.040 | General procurements | 0 | 63638.71 | 63638.71 | 7 | 76 | 760 | 7601 |  |  | 24 | 24% | 15273.2904
713.050 | Welding tools, materials & equipt | 0 | 56567.74 | 56567.74 | 7 | 76 | 760 | 7601 |  |  | 24 | 24% | 13576.2576
810.003 | Project Management Office PPPL FY05 | 131116.5493 | 332783.12 | 201666.5707 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 20166.6571
810.003 | Project Management Office PPPL FY05 | 81804.0215 | 207624.42 | 125820.3985 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 12582.0399
810.003 | Project Management Office PPPL FY05 | 18902.2288 | 47975.2 | 29072.9712 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 2907.2971
810.003 | Project Management Office PPPL FY05 | 3028.284 | 7686 | 4657.716 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 465.7716
810.003 | Project Management Office PPPL FY05 | 5248.08 | 13320 | 8071.92 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 807.192
810.003 | Project Management Office PPPL FY05 | 11263.7705 | 28588.25 | 17324.4795 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 1732.448
810.003 | Project Management Office PPPL FY05 | 15509.2 | 15509.2 | 0 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 0
810.003 | Project Management Office PPPL FY05 | 26900 | 26900 | 0 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 0
810.004 | Project Management Office PPPL FY06 | 0 | 369903.33 | 369903.33 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 36990.333
810.004 | Project Management Office PPPL FY06 | 0 | 244292.4 | 244292.4 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 24429.24
810.004 | Project Management Office PPPL FY06 | 0 | 42631.68 | 42631.68 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 4263.168
810.004 | Project Management Office PPPL FY06 | 0 | 2958 | 2958 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 295.8
810.004 | Project Management Office PPPL FY06 | 0 | 7248 | 7248 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 724.8
810.004 | Project Management Office PPPL FY06 | 0 | 31757.61 | 31757.61 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 3175.761
810.005 | Project Management OfficePPPL FY07 | 0 | 378470.43 | 378470.43 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 37847.043
810.005 | Project Management OfficePPPL FY07 | 0 | 249944 | 249944 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 24994.4
810.005 | Project Management OfficePPPL FY07 | 0 | 43621.76 | 43621.76 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 4362.176
810.005 | Project Management OfficePPPL FY07 | 0 | 2770 | 2770 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 277
810.005 | Project Management OfficePPPL FY07 | 0 | 7268 | 7268 | 8 | 81 | 810 | 8101 |  | 05 | 10 | 10% | 726.8
810.900 | Project Management Office PPPL FY08 | 0 | 322957.06 | 322957.06 | 8 | 81 | 810 | 8101 |  | 10 | 10 | 10% | 32295.706
810.900 | Project Management Office PPPL FY08 | 0 | 215687.16 | 215687.16 | 8 | 81 | 810 | 8101 |  | 10 | 10 | 10% | 21568.716
810.900 | Project Management Office PPPL FY08 | 0 | 33889.44 | 33889.44 | 8 | 81 | 810 | 8101 |  | 10 | 10 | 10% | 3388.944
810.900 | Project Management Office PPPL FY08 | 0 | 3696 | 3696 | 8 | 81 | 810 | 8101 |  | 10 | 10 | 10% | 369.6
810.909 | Project Management Office PPPL FY09 | 0 | 95401.78 | 95401.78 | 8 | 81 | 810 | 8101 |  | 10 | 10 | 10% | 9540.178
810.909 | Project Management Office PPPL FY09 | 0 | 99252.39 | 99252.39 | 8 | 81 | 810 | 8101 |  | 10 | 10 | 10% | 9925.239
810.909 | Project Management Office PPPL FY09 | 0 | 1880 | 1880 | 8 | 81 | 810 | 8101 |  | 10 | 10 | 10% | 188
810.103 | Project Management Office ORNL FY05 | 25063.8372 | 63613.8 | 38549.9628 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 3854.9963
810.103 | Project Management Office ORNL FY05 | 10541.5409 | 26755.18 | 16213.6391 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 1621.3639
810.103 | Project Management Office ORNL FY05 | 788 | 2000 | 1212 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 121.2
810.103 | Project Management Office ORNL FY05 | 1182 | 3000 | 1818 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 181.8
810.104 | Project Management Office ORNL FY06 | 0 | 48839.5 | 48839.5 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 4883.95
810.104 | Project Management Office ORNL FY06 | 0 | 22146.87 | 22146.87 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 2214.687
810.104 | Project Management Office ORNL FY06 | 0 | 2034 | 2034 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 203.4
810.104X | Project Management Office ORNL FY07 | 0 | 34002 | 34002 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 3400.2
810.104X | Project Management Office ORNL FY07 | 0 | 14444.32 | 14444.32 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 1444.432
810.104X | Project Management Office ORNL FY07 | 0 | 2068 | 2068 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 206.8
810.105X | Project Management Office ORNL FY08 | 0 | 34560 | 34560 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 3456
810.105X | Project Management Office ORNL FY08 | 0 | 0 | 0 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 0
810.105X | Project Management Office ORNL FY08 | 0 | 2104 | 2104 | 8 | 81 | 810 | 8102 |  |  | 10 | 10% | 210.4
820.003 | Proj engr FY05 | 106777.94 | 271010 | 164232.06 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 16423.206
820.003 | Proj engr FY05 | 4592.07 | 11655 | 7062.93 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 706.293
820.003 | Proj engr FY05 | 43611.7812 | 110689.8 | 67078.0188 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 6707.8019
820.003 | Proj engr FY05 | 5705.1594 | 14480.1 | 8774.9406 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 877.4941
820.003 | Proj engr FY05 | 5435.6713 | 13796.12 | 8360.4487 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 836.0449
820.003 | Proj engr FY05 | 48000 | 48000 | 0 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 0
820.004 | Proj engr FY06 | 0 | 301054.8 | 301054.8 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 30105.48
820.004 | Proj engr FY06 | 0 | 9060 | 9060 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 906
820.004 | Proj engr FY06 | 0 | 93146.76 | 93146.76 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 9314.676
820.004 | Proj engr FY06 | 0 | 16085.54 | 16085.54 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 1608.554
820.04X | Proj engr FY07 | 0 | 194581.52 | 194581.52 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 19458.152
820.04X | Proj engr FY07 | 0 | 9085 | 9085 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 908.5
820.04X | Proj engr FY07 | 0 | 31828.54 | 31828.54 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 3182.854
820.04X | Proj engr FY07 | 0 | 16457.49 | 16457.49 | 8 | 82 | 820 | 8202 |  | 20 | 10 | 10% | 1645.749
820.004Z | Proj engr FY08 | 0 | 201584.88 | 201584.88 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 20158.488
820.004Z | Proj engr FY08 | 0 | 9240 | 9240 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 924
820.004Z | Proj engr FY08 | 0 | 32975.53 | 32975.53 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 3297.553
820.004Z | Proj engr FY08 | 0 | 17050.88 | 17050.88 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 1705.088
820.005 | Proj engr FY09 | 0 | 104418.44 | 104418.44 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 10441.844
820.005 | Proj engr FY09 | 0 | 5640 | 5640 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 564
8205FY05 | System Engr Support FY05 | 78651.068 | 199622 | 120970.932 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 12097.0932
8205FY06 | Systems Engineering Support FY06 | 0 | 158420.91 | 158420.91 | 8 | 82 | 820 | 8202 |  | 21 | 10 | 10% | 15842.091
8203FY05 | Design Integration FY05 LOE | 41737.3065 | 105932.25 | 64194.9435 | 8 | 82 | 820 | 8203 |  | 50 | 10 | 10% | 6419.4944
8203FY05 | Design Integration FY05 LOE | 18555.9225 | 47096.25 | 28540.3275 | 8 | 82 | 820 | 8203 |  | 50 | 10 | 10% | 2854.0328
8203FY05 | Design Integration FY05 LOE | 18000 | 18000 | 0 | 8 | 82 | 820 | 8203 |  | 50 | 10 | 10% | 0
8203FY06 | Design Integration FY06 | 0 | 98123.1 | 98123.1 | 8 | 82 | 820 | 8203 |  | 60 | 10 | 10% | 9812.31
8203FY06 | Design Integration FY06 | 0 | 158420.91 | 158420.91 | 8 | 82 | 820 | 8203 |  | 60 | 10 | 10% | 15842.091
8203FY07 | Design Integration FY07 | 0 | 40139.59 | 40139.59 | 8 | 82 | 820 | 8203 |  | 70 | 10 | 10% | 4013.959
8203FY07 | Design Integration FY07 | 0 | 97304.66 | 97304.66 | 8 | 82 | 820 | 8203 |  | 70 | 10 | 10% | 9730.466
8204FY05 | Systems Analysis FY05 | 101113.5005 | 256633.25 | 155519.7495 | 8 | 82 | 820 | 8204 |  | 20 | 10 | 10% | 15551.9749
8204FY06 | Systems Analysis FY06 | 0 | 158420.91 | 158420.91 | 8 | 82 | 820 | 8204 |  | 20 | 10 | 10% | 15842.091
METFY06R | Metrology for FP & machine assy FY06 | 0 | 190178.52 | 190178.52 | 8 | 82 | 820 | 8205 |  |  | 25 | 25% | 47544.63
METFY07R | Metrology for FP & machine assy FY07 | 0 | 129614.38 | 129614.38 | 8 | 82 | 820 | 8205 |  |  | 25 | 25% | 32403.595
METFY08R | Metrology for FP & machine assy FY08 | 0 | 134260.2 | 134260.2 | 8 | 82 | 820 | 8205 |  |  | 25 | 25% | 33565.05
METFY05 | Dimensional control FY05 ECP24 | 5691.9808 | 49068.8 | 43376.8192 | 8 | 82 | 820 | 8205 |  | 20 | 25 | 25% | 10844.2048
METFY05 | Dimensional control FY05 ECP24 | 965.7 | 8325 | 7359.3 | 8 | 82 | 820 | 8205 |  | 20 | 25 | 25% | 1839.825
METFY052 | Dimensional control FY05 add'l increment | 0 | 49068.8 | 49068.8 | 8 | 82 | 820 | 8205 |  | 20 | 25 | 25% | 12267.2
METFY06 | Dimensional control FY06 | 0 | 150585.6 | 150585.6 | 8 | 82 | 820 | 8205 |  | 20 | 25 | 25% | 37646.4
99.05 | PPPL Allocations FY05 | 119262.618 | 302697 | 183434.382 | A | AA | AAA | 8998 |  |  | 10 | 10% | 18343.4382
99.05P | PPPL Allocations FY05 rebaeline re-estimate | 18971.8092 | 48151.8 | 29179.9908 | A | AA | AAA | 8998 |  |  | 10 | 10% | 2917.9991
99.06 | PPPL Allocations FY06 | 0 | 340474.8 | 340474.8 | A | AA | AAA | 8998 |  |  | 10 | 10% | 34047.48
99.07 | PPPL Allocations FY07 | 0 | 341437.41 | 341437.41 | A | AA | AAA | 8998 |  |  | 10 | 10% | 34143.741
99.08 | PPPL Allocations FY08 | 0 | 171438.96 | 171438.96 | A | AA | AAA | 8998 |  |  | 10 | 10% | 17143.896
|  | 3861444.4776 | 59474587.13 | 55613142.6524 | [8 empty] | 12242848.993

## Staffing
NCSX REBASELINE STAFFING | time axis 2005-10-01 to 2010-09-01
| B///CB - PPPL Project Clerical | 0.6 | 0.6 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5 | 0.4 | 0.5 | 0.5 | 0.4 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.3 | 0.2 | 0.4 | 0.3 | 0.3 | 0.4 | 0.4 | 0.3 | 0.4 | 0.3 | 0.4
| EA//EM - PPPL Analysis engineer | 5.6 | 5.5 | 4.9 | 5.4 | 5.5 | 12.9 | 7.5 | 7.5 | 6.7 | 6.4 | 5.9 | 5.6 | 6.1 | 6.1 | 5 | 6.6 | 6.2 | 6.6 | 5.9 | 6.7 | 6.4 | 4.9 | 5.3 | 4.8 | 6.2 | 5.7 | 4.7 | 5.9 | 5.1 | 5.5 | 4.1 | 4.1 | 3.9 | 4.2 | 4.4 | 3.8 | 3.6 | 3.4 | 2.8 | 3 | 2.7 | 2.6 | 2.2 | 2.2 | 2.1 | 2.8 | 2.2 | 2.3 | 2.7 | 2.2 | 2.5 | 2.4 | 2.2 | 2.4 | 2.4 | 2.3 | 1.9 | 2 | 1.9 | 1.9
| EA//SM - PPPL Designer | 0.8 | 1.4 | 1.6 | 2.2 | 2.7 | 6.5 | 4.7 | 6 | 4.7 | 4.2 | 3.3 | 2.8 | 2 | 1.9 | 1.6 | 2.1 | 1.6 | 1.6 | 2.5 | 2.7 | 2.7 | 2.2 | 1.7 | 1.5 | 4.6 | 4.4 | 3.4 | 4 | 2.7 | 2.3 | 2.3 | 2.3 | 2.3 | 2.6 | 2.7 | 1.5 | 1.4 | 1.5 | 0.9 | 0.9 | 0.7 | 0.6 | 0.7 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.2 | 0.1 | 0.1 | 0.1 | 0
| EC//EM - PPPL Comuter Engineer | 2005-10-01: 0; 2005-11-01: 0; 2005-12-01: 0; 2006-01-01: 0; 2006-02-01: 0; 2006-03-01: 0.1; 2006-04-01: 0; 2006-05-01: 0; 2006-06-01: 0.1; 2006-07-01: 0; 2006-08-01: 0.1; 2006-09-01: 0; 2008-09-01: 0.9; 2008-10-01: 2.2; 2008-11-01: 2.2; 2008-12-01: 2; 2009-01-01: 3.1; 2009-02-01: 3; 2009-03-01: 3.4; 2009-04-01: 4.1; 2009-05-01: 4.1; 2009-06-01: 4.1; 2009-07-01: 3.5; 2009-08-01: 3.3; 2009-09-01: 2.7; 2009-10-01: 1.7; 2009-11-01: 0.7; 2009-12-01: 0.9; 2010-01-01: 0.9; 2010-02-01: 0.8; 2010-03-01: 0.2
| EC//SM - PPPL Computer Senior Tech | 2009-01-01: 0.4; 2009-02-01: 0.6; 2009-03-01: 1.2; 2009-04-01: 1.9; 2009-05-01: 1.8; 2009-06-01: 1.8; 2009-07-01: 1.3; 2009-08-01: 1.2; 2009-09-01: 1; 2009-10-01: 0.5; 2009-11-01: 0.3
| EE//AM - | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| EE//EM - PPPL Electrical engineer | 0.1 | 0.2 | 0.2 | 0.3 | 0.3 | 1.5 | 1.3 | 1.3 | 0.9 | 1.1 | 0.5 | 0.2 | 0.4 | 0.5 | 0.4 | 0.4 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.3 | 0.4 | 0.2 | 2.4 | 2.3 | 2 | 2.7 | 2 | 1.7 | 1.6 | 1.4 | 1.3 | 1.3 | 1.7 | 1.7 | 2.8 | 2.7 | 1.9 | 2.5 | 2.1 | 1.6 | 1 | 0.8 | 0.7 | 0.8 | 0.7 | 0.7 | 1.5 | 1.4 | 2.4 | 2.3 | 2.1 | 1.6 | 1.4 | 1.3 | 1.4 | 1.5 | 1.3 | 1.4
| EE//SM - PPPL Electrical Senior Tech | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.6 | 0.2 | 0.2 | 0.1 | 0.1 | 0.6 | 0.7 | 0.5 | 0.6 | 0.5 | 0.8 | 0.5 | 0.6 | 0.6 | 0.6 | 0.8 | 0.6 | 1.6 | 1.5 | 0.9 | 1.3 | 1 | 1.1 | 1.3 | 1.9 | 1.9 | 2.6 | 2.8 | 1.9 | 3 | 2.5 | 1.8 | 3.1 | 2.7 | 2.5 | 3.1 | 3.2 | 3 | 2.3 | 2.2 | 1.4 | 1.5 | 1.3 | 1.5 | 1.4 | 1.3 | 1.4 | 1.4 | 1.3 | 1.4 | 1.5 | 1.3 | 1.4
| EE//TB - PPPL Electrical Technician | [6 empty] | 2 | 0.7 | 0.4 | 1.4 | 0.3 | 0.2 | 0.2 | 0.6 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.3 | 0.9 | 0.3 | 2.5 | 2.2 | 1 | 1.2 | 0.7 | 0.7 | 0.1 | 0.1 | 0.1 | 0.3 | 1.4 | 1.6 | 3.2 | 3.4 | 1.8 | 1.9 | 1.6 | 1 | 0.7 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 1.8 | 1.8 | 1.6 | 0.3
| EM//EM - PPPL FO&M Engineer | 2 | 1.9 | 1.5 | 2.9 | 2.7 | 4 | 3.4 | 2.6 | 2.3 | 2.1 | 3.2 | 2.9 | 1.9 | 1.9 | 1.3 | 1.7 | 0.8 | 1.3 | 1 | 1.2 | 1.3 | 1.3 | 1.6 | 1.1 | 2.5 | 2.4 | 1.9 | 2.7 | 2.5 | 2.8 | 2.7 | 3 | 2.5 | 2.9 | 3.2 | 3 | 4.1 | 3.4 | 2.4 | 4.1 | 4.3 | 4.5 | 4.2 | 3.8 | 3.5 | 3.6 | 3.4 | 3.5 | 3.9 | 3.7 | 6.2 | 5.4 | 4.3 | 3 | 1.7 | 1.6 | 1.7 | 1.8 | 1.6 | 1.7
| EM//SM - PPPL FO&M Senior Tech | 1.9 | 2.3 | 2.6 | 3.2 | 3.1 | 3.1 | 1.5 | 5 | 2.7 | 4.6 | 4.5 | 4.8 | 3.9 | 3.5 | 2.3 | 3.2 | 2.7 | 2.7 | 1.7 | 2.4 | 2.1 | 2.1 | 2.1 | 1.8 | 3.1 | 1.9 | 1.2 | 3.1 | 2.8 | 1.8 | 3.6 | 3.5 | 2.6 | 3.7 | 3.4 | 2.7 | 5.7 | 6.3 | 5.2 | 8.4 | 8.4 | 7.1 | 6.2 | 5.7 | 5.6 | 6.7 | 6.4 | 7.2 | 6.8 | 5.4 | 8 | 5 | 3.9 | 2.7 | 1.4 | 1.3 | 1.4 | 1.5 | 1.3 | 1.4
| EM//TB - PPPL FO&M Technician | 3.6 | 3.1 | 5.2 | 2.2 | 1.7 | 9.3 | 6.4 | 5.5 | 6.3 | 5.5 | 12.8 | 13.3 | 15.4 | 17.8 | 12.9 | 18.9 | 19.6 | 16.7 | 18.4 | 22.6 | 22.9 | 20 | 22.3 | 14.6 | 21.3 | 20.5 | 14.2 | 23.8 | 25.8 | 21.7 | 23.7 | 23.9 | 19.5 | 13.8 | 22.9 | 21.8 | 21.4 | 21.5 | 20.8 | 29.7 | 28.5 | 20.3 | 17 | 15.9 | 11.1 | 12 | 14 | 17.3 | 13.4 | 8.4 | 10 | 7.8 | 5.6 | 3.3 | 1.4 | 1.3 | 1.4 | 1.5 | 1.3 | 1.4
| FC//AM - PPPL P&CO am | 0.8 | 0.8 | 0.7 | 0.8 | 0.8 | 0.9 | 0.8 | 0.8 | 0.9 | 0.8 | 0.9 | 0.9 | 0.9 | 0.8 | 0.7 | 0.9 | 0.8 | 1 | 0.8 | 0.9 | 0.9 | 0.8 | 1 | 0.9 | 0.9 | 0.8 | 0.7 | 0.9 | 0.8 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 1 | 0.8 | 0.8 | 0.7 | 0.5 | 0.8 | 0.7 | 0.7 | 0.8 | 0.8 | 0.7 | 0.8 | 0.7 | 0.8 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| FC//EM - PPPL P&CO em | 0.7 | 0.6 | 0.5 | 0.7 | 0.6 | 0.7 | 0.7 | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.5 | 0.5 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.3 | 0.3 | 0.4 | 0.3 | 0.4 | 0.3 | 0.4 | 0.3 | 0.4 | 0.4 | 0.3 | 0
| ORNLAM - ORNL Admin | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0.1 | 0 | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0.1 | 0.1 | 0 | 0.1 | 0 | 0
| ORNLEM - ORNL Engineer | 5.4 | 4.9 | 4 | 5.1 | 6 | 20 | 9.7 | 8.1 | 6.7 | 5.6 | 6 | 5.4 | 2.5 | 2.3 | 2 | 2.4 | 2.1 | 2.4 | 2 | 2.2 | 2.2 | 2.6 | 2.3 | 2.1 | 1.6 | 1.4 | 1.1 | 1.5 | 2.3 | 2.3 | 2.7 | 2.8 | 2.7 | 3.3 | 3.6 | 2.7 | 1.9 | 1.7 | 1.3 | 2 | 1.4 | 0.9 | 0.9 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.8 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0
| ORNLRM - ORNL Scientist | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0.2 | 0.2 | 0.1 | 0.2 | 0.1 | 0.3 | 0.3 | 0.2 | 0.4 | 0.5 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
| R///RM2 - PPPL Scientist pdg2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.9 | 0.8 | 0.7 | 0.7 | 0.9 | 0.7 | 0.7 | 0.6 | 0.6 | 0.5 | 0.7 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.3 | 0.1 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.1 | 0.3 | 0.3 | 0.2 | 0.4 | 0.3 | 0.3 | 0.3 | 0.1 | [5 empty] | 0.1 | 1 | 1 | 0.9 | 0.2
| R///RM3 - PPPL Scientist pdg3 | 1 | 1 | 0.8 | 1 | 1 | 1.1 | 1 | 1 | 1.1 | 1 | 1.1 | 1.1 | 1 | 0.9 | 0.8 | 1 | 0.9 | 1.1 | 0.9 | 1 | 1 | 0.9 | 1.1 | 1 | 0.9 | 0.8 | 0.6 | 0.9 | 0.8 | 0.9 | 0.8 | 0.9 | 0.8 | 0.9 | 0.9 | 0.8 | 0.8 | 0.7 | 0.5 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| SH//TB - HP Techs | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.8 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.8 | 0.7 | 0.8 | 0.8 | 0.7 | 0.8 | 0.7 | 0.8 | 0.7 | 0.6 | 0.8 | 0.7 | 0.8 | 0.7 | 0.8 | 0.7 | 0.7 | 0.8 | 0.7 | 0.8 | 0.7 | 0.5 | 0.8 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7 | 0.8 | 0.7 | 0.7
| PPPL TECHS | 5.9 | 5.7 | 8.1 | 5.7 | 5.1 | 12.7 | 10.1 | 11.8 | 9.6 | 11.7 | 17.7 | 18.4 | 20.1 | 22.6 | 15.8 | 22.8 | 22.9 | 20.7 | 20.7 | 25.7 | 25.7 | 23 | 26.1 | 17.3 | 28.5 | 26.1 | 17.3 | 29.4 | 30.3 | 25.3 | 28.7 | 29.4 | 24.1 | 20.4 | 30.5 | 28 | 33.3 | 33.7 | 29.6 | 43.5 | 41.8 | 32.1 | 28.9 | 26.9 | 21.6 | 22.4 | 23.9 | 27 | 22.3 | 15.7 | 21.3 | 16 | 12.4 | 7.7 | 4.2 | 3.9 | 4.2 | 4.5 | 3.9 | 4.2
| PPPL ENGR | 7.7 | 7.6 | 6.6 | 8.6 | 8.5 | 18.5 | 12.2 | 11.4 | 10 | 9.6 | 9.7 | 8.7 | 8.4 | 8.5 | 6.7 | 8.7 | 7.2 | 8.1 | 7 | 8 | 7.8 | 6.5 | 7.3 | 6.1 | 11.1 | 10.4 | 8.6 | 11.3 | 9.6 | 10 | 8.4 | 8.5 | 7.7 | 8.4 | 9.3 | 9.4 | 12.7 | 11.7 | 9.1 | 12.7 | 12.1 | 12.1 | 11.5 | 10.9 | 10.4 | 10.7 | 9.6 | 9.2 | 9.8 | 8 | 12 | 11 | 9.4 | 7.2 | 5.5 | 5.2 | 5 | 5.3 | 4.8 | 5
| ORNL | 5.7 | 5.2 | 4.3 | 5.4 | 6.3 | 20.3 | 10 | 8.4 | 7 | 5.9 | 6.3 | 5.7 | 2.7 | 2.5 | 2.2 | 2.6 | 2.3 | 2.7 | 2.2 | 2.5 | 2.5 | 2.8 | 2.6 | 2.3 | 2 | 1.7 | 1.3 | 2 | 2.8 | 2.7 | 2.9 | 3.1 | 2.9 | 3.6 | 3.9 | 2.9 | 2.2 | 1.9 | 1.4 | 2.3 | 1.6 | 1.1 | 1.2 | 1 | 0.8 | 0.9 | 0.8 | 0.6 | 0.8 | 0.7 | 0.8 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0

## Milestones
NCSX Milestone Status
|  |  | CD-2 | CD-2 | CD-3 |  | New
|  |  | Baseline |  | Baseline | float | Baseline | Actual | master schedule | Milestone float
| Level I | CD-1 | 2003-05-01 | 0 | 2003-05-01 |  |  | 2003-05-01
M-0110 |  | CD-2 | 2004-02-01 | 0 | 2004-02-01 |  |  | 2004-02-01
M-0115 |  | CD-3 | 2004-09-30 | 0 | 2004-09-30 |  |  | 2004-10-30
0
1201-500 | Level II | Vacuum Vessel & Modular Coil Prel Dsn Rvw | 2003-10-07 | 0 | 2003-10-07 |  |  | 2003-10-07
1403-08 |  | Performance Baseline Review | 2003-11-18 | 0 | 2003-11-18 |  |  | 2003-11-18
1203-341 |  | Conduct VVSA FDR | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1403-51 |  | Mod Coil Winding Form Final Design Review | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19
1408-143.1 |  | Award MC Conductor Contract |  |  | 2004-12-19 |  |  | 2004-10-15
121-6-9 |  | Award VV Production Vendor | 2004-12-01 | -2 | 2004-10-15 |  |  | 2004-09-15
C-081 |  | Award MCWF Mfg Contract | 2004-11-01 | -1 | 2004-10-01 |  |  | 2004-09-15
C-121.1 |  | First MCWF Delivered | 2005-03-01 | 4 | 2005-07-30 | 0.5 | 2005-07-15 |  | 2005-06-13 | 1.0667
131-035 |  | Begin TF Coil fabrication activities | 2005-04-01 | 3 | 2005-07-30 | -2.0667 | 2005-09-30 |  | 2005-06-01 | 4.0333
P1-021.1 |  | Complete First Mod Coil Fabrication | 2005-08-31 | 6 | 2006-02-28 | -0.5 | 2006-03-15 |  | 2005-11-14 | 4.0333
121-038.1 |  | Vacuum Vessel Sectors Delivered | 2006-02-01 | 0 | 2006-02-28 | -2.5333 | 2006-05-15 |  | 2006-01-26 | 3.6333
C-501B1 |  | Last MCWF Delivered | 2006-08-01 | 4 | 2006-12-29 | -5.6 | 2007-06-15 |  | 2007-01-31 | 4.5
141-036 |  | PF Coils Awarded | 2006-06-01 | 7 | 2007-01-30 | -14.1667 | 2008-03-30 |  | 2007-10-27 | 5.1667
S3P1-101 |  | Begin Assembly of First Field Period | 2006-09-01 | 6 | 2007-03-30 | -3.1 | 2007-07-01 |  | 2007-02-01 | 5
131-038 |  | All TF Coils Delivered | 2007-01-01 | 4 | 2007-05-30 | -14.7667 | 2008-08-15 |  | 2008-03-07 | 5.3667
S4P3-115 |  | Last Field Period Assembled | 2007-06-01 | 3 | 2007-09-30 | -13.7333 | 2008-11-15 |  | 2008-06-26 | 4.7333
7503-250 |  | Begin Vac Vsl Pumpdown | 2007-09-01 | 2 | 2007-11-27 | -14.7333 | 2009-02-11 |  | 2008-09-11 | 5.1
7503-330 |  | Begin Cryostat Installation | 2007-11-01 | 2 | 2008-01-30 | -14.4333 | 2009-04-07 |  | 2008-11-07 | 5.0333
730.1250 |  | Operational Readiness | 2007-11-01 | 4 | 2008-03-30 | -14.2667 | 2009-06-01 |  | 2009-01-01 | 5.0333
920.004 |  | Begin Start-up Testing | 2008-03-31 | 0 | 2008-03-30 | -14.7667 | 2009-06-16 |  | 2009-01-16 | 5.0333
M-0120 |  | CD-4 | 2008-05-30 | 0 | 2008-05-30 | -14.2333 | 2009-07-31 |  | 2009-03-05 | 4.9333
0
1404-109.J | Joule | FY04 JOULE #1-Authorize Prototype Fab | 2003-12-20 | 0.33333 | 2003-12-30 |  |  | 2003-10-20 |  | 0
1406-040 |  | FY04 JOULE #2-Begin winding on 3D surface | 2004-03-01 | 1 | 2004-03-31 |  |  | 2004-01-30 |  | 0
1404-110.J |  | FY04 JOULE #3-Prototype Casting Ready for Machining | 2004-06-01 | 0.96667 | 2004-06-30 |  |  | 2004-05-26 |  | 0
C-081.1 |  | FY04 JOULE #4 - CD-3 Readiness | 2004-09-01 | 0.96667 | 2004-09-30 |  |  | 2004-09-15 |  | 0
1408-143.1 |  | FY05 JOULE #1- VVSA, MCWF and MC Copper Conductor Awarded |  | 1278.3667 | 2004-12-30 | 2.5333 |  | 2004-10-15 |  | 0
1406-017.3 |  | FY05 JOULE #2- Cmplt Assy of twisted racetrack |  | 1281.4 | 2005-03-31 | 1281.4 |  | 2005-03-30 |  | 0
1403-20 |  | FY05 JOULE #3- Mod Coil Winding Type C FDR |  | 1284.4333 | 2005-06-30 | 0 | 2005-06-30 |  |  | 1284.4333
P1-011J |  | FY05 JOULE #4- Complete Winding First MC |  | 1287.5 | 2005-09-30 | 0 | 2005-09-30 |  |  | 1287.5
0

## ECP24 ECPxxReconciliation
| NCSX rebaseline reconciliation | [9 empty] | FIRST PLASMA July 2009 | [13 empty] | S.O. (rates, BA driven schedule delays, LOE supervision, Project mngt) | Updated estimates | Cost Variance | total
wbs2 |  |  | ECP 14 | ECP 16 | change | description | ECP 18 | change | description | ECP 21 | ECP 29 | change | description | [6 empty] | WBS2 | DESC | ECPxx | increases |  | 10051.088 | 3302 | 6578.304 | 10619.848 |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | TOTAL
11 - In-Vessel Components |  | 111 - Limiters | 0.1 | 0.1 |  |  | 0.1 | 0 |  | 0.1 |  | 0 | [6 empty] | 11 - 11 - In-Vessel Components | 11 - 11 - In-Vessel Components | 111 - Limiters | 0.06 | [6 empty] | 11 - 11 - In-Vessel Components | 111 | 0.06 | [6 empty] | 0.06
| 12 - Vacuum Vessel Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
12 - Vacuum Vessel Systems |  | 121 - Vacuum Vessel Assembly | 7891.7 | 7906.3 | 14.6 | ECP 16 FY04 cost variance +14.6k | 8061.3 | 155 | .Increased Viola to 2 days /week oversight +$63k; Increased field weld joint full size sample =+$96k | 8061.3 | 8492.3 | 431 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 121 - Vacuum Vessel Assembly | 8360.69 | -131.61 |  | 41.544 |  |  |  | 12 - 12 - Vacuum Vessel Systems | 121 | 1217.44 | 1577.29 | 3780.95 | 1778.66 | 6.35 |  |  | 8360.69
12 - Vacuum Vessel Systems |  | 122 - Vacuum Vessel Thermal Insulation | 174.7 | 174.7 |  |  | 176.03 | 1.33 |  | 176.03 | 176.03 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 122 - Vacuum Vessel Thermal Insulation | 196.29 | 20.26 | [5 empty] | 12 - 12 - Vacuum Vessel Systems | 122 |  | 6.07 | 49.91 | 140.31 |  |  |  | 196.29
12 - Vacuum Vessel Systems |  | 123 - Vacuum Vessel Heating and Cooling Distrib | 375.7 | 375.7 |  |  | 373.37 | -2.33 |  | 373.37 | 373.37 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 123 - Vacuum Vessel Heating and Cooling Distrib | 430.72 | 57.35 | [5 empty] | 12 - 12 - Vacuum Vessel Systems | 123 |  | 3.63 | 49.53 | 377.56 |  |  |  | 430.72
12 - Vacuum Vessel Systems |  | 124 - Vacuum Vessel Supports | 62 | 62 |  |  | 97.63 | 35.63 | .Lateral supports +22k | 97.63 | 97.63 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 124 - Vacuum Vessel Supports | 110.76 | 13.13 | [5 empty] | 12 - 12 - Vacuum Vessel Systems | 124 |  | 5.99 | 64.92 | 39.13 | 0.72 |  |  | 110.76
12 - Vacuum Vessel Systems |  | 125 - Vacuum Vessel Local I&C | 27.3 | 27.3 |  |  | 29.04 | 1.74 |  | 29.04 | 29.04 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 125 - Vacuum Vessel Local I&C | 17.64 | -11.4 | [5 empty] | 12 - 12 - Vacuum Vessel Systems | 125 |  |  | 17.64 |  |  |  |  | 17.64
|  | subtotal | 8531.4 | 8546 | 14.6 |  | 8737.37 | 191.37 |  | 8737.37 | 9168.37 | 431 | [9 empty] | 9116.1 | -52.27 |  |  |  |  | 41.544
| 13 - Conventional Coils |  |  | 0 |  |  |  | 0 |  |  |  | 0
13 - Conventional Coils |  | 130 - Conventional Coil Design | 613.1 | 613.1 |  |  | 737.81 | 124.71 | Kalish re-estimate of new design | 737.81 | 849 | 111.19 | Completion of Prelim design and the re-estimate of final design tasks. | [6 empty] | 13 - 13 - Conventional Coils | 130 - Conventional Coil Design | 867.38 | 18.38 |  |  |  | 18.38 |  | 13 - 13 - Conventional Coils | 130 | 91.66 | 333.93 | 441.79 |  |  |  |  | 867.38
13 - Conventional Coils |  | 131 - TF Coils | 1458.8 | 1458.8 |  |  | 1594.58 | 135.78 | Kalish re-estimate of new design | 1594.58 | 1594.58 | 0 | [7 empty] | 13 - 13 - Conventional Coils | 131 - TF Coils | 2275.24 | 680.66 | TF Updated design $486 TF PPPL fab and oversight stretchout $$100. Casting fab and final assy $113. Testing after assembly $36 | 100 | 581 |  |  | 13 - 13 - Conventional Coils | 131 |  |  | 900.01 | 791.91 | 385.21 | 198.11 |  | 2275.24
13 - Conventional Coils |  | 132 - PF Coils | 1777.3 | 1777.3 |  |  | 1870.43 | 93.13 | Kalish re-estimate | 1870.43 | 1771 | -99.43 | [7 empty] | 13 - 13 - Conventional Coils | 132 - PF Coils | 1885.36 | 114.36 | PF dsn moved from FY05 to FY07 | 114 |  |  |  | 13 - 13 - Conventional Coils | 132 |  |  |  |  | 360.59 | 1524.77 |  | 1885.36
13 - Conventional Coils |  | 133 - External Trim Coils | 381.1 | 181.1 | -200 | ECP 16 simplification of trim coli sys -200k | 145.64 | -35.46 | Kalish re-estimate | 145.64 | 245 | 99.36 | [7 empty] | 13 - 13 - Conventional Coils | 133 - External Trim Coils | 257.67 | 12.67 | [5 empty] | 13 - 13 - Conventional Coils | 133 |  |  |  |  | 257.67 |  |  | 257.67
13 - Conventional Coils |  | 134 - Conventional Coil Local | 73.4 | 73.4 |  |  | 92.63 | 19.23 | Kalish re-estimate | 92.63 | 92.63 | 0 | [7 empty] | 13 - 13 - Conventional Coils | 134 - Conventional Coil Local | 91.87 | -0.76 | [5 empty] | 13 - 13 - Conventional Coils | 134 |  |  |  |  | 70.62 | 21.25 |  | 91.87
|  | subtotal | 4303.7 | 4103.7 | -200 |  | 4441.09 | 337.39 |  | 4441.09 | 4552.21 | 111.12 | [9 empty] | 5377.52 | 825.31 | Rates | 12 |  |  | 825.38
| 14 - Modular Coils |  |  | 0 |  |  |  | 0 |  |  |  | 0
14 - Modular Coils |  | 141 - Modular Coil Winding Form | 12788.6 | 12881.6 | 93 | ECP 16 FY04 cost variance +93 | 13180.68 | 299.08 | +$52k MCWF analysis, +85 EIO s/c,+54 JPP s/c,+79 title III MCWF fab | 13180.68 | 13180.68 | 0 | [7 empty] | 14 - 14 - Modular Coils | 141 - Modular Coil Winding Form | 13872.57 | 691.89 | MC assy hardware $677 | 37 | 640 |  |  | 14 - 14 - Modular Coils | 141 | 1128.23 | 3074.15 | 3961.35 | 4084.45 | 1624.39 |  |  | 13872.57
14 - Modular Coils |  | 142 - Modular Coil Windings and Assembly | 9438 | 9577 | 139 | ECP 16 FY04 cost variance +139. | 9614.03 | 37.03 | Chrzanowski/Meighan oversight of TRC +202k | 9853 | 10253 | 400 | [7 empty] | 14 - 14 - Modular Coils | 142 - Modular Coil Windings and Assembly | 11681.76 | 1428.76 | MC winding labor $97, Oversight Stretchout $499 Final Design $141,add'l copper $45, TRC ETC $54YTD | 499 | 337 |  |  | 14 - 14 - Modular Coils | 142 | 1028.98 | 1655.88 | 2849.78 | 3140.87 | 2609.9 | 396.35 |  | 11681.76
14 - Modular Coils |  | 143 - Modular Coil Local I&C | 121.2 | 121.2 |  |  | 120.42 | -0.78 |  | 120.42 | 120.42 | 0 | [7 empty] | 14 - 14 - Modular Coils | 143 - Modular Coil Local I&C | 86.11 | -34.31 | [5 empty] | 14 - 14 - Modular Coils | 143 |  |  | 19.25 | 31.96 | 32.09 | 2.81 |  | 86.11
14 - Modular Coils |  | 144 - Modular Coil Winding Facility & Fixtures | 2707.3 | 3214.3 | 507 | ECP 16 FY04 cost variance +507 | 3285.22 | 70.92 |  | 3285.22 | 3285.22 | 0 | [7 empty] | 14 - 14 - Modular Coils | 144 - Modular Coil Winding Facility & Fixtures | 3353.03 | 67.81 | [5 empty] | 14 - 14 - Modular Coils | 144 | 267.55 | 2598.03 | 487.45 |  |  |  |  | 3353.03
|  | subtotal | 25055.1 | 25794.1 | 739 |  | 26200.35 | 406.25 |  | 26439.32 | 26839.32 | 400 | [9 empty] | 28993.47 | 2154.15 | YTD CV 138 misc rates/s.o. $503 | 503 |  | 138 | 2154
| 15 - Structures |  |  | 0 |  |  |  | 0 |  |  |  | 0
15 - Structures |  | 151 - Coil Support Structure | 1447.8 | 1447.8 |  |  | 1380.71 | -67.09 | Kalish re-estimate | 1380.71 | 1380.71 | 0 | [7 empty] | 15 - 15 - Structures | 151 - Coil Support Structure | 1412.96 | 32.25 | Rate Variance | 52 |  | -20 | 32 | 15 - 15 - Structures | 151 |  | 34.61 |  | 186.87 | 1186.69 | 4.79 |  | 1412.96
| 16 - Coil Services |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | [10 empty] | 0
16 - Coil Services |  | 161 - LN2 Distribution | 337.5 | 337.5 |  |  | 338.11 | 0.61 |  | 338.11 | 338.11 | 0 | [7 empty] | 16 - 16 - Coil Services | 161 - LN2 Distribution | 373.54 | 35.43 | [5 empty] | 16 - 16 - Coil Services | 161 |  |  |  |  | 175.96 | 195.94 | 1.64 | 373.54
16 - Coil Services |  | 162 - Electrical Leads | 621.3 | 621.3 |  |  | 619.03 | -2.27 |  | 619.03 | 619.03 | 0 | [7 empty] | 16 - 16 - Coil Services | 162 - Electrical Leads | 685.66 | 66.63 | [5 empty] | 16 - 16 - Coil Services | 162 |  |  |  |  | 222.04 | 463.62 |  | 685.66
16 - Coil Services |  | 163 - Coil Protection System | 78.1 | 78.1 |  |  | 78.86 | 0.76 |  | 78.86 | 78.86 | 0 | [7 empty] | 16 - 16 - Coil Services | 163 - Coil Protection System | 86.3 | 7.44 | [5 empty] | 16 - 16 - Coil Services | 163 |  |  |  |  | 86.3 |  |  | 86.3
|  | subtotal | 1036.9 | 1036.9 |  |  | 1036 | -0.9 |  | 1036 | 1036 | 0 | [9 empty] | 1145.5 | 109.5 | Rate Variance | 110 |  |  | 110
| 17 - Cryostat and Base Support Structure |  |  | 0 |  |  |  | 0 |  |  |  | 0
17 - Cryostat and Base Support Structure |  | 171 -Cryostat | 862.9 | 862.9 |  |  | 877.69 | 14.79 |  | 877.69 | 877.69 | 0 | [7 empty] | 17 - 17 - Cryostat and Base Support Structure | 171 -Cryostat | 934.23 | 56.54 | [5 empty] | 17 - 17 - Cryostat and Base Support Structure | 171 | 12.18 | 59.33 | 72.67 |  | 253.69 | 528.93 | 7.43 | 934.23
17 - Cryostat and Base Support Structure |  | 172 - Base Support Structure | 438.2 | 438.2 |  |  | 443.45 | 5.25 |  | 443.45 | 443.45 | 0 | [7 empty] | 17 - 17 - Cryostat and Base Support Structure | 172 - Base Support Structure | 427.01 | -16.44 | [5 empty] | 17 - 17 - Cryostat and Base Support Structure | 172 |  | 23.93 | 72.74 | 15.28 | 308.28 | 6.78 |  | 427.01
|  | 173-Spacer manipulator | [8 empty] | 0 | [8 empty] | 17 - 17 - Cryostat and Base Support Structure | 173 - Spacer Manipulator | 0 | 0
|  | subtotal | 1301.1 | 1301.1 |  |  | 1321.14 | 20.04 |  | 1321.14 | 1321.14 | 0 | [9 empty] | 1361.24 | 40.1 | Rate Variance | 40 |  |  | 40
| 18 - Field Period Assembly |  |  | 0 |  |  |  | 0 |  |  |  | 0
18 - Field Period Assembly |  | 181 - Field Period Assembly Planning/Oversight | 1379.3 | 1379.3 |  |  | 1014.4 | -364.9 | Reduced Viola to .7 fte during FP assy.-$175k. $190 trabsferred to wbs185 | 1014.4 | 1014.4 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 181 - Field Period Assembly Planning/Oversight | 1505.27 | 490.87 | HP stretchout $243, FP assy oversight stretchout $230 | 473 |  |  |  | 18 - 18 - Field Period Assembly | 181 | 60.8 | 164.56 | 146.16 | 266.85 | 425.88 | 441.02 |  | 1505.27
18 - Field Period Assembly |  | 182 - TFTR Test Cell Area preparations | 92.9 | 92.9 |  |  | 1e-05 | -92.9 | part of FP assy | 1e-05 | 1e-05 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 182 - TFTR Test Cell Area preparations | 35.47 | 35.47 | TFTR test cell realestate clearout and fixt assy (crane oper) |  | 35 |  |  | 18 - 18 - Field Period Assembly | 182 |  |  | 18.56 | 16.91 |  |  |  | 35.47
18 - Field Period Assembly |  | 183 - Receive Inspect and Test Coils | 77.4 | 77.4 |  |  | 79.12 | 1.72 |  | 79.12 | 79.12 | 0 | [9 empty] | 0 | -79.12
18 - Field Period Assembly |  | 184 - Receive Inspect and Test VV | 326.3 | 326.3 |  |  | 530.14 | 203.84 | +202k increased cost for stud instl, cooling tubes, magnetics instl, | 530.14 | 530.14 | 0 | [9 empty] | 0 | -530.14
18 - Field Period Assembly |  | 185 - Assemble Field Periods | 1509.4 | 1509.4 |  |  | 1818.56 | 309.16 | +$129 MC sub-assy, | 1818.56 | 1818.56 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 185 - Assemble Field Periods | 2134.72 | 316.16 | Learning curve on last FP assy |  | -118 |  |  | 18 - 18 - Field Period Assembly | 185 |  |  |  | 200.83 | 1072.45 | 861.44 |  | 2134.72
18 - Field Period Assembly |  | 186 - Tooling Design and Fabrication | 1217.2 | 1217.2 |  |  | 1200.04 | -17.16 |  | 1200.04 | 1200.04 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 186 - Tooling Design and Fabrication | 1537.88 | 337.84 | MC turning fixture fabrication $350 | 76 | 262 |  |  | 18 - 18 - Field Period Assembly | 186 |  |  | 626.74 | 730.29 | 170.38 | 10.47 |  | 1537.88
18 - Field Period Assembly |  | 187 - Measurement Systems | 463.2 | 463.2 |  |  | 475.83 | 12.63 |  | 475.83 | 475.83 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 187 - Measurement Systems | 511.75 | 35.92 | [5 empty] | 18 - 18 - Field Period Assembly | 187 |  | 197.99 | 184.4 | 87.46 | 13.71 | 13.82 | 14.37 | 511.75
|  | subtotal | 5065.7 | 5065.7 |  |  | 5118.09 | 52.39 |  | 5118.09 | 5118.09 | 0 | [9 empty] | 5725.09 | 607 | YTD CV -$140 misc rates | 12 |  | -133 | 607
| 19 - Stellarator Core Management and Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0
19 - Stellarator Core Management and Integration |  | 191 - Stellarator Core Management & Oversight | 1083 | 1113 | 30 | ECP 16 FY04 cost variance +30 | 946.44 | -166.56 |  | 946.44 | 946.44 | 0 | [7 empty] | 19 - 19 - Stellarator Core Management and Integration | 191 - Stellarator Core Management & Oversight | 1041.61 | 95.17 | LOE Stretchout (Brad Nelson) | 141 |  |  |  | 19 - 19 - Stellarator Core Management and Integration | 191 | 187.09 | 131.5 | 178.83 | 193.87 | 198.95 | 96.59 | 54.78 | 1041.61
19 - Stellarator Core Management and Integration |  | 192 - Stellarator Core Integration & Analysis | 1568.5 | 1568.5 | 0 |  | 1474.58 | -93.92 | Demo method for determining current center +88.Moved Brooks to WBS 82 -158 | 1474.58 | 1474.58 | 0 | [7 empty] | 19 - 19 - Stellarator Core Management and Integration | 192 - Stellarator Core Integration & Analysis | 1710.42 | 235.84 | LOE Stretchout Mike Cole | 245 |  |  |  | 19 - 19 - Stellarator Core Management and Integration | 192 | 67.07 | 511.94 | 425.07 | 303.61 | 155.93 | 148.15 | 98.65 | 1710.42
|  | subtotal | 2651.5 | 2681.5 | 30 |  | 2421.02 | -260.48 |  | 2421.02 | 2421.02 | 0 | [9 empty] | 2752.03 | 331.01 |  |  |  | -55 | 331
|  | SUBTOTAL WBS 1 | 49393.3 | 49976.9 | 583.6 |  | 50655.87 | 678.97 |  | 50894.84 | 51836.86 | 942.12 | [9 empty] | 55883.97 | 4047.05 |  |  |  |  | 4140.924
21 - Fueling Systems | 21 - Fueling Systems |  | 140 | 80 | -60 | ECP 16 simplification offueling sys | 80.72 | 0.72 |  | 80.72 | 80.72 | 0 | [7 empty] | 21 - 21 - Fueling Systems |  | 86.54 | 5.82 | [5 empty] | 21 - 21 - Fueling Systems | [5 empty] | 51.65 | 34.89 |  | 86.54
22 - Torus Vacuum Pumping Systems | 22 - Torus Vacuum Pumping Systems |  | 388.1 | 388.1 |  |  | 388.7 | 0.6 |  | 388.7 | 388.7 | 0 | [7 empty] | 22 - 22 - Torus Vacuum Pumping Systems |  | 412.56 | 23.86 | [5 empty] | 22 - 22 - Torus Vacuum Pumping Systems |  | 63.67 |  |  |  | 123.31 | 225.58 |  | 412.56
25 - Neutral Beam Injection System | 25 - Neutral Beam Injection System |  | 308.9 | 308.9 | 0 |  | 308.9 | 0 |  | 308.9 | 308.9 | 0 | [7 empty] | 25 - 25 - Neutral Beam Injection System | 250 - Neutral Beam Injection System | 284.37 | -24.53 | [5 empty] | 25 - 25 - Neutral Beam Injection System | 250 | 123 | 161.37 | [5 empty] | 284.37
|  | SUBTOTAL WBS 2 | 837 | 777 | -60 |  | 778.32 | 1.32 |  | 778.32 | 778.32 | 0 | [9 empty] | 783.47 | 5.15 |  | 27 |  | -22 | 5
31 - Magnetic Diagnostics | 31 - Magnetic Diagnostics |  | 455.6 | 455.6 |  |  | 413.8 | -41.8 | Deleted $41k for install of sensors and mag diag. Alreadyy incl in wbs 184 | 413.8 | 413.8 | 0 | [7 empty] | 31 - 31 - Magnetic Diagnostics |  | 426.44 | 12.64 | [5 empty] | 31 - 31 - Magnetic Diagnostics |  |  |  | 206.18 | 137.7 | 76.15 | 6.41 |  | 426.44
36 - Edge and Divertor Diagnostics | 36 - Edge and Divertor Diagnostics |  | 43.3 | 43.3 |  |  | 42.9 | -0.4 |  | 42.9 | 42.9 | 0 | [7 empty] | 36 - 36 - Edge and Divertor Diagnostics |  | 45.95 | 3.05 | [5 empty] | 36 - 36 - Edge and Divertor Diagnostics | [5 empty] | 5.92 | 40.03 |  | 45.95
38 - Electron Beam (EB) Mapping | 38 - Electron Beam (EB) Mapping |  | 295.3 | 295.3 |  |  | 290.6 | -4.7 |  | 290.6 | 290.6 | 0 | [7 empty] | 38 - 38 - Electron Beam (EB) Mapping |  | 310.09 | 19.49 | [5 empty] | 38 - 38 - Electron Beam (EB) Mapping | [6 empty] | 310.09 |  | 310.09
39 - Diagnostics Integration | 39 - Diagnostics Integration |  | 366.7 | 366.7 |  |  | 369.4 | 2.7 |  | 369.4 | 369.4 | 0 | [7 empty] | 39 - 39 - Diagnostics Integration |  | 360.52 | -8.88 | [5 empty] | 39 - 39 - Diagnostics Integration |  | 155.45 | 65 | 66.36 | 73.71 |  |  |  | 360.52
|  | SUBTOTAL WBS 3 | 1160.9 | 1160.9 |  |  | 1116.7 | -44.2 |  | 1116.7 | 1116.7 | 0 | [9 empty] | 1143 | 26.3 |  | 45 |  | -19 | 26
| 41 - AC Power |  |  | 0 |  |  |  | 0 |  |  |  | 0
41 - AC Power |  | 411 - Auxliary AC Power Systems | 471.1 | 471.1 |  |  | 439.83 | -31.27 | eliminated outlets on 2nd level | 439.83 | 439.83 | 0 | [7 empty] | 41 - 41 - AC Power | 411 - Auxliary AC Power Systems | 382.03 | -57.8 | [5 empty] | 41 - 41 - AC Power | 411 |  | 81.44 |  | 152.28 | 148.31 |  |  | 382.03
41 - AC Power |  | 412 - Experimental AC Power Systems | 42.7 | 42.7 |  |  | 45 | 2.3 |  | 45 | 45 | 0 | [7 empty] | 41 - 41 - AC Power | 412 - Experimental AC Power Systems | 48.14 | 3.14 | [5 empty] | 41 - 41 - AC Power | 412 |  |  |  |  | 18.44 | 29.7 |  | 48.14
| 43 - DC Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [10 empty] | 0
43 - DC Systems |  | 431 - C-Site DC Systems | 523.6 | 523.6 |  |  | 445.5 | -78.1 |  | 445.5 | 445.5 | 0 | [7 empty] | 43 - 43 - DC Systems | 431 - C-Site DC Systems | 453.94 | 8.44 | [5 empty] | 43 - 43 - DC Systems | 431 |  |  | 232.56 | 5.1 | 216.28 |  |  | 453.94
43 - DC Systems |  | 432 - D-to-C Site DC Systems | 453.1 | 14 | -439.1 | ECP 16 reclassification to non MIE |  | -14 |  |  | 0 | 0 | [9 empty] | 0 | 0
43 - DC Systems |  | 433 - D-Site DC Systems | 13.4 | 13.4 |  |  |  | -13.4 |  |  | 0 | 0 | [9 empty] | 0 | 0
| 44 - Control and protection Systems |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | [10 empty] | 0
44 - Control and protection Systems |  | 441 - Electrical Interlocks | 330.4 | 330.4 |  |  | 343.5 | 13.1 |  | 343.5 | 343.5 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 441 - Electrical Interlocks | 377.67 | 34.17 | [5 empty] | 44 - 44 - Control and protection Systems | 441 |  |  |  |  | 106.45 | 253.32 | 17.9 | 377.67
44 - Control and protection Systems |  | 442 - Kirk Key Interlocks | 90.2 | 90.2 |  |  | 77.8 | -12.4 |  | 77.8 | 77.8 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 442 - Kirk Key Interlocks | 82.18 | 4.38 | [5 empty] | 44 - 44 - Control and protection Systems | 442 |  |  |  |  | 74.86 | 7.32 |  | 82.18
44 - Control and protection Systems |  | 443 - Real Time Control Systems | 12.8 | 12.8 |  |  | 13.3 | 0.5 |  | 13.3 | 13.3 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 443 - Real Time Control Systems | 14.27 | 0.97 | [5 empty] | 44 - 44 - Control and protection Systems | 443 |  |  |  |  | 11.26 | 3.01 |  | 14.27
44 - Control and protection Systems |  | 444 - Instrument Systems | 349.1 | 349.1 |  |  | 294.2 | -54.9 |  | 294.2 | 294.2 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 444 - Instrument Systems | 312.66 | 18.46 | [5 empty] | 44 - 44 - Control and protection Systems | 444 |  |  |  |  | 219.02 | 93.64 |  | 312.66
44 - Control and protection Systems |  | 445 - Coil protection Systems | 366.9 | 366.9 |  |  | 485.9 | 119 | Increased scope from Raki | 485.9 | 485.9 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 445 - Coil protection Systems | 522.1 | 36.2 | [5 empty] | 44 - 44 - Control and protection Systems | 445 |  | 1.05 |  | 61.03 | 382.57 | 77.45 |  | 522.1
| 45 - Power System Design and Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [10 empty] | 0
45 - Power System Design and Integration |  | 451 - System Design and Interfaces | 510 | 510 |  |  | 518.34 | 8.34 |  | 518.34 | 518.34 | 0 | [7 empty] | 45 - 45 - Power System Design and Integration | 451 - System Design and Interfaces | 520.34 | 2 | [5 empty] | 45 - 45 - Power System Design and Integration | 451 | 112.34 | 29.89 | 155.93 | 33.61 | 105.02 | 83.55 |  | 520.34
45 - Power System Design and Integration |  | 452 - Electrical Systems Support | 240.2 | 240.2 |  |  | 243.96 | 3.76 |  | 243.96 | 243.96 | 0 | [7 empty] | 45 - 45 - Power System Design and Integration | 452 - Electrical Systems Support | 261.74 | 17.78 | [5 empty] | 45 - 45 - Power System Design and Integration | 452 |  |  |  |  | 119.12 | 142.62 |  | 261.74
45 - Power System Design and Integration |  | 453 - System Testing (PTP's) | 302.4 | 302.4 |  |  | 305.49 | 3.09 |  | 305.49 | 305.49 | 0 | [7 empty] | 45 - 45 - Power System Design and Integration | 453 - System Testing (PTP's) | 324.72 | 19.23 | [5 empty] | 45 - 45 - Power System Design and Integration | 453 |  |  |  |  | 103.97 | 220.75 |  | 324.72
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
46 - FCPC Building Modifications | 46 - FCPC Building Modifications |  | 1.3 | 1.3 | 0 |  | 1.3 | 0 |  | 1.3 | 1.3 | 0 | [7 empty] | 46 - 46 - FCPC Building Modifications | 460 | 1.3 | 0 | [5 empty] | 46 - 46 - FCPC Building Modifications | 460 | 1.3 | [6 empty] | 1.3
|  | SUBTOTAL WBS 4 | 3707.2 | 3268.1 | -439.1 |  | 3214.12 | -53.98 |  | 3214.12 | 3214.12 | 0 | [9 empty] | 3301.09 | 86.97 |  | 170 |  | -83 | 87
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
51 - TCP/IP Infrastructure Systems | 51 - TCP/IP Infrastructure Systems |  | 292.9 | 292.9 |  |  | 288.9 | -4 |  | 288.9 | 288.9 | 0 | [7 empty] | 51 - 51 - TCP/IP Infrastructure Systems |  | 310.59 | 21.69 | [5 empty] | 51 - 51 - TCP/IP Infrastructure Systems |  | 11.9 | 16 |  |  |  | 282.69 |  | 310.59
52 - Central Instrumentation & Control | 52 - Central Instrumentation & Control |  | 660.7 | 660.7 |  |  | 569.3 | -91.4 |  | 569.3 | 569.3 | 0 | [7 empty] | 52 - 52 - Central Instrumentation & Control |  | 610.92 | 41.62 | [5 empty] | 52 - 52 - Central Instrumentation & Control | [5 empty] | 11.36 | 494.87 | 104.69 | 610.92
53 - Data Acquisition & Facility Computing | 53 - Data Acquisition & Facility Computing |  | 414.9 | 414.9 |  |  | 328.4 | -86.5 |  | 328.4 | 328.4 | 0 | [7 empty] | 53 - 53 - Data Acquisition & Facility Computing |  | 351.02 | 22.62 | [5 empty] | 53 - 53 - Data Acquisition & Facility Computing | [5 empty] | 12.07 | 318.95 | 20 | 351.02
54 - Facility Timing & Synchronization | 54 - Facility Timing & Synchronization |  | 292 | 292 |  |  | 206.8 | -85.2 |  | 206.8 | 206.8 | 0 | [7 empty] | 54 - 54 - Facility Timing & Synchronization |  | 220.96 | 14.16 | [5 empty] | 54 - 54 - Facility Timing & Synchronization | [6 empty] | 220.96 |  | 220.96
55 - Real Time Plasma & Power Supply Control Sys | 55 - Real Time Plasma & Power Supply Control Sys |  | 153.7 | 153.7 |  |  | 151.2 | -2.5 |  | 151.2 | 151.2 | 0 | [7 empty] | 55 - 55 - Real Time Plasma & Power Supply Control Sys |  | 161.65 | 10.45 | [5 empty] | 55 - 55 - Real Time Plasma & Power Supply Control Sys | [6 empty] | 161.65 |  | 161.65
56 - Central Safety Interlock Systems | 56 - Central Safety Interlock Systems |  | 361.7 | 361.7 |  |  | 357.7 | -4 |  | 357.7 | 357.7 | 0 | [7 empty] | 56 - 56 - Central Safety Interlock Systems |  | 381.94 | 24.24 | [5 empty] | 56 - 56 - Central Safety Interlock Systems | [6 empty] | 381.94 |  | 381.94
58 - Central I&C management and Integration | 58 - Central I&C management and Integration |  | 12.9 | 12.9 |  |  | 12.9 | 0 |  | 12.9 | 12.9 | 0 | [7 empty] | 58 - 58 - Central I&C management and Integration |  | 12.46 | -0.44 | [5 empty] | 58 - 58 - Central I&C management and Integration |  |  |  | 12.46 |  |  |  |  | 12.46
|  | SUBTOTAL WBS 5 | 2188.8 | 2188.8 |  |  | 1915.2 | -273.6 |  | 1915.2 | 1915.2 | 0 | [9 empty] | 2049.54 | 134.34 |  | 130 |  | 4 | 134
| 61 - Water Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
61 - Water Systems |  | 611 - C-Site Cooling System | 153.3 | 153.3 |  |  | 151.1 | -2.2 |  | 151.1 | 151.1 | 0 | [7 empty] | 61 - 61 - Water Systems | 611 - C-Site Cooling System | 0 | -151.1 | Full c-site water system not req'd for first plasma |  | -151
61 - Water Systems |  | 612 - NB Water Cooling Systems | 239.9 | -0.1 | -240 | ECP 16 not req'd for CD-4. |  | 0.1 |  |  | 0 | 0 | [10 empty] | 0
61 - Water Systems |  | 613 - Vacuum Pumping System | 100 | 100 |  |  | 89.4 | -10.6 |  | 89.4 | 89.4 | 0 | [7 empty] | 61 - 61 - Water Systems | 613 - Vacuum Pumping System | 94.51 | 5.11 | [5 empty] | 61 - 61 - Water Systems | 613 | [5 empty] | 94.51 |  | 94.51
61 - Water Systems |  | 614 - Bakeout Water System | 38.5 | 0 | -38.5 | ECP 16 not req'd for CD-4. |  | 0 |  |  | 0 | 0 | [10 empty] | 0
| 62 - Cryogenic Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
62 - Cryogenic Systems |  | 621 - LN2-LHe Supply System | 224.9 | 224.9 |  |  | 220.9 | -4 |  | 220.9 | 220.9 | 0 | [7 empty] | 62 - 62 - Cryogenic Systems | 621 - LN2-LHe Supply System | 233.05 | 12.15 | [5 empty] | 62 - 62 - Cryogenic Systems | 621 |  |  |  |  | 15.89 | 217.16 |  | 233.05
62 - Cryogenic Systems |  | 622 - LN2 Coil Cooling Supply |  | 0 |  |  |  | 0 |  |  | 0 | 0 | [7 empty] | 62 - 62 - Cryogenic Systems | 622 - LN2 Coil Cooling Supply |  | 0 | [5 empty] | 62 - 62 - Cryogenic Systems | 622
62 - Cryogenic Systems |  | 623 - GN2 Cryostat Cooling System | 222.5 | 222.5 |  |  | 218.7 | -3.8 |  | 218.7 | 218.7 | 0 | [7 empty] | 62 - 62 - Cryogenic Systems | 623 - GN2 Cryostat Cooling System | 230.22 | 11.52 | [5 empty] | 62 - 62 - Cryogenic Systems | 623 |  |  |  |  | 27.34 | 202.88 |  | 230.22
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [10 empty] | 0
63 - Utility Systems | 63 - Utility Systems |  | 122.7 | 122.7 |  |  | 103.5 | -19.2 |  | 103.5 | 103.5 | 0 | [6 empty] | 63 - 63 - Utility Systems |  | 109.2996 | 109.3 | 5.8 | [5 empty] | 63 - 63 - Utility Systems | [6 empty] | 109.3 |  | 109.3
| 65 - Facility Systems Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [10 empty] | 0
65 - Facility Systems Integration |  | 612 - NB Water Cooling Systems | 9.4 | 9.4 |  |  | 9.4 | 0 |  | 9.4 | 9.4 | 0 | [7 empty] | 65 - 65 - Facility Systems Integration | 612 - NB Water Cooling Systems | 9.38 | -0.02 | [5 empty] | 65 - 65 - Facility Systems Integration | 612 | 9.38 | [6 empty] | 9.38
65 - Facility Systems Integration |  | 650 - Facility Systems Integration | 32.2 | 32.2 | 0 |  | 32.2 | 0 |  | 32.2 | 32.2 | 0 | [7 empty] | 65 - 65 - Facility Systems Integration | 650 - Facility Systems Integration | 15 | -17.2 | [5 empty] | 65 - 65 - Facility Systems Integration | 650 |  | 15 | [5 empty] | 15
|  | SUBTOTAL WBS 6 | 1143.4 | 864.9 | -278.5 |  | 825.2 | -39.7 |  | 825.2 | 825.2 | 0 | [9 empty] | 691.46 | -133.74 |  | 34 |  | -17 | -134
71 - Shield Wall Seismic Modifications | 71 - Shield Wall Seismic Modifications |  | 32.2 | 32.2 |  |  | 32.2 | 0 |  | 32.2 | 32.2 | 0 | [7 empty] | 71 - 71 - Shield Wall Seismic Modifications | 740 - Machine Assembly Planning and Oversight | 32.15 | -0.05 | [5 empty] | 71 - 71 - Shield Wall Seismic Modifications | 740 | 32.15 | [6 empty] | 32.15
72 - Control Room Refurbishment | 72 - Control Room Refurbishment |  | 48.8 | 48.8 |  |  | 50.2 | 1.4 |  | 50.2 | 50.2 | 0 | [7 empty] | 72 - 72 - Control Room Refurbishment | 720 | 47.59 | -2.61 | [5 empty] | 72 - 72 - Control Room Refurbishment | 720 |  |  | 47.59 |  |  |  |  | 47.59
73 - Platform Design & Fabrication | 73 - Platform Design & Fabrication |  | 161 | 161 |  |  | 161.3 | 0.3 |  | 161.3 | 161.3 | 0 | [7 empty] | 73 - 73 - Platform Design & Fabrication | 730 - Test Cell & Basement Assembly Operations | 162.29 | 0.99 | [5 empty] | 73 - 73 - Platform Design & Fabrication | 730 |  |  | 86.54 | 1.3 | 74.45 |  |  | 162.29
| 74 - Machine Assembly Planning and Oversight |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [10 empty] | 0
74 - Machine Assembly Planning and Oversight |  | 740 - Machine Assembly Planning and Oversight | 148 | 148 |  |  | 152.55 | 4.55 |  | 152.55 | 152.55 | 0 | [7 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 740 - Machine Assembly Planning and Oversight | 152.71 | 0.16 | [5 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 740 |  | 89.67 | 63.04 |  |  |  |  | 152.71
74 - Machine Assembly Planning and Oversight |  | 741 - Planning Prior to Machine Assembly | 281.6 | 281.6 |  |  | 281.57 | -0.03 |  | 281.57 | 281.57 | 0 | [7 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 741 - Planning Prior to Machine Assembly | 312.58 | 31.01 | [5 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 741 | 164 | 148.58 | [5 empty] | 312.58
74 - Machine Assembly Planning and Oversight |  | 742 - Construction Management | 1194.2 | 1194.2 |  |  | 1068.15 | -126.05 |  | 1068.15 | 1068.15 | 0 | [7 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 742 - Construction Management | 1099.48 | 31.33 | [5 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 742 |  |  | 109.97 | 70.99 | 176.08 | 489.11 | 253.33 | 1099.48
| 75 - Test Cell and Basement Assembly Operations |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | [10 empty] | 0
75 - Test Cell and Basement Assembly Operations |  | 750 - Test Cell & Basement Assembly Operations | 2184.9 | 2184.9 |  |  | 2238.93 | 54.03 |  | 2238.93 | 2238.93 | 0 | [7 empty] | 75 - 75 - Test Cell and Basement Assembly Operations | 750 - Test Cell & Basement Assembly Operations | 2365.71 | 126.78 | [5 empty] | 75 - 75 - Test Cell and Basement Assembly Operations | 750 |  |  |  | 57.17 |  | 1619.2 | 689.34 | 2365.71
76 - Tooling Design & Fabrication | 76 - Tooling Design & Fabrication |  | 223.7 | 223.7 |  |  | 222.99 | -0.71 |  | 222.99 | 222.99 | 0 | [7 empty] | 76 - 76 - Tooling Design & Fabrication |  | 238.25 | 15.26 | [5 empty] | 76 - 76 - Tooling Design & Fabrication | [6 empty] | 176.77 | 61.48 | 238.25
|  | SUBTOTAL WBS 7 | 4274.4 | 4274.4 |  |  | 4207.89 | -66.51 |  | 4207.89 | 4207.89 | 0 | [9 empty] | 4410.76 | 202.87 | YTD CV $30 Rates& stretchout | 173 |  | 30 | 203
81 - Project Management and Control | 81 - Project Management and Control |  | 3556.8 | 3556.8 |  |  | 3450.278 | -106.522 | re-estimted out year needs. Cost share with res prep | 3450.278 | 3596 | 145.722 | Prior year scope retirement fore FY04 | [6 empty] | 81 - 81 - Project Management and Control | 810 - Project Management & Control | 4508.74 | 912.74 | LOE Stretchout& rates 950 | 950 | -37 |  | 913 | 81 - 81 - Project Management and Control | 810 | 445.94 | 961.12 | 787.86 | 771.81 | 732.59 | 612.89 | 196.53 | 4508.74
82 - Project Engineering | 82 - Project Engineering |  | 4013.7 | 4207.5 | 193 | ECP 16 FY04 cost variance +193 | 4367.5 | 160 |  | 4367.5 | 4426 | 58.5 | New scope for FY05. Dimensional control coordinator. | [6 empty] | 82 - 82 - Project Engineering | 820 - Project Engineering | 5310.88 | 884.88 | LOE Stretchout 563, Dimensional control coordination/support add'l$322 | 563 | 322 |  | 885 | 82 - 82 - Project Engineering | 820 | 518.9 | 1230.92 | 1203.38 | 1332.9 | 518.55 | 396.17 | 110.06 | 5310.88
84 - Project Physics | 84 - Project Physics |  | 412.2 | 412.2 |  |  | 412.47 | 0.27 |  | 470.17 | 470.17 | 0 | [7 empty] | 84 - 84 - Project Physics | 840 - Project Physics | 469.93 | -0.24 | [5 empty] | 84 - 84 - Project Physics | 840 | 251.25 | 218.68 | [5 empty] | 469.93
85 - Integrated Systems Testing | 85 - Integrated Systems Testing |  | 1220.1 | 1220.1 | 0 |  | 1220.68 | 0.58 |  | 1220.68 | 1220.68 | 0 | [7 empty] | 85 - 85 - Integrated Systems Testing |  | 1189.25 | -31.43 |  | 90 | -121 |  | -31 | 85 - 85 - Integrated Systems Testing | [6 empty] | 353.37 | 835.88 | 1189.25
|  | SUBTOTAL WBS 8 | 9202.8 | 9396.6 | 193 |  | 9450.928 | 54.328 |  | 9508.628 | 9712.85 | 204.222 | [9 empty] | 11478.8 | 1765.95
PPPL Allocations | PPPL Allocations |  | 983.3 | 983.3 |  |  | 1128.6 | 145.3 | Adjusted based upon FY04 allocation costs and estimated out year mapping | 1128.6 | 1128.6 | 0 | [7 empty] | AA - PPPL Allocations | PPPL Allocations | 1576.88 | 448.28 | LOE Stretchout $388, CV 60 | 388 |  | 60 | 448 | AA - PPPL Allocations | AAA | 112 | 260.69 | 350.85 | 340.47 | 340.08 | 172.79 |  | 1576.88
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Contingency | Contingency |  | 13454.9 | 13455 |  |  | 13052.89 | -402.11 |  | 12755.89 | 11609.548 | -1146.342 | [7 empty] | CC - Contingency | Contingency | 12242.24 | 632.692 | Contingency |  | -198 |  | -198 | CC - Contingency | CCC |  |  | 800.24 | 3000 | 2600 | 3100 | 2742 | 12242.24
[25 empty] | 5025.544 | 1750 | 6775.544 |  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09
[8 empty] | 0 | [16 empty] | Stretchout | Estimate Growth | -98.62 |  |  |  | 6062.34 | 13658.24 | 18470.71 | 18424.89 | 15888.54 | 15848.41 | 5208.08 | 93561.21 | 93561.21
|  |  | 86346 | 86345.9 | -0.1 | 0 | 86345.718 | -0.18199 |  | 86345.388 | 86345.288 | 0.2 | [9 empty] | 93561.21 | 7215.862 |  |  |  |  | BO Cum |  |  | 6062.34 | 19720.58 | 37391.05 | 52815.94 | 66104.48 | 78852.89 | 81318.97
[11 empty] | etc= | [10 empty] | 53533.97 | [5 empty] | BA cum |  |  | 7900 | 23800 | 41300 | 57200 | 73100 | 89000 | 93561.21 |  | 12242.24
[11 empty] | cont= | [10 empty] | 22.87% | [5 empty] | Contingency |  |  |  | 0 | 800.24 | 3000 | 2600 | 3100 | 2742 | 12242.24
[28 empty] | PMB |  |  | 6062.34 | 13658.24 | 17670.47 | 15424.89 | 13288.54 | 12748.41 | 2466.08 | 81318.97 | 93561.21
NCSX Rebaseline Overview
[11 empty] | ECP-24 (current) | [10 empty] | New | increase | % increase
[11 empty] | 86345.288 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93561.21 | 7215.862 | 8.357% | [6 empty] | 8.357%
Contingency
balance from 3/1/05
| VVSA contract | 4350517.4575 | [8 empty] | 217525.8729 | [10 empty] | 5%
| MCWF contract | 6635395.932 | [8 empty] | 663539.5932 | [10 empty] | 10%
| WBS 1-18 | 23980227.6095 | [8 empty] | 8029972.1653 | [10 empty] | 33.49%
| WBS 2-7 & 85(BOP) | 12125449.4399 | [8 empty] | 2373989.5974 | [10 empty] | 19.58%
| WBS 19 & 81 & 82 | 8521552.2134 | [8 empty] | 957821.7642 | [10 empty] | 11.24%
|  | 55613142.6524 | [8 empty] | 12242848.993 | [10 empty] | 22.01%
Reconciliation Summary
Stretchout Related
| 1) | WBS 81 Project management incl rate incr | [21 empty] | 950
| 2) | WBS 82 Project Engineering incl rate incr | [21 empty] | 563
| 3) | WBS 13 TF fab oversight stretchout and rates | [21 empty] | 226
| 4) | WBS 12 contract oversight,title III ,stretchout and rates | [21 empty] | 41.544
| 5) | WBS 142 MC winding oversight incl rate incr | [21 empty] | 499
| 6) | WBS 18 HP coverage and FP Assy supervision incl rate incr | [21 empty] | 473
| 7) | Allocations incl rate incr | [21 empty] | 388
| 8) | WBS 19 Stellarator core management incl rate incr | [21 empty] | 386
| 9) | Balance of rate increases (overhead and re-schedule) | [21 empty] | 1499
5025.544
Estimate Growth
| 1) | WBS 13 TFDesign & Fabrication | [21 empty] | 599
| 2) | WBS 141 MC Assy hardware | [21 empty] | 640
| 3) | WBS 82 Dimensional control & sprt | [21 empty] | 322
| 4) | WBS 18 FP Assy fixturing and setup | [21 empty] | 297
| 5) | WBS 12 VVSA Add'l Dies | [21 empty] | 431
| 6) | Project YTD cost variance | [21 empty] | 430
| 7) | WBS 142 MC winding | [21 empty] | 97
| 8) | WBS 12 Vac VslContract Oversight | [21 empty] | 240
| 9) | WBS 142 MC Final Design & TRC completion | [21 empty] | 195
| 10) | Scope reductions | [21 empty] | -570
|  | WBS 611 water sys | [8 empty] | -151 | [12 empty] | 2681
|  | WBS 185 FP assy LC | [8 empty] | -118
|  | WBS 85 ISTP doc. | [8 empty] | -121
|  | WBS 81 Proj mgt | [8 empty] | -37
|  | cont | [8 empty] | -121
|  | misc | [8 empty] | -22
-570
| Management Challenges & Drivers of contingency | [28 empty] | 7.9
| 1) | FP Assy Fixture Hardware | [20 empty] | 500
| 2) | Additional MC cold test ( first two of each coil type incl) | [20 empty] | 200 | [6 empty] | FY03
| 3) | Metrology staff to perform measurements for FP&Mach Assy | [20 empty] | 425 | [5 empty] | BA | 7.9
| 4) | Dimensional Control Oversight & analysis support | [20 empty] | 400 | [5 empty] | BO | 6.062
| 5) | Metrology Hardware-Laser tracker(HW,SW Training, maint) | [20 empty] | 230 | [5 empty] | CUM BA | 7.9
| 6) | Mod Coil Winding Learning curve factored in | [20 empty] | 185 | [5 empty] | CUM BO | 6.062
| 7) | Add'l TF Coil Cold Testing (first two coils incl) | [20 empty] | 150
| 8) | Magnetic Diagnostic design/fab | [20 empty] | 120
| 9) | WBS 19 As-builts | [20 empty] | 120
2330
[41 empty] | ECP-29 |  | Change | New Baseline | [19 empty] | Total
[40 empty] | 12 - Vacuum Vessel Systems | 9168.37 |  | 270.73 | 9439.1 | [11 empty] | Original BA | 7.9 | 15.83 | 15.84 | 22.14 | 19.42 | 5.2 |  | 86.33
[40 empty] | 13 - Conventional Coils | 4552.21 |  | 226.31 | 4778.52 | [11 empty] | New BA | 7.9 | 15.83 | 17.5 | 15.9 | 15.9 | 15.9 | 5.199 | 94.129
[40 empty] | 14 - Modular Coils | 26839.32 |  | 1207.15 | 28046.47 | [11 empty] | PMB | 6.062 | 13.658 | 18.238 | 15.425 | 13.289 | 12.748 | 2.466 | 81.886
[40 empty] | 15 - Structures | 1380.71 |  | 32.25 | 1412.96 | [11 empty] | Contingency |  |  | 0.8 | 3 | 2.6 | 3.1 | 2.742 | 12.242
[40 empty] | 16 - Coil Services | 1036 |  | 109.5 | 1145.5 | [11 empty] | BA cum old | 7.9 | 23.73 | 39.57 | 61.71 | 81.13 | 86.33 | 86.33
[40 empty] | 17 - Cryostat and Base Support Struct | 1321.14 |  | 40.1 | 1361.24 | [11 empty] | BA cum new | 7.9 | 23.73 | 41.23 | 57.13 | 73.03 | 88.93 | 94.129
[40 empty] | 18 - Field Period Assembly | 5118.09 |  | 306 | 5424.09 | [11 empty] | PMB cum | 6.062 | 19.72 | 37.958 | 53.383 | 66.672 | 79.42 | 81.886
[40 empty] | 19 - Stellarator Core Mgt & Integr | 2421.02 |  | 331.01 | 2752.03
[40 empty] | 1 Stellarator Core Systems | 51836.86 |  | 2523.05 | 54359.91
[40 empty] | 2 Heating, Fueling & Vac Sys | 778.32 |  | 5.15 | 783.47
[40 empty] | 3 Diagnostics | 1116.7 |  | 26.3 | 1143
[40 empty] | 4 Electrical Power Sys | 3214.12 |  | 86.97 | 3301.09
[40 empty] | 5 Central I&C Sys | 1915.2 |  | 134.34 | 2049.54
[40 empty] | 6 Facility Sys | 825.2 |  | 17.26 | 842.46
[40 empty] | 7 Test Cell Prep & MachAssy | 4207.89 |  | 202.87 | 4410.76
[40 empty] | 8 Project Oversight & Support | 10841.45 |  | 1791.23 | 12632.68
[40 empty] | subtotal | 74735.74 |  | 4787.17 | 79522.91
[40 empty] | Contingency | 11609.548 | 25% | 1194 | 12803.548 | 25%
[40 empty] | TEC = | 86345.288 |  | 5981.17 | 92326.458
%
PARS thru MAR 30th against ECP-29
[40 empty] | BCWS | 29171
[40 empty] | BCWP | 28005
[40 empty] | ACWP | 28004
[40 empty] | SPI | 0.96003
[40 empty] | CPI | 1
[40 empty] | BCWR |  |  |  | 51518.91
[40 empty] | Contingency balance |  |  |  | 12803.548 | 24.85% | [9 empty] | 24.8%
[59 empty] | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total
[56 empty] | 22.01% |  | BA | 7.9 | 15.83 | 17.5 | 15.9 | 15.9 | 15.9 | 3.38 | 92.31
[58 empty] | PMB | 6.062 | 13.658 | 18.1 | 14.3 | 12.9 | 12.3 | 2.22 | 79.54 | 79.523
[41 empty] | BCWR From Feb 28th |  | Contingency | [12 empty] | 5% |  | Contingency |  |  | 1 | 3.9 | 3.1 | 3 | 1.8 | 12.8 | 12.804
[40 empty] | VVSA contract | 4350.5175 |  | 217.5259 | 5% | [11 empty] | 10% |  | BO (PMB + Cont) | 6.062 | 13.658 | 19.1 | 18.2 | 16 | 15.3 | 4.02 | 92.34 | 92.327
[40 empty] | MCWF contract | 6635.3959 |  | 663.5396 | 10% | [11 empty] | 33.49% | [10 empty] | 92.34
[40 empty] | WBS 1-18 | 23980.2276 |  | 8029.9722 | 33.49% | [11 empty] | 19.58% |  | Cum BA | 7.9 | 23.73 | 41.23 | 57.13 | 73.03 | 88.93 | 92.31
[40 empty] | WBS 2-7 & 85(BOP) | 12125.4494 |  | 2373.9896 | 19.58% | [11 empty] | 11.24% |  | Cum PMB | 6.062 | 19.72 | 37.82 | 52.12 | 65.02 | 77.32 | 79.54
[40 empty] | WBS 19 & 81 & 82 | 8521.5522 |  | 957.8218 | 11.24% | [11 empty] | 22.01%
[40 empty] | Through March 1st = | 55613.1427 |  | 12242.849 | 22.01% | [13 empty] | Cum BO | 6.062 | 19.72 | 38.82 | 57.02 | 73.02 | 88.32 | 92.34
[50 empty] | bcwp= | 28003.6807
[40 empty] | Through April 1st= | 53757 |  |  | 22.77% | [13 empty] | pmb puts and takes |  |  | -0.415 | -1.047 | -0.712 | 0.151 | 0.121
[58 empty] | contingency puts and takes |  | 0 | 0.415 | 1.047 | 0.712 | -0.151 | -0.121
[59 empty] | wbs1 | -0.24 | -0.12 | -0.12
[59 empty] | wbs13 | -0.6 | -0.2 | -0.2 | -0.2
[59 empty] | wbs 141 | -0.64 |  | -0.32 | -0.32
[59 empty] | wbs142 | -0.095 | -0.095
[59 empty] | wbs142 | -0.097 |  | -0.097
[59 empty] | wbs18 | -0.3 |  | -0.15 | -0.15
[59 empty] | wbs82 | -0.32 |  | -0.16 | -0.16
[59 empty] | red | 0.48 |  |  | 0.118 | 0.151 | 0.121
0.09
[51 empty] | Re-baseline | BCWR | Contingency | %
[50 empty] | 12 - Vacuum Vessel Systems | 4327.215 | 1033.9897 | 372.2363 | 36%
[50 empty] | VVSA Contract | 5111.885 | 3818 | 381.8 | 10%
[50 empty] | 13 - Conventional Coils | 4778.52 | 4051.5521 | 1742.1674 | 43%
[50 empty] | 14 - Modular Coils | 19892.545 | 7443.7721 | 3126.3843 | 42%
[50 empty] | MCWF Contract | 8153.925 | 6368 | 636.8 | 10%
[50 empty] | 15 - Structures | 1412.96 | 1378.349 | 439.8714 | 31.91%
[50 empty] | 16 - Coil Services | 1145.5 | 1145.4998 | 284.3929 | 24.83%
[50 empty] | 17 - Cryostat and Base Support Struct | 1361.24 | 1166.2268 | 341.4229 | 29.28%
[50 empty] | 18 - Field Period Assembly | 5424.09 | 4754.8382 | 2087.1362 | 43.9%
[50 empty] | 19 - Stellarator Core Mgt & Integr | 2752.03 | 1567.1339 | 156.7134 | 10%
[50 empty] | 1 Stellarator Core Systems | 54359.91 | 32727.3615 | 9568.9248 | 29.24%
[50 empty] | 2 Heating, Fueling & Vac Sys | 783.47 | 435.4238 | 60.9593 | 14%
[50 empty] | 3 Diagnostics | 1143 | 868.5829 | 268.2592 | 30.88%
[50 empty] | 4 Electrical Power Sys | 3301.09 | 2976.3621 | 577.178 | 19.39%
[50 empty] | 5 Central I&C Sys | 2049.54 | 2016.7292 | 195.1655 | 9.677%
[50 empty] | 6 Facility Sys | 842.46 | 1310.8067 | 262.1613 | 20%
[50 empty] | 7 Test Cell Prep & Machine Assy | 4410.76 | 3904.043 | 815.2877 | 20.88%
[50 empty] | 8 Project Oversight & Support | 12632.68 | 7279.9202 | 1055.5884 | 14.5%
[50 empty] | subtotal | 79522.91 | 51519.2293 | 12803.5243 | 24.85%
[51 empty] | VVSA contract | 3818 | 381.8 | 10%
[46 empty] | Risks | Opportunities |  |  |  | MCWF contract | 6368 | 636.8 | 10%
[51 empty] | WBS 1-18 | 20974.2276 | 8393.6114 | 40.02%
[45 empty] | 240 | WBS 12 Vac VslContract Oversight | WBS 611 water sys |  | -151 |  | WBS 2-7 & 85(BOP) | 11511.9476 | 2179.0111 | 18.93%
[45 empty] | 599 | WBS 13 TF Design & Fabrication | WBS 185 FP assy LC |  | -118 |  | WBS 19 & 81 & 82 | 8847.054 | 1212.3018 | 13.7%
[45 empty] | 640 | WBS 141 MC Assy hardware | WBS 85 ISTP doc. |  | -121 |  | As of March 31st = | 51519.2293 | 12803.5243 | 24.85%
[45 empty] | 195 | WBS 142 MC Final Design & TRC completion | WBS 81 Proj mgt |  | -37
[45 empty] | 97 | WBS 142 MC winding |  |  | -61
[45 empty] | 297 | WBS 18 FP Assy fixturing and setup
[45 empty] | 322 | WBS 82 Dimensional control & sprt
[45 empty] | -488 | Scope reductions
1902
misc
-488
FY04 FY05 FY06 FY07 FY08 FY09
$23.7
$73.0
$57.1
41.2
$88.9
$92.3
$88.9