## Contingency Summary
Summary of Risk/Contingency Analysis Results
|  | 100% Confidence |  | 95% Confidence |  | 90% Confidence |  | 80% Confidence
Base Schedule |  | 46.3901 | months | 46.3901 | months | 46.3901 | months | 46.3901 | months
Schedule Uncertainty Contingency |  | 15.6984 |  | 9.4753 |  | 8.1225 |  | 6.5028 |  | Note: Schedule contingency reduced - mitigated by assuming work on Saturdays (cost added below)
Risk Schedule Contingency |  | 18.6667 |  | 12.3958 |  | 11.3125 |  | 9.9792
Total Schedule Contingency (90%) |  | 34.3651 | months | 21.8712 | months | 19.435 | months | 16.482 | months
Base ETC |  | 61794 |  | 61794 |  | 61794 |  | 61794
Contingency (Std Uncertainty) |  | 14310 |  | 9630 |  | 8990 | 14.55% | 8210 | 13.29%
Cost of Schedule Uncertainty Contingency |  | 4970 |  | 4970 |  | 4260 | 6.894% | 3410 | 5.518%
Cost of Schedule Mitigation (incl. 2nd Shift & Saturdays) |  | 360 |  | 290 |  | 260 | 0.4208% | 230 | 0.3722%
Total Uncertainty Contingency |  | 19640 |  | 14890 |  | 13510 | 21.86% | 11850 | 19.18%
Risk Cost Contingency (from Risk Model) |  | 4270 |  | 3200 |  | 2880 | 4.661% | 2630 | 4.256%
Risk Schedule Contingency (cost of stretch) |  | 11760 |  | 7810 |  | 7130 | 11.54% | 5240 | 8.48%
Total Risk Contingency |  | 16030 |  | 11010 |  | 10010 | 16.2% | 7870 | 12.74%
Total Cost Contingency |  | 35670 | 57.72% | 25900 | 41.91% | 23520 | 38.06% | 19720 | 31.91%
ETC with Contingency | [5 empty] | 85314 |  | 81514
| Contingency Spread by Year | [5 empty] | $M |  | $M
| 2008 | 10% | 3.567 | 10% | 2.59 | 10% | 2.352 | 10% | 1.972
| 2009 | 15% | 5.3505 | 15% | 3.885 | 15% | 3.528 | 15% | 2.958
| 2010 | 15% | 5.3505 | 15% | 3.885 | 15% | 3.528 | 15% | 2.958
| 2011 | 15% | 5.3505 | 15% | 3.885 | 15% | 3.528 | 15% | 2.958
| 2012 | 45% | 16.0515 | 45% | 11.655 | 45% | 10.584 | 45% | 8.874
|  |  | 35.67 |  | 25.9 |  | 23.52 |  | 19.72

## Probability Data
Percentiles | Total ETC With Uncertainty Contingency | Risk Cost Contingency | Risk Schedule Contingency | Schedule Mitigation Cost Adder | Total Schedule Duration
0% | 63315.7041 | -1230 | 0.275 | 0 | 42.4468
5% | 66093.8539 | 585 | 4.375 | 26.2984 | 45.3445
10% | 66613.9984 | 840 | 5.375 | 53.9647 | 46.2389
15% | 66983.5368 | 1050 | 5.9 | 77.3386 | 46.9068
20% | 67285.1429 | 1235 | 6.575 | 96.33 | 47.5113
25% | 67550.2861 | 1405 | 7.075 | 98.731 | 48.0591
30% | 67786.2125 | 1520 | 7.45 | 109.0342 | 48.5789
35% | 67992.8507 | 1620 | 7.875 | 118.8966 | 49.0566
40% | 68185.9345 | 1705 | 8.275 | 128.44 | 49.5936
45% | 68387.4068 | 1785 | 8.725 | 137.9303 | 50.1118
50% | 68584.0733 | 1875 | 9.075 | 147.3462 | 50.6279
55% | 68781.8689 | 1960 | 9.575 | 157.4959 | 51.1637
60% | 68989.6792 | 2080 | 9.9 | 167.6679 | 51.6931
65% | 69221.4278 | 2230 | 10.375 | 178.9907 | 52.2607
70% | 69466.1053 | 2390 | 10.875 | 190.4554 | 52.8461
75% | 69731.2991 | 2520 | 11.375 | 198.0204 | 53.4655
80% | 70007.3017 | 2630 | 11.975 | 210.5249 | 54.1934
85% | 70354.0635 | 2740 | 12.575 | 224.77 | 55.0147
90% | 70788.5916 | 2875 | 13.575 | 239.9569 | 56.137
95% | 71424.5317 | 3200 | 14.875 | 268.0634 | 57.7605
100% | 76106.9212 | 4265 | 22.4 | 321.1 | 65.2282
Schedule Contingency Adjustment (work Saturdays to mitigate)
|  | Unmitigated | Mitigated | Mitigation Cost
80% Uncertainty |  | 7.8033 | 6.5028 | 7.9599
80% Risk |  | 11.975 | 9.9792 | 12.2153
90% Uncertainty |  | 9.747 | 8.1225 | 9.9426
90% Risk |  | 13.575 | 11.3125 | 13.8474
95% |  | 11.3704 | 9.4753 | 11.5986
95% |  | 14.875 | 12.3958 | 15.1735
100% |  | 18.8381 | 15.6984 | 19.2161
100% |  | 22.4 | 18.6667 | 22.8495

## Contingency by Year Basis
Major Contributors to Uncertainty Contingency
|  | Spread of Dollars by Year | [5 empty] | Weighted Contingency Spread by Year
Job | % | 2008 | 2009 | 2010 | 2011 | 2012 |  | 2008 | 2009 | 2010 | 2011 | 2012
* Job 7503 Total | 24.27% | 0% | 0% | 32.28% | 53.56% | 14.17% | 100% | 0 | 0 | 0.07834 | 0.13 | 0.034384 |  | 24.27%
7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 10.9% | 3.717% | 5.54% | 29.52% | 54.52% | 6.697% | 100% | 0.0040494 | 0.0060359 | 0.032166 | 0.059404 | 0.0072965 |  | 10.9%
Estimating Process Uncertainty | 10.29% | 22.62% | 27.18% | 26.65% | 20.14% | 3.406% | 100% | 0.023283 | 0.027973 | 0.027432 | 0.020733 | 0.0035062 |  | 10.29%
8203 - Job: 8203 - Design Integration-BROWN | 4.18% | 3.585% | 8.817% | 29.74% | 30.59% | 25.41% | 5.452% | 0.0014985 | 0.0036853 | 0.01243 | 0.012785 | 0.010619 |  | 4.102%
* S2H6 - Station 2 MC subassy A6B6C6 | 3.711% | 3.823% | 0% | 88.06% | 11.94% | 0% | 0% | 0.0014187 | 0 | 0.032681 | 0.0044293 | 0 |  | 3.853%
* S2H2 - Station 2 MC subassy A2B2C2 | 3.648% | 79.25% | 20.75% | 0% | 0% | 0% | 100% | 0.028911 | 0.0075719 | 0 | 0 | 0 |  | 3.648%
* S2H1 - Station 2 MC subassy A1B1C1 | 3.567% | 85.07% | 14.93% | 0% | 0% | 0% | 100% | 0.030348 | 0.0053256 | 0 | 0 | 0 |  | 3.567%
* S2H4 - Station 2 MC subassy A4B4C4 | 3.508% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0.035076 | 0 | 0 | 0 |  | 3.508%
* S2H5 - Station 2 MC subassy A5B5C5 | 3.423% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0.034234 | 0 | 0 | 0 |  | 3.423%
* S2H3 - Station 2 MC subassy A3B3C3 | 3.276% | 47.04% | 52.96% | 0% | 0% | 0% | 100% | 0.015409 | 0.017348 | 0 | 0 | 0 |  | 3.276%
1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | 3.104% | 22.42% | 41.2% | 36.38% | 0% | 0% | 100% | 0.0069597 | 0.012789 | 0.011294 | 0 | 0 |  | 3.104%
7501 - Job: 7501 - Construction Support Crew-PERRY | 2.538% | 0% | 0% | 26.61% | 63.87% | 9.524% | 100% | 0 | 0 | 0.0067518 | 0.016208 | 0.0024168 |  | 2.538%
* S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | 2.187% | 0% | 0% | 100% | 0% | 0% | 100% | 0 | 0 | 0.021872 | 0 | 0 |  | 2.187%
* S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | 2.175% | 0% | 0% | 100% | 0% | 0% | 100% | 0 | 0 | 0.021748 | 0 | 0 |  | 2.175%
* S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 2.114% | 0% | 60.3% | 39.7% | 0% | 0% | 100% | 0 | 0.01275 | 0.0083942 | 0 | 0 |  | 2.114%
* S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | 2.012% | 0% | 100% | 0% | 0% | 0% | 100% | 0 | 0.020123 | 0 | 0 | 0 |  | 2.012%
* S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | 1.996% | 0% | 59.56% | 40.44% | 0% | 0% | 100% | 0 | 0.011888 | 0.008072 | 0 | 0 |  | 1.996%
* S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | 1.782% | 0% | 10.55% | 89.45% | 0% | 0% | 100% | 0 | 0.0018809 | 0.015943 | 0 | 0 |  | 1.782%
8101 - Job: 8101 - Project Management &Control-ANDERSON | 1.376% | 18.75% | 29.88% | 26.76% | 20.73% | 3.869% | 100% | 0.00258 | 0.0041111 | 0.0036822 | 0.0028524 | 0.00053229 |  | 1.376%
Other (Assume Spread over years) | 9.942% | 10% | 20% | 20% | 25% | 25% | 100% | 0.0099418 | 0.019884 | 0.019884 | 0.024855 | 0.024855 |  | 9.942%
B
| 100% |  |  | Total Uncertainty Contingency Spead |  |  |  | 12.44% | 22.07% | 30.07% | 27.13% | 8.361% |  | 100.1%
|  |  |  | Uncertainty Contingency |  |  | 9250 | 1150.6821 | 2041.236 | 2781.3806 | 2509.219 | 773.3857 |  | 9255.9033
|  |  |  | Spread of Dollars by Year | [5 empty] | Weighted Contingency Spread by Year
Major Contributors to Uncertainty Contingency |  | Job(s) |  | 2008 | 2009 | 2010 | 2011 | 2012 |  | 2008 | 2009 | 2010 | 2011 | 2012
Assy-4 | 31.82% | 1810, 1815, 7503 |  | 18.42% | 28.12% | 28.38% | 19.84% | 5.246% | 100% | 0.05861 | 0.089497 | 0.090295 | 0.063121 | 0.016695 | 31.82%
Mgmt-4 | 29.12% | 8101 |  | 18.75% | 29.88% | 26.76% | 20.73% | 3.869% | 100% | 0.05461 | 0.087018 | 0.077938 | 0.060376 | 0.011267 | 29.12%
Sys-1 | 16.66% | 1352 |  | 65.78% | 32.1% | 0.304% | 1.824% | 0% | 100% | 0.10958 | 0.053473 | 0.00050638 | 0.0030383 | 0 | 16.66%
Assy-3 | 6.061% | 7503 |  | 0% | 0% | 32.28% | 53.56% | 14.17% | 100% | 0 | 0 | 0.019562 | 0.032461 | 0.0085857 | 6.061%
Assy-2 | 3.399% | 1815 |  | 0% | 32.61% | 67.39% | 0% | 0% | 100% | 0 | 0.011083 | 0.022905 | 0 | 0 | 3.399%
Sys-13 | 3.296% | 15xx |  | 63.09% | 19.25% | 17.67% | 0% | 0% | 100% | 0.020795 | 0.0063437 | 0.0058236 | 0 | 0 | 3.296%
Stat5-8 | 2.288% | 1815 |  | 0% | 32.61% | 67.39% | 0% | 0% | 100% | 0 | 0.0074603 | 0.015418 | 0 | 0 | 2.288%
Stat5-11 | 1.469% | 1815, 7503 |  | 0% | 9.966% | 43.01% | 37.19% | 9.836% | 100% | 0 | 0.0014643 | 0.006319 | 0.0054643 | 0.0014452 | 1.469%
Assy-1 | 1.046% | 1810 |  | 39.47% | 48.88% | 11.65% | 0% | 0% | 100% | 0.0041269 | 0.0051107 | 0.0012181 | 0 | 0 | 1.046%
Other | 4.839% |  |  | 10% | 20% | 20% | 25% | 25% | 100% | 0.004839 | 0.009678 | 0.009678 | 0.012098 | 0.012098 | 4.839%
| 1810 |  |  | 2131 | 2639 | 629 | 0 | 0 | 5399 | [5 empty] | 100%
| 1815 |  |  | 0 | 615 | 1271 | 0 | 0 | 1886
| 7503 |  |  | 0 | 0 | 1383 | 2295 | 607 | 4285
|  |  |  | 2131 | 3254 | 3283 | 2295 | 607 | 11570
|  |  |  | Total Risk Spread | [5 empty] | 25.26% | 27.11% | 24.97% | 17.66% | 5.009%
|  |  |  | Cost Risk Contingency |  |  |  | 2880 |  | 727.3762 | 780.8493 | 719.028 | 508.488 | 144.2586
|  |  |  | Schedule Contingency all in 2012 |  |  |  | 11390 | [5 empty] | 11390
[10 empty] | 2008 | 2009 | 2010 | 2011 | 2012
|  |  |  | Total Contingency by Year |  |  |  | 23520 |  | 1878.0583 | 2822.0852 | 3500.4086 | 3017.7069 | 12307.6443
[10 empty] | 7.985% | 12% | 14.88% | 12.83% | 52.33%
[7 empty] | Conservative Projection |  |  | 10% | 15% | 15% | 15% | 45%
Note on B4: Chris Gruber: Contribution to Variance from Uncertainty Model Sensitivty Analysis
Note on I3: Chris Gruber: Contribution to Variance % times % by year
Note on K33: Chris Gruber: Contribution to Variance % times % by year
Note on D40: Chris Gruber: Used spread remaining after 2007 from Escalation Risk sheet for SS

## Estimate Data
[9 empty] | updated | Estimate Uncertainty Range |  |  | updated | updated | updated | updated | updated | Percent ETC by Year
WBS2 |  |  | Job | WBS4 |  | Maturity | Complexity | Lookup | TOTAL | Low | High | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2012 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2012
12 | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation |  | H | L | HL | 220 | 209 | 242 |  | 44 | 39 | 0 | 137 | 0 | 0% | 20% | 17.73% | 0% | 62.27% | 0% | 220
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124T - Heater Tape for Port Stub | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124T - Heater Tape for Port Stub |  | H | L | HL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124U - T/C and Heater Tape Leads | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124U - T/C and Heater Tape Leads |  | H | L | HL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124V - Spacer Flux Loops & Boxes | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124V - Spacer Flux Loops & Boxes |  | H | L | HL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 125 - VV Local I&C | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 125 - VV Local I&C |  | H | L | HL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1250 - Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | - | 1250 - Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | - |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1260 - Job: 1260 NB Transition Ducts- GORANSON | - | 1260 - Job: 1260 NB Transition Ducts- GORANSON | - |  | M | L | ML | 566 | 509.4 | 650.9 |  | 30 | 108 | 409 | 19 | 0 | 0% | 5.3% | 19.08% | 72.26% | 3.357% | 0%
| 1270 - Job: 1270 - Heater Control System-PPPL ( tbd) | - | 1270 - Job: 1270 - Heater Control System-PPPL ( tbd) | - |  | M | L | ML | 642 | 577.8 | 738.3 |  | 0 | 93 | 361 | 188 | 0 | 0% | 0% | 14.49% | 56.23% | 29.28% | 0%
13 | 1302 - Job: 1302 - PF Design -CHRZANOWSKI | - | 1302 - Job: 1302 - PF Design -CHRZANOWSKI | - |  | H | L | HL | 91 | 86.45 | 100.1 |  | 91 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1302 - Job: 1302 - PF Design -CHRZANOWSKI | RBLX - FY07 Rebaseline Exercise | 1302 - Job: 1302 - PF Design -CHRZANOWSKI | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1352 - Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 13P - PF Coil Fabrication | 1352 - Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 13P - PF Coil Fabrication |  | H | L | HL | 1638 | 1556.1 | 1801.8 |  | 1054 | 533 | 21 | 30 | 0 | 0% | 64.35% | 32.54% | 1.282% | 1.832% | 0%
| 1353 - Job: 1353 - CS Structure Procurement-PERRY | 132A - CS Support Structure | 1353 - Job: 1353 - CS Structure Procurement-PERRY | 132A - CS Support Structure |  | H | L | HL | 358 | 340.1 | 393.8 |  | 34 | 0 | 254 | 70 | 0 | 0% | 9.497% | 0% | 70.95% | 19.55% | 0%
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | TRIM - Trim Coil **Updated estimate** | 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | TRIM - Trim Coil **Updated estimate** |  | M | L | ML | 1433 | 1289.7 | 1647.95 |  | 858 | 575 | 0 | 0 | 0 | 0% | 59.87% | 40.13% | 0% | 0% | 0%
| 1355 - Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE | 134 - TF/PF Loacl I&C | 1355 - Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE | 134 - TF/PF Loacl I&C |  | M | L | ML | 109 | 98.1 | 125.35 |  | 57 | 50 | 0 | 2 | 0 | 0% | 52.29% | 45.87% | 0% | 1.835% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | - | 1361 - Job: 1361 - TF Fabrication-KALISH | - |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1361 - Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight | 1361 - Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight |  | H | M | HM | 153 | 137.7 | 175.95 |  | 136 | 17 | 0 | 0 | 0 | 0% | 88.89% | 11.11% | 0% | 0% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | 13Y - TF Fabrication Contract | 1361 - Job: 1361 - TF Fabrication-KALISH | 13Y - TF Fabrication Contract |  | H | M | HM | 474 | 426.6 | 545.1 |  | 427 | 47 | 0 | 0 | 0 | 0% | 90.08% | 9.916% | 0% | 0% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | RBLX - FY07 Rebaseline Exercise | 1361 - Job: 1361 - TF Fabrication-KALISH | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
14 | 1404 - Job: 1404 - MCWF R&D 1st Prod Casting**CLOSED** | - | 1404 - Job: 1404 - MCWF R&D 1st Prod Casting**CLOSED** | - |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - | 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - |  | L | L | LL | 123 | 104.55 | 153.75 |  | 123 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1411 - Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - | 1411 - Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - |  | Closed |  | Closed | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications |  | H | L | HL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDC - Blanket thermal insulation | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDC - Blanket thermal insulation |  | H | L | HL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDE - Top level assy models/drawings | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDE - Top level assy models/drawings |  | H | L | HL | 10 | 9.5 | 11 |  | 10 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDF - Analysis and closeout documentation | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDF - Analysis and closeout documentation |  | H | L | HL | 122 | 115.9 | 134.2 |  | 122 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | TCCO - Type C Design Closeout | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | TCCO - Type C Design Closeout |  | H | L | HL | 7 | 6.65 | 7.7 |  | 0 | 7 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | - | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | - |  | L | M | LM | 23 | 18.4 | 32.2 |  | 23 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142B - Outboard Interface-Bolted Joint Tests-Tension | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142B - Outboard Interface-Bolted Joint Tests-Tension |  | L | M | LM | 2 | 1.6 | 2.8 |  | 2 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142C - Outboard Interface-Bolted Joint Tests-Shear | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142C - Outboard Interface-Bolted Joint Tests-Shear |  | L | M | LM | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142F - Inboard Interface-AB/BC/AA | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142F - Inboard Interface-AB/BC/AA |  | L | M | LM | 3 | 2.4 | 4.2 |  | 3 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142G - Inboard Interface-CC | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142G - Inboard Interface-CC |  | L | M | LM | 1 | 0.8 | 1.4 |  | 1 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142H - Weld Access test | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142H - Weld Access test |  | L | M | LM | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142Z - Outboard Interface | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142Z - Outboard Interface |  | L | M | LM | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1429 - Job: 1429 - MC Interface R&D-DUDEK | 142D - Outboard Interface-Friction | 1429 - Job: 1429 - MC Interface R&D-DUDEK | 142D - Outboard Interface-Friction |  | Closed |  | Closed | 4 | FROZEN |  |  | 4 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders |  | H | M | HM | 5 | 4.5 | 5.75 |  | 5 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BUSH - Bushings | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BUSH - Bushings |  | H | M | HM | 19 | 17.1 | 21.85 |  | 19 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | PUCK - Pucks | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | PUCK - Pucks |  | H | M | HM | 36 | 32.4 | 41.4 |  | 30 | 6 | 0 | 0 | 0 | 0% | 83.33% | 16.67% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMS - Shims-Outboard | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMS - Shims-Outboard |  | H | M | HM | 593 | 533.7 | 681.95 |  | 593 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMT - Shims-Inboard | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMT - Shims-Inboard |  | H | M | HM | 131 | 117.9 | 150.65 |  | 93 | 38 | 0 | 0 | 0 | 0% | 70.99% | 29.01% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMU - Shims- C-C Joint | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMU - Shims- C-C Joint |  | H | M | HM | 28 | 25.2 | 32.2 |  | 0 | 0 | 28 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | STUD - Studs Washers Nuts | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | STUD - Studs Washers Nuts |  | H | M | HM | 143 | 128.7 | 164.45 |  | 143 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | TECH - Misc Tech Shop Support | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | TECH - Misc Tech Shop Support | 20 | H | M | HM | 119 | 107.1 | 136.85 |  | 48 | 71 | 0 | 0 | 0 | 0% | 40.34% | 59.66% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI |  | H | H | HH | 98 | 83.3 | 122.5 |  | 98 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1A - Station 1a/4 Casting Prep | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1A - Station 1a/4 Casting Prep |  | H | H | HH | 28 | 23.8 | 35 |  | 28 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2 - Station 2-Winding Instl Chill Plates Tubing Bag | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2 - Station 2-Winding Instl Chill Plates Tubing Bag |  | H | H | HH | 84 | 71.4 | 105 |  | 84 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3 - Station 3-Winding Instl Chill Plates Tubing Bag | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3 - Station 3-Winding Instl Chill Plates Tubing Bag |  | H | H | HH | 179 | 152.15 | 223.75 |  | 179 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5 - Station 5-VPI | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5 - Station 5-VPI |  | H | H | HH | 175 | 148.75 | 218.75 |  | 175 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | LABR - LOE Oversight & Supervision | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | LABR - LOE Oversight & Supervision |  | H | H | HH | 348 | 295.8 | 435 |  | 348 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians | 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians |  | M | L | ML | 143 | 128.7 | 164.45 |  | 130 | 13 | 0 | 0 | 0 | 0% | 90.91% | 9.091% | 0% | 0% | 0%
| 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLTS - Punchlist Tech shop/RESA | 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLTS - Punchlist Tech shop/RESA |  | M | L | ML | 139 | 125.1 | 159.85 |  | 139 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
15 | 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | - | 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | - |  | M | L | ML | 90 | 81 | 103.5 |  | 90 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1550 - Job: 1550 - Coil Struct. Procurement -PERRY | - | 1550 - Job: 1550 - Coil Struct. Procurement -PERRY | - |  | M | L | ML | 1440 | 1296 | 1656 |  | 230 | 1210 | 0 | 0 | 0 | 0% | 15.97% | 84.03% | 0% | 0% | 0%
16 | 1601 - Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution | 1601 - Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution |  | H | L | HL | 306 | 290.7 | 336.6 |  | 150 | 156 | 0 | 0 | 0 | 0% | 49.02% | 50.98% | 0% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 162 - 162 - Electrical Leads | 1601 - Job: 1601 - Coil Services Design-GORANSON | 162 - 162 - Electrical Leads |  | M | L | ML | 745 | 670.5 | 856.75 |  | 129 | 128 | 488 | 0 | 0 | 0% | 17.32% | 17.18% | 65.5% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 163 - 163 - Coil Protection System | 1601 - Job: 1601 - Coil Services Design-GORANSON | 163 - 163 - Coil Protection System |  | H | L | HL | 31 | 29.45 | 34.1 |  | 0 | 31 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | RBLX - FY07 Rebaseline Exercise | 1601 - Job: 1601 - Coil Services Design-GORANSON | RBLX - FY07 Rebaseline Exercise |  | H | L | HL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
17 | 1701 - Job: 1701 - Cryostat Design-RAFTOPOLOUS | - | 1701 - Job: 1701 - Cryostat Design-RAFTOPOLOUS | - |  | L | H | LH | 580 | 406 | 928 |  | 61 | 403 | 116 | 0 | 0 | 0% | 10.52% | 69.48% | 20% | 0% | 0%
| 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | - | 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | - |  | H | L | HL | 139 | 132.05 | 152.9 |  | 139 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1751 - Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | - | 1751 - Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | - |  | H | L | HL | 550 | 522.5 | 605 |  | 20 | 46 | 288 | 196 | 0 | 0% | 3.636% | 8.364% | 52.36% | 35.64% | 0%
| 1752 - Job: 1752 - Base Support Proc-PERRY | 172 - 172 - Base Support Structure | 1752 - Job: 1752 - Base Support Proc-PERRY | 172 - 172 - Base Support Structure |  | H | L | HL | 231 | 219.45 | 254.1 |  | 1 | 230 | 0 | 0 | 0 | 0% | 0.4329% | 99.57% | 0% | 0% | 0%
18 | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision |  | H | M | HM | 3826 | 3443.4 | 4399.9 |  | 814 | 1540 | 1472 | 0 | 0 | 0% | 21.28% | 40.25% | 38.47% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.00 - Station 3-Modular Coil to VVSA Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.00 - Station 3-Modular Coil to VVSA Assembly |  | M | L | ML | 250 | 225 | 287.5 |  | 236 | 14 | 0 | 0 | 0 | 0% | 94.4% | 5.6% | 0% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 5.00 - Station 5-Final Field Period Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 5.00 - Station 5-Final Field Period Assembly |  | M | L | ML | 203 | 182.7 | 233.45 |  | 203 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 6.00 - 6.00-Final Machine Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 6.00 - 6.00-Final Machine Assembly |  | L | M | LM | 541 | 432.8 | 757.4 |  | 313 | 228 | 0 | 0 | 0 | 0% | 57.86% | 42.14% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | - | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | - |  | M | M | MM | 54 | 45.9 | 67.5 |  | 48 | 6 | 0 | 0 | 0 | 0% | 88.89% | 11.11% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1.00 - 1.00-VV Prep Station | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1.00 - 1.00-VV Prep Station |  | M | M | MM | 19 | 16.15 | 23.75 |  | 10 | 9 | 0 | 0 | 0 | 0% | 52.63% | 47.37% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 2.00 - Station 2-Modular Coil Sub- Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 2.00 - Station 2-Modular Coil Sub- Assembly |  | M | M | MM | 2 | 1.7 | 2.5 |  | 2 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 3.00 - Station 3-Modular Coil to VVSA Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 3.00 - Station 3-Modular Coil to VVSA Assembly |  | M | M | MM | 30 | 25.5 | 37.5 |  | 30 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 5.00 - Station 5-Final Field Period Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 5.00 - Station 5-Final Field Period Assembly |  | M | M | MM | 114 | 96.9 | 142.5 |  | 114 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 6.00 - 6.00-Final Machine Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 6.00 - 6.00-Final Machine Assembly |  | M | M | MM | 137 | 116.45 | 171.25 |  | 135 | 2 | 0 | 0 | 0 | 0% | 98.54% | 1.46% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S0P0 - General Assy Support | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S0P0 - General Assy Support |  | H | M | HM | 1946 | 1751.4 | 2237.9 |  | 446 | 665 | 835 | 0 | 0 | 0% | 22.92% | 34.17% | 42.91% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 |  | H | M | HM | 189 | 170.1 | 217.35 |  | 189 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 |  | H | M | HM | 124 | 111.6 | 142.6 |  | 83 | 41 | 0 | 0 | 0 | 0% | 66.94% | 33.06% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 |  | H | M | HM | 128 | 115.2 | 147.2 |  | 43 | 85 | 0 | 0 | 0 | 0% | 33.59% | 66.41% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) |  | H | M | HM | 111 | 99.9 | 127.65 |  | 0 | 111 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H1 - Station 2 MC subassy A1B1C1 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H1 - Station 2 MC subassy A1B1C1 |  | M | H | MH | 414 | 331.2 | 579.6 |  | 351 | 63 | 0 | 0 | 0 | 0% | 84.78% | 15.22% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H2 - Station 2 MC subassy A2B2C2 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H2 - Station 2 MC subassy A2B2C2 |  | M | H | MH | 314 | 251.2 | 439.6 |  | 249 | 65 | 0 | 0 | 0 | 0% | 79.3% | 20.7% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H3 - Station 2 MC subassy A3B3C3 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H3 - Station 2 MC subassy A3B3C3 |  | M | H | MH | 317 | 253.6 | 443.8 |  | 147 | 170 | 0 | 0 | 0 | 0% | 46.37% | 53.63% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H4 - Station 2 MC subassy A4B4C4 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H4 - Station 2 MC subassy A4B4C4 |  | M | H | MH | 311 | 248.8 | 435.4 |  | 0 | 311 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H5 - Station 2 MC subassy A5B5C5 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H5 - Station 2 MC subassy A5B5C5 |  | M | H | MH | 312 | 249.6 | 436.8 |  | 0 | 312 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H6 - Station 2 MC subassy A6B6C6 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H6 - Station 2 MC subassy A6B6C6 |  | M | H | MH | 310 | 248 | 434 |  | 0 | 273 | 37 | 0 | 0 | 0% | 0% | 88.06% | 11.94% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks |  | M | H | MH | 323 | 258.4 | 452.2 |  | 257 | 66 | 0 | 0 | 0 | 0% | 79.57% | 20.43% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PR - Station 2 Trials & Development |  | M | H | MH | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PX - Setup | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PX - Setup |  | H | H | HH | 967 | 821.95 | 1208.75 |  | 804 | 92 | 71 | 0 | 0 | 0% | 83.14% | 9.514% | 7.342% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General |  | M | H | MH | 188 | 150.4 | 263.2 |  | 8 | 180 | 0 | 0 | 0 | 0% | 4.255% | 95.74% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 |  | M | H | MH | 585 | 468 | 819 |  | 0 | 585 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 |  | M | H | MH | 408 | 326.4 | 571.2 |  | 0 | 243 | 165 | 0 | 0 | 0% | 0% | 59.56% | 40.44% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 |  | M | H | MH | 398 | 318.4 | 557.2 |  | 0 | 42 | 356 | 0 | 0 | 0% | 0% | 10.55% | 89.45% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General |  | L | M | LM | 294 | 235.2 | 411.6 |  | 0 | 276 | 18 | 0 | 0 | 0% | 0% | 93.88% | 6.122% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) |  | L | M | LM | 534 | 427.2 | 747.6 |  | 0 | 339 | 195 | 0 | 0 | 0% | 0% | 63.48% | 36.52% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) |  | L | M | LM | 534 | 427.2 | 747.6 |  | 0 | 0 | 534 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) |  | L | M | LM | 524 | 419.2 | 733.6 |  | 0 | 0 | 524 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
19 | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 191 - 191 - Stellarator Core Management & Oversight | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 191 - 191 - Stellarator Core Management & Oversight |  | H | L | HL | 941 | 893.95 | 1035.1 |  | 145 | 237 | 258 | 261 | 40 | 0% | 15.41% | 25.19% | 27.42% | 27.74% | 4.251%
| 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 192 - 192 - Stellarator Core Integr & Global Analysis | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 192 - 192 - Stellarator Core Integr & Global Analysis |  | H | L | HL | 1309 | 1243.55 | 1439.9 |  | 231 | 386 | 402 | 250 | 40 | 0% | 17.65% | 29.49% | 30.71% | 19.1% | 3.056%
21 | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | - | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | - |  | L | L | LL | 334 | 283.9 | 417.5 |  | 0 | 161 | 53 | 120 | 0 | 0% | 0% | 48.2% | 15.87% | 35.93% | 0%
22 | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - |  | L | L | LL | 683 | 580.55 | 853.75 |  | 0 | 280 | 197 | 206 | 0 | 0% | 0% | 41% | 28.84% | 30.16% | 0%
31 | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads |  | H | L | HL | 47 | 44.65 | 51.7 |  | 47 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124V - Spacer Flux Loops & Boxes | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124V - Spacer Flux Loops & Boxes |  | H | L | HL | 56 | 53.2 | 61.6 |  | 0 | 56 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD2 - Modular Coil C-wound Loops | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD2 - Modular Coil C-wound Loops |  | H | L | HL | 18 | 17.1 | 19.8 |  | 16 | 2 | 0 | 0 | 0 | 0% | 88.89% | 11.11% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD3 - Rogowski Coils | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD3 - Rogowski Coils |  | H | L | HL | 180 | 171 | 198 |  | 92 | 68 | 20 | 0 | 0 | 0% | 51.11% | 37.78% | 11.11% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD4 - TF and PF Co-wound Loops | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD4 - TF and PF Co-wound Loops |  | H | L | HL | 46 | 43.7 | 50.6 |  | 42 | 4 | 0 | 0 | 0 | 0% | 91.3% | 8.696% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | VLPB - Voltage Loops & Protective Boxes | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | VLPB - Voltage Loops & Protective Boxes |  | H | L | HL | 62 | 58.9 | 68.2 |  | 57 | 5 | 0 | 0 | 0 | 0% | 91.94% | 8.065% | 0% | 0% | 0%
36 | 3601 - Job: 3601 - Edge Divertor Diagnostics-STRATTON | - | 3601 - Job: 3601 - Edge Divertor Diagnostics-STRATTON | - |  | M | L | ML | 29 | 26.1 | 33.35 |  | 0 | 0 | 29 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
38 | 3801 - Job: 3801 - Electron Beam Mapping-STRATTON | - | 3801 - Job: 3801 - Electron Beam Mapping-STRATTON | - |  | M | M | MM | 257 | 218.45 | 321.25 |  | 0 | 171 | 31 | 55 | 0 | 0% | 0% | 66.54% | 12.06% | 21.4% | 0%
39 | 3901 - Job: 3901 - Diagnostics sys Integration-STRATTON | - | 3901 - Job: 3901 - Diagnostics sys Integration-STRATTON | - |  | H | L | HL | 111 | 105.45 | 122.1 |  | 16 | 31 | 30 | 34 | 0 | 0% | 14.41% | 27.93% | 27.03% | 30.63% | 0%
41 | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | - | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | - |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems |  | H | L | HL | 120 | 114 | 132 |  | 0 | 20 | 33 | 67 | 0 | 0% | 0% | 16.67% | 27.5% | 55.83% | 0%
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 412 - 412 - Experimental AC Power Systems | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 412 - 412 - Experimental AC Power Systems |  | H | L | HL | 36 | 34.2 | 39.6 |  | 0 | 7 | 29 | 0 | 0 | 0% | 0% | 19.44% | 80.56% | 0% | 0%
43 | 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems | 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems |  | H | L | HL | 577 | 548.15 | 634.7 |  | 47 | 94 | 434 | 2 | 0 | 0% | 8.146% | 16.29% | 75.22% | 0.3466% | 0%
44 | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks |  | M | L | ML | 482 | 433.8 | 554.3 |  | 10 | 43 | 242 | 187 | 0 | 0% | 2.075% | 8.921% | 50.21% | 38.8% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 442 - 442 - Kirk Key Interlocks | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 442 - 442 - Kirk Key Interlocks |  | M | L | ML | 69 | 62.1 | 79.35 |  | 0 | 20 | 17 | 32 | 0 | 0% | 0% | 28.99% | 24.64% | 46.38% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 443 - 443 - Real Time Control Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 443 - 443 - Real Time Control Systems |  | M | L | ML | 14 | 12.6 | 16.1 |  | 0 | 0 | 14 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 444 - 444 - Instrument Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 444 - 444 - Instrument Systems |  | M | L | ML | 241 | 216.9 | 277.15 |  | 0 | 16 | 148 | 77 | 0 | 0% | 0% | 6.639% | 61.41% | 31.95% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 445 - 445 - Coil Protection Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 445 - 445 - Coil Protection Systems |  | M | L | ML | 276 | 248.4 | 317.4 |  | 24 | 48 | 71 | 133 | 0 | 0% | 8.696% | 17.39% | 25.72% | 48.19% | 0%
45 | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces |  | H | L | HL | 319 | 303.05 | 350.9 |  | 51 | 119 | 105 | 44 | 0 | 0% | 15.99% | 37.3% | 32.92% | 13.79% | 0%
| 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452 - 452 - Electrical Systems Support | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452 - 452 - Electrical Systems Support |  | H | L | HL | 199 | 189.05 | 218.9 |  | 0 | 0 | 133 | 66 | 0 | 0% | 0% | 0% | 66.83% | 33.17% | 0%
| 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453 - 453 - System Testing (PTP's) | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453 - 453 - System Testing (PTP's) |  | H | L | HL | 386 | 366.7 | 424.6 |  | 0 | 0 | 0 | 386 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
51 | 5101 - Job: 5101 - Network and Fiber Infrastruct-SICHTA | - | 5101 - Job: 5101 - Network and Fiber Infrastruct-SICHTA | - |  | M | L | ML | 222 | 199.8 | 255.3 |  | 0 | 0 | 133 | 89 | 0 | 0% | 0% | 0% | 59.91% | 40.09% | 0%
52 | 5201 - Job: 5201 - I&C Systems-SICHTA | - | 5201 - Job: 5201 - I&C Systems-SICHTA | - |  | M | L | ML | 411 | 369.9 | 472.65 |  | 0 | 19 | 282 | 110 | 0 | 0% | 0% | 4.623% | 68.61% | 26.76% | 0%
53 | 5301 - Job: 5301 - Data Acquisition-SICHTA | - | 5301 - Job: 5301 - Data Acquisition-SICHTA | - |  | M | L | ML | 165 | 148.5 | 189.75 |  | 0 | 10 | 118 | 37 | 0 | 0% | 0% | 6.061% | 71.52% | 22.42% | 0%
54 | 5401 - Job: 5401 - Facility Timing & Synchron.-SICHTA | - | 5401 - Job: 5401 - Facility Timing & Synchron.-SICHTA | - |  | M | M | MM | 357 | 303.45 | 446.25 |  | 0 | 0 | 262 | 95 | 0 | 0% | 0% | 0% | 73.39% | 26.61% | 0%
55 | 5501 - Job: 5501 - Real Time Control System-SICHTA | - | 5501 - Job: 5501 - Real Time Control System-SICHTA | - |  | M | L | ML | 503 | 452.7 | 578.45 |  | 0 | 0 | 349 | 154 | 0 | 0% | 0% | 0% | 69.38% | 30.62% | 0%
56 | 5601 - Job: 5601 - Central Safety &Interlock Sys-SICHTA | - | 5601 - Job: 5601 - Central Safety &Interlock Sys-SICHTA | - |  | L | L | LL | 372 | 316.2 | 465 |  | 0 | 11 | 233 | 128 | 0 | 0% | 0% | 2.957% | 62.63% | 34.41% | 0%
58 | 5801 - Job: 5801 - Central I&C Integr& Oversight-SICHTA | - | 5801 - Job: 5801 - Central I&C Integr& Oversight-SICHTA | - |  | H | L | HL | 65 | 61.75 | 71.5 |  | 16 | 13 | 17 | 19 | 0 | 0% | 24.62% | 20% | 26.15% | 29.23% | 0%
61 | 6101 - Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System | 6101 - Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System |  | M | L | ML | 113 | 101.7 | 129.95 |  | 0 | 0 | 61 | 52 | 0 | 0% | 0% | 0% | 53.98% | 46.02% | 0%
62 | 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 621 - 621 - LN2 Supply & LN2 coil cooling supply | 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 621 - 621 - LN2 Supply & LN2 coil cooling supply |  | L | H | LH | 803 | 562.1 | 1284.8 |  | 60 | 156 | 385 | 202 | 0 | 0% | 7.472% | 19.43% | 47.95% | 25.16% | 0%
| 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 623 - 623 - GN2 Cryostat Cooling System | 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 623 - 623 - GN2 Cryostat Cooling System |  | L | H | LH | 764 | 534.8 | 1222.4 |  | 18 | 351 | 138 | 257 | 0 | 0% | 2.356% | 45.94% | 18.06% | 33.64% | 0%
63 | 6301 - Job: 6301 - Utility Systems-DUDEK | - | 6301 - Job: 6301 - Utility Systems-DUDEK | - |  | M | L | ML | 109 | 98.1 | 125.35 |  | 0 | 0 | 0 | 109 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
64 | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | - | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | - |  | L | M | LM | 633 | 506.4 | 886.2 |  | 0 | 0 | 157 | 476 | 0 | 0% | 0% | 0% | 24.8% | 75.2% | 0%
73 | 7301 - Job: 7301 - Platform Design & Fab-PERRY | - | 7301 - Job: 7301 - Platform Design & Fab-PERRY | - |  | H | L | HL | 212 | 201.4 | 233.2 |  | 63 | 25 | 124 | 0 | 0 | 0% | 29.72% | 11.79% | 58.49% | 0% | 0%
74 | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - |  | L | M | LM | 2323 | 1858.4 | 3252.2 |  | 106 | 156 | 529 | 1332 | 200 | 0% | 4.563% | 6.715% | 22.77% | 57.34% | 8.61%
75 | 7501 - Job: 7501 - Construction Support Crew-PERRY | S0P0 - General Assy Support | 7501 - Job: 7501 - Construction Support Crew-PERRY | S0P0 - General Assy Support |  | L | M | LM | 1323 | 1058.4 | 1852.2 |  | 0 | 0 | 352 | 845 | 126 | 0% | 0% | 0% | 26.61% | 63.87% | 9.524%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S1 - 1.0 - Component Preparation | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S1 - 1.0 - Component Preparation |  | L | M | LM | 330 | 264 | 462 |  | 0 | 0 | 330 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S10 - 10.0 - Type-C Shim Sizing/Prep | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S10 - 10.0 - Type-C Shim Sizing/Prep |  | L | M | LM | 3 | 2.4 | 4.2 |  | 0 | 0 | 3 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S11 - 11.0 - Type-C Inboard Shim Installation Check | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S11 - 11.0 - Type-C Inboard Shim Installation Check |  | L | M | LM | 302 | 241.6 | 422.8 |  | 0 | 0 | 178 | 124 | 0 | 0% | 0% | 0% | 58.94% | 41.06% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S12 - 12.0 - Install Remaining TF Coils | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S12 - 12.0 - Install Remaining TF Coils |  | L | M | LM | 229 | 183.2 | 320.6 |  | 0 | 0 | 25 | 204 | 0 | 0% | 0% | 0% | 10.92% | 89.08% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S13 - 13.0 - Install PF-4 Lwr & Solenoid suprt column | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S13 - 13.0 - Install PF-4 Lwr & Solenoid suprt column |  | L | M | LM | 1 | 0.8 | 1.4 |  | 0 | 0 | 0 | 1 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S14 - 14.0 - Move all Periods to installed position | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S14 - 14.0 - Move all Periods to installed position |  | L | M | LM | 510 | 408 | 714 |  | 0 | 0 | 10 | 500 | 0 | 0% | 0% | 0% | 1.961% | 98.04% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S15 - 15.0 - Move VV Period to final position and Weld | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S15 - 15.0 - Move VV Period to final position and Weld |  | L | M | LM | 482 | 385.6 | 674.8 |  | 0 | 0 | 0 | 482 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S16 - 16.0 - Move TF Coils to final position | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S16 - 16.0 - Move TF Coils to final position |  | L | M | LM | 37 | 29.6 | 51.8 |  | 0 | 0 | 0 | 37 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S17 - 17.0 - Install Lower PF Colis | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S17 - 17.0 - Install Lower PF Colis |  | L | M | LM | 7 | 5.6 | 9.8 |  | 0 | 0 | 0 | 7 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S18 - 18.0 - Transfer Weight to Final Machine Supports | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S18 - 18.0 - Transfer Weight to Final Machine Supports |  | L | M | LM | 56 | 44.8 | 78.4 |  | 0 | 0 | 0 | 56 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S19 - 19.0 - Vacuum Pump System | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S19 - 19.0 - Vacuum Pump System |  | L | M | LM | 145 | 116 | 203 |  | 0 | 0 | 0 | 145 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S2 - 2.0 - Test Cell Metrology set-up/deflection test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S2 - 2.0 - Test Cell Metrology set-up/deflection test |  | L | M | LM | 203 | 162.4 | 284.2 |  | 0 | 0 | 203 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S20 - 20.0 - MC/VVSA Annulus insulation fill | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S20 - 20.0 - MC/VVSA Annulus insulation fill |  | L | M | LM | 109 | 87.2 | 152.6 |  | 0 | 0 | 0 | 109 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S21 - 21.0 - Instl Remaining Trim Coils & Mag struct | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S21 - 21.0 - Instl Remaining Trim Coils & Mag struct |  | L | M | LM | 37 | 29.6 | 51.8 |  | 0 | 0 | 0 | 37 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S22 - 22.0 - Install solenoid & Remaining PF Coils | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S22 - 22.0 - Install solenoid & Remaining PF Coils |  | L | M | LM | 66 | 52.8 | 92.4 |  | 0 | 0 | 0 | 66 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S23 - 23.0 - Instl/Route Mag Leads to Transition Box | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S23 - 23.0 - Instl/Route Mag Leads to Transition Box |  | L | M | LM | 283 | 226.4 | 396.2 |  | 0 | 0 | 0 | 283 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S24 - 24.0 - Install LN2 and I&C Services | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S24 - 24.0 - Install LN2 and I&C Services |  | L | M | LM | 279 | 223.2 | 390.6 |  | 0 | 0 | 0 | 123 | 156 | 0% | 0% | 0% | 0% | 44.09% | 55.91%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S25 - 25.0 thru 35.0 - Cryostat NB duct & I&C Routing | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S25 - 25.0 thru 35.0 - Cryostat NB duct & I&C Routing |  | L | M | LM | 551 | 440.8 | 771.4 |  | 0 | 0 | 0 | 94 | 457 | 0% | 0% | 0% | 0% | 17.06% | 82.94%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S3 - 3.0 - Pre-installation set-up and test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S3 - 3.0 - Pre-installation set-up and test |  | L | M | LM | 110 | 88 | 154 |  | 0 | 0 | 110 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S4 - 4.0 - FPA-1 Installation and Assembly Test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S4 - 4.0 - FPA-1 Installation and Assembly Test |  | L | M | LM | 206 | 164.8 | 288.4 |  | 0 | 0 | 206 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S5 - 5.0 - Spool piece installation test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S5 - 5.0 - Spool piece installation test |  | L | M | LM | 68 | 54.4 | 95.2 |  | 0 | 0 | 68 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S6 - 6.0 - Spool piece flange machining | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S6 - 6.0 - Spool piece flange machining |  | L | M | LM | 160 | 128 | 224 |  | 0 | 0 | 112 | 48 | 0 | 0% | 0% | 0% | 70% | 30% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S7 - 7.0 - FPA-2 Installation | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S7 - 7.0 - FPA-2 Installation |  | L | M | LM | 67 | 53.6 | 93.8 |  | 0 | 0 | 67 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S8 - 8.0 - FPA-3 Installation | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S8 - 8.0 - FPA-3 Installation |  | L | M | LM | 66 | 52.8 | 92.4 |  | 0 | 0 | 66 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S9 - 9.0 - Measure Type-C MC Flanges | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S9 - 9.0 - Measure Type-C MC Flanges |  | L | M | LM | 11 | 8.8 | 15.4 |  | 0 | 0 | 11 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
76 | 7601 - Job: 7601 - Tooling Design & Fabrication-PERRY | - | 7601 - Job: 7601 - Tooling Design & Fabrication-PERRY | - |  | H | L | HL | 406 | 385.7 | 446.6 |  | 0 | 0 | 168 | 238 | 0 | 0% | 0% | 0% | 41.38% | 58.62% | 0%
81 | 8101 - Job: 8101 - Project Management &Control-ANDERSON | - | 8101 - Job: 8101 - Project Management &Control-ANDERSON | - |  | H | L | HL | 4156 | 3948.2 | 4571.6 |  | 813 | 1313 | 1176 | 736 | 118 | 0% | 19.56% | 31.59% | 28.3% | 17.71% | 2.839%
| 8101 - Job: 8101 - Project Management &Control-ANDERSON | RBLX - FY07 Rebaseline Exercise | 8101 - Job: 8101 - Project Management &Control-ANDERSON | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 8102 - Job: 8102 - NCSX MIE Management ORNL-LYON | - | 8102 - Job: 8102 - NCSX MIE Management ORNL-LYON | - |  | H | L | HL | 661 | 627.95 | 727.1 |  | 217 | 199 | 144 | 84 | 17 | 0% | 32.83% | 30.11% | 21.79% | 12.71% | 2.572%
82 | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | - | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | - |  | H | L | HL | 3253 | 3090.35 | 3578.3 |  | 552 | 880 | 898 | 823 | 100 | 0% | 16.97% | 27.05% | 27.61% | 25.3% | 3.074%
| 8203 - Job: 8203 - Design Integration-BROWN | - | 8203 - Job: 8203 - Design Integration-BROWN | - |  | M | M | MM | 2583 | 2195.55 | 3228.75 |  | 225 | 769 | 791 | 657 | 141 | 0% | 8.711% | 29.77% | 30.62% | 25.44% | 5.459%
| 8204 - Job: 8204 - Systems Analysis-BROOKS | - | 8204 - Job: 8204 - Systems Analysis-BROOKS | - |  | M | M | MM | 1034 | 878.9 | 1292.5 |  | 364 | 411 | 157 | 85 | 17 | 0% | 35.2% | 39.75% | 15.18% | 8.221% | 1.644%
| 8205 - Job: 8205 - Dimensional Control Coordin-ELLIS | - | 8205 - Job: 8205 - Dimensional Control Coordin-ELLIS | - |  | M | H | MH | 541 | 432.8 | 757.4 |  | 84 | 237 | 168 | 47 | 5 | 0% | 15.53% | 43.81% | 31.05% | 8.688% | 0.9242%
| 8210 - Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise | 8210 - Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN | 0 | FROZEN |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 8215 - Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise | 8215 - Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN | 193 | FROZEN |  |  | 55 | 59 | 60 | 19 | 0 | 0% | 28.5% | 30.57% | 31.09% | 9.845% | 0%
85 | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | PROC - Startup Documentation | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | PROC - Startup Documentation |  | H | L | HL | 343 | 325.85 | 377.3 |  | 0 | 273 | 70 | 0 | 0 | 0% | 0% | 79.59% | 20.41% | 0% | 0%
| 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | SU - Start-up | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | SU - Start-up |  | H | L | HL | 450 | 427.5 | 495 |  | 0 | 0 | 0 | 0 | 450 | 0% | 0% | 0% | 0% | 0% | 100%
89 | 8998 - Job: 8998 - Allocations-STRYKOWSKY | - | 8998 - Job: 8998 - Allocations-STRYKOWSKY | - |  | H | L | HL | 1923 | 1826.85 | 2115.3 |  | 288 | 460 | 485 | 512 | 178 | 0% | 14.98% | 23.92% | 25.22% | 26.63% | 9.256%
[10 empty] | 54040.55 | 75490.05
[7 empty] | ETC= |  | 61794 | 54040.55 | 75490.05 | 0 | 14072 | 16629 | 17064 | 11984 | 2045 | 0% | 22.77% | 26.91% | 27.61% | 19.39% | 3.309%
[7 empty] | Cost thru 1/31/08= |  | 76365 | -12.55% | 22.16% | FY2007: 59749
[7 empty] | EAC= |  | 138159
61794
0
14072
Note on I2: Christopher O. Gruber: Enter L, M or H
Note on J2: Christopher O. Gruber: Enter L, M or H

## Estimate Uncertainty Model
[9 empty] | updated | Estimate Uncertainty Range |  |  |  | updated | updated | updated | updated | updated | Percent ETC by Year
WBS2 |  |  | Job | WBS4 |  | Maturity | Complexity | Lookup | TOTAL | Low | High | Model | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2012 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2012
12 | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation |  | H | L | HL | 220 | 209 | 242 | 226.7999 |  | 44 | 39 | 0 | 137 | 0 | 0% | 20% | 17.73% | 0% | 62.27% | 0% | 220
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124T - Heater Tape for Port Stub | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124T - Heater Tape for Port Stub |  | H | L | HL |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124U - T/C and Heater Tape Leads | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124U - T/C and Heater Tape Leads |  | H | L | HL |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124V - Spacer Flux Loops & Boxes | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124V - Spacer Flux Loops & Boxes |  | H | L | HL |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 125 - VV Local I&C | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 125 - VV Local I&C |  | H | L | HL |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1250 - Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | - | 1250 - Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | - |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1260 - Job: 1260 NB Transition Ducts- GORANSON | - | 1260 - Job: 1260 NB Transition Ducts- GORANSON | - |  | M | L | ML | 566 | 509.4 | 650.9 | 543.3859 |  | 30 | 108 | 409 | 19 | 0 | 0% | 5.3% | 19.08% | 72.26% | 3.357% | 0%
| 1270 - Job: 1270 - Heater Control System-PPPL ( tbd) | - | 1270 - Job: 1270 - Heater Control System-PPPL ( tbd) | - |  | M | L | ML | 642 | 577.8 | 738.3 | 669.6055 |  | 0 | 93 | 361 | 188 | 0 | 0% | 0% | 14.49% | 56.23% | 29.28% | 0%
13 | 1302 - Job: 1302 - PF Design -CHRZANOWSKI | - | 1302 - Job: 1302 - PF Design -CHRZANOWSKI | - |  | H | L | HL | 91 | 86.45 | 100.1 | 92.4 |  | 91 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1302 - Job: 1302 - PF Design -CHRZANOWSKI | RBLX - FY07 Rebaseline Exercise | 1302 - Job: 1302 - PF Design -CHRZANOWSKI | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1352 - Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 13P - PF Coil Fabrication | 1352 - Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 13P - PF Coil Fabrication |  | H | L | HL | 1638 | 1556.1 | 1801.8 | 1727.2495 |  | 1054 | 533 | 21 | 30 | 0 | 0% | 64.35% | 32.54% | 1.282% | 1.832% | 0%
| 1353 - Job: 1353 - CS Structure Procurement-PERRY | 132A - CS Support Structure | 1353 - Job: 1353 - CS Structure Procurement-PERRY | 132A - CS Support Structure |  | H | L | HL | 358 | 340.1 | 393.8 | 373.7999 |  | 34 | 0 | 254 | 70 | 0 | 0% | 9.497% | 0% | 70.95% | 19.55% | 0%
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | TRIM - Trim Coil **Updated estimate** | 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | TRIM - Trim Coil **Updated estimate** |  | M | L | ML | 1433 | 1289.7 | 1647.95 | 1757.447 |  | 858 | 575 | 0 | 0 | 0 | 0% | 59.87% | 40.13% | 0% | 0% | 0%
| 1355 - Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE | 134 - TF/PF Loacl I&C | 1355 - Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE | 134 - TF/PF Loacl I&C |  | M | L | ML | 109 | 98.1 | 125.35 | 117.6623 |  | 57 | 50 | 0 | 2 | 0 | 0% | 52.29% | 45.87% | 0% | 1.835% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | - | 1361 - Job: 1361 - TF Fabrication-KALISH | - |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1361 - Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight | 1361 - Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight |  | H | M | HM | 153 | 137.7 | 175.95 | 166.8665 |  | 136 | 17 | 0 | 0 | 0 | 0% | 88.89% | 11.11% | 0% | 0% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | 13Y - TF Fabrication Contract | 1361 - Job: 1361 - TF Fabrication-KALISH | 13Y - TF Fabrication Contract |  | H | M | HM | 474 | 426.6 | 545.1 | 507.0176 |  | 427 | 47 | 0 | 0 | 0 | 0% | 90.08% | 9.916% | 0% | 0% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | RBLX - FY07 Rebaseline Exercise | 1361 - Job: 1361 - TF Fabrication-KALISH | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
14 | 1404 - Job: 1404 - MCWF R&D 1st Prod Casting**CLOSED** | - | 1404 - Job: 1404 - MCWF R&D 1st Prod Casting**CLOSED** | - |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - | 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - |  | L | L | LL | 123 | 104.55 | 153.75 | 142.1985 |  | 123 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1411 - Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - | 1411 - Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - |  | Closed |  | Closed |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications |  | H | L | HL |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDC - Blanket thermal insulation | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDC - Blanket thermal insulation |  | H | L | HL |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDE - Top level assy models/drawings | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDE - Top level assy models/drawings |  | H | L | HL | 10 | 9.5 | 11 | 10.5 |  | 10 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDF - Analysis and closeout documentation | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDF - Analysis and closeout documentation |  | H | L | HL | 122 | 115.9 | 134.2 | 128.1 |  | 122 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | TCCO - Type C Design Closeout | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | TCCO - Type C Design Closeout |  | H | L | HL | 7 | 6.65 | 7.7 | 7.35 |  | 0 | 7 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | - | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | - |  | L | M | LM | 23 | 18.4 | 32.2 | 27.6 |  | 23 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142B - Outboard Interface-Bolted Joint Tests-Tension | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142B - Outboard Interface-Bolted Joint Tests-Tension |  | L | M | LM |  |  |  |  | FY2008: 2; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142C - Outboard Interface-Bolted Joint Tests-Shear | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142C - Outboard Interface-Bolted Joint Tests-Shear |  | L | M | LM |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142F - Inboard Interface-AB/BC/AA | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142F - Inboard Interface-AB/BC/AA |  | L | M | LM | 4 | 3.2 | 5.6 | 4.8 |  | 3 | 0 | 0 | 0 | 0 | 0% | 75% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142G - Inboard Interface-CC | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142G - Inboard Interface-CC |  | L | M | LM | Included above |  |  |  | FY2008: 1; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142H - Weld Access test | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142H - Weld Access test |  | L | M | LM |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142Z - Outboard Interface | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142Z - Outboard Interface |  | L | M | LM |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1429 - Job: 1429 - MC Interface R&D-DUDEK | 142D - Outboard Interface-Friction | 1429 - Job: 1429 - MC Interface R&D-DUDEK | 142D - Outboard Interface-Friction |  | Closed |  | Closed | 4 | FROZEN |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders |  | H | M | HM | 5 | 4.5 | 5.75 | 5.3483 |  | 5 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BUSH - Bushings | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BUSH - Bushings |  | H | M | HM | 19 | 17.1 | 21.85 | 21.3931 |  | 19 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | PUCK - Pucks | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | PUCK - Pucks |  | H | M | HM | 36 | 32.4 | 41.4 | 38.5077 |  | 30 | 6 | 0 | 0 | 0 | 0% | 83.33% | 16.67% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMS - Shims-Outboard | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMS - Shims-Outboard |  | H | M | HM | 593 | 533.7 | 681.95 | 649.282 |  | 593 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMT - Shims-Inboard | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMT - Shims-Inboard |  | H | M | HM | 131 | 117.9 | 150.65 | 146.5431 |  | 93 | 38 | 0 | 0 | 0 | 0% | 70.99% | 29.01% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMU - Shims- C-C Joint | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMU - Shims- C-C Joint |  | H | M | HM | 28 | 25.2 | 32.2 | 29.9504 |  | 0 | 0 | 28 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | STUD - Studs Washers Nuts | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | STUD - Studs Washers Nuts |  | H | M | HM | 143 | 128.7 | 164.45 | 156.17 |  | 143 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | TECH - Misc Tech Shop Support | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | TECH - Misc Tech Shop Support | 20 | H | M | HM | 119 | 107.1 | 136.85 | 127.2892 |  | 48 | 71 | 0 | 0 | 0 | 0% | 40.34% | 59.66% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI |  | H | H | HH | 912 | 775.2 | 1140 | 1040.1764 |  | 98 | 0 | 0 | 0 | 0 | 0% | 10.75% | 0% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1A - Station 1a/4 Casting Prep | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1A - Station 1a/4 Casting Prep |  | H | H | HH | Included above |  |  |  | FY2008: 28; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2 - Station 2-Winding Instl Chill Plates Tubing Bag | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2 - Station 2-Winding Instl Chill Plates Tubing Bag |  | H | H | HH | Included above |  |  |  | FY2008: 84; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3 - Station 3-Winding Instl Chill Plates Tubing Bag | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3 - Station 3-Winding Instl Chill Plates Tubing Bag |  | H | H | HH | Included above |  |  |  | FY2008: 179; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5 - Station 5-VPI | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5 - Station 5-VPI |  | H | H | HH | Included above |  |  |  | FY2008: 175; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | LABR - LOE Oversight & Supervision | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | LABR - LOE Oversight & Supervision |  | H | H | HH | Included above |  |  |  | FY2008: 348; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians | 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians |  | M | L | ML | 282 | 253.8 | 324.3 | 309.131 |  | 130 | 13 | 0 | 0 | 0 | 0% | 46.1% | 4.61% | 0% | 0% | 0%
| 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLTS - Punchlist Tech shop/RESA | 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLTS - Punchlist Tech shop/RESA |  | M | L | ML | Included above |  |  |  | FY2008: 139; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
15 | 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | - | 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | - |  | M | L | ML | 90 | 81 | 103.5 | 139.0555 |  | 90 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1550 - Job: 1550 - Coil Struct. Procurement -PERRY | - | 1550 - Job: 1550 - Coil Struct. Procurement -PERRY | - |  | M | L | ML | 1440 | 1296 | 1656 | 1547.7941 |  | 230 | 1210 | 0 | 0 | 0 | 0% | 15.97% | 84.03% | 0% | 0% | 0%
16 | 1601 - Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution | 1601 - Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution |  | H | L | HL | 306 | 290.7 | 336.6 | 344.3999 |  | 150 | 156 | 0 | 0 | 0 | 0% | 49.02% | 50.98% | 0% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 162 - 162 - Electrical Leads | 1601 - Job: 1601 - Coil Services Design-GORANSON | 162 - 162 - Electrical Leads |  | M | L | ML | 745 | 670.5 | 856.75 | 835.4024 |  | 129 | 128 | 488 | 0 | 0 | 0% | 17.32% | 17.18% | 65.5% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 163 - 163 - Coil Protection System | 1601 - Job: 1601 - Coil Services Design-GORANSON | 163 - 163 - Coil Protection System |  | H | L | HL | 31 | 29.45 | 34.1 | 32.55 |  | 0 | 31 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | RBLX - FY07 Rebaseline Exercise | 1601 - Job: 1601 - Coil Services Design-GORANSON | RBLX - FY07 Rebaseline Exercise |  | H | L | HL |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
17 | 1701 - Job: 1701 - Cryostat Design-RAFTOPOLOUS | - | 1701 - Job: 1701 - Cryostat Design-RAFTOPOLOUS | - |  | L | H | LH | 580 | 406 | 928 | 484.8 |  | 61 | 403 | 116 | 0 | 0 | 0% | 10.52% | 69.48% | 20% | 0% | 0%
| 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | - | 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | - |  | H | L | HL | 139 | 132.05 | 152.9 | 40.95 |  | 139 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1751 - Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | - | 1751 - Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | - |  | H | L | HL | 550 | 522.5 | 605 | 457.7999 |  | 20 | 46 | 288 | 196 | 0 | 0% | 3.636% | 8.364% | 52.36% | 35.64% | 0%
| 1752 - Job: 1752 - Base Support Proc-PERRY | 172 - 172 - Base Support Structure | 1752 - Job: 1752 - Base Support Proc-PERRY | 172 - 172 - Base Support Structure |  | H | L | HL | 231 | 219.45 | 254.1 | 201.5999 |  | 1 | 230 | 0 | 0 | 0 | 0% | 0.4329% | 99.57% | 0% | 0% | 0%
18 | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision |  | H | M | HM | 3826 | 3443.4 | 4399.9 | 3907.4581 |  | 814 | 1540 | 1472 | 0 | 0 | 0% | 21.28% | 40.25% | 38.47% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.00 - Station 3-Modular Coil to VVSA Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.00 - Station 3-Modular Coil to VVSA Assembly |  | M | L | ML | 250 | 225 | 287.5 | 272.7626 |  | 236 | 14 | 0 | 0 | 0 | 0% | 94.4% | 5.6% | 0% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 5.00 - Station 5-Final Field Period Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 5.00 - Station 5-Final Field Period Assembly |  | M | L | ML | 203 | 182.7 | 233.45 | 222.4887 |  | 203 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 6.00 - 6.00-Final Machine Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 6.00 - 6.00-Final Machine Assembly |  | L | M | LM | 541 | 432.8 | 757.4 | 658.8 |  | 313 | 228 | 0 | 0 | 0 | 0% | 57.86% | 42.14% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | - | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | - |  | M | M | MM | 54 | 45.9 | 67.5 | 60.4624 |  | 48 | 6 | 0 | 0 | 0 | 0% | 88.89% | 11.11% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1.00 - 1.00-VV Prep Station | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1.00 - 1.00-VV Prep Station |  | M | M | MM | 19 | 16.15 | 23.75 | 21.2738 |  | 10 | 9 | 0 | 0 | 0 | 0% | 52.63% | 47.37% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 2.00 - Station 2-Modular Coil Sub- Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 2.00 - Station 2-Modular Coil Sub- Assembly |  | M | M | MM | 2 | 1.7 | 2.5 | 2.2393 |  | 2 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 3.00 - Station 3-Modular Coil to VVSA Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 3.00 - Station 3-Modular Coil to VVSA Assembly |  | M | M | MM | 30 | 25.5 | 37.5 | 33.5902 |  | 30 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 5.00 - Station 5-Final Field Period Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 5.00 - Station 5-Final Field Period Assembly |  | M | M | MM | 114 | 96.9 | 142.5 | 127.6427 |  | 114 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 6.00 - 6.00-Final Machine Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 6.00 - 6.00-Final Machine Assembly |  | M | M | MM | 137 | 116.45 | 171.25 | 153.3952 |  | 135 | 2 | 0 | 0 | 0 | 0% | 98.54% | 1.46% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S0P0 - General Assy Support | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S0P0 - General Assy Support |  | H | M | HM | 1946 | 1751.4 | 2237.9 | 2092.2497 |  | 446 | 665 | 835 | 0 | 0 | 0% | 22.92% | 34.17% | 42.91% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 |  | H | M | HM | 552 | 496.8 | 634.8 | 599.0081 |  | 189 | 0 | 0 | 0 | 0 | 0% | 34.24% | 0% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 |  | H | M | HM | Included above |  |  |  | FY2008: 83; FY2009: 41; FY2010: 0; FY2011: 0; FY2012: 0
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 |  | H | M | HM | Included above |  |  |  | FY2008: 43; FY2009: 85; FY2010: 0; FY2011: 0; FY2012: 0
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) |  | H | M | HM | Included above |  |  |  | FY2008: 0; FY2009: 111; FY2010: 0; FY2011: 0; FY2012: 0
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H1 - Station 2 MC subassy A1B1C1 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H1 - Station 2 MC subassy A1B1C1 |  | M | H | MH | 414 | 331.2 | 579.6 | 506.4 |  | 351 | 63 | 0 | 0 | 0 | 0% | 84.78% | 15.22% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H2 - Station 2 MC subassy A2B2C2 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H2 - Station 2 MC subassy A2B2C2 |  | M | H | MH | 314 | 251.2 | 439.6 | 381.6 |  | 249 | 65 | 0 | 0 | 0 | 0% | 79.3% | 20.7% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H3 - Station 2 MC subassy A3B3C3 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H3 - Station 2 MC subassy A3B3C3 |  | M | H | MH | 317 | 253.6 | 443.8 | 385.2 |  | 147 | 170 | 0 | 0 | 0 | 0% | 46.37% | 53.63% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H4 - Station 2 MC subassy A4B4C4 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H4 - Station 2 MC subassy A4B4C4 |  | M | H | MH | 311 | 248.8 | 435.4 | 373.2 |  | 0 | 311 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H5 - Station 2 MC subassy A5B5C5 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H5 - Station 2 MC subassy A5B5C5 |  | M | H | MH | 312 | 249.6 | 436.8 | 372 |  | 0 | 312 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H6 - Station 2 MC subassy A6B6C6 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2H6 - Station 2 MC subassy A6B6C6 |  | M | H | MH | 310 | 248 | 434 | 372 |  | 0 | 273 | 37 | 0 | 0 | 0% | 0% | 88.06% | 11.94% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks |  | M | H | MH | 323 | 258.4 | 452.2 | 487.2 |  | 257 | 66 | 0 | 0 | 0 | 0% | 79.57% | 20.43% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PR - Station 2 Trials & Development |  | M | H | MH |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PX - Setup | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S2PX - Setup |  | H | H | HH | 967 | 821.95 | 1208.75 | 1086.083 |  | 804 | 92 | 71 | 0 | 0 | 0% | 83.14% | 9.514% | 7.342% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General |  | M | H | MH | 188 | 150.4 | 263.2 | 225.6 |  | 8 | 180 | 0 | 0 | 0 | 0% | 4.255% | 95.74% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 |  | M | H | MH | 585 | 468 | 819 | 703.2 |  | 0 | 585 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 |  | M | H | MH | 408 | 326.4 | 571.2 | 489.6 |  | 0 | 243 | 165 | 0 | 0 | 0% | 0% | 59.56% | 40.44% | 0% | 0%
| 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | 1810 - Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 |  | M | H | MH | 398 | 318.4 | 557.2 | 477.6 |  | 0 | 42 | 356 | 0 | 0 | 0% | 0% | 10.55% | 89.45% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General |  | L | M | LM | 294 | 235.2 | 411.6 | 355.2 |  | 0 | 276 | 18 | 0 | 0 | 0% | 0% | 93.88% | 6.122% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) |  | L | M | LM | 534 | 427.2 | 747.6 | 640.8 |  | 0 | 339 | 195 | 0 | 0 | 0% | 0% | 63.48% | 36.52% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) |  | L | M | LM | 534 | 427.2 | 747.6 | 640.8 |  | 0 | 0 | 534 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) |  | L | M | LM | 524 | 419.2 | 733.6 | 628.8 |  | 0 | 0 | 524 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
19 | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 191 - 191 - Stellarator Core Management & Oversight | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 191 - 191 - Stellarator Core Management & Oversight |  | H | L | HL | 941 | 893.95 | 1035.1 | 988.0497 |  | 145 | 237 | 258 | 261 | 40 | 0% | 15.41% | 25.19% | 27.42% | 27.74% | 4.251%
| 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 192 - 192 - Stellarator Core Integr & Global Analysis | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 192 - 192 - Stellarator Core Integr & Global Analysis |  | H | L | HL | 1309 | 1243.55 | 1439.9 | 972.2997 |  | 231 | 386 | 402 | 250 | 40 | 0% | 17.65% | 29.49% | 30.71% | 19.1% | 3.056%
21 | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | - | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | - |  | L | L | LL | 334 | 283.9 | 417.5 | 286.6363 |  | 0 | 161 | 53 | 120 | 0 | 0% | 0% | 48.2% | 15.87% | 35.93% | 0%
22 | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - |  | L | L | LL | 683 | 580.55 | 853.75 | 640.4531 |  | 0 | 280 | 197 | 206 | 0 | 0% | 0% | 41% | 28.84% | 30.16% | 0%
31 | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads |  | H | L | HL | 47 | 44.65 | 51.7 | 53.55 |  | 47 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124V - Spacer Flux Loops & Boxes | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124V - Spacer Flux Loops & Boxes |  | H | L | HL | 56 | 53.2 | 61.6 | 58.8 |  | 0 | 56 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD2 - Modular Coil C-wound Loops | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD2 - Modular Coil C-wound Loops |  | H | L | HL | 18 | 17.1 | 19.8 | 18.9 |  | 16 | 2 | 0 | 0 | 0 | 0% | 88.89% | 11.11% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD3 - Rogowski Coils | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD3 - Rogowski Coils |  | H | L | HL | 180 | 171 | 198 | 191.0999 |  | 92 | 68 | 20 | 0 | 0 | 0% | 51.11% | 37.78% | 11.11% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD4 - TF and PF Co-wound Loops | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD4 - TF and PF Co-wound Loops |  | H | L | HL | 46 | 43.7 | 50.6 | 49.35 |  | 42 | 4 | 0 | 0 | 0 | 0% | 91.3% | 8.696% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | VLPB - Voltage Loops & Protective Boxes | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | VLPB - Voltage Loops & Protective Boxes |  | H | L | HL | 62 | 58.9 | 68.2 | 65.1 |  | 57 | 5 | 0 | 0 | 0 | 0% | 91.94% | 8.065% | 0% | 0% | 0%
36 | 3601 - Job: 3601 - Edge Divertor Diagnostics-STRATTON | - | 3601 - Job: 3601 - Edge Divertor Diagnostics-STRATTON | - |  | M | L | ML | 29 | 26.1 | 33.35 | 31.0201 |  | 0 | 0 | 29 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
38 | 3801 - Job: 3801 - Electron Beam Mapping-STRATTON | - | 3801 - Job: 3801 - Electron Beam Mapping-STRATTON | - |  | M | M | MM | 257 | 218.45 | 321.25 | 287.756 |  | 0 | 171 | 31 | 55 | 0 | 0% | 0% | 66.54% | 12.06% | 21.4% | 0%
39 | 3901 - Job: 3901 - Diagnostics sys Integration-STRATTON | - | 3901 - Job: 3901 - Diagnostics sys Integration-STRATTON | - |  | H | L | HL | 111 | 105.45 | 122.1 | 118.65 |  | 16 | 31 | 30 | 34 | 0 | 0% | 14.41% | 27.93% | 27.03% | 30.63% | 0%
41 | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | - | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | - |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems |  | H | L | HL | 120 | 114 | 132 | 127.05 |  | 0 | 20 | 33 | 67 | 0 | 0% | 0% | 16.67% | 27.5% | 55.83% | 0%
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 412 - 412 - Experimental AC Power Systems | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 412 - 412 - Experimental AC Power Systems |  | H | L | HL | 36 | 34.2 | 39.6 | 28.35 |  | 0 | 7 | 29 | 0 | 0 | 0% | 0% | 19.44% | 80.56% | 0% | 0%
43 | 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems | 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems |  | H | L | HL | 577 | 548.15 | 634.7 | 614.2498 |  | 47 | 94 | 434 | 2 | 0 | 0% | 8.146% | 16.29% | 75.22% | 0.3466% | 0%
44 | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks |  | M | L | ML | 482 | 433.8 | 554.3 | 513.4355 |  | 10 | 43 | 242 | 187 | 0 | 0% | 2.075% | 8.921% | 50.21% | 38.8% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 442 - 442 - Kirk Key Interlocks | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 442 - 442 - Kirk Key Interlocks |  | M | L | ML | 69 | 62.1 | 79.35 | 75.9457 |  | 0 | 20 | 17 | 32 | 0 | 0% | 0% | 28.99% | 24.64% | 46.38% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 443 - 443 - Real Time Control Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 443 - 443 - Real Time Control Systems |  | M | L | ML | 14 | 12.6 | 16.1 | 14.9752 |  | 0 | 0 | 14 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 444 - 444 - Instrument Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 444 - 444 - Instrument Systems |  | M | L | ML | 241 | 216.9 | 277.15 | 228.9067 |  | 0 | 16 | 148 | 77 | 0 | 0% | 0% | 6.639% | 61.41% | 31.95% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 445 - 445 - Coil Protection Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 445 - 445 - Coil Protection Systems |  | M | L | ML | 276 | 248.4 | 317.4 | 294.1558 |  | 24 | 48 | 71 | 133 | 0 | 0% | 8.696% | 17.39% | 25.72% | 48.19% | 0%
45 | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces |  | H | L | HL | 319 | 303.05 | 350.9 | 312.8999 |  | 51 | 119 | 105 | 44 | 0 | 0% | 15.99% | 37.3% | 32.92% | 13.79% | 0%
| 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452 - 452 - Electrical Systems Support | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452 - 452 - Electrical Systems Support |  | H | L | HL | 199 | 189.05 | 218.9 | 208.9499 |  | 0 | 0 | 133 | 66 | 0 | 0% | 0% | 0% | 66.83% | 33.17% | 0%
| 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453 - 453 - System Testing (PTP's) | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453 - 453 - System Testing (PTP's) |  | H | L | HL | 386 | 366.7 | 424.6 | 405.2999 |  | 0 | 0 | 0 | 386 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
51 | 5101 - Job: 5101 - Network and Fiber Infrastruct-SICHTA | - | 5101 - Job: 5101 - Network and Fiber Infrastruct-SICHTA | - |  | M | L | ML | 222 | 199.8 | 255.3 | 237.4639 |  | 0 | 0 | 133 | 89 | 0 | 0% | 0% | 0% | 59.91% | 40.09% | 0%
52 | 5201 - Job: 5201 - I&C Systems-SICHTA | - | 5201 - Job: 5201 - I&C Systems-SICHTA | - |  | M | L | ML | 411 | 369.9 | 472.65 | 439.6292 |  | 0 | 19 | 282 | 110 | 0 | 0% | 0% | 4.623% | 68.61% | 26.76% | 0%
53 | 5301 - Job: 5301 - Data Acquisition-SICHTA | - | 5301 - Job: 5301 - Data Acquisition-SICHTA | - |  | M | L | ML | 165 | 148.5 | 189.75 | 176.4935 |  | 0 | 10 | 118 | 37 | 0 | 0% | 0% | 6.061% | 71.52% | 22.42% | 0%
54 | 5401 - Job: 5401 - Facility Timing & Synchron.-SICHTA | - | 5401 - Job: 5401 - Facility Timing & Synchron.-SICHTA | - |  | M | M | MM | 357 | 303.45 | 446.25 | 399.7233 |  | 0 | 0 | 262 | 95 | 0 | 0% | 0% | 0% | 73.39% | 26.61% | 0%
55 | 5501 - Job: 5501 - Real Time Control System-SICHTA | - | 5501 - Job: 5501 - Real Time Control System-SICHTA | - |  | M | L | ML | 503 | 452.7 | 578.45 | 538.0376 |  | 0 | 0 | 349 | 154 | 0 | 0% | 0% | 0% | 69.38% | 30.62% | 0%
56 | 5601 - Job: 5601 - Central Safety &Interlock Sys-SICHTA | - | 5601 - Job: 5601 - Central Safety &Interlock Sys-SICHTA | - |  | L | L | LL | 372 | 316.2 | 465 | 418.7578 |  | 0 | 11 | 233 | 128 | 0 | 0% | 0% | 2.957% | 62.63% | 34.41% | 0%
58 | 5801 - Job: 5801 - Central I&C Integr& Oversight-SICHTA | - | 5801 - Job: 5801 - Central I&C Integr& Oversight-SICHTA | - |  | H | L | HL | 65 | 61.75 | 71.5 | 68.25 |  | 16 | 13 | 17 | 19 | 0 | 0% | 24.62% | 20% | 26.15% | 29.23% | 0%
61 | 6101 - Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System | 6101 - Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System |  | M | L | ML | 113 | 101.7 | 129.95 | 120.8713 |  | 0 | 0 | 61 | 52 | 0 | 0% | 0% | 0% | 53.98% | 46.02% | 0%
62 | 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 621 - 621 - LN2 Supply & LN2 coil cooling supply | 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 621 - 621 - LN2 Supply & LN2 coil cooling supply |  | L | H | LH | 803 | 562.1 | 1284.8 | 346.8 |  | 60 | 156 | 385 | 202 | 0 | 0% | 7.472% | 19.43% | 47.95% | 25.16% | 0%
| 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 623 - 623 - GN2 Cryostat Cooling System | 6201 - Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 623 - 623 - GN2 Cryostat Cooling System |  | L | H | LH | 764 | 534.8 | 1222.4 | 829.2 |  | 18 | 351 | 138 | 257 | 0 | 0% | 2.356% | 45.94% | 18.06% | 33.64% | 0%
63 | 6301 - Job: 6301 - Utility Systems-DUDEK | - | 6301 - Job: 6301 - Utility Systems-DUDEK | - |  | M | L | ML | 109 | 98.1 | 125.35 | 116.5926 |  | 0 | 0 | 0 | 109 | 0 | 0% | 0% | 0% | 0% | 100% | 0%
64 | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | - | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | - |  | L | M | LM | 633 | 506.4 | 886.2 | 759.6 |  | 0 | 0 | 157 | 476 | 0 | 0% | 0% | 0% | 24.8% | 75.2% | 0%
73 | 7301 - Job: 7301 - Platform Design & Fab-PERRY | - | 7301 - Job: 7301 - Platform Design & Fab-PERRY | - |  | H | L | HL | 212 | 201.4 | 233.2 | 225.7499 |  | 63 | 25 | 124 | 0 | 0 | 0% | 29.72% | 11.79% | 58.49% | 0% | 0%
74 | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - |  | L | M | LM | 2323 | 1858.4 | 3252.2 | 3422.3998 |  | 106 | 156 | 529 | 1332 | 200 | 0% | 4.563% | 6.715% | 22.77% | 57.34% | 8.61%
75 | 7501 - Job: 7501 - Construction Support Crew-PERRY | S0P0 - General Assy Support | 7501 - Job: 7501 - Construction Support Crew-PERRY | S0P0 - General Assy Support |  | L | M | LM | 1323 | 1058.4 | 1852.2 | 1587.5999 |  | 0 | 0 | 352 | 845 | 126 | 0% | 0% | 0% | 26.61% | 63.87% | 9.524%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S1 - 1.0 - Component Preparation | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S1 - 1.0 - Component Preparation |  | L | M | LM | 4318 | 3454.4 | 6045.2 | 5141.9997 |  | 0 | 0 | 330 | 0 | 0 | 0% | 0% | 0% | 7.642% | 0% | 0%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S10 - 10.0 - Type-C Shim Sizing/Prep | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S10 - 10.0 - Type-C Shim Sizing/Prep |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 3; FY2011: 0; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S11 - 11.0 - Type-C Inboard Shim Installation Check | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S11 - 11.0 - Type-C Inboard Shim Installation Check |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 178; FY2011: 124; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S12 - 12.0 - Install Remaining TF Coils | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S12 - 12.0 - Install Remaining TF Coils |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 25; FY2011: 204; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S13 - 13.0 - Install PF-4 Lwr & Solenoid suprt column | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S13 - 13.0 - Install PF-4 Lwr & Solenoid suprt column |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 1; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S14 - 14.0 - Move all Periods to installed position | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S14 - 14.0 - Move all Periods to installed position |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 10; FY2011: 500; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S15 - 15.0 - Move VV Period to final position and Weld | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S15 - 15.0 - Move VV Period to final position and Weld |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 482; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S16 - 16.0 - Move TF Coils to final position | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S16 - 16.0 - Move TF Coils to final position |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 37; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S17 - 17.0 - Install Lower PF Colis | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S17 - 17.0 - Install Lower PF Colis |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 7; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S18 - 18.0 - Transfer Weight to Final Machine Supports | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S18 - 18.0 - Transfer Weight to Final Machine Supports |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 56; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S19 - 19.0 - Vacuum Pump System | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S19 - 19.0 - Vacuum Pump System |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 145; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S2 - 2.0 - Test Cell Metrology set-up/deflection test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S2 - 2.0 - Test Cell Metrology set-up/deflection test |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 203; FY2011: 0; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S20 - 20.0 - MC/VVSA Annulus insulation fill | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S20 - 20.0 - MC/VVSA Annulus insulation fill |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 109; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S21 - 21.0 - Instl Remaining Trim Coils & Mag struct | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S21 - 21.0 - Instl Remaining Trim Coils & Mag struct |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 37; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S22 - 22.0 - Install solenoid & Remaining PF Coils | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S22 - 22.0 - Install solenoid & Remaining PF Coils |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 66; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S23 - 23.0 - Instl/Route Mag Leads to Transition Box | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S23 - 23.0 - Instl/Route Mag Leads to Transition Box |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 283; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S24 - 24.0 - Install LN2 and I&C Services | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S24 - 24.0 - Install LN2 and I&C Services |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 123; FY2012: 156
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S25 - 25.0 thru 35.0 - Cryostat NB duct & I&C Routing | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S25 - 25.0 thru 35.0 - Cryostat NB duct & I&C Routing |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 94; FY2012: 457
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S3 - 3.0 - Pre-installation set-up and test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S3 - 3.0 - Pre-installation set-up and test |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 110; FY2011: 0; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S4 - 4.0 - FPA-1 Installation and Assembly Test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S4 - 4.0 - FPA-1 Installation and Assembly Test |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 206; FY2011: 0; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S5 - 5.0 - Spool piece installation test | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S5 - 5.0 - Spool piece installation test |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 68; FY2011: 0; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S6 - 6.0 - Spool piece flange machining | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S6 - 6.0 - Spool piece flange machining |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 112; FY2011: 48; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S7 - 7.0 - FPA-2 Installation | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S7 - 7.0 - FPA-2 Installation |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 67; FY2011: 0; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S8 - 8.0 - FPA-3 Installation | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S8 - 8.0 - FPA-3 Installation |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 66; FY2011: 0; FY2012: 0
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S9 - 9.0 - Measure Type-C MC Flanges | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 6S9 - 9.0 - Measure Type-C MC Flanges |  | L | M | LM | Included above |  |  |  | FY2008: 0; FY2009: 0; FY2010: 11; FY2011: 0; FY2012: 0
76 | 7601 - Job: 7601 - Tooling Design & Fabrication-PERRY | - | 7601 - Job: 7601 - Tooling Design & Fabrication-PERRY | - |  | H | L | HL | 406 | 385.7 | 446.6 | 426.2999 |  | 0 | 0 | 168 | 238 | 0 | 0% | 0% | 0% | 41.38% | 58.62% | 0%
81 | 8101 - Job: 8101 - Project Management &Control-ANDERSON | - | 8101 - Job: 8101 - Project Management &Control-ANDERSON | - |  | H | L | HL | 4156 | 3948.2 | 4571.6 | 4613.6985 |  | 813 | 1313 | 1176 | 736 | 118 | 0% | 19.56% | 31.59% | 28.3% | 17.71% | 2.839%
| 8101 - Job: 8101 - Project Management &Control-ANDERSON | RBLX - FY07 Rebaseline Exercise | 8101 - Job: 8101 - Project Management &Control-ANDERSON | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 8102 - Job: 8102 - NCSX MIE Management ORNL-LYON | - | 8102 - Job: 8102 - NCSX MIE Management ORNL-LYON | - |  | H | L | HL | 661 | 627.95 | 727.1 | 1232.6996 |  | 217 | 199 | 144 | 84 | 17 | 0% | 32.83% | 30.11% | 21.79% | 12.71% | 2.572%
82 | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | - | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | - |  | H | L | HL | 3253 | 3090.35 | 3578.3 | 3430.3489 |  | 552 | 880 | 898 | 823 | 100 | 0% | 16.97% | 27.05% | 27.61% | 25.3% | 3.074%
| 8203 - Job: 8203 - Design Integration-BROWN | - | 8203 - Job: 8203 - Design Integration-BROWN | - |  | M | M | MM | 2583 | 2195.55 | 3228.75 | 2895.4749 |  | 225 | 769 | 791 | 657 | 141 | 0% | 8.711% | 29.77% | 30.62% | 25.44% | 5.459%
| 8204 - Job: 8204 - Systems Analysis-BROOKS | - | 8204 - Job: 8204 - Systems Analysis-BROOKS | - |  | M | M | MM | 1034 | 878.9 | 1292.5 | 1166.6995 |  | 364 | 411 | 157 | 85 | 17 | 0% | 35.2% | 39.75% | 15.18% | 8.221% | 1.644%
| 8205 - Job: 8205 - Dimensional Control Coordin-ELLIS | - | 8205 - Job: 8205 - Dimensional Control Coordin-ELLIS | - |  | M | H | MH | 541 | 432.8 | 757.4 | 649.2 |  | 84 | 237 | 168 | 47 | 5 | 0% | 15.53% | 43.81% | 31.05% | 8.688% | 0.9242%
| 8210 - Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise | 8210 - Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN |  |  |  |  | FY2008: 0; FY2009: 0; FY2010: 0; FY2011: 0; FY2012: 0
| 8215 - Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise | 8215 - Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise |  | FROZEN |  | FROZEN | 193 | FROZEN |  | 193 |  | 55 | 59 | 60 | 19 | 0 | 0% | 28.5% | 30.57% | 31.09% | 9.845% | 0%
85 | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | PROC - Startup Documentation | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | PROC - Startup Documentation |  | H | L | HL | 343 | 325.85 | 377.3 | 360.1499 |  | 0 | 273 | 70 | 0 | 0 | 0% | 0% | 79.59% | 20.41% | 0% | 0%
| 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | SU - Start-up | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | SU - Start-up |  | H | L | HL | 450 | 427.5 | 495 | 449.3999 |  | 0 | 0 | 0 | 0 | 450 | 0% | 0% | 0% | 0% | 0% | 100%
89 | 8998 - Job: 8998 - Allocations-STRYKOWSKY | - | 8998 - Job: 8998 - Allocations-STRYKOWSKY | - |  | H | L | HL | 1923 | 1826.85 | 2115.3 | 1960.3494 |  | 288 | 460 | 485 | 512 | 178 | 0% | 14.98% | 23.92% | 25.22% | 26.63% | 9.256%
-
|  | - | [6 empty] | 61792 | 54038.95 | 75487.25 | 68183.9504 |  | 14072 | 16629 | 17064 | 11984 | 2045 |  | 22.77% | 26.91% | 27.61% | 19.39% | 3.309% | 61794
[6 empty] | Estimating Process Uncertainty |  |  | 0 | -1% | 3% | 0.6667%
[7 empty] | ETC= |  | 61792 | 53498.5605 | 77751.8675 | 68638.5101 | 0 | 14072 | 16629 | 17064 | 11984 | 2045 | 0% | 22.77% | 26.91% | 27.62% | 19.39% | 3.309%
[7 empty] | Cost thru 1/31/08= |  | 76365 | -13.42% | 25.83% |  | FY2007: 59749
[7 empty] | EAC= |  | 138157
61794
Note on H2: Christopher O. Gruber: Enter L, M or H
Note on I2: Christopher O. Gruber: Enter L, M or H
Note on N78: Chris Gruber: Correlated with othere Station 2 estimates using .8 coeeficient since common problems assumed
Note on N79: Chris Gruber: Correlated with othere Station 2 estimates using .8 coeeficient since common problems assumed
Note on N80: Chris Gruber: Correlated with othere Station 2 estimates using .8 coeeficient since common problems assumed
Note on N81: Chris Gruber: Correlated with othere Station 2 estimates using .8 coeeficient since common problems assumed
Note on N82: Chris Gruber: Correlated with othere Station 2 estimates using .8 coeeficient since common problems assumed
Note on N83: Chris Gruber: Correlated with othere Station 2 estimates using .8 coeeficient since common problems assumed
Note on N84: Chris Gruber: Correlated with othere Station 2 estimates using .8 coeeficient since common problems assumed
Note on N88: Chris Gruber: Correlated with othere Station 3 estimates using .8 coeeficient since common problems assumed
Note on N89: Chris Gruber: Correlated with othere Station 3 estimates using .8 coeeficient since common problems assumed
Note on N90: Chris Gruber: Correlated with othere Station 3 estimates using .8 coeeficient since common problems assumed
Note on N92: Chris Gruber: Correlated with othere Station 5 estimates using .8 coeeficient since common problems assumed
Note on N93: Chris Gruber: Correlated with othere Station 3 estimates using .8 coeeficient since common problems assumed
Note on N94: Chris Gruber: Correlated with othere Station 3 estimates using .8 coeeficient since common problems assumed

## Schedule Ranges
NCSX Schedule Uncertainty Model
Duration Range
Schedule Activity |  |  |  | Base Duration (mos) on Critical Path | Estimate Uncertainty | Low | High | Schedule Calc | Schedule Duration | Mitigation Cost Adder | Add'l second shift available (months) | Mitigation (2nd shift) Mos Needed
CP (within 1/2 month of CP) |  | start | finish
Job -1810 Field Period Assembly Stations 1,2,3 | Station 2 MC Sub-assy A1/B1/C1 | 2008-02-01 | 2008-11-18 | 9.5673 | MH | 7.6539 | 13.3943 | 10.9324 | 10.9324 | 0
| Station 2 MC Sub-assy A3/B3/C3 | 2008-11-18 | 2009-04-13 | 4.8001 | MH | 3.8401 | 6.7201 | 5.485 | 5.485 | 0
| Station 2 MC Sub-assy A6/B6/C6 | 2009-04-13 | 2009-11-03 | 6.707 | MH | 5.3656 | 9.3898 | 7.664 | 7.664 | 0
| Station 3 Assemble Mod Coils and VVSA FP#3 | 2009-11-03 | 2010-03-24 | 4.6357 | MH | 3.7086 | 6.49 | 5.2972 | 4.6357 | 42.4772 | 2 | 0.66143
Job - 1815 Field Period Assembly Station 5 | Station 5 Final Assembly FP#3 | 2010-03-24 | 2010-08-11 | 4.6028 | LM | 3.6823 | 6.444 | 5.2596 | 4.6028 | 42.1759 | 1.5 | 0.65674
Job 7503 Final Machine Assembly (Station 6) |  | 2010-08-11 | 2011-11-11 | 15.025 | LM | 12.02 | 21.035 | 17.1688 | 15.6688 | 96.33 | 1.5 | 1.5
Job 8501 - Integrated System Testing |  | 2011-11-11 | 2011-12-13 | 1.0521 | HL | 0.99947 | 1.1573 | 1.0896 | 1.0896 | 0
|  |  | 46.3992 | 46.3901 |  | 37.2699 | 64.6305 |  | 50.0783 | 180.9831
| Estimated Cost per month for Schedule Stretch |  |  | 525 | thousand
Formulas:
start = +[finish, row above]
Note on I6: Chris Gruber: Correlated with corresponding estimate uncertainty at .9 coefficient
Note on I7: Chris Gruber: Correlated with corresponding estimate uncertainty at .9 coefficient
Note on I8: Chris Gruber: Correlated with corresponding estimate uncertainty at .9 coefficient
Note on I9: Chris Gruber: Correlated with corresponding estimate uncertainty at .9 coefficient
Note on I10: Chris Gruber: Correlated with corresponding estimate uncertainty at .9 coefficient
Note on I11: Chris Gruber: Correlated with corresponding estimate uncertainty at .9 coefficient
Note on I12: Chris Gruber: Correlated with corresponding estimate uncertainty at .9 coefficient
Note on K3: Chris Gruber: If 2md shift used to reduce schedule, this is cost for added shift - see Misc Inputs sheet

## Risk Register
[7 empty] | Likelihood: VL: P>80% L: 80%>P>40% U: 40%>P>10% VU: P<10% NC: P<1% | Consequences: Negligible: ≤$100k, ≤0.5 month Marginal: $100k-$500k, 0.5-1 month Significant: $500k-$1M, 1-3 months Critical: $1M-$5M, 3-6 months Crisis: >$5M, > 6 months
No. | Affected Jobs (absorb the impacts) | Risk Description | Mitigation Plan (& job where budgeted) | Deadline to Retire Risk or Absorb Impact | Owner | Current Status (As of February 20, 2008) | Likelihood of Occurrence | Consequences | Risk Ranking | Basis of Estimate | Cost Impact ($k) | Schedule Impact (mos) | Cost and schedule impact calculation basis |  |  | Prob of Occurrence | Cost Risk | Schedule Risk
MANAGEMENT & ORGANIZATION RISKS
Mgmt-1 |  | Loss or prolonged unavailability of certain key personnel from the project could substantially impact the schedule. | See mitigation plans for individuals listed below.
a | 1901 | Mike Cole (ORNL) Loss of "corporate memory" of stellarator core design intent, delayed turnaround on Title III issues andproblem resolution might impact FPA schedule. | Brad Nelson is been budgeted (15%) on the project. Should Cole become unavailable, Nelson would step in and handle Cole's responsibilities until a suitable longer term solution was implemented. ORNL Mgt., Job 1901 |  | Harris | Oak Ridge is investigating securing additional engineering support for Mike Cole. Currently reviewing resumes and re-evluationg work load to determine whether additional staff will indeed be needed. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. | 0 | 0.5 |  | VU | 0.055 | 0.055 | 0 | 0.0275
b | 1810 7503 | Tom Brown, Art Brooks, Bob Ellis "Back office" support for FPA and final assembly becomes a chronic bottleneck, stretching out the time required to complete assembly operations | Additional support budgeted for Brown, Brooks, and Ellis providing "2 deep" back office support. Should be available to mitigate peak demands once training in key skills is completed. Jobs 8203, 8204, 8205. Identify backup personnel for "two deep" back office support & provide duplication of critical skills needed. Eng. Mgt. (Heitzenroeder) | After first MCHP | Heitzenroeder | "Two deep" back office support is now in place. Mark Smith has worked in all areas of back office support and will provide back-up for either Tom Brown, Art Brooks, or Bob Ellis as needed to handle over-loads, cover during vacations, etc. A new analyst, Han Zhang, has recently been hired and is providing support to Art Brooks. A new design engineer, Shri Avisarala, has been hired and is expected to start soon and will be working with Tom Brown to provide additional back-up in design integration. Design support has also been significantly increased: Gerald Paluzzi is supporting Bob Ellis his on non-NCSX tasks to help balance his workload ; Tod Cruickshank is working with Fred Dahlgren and Tom Brown on NCSX structures, and Richard Upcavage is working with Tom Brown on facilities and cryostat integration. . | VU | Significant | Low | Estimated impact is <2 months on the critical path. Cost impact covers up to 2 months of FPA/final assembly. | 0 | 2 |  | VU | 0.055 | 0.055 | 0 | 0.11
c | 8202 | Phil Heitzenroeder (PPPL) | Larry Dudek can step in to assume Phil's responsibilities as Engineering Manager for Design and Procurement. Erik Perry can step into Larry's role as Construction Manager. As time goes on (and the field period assembly is completed), Mike Viola can continue (with Erik's help) with final machine assembly. | After final machine design and major procurement activities are completed. | Williams | Larry Dudek, Erik Perry and Mike Viola are already intimately involved in NCSX design and construction activities and are able to assume varying responsibilities on short notice. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0.5 |  | VU | 0.055 | 0.055 | 0 | 0.0275
d | 8101 | Ron Strykowsky | Develop a succession plan Business Ops. Dept. |  | E. Winkler | ??? | VU | Marginal | Low | Cost impact = 50% cost increment cost for 1 year spool-up time for another senior project controls person | 115 | 0 | Loaded estimated annual cost = $230k x 50% = $115k | VU | 0.055 | 0.055 | 6.325 | 0
e | 5301 5401 5501 5601 | Loss of staff with experience in specialized software delays operation of Central I&C system. | Staff have recently been brought on board in anticipation of growing NCSX I&C needs. The planned shutdown of NSTX after FY10 will increase the availability of similar resources for NCSX. | NSTX Shutdown (following FY10) | P. Sichta S. Baumgartner A. vonHalle | Staff are presently on-board and available to handle the FY08-10 work plan. More will be available following the shutdown of NSTX. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on WBS 5 cost because impacted personnel would be assigned to other activities. | 0 | 0.5 |  | VU | 0.055 | 0.055 | 0 | 0.0275
Mgmt-2 | 4501 | Loss of knowledgeable staff delays operation of legacy power supplies. | Train staff in legacy systems. Eng. Dept. | Power Systems ISTP | A. von Halle | Staff presently assigned to NSTX are available to backup the staff presently responsible for the NCSX power supply work scope | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on WBS 4 cost because impacted personnel would be assigned to other activities. | 0 | 0.5 |  | VU | 0.055 | 0.055 | 0 | 0.0275
Mgmt-3 | 8101 | Overhead rates may change significantly which in turn could impact cost and schedule | None |  | Strykowsky | Current estimates reflect latest OFES guidance. Will revisit in semi-annual EAC update. | NC | Significant | Moderate | Impact of earlier-than planned NSTX shutdown. Assumed not to ioccur (bounding assumption) | 0 | 0 |  | NC | 0.005 | 0.005 | 0 | 0
Mgmt-4 | 8101 | Labor rates may be significantly lower than projected Opportunity | None |  | Strykowsky | Current estimatesreflect latest labor rates. Will revisit in semi-annual EAC update. | U | Marginal | Moderate | Retirements / resignations replaced with younger lower-salaried staff | -1000 | 1 |  | U | 0.25 | 0.25 | -250 | 0.25
Mgmt-5 | 8101 | GPP projects not completed in time to support project needs | The crane and the HVAC systems are the main GPP projects that would need to be completed. The GPP projects have strong Lab and DOE oversight. Ample float is provided in the schedule so project delays due to GPP delays are not considered credible (P<1%). Eng. & Infrastructure Dept. | End of FY-09 | Perry | All GPP projects supporting the NCSX inhabiting the C-Site test cell are presently scheduled for completion prior to the end of FY09. | NC | Crisis | Low |  | 0 | 1 |  | NC | 0.005 | 0.005 | 0 | 0.005
Mgmt-6 | 8101 | CR may delay funding to project. | None |  | Strykowsky | Current estimates reflect latest OFES guidance. Will revisit in semi-annual EAC update. | U | Significant | Moderate | Expected increase in FY-09 may be delayed by CR. | 0 | 2 |  | U | 0.25 | 0.25 | 0 | 0.5
TECHNICAL RISK - Generic Assembly Risks
Assy-1 | 1810 | Station 3: cost and schedule grows when Assembly Sequence Plan fully matures | Expedite Tooling Design and Assembly Sequence Plan Jobs 1803 / 8203 | When Station 3 Tooling FDR is complete | Brown |  | VL |  |  | 15% increase in time required for each F.P | 250 | 0.675 | Station 3 estimate of $1,579k x 15% plus schedule stretchout for the time station 3 is on the c.p (4.5mo x 15% (stretchout cost quantified and added separately) | VL | 0.9 | 0.9 | 225 | 0.6075
Assy-2 | 1815 | Station 5: cost and schedule grows when Assembly Sequence Plan fully matures | Expedite Component Designs and Assembly Sequence Plan Jobs 1354, 1501, 1601, 8203 | Coil services PDRs | Brown |  | VL |  |  | 25% increase in time required for each F.P | 500 | 1.125 | Station 5 estimate of $1889k x 25% plus schedule stretchout for the time station 5 is on the c.p (4.5mo x 25% (stretchout cost quantified and added separately) | VL | 0.9 | 0.9 | 450 | 1.0125
Assy-3 | 7503 | Station 6: cost and schedule grows when Assembly Sequence Plan fully matures | Expedite Component Designs, Plant Layout, and Assembly Sequence Plan Jobs 1701, 1702, 1803, 8215 | Cryostat PDR | Brown |  | VL |  |  | 15% increase in time required. | 650 | 2.175 | Station 6 estimate of $4,317k x 15%. plus schedule stretchout for the time station 6 is on the c.p (14.5mo x 15% (stretchout cost quantified and added separately) | VL | 0.9 | 0.9 | 585 | 1.9575
Assy-4 | 1810/ 1815 7503 | Photogrammetry replaces laser tracker for some operations and saves time and money. (Opportunity) | Acquire equipment, develop experience, assess potential. New H/W in place & personnel being trained. 1810 / 1815 | ~Sept., 2008 | Dodson / Dudek |  | L |  |  | 33% reduction in metrology tasks? | -900 | -3 | 50% reduction in metrology crew labor cost =$2,729k x 50% . Reduction of metrology dependent tasks on the c.p. =172 days x .5 = 86 dyas = 4 months. (stretchout cost quantified and added separately) | L | 0.6 | 0.6 | -540 | -1.8
Assy-5 | 1810/ 1815 7503 | Assembly delayed due to metrology equipment breakdowns or anomalies. | Maintain high availability via maintenance contracts, spares, and trained staff. F&OM Div. | Completion of FP#1, Station 5 | Priniski / Dudek | Have acquired new hardware and trained staff. | L |  |  | 2 occurrences @ 0.5 month each. | 0 | 1 | (stretchout cost quantified and added separately) | L | 0.6 | 0.6 | 0 | 0.6
Assy-6 | 1810 1815 7503 | General purpose tooling/ lifting equipment (e.g. cranes) not available to support the schedule. | Budget lift equipment in FPA . Jobs 1810, 1815 | After Station 5? | Dudek | Lift equipment estimated in 1810 & 1815 WAF. | U | Significant | High | Up to 2 week impact on FPA and critical path. | 0 | 0.5 | (stretchout cost quantified and added separately) | U | 0.25 | 0.25 | 0 | 0.125
TECHNICAL RISKS - Station 2 Assembly
Stat2-2 | 1810 | Station 2: Unacceptable distortion in a field period when welding modular coil shims requiring rework and or chair installation. Risk has been reduced by mitigation (design and process changes) | Perform extensive welding R&D and careful monitoring during welding. Develop suitable weld procedures and train welders to minimize likelihood of unacceptable distortion. Job 1810 | After first MCHP | Viola | See response to RR #5. Current weld trials dealing with options to control distortion. | U | Marginal | Low | Cut apart and re-weld two coils back together. Nominally a 2.5-man crew in 12 weeks. Fabrication and installation of chair nominally requires 2.5-man crew and ~3 weeks. | 150 | 1 | Updated. | U | 0.25 | 0.25 | 37.5 | 0.25
Stat2-3 | 1810 | Station 2. Unacceptable distortion in a field period when welding modular coil shims requiring complete disassembly and redesign and reassembly Risk is mitigated in the estimate. | Perform extensive welding R&D and careful monitoring during welding. Develop suitable weld procedures and train welders to minimize likelihood of unacceptable distortion. Job 1810 | After first MCHP | Viola | Weld trials should mitigate probability of occurance. | VU | Marginal | Low | Cut apart and re-weld two coils back together. Nominally a 2.5-man crew in 12 weeks. | 150 | 3 |  | VU | 0.055 | 0.055 | 8.25 | 0.165
Stat2-14 | 1810 | Station 2. Risk of loss of weld equipment or trained personnel. | Procure more equipment & qualify more staff | After first MCHP | Viola |  | NC | Negligible | Low |  |  |  |  | NC | 0.005 | 0.005 | 0 | 0
Stat2-5 | 1810 | Station 2. Shim sets not adequate or fail - need to fabricate more shims and measure and test | Change to G10 design and fabricate more shims than needed Job 1810 | After first MCHP | Viola | Switched to G10 design | U | Marginal | Low | Up to 3 week impact on FPA and critical path. |  | 1 |  | U | 0.25 | 0.25 | 0 | 0.25
Stat2-7 | 1810 | Station 2 - shim bag rupture & requires replacement | Pre-qulaify shim bags. Use wing chair in compression. Could require taking coil apart in worse case. Job 1810 | After first MCHP | Viola | Considered unlikely due to other mitigation plan options. | VU | Significant | Low | Rough assessment of cost and schedule impact of disassembling/re-assembling coils. 5 techs. X 3 months | 200 | 3 |  | VU | 0.055 | 0.055 | 11 | 0.165
Stat2-9 | 1810 | Station 2. Nose opens up while tightening outboard bolts | Change bolt tightening sequence Job 1810 | After first MCHP | Viola | ??? | U | Marginal | Low | Up to 2 week impact on FPA and critical path. |  | 0.5 |  | U | 0.25 | 0.25 | 0 | 0.125
Stat2-10 | 1810 | Station 2. Nose opens up while tightening outboard bolts. Change bolt tightening sequence is not adequate | Reexamine alignment criteria and potential impact Job 1810 | After first MCHP | Viola | ??? | U | Marginal | Low | Up to 4 week impact on FPA and critical path. |  | 1 |  | U | 0.25 | 0.25 | 0 | 0.25
Stat2-13 | 1810 | Station 2. Modular coil damaged during assembly requiring significant rework to coil. (Complete coil re-fabrication excluded) | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood. Include provisions to guard against coil damage in FPA procedures. Job 1810 | After Station 2 | Viola | Station 2 assembly has just started. Repeated trial fits have served to benchmark processes. The impacts consider the "worse case" scenario of when and what coils we damage - cost impact of this "worse case" in addition to the Mod Coil impact is ~$200K and up to 7 mos. | L | Negligible | Low | Nominally repaired with a 2-man crew within 2 weeks. Cost: 3-4 occurrence. No schedule impact | 50 |  | Change??? | L | 0.6 | 0.6 | 30 | 0
Stat2-15 | 1810 | Station 2. Modular coil damage requiring coil re-fabrication. | Extreme care will be taken when transporting and handling coils. Develop and follow appropriate procedures. Job 1810 | After Station 2 | Viola |  | NC | Crisis | Low | High impact-low probability event not covered by contingency |  |  |  | NC | 0.005 | 0.005 | 0 | 0
TECHNCIAL RISKS - Station 3 Assembly
Stat3-1 | 1810 | Station 3: vertical weld distortion excessive. Have to take apart, modify design or procedure, re-weld. | Perform vertical welding R&D and careful monitoring during welding. Develop suitable weld procedures and train welders to minimize likelihood of unacceptable distortion. Refine welding capabilites on Station 2. Job 1810 | After first A-A weld | Viola |  | L |  |  | 5 techs x 1 month | 100 | 1 |  | L | 0.6 | 0.6 | 60 | 0.6
Stat3-2 | 1810 | Station 3. Problems installing coils over vacuum vessel. Trajectory following scheme does not work like the concrete block. Have to re-invent. | R&D has been performed. Check in advance with trial dry fit. 1810 | After first MC-to-VV assembly | Viola |  | VU |  |  | 5 techs x .5 month | 50 | 0.5 |  | VU | 0.055 | 0.055 | 2.75 | 0.0275
Stat3-3 | 1810 | Station 3. VV surface component (coolant tube, flux loop, or TC) damaged during FPA requiring significant rework. (Note: There is only 0.2" of clearance currently projected.) | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood. Include provisions to guard against coil damage in FPA procedures. Job 1810 | After Station 3 | Viola |  | VU | Negligible | Low | Nominally repaired with a 2-man crew within 2 weeks | 20 | 0.5 | Updated. | VU | 0.055 | 0.055 | 1.1 | 0.0275
Stat3-4 | 1810 | Station 3. Interferences discovered during assembly; components don’t go together as planned. Assemblies have to be taken apart, components moved or re-worked, re-assembled. | CAD modeling with as-built dimensions to find interferences off critical path. Do simulations carefully Job 1901 & 8203 | After first MCHP assembled over VV | Cole |  | U |  |  | 0.5 months on C.P. |  | 0.5 |  | U | 0.25 | 0.25 | 0 | 0.125
Stat3-5 | 1810 | Station 3. Sag distortion while MCHP are vertical in station 3 | Our models have predicted acceptable amounts. Careful modeling contineus. Job 1810 | After first MC-to-VV assembly | Viola |  | U | Marginal | Low | Fabricate and install bracing. Nominally a 2.5-man crew in 2 weeks. Up to 4 week impact on FPA and critical path. | 25 | 1 |  | U | 0.25 | 0.25 | 6.25 | 0.25
Stat3-6 | 1810 | Station 3. Assembly tooling allows too much deflection and has to be redesigned. | Exercise tooling off the critical path. Compensated by design, metrology, exercise tooling & follow demonstrated procedures Assy stesp allow for this. Demonstrated in Station 2 Job 1810 | By start of Station 3 | Viola |  | VU |  |  | Rough assessment of cost and schedule impact of reinforcing or redesigning tooling. | 50 | 1 |  | VU | 0.055 | 0.055 | 2.75 | 0.055
TECHNICAL RISKS - Station 5 Assembly
Stat5-1 | 1815 | Station 5: Trim coils not available when needed in field period assembly sequence. Have to implement workaround. | Expedite design and procurement. Risk has been reduced via design choices (e.g. eliminate Port 12's). Retro-fit is possible. Jobs 1354 | When 10% of coils are wound. | Kalish |  | U |  |  | 2 weeks on CP |  | 0.5 |  | U | 0.25 | 0.25 | 0 | 0.125
Stat5-2 | 1815 | Station 5. TF Coils cannot be aligned | Reexamine alignment criteria and potential impact. Job 1810 | By start of Station 5 | Viola | ??? | U | Marginal | Low | Up to 4 week impact on FPA and critical path. |  | 1 |  | U | 0.25 | 0.25 | 0 | 0.25
Stat5-3 | 1815 | Station 5. TF coils become warped and have to be racked to restore proper geometry. | Measure a sampling of coils to assess need for racking. Add hard points on the coils- Jim C. WBS 13 | After measuring 2 coils. | Kalish | ???? | U |  |  | 2 weeks on CP & some retrofit of clamsp. Have to do some re-design of clamps. Maybe 4 wweks of Fred & designer + hardware | 60 | 0.5 |  | U | 0.25 | 0.25 | 15 | 0.125
Stat5-4 | 1815 | Station 5. PF & TF coil supports may have to change after FDRs to accommodate interfacing systems. | Push design integration of TF, PF, coil structures, coil services, & cryostat to resolve interfaes ASAP. Delay FDRs until integration adequately mature Job 8203 | Cryostat CDR | Brown |  | NC | [6 empty] | NC | 0.005 | 0.005 | 0 | 0
Stat5-8 | 1815 | Station 5. Problems installing ports due to interferences. Have to move components or modify ports. | CAD modeling with as-built dimensions to find interferences off critical path. Job 1901 | By start of Station 5 | Cole |  | L |  |  | Cost, not schedule 4 techs. X 2 weeks x 10 occurrences | 250 |  |  | L | 0.6 | 0.6 | 150 | 0
Stat5-9 | 1815 | Station 5. Interferences discovered during assembly; components don’t go together as planned. Assemblies have to be taken apart, components moved or re-worked, re-assembled. | Design integration during Title I & II design of components. Job 8203 | Coil Services PDRs | Brown |  | VU |  |  | Trim coil - port interferencese are biggest concer. Leads are a concern too?? 4 techs. X 2 weeks X 1 occurrence | 30 |  |  | VU | 0.055 | 0.055 | 1.65 | 0
Stat5-10 | 1815 | Station 5: Multiple vacuum leaks during initial pumpdown | Welds will be leak checked during FPA when leaks can be addressed without significantly impacting the critical path. Job 1810 | After leak check of first FP. | Viola |  | L | Marginal | Low | Impact of having only a few leaks is covered in estimate uncertainty with present mitigation plan | 25 |  |  | L | 0.6 | 0.6 | 15 | 0
Stat5-11 | 1815 7503 | Station 5. Rework/replacement of high permeability components Risk is mitigated in the estimate. | Expedite design & procurement of at-risk parts. Dudek | Coil structures FDR | Dahlgren | Assessing impact of annealing and machining on permeability | U | Marginal | Moderate | Initial impact assessment based on VVSA experience | 200 | 0 |  | U | 0.25 | 0.25 | 50 | 0
Stat5-12 | 1815 | Station 5. Field period damaged during loading, transport, or unloading from TFTR TC to NCSX TC | Extreme care will be taken when transporting a field period. Additional reviews including external reviewers will be performed. Develop appropriate procedures for transporting field periods. Arrange for a peer review of the procedures prior to transport. Will replace rollup door in CS test cell. Job 1815 | After first FP. | Viola |  | NC | Crisis | Low | High impact-low probability event not covered by contingency |  |  |  | NC | 0.005 | 0.005 | 0 | 0
TECHNICAL RISKS - Station 6 Assembly
Stat6-2 | 7503 | Station 6. Original base structure vendor(s) unable to deliver on schedule; not available when needed in machine assembly sequence. Have to implement workaround. | Alternate vendors exist & sufficient float exists to engage an alternate vendor. We procure components and assemble on site. Job 1702 | Coil structures FDR | Dahlgren | Still in design phase - future risk | VU | Marginal | Low | Base supports must be in place prior to the 3-periord machine assembly | 50 |  |  | VU | 0.055 | 0.055 | 2.75 | 0
Stat6-3 | 7503 | Station 6. PF 5L & 6L not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Could put FP#1 inplace if we had to. Could absorb 4 months delay Jobs 1302/1352 | When 1st coil is wound. | Chrzanowski |  | NC |  |  | Would impact CP. PF coils have ample float |  |  |  | NC | 0.005 | 0.005 | 0 | 0
Stat6-4 | 7503 | Station 6. PF coils out of round or not flat. Supports have to be modified. | Include adjustment provisions in coil structure designs. This is being done Job 1501 | Coil structures FDR | Dahlgren |  | NC |  |  | Addressed in base estimate |  |  |  | NC | 0.005 | 0.005 | 0 | 0
Stat6-5 | 7503 | Station 6. PF 4L, 4U, 5U, 6U not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Jobs 1302/1352 | When 1st PF is wound. | Chrzanowski |  | NC |  |  | Would impact CP day for day, but PF coils have ample float |  |  |  | NC | 0.005 | 0.005 | 0 | 0
Stat6-6 | 7503 | Station 6: Trim coils not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Risk has been reduced via design choices (e.g. eliminate Port 12's). Retro-fit is possible. Jobs 1354 | When 10% of coils are wound. | Kalish |  | NC |  |  | Would impact CP day for day, but risk mitigted by design and float. |  |  |  | NC | 0.005 | 0.005 | 0 | 0
Stat6-7 | 7503 | Station 6: Leads not available when needed in machine assembly sequence. Have to implement workaround. | Expedite design and procurement. Jobs 1601 | Electrical leads FDR | Goranson |  | NC |  |  | Would impact CP day for day, but risk mitigted by design and float. |  |  |  | NC | 0.005 | 0.005 | 0 | 0
Stat6-8 | 7503 | Station 6. High temperature Rogowski Loop damaged during installation resulting in loss of toroidal current measurement capability | Triple redundancy - 3 installed but only 1 required. Job 3101 | Rogowski loop FDR | Stratton | Starting installation in Feb 2008 | VU | Marginal | Low |  | 0 |  |  | VU | 0.055 | 0.055 | 0 | 0
Stat6-9 | 7503 | Station 6. Interferences discovered during assembly; components don’t go together as planned. Assemblies have to be taken apart, components moved or re-worked, re-assembled. | CAD modeling with as-built dimensions to find interferences off critical path. A Pro E model/sterolithography of the three period assemblies and mechanisum for positioning the FPA will be fabricated to evaluate the assembly of the coils. Job 1901 / 8203 | By start of Station 6 | Cole |  | L |  |  | 1 month on C.P. 4 techs x 1 mont | 50 | 1 |  | L | 0.6 | 0.6 | 30 | 0.6
Stat6-10 | 7503 | Station 6. Problems making up vacuum vessel field joint. Have to re-machine spool piece. | Careful metrology in FPA, back office analysis and CAD modeling. Job 8202 (Eng. Mgr.) | After first VV joint successfully made up. | Perry |  | U |  |  | 3 joints @ 1 month C.P. each |  | 3 |  | U | 0.25 | 0.25 | 0 | 0.75
Stat6-11 | 7503 | Station 6. Retainer and pucks do not stay on flange during assembly and moving of half field periods. Potential safety risk if individuals are under the machine. | Pucks will be held in place by Nomex felt and is being demonstrated to show feasiblity. Stud assembly sequence will be developed in model studies Job 1901 | By start of Station 6 | Cole | [11 empty] | 0 | 0
Stat6-12 | 7503 | Station 6. Problems making up C-C joint. Interferences, bolt access problems. | A Pro E model/sterolithography of the three period assemblies and mechanisum for positioning the FPA will be fabricated to evaluate the assembly of the coils. Also CAD modeling Job 1901 / 8203 | By start of Station 6 | Cole |  | U |  |  | Risk is mitigated in the estimate |  |  |  | U | 0.25 | 0.25 | 0 | 0
Stat6-13 | 7503 | Station 6. Pourable insulation installation problemss; can’t get what we need, don’t know if it fills all the voids, leaks out all over the place; have to invent methods to ensure complete fill and seal. | Perform R&D. Design special tooling for installation and verification. Job 7503 & 1901 | At least 1 year before start of Station 6 | Cole |  | U |  |  | Risk is mitigated in the estimate |  |  |  | U | 0.25 | 0.25 | 0 | 0
Stat6-14 | 7503 | Station 6. Modular coils are shorted across toroidal break between field periods causing problematic field errors | Ensure that required electrical breaks are not compromised. Check carefully during assembly. Job 1810, 1815, 7503 |  | Viola (FPA) Perry (MA) | Future risk - N/A | NC | Crisis | Low |  |  |  |  | NC | 0.005 | 0.005 | 0 | 0
Stat6-15 | 7503 | Station 6. Assembly sled for final assembly is not adequately stiff or does not provide repeatable motion | Functionality of sled will be determined with first FP. Ample time to make design modifications between arrival of the first and third FPs. Job 7503 | By start of Station 6 | Perry | Future risk - N/A | U | Negligible | Low | Nominal cost impact is 1 man-month of engineering design and up to half the fabrication cost of the sled | 75 | 0 |  | U | 0.25 | 0.25 | 18.75 | 0
Stat6-16 | 7503 | Station 6. Vacuum leaks occur. Takes time to locate and repair. | Leak check each field period independently in FPA. Job 1815 | After final VV weld | Perry |  | U |  |  | Risk is mitigated in the estimate |  |  |  | U | 0.25 | 0.25 | 0 | 0
Stat6-17 Added by Erik 2/28/2008 | 7503 | Welding of the Vacuum Vessel pieces to the spool pieces may require the addition of thin Inconel plates to bridge gaps caused by radial and/or angular out-of-tolerance consditions of either the VV or spool pieces. Risk is mitiagated in the estimate | Add Inconel plates to extend the vessel flange if radial out- of-tolerance and add flange plates ti soiil pieces and tehn bridge to vessel flange extension if angular out-of-tolerance. |  | Perry |  | VU |  |  |  | 50 | 4 |  | VU | 0.055 | 0.055 | 2.75 | 0.22
Stat6-18 | 7503 | Friction shims in sizes needed for C-C joint not avaialble when needed. | Qualify sources for alumina shims; investigate use of G10 shims in some locations. Make measurements after Station 3 to determine needed thicknesses. | After Station 3 | Dudek |  | VU |  |  | 6 weeks on CP |  | 1.5 |  | VU | 0.055 | 0.055 | 0 | 0.0825
TECHNICAL RISKS - Startup
S/U-1 | 8501 | Unanticipated problems with cryostat penetrations (icing, excessive condensation). May require warming up the stellarator core to effect repair with consequent impacts to critical path activities. | Careful cryostat design, including consultation with experts and R&D. Job 1701 | Cryostat FDR | Raftopoulos | Future risk - N/A | U | Marginal | Low | Nominally repaired with a 4-man crew in 1 week with 3 weeks for warmup/cooldown (if required) | 30 | 1 |  | U | 0.25 | 0.25 | 7.5 | 0.25
S/U-2 | 8501 | Coil cooling system fails to cool coil structure down to cryogenic temperature | Analyze coil thermal and heat transfer properties. (Jobs 14, 13) Perform R&D on cryogenic cooling system (Job 6201) | Cryostat PDR | Raftopoulos | [11 empty] | 0 | 0
S/U-3 | 8501 | Insulation on modular coil fails during initial cooldown and testing requiring in situ repair. | C1 tested at full current at cryogenic temperature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Job 1421 In addition, routine field tests will be performed on each assembly station to ensure that the electrical integrity is OK. Job 1810 | After Station 3 | Chrzanowski (MC) Viola (FPA) M. Viola & E. Perry - implement mitigation plan during field period and final assembly. | Future risk - N/A | VU | Marginal | Low | Insulation fault in lead area is considered the most likely failure scenario. Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellarator core. 3 techs/1 engr for duration of active repair )1-2 months). | 150 | 2 |  | VU | 0.055 | 0.055 | 8.25 | 0.11
S/U-4 | 8501 | Insulation on modular coil fails during initial cooldown and testing requiring stellarator core disassembly | C1 tested at full current at cryogenic temperature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Job 1421 In addition, routine field tests will be performed on each assembly station to ensure that the electrical integrity is OK. Job 1810 | After Station 3 | Chrzanowski (MC) Viola (FPA) M. Viola & E. Perry - implement mitigation plan during field period and final assembly. | 16 of 18 coils successfully wound. Remaining 2 coils in winding process. | NC | Crisis | Low | High impact-low probability event not covered by contingency |  |  |  | NC | 0.005 | 0.005 | 0 | 0
S/U-5 | 7503 1352 1361 8501 | Insulation on TF/PF coil fails during initial cooldown and testing requiring in situ repair | 1st of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . Job 1361 Job 1352 | After 1st PF Coil | Kalish (TF) Chrzanowski (PF) M. Viola & E. Perry - implement mitigation plan during field period and final assembly. | Mitgation plan being implemented during TF fab. There was an issue with TF Coil #3, but this has now been resolved. 6 TF coils shipped and/or received. | VU | Marginal | Low | Insulation fault in lead area is considered the most likely failure scenario. Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellarator core. 3 techs/1 engr for duration of active repair )1-2 months). | 150 | 2 |  | VU | 0.055 | 0.055 | 8.25 | 0.11
S/U-6 | 7503 1352 1361 8501 | Insulation on TF/PF coil fails during initial cooldown and testing requiring dismantling stellarator core | 1st of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . Job 1361 Job 1352 | After 1st PF Coil | Kalish (TF) Chrzanowski (PF) M. Viola & E. Perry - implement mitigation plan during field period and final assembly. | Mitgation plan being implemented during TF fab. There was an issue with TF Coil #3, but this has now been resolved. 6 TF coils shipped and/or received. | NC | Crisis | Low | High impact-low probability event not covered by contingency |  |  |  | NC | 0.005 | 0.005 | 0 | 0
S/U-7 | 8501 | Coils are hooked up with incorrect polarity | Ensure that coils are connected with correct polarity during final assembly by specifying testing in the assembly procedure. Job 7503 Test during ISTP and fix if necessary. Job 8501 |  | Perry | Future risk - N/A | NC | Negligible | Low | Covered in estimate uncertainty with present mitigation plan |  |  |  | NC | 0.005 | 0.005 | 0 | 0
S/U-8 | 8501 | Ground faults delay coil testing. | Machine Techs will be trained to search out / identify and correct ground faults. Implement ground fault detection system before other systems are installed in test cell. WBS 4401 | Start of installation | Ramakrishnan | Allowances made in current S/U plans | VL | Negligible | Moderate | Experience on NSTX S/U | 10 | 0.3 |  | VL | 0.9 | 0.9 | 9 | 0.27
S/U-9 | 8501 | Loop faults delay coil testing. | Machine Techs will be trained to search out / identify and correct ground faults. Implement ground fault detection system before other systems are installed in test cell. WBS 4401 | Start of installation | Ramakrishnan | Allowances made in current S/U plans | L | Negligible | Moderate | Experience on NSTX S/U | 10 | 0.3 |  | L | 0.6 | 0.6 | 6 | 0.18
S/U-10 | 8501 | Control System problems delay testing | During the development of the ISTP specific ( first plasma ) waveforms will be tested to ensure that they will work. WBS 5 | Start of installation | Sichta | Allowances made in current S/U plans | L | Negligible | Moderate | Experience on NSTX S/U | 10 | 0.3 |  | L | 0.6 | 0.6 | 6 | 0.18
S/U-11 | 8501 | Loss of a key component or system delays testing - e.g., pump failure | Comprehensive PTP's will be conducted prior to implementing the ISTP. WBS 1-6 | Start of installation | Gentile | Allowances made in current S/U plans - replace pumps => suspend S/U unitl replaced/repaired. | U | Negligible | Low | Experience on NSTX S/U | 50 | 0.5 |  | U | 0.25 | 0.25 | 12.5 | 0.125
S/U-12 | 8501 | Islands detected in e-beam mapping require troubleshooting and repair; delay CD-4. | Control sources of field error and maintain inventory. WBS 8204 | Completion of e-beam mapping | Brooks | Allowances made in current S/U plans - if islands deemed to be unacceptable, would have to adjust coils. | NC |  | Moderate | Experience on NSTX S/U Excluded as Bounding Assumption. | 0 | 0 |  | NC | 0.005 | 0.005 | 0 | 0
S/U-13 | 8501 | Loss of a key component or system delays testing - e.g., turn to turn failure | Comprehensive PTP's will be conducted prior to implementing the ISTP. WBS 1-6 | Start of installation | Gentile | Allowances made in current S/U plans | VU | Critical | Moderate | Experience on NSTX S/U Excluded as Bounting Assumption | 0 | 0 |  | VU | 0.055 | 0.055 | 0 | 0
S/U-14 | 3801 | E-beam mapping diagnostic is not installed and ready for use during start-up. Risk is possibly complex and challenging interface of hardware borrowed from Auburn University. | Start design of needed hardware early. | Completion of installation | Stratton | Work has not yet started on job 3801. Start of work should be brought forward to January 2009. | VU | Marginal | Moderate | Experience on NSTX S/U Mitigated by bringing the work forward. | 50 | 3 |  | VU | 0.055 | 0.055 | 2.75 | 0.165
S/U-15 | 1810 7503 | Station 2. Bolt preload could relax with time. Mostly an operations risk. | Will instrument some (~12?) bolts. Doing bolt tests with G10 shims. Retighten bolts/check periodically to verify that preload is okay. Job 1901 | After Station 5 | Viola | ???? | VU | [6 empty] | VU | 0.055 | 0.055 | 0 | 0
TECHNICAL RISKS - Components & Systems
Sys-1 | 1352 | No suitable PF coil vendor submits bid. PF coils need to be built in-house. | Issue sources sought advertisement. Job 1352 | After PF proposals received. | Chrzanowski | Future risk - N/A | U | Marginal | Low | Cost impact estimated to be up to $300k (1/3 of fabrication costs) for potentially higher labor rates at PPPL. No impact on critical path expected. | 770 | 0 |  | U | 0.25 | 0.25 | 192.5 | 0
Sys-2 | 1352 | PF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil will be procured in advance and available to wind a new coil if required. Job 1352 Float in schedule appears adequate to avoid critical path impact. | Completion of Last Coil | Chrzanowski | Future risk - N/A | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 35 | 0 |  | VU | 0.055 | 0.055 | 1.925 | 0
Sys-3 | 1361 | TF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil already procured. Ample float in schedule to avoid critical path impact. No additional action required Job 1361 | Completion of Coil #18 | Kalish | Quality improving - production mode established. | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 35 | 0 |  | VU | 0.055 | 0.055 | 1.925 | 0
Sys-4 | 1451 | Failure of major piece of winding equipment (e.g., motor, gear box, etc.) resulting in extended downtime in a winding station | Use three remaining winding stations to continue MC fabrication while fourth station is being repaired. Job 1451 | Retired? | Chrzanowski | Future risk, has not occurred yet - N/A. Only 2 coils left. Redundant winding tooling mages this risk negligible. | U | Negligible | Low | ~$10K for equipment plus repair costs | 30 | 0 |  | U | 0.25 | 0.25 | 7.5 | 0
Sys-5 | 1451 | Damage or loss of modular coil during VPI or testing requiring the conductor to be stripped off and re-wound Risk nearly retired. VPI'd 16 of 18. Exclude as bounding assumption. | Continue to use same rigorous process used for first 14 coils during which there were no fabrication mishaps requiring re-winding a coil. Job 1451 | After last coil complete. | Chrzanowski | 16 of 18 coils successfully wound.Remaining 2 coils in winding process. | NC | Significant | Moderate | ~$35K in materials; ~$380K in labor. 7.5 months to do work with the potential for a 2 month impact on the critical path. | 0 | 0 |  | NC | 0.005 | 0.005 | 0 | 0
Sys-6 | 1701 | Additional thermal analysis may be required to establish limits on temperature differences for cooldown. | Budget an approximate amount for thermal analysis support in WBS 82. Perform detailed evaluation of analysis needs to see if more is needed. Job 8204. | Cryostat PDR | Raftopoulos | [11 empty] | 0 | 0
Sys-7 | 2201 | Legacy vacuum pumps unexpectedly require modifications or additional protection as a result of failure modes analysis. | Complete failure modes analysis and/or testing. WBS 2101 | Vacuum pumping system | Blanchard | [11 empty] | 0 | 0
Sys-8 | 4301 | Legacy power supplies unexpectedly require modifications or additional protection as a result of failure modes analysis. | Complete failure modes analysis and/or testing. WBS 4401 | Power Systems PDR | Ramakrishnan | [11 empty] | 0 | 0
Sys-9 | 4401 | Coil protection system costs grow when requirements fully mature. | Establish requirements Job 4401. | Power Systems PDR | Ramakrishnan | [11 empty] | 0 | 0
Sys-10 New PG | 1260 | NB Transition duct design is vintage and revisit could result in criteria changes, i.e. diagnostic requirements, number of ports, NB alignment, further design review, etc. | Schedule was made more aggressive with early start to assure ageement with design. | ??? | Goranson |  | U |  |  | Engineering hours to redo models and hold design review. Not on CP | 60 | 0 |  | U | 0.25 | 0.25 | 15 | 0
Sys-11 New PG | 1601-161 | Change in scope, i.e. addition of cooling to trim coils. | Add one more designer for short term. | ??? | Goranson |  | VL |  |  | Increase proportional to increase in number of circuits. | 30 | 0 |  | VL | 0.9 | 0.9 | 27 | 0
Sys-12 New PG | 1601-162 | Design of cables not firmly established, satisfying field error requirements could require more costly solutions and longer lead time. | Moving preliminary design into FY08 to give more lead time. | ??? | Goranson |  | L |  |  | Increased time for Engineering study of alternate configurations. Not on CP | 60 | 0 |  | L | 0.6 | 0.6 | 36 | 0
Sys-13 Transferred from Mgmt Section | 15xx | Escalation of Stainless Sheet and Inconel higher than base escalation rates. | None | After structure materials procured. | Dahlgren | Current estimates have "best" info on SS and Inconel prices. Will revisit in semi-annual EAC update. | VL | Marginal | Moderate | See separate sheet - assume 3% to 20% higher per year escalation rate | 500 | 0 | total cost of statinless components assuming 50% of which is material cost x 20% per year escalation rate. (see conr=tingency model tab esclation) | VL | 0.9 | 0.9 | 450 | 0
Sys-14 Transferred from Mgmt Section | 13xx, 4, et al. | Escalation of Copper higher than base escalation rates | None | After all conductor procured. |  | Current estimates have "best" info on Cu prices. Will revisit in semi-annual EAC update. | VL | Negligible | Low | See separate sheet - assume 5% to 20% higher per year escalation rate | 225 | 0 | total cost of copper components assuming 50% of which is material cost x 20% per year escalation rate. (see conr=tingency model tab esclation) | VL | 0.9 | 0.9 | 202.5 | 0
Sys-15 Transferred from Assy Section | 1354 | Trim coil performance requirements might have to increase to compensate for grater-than-expected assembly errors. | Design trim coil structures with adequate margin in case currents have to be increased by factor 2. | After first MCHP, implement mitigation plan if indicated by MCHP results. Job 1810 | Viola |  | U | Significant | Moderate | Phil, estimate impact. |  |  |  | U | 0.25 | 0.25 | 0 | 0
[17 empty] | 1916.425 | 9.31

## Data
Percentiles | Total ETC With Uncertainty Contingency | Cost Risk | Schedule Risk | Schedule Mitigation Cost Adder | Total Schedule Duration
0% | 63315.7041 | -1230 | 0.275 | 0 | 42.4468
5% | 66093.8539 | 585 | 4.375 | 26.2984 | 45.3445
10% | 66613.9984 | 840 | 5.375 | 53.9647 | 46.2389
15% | 66983.5368 | 1050 | 5.9 | 77.3386 | 46.9068
20% | 67285.1429 | 1235 | 6.575 | 96.33 | 47.5113
25% | 67550.2861 | 1405 | 7.075 | 98.731 | 48.0591
30% | 67786.2125 | 1520 | 7.45 | 109.0342 | 48.5789
35% | 67992.8507 | 1620 | 7.875 | 118.8966 | 49.0566
40% | 68185.9345 | 1705 | 8.275 | 128.44 | 49.5936
45% | 68387.4068 | 1785 | 8.725 | 137.9303 | 50.1118
50% | 68584.0733 | 1875 | 9.075 | 147.3462 | 50.6279
55% | 68781.8689 | 1960 | 9.575 | 157.4959 | 51.1637
60% | 68989.6792 | 2080 | 9.9 | 167.6679 | 51.6931
65% | 69221.4278 | 2230 | 10.375 | 178.9907 | 52.2607
70% | 69466.1053 | 2390 | 10.875 | 190.4554 | 52.8461
75% | 69731.2991 | 2520 | 11.375 | 198.0204 | 53.4655
80% | 70007.3017 | 2630 | 11.975 | 210.5249 | 54.1934
85% | 70354.0635 | 2740 | 12.575 | 224.77 | 55.0147
90% | 70788.5916 | 2875 | 13.575 | 239.9569 | 56.137
95% | 71424.5317 | 3200 | 14.875 | 268.0634 | 57.7605
100% | 76106.9212 | 4265 | 22.4 | 321.1 | 65.2282
Sensitivity: Total ETC With Uncertainty Contingency
Assumptions | ContributionToVariance | RankCorrelation
* Job 7503 Total | 24.27% | 0.54804
7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 10.9% | 0.36717
Estimating Process Uncertainty | 10.29% | 0.35688
8203 - Job: 8203 - Design Integration-BROWN | 4.18% | 0.22742
* S2H6 - Station 2 MC subassy A6B6C6 | 3.711% | 0.21429
* S2H2 - Station 2 MC subassy A2B2C2 | 3.648% | 0.21247
* S2H1 - Station 2 MC subassy A1B1C1 | 3.567% | 0.2101
* S2H4 - Station 2 MC subassy A4B4C4 | 3.508% | 0.20834
* S2H5 - Station 2 MC subassy A5B5C5 | 3.423% | 0.20582
* S2H3 - Station 2 MC subassy A3B3C3 | 3.276% | 0.20133
1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | 3.104% | 0.19599
7501 - Job: 7501 - Construction Support Crew-PERRY | 2.538% | 0.1772
* S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | 2.187% | 0.16451
* S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | 2.175% | 0.16405
* S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 2.114% | 0.16175
* S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | 2.012% | 0.1578
* S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | 1.996% | 0.15716
* S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | 1.782% | 0.14851
8101 - Job: 8101 - Project Management &Control-ANDERSON | 1.376% | 0.13048
Other | 9.942%
Sensitivity: Cost Risk
Assumptions | ContributionToVariance | RankCorrelation
Assy-4 | 31.82% | -0.55494
Mgmt-4 | 29.12% | -0.53087
Sys-1 | 16.66% | 0.40153
Assy-3 | 6.061% | 0.24219
Assy-2 | 3.399% | 0.18136
Sys-13 | 3.296% | 0.1786
Stat5-8 | 2.288% | 0.1488
Stat5-11 | 1.469% | 0.11924
Assy-1 | 1.046% | 0.10059
Other | 4.839%

## Likelihood
| Probability of Occurrence |  | Criteria
| Qualitative | Quantitative
| Non-credible | <0.01 | Extremely unlikely occur anytime in the project life cycle, or the probability of the occurrence judged to be less than 1%.
VU | Very Unlikely | >0.01 but <0.1 | Very unlikely to occur anytime in the project life cycle, or the probability of the occurrence is judged to be less than 10%.
U | Unlikely | >0.1 but <0.4 | Unlikely to occur in the project life cycle , or the probability of the occurrence is judged to be greater than 10% but less than 40%.
L | Likely | >0.4 but <0.8 | Will likely occur sometime during the project life cycle of the project or its facilities, or the probability of the occurrence is judged to be greater than 40% but less than 80%.
VL | Very Likely | >0.8 | Very likely to occur sometime during the project life cycle or the probability of occurrence is judged to be 80% or greater.
* P = Probability of Occurrence
Concept Explanation
For each identified risk, a Probability of Occurrence is defined using the above criteria.
Also for each risk, the consequential impacts are estimated -- as either an absolute value or a range with most likely, low and high values defined
Both cost impacts and schedule impacts should be estimated.
For schedule impact, the value (or range) should reflect impact to the project completion -- that is the impact to the project critical path
Separate models will then be constructed to determine overall cost and schedule probability profiles (using Monte Carlo simulation)
Each risk will represent a variable in the model. The Pr of Occurrence will use the values shown on the right above and
the ranges for cost and schedule impacts.
NC | 0.005
VU | 0.055
U | 0.25
L | 0.6
VL | 0.9

## Standard Estimate Uncertainty
Estimate Uncertainty Matrix
Design Complexity
| Design Maturity | Low |  | Medium |  | High
| Low | -15% | 25% | -20% | 40% | -30% | 60%
| Medium | -10% | 15% | -15% | 25% | -20% | 40%
| High | -5% | 10% | -10% | 15% | -15% | 25%
|  | Low | High
| HH | -15% | 25%
| HL | -5% | 10%
| HM | -10% | 15%
| LH | -30% | 60%
| LL | -15% | 25%
| LM | -20% | 40%
| MH | -20% | 40%
| ML | -10% | 15%
| MM | -15% | 25%
Definitions
Design Maturity
| High | Final design available. All design features/requirements well known.
No further design development or evolution expected that will impact estimate
| Medium | Preliminary design available. Some additional design evolution likely
Further developments can be somewhat expected/anticipated and reflected in estimate
| Low | No better than conceptual design basis currently available. Design details, procedures,
etc. still need much development and evolution of requirements beyond estimate basis is likely and expected
Design Complexity
| Low | Work is fairly well understood -- either standard construction or repetition of activities performed in past
Little likelihood of estimate not being well understood and requirements not being well defined
| Medium | More complex work requirements that have potential to impact cost and schedule estimates
Limited experience performing similar tasks, so ability to estimate accurately is somewhat suspect
| High | Extremely challenging tasks and/or requirements. Unique or first-of-a-kind assembly or work tasks
No good basis for estimating work exists so there is a high degree of estimate uncertainty
Basis for Estimate Uncertainties
Per AACEI Recommended Practice 18R-97, Cost Estimate Classification System
As Applied in Engineering, Procurement and Construction for the Process Industry
| Estimate Class | Level of Definition |  | Accuracy Range |  |  |  | NCSX Definition | Range Used
| 5 | 0 - 2% |  | -20 to -50% - +30 to +100% |  |  |  | L maturity; H complexity | -30/+60%
| 4 | 1 - 15% |  | -15 to -30% - +20 to +50% |  |  |  | MH and LM | -20/+40%
| 3 | 10 - 40% |  | -10 to -20% - +10 to +30% |  |  |  | MM and LL | -15/+25%
| 2 | 30 - 70% |  | -5 to -15% - +5 to +20% |  |  |  | ML and HM | -10/+15%
| 1 | 50 - 100% |  | -3 to -10% - +3 to +15% |  |  |  | H maturity; L complexity | -5/+10%

## Misc Inputs
Standing army calculation
WBS | JOB | Description | Cost/yr | Cost/mo. |  | last Lehman review
18/7 | 1802/1810/7401/7501 | Field Period Assy & Machine assy | 2376 | 198 | average of the 2 assy ops | 0
19 | 1901 | Stellarator core management | 504 | 42 |  | 15.4167
81 | 8101 | PPPL Management | 912 | 76 |  | 83.3333
81 | 8102 | ORNL Management | 312 | 26 |  | 13.1667
82 | 8202 | Engineering mgt | 792 | 66 |  | 45.8333
82 | 8203 | Design Integration | 660 | 55 |  | 8.1667
82 | 8204 | Systems Analysis | 132 | 11 |  | 0
82 | 8205 | Dimensional control | 60 | 5 |  | 0
82 | 8215 | Plant Design | 60 | 5 |  | 0
89 | 8998 | Allocations | 492 | 41 |  | 35.8333
|  |  |  | 525 |  | 201.75
Second Shift oversight,support, cost dif
Crane support, fixture setup, misc support |  |  | 1.2 fte | 16.6
Field Supervision |  |  | 1.0 fte | 24.69
Metrology crews (task dependent) |  |  | n/a | 0
Metrology engineer |  |  | .5 fte | 16
Shift differntial (@ 5fte crew size) |  |  |  | 6.93
64.22

## Escalation Risk
Special Materials
Delivery cost estimate (includes raw material cost, and vendor fabrication) |  |  |  | as spent $K
|  |  |  | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | TOTAL
C - copper
| 1352 - Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 141-038.1 | PF Conductor Delivery |  | 206 |  |  |  |  | 206
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | TRIM-120 | Procure Trim Coil Conductor |  | 6 |  |  |  |  | 6
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 132-038 | Deliver Lead hardware and cables |  |  | 467 |  |  |  | 467
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 162-013.1 | Procure MC lead stubs |  |  | 19 |  |  |  | 19
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-4 | Grounding-Procure |  |  |  | 13 |  |  | 13
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-265 | Fabricate bus components |  |  |  | 60 |  |  | 60
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-275 | Power cabling & Installation |  |  |  | 187 |  |  | 187
|  |  |  | 0 | 212 | 486 | 260 | 0 | 0 | 958
S - Stainless Steel/Inconnel
| 1353 - Job: 1353 - CS Structure Procurement-DAHLGREN | 163-037 | CS Support Structure Procurement/Fab |  |  |  | 256 |  |  | 256
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 99 | [5 empty] | 99
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3062 | balance of studs for a-b-b-c |  | 84 |  |  |  |  | 84
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3072 | Deliver studs & washers for c-c joint |  | 37 |  |  |  |  | 37
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3073 | Deliver supernuts for c-c joint |  | 11 |  |  |  |  | 11
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3060 | Deliver Outboard Shim Stock | 39 | [5 empty] | 39
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3060I | Deliver Inboard Shim Stock | 39 | [5 empty] | 39
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3062X | Inboard Shims |  | 47 | 0 |  |  |  | 47
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3066 | Outboard Shims |  | 603 |  |  |  |  | 603
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3105 | Deliver bar stock |  | 25 |  |  |  |  | 25
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3110 | PPPL cut and grind to thickness
| 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 161-036.9 | Deliver base support materials |  | 69 | 86 |  |  |  | 155
| 1260 - Job: 1260 NB Transition Ducts- GORANSON | 1260-130 | Fabr &deliver 3 port duct extensions incl suprts |  |  | 159 | 259 |  |  | 419
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-037 | Fabricate structure components |  | 895 | 253 |  |  |  | 1148
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-053 | Deliver Inconnel hardware |  | 59 | 48 |  |  |  | 107
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-057 | Deliver Belleville Washers |  | 9 | 15 |  |  |  | 24
|  |  |  | 177 | 1839 | 561 | 515 | 0 | 0 | 3093 | 2915
[5 empty] | 0.63087 | 0.19245 | 0.17667 | 0 | 0
Estimate Raw material cost (delivery cost estimate x 50%)
| C - copper - base estimate (assumes 2.5%/year escalation) |  |  | 0 | 106 | 243 | 130 | 0 | 0
| Additional Copper Escalation - Low End of Range | 0.03 | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 3.18 | 14.7987 | 12.0545 | 0 | 30.0332
| Additional Copper Escalation - High End of Range | 0.2 | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 21.2 | 106.92 | 94.64 | 0 | 222.76
| S - Stainless Steel/Inconnel (assumes 2.5%/year escalation) |  |  | 88.5 | 919.5 | 280.5 | 257.5 | 0 | 0
| Additional SS/Inconel Escalation - Low End of Range | 0.03 | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 27.585 | 17.0824 | 23.8772 | 0 | 68.5447
| Additional SS/Inconel Escalation - High End of Range | 0.2 | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 183.9 | 123.42 | 187.46 | 0 | 494.78