## Sheet1
|  |  |  | Improved estimates to correct previous errors/oversights |  | Better design maturity and/or interface definition
Job # | BUDGET to COMPLETE $K (from May 1,2007) | Bottoms up EAC $K (Feb 22, 2008) | Increase ($K) | Anticipated (identified in your waf's estimate uncertainty and risk) (%) | Unanticipated (%) | Anticipated (identified in your waf's estimate uncertainty and risk) (%) | Unanticipated | Proactive measures (New tasks) to reduce risks (%) | New tasks from implementing recommendations from Lehman, Constructability, and design reviews (%) | Project schedule stretch-out due to other WBS's schedule growth (%) | Other (%) | % Sum | Comments
1260 Transition Ducts GORANSON | 0 | 508 | 508 | [5 empty] | 100% |  |  | 100%
1270 Heater Controls GORANSON | 0 | 626 | 626 | [5 empty] | 100% |  |  | 100%
1354 Trim Coils KALISH | 162 | 1692 | 1530 | [5 empty] | 100% |  |  | 100%
1802/1810/1815 Assy VIOLA | 9068 | 14967 | 5899 | 16.3% | 16.3% | 6.1% | 16.3% | 16.3% | 10.2% | 18.5% |  | 100%
1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 | 1294 | 772 |  | 5% |  | 30% | 40% |  |  | 25% | 100% | Vendor Prices Higher
7401 - TC Prep & Mach Assy Planning-PERRY | 1417 | 2070 | 653 | [5 empty] | 36% | 64% |  | 100%
8203 Design Integration - BROWN | 1408 | 2702 | 1294 |  | 80% |  |  |  | 0% | 20% |  | 100%
8202 - Engr Mgmt & Sys Eng Support-HEITZENRO | 2649 | 3804 | 1155 | 0 | 20% | 10% |  | 25% | 25% | 20% | 0% | 100%
8101 Project Management & Controls REJ | 3843 | 4880 | 1037 |  | 0% |  |  | 80% |  | 20% |  | 100%
Total | 19069 | 32543 | 13474
1260 Transition Ducts GORANSON | 0 | 508 | 508 | 0 | 0 | 0 | 0 | 0 | 508 | 0 | 0 | 508
1270 Heater Controls GORANSON | 0 | 626 | 626 | 0 | 0 | 0 | 0 | 0 | 626 | 0 | 0 | 626
1354 Trim Coils KALISH | 162 | 1692 | 1530 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 1530
1802/1810/1815 Assy VIOLA | 9068 | 14967 | 5899 | 961.537 | 961.537 | 359.839 | 961.537 | 961.537 | 601.698 | 1091.315 | 0 | 5899
1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 | 1294 | 772 | 0 | 38.6 | 0 | 231.6 | 308.8 | 0 | 0 | 193 | 772
7401 - TC Prep & Mach Assy Planning-PERRY | 1417 | 2070 | 653 | 0 | 0 | 0 | 0 | 0 | 235.08 | 417.92 | 0 | 653
8203 Design Integration - BROWN | 1408 | 2702 | 1294 | 0 | 1035.2 | 0 | 0 | 0 | 0 | 258.8 | 0 | 1294
8202 - Engr Mgmt & Sys Eng Support-HEITZENRO | 2649 | 3804 | 1155 | 0 | 231 | 115.5 | 0 | 288.75 | 288.75 | 231 | 0 | 1155
8101 Project Management & Controls REJ | 3843 | 4880 | 1037 | 0 | 0 | 0 | 0 | 829.6 | 0 | 207.4 | 0 | 1037
Total | 19069 | 32543 | 13474 | 961.537 | 2266.337 | 475.339 | 1193.137 | 2388.687 | 3789.528 | 2206.435 | 193 | 13474 | 13474
|  |  |  | 7.136% | 16.82% | 3.528% | 8.855% | 17.73% | 28.12% | 16.38% | 1.432% | 100%
|  |  |  | Corrections | Design Maturity | Risk Reduction | New Tasks | Schedule Stretch | Procurement
|  |  |  | 23.96% | 12.38% | 17.73% | 28.12% | 16.38% | 1.432% |  |  | 100%

## rls
|  |  |  | Improved estimates to correct previous errors/oversights |  | Better design maturity and/or interface definition
Job # | BUDGET to COMPLETE $K (from May 1,2007) | Bottoms up EAC $K (Feb 22, 2008) | Increase ($K) | Anticipated (identified in your waf's estimate uncertainty and risk) (%) | Unanticipated (%) | Anticipated (identified in your waf's estimate uncertainty and risk) (%) | Unanticipated | Proactive measures (New tasks) to reduce risks (%) | New tasks from implementing recommendations from Lehman, Constructability, and design reviews (%) | Project schedule stretch-out due to other WBS's schedule growth (%) | Other (%) | % Sum | Comments
1260 Transition Ducts GORANSON | 0 | 508 | 508 | [5 empty] | 100% |  |  | 100%
1270 Heater Controls GORANSON | 0 | 626 | 626 | [5 empty] | 100% |  |  | 100%
1354 Trim Coils KALISH | 162 | 1692 | 1530 | [5 empty] | 100% |  |  | 100%
1802/1810/1815 Assy VIOLA | 9068 | 14967 | 5899 | 16.3% | 16.3% | 6.1% | 16.3% | 16.3% | 10.2% | 18.5% |  | 100%
1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 | 1294 | 772 |  | 5% |  | 30% | 40% |  |  | 25% | 100% | Vendor Prices Higher
7401 - TC Prep & Mach Assy Planning-PERRY | 1417 | 2070 | 653 | [5 empty] | 36% | 64% |  | 100%
8203 Design Integration - BROWN | 1408 | 2702 | 1294 |  | 80% |  |  |  | 0% | 20% |  | 100%
8202 - Engr Mgmt & Sys Eng Support-HEITZENRO | 2649 | 3804 | 1155 | 0 | 20% | 10% |  | 25% | 25% | 20% | 0% | 100%
8101 Project Management & Controls REJ | 3843 | 4880 | 1037 |  | 0% |  |  | 80% |  | 20% |  | 100%
WBS 5 I&C Scope add-backs | 1067 | 2032 | 965 | [5 empty] | 100% |  |  |  | strykowsky assessment
1601 coil services | 861 | 1141 | 280 | [5 empty] | 100% |  |  |  | strykowsky assessment
ancilliary systems 6101/2201/2101 water vacuum fueling | 287 | 941 | 654 | [5 empty] | 100% |  |  |  | strykowsky assessment
wbs 4 power systems | 2425 | 2569 | 144 | [5 empty] | 100% |  |  |  | strykowsky assessment
wbs 19 stellarator core mngt & integr | 1620 | 2444 | 824 | [6 empty] | 100% |  |  | strykowsky assessment
8102 ORNL Project management | 499 | 1341 | 842 |  |  |  |  | 80% |  | 20% |  |  | strykowsky assessment
8998 allocations | 1453 | 2239 | 786 |  |  | 13% |  |  |  | 87% |  |  | strykowsky assessment
Total | 27281 | 45250 | 17969
1260 Transition Ducts GORANSON | 0 | 508 | 508 | 0 | 0 | 0 | 0 | 0 | 508 | 0 | 0 | 508
1270 Heater Controls GORANSON | 0 | 626 | 626 | 0 | 0 | 0 | 0 | 0 | 626 | 0 | 0 | 626
1354 Trim Coils KALISH | 162 | 1692 | 1530 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 1530
1802/1810/1815 Assy VIOLA | 9068 | 14967 | 5899 | 961.537 | 961.537 | 359.839 | 961.537 | 961.537 | 601.698 | 1091.315 | 0 | 5899
1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 | 1294 | 772 | 0 | 38.6 | 0 | 231.6 | 308.8 | 0 | 0 | 193 | 772
7401 - TC Prep & Mach Assy Planning-PERRY | 1417 | 2070 | 653 | 0 | 0 | 0 | 0 | 0 | 235.08 | 417.92 | 0 | 653
8203 Design Integration - BROWN | 1408 | 2702 | 1294 | 0 | 1035.2 | 0 | 0 | 0 | 0 | 258.8 | 0 | 1294
8202 - Engr Mgmt & Sys Eng Support-HEITZENRO | 2649 | 3804 | 1155 | 0 | 231 | 115.5 | 0 | 288.75 | 288.75 | 231 | 0 | 1155
8101 Project Management & Controls REJ | 3843 | 4880 | 1037 | 0 | 0 | 0 | 0 | 829.6 | 0 | 207.4 | 0 | 1037
WBS 5 I&C Scope add-backs | 1067 | 2032 | 965 | 0 | 0 | 0 | 0 | 0 | 965 | 0 | 0 | 965
1601 coil services | 861 | 1141 | 280 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 280
ancilliary systems 6101/2201/2101 water vacuum fueling | 287 | 941 | 654 | 0 | 0 | 0 | 0 | 0 | 654 | 0 | 0 | 654
wbs 4 power systems | 2425 | 2569 | 144 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 144
wbs 19 stellarator core mngt & integr | 1620 | 2444 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 0 | 824
8102 ORNL Project management | 499 | 1341 | 842 | 0 | 0 | 0 | 0 | 673.6 | 0 | 168.4 | 0 | 842
8998 allocations | 1453 | 2239 | 786 | 0 | 0 | 102.18 | 0 | 0 | 0 | 683.82 | 0 | 786
Total | 27281 | 45250 | 17969 | 961.537 | 2266.337 | 577.519 | 1193.137 | 3062.287 | 5832.528 | 3882.655 | 193 | 17969 | 17969
total erc |  |  | 20071 | 5.351% | 12.61% | 3.214% | 6.64% | 17.04% | 32.46% | 21.61% | 1.074% | 100%
89.53%
|  |  |  | Corrections | Design Maturity | Risk Reduction | New Tasks | Schedule Stretch | Procurement
|  |  |  | 17.96% | 9.854% | 17.04% | 32.46% | 21.61% | 1.074% |  |  | 100%
12
13
14
15
16
17
18
19
2
3
4
5
6
7
8

## x
[5 empty] | Improved estimates to correct previous errors/oversights |  | Better design maturity and/or interface definition
| Job # | BUDGET to COMPLETE $K (from May 1,2007) | Bottoms up EAC $K (Feb 22, 2008) | Increase ($K) | Anticipated (identified in your waf's estimate uncertainty and risk) (%) | Unanticipated (%) | Anticipated (identified in your waf's estimate uncertainty and risk) (%) | Unanticipated | Proactive measures (New tasks) to reduce risks (%) | New tasks from implementing recommendations from Lehman, Constructability, and design reviews (%) | Project schedule stretch-out due to other WBS's schedule growth (%) | Other (%) | % Sum | Comments
12 | 1260 Transition Ducts GORANSON | 0 | 508 | 508 | [5 empty] | 100% |  |  | 100%
12 | 1270 Heater Controls GORANSON | 0 | 626 | 626 | [5 empty] | 100% |  |  | 100%
12 |  | 156 | 212.0406 | 56.0406 | [5 empty] | 100% |  |  | 100%
13 | 1354 Trim Coils KALISH | 162 | 1692 | 1530 | [5 empty] | 100% |  |  | 100%
13 |  | 3300 | 3385.4125 | 85.4125 | [5 empty] | 100% |  |  | 100%
14 |  | 6246 | 6642.7101 | 396.7101 | 50% |  | 50% | [5 empty] | 100%
15 |  | 1262 | 1778.5641 | 516.5641 |  | 50% | 25% |  |  | 25% |  |  | 100%
17 |  | 784 | 1127.2122 | 343.2122 |  |  | 100% | [5 empty] | 100%
18 | 1802/1810/1815 Assy VIOLA | 9068 | 14967 | 5899 | 16.3% | 16.3% | 6.1% | 16.3% | 16.3% | 10.2% | 18.5% |  | 100%
18 | 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 | 1294 | 772 |  | 5% |  | 30% | 40% |  |  | 25% | 100% | Vendor Prices Higher
18 | 1806 | 514 | 365.422 | -148.578 |  |  | 100% | [5 empty] | 100%
7 | 7401 - TC Prep & Mach Assy Planning-PERRY | 7951 | 8330.9247 | 379.9247 | [5 empty] | 36% | 64% |  | 100%
82 | 8203 Design Integration - BROWN | 1408 | 2702 | 1294 |  | 80% |  |  |  | 0% | 20% |  | 100%
82 | 8202 - Engr Mgmt & Sys Eng Support-HEITZENRO | 2649 | 3804 | 1155 | 0 | 20% | 10% |  | 25% | 25% | 20% | 0% | 100%
82 |  | 1892 | 2374.0599 | 482.0599 | 0.3 |  | 10% |  | 30% | 10% | 20% |  | 100%
81 | 8101 Project Management & Controls REJ | 3843 | 4880 | 1037 |  | 0% |  |  | 80% |  | 20% |  | 100%
5 | WBS 5 I&C Scope add-backs | 1136 | 2097 | 961 | [5 empty] | 100% |  |  | 100% | strykowsky assessment
16 | 1601 coil services | 861 | 1141 | 280 | [5 empty] | 100% |  |  | 100% | strykowsky assessment
2 | 2201/2101 fueling and vacuum pumping | 241 | 828 | 587 | [5 empty] | 100% |  |  | 100%
6 | 6101 water | 46 | 113 | 67 | [5 empty] | 100% |  |  | 100%
6 |  | 1333 | 1725 | 392 |  |  | 100% | [5 empty] | 100%
3 | 3 | 717 | 991.4648 | 274.4648 |  |  | 100% | [5 empty] | 100% | strykowsky assessment
4 | wbs 4 power systems | 2425 | 2569.3415 | 144.3415 | [5 empty] | 100% |  |  | 100% | strykowsky assessment
19 | wbs 19 stellarator core mngt & integr | 1620 | 2444 | 824 | [6 empty] | 100% |  | 100% | strykowsky assessment
85 |  | 765 | 771 | 6 |  |  | 100% | [5 empty] | 100%
81 | 8102 ORNL Project management | 499 | 1341 | 842 |  |  |  |  | 80% |  | 20% |  | 100% | strykowsky assessment
89 | 8998 allocations | 1453 | 2239 | 786 |  |  | 13% |  |  |  | 87% |  | 100% | strykowsky assessment
| Total | 50853 | 70949.1526 | 20096.1526
12 | 1260 Transition Ducts GORANSON | 0 | 508 | 508 | 0 | 0 | 0 | 0 | 0 | 508 | 0 | 0 | 508
12 | 1270 Heater Controls GORANSON | 0 | 626 | 626 | 0 | 0 | 0 | 0 | 0 | 626 | 0 | 0 | 626
12 |  | 156 | 212.0406 | 56.0406 | 0 | 0 | 0 | 0 | 0 | 56.0406 | 0 | 0 | 56.0406
13 | 1354 Trim Coils KALISH | 162 | 1692 | 1530 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 1530
13 |  | 3300 | 3385.4125 | 85.4125 | 0 | 0 | 0 | 0 | 0 | 85.4125 | 0 | 0 | 85.4125
14 |  | 6246 | 6642.7101 | 396.7101 | 198.3551 | 0 | 198.3551 | 0 | 0 | 0 | 0 | 0 | 396.7101
15 |  | 1262 | 1778.5641 | 516.5641 | 0 | 258.2821 | 129.141 | 0 | 0 | 129.141 | 0 | 0 | 516.5641
17 |  | 784 | 1127.2122 | 343.2122 | 0 | 0 | 343.2122 | 0 | 0 | 0 | 0 | 0 | 343.2122
18 | 1802/1810/1815 Assy VIOLA | 9068 | 14967 | 5899 | 961.537 | 961.537 | 359.839 | 961.537 | 961.537 | 601.698 | 1091.315 | 0 | 5899
18 | 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 | 1294 | 772 | 0 | 38.6 | 0 | 231.6 | 308.8 | 0 | 0 | 193 | 772
18 | 1806 | 514 | 365.422 | -148.578 | 0 | 0 | -148.578 | 0 | 0 | 0 | 0 | 0 | -148.578
7 | 7401 - TC Prep & Mach Assy Planning-PERRY | 7951 | 8330.9247 | 379.9247 | 0 | 0 | 0 | 0 | 0 | 136.7729 | 243.1518 | 0 | 379.9247
82 | 8203 Design Integration - BROWN | 1408 | 2702 | 1294 | 0 | 1035.2 | 0 | 0 | 0 | 0 | 258.8 | 0 | 1294
82 | 8202 - Engr Mgmt & Sys Eng Support-HEITZENRO | 2649 | 3804 | 1155 | 0 | 231 | 115.5 | 0 | 288.75 | 288.75 | 231 | 0 | 1155
82 |  | 1892 | 2374.0599 | 482.0599 | 144.618 | 0 | 48.206 | 0 | 144.618 | 48.206 | 96.412 | 0 | 482.0599
81 | 8101 Project Management & Controls REJ | 3843 | 4880 | 1037 | 0 | 0 | 0 | 0 | 829.6 | 0 | 207.4 | 0 | 1037
5 | WBS 5 I&C Scope add-backs | 1136 | 2097 | 961 | 0 | 0 | 0 | 0 | 0 | 961 | 0 | 0 | 961
16 | 1601 coil services | 861 | 1141 | 280 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 280
2 | 2201/2101 fueling and vacuum pumping | 241 | 828 | 587 | 0 | 0 | 0 | 0 | 0 | 587 | 0 | 0 | 587
6 | 6101 water | 46 | 113 | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 67
6 |  | 1333 | 1725 | 392 | 0 | 0 | 392 | 0 | 0 | 0 | 0 | 0 | 392
3 | 3 | 717 | 991.4648 | 274.4648 | 0 | 0 | 274.4648 | 0 | 0 | 0 | 0 | 0 | 274.4648
4 | wbs 4 power systems | 2425 | 2569.3415 | 144.3415 | 0 | 0 | 0 | 0 | 0 | 144.3415 | 0 | 0 | 144.3415
19 | wbs 19 stellarator core mngt & integr | 1620 | 2444 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 0 | 824
85 |  | 765 | 771 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6
81 | 8102 ORNL Project management | 499 | 1341 | 842 | 0 | 0 | 0 | 0 | 673.6 | 0 | 168.4 | 0 | 842
89 | 8998 allocations | 1453 | 2239 | 786 | 0 | 0 | 102.18 | 0 | 0 | 0 | 683.82 | 0 | 786
| Total | 50853 | 70949.1526 | 20096.1526 | 1304.51 | 2524.6191 | 1820.3201 | 1193.137 | 3206.905 | 6049.3626 | 3804.2988 | 193 | 20096.1526 | 20096.1526
| total erc |  |  | 20071 | 6.491% | 12.56% | 9.058% | 5.937% | 15.96% | 30.1% | 18.93% | 0.9604% | 100%
100.1%
[5 empty] | Corrections | Design Maturity | Risk Reduction | New Tasks | Schedule Stretch | other
[5 empty] | 19.05% | 15% | 15.96% | 30.1% | 18.93% | 0.9604% |  |  | 100%
12 | Vacuum Vessel | 156 | 1346.0406 | 1190.0406 | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 100%
13 | Conventional Coils | 3462 | 5077.4125 | 1615.4125 | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 100%
14 | Modular Coils | 6246 | 6642.7101 | 396.7101 | 50% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
15 | Structures | 1262 | 1778.5641 | 516.5641 | 0% | 50% | 25% | 0% | 0% | 25% | 0% | 0% | 100% | 100%
16 | Coil Services | 861 | 1141 | 280 | [8 empty] | 100% | 0%
17 | Cryostat & Base Support Structure | 784 | 1127.2122 | 343.2122 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
18 | Field Period Assembly | 10104 | 16626.422 | 6522.422 | 14.74% | 15.33% | 3.239% | 18.29% | 19.48% | 9.225% | 16.73% | 2.959% | 100% | 100%
19 | Stellarator Core Mgmt & Integr | 1620 | 2444 | 824 | [8 empty] | 100% | 0%
2 | Auxiliary Systems | 241 | 828 | 587 | [8 empty] | 100% | 0%
3 | Diagnostics | 717 | 991.4648 | 274.4648 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
4 | Electrical Power Systems | 2425 | 2569.3415 | 144.3415 | [8 empty] | 100% | 0%
5 | I&C Systems | 1136 | 2097 | 961 | [8 empty] | 100% | 0%
6 | Facility Systems | 1379 | 1838 | 459 | 0% | 0% | 85.4% | 0% | 0% | 14.6% | 0% | 0% | 100% | 100%
7 | Test Cell Prep & Machine Assy | 7951 | 8330.9247 | 379.9247 | [8 empty] | 100% | 0%
81 | Project Management and Oversight | 5795 | 8460 | 2665 | 0% | 0% | 3.834% | 0% | 56.41% | 0% | 39.76% | 0% | 100% | 100%
82 | Project Engineering | 5949 | 8880.0599 | 2931.0599 | 4.934% | 43.2% | 5.585% | 0% | 14.79% | 11.5% | 20% | 0% | 100% | 100%
85 | Integrated Systems Testing | 765 | 771 | 6 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
|  | 50853 | 70949.1526 | 20096.1526 | 6.491% | 12.56% | 9.058% | 5.937% | 15.96% | 30.1% | 18.93% | 0.9604% | 100% | 100%
|  | August 2007 (ETC from 5/1/07) | March 2008 (ETC from 5/1/07) | Increase ($K) | Corrections | Design Maturity | Risk Reduction | New Scope | Schedule Stretch
12 | Vacuum Vessel | 156 | 1419.0306 | 1263.0306 |  |  |  | 100% |  |  | 100%
13 | Conventional Coils | 3462 | 4862.1485 | 1400.1485 |  |  |  | 100% |  |  | 100%
14 | Modular Coils | 6246 | 6534.5428 | 288.5428 | 50% | 50% |  |  |  |  | 100%
15 | Structures | 1262 | 1737.5341 | 475.5341 | 50% | 25% |  | 25% |  |  | 100%
16 | Coil Services | 861 | 1084.66 | 223.66 |  | 100% |  |  |  |  | 100%
17 | Cryostat & Base Suprt Structure | 784 | 1554.7222 | 770.7222 |  | 100% |  |  |  |  | 100%
18 | Field Period Assembly | 10104 | 16482.5067 | 6378.5067 | 32% | 23% | 16% | 10% | 19% |  | 100%
19 | Stellarator Core Mgmt & Integr | 1620 | 2444.109 | 824.109 |  |  | 45% |  | 55% |  | 100%
2 | Auxiliary Systems | 241 | 1017.59 | 776.59 |  |  |  | 100% |  |  | 100%
3 | Diagnostics | 717 | 987.4248 | 270.4248 |  |  |  | 100% |  |  | 100% |  |  |  | x | 12 | 156 | 1346.0406 | 1190.0406 | 0 | 0 | 0 | 0 | 0 | 1190.0406 | 0 | 0 | 1190.0406
4 | Electrical Power Systems | 2425 | 2613.6715 | 188.6715 |  |  |  | 100% |  |  | 100% |  |  |  |  | 13 | 3462 | 5077.4125 | 1615.4125 | 0 | 0 | 0 | 0 | 0 | 1615.4125 | 0 | 0 | 1615.4125
5 | I&C Systems | 1136 | 2098.5 | 962.5 |  |  |  | 100% |  |  | 100% |  |  |  |  | 14 | 6246 | 6642.7101 | 396.7101 | 198.3551 | 0 | 198.3551 | 0 | 0 | 0 | 0 | 0 | 396.7101
6 | Facility Systems | 1379 | 2423.19 | 1044.19 | 50% | 50% |  |  |  |  | 100% |  |  |  |  | 15 | 1262 | 1778.5641 | 516.5641 | 0 | 258.2821 | 129.141 | 0 | 0 | 129.141 | 0 | 0 | 516.5641
7 | Test Cell Prep & Machine Assy | 7951 | 8321.8147 | 370.8147 |  |  |  | 36% | 64% |  | 100% |  |  |  |  | 16 | 861 | 1141 | 280 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 280
81 | Project Management and Oversight | 5795 | 7767.1276 | 1972.1276 |  |  | 70% |  | 30% |  | 100% |  |  |  |  | 17 | 784 | 1127.2122 | 343.2122 | 0 | 0 | 343.2122 | 0 | 0 | 0 | 0 | 0 | 343.2122
82 | Project Engineering | 5949 | 8857.425 | 2908.425 | 30% | 10% | 25% | 14.5% | 20% |  | 99.5% |  |  |  |  | 18 | 10104 | 16626.422 | 6522.422 | 961.537 | 1000.137 | 211.261 | 1193.137 | 1270.337 | 601.698 | 1091.315 | 193 | 6522.422
85 | Integrated Systems Testing | 765 | 794.61 | 29.61 | 100% | [5 empty] | 100% |  |  |  |  | 19 | 1620 | 2444 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 0 | 824
|  | 50853 | 71000.6076 | 20146.6076 | 19.11% | 17.57% | 17.38% | 30.66% | 15.28% |  | 100% |  |  |  |  | 2 | 241 | 828 | 587 | 0 | 0 | 0 | 0 | 0 | 587 | 0 | 0 | 587
[5 empty] | 19.11% | 17.57% | 17.38% | 30.66% | 15.28% |  | 100% |  |  |  |  | 3 | 717 | 991.4648 | 274.4648 | 0 | 0 | 274.4648 | 0 | 0 | 0 | 0 | 0 | 274.4648
[5 empty] | 18% | 15% | 20% | 30% | 17% |  | 100% |  |  |  |  | 4 | 2425 | 2569.3415 | 144.3415 | 0 | 0 | 0 | 0 | 0 | 144.3415 | 0 | 0 | 144.3415
[5 empty] | 0 | 0 | 0 | 1263.0306 | 0 | [6 empty] | 5 | 1136 | 2097 | 961 | 0 | 0 | 0 | 0 | 0 | 961 | 0 | 0 | 961
[5 empty] | 0 | 0 | 0 | 1400.1485 | 0 | [6 empty] | 6 | 1379 | 1838 | 459 | 0 | 0 | 392 | 0 | 0 | 67 | 0 | 0 | 459
[5 empty] | 144.2714 | 144.2714 | 0 | 0 | 0 | [6 empty] | 7 | 7951 | 8330.9247 | 379.9247 | 0 | 0 | 0 | 0 | 0 | 136.7729 | 243.1518 | 0 | 379.9247
[5 empty] | 237.7671 | 118.8835 | 0 | 118.8835 | 0 | [6 empty] | 81 | 5795 | 8460 | 2665 | 0 | 0 | 102.18 | 0 | 1503.2 | 0 | 1059.62 | 0 | 2665
[5 empty] | 0 | 223.66 | 0 | 0 | 0 | [6 empty] | 82 | 5949 | 8880.0599 | 2931.0599 | 144.618 | 1266.2 | 163.706 | 0 | 433.368 | 336.956 | 586.212 | 0 | 2931.0599
[5 empty] | 0 | 770.7222 | 0 | 0 | 0 | [6 empty] | 85 | 765 | 771 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6
[5 empty] | 2041.1221 | 1467.0565 | 1020.5611 | 637.8507 | 1211.9163 | [7 empty] | 50853 | 70949.1526 | 20096.1526 | 1304.51 | 2524.6191 | 1820.3201 | 1193.137 | 3206.905 | 6049.3626 | 3804.2988 | 193 | 20096.1526
[5 empty] | 0 | 0 | 370.849 | 0 | 453.26
[5 empty] | 0 | 0 | 0 | 776.59 | 0
[5 empty] | 0 | 0 | 0 | 270.4248 | 0
[5 empty] | 0 | 0 | 0 | 188.6715 | 0
[5 empty] | 0 | 0 | 0 | 962.5 | 0
[5 empty] | 522.095 | 522.095 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 133.4933 | 237.3214
[5 empty] | 0 | 0 | 1380.4893 | 0 | 591.6383
[5 empty] | 872.5275 | 290.8425 | 727.1063 | 421.7216 | 581.685
|  |  |  | 20133.0654 | 29.61 | 0 | 0 | 0 | 0
[5 empty] | 3847.3931 | 3537.5312 | 3499.0057 | 6173.3146 | 3075.8209