## Sheet2
Sum of TOTAL | DESC
WBS2 | Design | R&D | Procurement | Fabrication/Assembly | Grand Total
12 - 12 - Vacuum Vessel Systems | 223 |  | 990 | 216.2 | 1429.2
13 - 13 - Conventional Coils | 387.1 |  | 3653.7 | 215.4 | 4256.2
14 - 14 - Modular Coils | 166.3 | 4.4 | 1044.7 | 1386.7 | 2602.1
15 - 15 - Coil Structures | 88.9 |  | 1430.3 | 12.3 | 1531.5
16 - 16 - Coil Services | 386.1 | 24 | 496.2 | 178.5 | 1084.8
17 - 17 - Cryostat and Base Support Structure | 717 |  | 779.6 |  | 1496.6
18 - 18 - Field Period Assembly | 1081.1 |  | 354.9 | 13001.5 | 14437.5
21 - 21 - Fueling Systems | 161.4 |  | 57.2 | 119.2 | 337.8
22 - 22 - Torus Vacuum Pumping Systems | 274.5 |  | 157.8 | 247.1 | 679.4
31 - 31 - Magnetic Diagnostics | 76.7 |  | 31.5 | 301.8 | 410
36 - 36 - Edge and Divertor Diagnostics | 13.3 |  | 4.7 | 12.3 | 30.3
38 - 38 - Electron Beam (EB) Mapping | 171 |  | 32.2 | 54.9 | 258.1
39 - 39 - Diagnostics Integration | 111.6 |  |  |  | 111.6
41 - 41 - AC Power | 49.9 |  | 20.1 | 84.3 | 154.3
43 - 43 - DC Systems | 9.3 |  |  | 569.6 | 578.9
44 - 44 - Control and protection Systems | 291.9 |  | 162.8 | 625.4 | 1080.1
45 - 45 - Power System Design and Integration | 403.1 |  | 32.6 | 469.5 | 905.2
51 - 51 - Network and Fiber Infrastructure | 21 |  | 95.2 | 105.3 | 221.5
52 - 52 - Central Instrumentation & Control | 173.3 |  | 100.7 | 137.8 | 411.8
53 - 53 - Data Acquisition & Facility Computing | 107.5 |  | 32.3 | 26.7 | 166.5
54 - 54 - Facility Timing & Synchronization | 119.1 |  | 101.3 | 137.6 | 358
55 - 55 - Real Time Plasma & Power Supply Control Sys | 180.8 |  | 199.4 | 121.7 | 501.9
56 - 56 - Central Safety and Interlock Systems | 117.2 |  | 95.5 | 159.6 | 372.3
58 - 58 - Central I&C management and Integration | 66.5 |  |  |  | 66.5
61 - 61 - Water Systems | 39.9 |  | 31 | 41.4 | 112.3
62 - 62 - Cryogenic Systems | 639.6 | 104 | 388.3 | 436 | 1567.9
63 - 63 - Utility Systems | 34.8 |  | 36.9 | 37.7 | 109.4
64 - 64 - PFC/VV Heating & Cooling (Bakeout) | 157.9 |  | 265.3 | 210.4 | 633.6
73 - 73 - Platform Design & Fabrication |  |  |  | 212.8 | 212.8
74 - 74 - Machine Assembly Planning and Oversight |  |  |  | 2322.7 | 2322.7
75 - 75 - Test Cell and Basement Assembly Operations |  |  |  | 5642.8 | 5642.8
76 - 76 - Tooling Design & Fabrication |  |  | 366.6 | 32.4 | 399
Grand Total | 6269.8 | 132.4 | 10960.8 | 27119.6 | 44482.6
| Design | R&D | Procurement | Fabrication/Assembly | Grand Total
12 - 12 - Vacuum Vessel Systems | 223 | 0 | 990 | 216.2 | 1429.2
13 - 13 - Conventional Coils | 387.1 | 0 | 3653.7 | 215.4 | 4256.2
14 - 14 - Modular Coils | 166.3 | 4.4 | 1044.7 | 1386.7 | 2602.1
15 - 15 - Coil Structures | 88.9 | 0 | 1430.3 | 12.3 | 1531.5
16 - 16 - Coil Services | 386.1 | 24 | 496.2 | 178.5 | 1084.8
17 - 17 - Cryostat and Base Support Structure | 717 | 0 | 779.6 | 0 | 1496.6
18 - 18 - Field Period Assembly | 1081.1 | 0 | 354.9 | 13001.5 | 14437.5
2 | 435.9 | 0 | 215 | 366.3 | 1017.2
3 | 372.6 | 0 | 68.4 | 369 | 810
4 | 754.2 | 0 | 215.5 | 1748.8 | 2718.5
5 | 785.4 | 0 | 624.4 | 688.7 | 2098.5
6 | 872.2 | 104 | 721.5 | 725.5 | 2423.2
7 | 0 | 0 | 366.6 | 8210.7 | 8577.3
| 6269.8 | 132.4 | 10960.8 | 27119.6 | 44482.6
44482.6

## P3
WBS2 | PHAS | ACT ID | DESC | TOTAL | OCT FY08 | NOV FY08 | DEC FY08 | JAN FY08 | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09 | OCT FY10 | NOV FY10 | DEC FY10 | JAN FY10 | FEB FY10 | MAR FY10 | APR FY10 | MAY FY10 | JUN FY10 | JUL FY10 | AUG FY10 | SEP FY10 | OCT FY11 | NOV FY11 | DEC FY11 | JAN FY11 | FEB FY11 | MAR FY11 | APR FY11 | MAY FY11 | JUN FY11 | JUL FY11 | AUG FY11 | SEP FY11 | OCT FY12 | NOV FY12 | DEC FY12 | JAN FY12 | FEB FY12 | MAR FY12 | APR FY12 | MAY FY12 | JUN FY12 | JUL FY12 | AUG FY12 | SEP FY12
36 - 36 - Edge and Divertor Diagnostics | F - Fabrication/Assembly | F | Fabrication/Assembly | 12.3 | [29 empty] | 9.2 | 3.1
15 - 15 - Coil Structures | F - Fabrication/Assembly | F | Fabrication/Assembly | 12.3 | [11 empty] | 1.5 | 2.4 | 1.9 | 1.8 | 2.2 | 2.1 | 0.4
53 - 53 - Data Acquisition & Facility Computing | F - Fabrication/Assembly | F | Fabrication/Assembly | 26.7 | [26 empty] | 0.9 | 2 | 11 | 0.6 | [10 empty] | 10.5 | 1.7
76 - 76 - Tooling Design & Fabrication | F - Fabrication/Assembly | F | Fabrication/Assembly | 32.4 | [27 empty] | 0.4 | 1.5 | 1.7 | 1.7 | 1.5 | 1.7 | 1.6 | 1.7 | 1.6 | 1.6 | 1.5 | 1.3 | 1.6 | 1.5 | 1.7 | 1.6 | 1.6 | 1.7 | 1.5 | 1.7 | 1.6 | 0.1
63 - 63 - Utility Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 37.7 | [40 empty] | 5.7 | 18.8 | 13.2
61 - 61 - Water Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 41.4 | [37 empty] | 10.9 | 15.5 | 12.3 | 2.7
38 - 38 - Electron Beam (EB) Mapping | F - Fabrication/Assembly | F | Fabrication/Assembly | 54.9 | [36 empty] | 16.9 | 16.9 | 14.3 | 6.8
41 - 41 - AC Power | F - Fabrication/Assembly | F | Fabrication/Assembly | 57 | [27 empty] | 3.6 | 5.6 | 2 | [7 empty] | 6.4 | 18.1 | 21.3
51 - 51 - Network and Fiber Infrastructure | F - Fabrication/Assembly | F | Fabrication/Assembly | 105.3 | [35 empty] | 15.9 | 25.7 | 24.5 | 20.8 | 17.3 | 1.1
21 - 21 - Fueling Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 119.2 | [36 empty] | 17.8 | 17 | 14.4 | 17.8 | 17 | 35.2
55 - 55 - Real Time Plasma & Power Supply Control Sys | F - Fabrication/Assembly | F | Fabrication/Assembly | 121.7 | [33 empty] | 2.4 | 10.7 | 12.4 | 12.4 | 11.8 | 10.1 | 25.2 | 32.1 | 4.6
54 - 54 - Facility Timing & Synchronization | F - Fabrication/Assembly | F | Fabrication/Assembly | 137.6 | [32 empty] | 2.1 | 22.1 | 19 | 11.7 | 11.7 | 11.1 | 9.5 | 26.8 | 23.6
52 - 52 - Central Instrumentation & Control | F - Fabrication/Assembly | F | Fabrication/Assembly | 137.8 | [34 empty] | 2.5 | 26.3 | 26.3 | 25 | 21.3 | 18.8 | 12.6 | 5
56 - 56 - Central Safety and Interlock Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 159.6 | [34 empty] | 22.5 | 27.8 | 27.8 | 26.4 | 22.5 | 20.8 | 11.8
16 - 16 - Coil Services | F - Fabrication/Assembly | F | Fabrication/Assembly | 178.5 | [11 empty] | 3.5 | 27.4 | 31 | 29.2 | 36.1 | 32.9 | 0.5 | 1.5 | 1.4 | 1.5 | 1.5 | 1.4 | 1.4 | 1.5 | 1.3 | 1.1 | 1.4 | 1.4 | 1.6 | 0.9
64 - 64 - PFC/VV Heating & Cooling (Bakeout) | F - Fabrication/Assembly | F | Fabrication/Assembly | 210.4 | [39 empty] | 38.7 | 55.3 | 63.6 | 39.5 | 13.3
73 - 73 - Platform Design & Fabrication | F - Fabrication/Assembly | F | Fabrication/Assembly | 212.8 |  |  | 0.8 | 1.8 | [6 empty] | 24 | 38.6 | [11 empty] | 25.4 | 91.5 | 33.3
13 - 13 - Conventional Coils | F - Fabrication/Assembly | F | Fabrication/Assembly | 215.4 | [7 empty] | 7.4 | 8.2 | 8.6 | 8.2 | 8.2 | 9 | 7 | 6.7 | 8.2 | 13.5 | 10 | 8.6 | 7.8 | 8.6 | 8.6 | 8.2 | 8.2 | 21.3 |  |  |  |  | 1.9 | 2.5 | 2.3 | 2.5 | 2.4 | 2.5 | 2.4 | 8.2 | 13.9 | 10.5
12 - 12 - Vacuum Vessel Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 216.2 |  |  |  | 14.5 | [11 empty] | 0.6 | 0.8 | 0.9 | 0.9 | 0.8 | 0.9 | 0.9 | 0.8 | 0.8 | 0.9 | 0.8 | 0.6 | 0.8 | 0.8 | 0.9 | 0.9 | 0.8 | 0.9 | 0.8 | 0.5 | 11.7 | 11.7 | 11.1 | 9.4 | 11.7 | 11.1 | 31.1 | 41.3 | 41.3 | 19.7
22 - 22 - Torus Vacuum Pumping Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 247.1 | [20 empty] | 0.9 | 1 | 0.9 | 0.9 | 1 | 0.8 | 0.7 | 0.9 | 0.9 | 1 | 1 | 0.9 | 1 | 0.9 | 1 | 28.9 | 28.9 | 27.5 | 23.4 | 28.9 | 27.5 | 31.6 | 15 |  |  | 21.6
45 - 45 - Power System Design and Integration | F - Fabrication/Assembly | F | Fabrication/Assembly | 273.8 | [29 empty] | 5.7 | 10.4 | 4.3 | 4.3 | 12.8 | 13.4 | 12.8 | 12.8 | 12.2 | 10.3 | 0.6 |  |  |  |  | 17.4 | 87.1 | 69.7
31 - 31 - Magnetic Diagnostics | F - Fabrication/Assembly | F | Fabrication/Assembly | 301.8 | 6.8 | 13.8 | 8.8 | 8.7 | 31 | 11.1 | 36.4 | 30.6 | 16 | 17.2 | 11.4 | 8 | 57.3 | 18.3 | 33.6 | 12.2 | 3.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1.6 | 1.8 | 1.6 | 1.9 | 1.9 | 2.2 | 1.6
44 - 44 - Control and protection Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 398.3 | [27 empty] | 7.7 | 21.6 | 15.9 |  |  |  |  | 19.4 | 46.4 | 74.7 | 69.6 | 71.1 | 60.8 | 11.1
62 - 62 - Cryogenic Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 436 | [28 empty] | 1.5 | 3.4 | 3.2 | 2.9 | 3.2 | 3.1 | 3.2 | 3.1 | 32.1 | 30.6 | 46.3 | 62.5 | 59.5 | 68.5 | 62.5 | 35.9 | 14.5
43 - 43 - DC Systems | F - Fabrication/Assembly | F | Fabrication/Assembly | 569.6 | 0.5 | 0.4 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 3.4 | 4.5 | 25.7 | 6.6 | 6.6 | 6.1 | 4.7 | 4.3 | 3.4 | 7.8 | 8.6 | 8.6 | 7.8 | 8.6 | 8.6 | 8.2 | 8.2 | 12.3 | 10.6 | 8.9 | 11.2 | 40.1 | 90.5 | 64.8 | 58.9 | 64.8 | 61.9 | 6.3 | 0.5 | 0.5 | 0.4 | 0.4 | 0.5 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.5 | 0.5
14 - 14 - Modular Coils | F - Fabrication/Assembly | F | Fabrication/Assembly | 1386.7 | 220.7 | 225.3 | 149.5 | 217.2 | 267.7 | 198.4 | 224 | 208.5 | 128.8 | 120.8 | 68.7 | 45.4 | 29.2 | 8.1 | 4.8 | 5.9 | 5.7 | 6.2 | 6.2 | 5.7 | 6.2 | 6.2 | 5.9 | 5.9 | 23.2 | 5.2
74 - 74 - Machine Assembly Planning and Oversight | F - Fabrication/Assembly | F | Fabrication/Assembly | 2322.7 | 13.8 | 12 | 9 | 13.2 | 13.1 | 13.1 | 13.7 | 13.1 | 13.1 | 13.7 | 13.1 | 13.1 | 14.3 | 11.2 | 10.6 | 13.1 | 12.5 | 13.7 | 13.7 | 12.5 | 13.7 | 13.7 | 13.1 | 13.7 | 13.7 | 13.1 | 14.3 | 23.7 | 52.5 | 60.3 | 57.7 | 52.5 | 57.7 | 55.1 | 57.7 | 71.2 | 90.9 | 109.8 | 99.7 | 112.2 | 106.9 | 122.9 | 112.2 | 113.7 | 117.6 | 108.3 | 122.9 | 113.7 | 112.2 | 88.4
75 - 75 - Test Cell and Basement Assembly Operations | F - Fabrication/Assembly | F | Fabrication/Assembly | 5642.8 | [26 empty] | 59.3 | 132.8 | 292.7 | 176.1 | 101 | 133.6 | 152.2 | 214.2 | 188.5 | 288.2 | 329.7 | 154.9 | 183 | 284.1 | 301.8 | 221.6 | 254.1 | 186.5 | 211.5 | 370.8 | 333.4 | 333.9 | 373 | 365.9
18 - 18 - Field Period Assembly | F - Fabrication/Assembly | F | Fabrication/Assembly | 13001.5 | 196 | 208.1 | 85.8 | 229.6 | 486.9 | 450.1 | 499.8 | 502.1 | 301.1 | 358.1 | 352.2 | 364 | 565.5 | 612 | 382.1 | 460.2 | 397.4 | 496 | 483.1 | 458.4 | 429.5 | 424 | 391.4 | 383.2 | 490.6 | 381.9 | 280.9 | 381.2 | 422.1 | 441.6 | 408.8 | 482.3 | 441.1 | 296.8 | 152.2 | 24.9
36 - 36 - Edge and Divertor Diagnostics | T - Procurement | T | Procurement | 4.7 | [25 empty] | 0.1 | 1.2 | 1.4 | 1.4 | 0.6
41 - 41 - AC Power | T - Procurement | T | Procurement | 20.1 | [23 empty] | 0.1 | 2.3 | 2 | 1.6 | 0.7 |  |  |  |  | 1 | 2.6 | 2.8 | 2.6 | 2.6 | 1.8
61 - 61 - Water Systems | T - Procurement | T | Procurement | 31 | [33 empty] | 6.2 | 7.6 | 7.2 | 7.2 | 2.8
31 - 31 - Magnetic Diagnostics | T - Procurement | T | Procurement | 31.5 |  | 3.8 | 1.9 | 3.1 | 7.6 | 7.6 | 6.9 | 1.5 | 1.3 | 0.2 |  |  | 6.4
38 - 38 - Electron Beam (EB) Mapping | T - Procurement | T | Procurement | 32.2 | [33 empty] | 10.4 | 10.9 | 10.4 | 0.5
53 - 53 - Data Acquisition & Facility Computing | T - Procurement | T | Procurement | 32.3 | [24 empty] | 4.3 | 20.5 | 7.5
45 - 45 - Power System Design and Integration | T - Procurement | T | Procurement | 32.6 | [26 empty] | 0.6 | 0.8 | 0.8 | 0.5 | 0.3 | 1.2 | 0.9 |  |  |  | 8.9 | 8.4 | 7.2 | 3
63 - 63 - Utility Systems | T - Procurement | T | Procurement | 36.9 | [37 empty] | 5.5 | 10.5 | 12.9 | 8
21 - 21 - Fueling Systems | T - Procurement | T | Procurement | 57.2 | [20 empty] | 0 | 0.3 | 0.3 | 0.3 | 17.5 | 15.1 | 12.8 | 6.6 | 0.3 | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
51 - 51 - Network and Fiber Infrastructure | T - Procurement | T | Procurement | 95.2 | [32 empty] | 14.3 | 33.3 | 34.9 | 12.7
56 - 56 - Central Safety and Interlock Systems | T - Procurement | T | Procurement | 95.5 | [31 empty] | 19.1 | 35 | 33.4 | 8
52 - 52 - Central Instrumentation & Control | T - Procurement | T | Procurement | 100.7 | [25 empty] | 27.9 | 24.8 | 31 | 17
54 - 54 - Facility Timing & Synchronization | T - Procurement | T | Procurement | 101.3 | [28 empty] | 5.6 | 25.9 | 24.8 | 22.5 | 22.5
22 - 22 - Torus Vacuum Pumping Systems | T - Procurement | T | Procurement | 157.8 | [24 empty] | 39.9 | 34.5 | 29 | 36.3 | 18.1
44 - 44 - Control and protection Systems | T - Procurement | T | Procurement | 162.8 | [24 empty] | 5.2 | 14.7 | 12.4 | 15.5 | 14.2 | 14.5 | 13.9 | 12.9 | 21.1 | 20.2 | 11.5 | 2.8 | 2 | 1.9
55 - 55 - Real Time Plasma & Power Supply Control Sys | T - Procurement | T | Procurement | 199.4 | [30 empty] | 27.4 | 58 | 68.1 | 43.1 | 2.8
64 - 64 - PFC/VV Heating & Cooling (Bakeout) | T - Procurement | T | Procurement | 265.3 | [36 empty] | 85.7 | 81.6 | 69.4 | 28.6
18 - 18 - Field Period Assembly | T - Procurement | T | Procurement | 354.9 |  |  |  | 1.7 | 35.8 | 26.2 | 35.1 | 16.5 | 8.5 | 8.9 | 8.5 | 0.4 | 33 | 25.8 | 24.4 | 30.1 | 28.7 | 31.5 | 31.5 | 10
76 - 76 - Tooling Design & Fabrication | T - Procurement | T | Procurement | 366.6 | [27 empty] | 4.3 | 17.2 | 19.8 | 18.9 | 17.2 | 18.9 | 18.1 | 18.9 | 18.1 | 18.1 | 17.2 | 14.6 | 18.1 | 17.2 | 19.8 | 18.1 | 18.1 | 18.9 | 17.2 | 19.8 | 18.1
62 - 62 - Cryogenic Systems | T - Procurement | T | Procurement | 388.3 | [29 empty] | 5.8 | 42.5 | 38.6 | 65.7 | 62.7 | 65.7 | 60.8 | 22.2 | 21.1 | 3.2
16 - 16 - Coil Services | T - Procurement | T | Procurement | 496.2 | [12 empty] | 6.7 | 5.2 | 4.9 | 2 | [8 empty] | 81.4 | 70.2 | 58.6 | 73.2 | 73.2 | 84.2 | 36.6
17 - 17 - Cryostat and Base Support Structure | T - Procurement | T | Procurement | 779.6 |  |  |  | 0.1 | 1.1 | 1.1 | 1.1 | 1.3 | 1.6 | 5.5 | 5.2 | 5.2 | 39.7 | 31.1 | 29.4 | 36.3 | 34.5 | 38 | 28.6 | 20.1 | 10.4 | 1.7 | 1.2 | 1.1 | 1.1 | 1 | 0.8 | 1 | 18.1 | 39.9 | 38.2 | 34.7 | 38.2 | 36.4 | 39.6 | 39.5 | 39.5 | 34.2 | 23.8 | 29.4 | 28 | 32.2 | 9.8
12 - 12 - Vacuum Vessel Systems | T - Procurement | T | Procurement | 990 | 3.8 | 3.3 | 2.5 | 3.5 | 44.4 | [7 empty] | 13.9 | 10.8 | 10.2 | 4.2 | [8 empty] | 35.6 | 30.8 | 25.9 | 32.4 | 32.4 | 98.9 | 94.6 | 86 | 94.6 | 90.3 | 94.6 | 34 | 77.6 | 68.5 | 10.3
14 - 14 - Modular Coils | T - Procurement | T | Procurement | 1044.7 | 36.4 | 18.1 | 13.6 | 26.5 | 124 | 136.3 | 155.3 | 143.1 | 154.5 | 145.8 | 119.8 | 23.4 | 15.6 | 12.2 | 11.5 | 1.5 | 0.8 | 0.9
15 - 15 - Coil Structures | T - Procurement | T | Procurement | 1430.3 | [11 empty] | 160.4 | 263.4 | 266.3 | 258.6 | 319.4 | 130.5 | 31.7
13 - 13 - Conventional Coils | T - Procurement | T | Procurement | 3653.7 | 62.4 | 58.5 | 32.1 | 74.3 | 28.9 | 81.9 | 179.9 | 363.2 | 310.8 | 420.9 | 445.1 | 395 | 360.1 | 155 | 133.1 | 144.9 | 103.1 | 41.2 | 41.2 | 32.2 | 28.4 | 28.4 | 27.1 | 27.1 | 0.3 | [6 empty] | 37.8 | 43.8 | 41.8 | 57.1 | 56.5 | 56.5 | 12.4
14 - 14 - Modular Coils | R - R&D | R | R&D | 4.4 | 4.8 | 4.2 | 3.2 | 4.6 | 4.4
16 - 16 - Coil Services | R - R&D | R | R&D | 24 | [8 empty] | 5.6 | 8.8 | 8.4 | 1.2
62 - 62 - Cryogenic Systems | R - R&D | R | R&D | 104 | [15 empty] | 16.8 | 16 | 17.6 | 17.6 | 16 | 17.6 | 2.4
41 - 41 - AC Power | S - Startup/Ops | S | Fabrication/Assembly | 27.3 | [29 empty] | 2.2 | 3.1 | 2.8 | 2.8 | [6 empty] | 0.6 | 11.3 | 4.5
45 - 45 - Power System Design and Integration | S - Startup/Ops | S | Fabrication/Assembly | 195.7 | [31 empty] | 6.3 | [7 empty] | 20.1 | 10.1 |  |  |  | 15.9 | 79.6 | 63.7
44 - 44 - Control and protection Systems | S - Startup/Ops | S | Fabrication/Assembly | 227.1 | [20 empty] | 14.7 | 13.5 | 9.8 |  | 1 | 0.8 | 0.7 | 0.9 | 0.9 | 1 | 1 | 0.9 | 1 | 3.5 | 20 | 19 | 19.5 | 30.2 | 40.8 | 20.3 | 21.6 | 3.5 | 2.5
43 - 43 - DC Systems | 1 - Title I | 1 | Design | 9.3 | [22 empty] | 2.4 | 4.7 | 2.2
51 - 51 - Network and Fiber Infrastructure | 1 - Title I | 1 | Design | 21 | [24 empty] | 6.6 | 4.6 | 3.2 | 4 | 2.6
58 - 58 - Central I&C management and Integration | 1 - Title I | 1 | Design | 66.5 | 1.9 | 1.7 | 1.3 | 1.9 | 1.8 | 1.8 | 1.9 | 1.8 | 1.8 | 1.9 | 1.8 | 1.8 | 1.5 | 1.2 | 1.1 | 1.4 | 1.3 | 1.5 | 1.5 | 1.3 | 1.5 | 1.5 | 1.4 | 1.4 | 1.5 | 1.3 | 1.1 | 1.4 | 1.4 | 1.6 | 1.5 | 1.4 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.2 | 1.5 | 1.5 | 1.7 | 1.5 | 1.5 | 1.6 | 1.5 | 1.7 | 1.4
31 - 31 - Magnetic Diagnostics | 1 - Title I | 1 | Design | 76.7 |  | 7.2 | 5.4 | 9.2 | 33.3 | 23.9 | 10.6 | 2.4 |  |  |  |  | 2.6 |  | 1.8 | 2.1
15 - 15 - Coil Structures | 1 - Title I | 1 | Design | 88.9 | 33 | 28.7 | 21.5 | 30.7 | 12 | 12 | 12.6 | 20.9 | 22 | 9.4
53 - 53 - Data Acquisition & Facility Computing | 1 - Title I | 1 | Design | 107.5 | [22 empty] | 3.9 | 6.2 | 6.8 |  |  |  |  | 12.7 | 12.5 | 10.6 | 11.6 | 7.4 | 2.8 | 8.3 | 8.3 | 6.3 | 3.7 | 4.6 | 1.8
56 - 56 - Central Safety and Interlock Systems | 1 - Title I | 1 | Design | 117.2 | [22 empty] | 3.9 | 6.8 | 9.4 | 15 | 13.9 | 10.9 | 10.9 | 12.5 | 4.4 |  |  |  | 5 | 6.2 | 6.2 | 5.9 | 5 | 1.2
54 - 54 - Facility Timing & Synchronization | 1 - Title I | 1 | Design | 119.1 | [25 empty] | 7.2 | 7.1 | 11.8 | 13.5 | 22.1 | 24.4 | 3.8 | 4.2 | 4 | 4.2 | 4 | 7.6 | 5.2
44 - 44 - Control and protection Systems | 1 - Title I | 1 | Design | 120.3 | [7 empty] | 1.5 | 1.5 | 1.6 | 1.5 | 1.5 | 3.7 | 3 | 2.6 | 7.4 | 7.1 | 7 | 2.1 | 1.9 | 2.1 | 2.1 | 2 | 2 | 8.3 | 7.1 | 6 | 6.2 | 5.6 | 6.4 | 6.1 | 5.6 | 6.1 | 5.9 | 6.1 | 0.3
14 - 14 - Modular Coils | 1 - Title I | 1 | Design | 132.8 | 8 | 10.1 | 4.6 | 17.1 | 36.6 | 42.2 | 43.9 | 10.1
21 - 21 - Fueling Systems | 1 - Title I | 1 | Design | 161.4 | [17 empty] | 20.3 | 23.2 | 57.5 | 60.4
52 - 52 - Central Instrumentation & Control | 1 - Title I | 1 | Design | 173.3 | [22 empty] | 10.3 | 9.4 | 9.8 | 18.1 | 15.7 | 17.7 | 21.4 | 21.7 | 11.5 | 9.3 | 10.2 | 7.1 | 5.3 | 5.1 | 0.7
55 - 55 - Real Time Plasma & Power Supply Control Sys | 1 - Title I | 1 | Design | 180.8 | [24 empty] | 23 | 17.5 | 13.3 | 16.6 | 10.8 |  |  |  |  | 6.1 | 18.2 | 18.2 | 18.2 | 17.3 | 14.7 | 6.8 | 0.1
16 - 16 - Coil Services | 1 - Title I | 1 | Design | 185.6 | 4.7 | 4.1 | 12.7 | 18.9 | 25.2 | 25.2 | 26.4 | 25.2 | 21.2 | 14 | 16.8 |  | 11.2 | 8.7 | 8.3 | 3.4
12 - 12 - Vacuum Vessel Systems | 1 - Title I | 1 | Design | 223 | [8 empty] | 0.5 | 10.2 | 9.8 | 9.8 | 35.2 | 27.6 | 26 | 10.7 | 14.3 | 15.8 | 15.8 | 14.3 | 15.8 | 15.8 | 1.4
22 - 22 - Torus Vacuum Pumping Systems | 1 - Title I | 1 | Design | 274.5 | [12 empty] | 35.2 | 27.5 | 26 | 32.1 | 33.8 | 40.6 | 40.6 | 36.9 | 1.8
13 - 13 - Conventional Coils | 1 - Title I | 1 | Design | 296.2 |  |  | 5.5 | 30.8 | 51.1 | 58.1 | 86.9 | 58.7 | 22.7 | 12.7 | 6
62 - 62 - Cryogenic Systems | 1 - Title I | 1 | Design | 639.6 | [8 empty] | 14.1 | 21.6 | 20.6 | 20.6 | 22.5 | 17.6 | 16.7 | 38.7 | 36.9 | 40.5 | 40.5 | 53.7 | 65.3 | 28.2 | 21.3 | 21.3 | 24.6 | 33.4 | 28.1 | 29.8 | 27 | 16.6
18 - 18 - Field Period Assembly | 1 - Title I | 1 | Design | 672.4 | 5.4 | 4.7 | 7.6 | 1.9 | 142.7 | 61.7 | 76.8 | 91.8 | 127.5 | 96.1 | 25.8 | 24.3 | 11.7 |  |  | 9.3 | 4.7
17 - 17 - Cryostat and Base Support Structure | 1 - Title I | 1 | Design | 717 | 25.5 | 22.1 | 16.6 | 27 | 46.7 | 41.1 | 43.1 | 8.4 |  | 20.9 | 19.9 | 19.9 | 21.8 | 17.1 | 16.1 | 42.5 | 40.5 | 44.6 | 44.6 | 40.5 | 44.6 | 31.6 | 28.2 | 28.2 | 29.5 | 25.5 | 21.5 | 26.8 | 13.4
36 - 36 - Edge and Divertor Diagnostics | 2 - Title II | 2 | Design | 13.3 | [24 empty] | 7.3 | 6
14 - 14 - Modular Coils | 2 - Title II | 2 | Design | 33.5 | 46.5 | 36 | 30 | 43.2 | 26 | [16 empty] | 5.5 | 2
63 - 63 - Utility Systems | 2 - Title II | 2 | Design | 34.8 | [36 empty] | 20.9 | 13.9
61 - 61 - Water Systems | 2 - Title II | 2 | Design | 39.9 | [31 empty] | 17.7 | 19.5 | 2.7
41 - 41 - AC Power | 2 - Title II | 2 | Design | 49.9 | [15 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 4.3 | 4.8 | 4.8 | 4.7 | 4.7 | 4.4 | 4.9 | 4.1 | 1.7 | 1.3 | 1.5 | 1.4 | 1.2 | 1.3 | 1.2 | 1.3 | 0.3
13 - 13 - Conventional Coils | 2 - Title II | 2 | Design | 90.9 | 19.3 | 16.7 | 28.1 | 28 | 78.4 | 5.8 | 6.1 | 0.6
39 - 39 - Diagnostics Integration | 2 - Title II | 2 | Design | 111.6 | 2.6 | 2.3 | 1.7 | 2.5 | 2.4 | 2.4 | 2.5 | 2.4 | 2.4 | 2.5 | 2.4 | 2.3 | 2.8 | 2.2 | 2 | 2.5 | 2.4 | 2.6 | 2.6 | 2.4 | 2.6 | 2.6 | 2.5 | 2.3 | 2.7 | 2.4 | 2 | 2.5 | 2.5 | 2.9 | 2.7 | 2.5 | 2.7 | 2.6 | 2.7 | 2.4 | 2.7 | 2.6 | 2.2 | 2.7 | 2.6 | 3 | 2.7 | 2.7 | 2.9 | 2.6 | 3 | 2.5
64 - 64 - PFC/VV Heating & Cooling (Bakeout) | 2 - Title II | 2 | Design | 157.9 | [24 empty] | 8.5 | 8.2 | 20.7 | 25.9 | 21.9 | 27.2 | 31.2 | 14.3
38 - 38 - Electron Beam (EB) Mapping | 2 - Title II | 2 | Design | 171 | [17 empty] | 36.5 | 37.7 | 52.3 | 44.5
44 - 44 - Control and protection Systems | 2 - Title II | 2 | Design | 171.6 | [9 empty] | 8.3 | 7.9 | 7.9 | 8.6 |  |  |  |  | 4.9 | 4.9 | 4.4 | 7 | 7 | 6.7 | 4 | 13.8 | 14.3 | 12 | 12.5 | 10.8 | 12.4 | 11.8 | 10.8 | 1.6
16 - 16 - Coil Services | 2 - Title II | 2 | Design | 200.5 | [8 empty] | 15.2 | 23.9 | 22.8 | 36.1 | 19.7 | 15.4 | 14.6 | 18 | 17.2 | 17.6
45 - 45 - Power System Design and Integration | 2 - Title II | 2 | Design | 403.1 | [9 empty] | 18.7 | 18 | 13.5 | 9.3 | 7.3 | 6.9 | 8.5 | 8.1 | 14.9 | 14.5 | 10.5 | 10.4 | 10.4 | 9.9 | 9.9 | 22.3 | 17.5 | 7 | 7.3 | 7.3 | 27.8 | 25.3 | 12.6 | 11.8 | 7.7 | 8.1 | 7.7 | 13.6 | 12.9 | 11 | 13.6 | 10.4 | 8.4
18 - 18 - Field Period Assembly | 2 - Title II | 2 | Design | 408.7 | 21.3 | 18.6 | 13.9 | 19.6 | 41.5 | 39.7 | 55.9 | 61.6 | 51.5 | 50.7 | 40.2 | 43.8 | 23.8