## P3
rebaseline | WBS4 | DESC | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | TOTAL |  |  |  | 41 rebaseline | WBS4 | ACT ID | DESC | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | TOTAL
1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | Oversight and Supervision | 841 | 1092 | 1022 |  |  | 2955 |  | 1342.44 | 1486 | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | A | Oversight and Supervision | 35 | 46 | 45 |  |  | 126 |  | 126
[8 empty] | 123 | cv
[12 empty] | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General Assy Support | S0P0 | General Assy Support | 51 | 52 | 47 |  |  | 150 |  | 45.25 | 63.14
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General Assy Support | General Assy Support | 800 | 683 | 908 |  |  | 1966 | -578.4 |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | S1P1 | Station 1-VV Prep (hard surface components) FP#1 | 14 |  |  |  |  | 14 |  | 14
| metrology crews | [10 empty] | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | S1P2 | Station 1- VV Prep (hrd surf cmpntsFP#2 | 4 |  |  |  |  | 4 |  | 2.69
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | Station 1-VV Prep (hard surface components) FP#1 | 207 |  |  |  |  | 207 | 171.75 |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | S1P3 | Station 1- VV Prep (hrd surf cmpntsFP#3 | 1 |  |  |  |  | 1 |  | 0.2
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | Station 1- VV Prep (hrd surf cmpntsFP#2 | 130 |  |  |  |  | 130 | 64.6 |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | S1SP | Station 1-Spool pieces (3) (spacers) |  | 1 |  |  |  | 1 |  | 1
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | Station 1- VV Prep (hrd surf cmpntsFP#3 | 118 | 37 |  |  |  | 154 | 87.59
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | Station 1-Spool pieces (3) (spacers) |  | 111 |  |  |  | 111 | 79.67 |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | S2PR | Station 2 Trials & Development | 22 |  |  |  |  | 22 | 1342 | 1254.54
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | Station 2 Trials & Development | 48 |  |  |  |  | 48 | -121.82 |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PX - Setup | S2PX | Setup | 1064 | 256 |  |  |  | 1320
[12 empty] | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | S2PM | Pre-Measuring and fitup checks
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PX - Setup | Setup | 1333 | 256 |  |  |  | 1589 |  | 1575.34 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H1 - Station 2 MC subassy A1B1C1 | S2H1 | Station 2 MC subassy A1B1C1
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | Pre-Measuring and fitup checks | 624 | 10 |  |  |  | 375 |  | 225.9 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H2 - Station 2 MC subassy A2B2C2 | S2H2 | Station 2 MC subassy A2B2C2
[12 empty] | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H3 - Station 2 MC subassy A3B3C3 | S2H3 | Station 2 MC subassy A3B3C3
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H1 - Station 2 MC subassy A1B1C1 | Station 2 MC subassy A1B1C1 | 388 | 32 |  |  |  | 251 |  | 325.76 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H4 - Station 2 MC subassy A4B4C4 | S2H4 | Station 2 MC subassy A4B4C4
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H2 - Station 2 MC subassy A2B2C2 | Station 2 MC subassy A2B2C2 | 265 | 52 |  |  |  | 185 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H5 - Station 2 MC subassy A5B5C5 | S2H5 | Station 2 MC subassy A5B5C5
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H3 - Station 2 MC subassy A3B3C3 | Station 2 MC subassy A3B3C3 | 151 | 171 |  |  |  | 188 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H6 - Station 2 MC subassy A6B6C6 | S2H6 | Station 2 MC subassy A6B6C6
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H4 - Station 2 MC subassy A4B4C4 | Station 2 MC subassy A4B4C4 |  | 310 |  |  |  | 174
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H5 - Station 2 MC subassy A5B5C5 | Station 2 MC subassy A5B5C5 |  | 310 |  |  |  | 174 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | S3P0 | Station 3 Setup/Preparations/General | 56 | 185 | 67 |  |  | 308 | 343 | 173.37
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2H6 - Station 2 MC subassy A6B6C6 | Station 2 MC subassy A6B6C6 |  | 303 | 7 |  |  | 174 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | S3P1 | Station 3-Assemble Mod Coils and VVSA-FP#1 |  | 14 |  |  |  | 14
[9 empty] | 0 |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | S3P2 | Station 3-Assemble Mod Coils and VVSA-FP#2 |  | 8 | 1 |  |  | 9 |  |  | 1427.91
[9 empty] | 0 |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | S3P3 | Station 3-Assemble Mod Coils and VVSA-FP#3 |  |  | 12 |  |  | 12
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | Station 3 Setup/Preparations/General | 256 | 342 | 67 |  |  | 596 | 414.84 | 743.18
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | Station 3-Assemble Mod Coils and VVSA-FP#1 |  | 498 |  |  |  | 312 | 145.15 |  |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | S4P0 | Setup/Preparations/General |  | 265 | 71 |  |  | 336 | 501 | 349.6
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | Station 3-Assemble Mod Coils and VVSA-FP#2 |  | 276 | 140 |  |  | 260 | 88.92 |  |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | S4P1 | Station 5- Final FP Assy -FP#1 (in NCSX TC) |  | 24 | 38 |  |  | 61
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | Station 3-Assemble Mod Coils and VVSA-FP#3 |  | 22 | 404 |  |  | 267 | 94.27 |  |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | S4P2 | Station 5- Final FP Assy -FP#2 (in NCSX TC) |  |  | 52 |  |  | 52
[12 empty] | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | S4P3 | Station 5- Final FP Assy -FP#3 (in NCSX TC) |  |  | 52 |  |  | 52
[21 empty] | 2482 |  | 1840.65
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | Setup/Preparations/General |  | 350 | 89 |  |  | 438 | 214.82 | 1052.46 | 1426
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | Station 5- Final FP Assy -FP#1 (in NCSX TC) |  | 305 | 559 |  |  | 725 | 362.18
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | Station 5- Final FP Assy -FP#2 (in NCSX TC) |  |  | 729 |  |  | 612 | 239 |  |  | lehman 41 | WBS4 | ACT ID | DESC | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | TOTAL
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | Station 5- Final FP Assy -FP#3 (in NCSX TC) |  |  | 729 |  |  | 612 | 236.46 |  |  | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | A | Oversight and Supervision
|  |  | 5161 | 5160 | 4654 | 0 | 0 | 12626 | 12626
[10 empty] | 5265.08 | 7687 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General Assy Support | S0P0 | General Assy Support | 47.09 | 51.1 | 6.57 |  |  | 104.75
[12 empty] | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | S1P1 | Station 1-VV Prep (hard surface components) FP#1
lehman | WBS4 | DESC | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | TOTAL |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | S1P2 | Station 1- VV Prep (hrd surf cmpntsFP#2 | 1.31 |  |  |  |  | 1.31
1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | Oversight and Supervision | 789.76 | 857.93 | 87.88 |  |  | 1735.56 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | S1P3 | Station 1- VV Prep (hrd surf cmpntsFP#3 | 0.8 |  |  |  |  | 0.8
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General Assy Support | General Assy Support | 1229.89 | 1149.69 | 164.82 |  |  | 2544.4 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | S1SP | Station 1-Spool pieces (3) (spacers)
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | Station 1-VV Prep (hard surface components) FP#1 | 35.25 |  |  |  |  | 35.25 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | S2PR | Station 2 Trials & Development | 61.44 | 26.02 |  |  |  | 87.46
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | Station 1- VV Prep (hrd surf cmpntsFP#2 | 65.4 |  |  |  |  | 65.4 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PX - Setup | S2PX | Setup
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | Station 1- VV Prep (hrd surf cmpntsFP#3 | 66.41 |  |  |  |  | 66.41 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | S2PM | Pre-Measuring and fitup checks
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | Station 1-Spool pieces (3) (spacers) |  | 31.33 |  |  |  | 31.33 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P1 - Station 2-MC Sub Assy A1-B1-C1 | S2P1 | Station 2-MC Sub Assy A1-B1-C1
[12 empty] | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PZ - Station 2 MC Sub Assy A2-B2-C2 | S2PZ | Station 2 MC Sub Assy A2-B2-C2
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PX - Setup | Setup | 13.66 |  |  |  |  | 13.66 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P2 - Station 2-Modular Coil Subassembly-FP#2 | S2P2 | Station 2-Modular Coil Subassembly-FP#2
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | Pre-Measuring and fitup checks | 118.62 | 30.47 |  |  |  | 149.1 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P3 - Station 2-Modular Coil Subassembly-FP#3 | S2P3 | Station 2-Modular Coil Subassembly-FP#3
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | Station 2 Trials & Development | 131.42 | 38.4 |  |  |  | 169.82
[12 empty] | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | S3P0 | Station 3 Setup/Preparations/General | 149.11 |  |  |  |  | 149.11 | 169.63
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P1 - Station 2-MC Sub Assy A1-B1-C1 | Station 2-MC Sub Assy A1-B1-C1 | 159.82 |  |  |  |  | 159.82 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | S3P1 | Station 3-Assemble Mod Coils and VVSA-FP#1 | 6.54 |  |  |  |  | 6.54
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PZ - Station 2 MC Sub Assy A2-B2-C2 | Station 2 MC Sub Assy A2-B2-C2 | 95.33 |  |  |  |  | 95.33 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | S3P2 | Station 3-Assemble Mod Coils and VVSA-FP#2 |  | 6.99 |  |  |  | 6.99
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P2 - Station 2-Modular Coil Subassembly-FP#2 | Station 2-Modular Coil Subassembly-FP#2 | 190.5 | 89.28 |  |  |  | 279.78 |  |  |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | S3P3 | Station 3-Assemble Mod Coils and VVSA-FP#3 |  | 6.99 |  |  |  | 6.99
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P3 - Station 2-Modular Coil Subassembly-FP#3 | Station 2-Modular Coil Subassembly-FP#3 |  | 285.31 |  |  |  | 285.31
[12 empty] | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | S4P0 | Setup/Preparations/General | 151.4 |  |  |  |  | 151.4
[12 empty] | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | S4P1 | Station 5- Final FP Assy -FP#1 (in NCSX TC)
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | Station 3 Setup/Preparations/General | 181.16 |  |  |  |  | 181.16 |  |  |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | S4P2 | Station 5- Final FP Assy -FP#2 (in NCSX TC)
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | Station 3-Assemble Mod Coils and VVSA-FP#1 | 135.63 | 31.22 |  |  |  | 166.85 |  |  |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | S4P3 | Station 5- Final FP Assy -FP#3 (in NCSX TC)
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | Station 3-Assemble Mod Coils and VVSA-FP#2 |  | 171.08 |  |  |  | 171.08 | [12 empty] | 515.35
1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | Station 3-Assemble Mod Coils and VVSA-FP#3 |  | 172.73 |  |  |  | 172.73
1966.65
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | Setup/Preparations/General | 223.18 |  |  |  |  | 223.18
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | Station 5- Final FP Assy -FP#1 (in NCSX TC) |  | 362.82 |  |  |  | 362.82
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | Station 5- Final FP Assy -FP#2 (in NCSX TC) |  | 364.47 | 8.53 |  |  | 373
1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | Station 5- Final FP Assy -FP#3 (in NCSX TC) |  | 289.77 | 85.77 |  |  | 375.54
|  |  | 3436.03 | 3874.5 | 347 | 0 | 0 | 7657.53
FPA rebaseline re-conciliation
[8 empty] | Jobs 1802,1810,1815 | EAC from 5/1/07
[9 empty] | Lehman 20078 | Rebaseline 2008 | increase |  |  | SUMMARY
[8 empty] | 1802 | 1989 | 4346 | 2357 |  |  | COST GROWTH RECONCILIATION (incl 30% contingency)
[8 empty] | 1810 | 5745 | 8605 | 2860
[8 empty] | 1815 | 1334 | 1888 | 554 |  |  | 12 month stretchout |  |  |  | 4400 |  | 5720
[8 empty] | total | 9068 | 14839 | 5771 |  |  |  | wbs 18,81,82,89,19 |  |  |  |  | 0
[9 empty] | M&S (see supplemental detail) | [10 empty] | 0
[10 empty] | misc daily cost for tools,parts,hardwaremsupplies | 388 | 388 |  | Scope Add-backs |  |  |  | 4564 |  | 5933.2
[10 empty] | weld engr | 208 | 208 |  |  | Trim coils |  |  |  |  | 0
[10 empty] | other | 206 | 206
[10 empty] | laser tracker | 161 | 161
[10 empty] | additional wedges | 148 | 148 |  |  | Hetare control sys |  |  |  |  | 0
[10 empty] | Photogramtry targets | 89 | 89 |  |  | VPS,NB ducts,water sys |  |  |  |  | 0
[10 empty] | gantry crane & electr torque wrench | 49 | 49
[9 empty] | metrology crews |  | 1268.1 | 1268.1 | [7 empty] | 0
[9 empty] | Station 5 task estimate growth incl revised assy sequence AND trim coils |  | 139 | 720 |  | Field period assy (WBS 18 excl strecthout) |  |  |  | 6916 |  | 8990.8 | 8116
[9 empty] | Station 3 task estimate growth |  | 367 | 570 | [7 empty] | 0
[9 empty] | PU Title III field ineering support (Sands) |  | 488 | 419 | [7 empty] | 0
[9 empty] | PPPL Title III Integrated design support (Brown) |  | 681 |  |  | Final Machine Assy (WBS 7 excl stretchout) |  |  |  | 1200 |  | 1560
0
[9 empty] | station 1 heater tape,terminations, spools pieces |  | 397 | 397 | [7 empty] | 0
[9 empty] | Support crews & field supervision stretchout |  | 270 | 330 |  | Management wbs 81 | [5 empty] | 0
[9 empty] | Station 2 task estimate growth |  | 318 | 326 |  |  | PPPL |  |  | 1230 |  | 1599
[9 empty] | HP coverage (stretchout plus station now at d-site) |  | 408 | 408 |  |  | ORNL |  |  | 1713 |  | 2226.9
[9 empty] | Pre-measurement of coils, drill stycast holes,verify mating of coils |  | 248 | 248 | [7 empty] | 0
[9 empty] | Viola oversight stretchout |  | 145 | 200 | [7 empty] | 0
[9 empty] | Metrology engineer stretchout |  | 92 | 100 |  | Constructability design (title III during assy job 1803)) |  |  |  | 1547 |  | 2011.1
[9 empty] | Drexel co-op |  | 67 | 67 | [7 empty] | 0
[9 empty] | other/misc |  |  | 491 | [7 empty] | 0
[11 empty] | 6137.1 | 6793.1 |  | Other |  |  |  | 1243 |  | 956.1538
0
[8 empty] | WBS 81 | [8 empty] | subtotal = | 22813 |  | #REF!
[9 empty] | neilson,rej,strykowsky,hampton | stretchout | 1456
[9 empty] | neilson,rej,strykowsky,hampton | growth | 422
[9 empty] | ornl harris et el | stretchout | 560
[9 empty] | ornl harris et el | growth | 477
[8 empty] | WBS 82 | 82