## P3
Engineer,Designer, Metrology crews and ORNL Loading Profile
|  |  | HOD/PDG | Name |  | Job |  | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09 | OCT FY10 | NOV FY10 | DEC FY10 | JAN FY10 | FEB FY10 | MAR FY10 | APR FY10 | MAY FY10 | JUN FY10 | JUL FY10 | AUG FY10 | SEP FY10 | OCT FY11 | NOV FY11 | DEC FY11 | JAN FY11 | FEB FY11 | MAR FY11 | APR FY11 | MAY FY11 | JUN FY11 | JUL FY11 | AUG FY11 | SEP FY11 | OCT FY12 | NOV FY12 | DEC FY12 | JAN FY12
| subtotal | = | EA//DM | CRUIKSHANK | Cruikshank | Job: 1501 - Coil Structures Design-DAHLGREN | 0.78 | 0.17 | 0.17 | 0.18 | 0.17 | 0.09
| subtotal | = | EA//DM | CRUIKSHANK | Cruikshank | Job: 1353 - CS Structure Procurement-PERRY | 0.93 |  |  | 0.93
| subtotal | = | EA//DM | CRUIKSHANK | Cruikshank | Job: 1354 - Trim Coil Design &Procurement-KALISH | 1.92 | 0.45 | 0.89 | 0.58
| subtotal | = | EA//DM | CRUIKSHANK | Cruikshank | Job: 1702 - Base Support Struct Design-DAHLGREN | 2.96 | 0.96 | 0.9 | 0.94 | 0.16
| subtotal | = |  |  |  | CRUIKSHANK subtotal = | 6.59 | 1.58 | 1.96 | 2.63 | 0.33 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//DM | RUSHINSKI | Rushinski | Job: 1501 - Coil Structures Design-DAHLGREN | 1.54 | 0.17 | 0.17 | 0.18 | 0.68 | 0.34
| subtotal | = | EA//DM | RUSHINSKI | Rushinski | Job: 1354 - Trim Coil Design &Procurement-KALISH | 2.7 | 0.45 | 1 | 0.61 | 0.08 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.02
| subtotal | = |  |  |  | RUSHINSKI subtotal = | 4.24 | 0.62 | 1.17 | 0.79 | 0.76 | 0.4 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//DM | SIEGEL | Siegel | Job: 5101 - Network and Fiber | 1.87 | [20 empty] | 0.1 | 0.06 | 0.04 | 0.04 | 0.03 | [6 empty] | 0.26 | 0.42 | 0.4 | 0.34 | 0.18
| subtotal | = | EA//DM | SIEGEL | Siegel | Job: 1270 - Heater Control System-PPPL ( tbd) | 2.27 | [12 empty] | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.03 | [6 empty] | 0.03 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03 | [6 empty] | 0.05 | 0.09 | 0.09 | 0.04
| subtotal | = | EA//DM | SIEGEL | Siegel | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 2.67 | [19 empty] | 0.07 | 0.13 | 0.07 | 0.09 | 0.2 | 0.2 | 0.23 | 0.08 |  |  |  | 0.27 | 0.34 | 0.34 | 0.32 | 0.27 | 0.06
| subtotal | = |  |  |  | SIEGEL subtotal = | 6.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.03 | 0.07 | 0.23 | 0.13 | 0.13 | 0.24 | 0.23 | 0.26 | 0.11 | 0.02 | 0.03 | 0.03 | 0.3 | 0.6 | 0.76 | 0.72 | 0.61 | 0.24 | 0 | 0.05 | 0.09 | 0.09 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//DM | UPCAVAGE | Upcavage | Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | 0.8 | [24 empty] | 0.04 | 0.09 | 0.09 | 0.08 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.05
| subtotal | = | EA//DM | UPCAVAGE | Upcavage | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1.41 |  |  |  | 0.28 | 0.28 | 0.29 | 0.28 | 0.28
| subtotal | = | EA//DM | UPCAVAGE | Upcavage | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 1.61 | 1.07 | 0.27 |  |  |  | 0.27
| subtotal | = | EA//DM | UPCAVAGE | Upcavage | Job: 8215 Plant Design | 7.22 | 0.69 | 0.19 | 0.2 | 0.19 | 0.19 | 0.2 | 0.19 | 0.19 | 0.2 | 0.16 | 0.15 | 0.19 | 0.18 | 0.2 | 0.2 | 0.18 | 0.2 | 0.2 | 0.19 | 0.19 | 0.2 | 0.17 | 0.14 | 0.18 | 0.18 | 0.2 | 0.2 | 0.18 | 0.2 | 0.19 | 0.2 | 0.19 | 0.19 | 0.18 | 0.15 | 0.19
| subtotal | = | EA//DM | UPCAVAGE | Upcavage | Job: 1701 - Cryostat Design-RAFTOPOLOUS | 8.65 | [5 empty] | 0.32 | 0.3 | 0.3 | 0.33 | 0.26 | 0.25 | 0.66 | 0.63 | 0.69 | 0.69 | 0.63 | 0.69 | 0.45 | 0.4 | 0.4 | 0.42 | 0.36 | 0.3 | 0.38 | 0.19
| subtotal | = | EA//DM | UPCAVAGE | Upcavage | Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 10.04 |  |  |  |  | 0.13 | 0.14 | 0.13 | 0.13 | 0.15 | 0.11 | 0.11 | 0.69 | 0.65 | 0.72 | 0.72 | 0.65 | 0.72 | 0.53 | 0.47 | 0.47 | 0.55 | 0.75 | 0.64 | 0.67 | 0.61 | 0.3
| subtotal | = | EA//DM | UPCAVAGE | Upcavage | Job: 8203 - Design Integration-BROWN | 15.2 | 0.13 | 0.13 | 1.18 | 1.17 | 0.65 | 0.71 | 0.16 | 0.13 | 0.51 | 0.4 | 0.37 | 0.46 | 0.44 | 0.48 | 0.48 | 0.44 | 0.48 | 0.48 | 0.46 | 0.46 | 0.49 | 0.42 | 0.35 | 0.44 | 0.44 | 0.51 | 0.49 | 0.44 | 0.49 | 0.46 | 0.49 | 0.46
| subtotal | = |  |  |  | UPCAVAGE subtotal = | 44.93 | 1.89 | 0.59 | 1.38 | 1.64 | 1.25 | 1.93 | 1.06 | 1.03 | 1.19 | 0.93 | 0.88 | 2 | 1.9 | 2.09 | 2.09 | 1.9 | 2.09 | 1.66 | 1.52 | 1.52 | 1.66 | 1.7 | 1.43 | 1.67 | 1.46 | 1.1 | 0.78 | 0.7 | 0.78 | 0.74 | 0.78 | 0.74 | 0.28 | 0.23 | 0.15 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//SB | JONES | Jones | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0.53 | [20 empty] | 0.29 | 0.24
| subtotal | = | EA//SB | JONES | Jones | Job: 3801 - Electron Beam Mapping-STRATTON | 1.31 | [13 empty] | 0.36 | 0.34 | 0.33 | 0.28
| subtotal | = | EA//SB | JONES | Jones | Job: 4101 - AC Power-RAMAKRISHNAN | 1.84 | [11 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.14 | 0.15 | 0.15 | 0.15 | 0.15 | 0.14 | 0.12 | 0.1 | 0.03 | 0.03 | 0.01 | [7 empty] | 0.05 | 0.15 | 0.18 | 0.18 | 0.07
| subtotal | = | EA//SB | JONES | Jones | Job: 3101 - Magnetic Diagnostics-STRATTON | 2.57 | 0.71 | 0.71 | 0.1 | 0.02 |  |  |  |  | 0.54 | 0.21 | 0.2 | 0.08
| subtotal | = | EA//SB | JONES | Jones | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 6.25 | [5 empty] | 0.09 | 0.45 | 0.32 | 0.19 | 0.15 | 0.14 | 0.18 | 0.17 | 0.18 | 0.18 | 0.09 | 0.07 | 0.07 | 0.06 | 0.06 | 0.6 | 0.47 | 0.05 |  |  | 0.61 | 0.46 | 0.03 | 0.05 | 0.09 | 0.09 | 0.09 | 0.34 | 0.32 | 0.27 | 0.25 | 0.13
| subtotal | = |  |  |  | JONES subtotal = | 12.5 | 0.71 | 0.71 | 0.1 | 0.02 | 0 | 0.09 | 0.45 | 0.32 | 0.73 | 0.36 | 0.34 | 0.27 | 0.18 | 0.55 | 0.53 | 0.56 | 0.5 | 0.22 | 0.21 | 0.21 | 1.03 | 0.83 | 0.15 | 0.03 | 0.03 | 0.62 | 0.46 | 0.03 | 0.05 | 0.09 | 0.09 | 0.09 | 0.34 | 0.37 | 0.42 | 0.43 | 0.31 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//SB | MORRIS | Morris Lew | Job: 6301 - Utility Systems-DUDEK | 1.06 | [32 empty] | 0.53 | 0.53
| subtotal | = | EA//SB | MORRIS | Morris Lew | Job: 6101 - Water Systems-DUDEK | 1.33 | [27 empty] | 0.59 | 0.65 | 0.09
| subtotal | = | EA//SB | MORRIS | Morris Lew | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 2.31 | [32 empty] | 0.03 | 0.17 | 0.14 | 0.18 | 0.17 | 0.2 | 0.18 | 0.18 | 0.19 | 0.17 | 0.2 | 0.18 | 0.18 | 0.14
| subtotal | = | EA//SB | MORRIS | Morris Lew | Job: 1802 - FP Assy Oversight&Support-VIOLA | 4.54 | [8 empty] | 0.21 | 0.16 | 0.15 | 0.19 | 0.18 | 0.2 | 0.2 | 0.18 | 0.2 | 0.2 | 0.19 | 0.19 | 0.2 | 0.18 | 0.15 | 0.19 | 0.19 | 0.21 | 0.2 | 0.19 | 0.2 | 0.19 | 0.2 | 0.19
| subtotal | = | EA//SB | MORRIS | Morris Lew | Job: 7503 - Machine Assembly (station 6)-PERRY | 6.58 | [26 empty] | 0.03 | 1.54 | 0.24 | 0.24 | 0.56 | 0.21 | 0.03 | 0.11 | [7 empty] | 0.11 | 0.32 | 1.25 | 1.07 | 0.87
| subtotal | = | EA//SB | MORRIS | Morris Lew | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 9.41 | 1.27 | 1.26 | 1.02 | 1.05 | 1.45 | 0.66 | 0.87 | 0.99 | 0.57 |  |  | 0.18 | 0.09
| subtotal | = | EA//SB | MORRIS | Morris Lew | Job: 8203 - Design Integration-BROWN | 30 | 0.24 | 0.24 | 0.25 | 0.24 | 0.24 | 0.25 | 0.24 | 0.24 | 0.81 | 0.64 | 0.6 | 0.74 | 0.71 | 0.78 | 0.78 | 0.71 | 0.78 | 0.78 | 0.74 | 0.74 | 0.78 | 0.67 | 0.57 | 0.71 | 0.71 | 0.82 | 0.78 | 0.71 | 0.78 | 0.74 | 0.78 | 0.74 | 0.74 | 0.7 | 0.6 | 0.74 | 0.7 | 0.81 | 0.74 | 0.74 | 0.77 | 0.7 | 0.81 | 0.74 | 0.7 | 0.67 | 0.3
| subtotal | = |  |  |  | MORRIS subtotal = | 55.23 | 1.51 | 1.5 | 1.27 | 1.29 | 1.69 | 0.91 | 1.11 | 1.23 | 1.59 | 0.8 | 0.75 | 1.11 | 0.98 | 0.98 | 0.98 | 0.89 | 0.98 | 0.98 | 0.93 | 0.93 | 0.98 | 0.85 | 0.72 | 0.9 | 0.9 | 1.03 | 1.01 | 3.03 | 1.87 | 1.26 | 1.54 | 1.14 | 1.33 | 1.51 | 0.74 | 0.92 | 0.87 | 1.01 | 0.92 | 0.92 | 0.96 | 0.98 | 1.33 | 2.17 | 1.95 | 1.68 | 0.3 | 0
| subtotal | = | EA//SB | NELSON | Nelson | Job: 4301 - DC Systems-RAMAKRISHNAN | 0.06 | [18 empty] | 0 | 0.06
| subtotal | = | EA//SB | NELSON | Nelson | Job: 4101 - AC Power-RAMAKRISHNAN | 0.07 | [18 empty] | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//SB | NELSON | Nelson | Job: 5401 - Facility Timing & | 0.66 | [21 empty] | 0.08 | 0.08 | 0.13 | 0.1 | [5 empty] | 0.01 | 0.06 | 0.06 | 0.06 | 0.05 | 0.03
| subtotal | = | EA//SB | NELSON | Nelson | Job: 5501 - Real Time Control | 0.96 | [20 empty] | 0.39 | 0.19 | 0.07 | 0.09 | 0.06 | [5 empty] | 0.02 | 0.03 | 0.03 | 0.03 | 0.02 | 0.03 | 0
| subtotal | = | EA//SB | NELSON | Nelson | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 1.87 | [21 empty] | 0.02 | 0.32 | 0.4 | 0.06 | 0.24 | 0.59 | 0.24
| subtotal | = | EA//SB | NELSON | Nelson | Job: 5201 - I&C Systems-SICHTA | 2.13 | [30 empty] | 0.05 | 0.5 | 0.5 | 0.47 | 0.4 | 0.21
| subtotal | = |  |  |  | NELSON subtotal = | 5.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0.4 | 0.3 | 0.48 | 0.63 | 0.23 | 0.25 | 0.6 | 0.24 | 0 | 0 | 0.08 | 0.59 | 0.59 | 0.56 | 0.47 | 0.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//SB | PAUL | Paul | Job: 1302 - PF Design -CHRZANOWSKI | 0.65 | 0.65
| subtotal | = |  |  |  | PAUL subtotal = | 0.65 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//SB | VANKIRK | vanKirk | Job: 2101 - Fueling Systems-BLANCHARD | 1.57 | [13 empty] | 0.08 | 0.11 | 0.67 | 0.71
| subtotal | = | EA//SB | VANKIRK | vanKirk | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 3.41 | [8 empty] | 0.33 | 0.26 | 0.25 | 0.3 | 0.47 | 0.61 | 0.61 | 0.55 | 0.03
| subtotal | = | EA//SB | VANKIRK | vanKirk | Job: 4401 - Control & Protection-RAMAKRISHNAN | 4.49 | [5 empty] | 0.07 | 0.06 | 0.06 | 0.09 | 0.02 | 0.01 | 0.02 | 0.02 | 0.14 | 0.14 | 0.13 | 0.21 | 0.32 | 0.28 | 0.12 | 0.08 | 0.07 | 0.06 | 0.07 | 0.18 | 0.21 | 0.06 | 0.05 | 0.04 | 0.05 | 0.13 | 0.21 | 0.38 | 0.37 | 0.33 | 0.4 | 0.11
| subtotal | = | EA//SB | VANKIRK | vanKirk | Job: 4301 - DC Systems-RAMAKRISHNAN | 5.05 |  |  |  | 0.09 | 0.11 | 0.12 | 0.11 | 0.11 | 0.1 | 0.08 | 0.08 | 0.09 | 0.21 | 0.24 | 0.24 | 0.21 | 0.24 | 0.24 | 0.22 | 0.22 | 0.17 | 0.15 | 0.12 | 0.15 | 0.2 | 0.33 | 0.31 | 0.28 | 0.31 | 0.29 | 0.03
| subtotal | = | EA//SB | VANKIRK | vanKirk | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 6.59 | [5 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.18 | 0.18 | 0.16 | 0.18 | 0.18 | 0.17 | 0.17 | 0.18 | 0.16 | 0.13 | 0.16 | 0.16 | 0.19 | 0.25 | 0.28 | 0.26 | 0.17 | 0.18 | 0.17 | 0.17 | 0.16 | 0.14 | 0.17 | 0.16 | 0.19 |  |  | 0.2 | 1.01 | 0.81
[6 empty] | VANKIRK subtotal = | 21.11 | 0 | 0 | 0 | 0.09 | 0.11 | 0.19 | 0.18 | 0.18 | 0.53 | 0.37 | 0.35 | 0.42 | 0.71 | 1.25 | 1.28 | 1.72 | 1.37 | 0.74 | 0.67 | 0.51 | 0.43 | 0.38 | 0.31 | 0.38 | 0.54 | 0.73 | 0.62 | 0.61 | 0.61 | 0.51 | 0.34 | 0.38 | 0.55 | 0.53 | 0.47 | 0.57 | 0.27 | 0.19 | 0 | 0 | 0.2 | 1.01 | 0.81 | 0 | 0 | 0 | 0 | 0
[6 empty] | TOTAL DESIGNERS = | 157.81 | 6.96 | 5.93 | 6.17 | 4.13 | 3.54 | 3.17 | 2.85 | 2.81 | 4.09 | 2.5 | 2.36 | 3.85 | 4.1 | 5.23 | 5.24 | 5.37 | 5.25 | 3.91 | 3.36 | 3.3 | 4.73 | 4.19 | 3.22 | 3.85 | 3.39 | 3.99 | 3.58 | 4.63 | 3.34 | 2.63 | 3.13 | 3.54 | 3.85 | 3.92 | 2.86 | 2.62 | 1.45 | 1.32 | 1.01 | 1.01 | 1.2 | 1.99 | 2.14 | 2.17 | 1.95 | 1.68 | 0.3 | 0 |  | 157.81
[6 empty] | Assigned = | 100%
| subtotal | =
| subtotal | =
| subtotal | =
| subtotal | = | EA//EM | AVASARALA | Avasarala | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 4.01 | 0.27 | 0.64 | 0.39 | 0.56 | 1.44 | 0.69 | 0.02
| subtotal | = | EA//EM | AVASARALA | Avasarala | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 4.47 | [32 empty] | 0.07 | 0.33 | 0.28 | 0.35 | 0.33 | 0.38 | 0.35 | 0.35 | 0.36 | 0.33 | 0.38 | 0.35 | 0.35 | 0.26
| subtotal | = | EA//EM | AVASARALA | Avasarala | Job: 1802 - FP Assy Oversight&Support-VIOLA | 7.5 | [8 empty] | 0.32 | 0.25 | 0.24 | 0.29 | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.29 | 0.29 | 0.36 | 0.31 | 0.26 | 0.32 | 0.32 | 0.37 | 0.36 | 0.32 | 0.36 | 0.34 | 0.36 | 0.34
| subtotal | = | EA//EM | AVASARALA | Avasarala | Job: 8203 - Design Integration-BROWN | 16.23 | [8 empty] | 0.51 | 0.4 | 0.37 | 0.46 | 0.44 | 0.48 | 0.48 | 0.44 | 0.48 | 0.48 | 0.46 | 0.46 | 0.49 | 0.42 | 0.35 | 0.44 | 0.44 | 0.51 | 0.49 | 0.44 | 0.49 | 0.46 | 0.49 | 0.46 | 0.37 | 0.35 | 0.3 | 0.37 | 0.35 | 0.41 | 0.37 | 0.37 | 0.39 | 0.35 | 0.41 | 0.37 | 0.37 | 0.35 | 0.16
| subtotal | = |  |  |  | AVASARALA subtotal = | 32.21 | 0.27 | 0.64 | 0.39 | 0.56 | 1.44 | 0.69 | 0.02 | 0 | 0.83 | 0.65 | 0.61 | 0.75 | 0.72 | 0.79 | 0.79 | 0.72 | 0.79 | 0.79 | 0.75 | 0.75 | 0.85 | 0.73 | 0.61 | 0.76 | 0.76 | 0.88 | 0.85 | 0.76 | 0.85 | 0.8 | 0.85 | 0.8 | 0.44 | 0.68 | 0.58 | 0.72 | 0.68 | 0.79 | 0.72 | 0.72 | 0.75 | 0.68 | 0.79 | 0.72 | 0.72 | 0.61 | 0.16 | 0
| subtotal | = | EA//EM | BROOKS | Brooks | Job: 8204 - Systems Analysis-BROOKS | 18.42 | 0.77 | 0.77 | 0.8 | 0.77 | 0.77 | 0.8 | 0.77 | 0.77 | 0.67 | 0.53 | 0.5 | 0.62 | 0.59 | 0.64 | 0.64 | 0.59 | 0.64 | 0.64 | 0.62 | 0.62 | 0.32 | 0.28 | 0.23 | 0.29 | 0.29 | 0.33 | 0.32 | 0.29 | 0.32 | 0.3 | 0.32 | 0.3 | 0.09 | 0.09 | 0.07 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.04
| subtotal | = |  |  |  | BROOKS subtotal = | 18.42 | 0.77 | 0.77 | 0.8 | 0.77 | 0.77 | 0.8 | 0.77 | 0.77 | 0.67 | 0.53 | 0.5 | 0.62 | 0.59 | 0.64 | 0.64 | 0.59 | 0.64 | 0.64 | 0.62 | 0.62 | 0.32 | 0.28 | 0.23 | 0.29 | 0.29 | 0.33 | 0.32 | 0.29 | 0.32 | 0.3 | 0.32 | 0.3 | 0.09 | 0.09 | 0.07 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.04 | 0
| subtotal | = | EA//EM | BROWN | Brown | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1.17 | [32 empty] | 0.02 | 0.09 | 0.07 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.07
| subtotal | = | EA//EM | BROWN | Brown | Job: 1802 - FP Assy Oversight&Support-VIOLA | 3.39 | [8 empty] | 0.21 | 0.16 | 0.15 | 0.19 | 0.18 | 0.2 | 0.2 | 0.18 | 0.2 | 0.2 | 0.19 | 0.19 | 0.1 | 0.09 | 0.07 | 0.09 | 0.09 | 0.11 | 0.1 | 0.09 | 0.1 | 0.1 | 0.1 | 0.1
| subtotal | = | EA//EM | BROWN | Brown | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 7.1 | 1.21 | 0.62 | 0.49 | 0.81 | 1.6 | 1.63 | 0.4 | 0.27 | 0.07
| subtotal | = | EA//EM | BROWN | Brown | Job: 8203 - Design Integration-BROWN | 31.35 | 0.33 | 0.59 | 0.85 | 0.58 | 0.68 | 0.77 | 0.34 | 0.32 | 0.81 | 0.64 | 0.6 | 0.74 | 0.71 | 0.78 | 0.78 | 0.71 | 0.78 | 0.78 | 0.74 | 0.74 | 0.78 | 0.67 | 0.57 | 0.71 | 0.71 | 0.82 | 0.78 | 0.71 | 0.78 | 0.74 | 0.78 | 0.74 | 0.65 | 0.62 | 0.53 | 0.65 | 0.62 | 0.71 | 0.65 | 0.65 | 0.68 | 0.62 | 0.71 | 0.65 | 0.65 | 0.62 | 0.28
| subtotal | = |  |  |  | BROWN subtotal = | 43.01 | 1.54 | 1.21 | 1.34 | 1.39 | 2.28 | 2.4 | 0.74 | 0.59 | 1.09 | 0.8 | 0.75 | 0.93 | 0.89 | 0.98 | 0.98 | 0.89 | 0.98 | 0.98 | 0.93 | 0.93 | 0.88 | 0.76 | 0.64 | 0.8 | 0.8 | 0.93 | 0.88 | 0.8 | 0.88 | 0.84 | 0.88 | 0.84 | 0.67 | 0.71 | 0.6 | 0.74 | 0.71 | 0.81 | 0.74 | 0.74 | 0.77 | 0.71 | 0.81 | 0.74 | 0.74 | 0.69 | 0.28 | 0
| subtotal | = | EA//EM | CHRZANOWSKI | Chrzanowski | Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE | 0.27 | [9 empty] | 0.01 | 0.07 | 0.09 | 0.02 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | [12 empty] | 0.01
| subtotal | = | EA//EM | CHRZANOWSKI | Chrzanowski | Job: 7503 - Machine Assembly (station 6)-PERRY | 0.62 | [42 empty] | 0.27 | 0.35
| subtotal | = | EA//EM | CHRZANOWSKI | Chrzanowski | Job: 1353 - CS Structure Procurement-PERRY | 0.68 | [25 empty] | 0.07 | 0.09 | 0.08 | 0.09 | 0.08 | 0.09 | 0.08 | 0.08 | 0.02
| subtotal | = | EA//EM | CHRZANOWSKI | Chrzanowski | Job: 1302 - PF Design -CHRZANOWSKI | 1.81 | 1.34 | 0.22 | 0.23 | 0.02
| subtotal | = | EA//EM | CHRZANOWSKI | Chrzanowski | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3.58 | 0.59 | 0.59 | 0.61 | 0.59 | 0.59 | 0.61
| subtotal | = | EA//EM | CHRZANOWSKI | Chrzanowski | Job: 1354 - Trim Coil Design &Procurement-KALISH | 3.67 |  |  |  |  | 0.22 | 0.35 | 0.33 | 0.33 | 0.37 | 0.29 | 0.27 | 0.33 | 0.32 | 0.35 | 0.35 | 0.16
| subtotal | = | EA//EM | CHRZANOWSKI | Chrzanowski | Job: 1352 - PF Coil Procurement-CHRZANOWSKI | 7.58 | 0.3 | 0.62 | 0.39 | 0.64 | 0.3 | 0.31 | 0.3 | 0.3 | 0.32 | 0.25 | 0.24 | 0.3 | 0.39 | 0.34 | 0.31 | 0.28 | 0.31 | 0.31 | 0.3 | 0.3 | 0.51 | [12 empty] | 0.14 | 0.12
| subtotal | = |  |  |  | CHRZANOWSKI subtotal = | 18.21 | 2.23 | 1.43 | 1.23 | 1.25 | 1.11 | 1.27 | 0.63 | 0.63 | 0.69 | 0.55 | 0.58 | 0.72 | 0.73 | 0.7 | 0.67 | 0.45 | 0.32 | 0.32 | 0.31 | 0.31 | 0.51 | 0 | 0 | 0 | 0 | 0.07 | 0.09 | 0.08 | 0.09 | 0.08 | 0.09 | 0.08 | 0.08 | 0.17 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27 | 0.35 | 0 | 0 | 0 | 0
| subtotal | = | EA//EM | DAHLGREN | Dahlgren | Job: 1353 - CS Structure Procurement-PERRY | 0.67 |  |  |  | 0.67
| subtotal | = | EA//EM | DAHLGREN | Dahlgren | Job: 1354 - Trim Coil Design &Procurement-KALISH | 0.77 | 0.58 | 0.19
| subtotal | = | EA//EM | DAHLGREN | Dahlgren | Job: 1501 - Coil Structures Design-DAHLGREN | 1.84 | 0.23 | 0.23 | 0.24 | 0.5 | 0.57 | 0.07
| subtotal | = | EA//EM | DAHLGREN | Dahlgren | Job: 1702 - Base Support Struct Design-DAHLGREN | 3.32 | 1.14 | 0.96 | 1.01 | 0.21
| subtotal | = |  |  |  | DAHLGREN subtotal = | 6.6 | 1.95 | 1.38 | 1.25 | 1.38 | 0.57 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//EM | ELLIS | Ellis | Job: 8205 - Dimensional Control Coordin-ELLIS | 12.72 | 0.54 | 0.59 | 0.08 | 0.08 | 0.36 | 0.52 | 0.16 | 0.16 | 0.49 | 0.18 | 0.14 | 0.17 | 0.17 | 0.29 | 0.66 | 0.7 | 0.56 | 0.56 | 0.86 | 0.96 | 1.01 | 0.86 | 0.27 | 0.26 | 0.26 | 0.27 | 0.18 | 0.16 | 0.13 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.05 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.02
| subtotal | = |  |  |  | ELLIS subtotal = | 12.72 | 0.54 | 0.59 | 0.08 | 0.08 | 0.36 | 0.52 | 0.16 | 0.16 | 0.49 | 0.18 | 0.14 | 0.17 | 0.17 | 0.29 | 0.66 | 0.7 | 0.56 | 0.56 | 0.86 | 0.96 | 1.01 | 0.86 | 0.27 | 0.26 | 0.26 | 0.27 | 0.18 | 0.16 | 0.13 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.05 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.02 | 0 | 0
| subtotal | = | EA//EM | FAN | Fan | Job: 1302 - PF Design -CHRZANOWSKI | 0.72 | 0.72
| subtotal | = | EA//EM | FAN | Fan | Job: 1701 - Cryostat Design-RAFTOPOLOUS | 2.4 | [17 empty] | 0.31 | 0.34 | 0.34 | 0.36 | 0.31 | 0.26 | 0.32 | 0.16
| subtotal | = | EA//EM | FAN | Fan | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 2.93 | 0.53 | 0.69 | 0.59 | 0.05 | 0.71 | 0.36
| subtotal | = | EA//EM | FAN | Fan | Job: 8204 - Systems Analysis-BROOKS | 9.52 | 0.56 | 0.56 | 0.59 | 0.56 | 0.56 | 0.59 | 0.56 | 0.56 | 0.34 | 0.27 | 0.25 | 0.31 | 0.3 | 0.33 | 0.33 | 0.3 | 0.33 | 0.33 | 0.31 | 0.31 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.04 | 0.02
| subtotal | = |  |  |  | FAN subtotal = | 15.57 | 1.81 | 1.25 | 1.18 | 0.61 | 1.27 | 0.95 | 0.56 | 0.56 | 0.34 | 0.27 | 0.25 | 0.31 | 0.3 | 0.33 | 0.33 | 0.3 | 0.33 | 0.64 | 0.65 | 0.65 | 0.41 | 0.36 | 0.3 | 0.37 | 0.21 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.04 | 0.02 | 0
| subtotal | = | EA//EM | HEITZENROED | Heitzenroeder | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 31.98 | 0.78 | 0.78 | 0.82 | 0.78 | 0.78 | 0.82 | 0.78 | 0.78 | 0.8 | 0.62 | 0.59 | 0.73 | 0.69 | 0.76 | 0.76 | 0.69 | 0.76 | 0.76 | 0.73 | 0.73 | 0.77 | 0.66 | 0.56 | 0.7 | 0.7 | 0.8 | 0.77 | 0.7 | 0.77 | 0.73 | 0.77 | 0.73 | 0.63 | 0.6 | 0.51 | 0.63 | 0.6 | 0.69 | 0.63 | 0.63 | 0.66 | 0.6 | 0.69 | 0.63 | 0.37 | 0.35 | 0.16
| subtotal | = |  |  |  | HEITZENROED subtotal = | 31.98 | 0.78 | 0.78 | 0.82 | 0.78 | 0.78 | 0.82 | 0.78 | 0.78 | 0.8 | 0.62 | 0.59 | 0.73 | 0.69 | 0.76 | 0.76 | 0.69 | 0.76 | 0.76 | 0.73 | 0.73 | 0.77 | 0.66 | 0.56 | 0.7 | 0.7 | 0.8 | 0.77 | 0.7 | 0.77 | 0.73 | 0.77 | 0.73 | 0.63 | 0.6 | 0.51 | 0.63 | 0.6 | 0.69 | 0.63 | 0.63 | 0.66 | 0.6 | 0.69 | 0.63 | 0.37 | 0.35 | 0.16 | 0
| subtotal | = | EA//EM | KALISH | Kalish | Job: 1302 - PF Design -CHRZANOWSKI | 0.46 | 0.46
| subtotal | = | EA//EM | KALISH | Kalish | Job: 1361 - TF Fabrication-KALISH | 2.19 | 0.24 | 0.24 | 0.25 | 0.24 | 0.24 | 0.25 | 0.24 | 0.24 | 0.25
| subtotal | = | EA//EM | KALISH | Kalish | Job: 1354 - Trim Coil Design &Procurement-KALISH | 3.25 | 0.66 | 1.28 | 0.68 | 0.48 | 0.15
| subtotal | = | EA//EM | KALISH | Kalish | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 5 | [20 empty] | 0.29 | 0.27 | 0.51 | 0.64 | 0.15 | 0.29 | 0.7 | 0.34 |  |  |  |  | 0.41 | 0.39 | 0.33 | 0.14 |  |  | 0.35 | 0.19
| subtotal | = |  |  |  | KALISH subtotal = | 10.9 | 1.36 | 1.52 | 0.93 | 0.72 | 0.39 | 0.25 | 0.24 | 0.24 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29 | 0.27 | 0.51 | 0.64 | 0.15 | 0.29 | 0.7 | 0.34 | 0 | 0 | 0 | 0 | 0.41 | 0.39 | 0.33 | 0.14 | 0 | 0 | 0.35 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//EM | PRINISKI | Priniski | Job: 1802 - FP Assy Oversight&Support-VIOLA | 13.75 | 0.48 | 0.48 | 0.51 | 0.48 | 0.48 | 0.51 | 0.48 | 0.48 | 0.51 | 0.4 | 0.38 | 0.46 | 0.44 | 0.49 | 0.49 | 0.44 | 0.49 | 0.49 | 0.46 | 0.46 | 0.49 | 0.42 | 0.35 | 0.44 | 0.44 | 0.51 | 0.49 | 0.44 | 0.49 | 0.27
| subtotal | = |  |  |  | PRINISKI subtotal = | 13.75 | 0.48 | 0.48 | 0.51 | 0.48 | 0.48 | 0.51 | 0.48 | 0.48 | 0.51 | 0.4 | 0.38 | 0.46 | 0.44 | 0.49 | 0.49 | 0.44 | 0.49 | 0.49 | 0.46 | 0.46 | 0.49 | 0.42 | 0.35 | 0.44 | 0.44 | 0.51 | 0.49 | 0.44 | 0.49 | 0.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//EM | RAFTOPOULOS | Raftopoulos | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2.8 | 0.46 | 0.46 | 0.48 | 0.46 | 0.46 | 0.48
| subtotal | = | EA//EM | RAFTOPOULOS | Raftopoulos | Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | 3.53 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | 0.03 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | 0.04 | 0.16 | 0.3 | 0.29 | 0.26 | 0.29 | 0.28 | 0.29 | 0.28 | 0.28 | 0.17
| subtotal | = | EA//EM | RAFTOPOULOS | Raftopoulos | Job: 1701 - Cryostat Design-RAFTOPOLOUS | 7.48 | [5 empty] | 0.41 | 0.39 | 0.39 | 0.43 | 0.34 | 0.32 | 0.4 | 0.38 | 0.42 | 0.42 | 0.38 | 0.42 | 0.41 | 0.39 | 0.39 | 0.4 | 0.35 | 0.29 | 0.37 | 0.18
| subtotal | = | EA//EM | RAFTOPOULOS | Raftopoulos | Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 12.25 |  |  |  |  | 0.33 | 0.58 | 0.56 | 0.56 | 0.61 | 0.48 | 0.45 | 0.68 | 0.64 | 0.71 | 0.71 | 0.64 | 0.71 | 0.33 | 0.26 | 0.26 | 0.3 | 0.43 | 0.36 | 0.4 | 0.43 | 0.41 | 0.11 | 0.1 | 0.11 | 0.1 | 0.11 | 0.1 | 0.1 | 0.1 | 0.08 | 0.1 | 0.1 | 0.11 | 0.1 | 0.09
| subtotal | = |  |  |  | RAFTOPOULOS subtotal = | 26.06 | 0.5 | 0.5 | 0.52 | 0.5 | 0.83 | 1.51 | 0.99 | 0.99 | 1.08 | 0.85 | 0.8 | 1.12 | 1.06 | 1.17 | 1.17 | 1.06 | 1.17 | 0.78 | 0.69 | 0.69 | 0.74 | 0.82 | 0.68 | 0.81 | 0.77 | 0.71 | 0.4 | 0.36 | 0.4 | 0.38 | 0.4 | 0.38 | 0.38 | 0.27 | 0.08 | 0.1 | 0.1 | 0.11 | 0.1 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EA//EM | REIERSEN | Reiersen | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 7.65 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.32 | 0.25 | 0.24 | 0.29 | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.29 | 0.29 | 0.15 | 0.13 | 0.11 | 0.14 | 0.14 | 0.16 | 0.15 | 0.14 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 0.09 | 0.08 | 0.1 | 0.09 | 0.11 | 0.1 | 0.1 | 0.1 | 0.09 | 0.11 | 0.1
| subtotal | = |  |  |  | REIERSEN subtotal = | 7.65 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.32 | 0.25 | 0.24 | 0.29 | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.29 | 0.29 | 0.15 | 0.13 | 0.11 | 0.14 | 0.14 | 0.16 | 0.15 | 0.14 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 0.09 | 0.08 | 0.1 | 0.09 | 0.11 | 0.1 | 0.1 | 0.1 | 0.09 | 0.11 | 0.1 | 0 | 0 | 0 | 0
| subtotal | = | EA//EM | SIMMONS | Simmons | Job: 8101 - Project Management &Control-ANDERSON | 2.87 | [8 empty] | 0.16 | 0.12 | 0.12 | 0.15 | 0.14 | 0.15 | 0.15 | 0.14 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 0.09 | 0.07 | 0.09 | 0.09 | 0.11 | 0.1 | 0.09 | 0.1 | 0.1 | 0.1 | 0.1
| subtotal | = | EA//EM | SIMMONS | Simmons | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 25.7 | 0.68 | 0.68 | 0.71 | 0.68 | 0.68 | 0.71 | 0.68 | 0.68 | 0.64 | 0.5 | 0.47 | 0.58 | 0.55 | 0.61 | 0.61 | 0.55 | 0.61 | 0.61 | 0.58 | 0.58 | 0.61 | 0.53 | 0.45 | 0.56 | 0.56 | 0.64 | 0.61 | 0.56 | 0.61 | 0.58 | 0.61 | 0.58 | 0.48 | 0.46 | 0.39 | 0.48 | 0.46 | 0.53 | 0.48 | 0.48 | 0.51 | 0.46 | 0.53 | 0.48 | 0.28 | 0.27 | 0.12
| subtotal | = |  |  |  | SIMMONS subtotal = | 28.57 | 0.68 | 0.68 | 0.71 | 0.68 | 0.68 | 0.71 | 0.68 | 0.68 | 0.8 | 0.62 | 0.59 | 0.73 | 0.69 | 0.76 | 0.76 | 0.69 | 0.76 | 0.76 | 0.73 | 0.73 | 0.71 | 0.62 | 0.52 | 0.65 | 0.65 | 0.75 | 0.71 | 0.65 | 0.71 | 0.68 | 0.71 | 0.68 | 0.48 | 0.46 | 0.39 | 0.48 | 0.46 | 0.53 | 0.48 | 0.48 | 0.51 | 0.46 | 0.53 | 0.48 | 0.28 | 0.27 | 0.12 | 0
| subtotal | = | EA//EM | ZHANG | Zhang | Job: 8204 - Systems Analysis-BROOKS | 8.99 | 0.36 | 0.36 | 0.37 | 0.36 | 0.36 | 0.37 | 0.36 | 0.36 | 0.34 | 0.26 | 0.25 | 0.31 | 0.29 | 0.32 | 0.32 | 0.29 | 0.32 | 0.32 | 0.31 | 0.31 | 0.1 | 0.09 | 0.07 | 0.09 | 0.09 | 0.11 | 0.1 | 0.09 | 0.1 | 0.1 | 0.1 | 0.1 | 0.09 | 0.09 | 0.07 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.04
| subtotal | = |  |  |  | ZHANG subtotal = | 8.99 | 0.36 | 0.36 | 0.37 | 0.36 | 0.36 | 0.37 | 0.36 | 0.36 | 0.34 | 0.26 | 0.25 | 0.31 | 0.29 | 0.32 | 0.32 | 0.29 | 0.32 | 0.32 | 0.31 | 0.31 | 0.1 | 0.09 | 0.07 | 0.09 | 0.09 | 0.11 | 0.1 | 0.09 | 0.1 | 0.1 | 0.1 | 0.1 | 0.09 | 0.09 | 0.07 | 0.09 | 0.09 | 0.1 | 0.09 | 0.09 | 0.1 | 0.09 | 0.1 | 0.09 | 0.09 | 0.09 | 0.04 | 0
| subtotal | = | EA//EM | unassigned |  | Job: 1601 - Coil Services Design-GORANSON | 0.26 | [8 empty] | 0.09 | 0.07 | 0.07 | 0.03
| subtotal | = | EA//EM | unassigned |  | Job: 8501 - Integrated Systems Testing-GENTILE | 0.61 | [45 empty] | 0.29 | 0.32 | 0.06
| subtotal | = | EA//EM | unassigned |  | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 1.07 | [24 empty] | 0.57 | 0.5
| subtotal | = | EA//EM | unassigned |  | Job: 1260 NB Transition Ducts- GORANSON | 1.07 | [8 empty] | 0.38 | 0.3 | 0.28 | 0.11
| subtotal | = | EA//EM | unassigned |  | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 1.39 | 0.37 | 0.37 | 0.39 | [14 empty] | 0.19 | 0.07
| subtotal | = | EA//EM | unassigned |  | Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 2.69 |  |  |  |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.63 | 0.91 | 0.23 | 0.12 | 0.12 | 0.12 | 0.08 | 0.07 | 0.03
| subtotal | = | EA//EM | unassigned |  | Job: 7503 - Machine Assembly (station 6)-PERRY | 2.85 | [22 empty] | 0.15 | 0.21 | 0.21 | 0.02 | [17 empty] | 0.19 | 1.72 | 0.35
| subtotal | = | EA//EM | unassigned |  | Job: 1802 - FP Assy Oversight&Support-VIOLA | 5.02 | [20 empty] | 0.49 | 0.42 | 0.35 | 0.44 | 0.44 | 0.51 | 0.49 | 0.44 | 0.49 | 0.46 | 0.49
| subtotal | = |  |  |  | unassigned subtotal = | 14.96 | 0.37 | 0.37 | 0.39 | 0 | 0.04 | 0.04 | 0.04 | 0.04 | 0.51 | 0.4 | 0.38 | 0.17 | 0.03 | 0.03 | 0.03 | 0.63 | 0.91 | 0.42 | 0.19 | 0.12 | 0.61 | 0.5 | 0.57 | 0.68 | 1.22 | 1.03 | 0.49 | 0.44 | 0.49 | 0.46 | 0.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 1.72 | 0.64 | 0.32 | 0.06 |  | 15.02
|  | = |  |  |  | TOTAL EA ENGINEERS = | 289.6 | 13.8 | 12.12 | 10.68 | 9.72 | 11.52 | 11.07 | 6.61 | 6.44 | 8.72 | 6.38 | 6.06 | 7.31 | 6.88 | 7.57 | 7.91 | 7.73 | 8.34 | 7.77 | 7.52 | 7.55 | 7.84 | 6.5 | 5.42 | 6.63 | 6.48 | 6.9 | 6.18 | 5.3 | 5.43 | 4.91 | 4.88 | 4.18 | 3.49 | 3.65 | 2.92 | 3.21 | 2.92 | 3.36 | 3.42 | 3.25 | 3.11 | 2.82 | 3.52 | 3.51 | 4.13 | 2.8 | 1.14 | 0.06 |  | 289.66 | 5.185%
[6 empty] | Assigned = | 94.83%
| subtotal | = | EC//EM | DAVIS |  | Job: 5301 - Data Acquisition-SICHTA | 1.85 | [19 empty] | 0.11 | 0.16 |  |  |  |  | 0.53 | 0.06 | 0.28 | 0.31 | 0.2 | [6 empty] | 0.17 | 0.03
| subtotal | = | EC//EM |  |  | DAVIS subtotal = | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11 | 0.16 | 0 | 0 | 0 | 0 | 0.53 | 0.06 | 0.28 | 0.31 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EC//EM | DONG |  | Job: 5101 - Network and Fiber | 0.97 | [20 empty] | 0.02 | 0.03 | 0.04 | 0.04 | 0.03 |  |  |  | 0.02 | 0.06 | 0.06 | 0.1 | 0.12 | 0.11 | 0.1 | 0.21 | 0.03
| subtotal | = | EC//EM | DONG |  | Job: 5201 - I&C Systems-SICHTA | 4.66 | [18 empty] | 0.01 | 0.12 | 0.13 | 0.19 | 0.17 | 0.56 | 0.73 | 0.53 | 0.29 | 0.24 | 0.26 | 0.19 | 0.16 | 0.27 | 0.15 | 0.12 | 0.11 | 0.17 | 0.19 | 0.07
| subtotal | = | EC//EM | DONG |  | Job: 5401 - Facility Timing & | 0.38 | [30 empty] | 0.01 | 0.09 | 0.09 | 0.08 | 0.07 | 0.04
| subtotal | = | EC//EM | DONG |  | Job: 5501 - Real Time Control | 0.6 | [29 empty] | 0.04 | 0.1 | 0.1 | 0.1 | 0.09 | 0.08 | 0.06 | 0.03
| subtotal | = | EC//EM | DONG |  | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 1.58 | [21 empty] | 0.14 | 0.14 | 0.03 | 0.03 | 0.04 | 0.01 |  |  |  | 0.15 | 0.18 | 0.18 | 0.17 | 0.15 | 0.22 | 0.14
| subtotal | = | EC//EM |  |  | DONG subtotal = | 8.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.12 | 0.15 | 0.36 | 0.35 | 0.63 | 0.79 | 0.57 | 0.3 | 0.24 | 0.28 | 0.29 | 0.48 | 0.74 | 0.64 | 0.57 | 0.51 | 0.7 | 0.39 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EC//EM | ISAACS |  | Job: 5301 - Data Acquisition-SICHTA | 2.65 | [24 empty] | 0.51 | 0.08 | 0.48 |  |  |  | 0.12 | 0.37 | 0.37 | 0.28 | 0.16 | 0.2 | 0.08
| subtotal | = | EC//EM | ISAACS |  | Job: 5401 - Facility Timing & | 1.19 | [22 empty] | 0.03 | 0.11 | 0.12 | 0.17 | 0.2 | 0.07 | 0.07 | 0.08 | 0.07 |  |  |  |  | 0.13 | 0.14
| subtotal | = | EC//EM | ISAACS |  | Job: 5501 - Real Time Control | 1.97 | [20 empty] | 0.06 | 0.06 | 0.05 | 0.07 | 0.04 |  | 0.02 | 0.08 | 0.14 | 0.12 | 0.13 | 0.15 | 0.15 | 0.14 | 0.12 | 0.18 | 0.36 | 0.1
| subtotal | = | EC//EM |  |  | ISAACS subtotal = | 5.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0.08 | 0.18 | 0.67 | 0.25 | 0.7 | 0.15 | 0.21 | 0.2 | 0.32 | 0.52 | 0.52 | 0.42 | 0.28 | 0.51 | 0.58 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EC//EM | MASTROVITO |  | Job: 5501 - Real Time Control | 3.94 | [20 empty] | 0.12 | 0.2 | 0.22 | 0.28 | 0.18 |  |  |  |  | 0.17 | 0.46 | 0.44 | 0.44 | 0.42 | 0.35 | 0.39 | 0.27
| subtotal | = | EC//EM |  |  | MASTROVITO subtotal = | 3.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0.2 | 0.22 | 0.28 | 0.18 | 0 | 0 | 0 | 0 | 0.17 | 0.46 | 0.44 | 0.44 | 0.42 | 0.35 | 0.39 | 0.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EC//EM | SICHTA |  | Job: 1270 - Heater Control System-PPPL ( tbd) | 0.83 | [12 empty] | 0.13 | 0.14 | 0.14 | 0.13 | 0.14 | 0.14 | 0.01
| subtotal | = | EC//EM | SICHTA |  | Job: 5101 - Network and Fiber | 0.44 | [20 empty] | 0.18 | 0.1 | 0.05 | 0.07 | 0.04
| subtotal | = | EC//EM | SICHTA |  | Job: 5201 - I&C Systems-SICHTA | 1.5 | [18 empty] | 0.41 | 0.19 | 0.2 | 0.04 | 0.03 | 0.05 | 0.11 | 0.16 | 0.06 | 0.04 | 0.05 | 0.02 | [5 empty] | 0.04 | 0.07 | 0.03
| subtotal | = | EC//EM | SICHTA |  | Job: 5301 - Data Acquisition-SICHTA | 0.67 | [18 empty] | 0.19 | 0.19 | 0.18 | 0.08 | 0.03
| subtotal | = | EC//EM | SICHTA |  | Job: 5401 - Facility Timing & | 1.19 | [21 empty] | 0.25 | 0.19 | 0.16 | 0.14 | 0.07 | [6 empty] | 0.15 | 0.12 |  | 0.05 | 0.06
| subtotal | = | EC//EM | SICHTA |  | Job: 5501 - Real Time Control | 1.23 | [20 empty] | 0.41 | 0.25 | 0.15 | 0.19 | 0.12 | [11 empty] | 0.08 | 0.03
| subtotal | = | EC//EM | SICHTA |  | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 1.27 | [18 empty] | 0.13 | 0.18 | 0.23 | 0.11 | 0.05 | 0.1 | 0.1 | 0.12 | 0.04 | [8 empty] | 0.12 | 0.09
| subtotal | = | EC//EM | SICHTA |  | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 3.07 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.07 | 0.06 | 0.05 | 0.07 | 0.06 | 0.07 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.05 | 0.06 | 0.06 | 0.07 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.05 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.07 | 0.06
| subtotal | = | EC//EM |  |  | SICHTA subtotal = | 10.2 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.07 | 0.06 | 0.05 | 0.07 | 0.19 | 0.21 | 0.21 | 0.19 | 0.21 | 0.21 | 0.81 | 0.63 | 1.27 | 0.89 | 0.55 | 0.63 | 0.57 | 0.42 | 0.17 | 0.1 | 0.12 | 0.09 | 0.07 | 0.07 | 0.22 | 0.18 | 0.05 | 0.28 | 0.36 | 0.13 | 0.07 | 0.07 | 0.07 | 0.06 | 0.07 | 0.06 | 0 | 0 | 0 | 0
| subtotal | = | EC//EM | TCHILINGUIR |  | Job: 5201 - I&C Systems-SICHTA | 2.94 | [21 empty] | 0.67 | 0.6 | 0.25 | 0.11 | 0.26 | 0.18 | 0.15 | 0.17 | 0.12 | 0.1 | 0.09 | 0.01 |  |  | 0.07 | 0.11 | 0.05
| subtotal | = | EC//EM | TCHILINGUIR |  | Job: 5401 - Facility Timing & | 0.92 | [22 empty] | 0.01 | 0.03 | 0.02 |  | 0.04 | 0.07 | 0.08 | 0.07 | 0.08 | 0.07 | 0.17 | 0.12 |  | 0.08 | 0.08
| subtotal | = | EC//EM | TCHILINGUIR |  | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 3.6 | [18 empty] | 0.06 | 0.08 | 0.1 | 0.26 | 0.28 | 0.2 | 0.2 | 0.23 | 0.08 | 0.07 | 0.12 | 0.12 | 0.24 | 0.26 | 0.26 | 0.25 | 0.21 | 0.35 | 0.23
| subtotal | = | EC//EM |  |  | TCHILINGUIR subtotal = | 7.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0.08 | 0.1 | 0.93 | 0.89 | 0.48 | 0.33 | 0.49 | 0.3 | 0.29 | 0.37 | 0.31 | 0.42 | 0.42 | 0.44 | 0.37 | 0.21 | 0.5 | 0.42 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EC//EM | ZIMMER |  | Job: 5301 - Data Acquisition-SICHTA | 0.8 | [26 empty] | 0.04 | 0.2 | 0.22 | 0.14 | [6 empty] | 0.17 | 0.03
| subtotal | = | EC//EM | ZIMMER |  | Job: 5401 - Facility Timing & | 0.64 | [26 empty] | 0.05 | 0.11 | 0.12 | 0.11 | 0.12 | 0.11 | 0.02
| subtotal | = | EC//EM |  |  | ZIMMER subtotal = | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09 | 0.31 | 0.34 | 0.25 | 0.12 | 0.11 | 0.02 | 0 | 0 | 0 | 0.17 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EC//EM | unassigned |  | Job: 1270 - Heater Control System-PPPL ( tbd) | 0.31 | [37 empty] | 0.06 | 0.1 | 0.1 | 0.05
| subtotal | = | EC//EM | unassigned |  | Job: 3801 - Electron Beam Mapping-STRATTON | 2 | [14 empty] | 0.15 | 1 | 0.85
| subtotal | = | EC//EM | unassigned |  | Job: 8501 - Integrated Systems Testing-GENTILE | 2 | [45 empty] | 0.86 | 0.97 | 0.17
[6 empty] | unassigned subtotal = | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 1 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0.1 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0.86 | 0.97 | 0.17
[6 empty] | TOTAL EC ENGINEERS = | 43.2 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.07 | 0.06 | 0.05 | 0.07 | 0.19 | 0.21 | 0.36 | 1.19 | 1.06 | 0.21 | 0.88 | 0.94 | 1.86 | 2.44 | 2.09 | 2.2 | 2.54 | 2.26 | 1.62 | 1.37 | 1.63 | 1.51 | 1.87 | 2.3 | 2.28 | 1.96 | 1.4 | 2.38 | 2.36 | 0.47 | 0.17 | 0.17 | 0.12 | 0.06 | 0.07 | 0.06 | 0 | 0.86 | 0.97 | 0.17 |  | 43.2
[6 empty] | Assigned = | 90.02%
| subtotal | = | EE//EM | BAKER | Baker | Job: 4101 - AC Power-RAMAKRISHNAN | 0.22 | [23 empty] | 0.02 | 0.03 | 0.04 | 0.05 | 0.04 | 0.04
| subtotal | = | EE//EM | BAKER | Baker | Job: 4301 - DC Systems-RAMAKRISHNAN | 0.35 |  |  |  |  | 0 | 0 | 0 | 0 | [12 empty] | 0.01 | 0 | 0 | 0 | 0.04 | 0.1 | 0.05 | 0.05 | 0.05 | 0.05 | 0
| subtotal | = | EE//EM | BAKER | Baker | Job: 4401 - Control & Protection-RAMAKRISHNAN | 2.2 | [20 empty] | 0.01 | 0.01 | 0.01 | 0.17 | 0.35 | 0.21 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.08 | 0.14 | 0.13 | 0.57 | 0.27 | 0.11 | 0.05 | 0.04
| subtotal | = | EE//EM | BAKER | Baker | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 2.74 | [25 empty] | 0.31 | 0.23 | 0.05 | 0.01 | 0.03 | 0.03 | 0.03 | 0.06 | 0.06 | 0.05 | 0.04 | 0.02 |  |  |  | 0.18 | 0.91 | 0.73
| subtotal | = |  |  |  | BAKER subtotal = | 5.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0.01 | 0.01 | 0.19 | 0.42 | 0.66 | 0.34 | 0.15 | 0.11 | 0.09 | 0.04 | 0.11 | 0.2 | 0.19 | 0.62 | 0.31 | 0.13 | 0.05 | 0.04 | 0 | 0.18 | 0.91 | 0.73 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EE//EM | HATCHER | Hatcher | Job: 4301 - DC Systems-RAMAKRISHNAN | 1.43 | [5 empty] | 0.28 | 0.04 | 0.04 | 0.05 | 0.04 | 0.03 | [7 empty] | 0.06 | 0.12 | 0.25 | 0.15 | 0.12 | 0.15 | 0.1
| subtotal | = |  |  |  | HATCHER subtotal = | 1.43 | 0 | 0 | 0 | 0 | 0 | 0.28 | 0.04 | 0.04 | 0.05 | 0.04 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0.12 | 0.25 | 0.15 | 0.12 | 0.15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EE//EM | LAWSON | Lawson | Job: 4401 - Control & Protection-RAMAKRISHNAN | 4.26 |  |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | [9 empty] | 0.34 | 0.38 | 0.32 | 0.4 | 0.4 | 0.46 | 0.44 | 0.4 | 0.06 |  | 0.17 | 0.2 | 0.24 | 0.24 | 0.06
| subtotal | = |  |  |  | LAWSON subtotal = | 4.26 | 0 | 0 | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34 | 0.38 | 0.32 | 0.4 | 0.4 | 0.46 | 0.44 | 0.4 | 0.06 | 0 | 0.17 | 0.2 | 0.24 | 0.24 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EE//EM | MARSALA | Marsala | Job: 4401 - Control & Protection-RAMAKRISHNAN | 5 | [5 empty] | 0.27 | 0.26 | 0.26 | 0.28 |  |  |  |  | 0.03 | 0.03 | 0.02 | 0.63 | 0.42 | 0.32 | 0.04 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | 0.04 | 0.23 | 0.24 | 0.31 | 0.53 | 0.45 | 0.28 | 0.19
| subtotal | = |  |  |  | MARSALA subtotal = | 5 | 0 | 0 | 0 | 0 | 0 | 0.27 | 0.26 | 0.26 | 0.28 | 0 | 0 | 0 | 0 | 0.03 | 0.03 | 0.02 | 0.63 | 0.42 | 0.32 | 0.04 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | 0.04 | 0.23 | 0.24 | 0.31 | 0.53 | 0.45 | 0.28 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EE//EM | MCBRIDE | McBride | Job: 4101 - AC Power-RAMAKRISHNAN | 0.36 | [18 empty] | 0 | 0 | 0 | 0.01 | 0.01 | 0.04 | 0.06 | 0.06 | 0.06 | 0.05 | 0.05 | 0.01 | 0.01 | 0
| subtotal | = | EE//EM | MCBRIDE | McBride | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1.4 | [25 empty] | 0.06 | 0.11 | 0.15 | 0.03 | 0.09 | 0.09 | 0.09 | 0.09 | 0.08 | 0.07 | 0.36 | 0.18
| subtotal | = | EE//EM | MCBRIDE | McBride | Job: 4301 - DC Systems-RAMAKRISHNAN | 2.04 |  |  |  |  | 0.01 | 0.07 | 0.02 | 0.02 | 0.01 | 0.01 | 0.01 | [7 empty] | 0.04 | 0.02 | 0.03 | 0.03 | 0.02 | 0.03 | 0.14 | 0.36 | 0.31 | 0.28 | 0.31 | 0.29 | 0.03
| subtotal | = | EE//EM | MCBRIDE | McBride | Job: 4401 - Control & Protection-RAMAKRISHNAN | 2.17 | [5 empty] | 0.03 | 0.03 | 0.03 | 0.03 |  |  |  |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.02 |  |  |  | 0.16 | 0.27 | 0.11 |  | 0 | 0.05 | 0.05 | 0.05 | 0.07 | 0.13 | 0.12 | 0.17 | 0.25 | 0.27 | 0.05 | 0.04
| subtotal | = |  |  |  | MCBRIDE subtotal = | 5.97 | 0 | 0 | 0 | 0 | 0.01 | 0.1 | 0.05 | 0.05 | 0.04 | 0.01 | 0.01 | 0 | 0 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.08 | 0.04 | 0.03 | 0.04 | 0.03 | 0.23 | 0.47 | 0.59 | 0.48 | 0.48 | 0.44 | 0.44 | 0.18 | 0.16 | 0.22 | 0.2 | 0.24 | 0.61 | 0.45 | 0.05 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EE//EM | NEUMEYER | Neumeyer | Job: 4401 - Control & Protection-RAMAKRISHNAN | 0.54 | [20 empty] | 0.18 | 0.16 | 0.13 | 0.07
| subtotal | = | EE//EM | NEUMEYER | Neumeyer | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 1.29 | [5 empty] | 0.66 | 0.09 | 0.09 | 0.1 | 0.08 | 0.07 | 0.09 | 0.09 | 0.02
| subtotal | = |  |  |  | NEUMEYER subtotal = | 1.83 | 0 | 0 | 0 | 0 | 0 | 0.66 | 0.09 | 0.09 | 0.1 | 0.08 | 0.07 | 0.09 | 0.09 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0.16 | 0.13 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EE//EM | RAMAKRISHNA | Ramakrishnan | Job: 7503 - Machine Assembly (station 6)-PERRY | 0.44 | [42 empty] | 0.44
| subtotal | = | EE//EM | RAMAKRISHNA |  | Job: 4101 - AC Power-RAMAKRISHNAN | 1.01 | [11 empty] | 0.01 | 0.01 | 0.01 | 0.01 | 0.07 | 0.08 | 0.08 | 0.07 | 0.07 | 0.07 | 0.06 | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 |  | 0.03 | 0.07 | 0.09 | 0.11 | 0.04
| subtotal | = | EE//EM | RAMAKRISHNA |  | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1.12 | [8 empty] | 0.04 | 0.03 | 0.03 | 0.09 | 0.09 | 0.13 | 0.08 | 0.07 | 0.08 | 0.08 | 0.08 | 0.06 | 0.04 | 0.03 | 0.03 | 0.01 |  |  |  | 0 | 0.05 | 0.05 | 0.05 | 0
| subtotal | = | EE//EM | RAMAKRISHNA |  | Job: 4301 - DC Systems-RAMAKRISHNAN | 2.03 |  |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.06 | 0.04 | 0.04 | 0.05 | 0.14 | 0.15 | 0.15 | 0.14 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 0.09 | 0.07 | 0.09 | 0.06
| subtotal | = | EE//EM | RAMAKRISHNA |  | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 8.45 | [5 empty] | 0.06 | 0.34 | 0.24 | 0.13 | 0.1 | 0.09 | 0.12 | 0.11 | 0.3 | 0.3 | 0.23 | 0.22 | 0.22 | 0.21 | 0.21 | 0.3 | 0.23 | 0.14 | 0.16 | 0.16 | 0.22 | 0.3 | 0.3 | 0.26 | 0.17 | 0.18 | 0.17 | 0.17 | 0.16 | 0.14 | 0.28 | 0.22 | 0.19 |  |  | 0.18 | 0.91 | 0.73
raki | subtotal | = | EE//EM | RAMAKRISHNA |  | Job: 8501 - Integrated Systems Testing-GENTILE | 1.83 | [45 empty] | 0.86 | 0.97 | 0.17
| subtotal | = |  |  |  | RAMAKRISHNA subtotal = | 14.88 | 0 | 0 | 0 | 0.05 | 0.05 | 0.11 | 0.39 | 0.29 | 0.23 | 0.17 | 0.16 | 0.27 | 0.35 | 0.59 | 0.54 | 0.51 | 0.53 | 0.53 | 0.51 | 0.49 | 0.51 | 0.41 | 0.29 | 0.27 | 0.23 | 0.23 | 0.31 | 0.31 | 0.32 | 0.23 | 0.24 | 0.17 | 0.17 | 0.19 | 0.21 | 0.37 | 0.33 | 0.23 | 0 | 0 | 0.18 | 0.91 | 1.17 | 0 | 0 | 0.86 | 0.97 | 0.17
| subtotal | = | EE//EM | VONHALLE | vonHalle | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 15.44 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.32 | 0.25 | 0.24 | 0.29 | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.29 | 0.29 | 0.51 | 0.44 | 0.37 | 0.46 | 0.46 | 0.53 | 0.51 | 0.46 | 0.51 | 0.49 | 0.51 | 0.49 | 0.39 | 0.37 | 0.31 | 0.39 | 0.37 | 0.42 | 0.39 | 0.39 | 0.4 | 0.37 | 0.42 | 0.39 | 0.14 | 0.13 | 0.06
| subtotal | = |  |  |  | VONHALLE subtotal = | 15.44 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.32 | 0.25 | 0.24 | 0.29 | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.29 | 0.29 | 0.51 | 0.44 | 0.37 | 0.46 | 0.46 | 0.53 | 0.51 | 0.46 | 0.51 | 0.49 | 0.51 | 0.49 | 0.39 | 0.37 | 0.31 | 0.39 | 0.37 | 0.42 | 0.39 | 0.39 | 0.4 | 0.37 | 0.42 | 0.39 | 0.14 | 0.13 | 0.06 | 0
| subtotal | = | EE//EM | LAWSON |  | Job: 5401 - Facility Timing & | 2.13 | [24 empty] | 0.12 | 0.58 | 0.63 |  | 0.04 | 0.42 | 0.34
| subtotal | = | EE//EM | LAWSON |  | Job: 5501 - Real Time Control | 3.1 | [20 empty] | 0.12 | 0.12 | 0.11 | 0.13 | 0.09 |  | 0.04 | 0.08 | 0.09 | 0.15 | 0.29 | 0.29 | 0.29 | 0.28 | 0.24 | 0.38 | 0.37 | 0.03
[6 empty] | LAWSON subtotal = | 5.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0.12 | 0.11 | 0.13 | 0.21 | 0.58 | 0.67 | 0.08 | 0.13 | 0.57 | 0.63 | 0.29 | 0.29 | 0.28 | 0.24 | 0.38 | 0.37 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
hans | subtotal | = | EE//EM | SCHHNEIDER |  | Job: 3801 - Electron Beam Mapping-STRATTON | 0.06 | [32 empty] | 0.02 | 0.02 | 0.01 | 0.01
hans | subtotal | = | EE//EM | SCHHNEIDER |  | Job: 3101 - Magnetic Diagnostics-STRATTON | 0.21 | [8 empty] | 0.21
hans | subtotal | = | EE//EM | SCHHNEIDER |  | Job: 6201 - Cryogenic Syst-RAFTOPOLOUS | 3.19 |  |  |  |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.09 | 0.07 | 0.06 | 0.25 | 0.24 | 0.26 | 0.26 | 0.24 | 0.26 | 0.11 | 0.08 | 0.08 | 0.1 | 0.17 | 0.15 | 0.18 | 0.18 | 0.09
hans | subtotal | = | EE//EM | SCHHNEIDER |  | Job: 1270 - Heater Control System-PPPL ( tbd) | 4.79 | [12 empty] | 0.22 | 0.24 | 0.24 | 0.22 | 0.24 | 0.24 | 0.02 | [6 empty] | 0.03 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03 | 0.39 | 0.39 | 0.37 | 0.31 | 0.39 | 0.37 | 0.34 | 0.26 | 0.26 | 0.12
hans | subtotal | = | EE//EM | SCHHNEIDER |  | Job: 2101 - Fueling Systems-BLANCHARD | 5.52 | [13 empty] | 0.37 | 0.44 | 1.42 | 1.49 | [15 empty] | 0.23 | 0.22 | 0.19 | 0.23 | 0.22 | 0.71
hans | subtotal | = | EE//EM | SCHHNEIDER |  | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 7.56 | [8 empty] | 0.62 | 0.49 | 0.46 | 0.57 | 0.57 | 0.67 | 0.67 | 0.61 | 0.03 | [14 empty] | 0.32 | 0.32 | 0.3 | 0.26 | 0.32 | 0.3 | 0.35 | 0.17 |  |  | 0.53
[6 empty] | SCHHNEIDER subtotal = | 21.33 | 0 | 0 | 0 | 0 | 0.08 | 0.08 | 0.08 | 0.08 | 0.92 | 0.56 | 0.52 | 0.82 | 1.03 | 1.54 | 1.61 | 2.49 | 2.02 | 0.35 | 0.1 | 0.08 | 0.1 | 0.17 | 0.15 | 0.18 | 0.18 | 0.12 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03 | 0.71 | 0.96 | 0.91 | 0.77 | 0.95 | 0.89 | 1.4 | 0.43 | 0.26 | 0.12 | 0.53 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21.33
[6 empty] | TOTAL EE ENGINERS = | 80.88 | 0.16 | 0.16 | 0.16 | 0.23 | 0.32 | 1.68 | 1.09 | 0.99 | 1.96 | 1.13 | 1.04 | 1.47 | 1.75 | 2.53 | 2.53 | 3.34 | 3.53 | 1.65 | 1.36 | 1.06 | 2.08 | 1.9 | 1.55 | 2.1 | 2.49 | 3.19 | 2.8 | 1.92 | 1.61 | 1.89 | 2.03 | 2.37 | 2.78 | 2.91 | 2.9 | 3.29 | 2.73 | 2.18 | 0.9 | 0.65 | 0.88 | 2.72 | 2.32 | 0.39 | 0.14 | 0.99 | 1.03 | 0.17 |  | 81.05 | 26.32%
[6 empty] | Assigned = | 100%
| subtotal | = | EM//EM | BLANCHARD | Blanchard | Job: 2101 - Fueling Systems-BLANCHARD | 1.38 | [13 empty] | 0.16 | 0.17 | 0.28 | 0.29 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.28
| subtotal | = | EM//EM | BLANCHARD | Blanchard | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 3.74 | [8 empty] | 0.33 | 0.26 | 0.25 | 0.3 | 0.33 | 0.4 | 0.4 | 0.37 | 0.05 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | 0.03 | 0.03 | 0.03 | 0.04 | 0.04 | 0.03 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.03 | 0.03 | 0.04 | 0.03 | 0.04 | 0.02 |  |  | 0.27
[6 empty] | BLANCHARD subtotal = | 5.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0.26 | 0.25 | 0.3 | 0.33 | 0.56 | 0.57 | 0.65 | 0.34 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.04 | 0.04 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | 0.05 | 0.04 | 0.32 | 0.02 | 0 | 0 | 0.27 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EM//EM | DUDEK | Dudek | Job: 6301 - Utility Systems-DUDEK | 0.86 | [32 empty] | 0.4 | 0.15 | 0.04 | 0.05 | 0.05 | 0.08 | 0.09
| subtotal | = | EM//EM | DUDEK | Dudek | Job: 6101 - Water Systems-DUDEK | 0.99 | [27 empty] | 0.27 | 0.29 | 0.04 |  |  |  | 0.1 | 0.14 | 0.12 | 0.03
| subtotal | = | EM//EM | DUDEK | Dudek | Job: 8202 - Engr Mgmt & Sys Eng Sprt-HEITZENROED | 34.34 | 0.83 | 0.83 | 0.87 | 0.83 | 0.83 | 0.87 | 0.83 | 0.83 | 0.85 | 0.67 | 0.63 | 0.78 | 0.74 | 0.81 | 0.81 | 0.74 | 0.81 | 0.81 | 0.78 | 0.78 | 0.77 | 0.66 | 0.56 | 0.7 | 0.7 | 0.8 | 0.77 | 0.7 | 0.77 | 0.73 | 0.77 | 0.73 | 0.73 | 0.69 | 0.59 | 0.73 | 0.69 | 0.79 | 0.73 | 0.73 | 0.76 | 0.69 | 0.79 | 0.73 | 0.46 | 0.44 | 0.2
[6 empty] | DUDEK subtotal = | 36.19 | 0.83 | 0.83 | 0.87 | 0.83 | 0.83 | 0.87 | 0.83 | 0.83 | 0.85 | 0.67 | 0.63 | 0.78 | 0.74 | 0.81 | 0.81 | 0.74 | 0.81 | 0.81 | 0.78 | 0.78 | 0.77 | 0.66 | 0.56 | 0.7 | 0.7 | 0.8 | 0.77 | 0.97 | 1.06 | 0.77 | 0.77 | 0.73 | 1.13 | 0.94 | 0.77 | 0.9 | 0.77 | 0.87 | 0.82 | 0.73 | 0.76 | 0.69 | 0.79 | 0.73 | 0.46 | 0.44 | 0.2 | 0
| subtotal | = | EM//EM | GENTILE | Gentile | Job: 8501 - Integrated Systems Testing-GENTILE | 7.61 | [9 empty] | 0.48 | 0.71 | 0.64 | 0.53 | 0.45 | 0.59 | 0.53 | 0.59 | 0.52 | 0.49 | 0.56 | 0.59 | 0.31 | 0.43 | 0.19
[6 empty] | GENTILE subtotal = | 7.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0.71 | 0.64 | 0.53 | 0.45 | 0.59 | 0.53 | 0.59 | 0.52 | 0.49 | 0.56 | 0.59 | 0.31 | 0.43 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EM//EM | LABIK | Labik | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0.26 | [20 empty] | 0.07 | 0.06 |  |  |  | 0.1 | 0.03
| subtotal | = | EM//EM | LABIK | Labik | Job: 3801 - Electron Beam Mapping-STRATTON | 1.07 | [13 empty] | 0.22 | 0.21 | 0.2 | 0.17 | [12 empty] | 0.09 | 0.09 | 0.09 | 0
| subtotal | = | EM//EM | LABIK | Labik | Job: 3101 - Magnetic Diagnostics-STRATTON | 5.25 | 0.96 | 0.69 | 0.66 | 0.21 | 0.11 | 0.12 | 0.16 | 0.17 | 1.18 | 0.1 | 0.27 | 0.16 | [8 empty] | 0.05 | 0.07 | 0.06 | 0.07 | 0.07 | 0.08 | 0.06
[6 empty] | LABIK subtotal = | 6.58 | 0.96 | 0.69 | 0.66 | 0.21 | 0.11 | 0.12 | 0.16 | 0.17 | 1.18 | 0.1 | 0.27 | 0.16 | 0 | 0.22 | 0.21 | 0.2 | 0.17 | 0 | 0 | 0 | 0.12 | 0.13 | 0.06 | 0.07 | 0.07 | 0.18 | 0.09 | 0 | 0 | 0.09 | 0.09 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EM//EM | LANGISH | Langish | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3.64 | 0.45 | 0.45 | 0.47 | 0.45 | 0.45 | 0.47 | 0.45 | 0.45
[6 empty] | LANGISH subtotal = | 3.64 | 0.45 | 0.45 | 0.47 | 0.45 | 0.45 | 0.47 | 0.45 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EM//EM | PERRY | Perry | Job: 1752 - Base Support Proc-PERRY | 0.29 |  |  |  | 0.01 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0
| subtotal | = | EM//EM | PERRY | Perry | Job: 1550 - Coil Struct. Procurement -PERRY | 0.51 | [7 empty] | 0.09 | 0.1 | 0.08 | 0.07 | 0.09 | 0.08
| subtotal | = | EM//EM | PERRY | Perry | Job: 7601 - Tooling Design & Fabrication-PERRY | 0.55 | [23 empty] | 0.01 | 0.02 | 0.03 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 | 0.02 | 0.03 | 0.02 | 0.03 | 0.03 | 0.03 | 0.03 | 0.02 | 0.03 | 0.03 | 0
| subtotal | = | EM//EM | PERRY | Perry | Job: 7301 - Platform Design & | 0.8 | [6 empty] | 0.06 | 0.15 | [11 empty] | 0.27 | 0.23 | 0.09
| subtotal | = | EM//EM | PERRY | Perry | Job: 8215 Plant Design | 2.15 | 0.31 | 0.05 | 0.06 | 0.05 | 0.05 | 0.06 | 0.05 | 0.05 | 0.06 | 0.05 | 0.04 | 0.05 | 0.05 | 0.06 | 0.06 | 0.05 | 0.06 | 0.06 | 0.05 | 0.05 | 0.06 | 0.05 | 0.04 | 0.05 | 0.05 | 0.06 | 0.06 | 0.05 | 0.06 | 0.05 | 0.06 | 0.05 | 0.05 | 0.05 | 0.04 | 0.05
| subtotal | = | EM//EM | PERRY | Perry | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 31.49 | 0.46 | 0.46 | 0.48 | 0.46 | 0.46 | 0.48 | 0.46 | 0.46 | 0.51 | 0.4 | 0.37 | 0.46 | 0.44 | 0.48 | 0.48 | 0.44 | 0.48 | 0.48 | 0.46 | 0.48 | 0.48 | 0.46 | 0.51 | 0.6 | 0.88 | 1.02 | 0.97 | 0.88 | 0.97 | 0.93 | 0.97 | 0.93 | 0.93 | 0.88 | 0.75 | 0.93 | 0.88 | 1.02 | 0.93 | 0.93 | 0.97 | 0.88 | 1.02 | 0.93 | 0.93 | 0.71
[6 empty] | PERRY subtotal = | 35.79 | 0.77 | 0.51 | 0.54 | 0.52 | 0.53 | 0.56 | 0.59 | 0.77 | 0.69 | 0.55 | 0.5 | 0.62 | 0.59 | 0.56 | 0.56 | 0.51 | 0.56 | 0.56 | 0.51 | 0.8 | 0.77 | 0.6 | 0.55 | 0.66 | 0.95 | 1.11 | 1.06 | 0.95 | 1.06 | 1.01 | 1.06 | 1.01 | 1.01 | 0.95 | 0.81 | 1.01 | 0.9 | 1.05 | 0.96 | 0.96 | 1 | 0.9 | 1.05 | 0.96 | 0.93 | 0.71 | 0 | 0
| subtotal | = | EM//EM | SANDS | Sands | Job: 1802 - FP Assy Oversight&Support-VIOLA | 20.09 | 0.1 | 0.69 | 0.72 | 0.69 | 0.69 | 0.72 | 0.69 | 0.69 | 0.75 | 0.59 | 0.56 | 0.69 | 0.65 | 0.72 | 0.72 | 0.65 | 0.72 | 0.72 | 0.69 | 0.69 | 0.72 | 0.62 | 0.52 | 0.65 | 0.65 | 0.75 | 0.72 | 0.65 | 0.72 | 0.69 | 0.26
[6 empty] | SANDS subtotal = | 20.09 | 0.1 | 0.69 | 0.72 | 0.69 | 0.69 | 0.72 | 0.69 | 0.69 | 0.75 | 0.59 | 0.56 | 0.69 | 0.65 | 0.72 | 0.72 | 0.65 | 0.72 | 0.72 | 0.69 | 0.69 | 0.72 | 0.62 | 0.52 | 0.65 | 0.65 | 0.75 | 0.72 | 0.65 | 0.72 | 0.69 | 0.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EM//EM | SMITH | Smith | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.2 | 1.46 | 0.94 |  |  | 0.13 | 0.4 | [5 empty] | 0.18 | 0.09
| subtotal | = | EM//EM | SMITH | Smith | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 4.47 | [32 empty] | 0.07 | 0.33 | 0.28 | 0.35 | 0.33 | 0.38 | 0.35 | 0.35 | 0.36 | 0.33 | 0.38 | 0.35 | 0.35 | 0.26
| subtotal | = | EM//EM | SMITH | Smith | Job: 8205 - Dimensional Control Coordin-ELLIS | 6.42 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.14 | 0.14 | 0.17 | 0.17 | 0.29 | 0.29 | 0.26 | 0.29 | 0.29 | 0.28 | 0.28 | 0.3 | 0.25 | 0.2 | 0.26 | 0.26 | 0.27 | 0.18 | 0.16 | 0.13 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.05 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.07 | 0.06 | 0.07 | 0.07 | 0.07 | 0.02
| subtotal | = | EM//EM | SMITH | Smith | Job: 1802 - FP Assy Oversight&Support-VIOLA | 10.78 |  |  |  | 0.65 | 0.65 | 0.68 | 0.65 | 0.65 | 0.32 | 0.25 | 0.24 | 0.29 | 0.28 | 0.31 | 0.31 | 0.28 | 0.31 | 0.31 | 0.29 | 0.29 | 0.36 | 0.31 | 0.26 | 0.32 | 0.32 | 0.37 | 0.36 | 0.32 | 0.36 | 0.34 | 0.36 | 0.34
| subtotal | = | EM//EM | SMITH | Smith | Job: 8203 - Design Integration-BROWN | 14.05 | [8 empty] | 0.41 | 0.32 | 0.3 | 0.37 | 0.35 | 0.39 | 0.39 | 0.35 | 0.39 | 0.39 | 0.37 | 0.37 | 0.39 | 0.34 | 0.28 | 0.35 | 0.35 | 0.41 | 0.39 | 0.35 | 0.39 | 0.37 | 0.39 | 0.37 | 0.37 | 0.35 | 0.3 | 0.37 | 0.35 | 0.4 | 0.37 | 0.37 | 0.39 | 0.35 | 0.4 | 0.37 | 0.37 | 0.35 | 0.16
[6 empty] | SMITH subtotal = | 38.92 | 1.54 | 1.02 | 0.08 | 0.73 | 0.86 | 1.16 | 0.73 | 0.73 | 0.81 | 0.71 | 0.68 | 1.01 | 0.89 | 0.99 | 0.99 | 0.89 | 0.99 | 0.99 | 0.94 | 0.94 | 1.05 | 0.9 | 0.74 | 0.93 | 0.93 | 1.05 | 0.93 | 0.83 | 0.88 | 0.78 | 0.82 | 0.78 | 0.51 | 0.74 | 0.63 | 0.79 | 0.74 | 0.85 | 0.79 | 0.79 | 0.82 | 0.74 | 0.85 | 0.79 | 0.79 | 0.63 | 0.16 | 0
| subtotal | = | EM//EM | VIOLA | Viola | Job: 1802 - FP Assy Oversight&Support-VIOLA | 27.02 | 0.92 | 0.92 | 0.96 | 0.92 | 0.92 | 0.96 | 0.92 | 0.92 | 1.01 | 0.79 | 0.75 | 0.92 | 0.88 | 0.97 | 0.97 | 0.88 | 0.97 | 0.97 | 0.92 | 0.92 | 0.97 | 0.84 | 0.7 | 0.88 | 0.88 | 1.01 | 0.97 | 0.88 | 0.97 | 0.53
[6 empty] | VIOLA subtotal = | 27.02 | 0.92 | 0.92 | 0.96 | 0.92 | 0.92 | 0.96 | 0.92 | 0.92 | 1.01 | 0.79 | 0.75 | 0.92 | 0.88 | 0.97 | 0.97 | 0.88 | 0.97 | 0.97 | 0.92 | 0.92 | 0.97 | 0.84 | 0.7 | 0.88 | 0.88 | 1.01 | 0.97 | 0.88 | 0.97 | 0.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | EM//EM | unassigned |  | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 0.17 | 0.17
| subtotal | = | EM//EM | unassigned |  | Job: 7601 - Tooling Design & Fabrication-PERRY | 0.2 | [23 empty] | 0 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
| subtotal | = | EM//EM | unassigned |  | Job: 1601 - Coil Services Design-GORANSON | 0.51 | [7 empty] | 0.07 | 0.1 | 0.08 | 0.07 | 0.09 | 0.09 | 0.01
| subtotal | = | EM//EM | unassigned |  | Job: 7503 - Machine Assembly (station 6)-PERRY | 0.66 | [29 empty] | 0.17 | 0.09 | [10 empty] | 0.4
| subtotal | = | EM//EM | unassigned |  | Job: 1810 - Field Period AssyStation 1 2 3 VIOLA | 1.84 | 0.64 | 0.36 | 0.42 | 0.14 | 0.01 |  |  |  |  | 0.27
| subtotal | = | EM//EM | unassigned |  | Job: 8501 - Integrated Systems Testing-GENTILE | 2.07 | [45 empty] | 0.97 | 1.1 | 0.19
| subtotal | = | EM//EM | unassigned |  | Job: 1815 - Field Period Assy | 3.67 | [19 empty] | 0.32 | 0.44 | 0.57 | [5 empty] | 0.37 | 1.07 | 0.47 | 0.43
| subtotal | = | EM//EM | unassigned |  | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 9.33 | [31 empty] | 0.33 | 0.63 | 0.66 | 0.69 | 0.63 | 0.6 | 0.69 | 0.63 | 0.66 | 0.66 | 0.63 | 0.69 | 0.66 | 0.63 | 0.54
[6 empty] | unassigned subtotal = | 18.45 | 0.81 | 0.36 | 0.42 | 0.14 | 0.01 | 0 | 0 | 0.07 | 0.1 | 0.35 | 0.07 | 0.09 | 0.09 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0.44 | 0.57 | 0 | 0 | 0.01 | 0.01 | 0.01 | 0.38 | 1.08 | 0.65 | 0.53 | 0.34 | 0.64 | 0.67 | 0.7 | 0.64 | 0.61 | 0.7 | 0.64 | 0.67 | 0.67 | 1.04 | 0.7 | 0.67 | 0.63 | 1.51 | 1.1 | 0.19 |  | 18.64
[6 empty] | TOTAL FO&M ENGINEERS = | 199.41 | 6.38 | 5.47 | 4.72 | 4.49 | 4.4 | 4.86 | 4.37 | 4.63 | 5.72 | 4.5 | 4.42 | 5.21 | 4.7 | 5.29 | 5.42 | 5.05 | 5.15 | 4.62 | 4.38 | 5.06 | 5.48 | 4.67 | 3.6 | 4.12 | 4.23 | 4.96 | 4.6 | 4.7 | 5.82 | 4.57 | 3.58 | 3 | 3.34 | 3.34 | 2.95 | 3.39 | 3.06 | 3.79 | 3.23 | 3.15 | 3.25 | 3.64 | 3.39 | 3.15 | 2.81 | 3.29 | 1.46 | 0.19 |  | 199.6 | 9.339%
[6 empty] | Assigned = | 90.75%
| subtotal | = | ORNL | AKERS | Akers | Job: 8102 - NCSX MIE Management ORNL-LYON | 4.52 | 0.17 | 0.17 | 0.18 | 0.17 | 0.17 | 0.18 | 0.17 | 0.16 | 0.11 | 0.09 | 0.08 | 0.1 | 0.1 | 0.11 | 0.11 | 0.1 | 0.11 | 0.11 | 0.1 | 0.09 | 0.11 | 0.09 | 0.08 | 0.1 | 0.1 | 0.11 | 0.11 | 0.1 | 0.11 | 0.1 | 0.11 | 0.09 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 | 0.06 | 0.05 | 0.05 | 0.05 | 0.02
| subtotal | = | ORNL | BNELSON | BNelson | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 6.86 | 0.15 | 0.15 | 0.16 | 0.15 | 0.15 | 0.16 | 0.15 | 0.14 | 0.17 | 0.13 | 0.12 | 0.15 | 0.15 | 0.16 | 0.16 | 0.15 | 0.16 | 0.16 | 0.15 | 0.14 | 0.16 | 0.14 | 0.12 | 0.14 | 0.14 | 0.17 | 0.16 | 0.14 | 0.16 | 0.15 | 0.16 | 0.15 | 0.15 | 0.14 | 0.12 | 0.15 | 0.14 | 0.17 | 0.15 | 0.15 | 0.16 | 0.14 | 0.17 | 0.15 | 0.15 | 0.12
| subtotal | = | ORNL | COLE | Cole | Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE | 0.69 |  |  |  | 0.15 | 0.15 | 0.16 | 0.15 | 0.08
| subtotal | = | ORNL | COLE | Cole | Job: 1260 NB Transition Ducts- | 4.93 | [9 empty] | 0.02 | 0.45 | 0.43 | 0.43 | 1.04 | 0.81 | 0.77 | 0.34 | 0.03 | 0.04 | 0.04 | 0.03 | 0.04 | 0.04 | 0.03 | 0.03 | 0.04 | 0.03 | 0.03 | 0.03 | 0.03 | 0.04 | 0.04 | 0.03 | 0.04 | 0.03 | 0.02
| subtotal | = | ORNL | COLE | Cole | Job: 1806 - FP Assembly specs & drawings | 6.03 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67 | 0.67
| subtotal | = | ORNL | COLE | Cole | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 21.19 | 0.31 | 0.31 | 0.33 | 0.31 | 0.31 | 0.33 | 0.31 | 0.28 | 0.36 | 0.44 | 0.41 | 0.51 | 0.49 | 0.53 | 0.53 | 0.49 | 0.53 | 0.53 | 0.51 | 0.46 | 0.53 | 0.46 | 0.39 | 0.48 | 0.48 | 0.55 | 0.53 | 0.48 | 0.53 | 0.51 | 0.53 | 0.51 | 0.51 | 0.48 | 0.41 | 0.51 | 0.48 | 0.55 | 0.51 | 0.51 | 0.53 | 0.48 | 0.55 | 0.51 | 0.51 | 0.39
[6 empty] | COLE subtotal = |  | 0.98 | 0.98 | 1 | 1.13 | 1.13 | 1.16 | 1.13 | 1.03 | 1.03 | 0.46 | 0.86 | 0.94 | 0.92 | 1.57 | 1.34 | 1.26 | 0.87 | 0.56 | 0.55 | 0.5 | 0.56 | 0.5 | 0.43 | 0.51 | 0.51 | 0.59 | 0.56 | 0.51 | 0.56 | 0.54 | 0.57 | 0.55 | 0.54 | 0.52 | 0.44 | 0.53 | 0.48 | 0.55 | 0.51 | 0.51 | 0.53 | 0.48 | 0.55 | 0.51 | 0.51 | 0.39 | 0 | 0
| subtotal | = | ORNL | DIXON | Dixon | Job: 1601 - Coil Services Design-GORANSON | 3.59 | 0.32 | 0.32 | 0.33 | 0.32 | 0.42 | 0.64 | 0.61 | 0.09 | 0.19 | 0.15 | 0.14 | 0.06
| subtotal | = | ORNL | FOGARTY | Fogarty | Job: 7503 - Machine Assembly (station 6)-PERRY | 1.53 | [32 empty] | 0.48 |  |  |  | 0.27 | [5 empty] | 0.27 | 0.35 | 0.16
| subtotal | = | ORNL | FOGARTY | Fogarty | Job: 1802 - FP Assy Oversight&Support-VIOLA | 9.82 | 0.63 | 0.25 | 0.26 | 0.21 | 0.21 | 0.22 | 0.21 | 0.19 | 0.21 | 0.77 | 0.33 | 0.36 | 0.34 | 1.03 | 0.56 | 0.48 | 0.51 | 0.47 | 0.42 | 0.38 | 0.38 | 0.25 | 0.18 | 0.21 | 0.19 | 0.19 | 0.12 | 0.08 | 0.08 | 0.07 | 0.03
| subtotal | = | ORNL | FOGARTY | Fogarty | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 30.238 | 0.26213 | 0.26213 | 0.40234 | 0.38406 | 0.38406 | 0.40234 | 0.38406 | 0.37186 | 1.39 | 0.545 | 0.515 | 0.635 | 0.605 | 0.665 | 0.665 | 0.605 | 0.665 | 0.665 | 0.635 | 0.595 | 0.66 | 0.57 | 0.48 | 0.6 | 0.6 | 0.69 | 0.66 | 0.6 | 0.66 | 0.63 | 0.66 | 0.63 | 0.86 | 0.82 | 0.7 | 0.86 | 0.82 | 0.94 | 0.86 | 0.86 | 0.9 | 0.82 | 0.94 | 0.86 | 0.86 | 0.66
[6 empty] | FOGARTY subtotal = |  | 0.89213 | 0.51213 | 0.66234 | 0.59406 | 0.59406 | 0.62234 | 0.59406 | 0.56186 | 1.6 | 1.315 | 0.845 | 0.995 | 0.945 | 1.695 | 1.225 | 1.085 | 1.175 | 1.135 | 1.055 | 0.975 | 1.04 | 0.82 | 0.66 | 0.81 | 0.79 | 0.88 | 0.78 | 0.68 | 0.74 | 0.7 | 0.69 | 0.63 | 1.34 | 0.82 | 0.7 | 0.86 | 1.09 | 0.94 | 0.86 | 0.86 | 0.9 | 0.82 | 1.21 | 1.21 | 1.02 | 0.66 | 0 | 0
| subtotal | = | ORNL | Campbell | Fogarty | Job: 1901 - Stellarator Core Mngtt&Integr | 2.1068 | 0.19358 | 0.19358 | 0.29712 | 0.28361 | 0.28361 | 0.29712 | 0.28361 | 0.27461
| subtotal | = | ORNL | Holder | Fogarty | Job: 1901 - Stellarator Core Mngtt&Integr | 2.1068 | 0.19358 | 0.19358 | 0.29712 | 0.28361 | 0.28361 | 0.29712 | 0.28361 | 0.27461
| subtotal | = | ORNL | Benson | Fogarty | Job: 1901 - Stellarator Core Mngtt&Integr | 0.92174 | 0.084689 | 0.084689 | 0.12999 | 0.12408 | 0.12408 | 0.12999 | 0.12408 | 0.12014
| subtotal | = | ORNL | FREUDENBERG | Freudenberg | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 1.45 | 0.45 | 0.52 | 0.33 | 0.15
| subtotal | = | ORNL | FREUDENBERG | Freudenberg | Job: 1901 - Stellarator Core Mngtt&Integr |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
[6 empty] | FREUDENBERG subtotal = |  | 0.65 | 0.72 | 0.53 | 0.35 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| subtotal | = | ORNL | GORANSON | Goanson | Job: 1751 - Cryostat Procurement-RAFTOPOLOUS | 0.18 | [24 empty] | 0.01 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01
| subtotal | = | ORNL | GORANSON | Goanson | Job: 1270 - Heater Control System-PPPL ( tbd) | 0.55 | [12 empty] | 0.04 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0 | [18 empty] | 0.05 | 0.09 | 0.09 | 0.04
| subtotal | = | ORNL | GORANSON | Goanson | Job: 1601 - Coil Services Design-GORANSON | 11.57 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.64 | 0.6 | 0.6 | 0.51 | 0.48 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.05 | 0.04 | 0.06 | 0.06 | 0.06 | 0.04
[6 empty] | GORANSON subtotal = |  | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.89 | 0.64 | 0.6 | 0.6 | 0.55 | 0.53 | 0.11 | 0.1 | 0.11 | 0.11 | 0.06 | 0.06 | 0.06 | 0.05 | 0.04 | 0.06 | 0.07 | 0.08 | 0.06 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.01 | 0 | 0 | 0 | 0.05 | 0.09 | 0.09 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| subtotal | = | ORNL | HARRIS | Harris | Job: 8102 - NCSX MIE Management ORNL-LYON | 10.42 | 0.44 | 0.44 | 0.47 | 0.44 | 0.44 | 0.47 | 0.44 | 0.42 | 0.28 | 0.22 | 0.21 | 0.26 | 0.24 | 0.27 | 0.27 | 0.24 | 0.27 | 0.27 | 0.26 | 0.23 | 0.21 | 0.19 | 0.16 | 0.2 | 0.2 | 0.22 | 0.21 | 0.2 | 0.21 | 0.2 | 0.21 | 0.19 | 0.1 | 0.1 | 0.08 | 0.1 | 0.1 | 0.11 | 0.1 | 0.1 | 0.11 | 0.1 | 0.11 | 0.09 | 0.1 | 0.1 | 0.04
| subtotal | = | ORNL | HILLIS | Hillis | Job: 8102 - NCSX MIE Management ORNL-LYON | 2.08 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.1 | 0.11 | 0.09 | 0.08 | 0.1 | 0.1 | 0.11 | 0.11 | 0.1 | 0.11 | 0.11 | 0.1 | 0.09
| subtotal | = | ORNL | HOMESCU | Homescu | Job: 1601 - Coil Services Design-GORANSON | 5.5 | 0.36 | 0.36 | 0.37 | 0.36 | 0.36 | 0.37 | 0.26 | 0.46 | 0.51 | 0.4 | 0.37 | 0.46 | 0.44 | 0.42
| subtotal | = | ORNL | Moon |  | Job: 1806 - FP Assembly specs & drawings |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| subtotal | = | ORNL | LOVETT | Lovett | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 0.57 | 0.08 | 0.17 | 0.17 | 0.15
| subtotal | = | ORNL | LOVETT |  | Job: 1806 - FP Assembly specs & drawings |  | 0.2 | 0.2 | 0.5 | 0.75 | 0.75 | 0.75 | 0.3 | 0.5
| subtotal | = | ORNL | LOVETT | Cole | Job: 1355 - WBS 13 I&C Proc and Coil Assy-COLE |  |  |  |  | 0.35 | 0.35 | 0.35 | 0.35
[6 empty] | LOVETT subtotal = |  | 0.28 | 0.37 | 0.67 | 1.25 | 1.1 | 1.1 | 0.65 | 0.5
| subtotal | = | ORNL | MCGINNIS | McGinnis | Job: 7503 - Machine Assembly (station 6)-PERRY | 0.66 | [32 empty] | 0.24 |  |  |  | 0.13 | [5 empty] | 0.13 | 0.08 | 0.08
| subtotal | = | ORNL | MCGINNIS | Fogarty | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 14.235 | [9 empty] | 0.545 | 0.515 | 0.635 | 0.605 | 0.665 | 0.665 | 0.605 | 0.665 | 0.665 | 0.635 | 0.595 | 0.66 | 0.57 | 0.48 | 0.6 | 0.6 | 0.69 | 0.66 | 0.6 | 0.66 | 0.63 | 0.66 | 0.63
| subtotal | = | ORNL | MCGINNIS | McGinnis | Job: 1802 - FP Assy Oversight&Support-VIOLA | 9.26 | 0.63 | 0.25 | 0.26 | 0.21 | 0.21 | 0.22 | 0.21 | 0.19 | 0.21 | 0.21 | 0.33 | 0.36 | 0.34 | 1.03 | 0.56 | 0.48 | 0.51 | 0.47 | 0.42 | 0.38 | 0.38 | 0.25 | 0.18 | 0.21 | 0.19 | 0.19 | 0.12 | 0.08 | 0.08 | 0.07 | 0.03
| subtotal | = | ORNL | MCGINNIS |  | Job: 1806 - FP Assembly specs & drawings | 6.4 | 0.4 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
[6 empty] | MCGINNIS subtotal = |  | 1.03 | 1 | 1.01 | 0.96 | 0.96 | 0.97 | 0.96 | 0.94 | 0.96 | 0.755 | 0.845 | 0.995 | 0.945 | 1.695 | 1.225 | 1.085 | 1.175 | 1.135 | 1.055 | 0.975 | 1.04 | 0.82 | 0.66 | 0.81 | 0.79 | 0.88 | 0.78 | 0.68 | 0.74 | 0.7 | 0.69 | 0.63 | 0.24 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0.08 | 0.08 | 0 | 0 | 0
| subtotal | = | ORNL | MMORRIS | Mike Morris | Job: 8102 - NCSX MIE Management ORNL-LYON | 5.39 | 0.28 | 0.28 | 0.29 | 0.28 | 0.28 | 0.29 | 0.28 | 0.26 | 0.11 | 0.09 | 0.08 | 0.1 | 0.1 | 0.11 | 0.11 | 0.1 | 0.11 | 0.11 | 0.1 | 0.09 | 0.11 | 0.09 | 0.08 | 0.1 | 0.1 | 0.11 | 0.11 | 0.1 | 0.11 | 0.1 | 0.11 | 0.09 | 0.05 | 0.05 | 0.04 | 0.05 | 0.05 | 0.06 | 0.05 | 0.05 | 0.05 | 0.05 | 0.06 | 0.05 | 0.05 | 0.05 | 0.02
| subtotal | = | ORNL | WILLIAMSON | Williamson | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 0.57 | 0.08 | 0.17 | 0.17 | 0.15
| subtotal | = | ORNL | WILLIAMSON | Williamson | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1.03 | 1.01 | 0.02
[6 empty] | WILLIAMSON subtotal = |  | 1.09 | 0.19 | 0.17 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | TOTAL ORNL = | 164.3984 | 8.6421 | 7.4921 | 7.8423 | 8.1541 | 7.8041 | 8.1623 | 7.4441 | 6.7519 | 7.16 | 4.19 | 4.23 | 4.76 | 4.49 | 6.67 | 4.66 | 4.22 | 4.09 | 3.7 | 3.43 | 3.15 | 3.29 | 2.7 | 2.23 | 2.73 | 2.7 | 3.04 | 2.77 | 2.43 | 2.65 | 2.51 | 2.56 | 2.35 | 2.49 | 1.69 | 1.42 | 1.74 | 2.04 | 1.94 | 1.81 | 1.81 | 1.84 | 1.64 | 2.29 | 2.14 | 1.96 | 1.37 | 0.08 | 0 |  | 175.263 |  |  | 98.19 | 848.393 | 89.63%
[6 empty] | Assigned = | 100% | [52 empty] | 946.583
[8 empty] | FEB FY08 | MAR FY08 | APR FY08 | MAY FY08 | JUN FY08 | JUL FY08 | AUG FY08 | SEP FY08 | OCT FY09 | NOV FY09 | DEC FY09 | JAN FY09 | FEB FY09 | MAR FY09 | APR FY09 | MAY FY09 | JUN FY09 | JUL FY09 | AUG FY09 | SEP FY09 | OCT FY10 | NOV FY10 | DEC FY10 | JAN FY10 | FEB FY10 | MAR FY10 | APR FY10 | MAY FY10 | JUN FY10 | JUL FY10 | AUG FY10 | SEP FY10 | OCT FY11 | NOV FY11 | DEC FY11 | JAN FY11 | FEB FY11 | MAR FY11 | APR FY11 | MAY FY11 | JUN FY11 | JUL FY11 | AUG FY11 | SEP FY11 | OCT FY12 | NOV FY12
|  |  |  | TOTAL DESIGNERS |  |  |  | 6.96 | 5.93 | 6.17 | 4.13 | 3.54 | 3.17 | 2.85 | 2.81 | 4.09 | 2.5 | 2.36 | 3.85 | 4.1 | 5.23 | 5.24 | 5.37 | 5.25 | 3.91 | 3.36 | 3.3 | 4.73 | 4.19 | 3.22 | 3.85 | 3.39 | 3.99 | 3.58 | 4.63 | 3.34 | 2.63 | 3.13 | 3.54 | 3.85 | 3.92 | 2.86 | 2.62 | 1.45 | 1.32 | 1.01 | 1.01 | 1.2 | 1.99 | 2.14 | 2.17 | 1.95 | 1.68
|  |  |  | TOTAL EA ENGINEERS |  |  |  | 13.8 | 12.12 | 10.68 | 9.72 | 11.52 | 11.07 | 6.61 | 6.44 | 8.72 | 6.38 | 6.06 | 7.31 | 6.88 | 7.57 | 7.91 | 7.73 | 8.34 | 7.77 | 7.52 | 7.55 | 7.84 | 6.5 | 5.42 | 6.63 | 6.48 | 6.9 | 6.18 | 5.3 | 5.43 | 4.91 | 4.88 | 4.18 | 3.49 | 3.65 | 2.92 | 3.21 | 2.92 | 3.36 | 3.42 | 3.25 | 3.11 | 2.82 | 3.52 | 3.51 | 4.13 | 2.8
|  |  |  | TOTAL Electrical ENGINEERS |  |  |  | 0.16 | 0.16 | 0.16 | 0.23 | 0.32 | 1.68 | 1.09 | 0.99 | 1.96 | 1.13 | 1.04 | 1.47 | 1.75 | 2.53 | 2.53 | 3.34 | 3.53 | 1.65 | 1.36 | 1.06 | 2.08 | 1.9 | 1.55 | 2.1 | 2.49 | 3.19 | 2.8 | 1.92 | 1.61 | 1.89 | 2.03 | 2.37 | 2.78 | 2.91 | 2.9 | 3.29 | 2.73 | 2.18 | 0.9 | 0.65 | 0.88 | 2.72 | 2.32 | 0.39 | 0.14 | 0.99
|  |  |  | TOTAL FO&M ENGINEERS |  |  |  | 6.38 | 5.47 | 4.72 | 4.49 | 4.4 | 4.86 | 4.37 | 4.63 | 5.72 | 4.5 | 4.42 | 5.21 | 4.7 | 5.29 | 5.42 | 5.05 | 5.15 | 4.62 | 4.38 | 5.06 | 5.48 | 4.67 | 3.6 | 4.12 | 4.23 | 4.96 | 4.6 | 4.7 | 5.82 | 4.57 | 3.58 | 3 | 3.34 | 3.34 | 2.95 | 3.39 | 3.06 | 3.79 | 3.23 | 3.15 | 3.25 | 3.64 | 3.39 | 3.15 | 2.81 | 3.29
|  |  |  | Metrology staff |  |  |  | 0 | 0 | 1.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22 | 0.21 | 0.2 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09 | 0.09 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL Computing ENGINEERS |  |  |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.07 | 0.06 | 0.05 | 0.07 | 0.19 | 0.21 | 0.36 | 1.19 | 1.06 | 0.21 | 0.88 | 0.94 | 1.86 | 2.44 | 2.09 | 2.2 | 2.54 | 2.26 | 1.62 | 1.37 | 1.63 | 1.51 | 1.87 | 2.3 | 2.28 | 1.96 | 1.4 | 2.38 | 2.36 | 0.47 | 0.17 | 0.17 | 0.12 | 0.06 | 0.07 | 0.06 | 0 | 0.86
|  |  |  | ornl |  |  |  | 8.6421 | 7.4921 | 7.8423 | 8.1541 | 7.8041 | 8.1623 | 7.4441 | 6.7519 | 7.16 | 4.19 | 4.23 | 4.76 | 4.49 | 6.67 | 4.66 | 4.22 | 4.09 | 3.7 | 3.43 | 3.15 | 3.29 | 2.7 | 2.23 | 2.73 | 2.7 | 3.04 | 2.77 | 2.43 | 2.65 | 2.51 | 2.56 | 2.35 | 2.49 | 1.69 | 1.42 | 1.74 | 2.04 | 1.94 | 1.81 | 1.81 | 1.84 | 1.64 | 2.29 | 2.14 | 1.96 | 1.37 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Metrology |  |  |  | 1.2 | 2.2 | 2.7 | 7 | 3 | 4.8 | 5.6 | 3.5 | 6.1 | 5.8 | 3.9 | 8.2 | 5.8 | 4 | 5.3 | 4.4 | 5.8 | 5 | 4.2 | 4 | 5.2 | 3.1 | 1.8 | 3.2 | 4.1 | 3.3 | 3.3 | 5.1 | 3.1 | 2.8 | 1 | 0.5 | 0.3 | 1.3 | 2.5 | 0.8 | 3.9 | 1.3 | 1.7 | 1.5 | 0.3 | 0.2 | 0.5
|  |  |  | ornl wbs 81 |  |  |  | 1 | 1 | 1.05 | 1 | 1 | 1.05 | 1 | 0.94 | 0.61 | 0.49 | 0.45 | 0.56 | 0.54 | 0.6 | 0.6 | 0.54 | 0.6 | 0.6 | 0.56 | 0.5 | 0.43 | 0.37 | 0.32 | 0.4 | 0.4 | 0.44 | 0.43 | 0.4 | 0.43 | 0.4 | 0.43 | 0.37 | 0.2 | 0.2 | 0.16 | 0.2 | 0.2 | 0.23 | 0.2 | 0.2 | 0.21 | 0.2 | 0.23 | 0.19 | 0.2 | 0.2 | 0.08
|  |  |  | ornl technical support |  |  |  | 7.6421 | 6.4921 | 6.7923 | 7.1541 | 6.8041 | 7.1123 | 6.4441 | 5.8119 | 6.55 | 3.7 | 3.78 | 4.2 | 3.95 | 6.07 | 4.06 | 3.68 | 3.49 | 3.1 | 2.87 | 2.65 | 2.86 | 2.33 | 1.91 | 2.33 | 2.3 | 2.6 | 2.34 | 2.03 | 2.22 | 2.11 | 2.13 | 1.98 | 2.29 | 1.49 | 1.26 | 1.54 | 1.84 | 1.71 | 1.61 | 1.61 | 1.63 | 1.44 | 2.06 | 1.95 | 1.76 | 1.17 | -0.08
current assigned levels