## P3
NCSX FLAT FUNDING SCENARIO
|  | TOTAL | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2012 | FY2013
1204 | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 411 |  |  |  |  | 47 | 162 | 1 | 84 | 117 |  |  | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK
1250 | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -252 |  |  |  |  | -252 | [6 empty] | Job: 1250 - Vacuum Vessel Fabrication**CLOSED**
1302 | Job: 1302 - PF Design -KALISH | 257 |  |  |  |  | 44 | 213 | [5 empty] | Job: 1302 - PF Design -KALISH
1352 | Job: 1352 - PF Coil Procurement-KALISH | 1630 | [5 empty] | 968 | 634 | 28 |  |  |  | Job: 1352 - PF Coil Procurement-KALISH
1353 | Job: 1353 - CS Structure Procurement-DAHLGREN | 337 | [6 empty] | 78 | 259 |  |  |  | Job: 1353 - CS Structure Procurement-DAHLGREN
1354 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 162 | [6 empty] | 162 |  |  |  |  | Job: 1354 - Trim Coil Design &Procurement-KALISH
1355 | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 73 | [5 empty] | 32 | 39 | 2 |  |  |  | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH
1361 | Job: 1361 - TF Fabrication-KALISH | 1003 |  |  |  |  | 228 | 775 | [5 empty] | Job: 1361 - TF Fabrication-KALISH
1404 | Job: 1404 - MCWF R&D 1st Prod | -36 |  |  |  |  | -36 | [6 empty] | Job: 1404 - MCWF R&D 1st Prod
1408 | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 350 |  |  |  |  | 178 | 172 | [5 empty] | Job: 1408 - MC Winding Supplies-CHRZANOWSKI
1411 | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -80 |  |  |  |  | -80 | [6 empty] | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER
1416 | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 280 |  |  |  |  | 70 | 210 | [5 empty] | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON
1421 | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1208 |  |  |  |  | 996 | 212 | [5 empty] | Job: 1421 - Mod Coil Interface Design-WILLIAMSON
| Job: 1429 - MC Interface R&D-GETTELFINGER | 118 |  |  |  |  | 118 | [6 empty] | Job: 1429 - MC Interface R&D-GETTELFINGER
1431 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1039 |  |  |  |  | 362 | 660 |  | 17 |  |  |  | Job: 1431 - Mod. Coil Interface Hardware-DUDEK
1451 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2862 |  |  |  |  | 1141 | 1721 | [5 empty] | Job: 1451 - Mod Coil Winding-CHRZANOWSKI
1459 | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 501 |  |  |  |  | 90 | 411 | [5 empty] | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI
1501 | Job: 1501 - Coil Structures Design-DAHLGREN | 186 |  |  |  |  | 164 | 22 | [5 empty] | Job: 1501 - Coil Structures Design-DAHLGREN
1550 | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 1077 | [5 empty] | 370 | 707 |  |  |  |  | Job: 1550 - Coil Struct. Procurement -DAHLGREN
1601 | Job: 1601 - Coil Services Design-GORANSON | 861 |  |  |  |  | 6 | 323 | 372 | 160 |  |  |  | Job: 1601 - Coil Services Design-GORANSON
1701 | Job: 1701 - Cryostat Design-GETTLEFINGER | 207 | [6 empty] | 207 |  |  |  |  | Job: 1701 - Cryostat Design-GETTLEFINGER
1702 | Job: 1702 - Base Support Struct Design-DAHLGREN | 163 | [5 empty] | 163 | [5 empty] | Job: 1702 - Base Support Struct Design-DAHLGREN
1751 | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 327 | [7 empty] | 263 | 64 |  |  | Job: 1751 - Cryostat Procurement-GETTLEFINGER
1752 | Job: 1752 - Base Support Proc-DAHLGREN | 89 | [5 empty] | 61 | 28 |  |  |  |  | Job: 1752 - Base Support Proc-DAHLGREN
1802 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 2153 |  |  |  |  | 253 | 781 | 773 | 346 |  |  |  | Job: 1802 - FP Assy Oversight&Support-VIOLA
1803 | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 |  |  |  |  | 131 | 316 | 75 |  |  |  |  | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK
1806 | Job: 1806 - FP Assembly specs | 514 |  |  |  |  | 92 | 382 | 40 |  |  |  |  | Job: 1806 - FP Assembly specs
1810 | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 5918 |  |  |  |  | 1266 | 2353 | 1673 | 626 |  |  |  | Job:1810-Field Period Assy -Station 1 2 3 VIOLA
1815 | Job: 1815 - Field Period Assy | 1354 | [5 empty] | 223 | 442 | 689 |  |  |  | Job: 1815 - Field Period Assy
1901 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 1889 |  |  |  |  | 162 | 408 | 432 | 448 | 439 |  |  | Job: 1901 - Stellarator Core Mngtt&Integr-COLE
2101 | Job: 2101 - Fueling Systems-BLANCHARD | 70 | [6 empty] | 13 | 31 | 26 |  |  | Job: 2101 - Fueling Systems-BLANCHARD
2201 | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 172 | [6 empty] | 70 | 102 |  |  |  | Job: 2201 - Vacuum Pumping Systems-BLANCHARD
3101 | Job: 3101 - Magnetic Diagnostics-STRATTON | 291 |  |  |  |  | 184 | 107 | [5 empty] | Job: 3101 - Magnetic Diagnostics-STRATTON
3601 | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 31 | [7 empty] | 31 |  |  |  | Job: 3601 - Edge Divertor Diagnostics-STRATTON
3801 | Job: 3801 - Electron Beam Mapping-STRATTON | 263 | [6 empty] | 101 | 162 |  |  |  | Job: 3801 - Electron Beam Mapping-STRATTON
3901 | Job: 3901 - Diagnostics sys Integration-STRATTON | 132 |  |  |  |  | 11 | 29 | 30 | 62 |  |  |  | Job: 3901 - Diagnostics sys Integration-STRATTON
4101 | Job: 4101 - AC Power-RAMAKRISHNAN | 54 |  |  |  |  | -104 |  | 50 | 108 |  |  |  | Job: 4101 - AC Power-RAMAKRISHNAN
4301 | Job: 4301 - DC Systems-RAMAKRISHNAN | 606 | [5 empty] | 11 | 188 | 407 |  |  |  | Job: 4301 - DC Systems-RAMAKRISHNAN
4401 | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1093 | [6 empty] | 202 | 717 | 174 |  |  | Job: 4401 - Control & Protection-RAMAKRISHNAN
4501 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 689 | [6 empty] | 349 | 118 | 222 |  |  | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN
5101 | Job: 5101 - Network and Fiber | 151 | [6 empty] | 6 | 145 |  |  |  | Job: 5101 - Network and Fiber
5201 | Job: 5201 - I&C Systems-SICHTA | 200 | [6 empty] | 10 | 155 | 35 |  |  | Job: 5201 - I&C Systems-SICHTA
5301 | Job: 5301 - Data Acquisition-SICHTA | 165 | [6 empty] | 11 | 144 | 10 |  |  | Job: 5301 - Data Acquisition-SICHTA
5401 | Job: 5401 - Facility Timing & | 205 | [6 empty] | 8 | 197 |  |  |  | Job: 5401 - Facility Timing &
5501 | Job: 5501 - Real Time Control | 129 | [6 empty] | 16 | 113 |  |  |  | Job: 5501 - Real Time Control
5601 | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 223 | [7 empty] | 199 | 24 |  |  | Job: 5601 - Central Safety &Interlock Sys-SICHTA
5801 | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 83 |  |  |  |  | 7 | 24 | 19 | 19 | 14 |  |  | Job: 5801 - Central I&C Integr& Oversight-SICHTA
6101 | Job: 6101 - Water Systems-DUDEK | 47 | [6 empty] | 42 | 5 |  |  |  | Job: 6101 - Water Systems-DUDEK
6201 | Job: 6201 - Cryogenic Syst-GETTELFINGER | 655 | [6 empty] | 271 | 384 |  |  |  | Job: 6201 - Cryogenic Syst-GETTELFINGER
6301 | Job: 6301 - Utility Systems-DUDEK | 105 | [6 empty] | 105 |  |  |  |  | Job: 6301 - Utility Systems-DUDEK
6401 | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 574 | [6 empty] | 86 | 488 |  |  |  | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH
7301 | Job: 7301 - Platform Design & | 204 |  |  |  |  | 2 | 5 | 197 |  |  |  |  | Job: 7301 - Platform Design &
7401 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1422 |  |  |  |  | -308 | 23 | 333 | 671 | 703 |  |  | Job: 7401 - TC Prep & Mach Assy Planning-PERRY
7501 | Job: 7501 - Construction Support Crew-PERRY | 1372 | [6 empty] | 154 | 467 | 751 |  |  | Job: 7501 - Construction Support Crew-PERRY
7503 | Job: 7503 - Machine Assembly (station 6)-PERRY | 4564 | [6 empty] | 1244 | 1565 | 1755 |  |  | Job: 7503 - Machine Assembly (station 6)-PERRY
7601 | Job: 7601 - Tooling Design & Fabrication-PERRY | 416 | [6 empty] | 102 | 296 | 18 |  |  | Job: 7601 - Tooling Design & Fabrication-PERRY
8101 | Job: 8101 - Project Management & Control-NEILSON | 4330 |  |  |  |  | 278 | 1034 | 1158 | 1074 | 786 |  |  | Job: 8101 - Project Management & Control-NEILSON
8102 | Job: 8102 - NCSX MIE Management ORNL-LYON | 530 |  |  |  |  | 60 | 159 | 159 | 102 | 50 |  |  | Job: 8102 - NCSX MIE Management ORNL-LYON
8202 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2953 |  |  |  |  | 476 | 659 | 657 | 654 | 507 |  |  | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN
8203 | Job: 8203 - Design Integration-BROWN | 1480 |  |  |  |  | 148 | 349 | 347 | 346 | 290 |  |  | Job: 8203 - Design Integration-BROWN
8204 | Job: 8204 - Systems Analysis-BROOKS | 1162 |  |  |  |  | 169 | 266 | 265 | 264 | 198 |  |  | Job: 8204 - Systems Analysis-BROOKS
8205 | Job: 8205 - Dimensional Control Coordin-ELLIS | 599 |  |  |  |  | 102 | 258 | 129 | 76 | 34 |  |  | Job: 8205 - Dimensional Control Coordin-ELLIS
8210 | Job: 8210 - FY07 Rebaseling tasks | 19 |  |  |  |  | 19 | [6 empty] | Job: 8210 - FY07 Rebaseling tasks
8215 | Job: 8215 Plant Design | 135 |  |  |  |  | 15 | 32 | 32 | 32 | 24 |  |  | Job: 8215 Plant Design
8501 | Job: 8501 - Integrated Systems Testing-GENTILE | 767 | [6 empty] | 211 | 137 | 419 |  |  | Job: 8501 - Integrated Systems Testing-GENTILE
8998 | Job: 8998 - Allocations-STRYKOWSKY | 1570 |  |  |  |  | 144 | 384 | 406 | 431 | 205 |  |  | Job: 8998 - Allocations-STRYKOWSKY
Contingency-Project
| ETC (from May1st 2007)= | 52584 |  |  |  |  | 6183 | 14278 | 12634 | 12624 | 6865 |  |  | Actual Cost
52584
| Contingency = | 14858 | 28.26% |  |  |  | 144 | 1622 | 3266 | 3276 | 6550
[8 empty] | 11.36% | 25.85% | 25.95% | 95.41%
| Actual Cost (through April 30th)= | 67178.41 | 5941.92 | 14314.35 | 18131.61 | 19072.81 | 9717.72
| EAC = | 134620.41 | 5942.2026 | 14314.35 | 18131.61 | 19072.81 | 16044.72 | 15900 | 15900 | 15900 | 13415
| MIE Funding = | [5 empty] | 16771 | 15900 | 15900 | 15900 | 13415 | 0
| Research Funding = | [5 empty] | 680 | 720 | 720 | 720 | 3205 | 16620 | 45000
| TOTAL PROGRAM FUNDING = | [5 empty] | 17451 | 16620 | 16620 | 16620 | 16620 | 16620 | 45000
[8 empty] | 16620 | 16620 | 16620 | 16620 | 16620 | 45000
PPPL
| Plan with all contingency = | 117717.23 | 4795.65 | 11466.93 | 15970.77 | 17296.55 | 13953.22 | 14860.17 | 14697.79 | 15115.36 | 9560.79 | 132009.74 |  | 132009.74
| Funding= | [5 empty] | 15152 | 14950
| ORNL | [12 empty] | 132009.74
| Plan= | 14292.51 | 1146.27 | 2847.42 | 2160.84 | 1776.26 | 2089.85 | 1767.86 | 1202.23 | 784.95 | 516.83
| Funding= | [5 empty] | 1619 | 950
|  |  | Planned Finish = | 2011-08-02
|  |  | CD-4= | 2012-07-02
|  |  | Schedule Contingency = | 11.0161 | months
Changes from Wednesday
Cost Increases
| Title III for PF and TF contract | 84 |  |  |  |  | 1 | 91 | -8
| Winding Punch list insert repair | 16 |  |  |  |  | -13 | 29
| 1802 FPA add'l 2nd shift to keep schedule | 22
| 1810 FPA station 2 & 3 Bushings($200k) and add'l tasks | 260
| contingency increment | 114
496
Schedule changes
| Job: 1601 - Coil Services Design-GORANSON | -11 | [5 empty] | 139 | -73 | -78
| Job: 1352 - PF Coil Procurement-KALISH | 34 | [5 empty] | 42 | -8 | 0
| Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | -7 | [5 empty] | 72 | 1 | -80
| Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 2 |  |  |  |  | -54 | 55
[7 empty] | -66 | 428 | -88 | -158 | 0
| Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | -7 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | -80 | 0
| Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1302 - PF Design -KALISH | 4 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0
| Job: 1352 - PF Coil Procurement-KALISH | 34 | 0 | 0 | 0 | 0 | 0 | 42 | -8 | 0 | 0
| Job: 1353 - CS Structure Procurement-DAHLGREN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1354 - Trim Coil Design &Procurement-KALISH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 0 | 0 | 0 | 0 | 0 | 0 | -9 | 10 | 0 | 0
| Job: 1361 - TF Fabrication-KALISH | 50 | 0 | 0 | 0 | 0 | 1 | 49 | 0 | 0 | 0
| Job: 1404 - MCWF R&D 1st Prod | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 2 | 0 | 0 | 0 | 0 | -54 | 55 | 0 | 0 | 0
| Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 16 | 0 | 0 | 0 | 0 | -13 | 29 | 0 | 0 | 0
| Job: 1501 - Coil Structures Design-DAHLGREN | 1 | 0 | 0 | 0 | 0 | -22 | 22 | 0 | 0 | 0
| Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1601 - Coil Services Design-GORANSON | -11 | 0 | 0 | 0 | 0 | 0 | 139 | -73 | -78 | 0
| Job: 1701 - Cryostat Design-GETTLEFINGER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1702 - Base Support Struct Design-DAHLGREN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 1752 - Base Support Proc-DAHLGREN | 1 | 0 | 0 | 0 | 0 | 0 | -8 | 8 | 0 | 0
| Job: 1802 - FP Assy Oversight&Support-VIOLA | 22 | 0 | 0 | 0 | 0 | 0 | -3 | 21 | 5 | 0
| Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 0 | 0 | 0 | 0 | 0 | -10 | 11 | 0 | 0 | 0
| Job: 1806 - FP Assembly specs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 260 | 0 | 0 | 0 | 0 | 0 | -50 | 300 | 10 | 0
| Job: 1815 - Field Period Assy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 5 | 0
| Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 2101 - Fueling Systems-BLANCHARD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -43 | 45 | 0
| Job: 3101 - Magnetic Diagnostics-STRATTON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 3801 - Electron Beam Mapping-STRATTON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 2 | 0
| Job: 3901 - Diagnostics sys Integration-STRATTON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 4101 - AC Power-RAMAKRISHNAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0
| Job: 4301 - DC Systems-RAMAKRISHNAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 4401 - Control & Protection-RAMAKRISHNAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 5101 - Network and Fiber | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 5201 - I&C Systems-SICHTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 5301 - Data Acquisition-SICHTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 5401 - Facility Timing & | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 5501 - Real Time Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 5601 - Central Safety &Interlock Sys-SICHTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 5801 - Central I&C Integr& Oversight-SICHTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 6101 - Water Systems-DUDEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 6201 - Cryogenic Syst-GETTELFINGER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 6301 - Utility Systems-DUDEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 3 | 0 | 0 | 0 | 0 | 0 | 0 | -138 | 141 | 0
| Job: 7301 - Platform Design & | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 7501 - Construction Support Crew-PERRY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 7503 - Machine Assembly (station 6)-PERRY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 7601 - Tooling Design & Fabrication-PERRY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8101 - Project Management & Control-NEILSON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8102 - NCSX MIE Management ORNL-LYON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8203 - Design Integration-BROWN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8204 - Systems Analysis-BROOKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8205 - Dimensional Control Coordin-REIERSEN | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 1 | 2 | 0
| Job: 8210 - FY07 Rebaseling tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8215 Plant Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8501 - Integrated Systems Testing-GENTILE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Job: 8998 - Allocations-STRYKOWSKY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ETC (from May1st 2007)= | 377 | 0 | 0 | 0 | 0 | -101 | 353 | 59 | 65 | 0
| Contingency = | 114 | 0.00051407 | 0 | 0 | 0 | 166 | -386 | -62 | 396 | 0
[7 empty] | 0.060297 | 0.14768 | 0.25685 | 0.26234 | 0.75311
[7 empty] | Gruber range = | 9%-17% | 0.21 | 0.28
| Actual Cost (through April 30th)= | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EAC = | 491 | 0.00051407 | 0 | 0 | 0 | 65 | -33 | -3 | 461 | 0
| Funding = | [5 empty] | 16771 | 15900 | 18200 | 18900 | 19500
PPPL
| Plan with all contingency = | 495 | 0 | 0 | 0 | 0 | 67 | -105 | 69 | 464 | 0
| Funding= | [5 empty] | 15152 | 14950
ORNL
| Plan= | -4 | 0 | 0 | 0 | 0 | 0 | 73 | -74 | -3 | 0
| Funding= | [5 empty] | 1619 | 950
|  | pppl | 4796 | 11467 | 15971 | 17297 | 13976 | 14822 | 17262 | 15699 | 4688
|  | ornl | 1146 | 2847 | 2161 | 1776 | 2090 | 1776 | 1299 | 723 | 212
[5 empty] | conservative= |  |  | 0.167 | 0.2041 | 0.28027 | 0.56043
[7 empty] | 14680 | 14123 | 16901 | 16361 | 4688
[7 empty] | 2090 | 1776 | 1299 | 723 | 212
132009.74