## Sheet1
|  |  |  | PROJECT ESTIMATE | [9 empty] | DOE Review Estimate
[5 empty] | Allocation of Contingency Allowances | [9 empty] | Contingency
| WBS | Baseline (ECP-31 DOE Directed re-baseline April 2005) | ACWP (Through 4/30/07) | ETC | Uncertainty | Schedule | Sched Mitig | Risk | Management Increment ("unknown unknowns") | Total | % of ETC | TOTAL EAC with contingency | Increase explanation | ETC | Total | % of ETC | TOTAL EAC
12 | Vacuum Vessel | 9531 | 9753 | 156 | 29.6375 |  |  | 10.4425 | 0 | 40.08 | 25.69% | 9949.08 | Heating and cooling system re-design |  |  | #DIV/0! | 9753
13 | Conventional Coils | 4790 | 3226 | 3462 | 527.3565 |  |  | 175.1056 | 200 | 902.4621 | 26.07% | 7590.4621 | TF coil fabrication $1.5m and PF coil fabrication $0.4m based on vendor quotes. |  |  | #DIV/0! | 3226
14 | Modular Coils | 28091.4 | 34196 | 6247 | 1002.0523 |  |  | 405.7351 | 200 | 1607.7874 | 25.74% | 42050.7874 | Design/R&D $3.3m, Winding form fabrication $1.5m, Mod coil winding $6.5m, Coil testing $1.0m |  |  | #DIV/0! | 34196
15 | Structures | 1413 | 335 | 1262 | 173.2647 |  |  | 7.9662 | 100 | 281.2309 | 22.28% | 1878.2309 | Redesign of concept to cheaper fabrication |  |  | #DIV/0! | 335
16 | Coil Services | 1140 | 3 | 861 | 66.7872 |  |  | 225.0106 | 100 | 391.7979 | 45.5% | 1255.7979 | Simplification in the electrical & coolant circuit configuration |  |  | #DIV/0! | 3
17 | Cryostat & Base Support Structure | 1361 | 431 | 784 | 111.7813 |  |  | 4.9534 | 100 | 216.7347 | 27.64% | 1431.7347 | Simpler cryostat based on experience gained with the coil test facility as well as a stationary base support structure |  |  | #DIV/0! | 431
18 | Field Period Assembly | 5430 | 3479 | 10104 | 1645.4569 |  | 355.2814 | 127.1874 | 885 | 3012.9257 | 29.82% | 16595.9257 | More mature assy sequence plan as well as a better appreciation of metrology and dimensional control reqmnts. |  |  | #DIV/0! | 3479
19 | Stellarator Core Mgmt & Integr | 2752 | 2128 | 1620 | 127.1447 | 179.366 |  | 10.2213 | 0 | 316.7321 | 19.55% | 4064.7321 | Title III support of assy, CAD modeling as well as project stretch-out. |  |  | #DIV/0! | 2128
2 | Auxiliary Systems | 783.44 | 348 | 241 | 34.0614 |  |  | 1.5175 |  | 35.5789 | 14.76% | 624.5789 | Fueling and vacuum pumping system designs simplified. |  |  | #DIV/0! | 348
3 | Diagnostics | 1143.44 | 954 | 717 | 83.663 |  |  | 4.5258 |  | 88.1888 | 12.3% | 1759.1888 | Fabrication of magnetic diagnostic loops and first plasma imaging/ e-beam mapping equipt. |  |  | #DIV/0! | 954
4 | Electrical Power Systems | 3301.44 | 720 | 2425 | 182.33 |  |  | 52.7055 | 150 | 385.0355 | 15.88% | 3530.0355 | Cost growth offset by reduction in reqmnts (controls, number of circuits to minimum req'd for CD-4. |  |  | #DIV/0! | 720
5 | I&C Systems | 2050.4 | 33 | 1136 | 155.8583 |  |  | 7.169 | 0 | 163.0274 | 14.35% | 1332.0274 | Reqmnts reduced to minimum req'd to satisfy CD-4. |  |  | #DIV/0! | 33
6 | Facility Systems | 691.4 | 24 | 1379 | 372.2653 |  |  | 8.7037 | 0 | 380.969 | 27.63% | 1783.969 | Bake-out system added $.6m and cryogenic system cost growth based on experience. |  |  | #DIV/0! | 24
7 | Test Cell Prep & Machine Assy | 4413.4 | 963 | 7951 | 2374.6555 |  |  | 161.6839 | 500 | 3036.3394 | 38.19% | 11950.3394 | More mature assy sequence plan as well as a better appreciation of metrology and dimensional control reqmnts. |  |  | #DIV/0! | 963
81 | Project Management | 4508.5 | 3376 | 4342 | 375 | 1122 |  | 79 |  | 1576 | 36.3% | 9294 | Addition of a construction manager, add'l project control staff, as well as project stretch-out cost. |  |  | #DIV/0! | 3376
82 | Project Engineering | 4884.5 | 5248 | 5948 | 600 | 628 |  |  |  | 1228 | 20.65% | 12424 | Dimensional control planning, support of metrology ops, on on-going CAD modeling,& engineering analysis. |  |  | #DIV/0! | 5248
84 | Project Physics | 470 | 470 | [6 empty] | 0 |  | 470 |  |  |  | #DIV/0! | 470
85 | Start-up | 1189 | 0 | 764.83 | 75 |  |  |  | 125 | 200 | 26.15% | 964.83 | Test plans streamlined based on NSTX experience. |  |  | #DIV/0! | 0
89 | Allocations | 1577.4 | 1416 | 1453.77 | 100 | 417 |  |  |  | 517 | 35.56% | 3386.77 | Indirect overhead as a function of project stretch-out. |  |  | #DIV/0! | 1416
| dcma | 75 | 75 | [8 empty] | 75 |  |  |  |  | 75
| contingency | 12804.4
| Total | 92400.72 | 67178 | 50853.6 | 8036.3147 | 2346.366 | 355.2814 | 1281.9276 | 2360 | 14379.8897 | 28.28% | 132411.4897 |  | 0 | 0 | #DIV/0! | 67178
Note on G6: Chris Gruber: Based on % of total Uncertainty Contingency)- see Uncertainty Results worksheets
Note on H6: Chris Gruber: Total of both Uncertainty and Risk schedule contingency cost allowance split on basis of contribution to standing army calc - see Mis Inputs sheet
Note on J6: Chris Gruber: Based on % of total risk impact by WBS -- see Risk Model worksheet

## Sheet2
NCSX System Design budget relative to total ETC
|  |  |  | PROJECT ESTIMATE | [11 empty] | DOE Review Estimate
[7 empty] | Allocation of Contingency Allowances | [9 empty] | Contingency
| WBS | Baseline (ECP-31 DOE Directed re-baseline April 2005) | ACWP (Through 4/30/07) | ETC | Engineering through FDR's (1) | % of ETC | Uncertainty | Schedule | Sched Mitig | Risk | Management Increment ("unknown unknowns") | Total | % of ETC | TOTAL EAC with contingency | Increase explanation | ETC | Total | % of ETC | TOTAL EAC
12 | Vacuum Vessel | 9531 | 9753 | 156 | 0 | 0% | 29.6375 |  |  | 10.4425 | 0 | 40.08 | 25.69% | 9949.08 | Heating and cooling system re-design |  |  | #DIV/0! | 9753
13 | Conventional Coils | 4790 | 3226 | 3462 | 328 | 9.474% | 527.3565 |  |  | 175.1056 | 200 | 902.4621 | 26.07% | 7590.4621 | TF coil fabrication $1.5m and PF coil fabrication $0.4m based on vendor quotes. |  |  | #DIV/0! | 3226
14 | Modular Coils | 28091.4 | 34196 | 6247 | 1243 | 19.9% | 1002.0523 |  |  | 405.7351 | 200 | 1607.7874 | 25.74% | 42050.7874 | Design/R&D $3.3m, Winding form fabrication $1.5m, Mod coil winding $6.5m, Coil testing $1.0m |  |  | #DIV/0! | 34196
15 | Structures | 1413 | 335 | 1262 | 156 | 12.36% | 173.2647 |  |  | 7.9662 | 100 | 281.2309 | 22.28% | 1878.2309 | Redesign of concept to cheaper fabrication |  |  | #DIV/0! | 335
16 | Coil Services | 1140 | 3 | 861 | 529 | 61.44% | 66.7872 |  |  | 225.0106 | 100 | 391.7979 | 45.5% | 1255.7979 | Simplification in the electrical & coolant circuit configuration |  |  | #DIV/0! | 3 |  | FY07 | FY08 | FY09 | FY10 | FY11 | Total ETC
17 | Cryostat & Base Support Structure | 1361 | 431 | 784 | 280 | 35.71% | 111.7813 |  |  | 4.9534 | 100 | 216.7347 | 27.64% | 1431.7347 | Simpler cryostat based on experience gained with the coil test facility as well as a stationary base support structure |  |  | #DIV/0! | 431 | Total Project | 6.12 | 14.483 | 15.068 | 12.581 | 2.602 | 50.854
18 | Field Period Assembly | 5430 | 3479 | 10104 | 740 | 7.324% | 1645.4569 |  | 355.2814 | 127.1874 | 885 | 3012.9257 | 29.82% | 16595.9257 | More mature assy sequence plan as well as a better appreciation of metrology and dimensional control reqmnts. |  |  | #DIV/0! | 3479 | Systems Designs | 1.28 | 1.52 | 1.93 | 0.78 |  | 5.51
19 | Stellarator Core Mgmt & Integr | 2752 | 2128 | 1620 | 0 | 0% | 127.1447 | 179.366 |  | 10.2213 | 0 | 316.7321 | 19.55% | 4064.7321 | Title III support of assy, CAD modeling as well as project stretch-out. |  |  | #DIV/0! | 2128
2 | Auxiliary Systems | 783.44 | 348 | 241 | 104 | 43.15% | 34.0614 |  |  | 1.5175 |  | 35.5789 | 14.76% | 624.5789 | Fueling and vacuum pumping system designs simplified. |  |  | #DIV/0! | 348 |  | 20.92% | 10.5% | 12.81% | 6.2% | 0% | 10.83%
3 | Diagnostics | 1143.44 | 954 | 717 | 333 | 46.44% | 83.663 |  |  | 4.5258 |  | 88.1888 | 12.3% | 1759.1888 | Fabrication of magnetic diagnostic loops and first plasma imaging/ e-beam mapping equipt. |  |  | #DIV/0! | 954
4 | Electrical Power Systems | 3301.44 | 720 | 2425 | 926 | 38.19% | 182.33 |  |  | 52.7055 | 150 | 385.0355 | 15.88% | 3530.0355 | Cost growth offset by reduction in reqmnts (controls, number of circuits to minimum req'd for CD-4. |  |  | #DIV/0! | 720
5 | I&C Systems | 2050.4 | 33 | 1136 | 467 | 41.11% | 155.8583 |  |  | 7.169 | 0 | 163.0274 | 14.35% | 1332.0274 | Reqmnts reduced to minimum req'd to satisfy CD-4. |  |  | #DIV/0! | 33
6 | Facility Systems | 691.4 | 24 | 1379 | 407 | 29.51% | 372.2653 |  |  | 8.7037 | 0 | 380.969 | 27.63% | 1783.969 | Bake-out system added $.6m and cryogenic system cost growth based on experience. |  |  | #DIV/0! | 24
7 | Test Cell Prep & Machine Assy | 4413.4 | 963 | 7951 |  | 0% | 2374.6555 |  |  | 161.6839 | 500 | 3036.3394 | 38.19% | 11950.3394 | More mature assy sequence plan as well as a better appreciation of metrology and dimensional control reqmnts. |  |  | #DIV/0! | 963
81 | Project Management | 4508.5 | 3376 | 4342 |  | 0% | 375 | 1122 |  | 79 |  | 1576 | 36.3% | 9294 | Addition of a construction manager, add'l project control staff, as well as project stretch-out cost. |  |  | #DIV/0! | 3376
82 | Project Engineering | 4884.5 | 5248 | 5948 |  | 0% | 600 | 628 |  |  |  | 1228 | 20.65% | 12424 | Dimensional control planning, support of metrology ops, on on-going CAD modeling,& engineering analysis. |  |  | #DIV/0! | 5248
84 | Project Physics | 470 | 470 | [8 empty] | 0 |  | 470 |  |  |  | #DIV/0! | 470
85 | Start-up | 1189 | 0 | 764.83 |  | 0% | 75 |  |  |  | 125 | 200 | 26.15% | 964.83 | Test plans streamlined based on NSTX experience. |  |  | #DIV/0! | 0
89 | Allocations | 1577.4 | 1416 | 1453.77 |  | 0% | 100 | 417 |  |  |  | 517 | 35.56% | 3386.77 | Indirect overhead as a function of project stretch-out. |  |  | #DIV/0! | 1416
| dcma | 75 | 75 | [10 empty] | 75 |  |  |  |  | 75
| contingency | 12804.4
| Total | 92400.72 | 67178 | 50853.6 | 5513 | 10.84% | 8036.3147 | 2346.366 | 355.2814 | 1281.9276 | 2360 | 14379.8897 | 28.28% | 132411.4897 |  | 0 | 0 | #DIV/0! | 67178
(1) includes engineering and design labor required to acheive FDR status on all systems
Excludes wbs 19, 8, titile III, field supervision and oversight engrs,
Note on I6: Chris Gruber: Based on % of total Uncertainty Contingency)- see Uncertainty Results worksheets
Note on J6: Chris Gruber: Total of both Uncertainty and Risk schedule contingency cost allowance split on basis of contribution to standing army calc - see Mis Inputs sheet
Note on L6: Chris Gruber: Based on % of total risk impact by WBS -- see Risk Model worksheet