## Sheet1
NCSX Project Budget vs EAC Comparison
WBS |  | Baseline (ECP-31 DOE Directed re-baseline April 2005) | Project Cost to date (4/1/03 thru 4/30/07) | Proposed ETC | Current EAC (June 2007) | Increase
[10 empty] | etc | actual | EAC
12 | Vacuum Vessel | 9531 | 9753 | 156 | 9909 | 378 | 3.966% | Heating and cooling system re-design | 12 - Vacuum Vessel Systems | 413.253 | 9753 | 10166.253
13 | Conventional Coils | 4790 | 3224.3 | 3462 | 6686.3 | 1896.3 | 39.59% | TF coil fabrication $1.5m and PF coil fabrication $0.4m based on vendor quotes. | 13 - Conventional Coils | 3396.931 | 3237 | 6633.931
14 | Modular Coils | 28091.4 | 34200.1 | 6247 | 40447.1 | 12355.7 | 43.98% | Design/R&D $3.3m, Winding form fabrication $1.5m, Mod coil winding $6.5m, Coil testing $1.0m | 14 - Modular Coils | 4916.613 | 34256 | 39172.613
15 | Structures | 1413 | 340 | 1262 | 1602 | 189 | 13.38% | Redesign of concept to cheaper fabrication | 15 - Coil Structures | 2130.934 | 340 | 2470.934
16 | Coil Services | 1140 | 3 | 861 | 864 | -276 | -24.21% | Simplification in the electrical & coolant circuit configuration | 16 - Coil Services | 859.373 | 3 | 862.373
17 | Cryostat & Base Support Structure | 1361 | 431 | 784 | 1215 | -146 | -10.73% | Simpler cryostat based on experience gained with the coil test facility as well as a stationary base support structure | 17 - Cryostat and Base Support Structure | 751.4 | 431 | 1182.4
18 | Field Period Assembly | 5430 | 3469.25 | 10104 | 13573.25 | 8143.25 | 150% | More mature assy sequence plan as well as a better appreciation of metrology and dimensional control reqmnts. | 18 - Field Period Assembly | 9313.821 | 3501 | 12814.821
19 | Stellarator Core Mgmt & Integr | 2752 | 2128 | 1620 | 3748 | 996 | 36.19% | Title III support of assy, CAD modeling as well as project stretch-out. | 19 - Stellarator Core Management and Integration | 1487.917 | 2128 | 3615.917
1 | Stellarator Core | 54508.4 | 53548.65 | 24496 | 78044.65 | 23536.25 | 43.18% |  | 1 | 23270.242 | 53649 | 76919.242
2 | Auxiliary Systems | 783.44 | 348 | 241 | 589 | -194.44 | -24.82% | Fueling and vacuum pumping system designs simplified. | 3 | 691.593 | 957
3 | Diagnostics | 1143.44 | 954.46 | 717 | 1671.46 | 528.02 | 46.18% | Fabrication of magnetic diagnostic loops and first plasma imaging/ e-beam mapping equipt. | 5 | 1121.631 | 33
4 | Electrical Power Systems | 3301.44 | 720 | 2425 | 3145 | -156.44 | -4.739% | Cost growth offset by reduction in reqmnts (controls, number of circuits to minimum req'd for CD-4. | 7 | 6101.111 | 963
5 | I&C Systems | 2050.4 | 33 | 1136 | 1169 | -881.4 | -42.99% | Reqmnts reduced to minimum req'd to satisfy CD-4. | a | 1016.404 | 1420
6 | Facility Systems | 691.4 | 24 | 1379 | 1403 | 711.6 | 102.9% | Bake-out system added $.6m and cryogenic system cost growth based on experience.
7 | Test Cell Prep & Machine Assy | 4413.4 | 963 | 7951 | 8914 | 4500.6 | 102% | More mature assy sequence plan as well as a better appreciation of metrology and dimensional control reqmnts. | dcma |  | 75 | 75
81 | Project Management and Oversight | 4508.5 | 3372 | 4342 | 7714 | 3205.5 | 71.1% | Addition of a construction manager, add'l project control staff, as well as project stretch-out cost.
82 | Project Engineering | 4884.5 | 5250 | 5948 | 11198 | 6313.5 | 129.3% | Dimensional control planning, support of metrology ops, on on-going CAD modeling,& engineering analysis.
84 | Project Physics | 470 | 470 | 0 | 470 | 0 | 0%
85 | Integrated Systems Testing | 1189 | 0 | 765 | 765 | -424 | -35.66% | Test plans streamlined based on NSTX experience.
8 | Project Oversight & Support | 11052 | 9092 | 11055 | 20147 | 9095 | 82.29%
Allocations |  | 1577.4 | 1420 | 1453.78 | 2873.78 | 1296.38 | 82.18% | Indirect overhead as a function of project stretch-out.
Subtotal |  | 79521.32 | 67103.11 | 50853.78 | 117956.89 | 38435.57 | 48.33%
Contingency |  | 12804 |  | 14380 | 14380
|  | 25% |  | 28.28%
DCMA |  | 75 | 75 |  | 75
TOTAL |  | 92400.57 | 67178.11 | 65234.0628 | 132411.89 | 40011.32 | 43.3%
| Planned Finish = | 2009-02-28 |  |  | 2011-01-31 | 23 mo. Increase
| CD-4 = | 2009-07-31 |  |  | 2011-12-31 | 29 mo. Increase
| Schedule Contingency = | 5 mo. |  |  | 11 mo.