## scatter plot
Sum of BC | TF
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 42 | 43 | 44 | 45 | 46 | 47 | 49 | 50 | 51 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 73 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 84 | 85 | 86 | 87 | 88 | 91 | 93 | 97 | 99 | 100 | 101 | 102 | 103 | 104 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 119 | 121 | 122 | 124 | 125 | 126 | 127 | 128 | 129 | 132 | 134 | 136 | 137 | 140 | 143 | 144 | 146 | 149 | 150 | 154 | 157 | 159 | 163 | 164 | 168 | 170 | 171 | 173 | 176 | 179 | 181 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 193 | 195 | 202 | 205 | 216 | 217 | 219 | 221 | 222 | 227 | 229 | 234 | 237 | 239 | 240 | 241 | 242 | 249 | 258 | 259 | 260 | 261 | 273 | 275 | 285 | 286 | 288 | 299 | 320 | 331 | 336 | 340 | 341 | 348 | 352 | 356 | 357 | 360 | 369 | 374 | 376 | 379 | 380 | 385 | 387 | 390 | 391 | 393 | 402 | 405 | 418 | 422 | 426 | 442 | 445 | 449 | 450 | 497 | 593 | 1060 | 1089 | 1249 | 1261 | 1314 | 1322 | 1360 | (blank) | Grand Total
Total | 3466358.12 | 47899.22 | 44163.88 | 1492880.36 | 506336.9 | 538051.5 | 86834.8 | 67892.28 | 39841.6 | 524746.6 | 7672.82 | 29397.18 | 209006.04 | 643652.46 | 43170 | 715264.06 | 481600.81 | 91357.18 | 556048.28 | 116974.4 | 8412.3 | 319420.92 | 101997.04 | 15480.9 | 15105.15 | 779063.4 | 20588 | 200328.31 | 4208.4 | 11888.64 | 15572 | 39841.6 | 19085 | 9343.2 | 701478.19 | 6012 | 163054.09 | 133516.96 | 83794.68 | 15706.35 | 107471.8 | 166488.84 | 207270.83 | 1133350.27 | 123906.66 | 51323.81 | 85066.09 | 274245.26 | 225383.07 | 278411.6 | 29046.19 | 187446.14 | 104653 | 3561.3 | 3925.39 | 7786 | 53180.95 | 326559.26 | 328573.92 | 134846.64 | 33165.2 | 235043.14 | 346213.27 | 203006 | 54814.28 | 3925.39 | 424304.45 | 72997.33 | 61861.52 | 408475.32 | 74128.22 | 38150.2 | 148517.86 | 13287.36 | 162477.07 | 31656 | 32604.96 | 38218.4 | 23151.79 | 749667.79 | 112627.2 | 687952.67 | 55106.24 | 511496.25 | 25363.76 | 31617.8 | 3925.39 | 14860.8 | 340213.98 | 123292.23 | 3925.39 | 113958.95 | 32700 | 62600.4 | 22291.2 | 66762.88 | 373341.31 | 60554.16 | 58166.95 | 24674.11 | 219076.66 | 12942.86 | 91931.04 | 69098.55 | 162032.86 | 36951 | 62644.8 | 20143.2 | 41085.44 | 58716.09 | 184417.72 | 145874.07 | 274418.52 | 434132.37 | 8996.8 | 15374.8 | 29706.6 | 44840.62 | 19513.76 | 144627.65 | 12196.1 | 30526 | 114560 | 47801.36 | 68750.16 | 297766.9 | 48236.8 | 8130.56 | 64836.6 | 88181.45 | 105854.43 | 69998.32 | 16891.84 | 14772 | 57298.22 | 54448.23 | 30371.84 | 28187.69 | 31563 | 20241.32 | 21228.68 | 4509 | 25095.47 | 25757.68 | 83629.52 | 73092.52 | 8515.44 | 57379.48 | 41016.77 | 1118.28 | 23847.09 | 96653.42 | 132816.56 | 24732.73 | 19226.4 | 3204.4 | 70384 | 3002.9 | 48343.08 | 41657.2 | 12619 | 47210 | 47220 | 56660 | 164364.3 | 47210 | 47220 | 99453.2 | 47210 | 84815.36 | 47220 | 47210 | 3561.3 | 47210 | 47210 | 47220 | 43884.16 | 20134 | 43590 | 47210 | 94420 | 24686.4 | 47210 | 47210 | 418829 | 6012 | 7430.4 | 97056 | 28557 | 5728.8 | 6747.6 | 6540 | 3889.44 | 15029.6 | 89320 | 103998.8 | 40762.56 | 6969.2 | 147263.82 | 28425080.65

## Sheet2
Sum of BC | float range
| A Critical path | B <1 week | C <2 weeks | D <3 weeks | E <4 weeks | F <5 weeks | G <6 weeks | H <7 weeks | I < 8 weeks | J < 9 weeks | K < 10 weeks | L < 11 weeks | M < 12 weeks | N < 13 weeks | o < 4 months | P < 5 months | Q < 6 months | R > 6 months | Grand Total
Total | 3466358.12 | 2629331.86 | 726988.1 | 1640489.74 | 1129006.27 | 546804.66 | 1030565.76 | 90595.64 | 879887.48 | 340489.79 | 1631016.6 | 636018.23 | 603118.23 | 720025.52 | 2479474.21 | 2239127.29 | 1621292.92 | 5867226.41 | 28277816.83

## weeks
Sum of BC | float range 2
| A Critical path | B <1 week | C <2 weeks | D <3 weeks | E <4 weeks | F <5 weeks | G <6 weeks | H <7 weeks | I < 8 weeks | J < 9 weeks | K < 10 weeks | L < 11 weeks | M < 12 weeks | N < 13 weeks | o < 14 weeks' | P < 15 weeks | Q < 16 weeks | R < 17 weeks | S < 18 weeks | T < 19 weeks | U < 20 weeks | V < 21 weeks | W < 22 weeks | X < 23 weeks | Y < 24 weeks | Z < 25 weeks | AA < 26 weeks | AB > 6 months | AC > 12 months | AD > 18 months | AE > 24 months | XX LOE | Grand Total
Total | 3466358.12 | 2629331.86 | 726988.1 | 1640489.74 | 1129006.27 | 546804.66 | 1030565.76 | 90595.64 | 879887.48 | 340489.79 | 1631016.6 | 636018.23 | 603118.23 | 720025.52 | 952274.25 | 483044.12 | 655612.59 | 324282.29 | 102479.36 | 772819.58 | 855686.11 | 572403.2 | 14860.8 | 614090.55 | 84891.6 | 558825.3 | 348624.67 | 3425031.02 | 1344588.59 | 824349.6 | 273257.2 | 21796061.3 | 50073878.13
| 6.922% | 5.251% | 1.452% | 3.276% | 2.255% | 1.092% | 2.058% | 0.1809% | 1.757% | 0.68% | 3.257% | 1.27% | 1.204% | 1.438% | 1.902% | 0.9647% | 1.309% | 0.6476% | 0.2047% | 1.543% | 1.709% | 1.143% | 0.02968% | 1.226% | 0.1695% | 1.116% | 0.6962% | 6.84% | 2.685% | 1.646% | 0.5457% | 43.53%
Sum of BC | float range 2
| Critical path | <1 week | <2 weeks | <3 weeks | <4 weeks | <5 weeks | <6 weeks | <7 weeks | < 8 weeks | < 9 weeks | < 10 weeks | < 11 weeks | < 12 weeks | < 13 weeks | < 14 weeks' | < 15 weeks | < 16 weeks | < 17 weeks | < 18 weeks | < 19 weeks | < 20 weeks | < 21 weeks | < 22 weeks | < 23 weeks | < 24 weeks | < 25 weeks | < 26 weeks | > 6 months | > 12 months | > 18 months | > 24 months | Grand Total
Total | 3466358.12 | 2629331.86 | 726988.1 | 1640489.74 | 1129006.27 | 546804.66 | 1030565.76 | 90595.64 | 879887.48 | 340489.79 | 1631016.6 | 636018.23 | 603118.23 | 720025.52 | 952274.25 | 483044.12 | 655612.59 | 324282.29 | 102479.36 | 772819.58 | 855686.11 | 572403.2 | 14860.8 | 614090.55 | 84891.6 | 558825.3 | 348624.67 | 3425031.02 | 1344588.59 | 824349.6 | 273257.2 | 28277816.83
Total | 12.26% | 9.298% | 2.571% | 5.801% | 3.993% | 1.934% | 3.644% | 0.3204% | 3.112% | 1.204% | 5.768% | 2.249% | 2.133% | 2.546% | 3.368% | 1.708% | 2.318% | 1.147% | 0.3624% | 2.733% | 3.026% | 2.024% | 0.05255% | 2.172% | 0.3002% | 1.976% | 1.233% | 12.11% | 4.755% | 2.915% | 0.9663% | 100%

## months
Sum of BC | float range 3
| CRITICAL PATH | <1 month | <2 month | <3 month | < 4 month | <5 month | <6 month | <7 month | < 8 month | <9 month | <10 month | <11 month | <12 month | <13 month | <14 month | <15 month | <16 month | <18 month | < 19 month | < 20 month | <21 month | V <22 month | W <23 month | X <24 month | Z >24 month | Grand Total
Total | 3466358.12 | 6125815.97 | 2547853.54 | 3275535.19 | 2907869.36 | 2465865.32 | 1297342.36 | 959040.22 | 972857.54 | 1101466.33 | 143410.29 | 161197 | 543826.76 | 47163.53 | 163387.18 | 12619 | 362664.3 | 625938.02 | 166316.4 | 513249 | 139055.4 | 0 | 5728.8 | 6747.6 | 266509.6 | 28277816.83
Total | 12.26% | 21.66% | 9.01% | 11.58% | 10.28% | 8.72% | 4.588% | 3.391% | 3.44% | 3.895% | 0.5071% | 0.57% | 1.923% | 0.1668% | 0.5778% | 0.04463% | 1.283% | 2.214% | 0.5882% | 1.815% | 0.4917% | 0% | 0.02026% | 0.02386% | 0.9425% | 100%
| 9592174.09 | 5823388.73 | 5373734.68 | 7488519.33 | 28277816.83
| 0 to 1 month float | >1-3 month float | >3-6 months float | >6 months float
total | 33.92% | 20.59% | 19% | 26.48% | 1

## FLOAT19
ACT | TITLE | TF | float range | float range 2 | float range 3 | WBS1 | WBS2 | WBS3 | RLM | CCCC | WPWP | JJJJ | PHAS | FWP | MCAP | BABO | WBS4 | ORDR | DSNR | WAF | JOBX | CCXX | PCTC | ROLL | SJOB | BC
S21-6.041 | Stuff shim bag w/fiberglass & place on wing | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2060 |  |  |  | 400.55
453-1-6 | Trim Coil Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 726.8
S21-5.04 | Place shims on coil identical to A1-A2 fit up | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A2 | 2050 |  |  |  | 801.1
S32-3.01 | Move right base support cart to its final positi | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 23 |  | C | [5 empty] | 824.6
S32-6.01 | Install bumper protection components on the VV | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 44 |  | C | [5 empty] | 824.6
S32-7.03 | move the left MCHP to its final position. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 53 |  | C | [5 empty] | 824.6
S32-7.04 | engage the preinstalled Type-A flange bushings. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 54 |  | C | [5 empty] | 824.6
S32-7.06 | AirLoc Wedgemount leveler up to take the load. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 56 |  | C | [5 empty] | 824.6
S33-3.01 | Move right base support cart to its final positi | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 23 |  | C | [5 empty] | 824.6
S33-6.01 | Install bumper protection components on the VV | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 44 |  | C | [5 empty] | 824.6
S33-7.03 | move the left MCHP to its final position. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 53 |  | C | [5 empty] | 824.6
S33-7.04 | engage the preinstalled Type-A flange bushings. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 54 |  | C | [5 empty] | 824.6
S33-7.06 | AirLoc Wedgemount leveler up to take the load. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 56 |  | C | [5 empty] | 824.6
7503-440 | Install solenoid assembly | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 54 | X | C | 6 |  |  |  |  | 852.6
7503-444 | Install solenoid support structure | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 53 | X | C | 6 |  |  |  |  | 852.6
7503-440 | Install solenoid assembly | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 54 | X | C | 6 |  |  |  |  | 988.55
7503-444 | Install solenoid support structure | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 53 | X | C | 6 |  |  |  |  | 988.55
7503-438 | Align guide mechanism for solenoid installation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 52 | X | C | 6 |  |  |  |  | 1023.12
453-1-4 | TF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 1041.79
453-1-5 | PF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 1041.79
453-1-6 | Trim Coil Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 1041.79
7503-442 | Connect cabling, LN2 andI&C to solenoid assy | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 55 | X | C | 6 |  |  |  |  | 1124.8
7503-446 | Install PF4L | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 56 | X | C | 6 |  |  |  |  | 1124.8
7503-448 | Connect cabling, LN2 and I&C to PF4L | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 57 | X | C | 6 |  |  |  |  | 1124.8
7503-450 | Adjust spring compression in solenoid sprt struc | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 58 | X | C | 6 |  |  |  |  | 1124.8
7503-438 | Align guide mechanism for solenoid installation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 52 | X | C | 6 |  |  |  |  | 1186.26
1421-3067 | Procure 2 studs f/joint test.Use existing part | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 21 | X | C |  | C |  |  |  | 1206.56
1421-3067 | Procure 2 studs f/joint test.Use existing part | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 21 | X | C |  | C |  |  |  | 1276
S33-1.02 | Install floor mounted tracks and VV base support | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 12 |  | C | [5 empty] | 1397
7503-440 | Install solenoid assembly | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 54 | X | C | 6 |  |  |  |  | 1406
7503-444 | Install solenoid support structure | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 53 | X | C | 6 |  |  |  |  | 1406
453-1-4 | TF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 1453.6
453-1-5 | PF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 1453.6
S21-11.01 | Identify primary fiducials for positioning Sta 3 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 12 |  | C | C1 | 2070 |  |  |  | 1602.2
S21-11.06 | Remove from stand & measure weight of assy | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 13 |  | C |  | 2110 |  |  |  | 1602.2
S21-5.06 | Lower mating A1 modular coil into position. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 1602.2
S21-5.07 | Meas monuments bottom coil. Jack to .002ö | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 1602.2
S21-5.08 | Using 3 points, position as was done inA1A2 fit | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 1602.2
S21-5.1 | Make "wiggle" test Tighten bolt and recheck. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 1602.2
S21-5.15 | Remove studs,nuts,shims. Identify shim locations | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 1602.2
S21-6.05 | Lower the Type-B coil onto the Type-A coil. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.06 | Measure monuments on A coil. Jack to .002ö | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.061 | instl dial indicators for x-y positioning | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.062 | instl dial indicators for x-y positioning | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 10 |  | C | C1 | 2070 |  |  |  | 1602.2
S21-6.07 | Perform the X-Y positioning of the B coil. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.09 | Make "wiggle" test Tighten bolt and recheck. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.12 | Install alumina shims. Re-torque to 50%. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.13 | Make "wiggle" test Tighten bolt and recheck. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.17 | Complete tightening of flange bolts to 100%. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-6.19 | Scan the ôBö flange of Type-B coil | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 1602.2
S21-7.05 | Lower the Type-C coil onto the Type-B coil. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 09 |  | C | C1 | 2070 |  |  |  | 1602.2
S21-7.07 | Perform the X-Y positioning of the coil. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 1602.2
S21-7.09 | "wiggle" test Tighten bolt and recheck. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 1602.2
S21-7.12 | Iinstall alumina shims. Re-torque all studs to | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 1602.2
S21-7.13 | "wiggle" test Tighten bolt and recheck. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 1602.2
S21-7.17 | Complete tightening of flange bolts to 100%. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 1602.2
S32-2.04 | Position left MCHP on the cart assembly | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 19 |  | C | [5 empty] | 1649.2
S32-2.07 | Set positioning stop on the cart | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 22 |  | C | [5 empty] | 1649.2
S32-3.02 | Lift the right side MCHP and position | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 24 |  | C | [5 empty] | 1649.2
S32-3.05 | Install temp scaffolding to install flange hw | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 27 |  | C | [5 empty] | 1649.2
S32-3.06 | Install bolts and shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 28 |  | C | [5 empty] | 1649.2
S32-3.07 | Tighten flange fasteners to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 29 |  | C | [5 empty] | 1649.2
S32-3.11 | Remove flange hardware and temp platforms | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 33 |  | C | [5 empty] | 1649.2
S32-4.03 | Determine laser alignment. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 36 |  | C | [5 empty] | 1649.2
S32-4.05 | Disengage MCHP's to move the left MCHP. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 38 |  | C | [5 empty] | 1649.2
S32-5.03 | Install VVSA to base support | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 42 |  | C | [5 empty] | 1649.2
S32-7.1 | Tighten flange fasteners to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 60 |  | C | [5 empty] | 1649.2
S32-7.11 | "wiggle" test Tighten bolt and recheck. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 61 |  | C | [5 empty] | 1649.2
S32-7.16 | Tighten nuts 100%. & Measure | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 66 |  | C | [5 empty] | 1649.2
S32-9.02 | Attach temporary VV vertical supports | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 70 |  | C | [5 empty] | 1649.2
S32-9.03 | Transfer load to vertical supports. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 71 |  | C | [5 empty] | 1649.2
S33-2.04 | Position left MCHP on the cart assembly | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 19 |  | C | [5 empty] | 1649.2
S33-2.07 | Set positioning stop on the cart | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 22 |  | C | [5 empty] | 1649.2
S33-3.05 | Install temp scaffolding to install flange hw | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 27 |  | C | [5 empty] | 1649.2
S33-3.06 | Install bolts and shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 28 |  | C | [5 empty] | 1649.2
S33-3.07 | Tighten flange fasteners to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 29 |  | C | [5 empty] | 1649.2
S33-3.11 | Remove flange hardware and temp platforms | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 33 |  | C | [5 empty] | 1649.2
S33-4.03 | Determine laser alignment. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 36 |  | C | [5 empty] | 1649.2
S33-4.05 | Disengage MCHP's to move the left MCHP. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 38 |  | C | [5 empty] | 1649.2
S33-5.03 | Install VVSA to base support | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 42 |  | C | [5 empty] | 1649.2
S33-7.1 | Tighten flange fasteners to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 60 |  | C | [5 empty] | 1649.2
S33-7.11 | "wiggle" test Tighten bolt and recheck. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 61 |  | C | [5 empty] | 1649.2
S33-7.16 | Tighten nuts 100%. & Measure | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 66 |  | C | [5 empty] | 1649.2
S33-9.02 | Attach temporary VV vertical supports | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 70 |  | C | [5 empty] | 1649.2
S33-9.03 | Transfer load to vertical supports. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 71 |  | C | [5 empty] | 1649.2
S53-6.02 | Attach the temp support at end of Type-C MC | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 26 |  | C | [5 empty] | 1649.2
S53-6.05 | Secure First TF assy | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 29 |  | C | [5 empty] | 1649.2
S53-6.07 | Secure 2nd TF coil | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 31 |  | C | [5 empty] | 1649.2
S53-6.1 | Installed one side of the TF support brackets | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 34 |  | C | [5 empty] | 1649.2
7503-438 | Align guide mechanism for solenoid installation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 52 | X | C | 6 |  |  |  |  | 1687.2
S53-14.02 | Remove platforms | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 55 |  | C | [5 empty] | 1705.2
7503-410 | Install spacer supports and spacers | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 2249.6
7503-415 | Re-install spacers | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 2249.6
7503-432 | Fill MC/VVSA annulus with pourable aerogel insul | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 47 | X | C | 6 |  |  |  |  | 2249.6
S33-3.02 | Lift the right side MCHP and position | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 24 |  | C | [5 empty] | 2473.8
7503-424 | Install TF alignment & traction ring | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 41 | X | C | 6 |  |  |  |  | 2570.23
7503-426 | Pull TF coil radially inward. Verify nose fit up | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 42 | X | C | 6 |  |  |  |  | 2570.23
7503-428 | Lock TF coils at four support locations | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 43 | X | C | 6 |  |  |  |  | 2570.23
7503-402 | Move all FPA's together, chk fitup,tack shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 2728.32
7503-412 | Move FPA's & spacers together/chk fitup | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 2728.32
7503-442 | Connect cabling, LN2 andI&C to solenoid assy | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 55 | X | C | 6 |  |  |  |  | 2728.32
7503-446 | Install PF4L | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 56 | X | C | 6 |  |  |  |  | 2728.32
7503-448 | Connect cabling, LN2 and I&C to PF4L | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 57 | X | C | 6 |  |  |  |  | 2728.32
7503-450 | Adjust spring compression in solenoid sprt struc | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 58 | X | C | 6 |  |  |  |  | 2728.32
S32-4.01 | EMeasure monuments on the MCHP's &walls. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 34 |  | C | [5 empty] | 2794
S33-1.01 | Install Station 3 site monuments | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 11 |  | C | [5 empty] | 2794
S33-4.01 | EMeasure monuments on the MCHP's &walls. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 34 |  | C | [5 empty] | 2794
S21-11.05 | Install lift support beams | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 13 |  | C |  | 2110 |  |  |  | 3204.4
S21-5.01 | Place A2 "B" side down. Obtain fiduals | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A2 | 2050 |  |  |  | 3204.4
S21-5.05 | Install dial indicators on the MC to see deflec | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A2 | 2050 |  |  |  | 3204.4
S21-5.09 | Torque to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 3204.4
S21-5.14 | Install A-A locator bushings | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 3204.4
S21-6.01 | Place Type A "A" side down. Obtain fiduals | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2060 |  |  |  | 3204.4
S21-6.04 | Place the an initial set shims on coil | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2060 |  |  |  | 3204.4
S21-6.08 | Install remaining metal shims torque to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 3204.4
S21-7.04 | Place initial set metal shims on the coil | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 09 |  | C | B1 | 2070 |  |  |  | 3204.4
S21-7.08 | Install remaining metal shims torque to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 3204.4
S21-8.01 | Tack weld inboard shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 12 |  | C |  | 2080 |  |  |  | 3204.4
S32-10.02 | Transfer Period 2 to Station 5 in NCSX TC | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 75 |  | C | [5 empty] | 3298.4
S32-2.05 | Secure left MCHP on support cart base. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 20 |  | C | [5 empty] | 3298.4
S32-3.09 | Perform position adjust on right side MCHP | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 31 |  | C | [5 empty] | 3298.4
S32-4.02 | Place all of the laser screens | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 35 |  | C | [5 empty] | 3298.4
S32-4.06 | Remove both MCHP's. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 39 |  | C | [5 empty] | 3298.4
S32-5.02 | Install VV NBI port support stand. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 41 |  | C | [5 empty] | 3298.4
S32-5.04 | Secure the VVSA to base & NBI port sprt stand. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 43 |  | C | [5 empty] | 3298.4
S32-6.03 | move the left MCHP over the VV. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 46 |  | C | [5 empty] | 3298.4
S32-6.05 | Make adjustments to properly align MCHP. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 48 |  | C | [5 empty] | 3298.4
S32-7.02 | move the right MCHP over the VV | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 52 |  | C | [5 empty] | 3298.4
S32-7.09 | Install bolts, alumina and inboard weld shims. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 59 |  | C | [5 empty] | 3298.4
S32-9.01 | Attach VV permanent vertical supports | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 69 |  | C | [5 empty] | 3298.4
S32-9.05 | Prepare VVSA for transport. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 73 |  | C | [5 empty] | 3298.4
S33-1.03 | Establish the MCHP CG location. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 15 |  | C | [5 empty] | 3298.4
S33-10.02 | Transfer Period 3 to Station 5 in NCSX TC | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 75 |  | C | [5 empty] | 3298.4
S33-2.02 | Verify cart motion. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 17 |  | C | [5 empty] | 3298.4
S33-2.05 | Secure left MCHP on support cart base. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 20 |  | C | [5 empty] | 3298.4
S33-3.09 | Perform position adjust on right side MCHP | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 31 |  | C | [5 empty] | 3298.4
S33-4.02 | Place all of the laser screens | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 35 |  | C | [5 empty] | 3298.4
S33-4.06 | Remove both MCHP's. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 39 |  | C | [5 empty] | 3298.4
S33-5.02 | Install VV NBI port support stand. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 41 |  | C | [5 empty] | 3298.4
S33-5.04 | Secure the VVSA to base & NBI port sprt stand. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 43 |  | C | [5 empty] | 3298.4
S33-6.05 | Make adjustments to properly align MCHP. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 48 |  | C | [5 empty] | 3298.4
S33-7.02 | move the right MCHP over the VV | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 52 |  | C | [5 empty] | 3298.4
S33-7.09 | Install bolts, alumina and inboard weld shims. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 59 |  | C | [5 empty] | 3298.4
S33-9.01 | Attach VV permanent vertical supports | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 69 |  | C | [5 empty] | 3298.4
S33-9.05 | Prepare VVSA for transport. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 73 |  | C | [5 empty] | 3298.4
S53-1.01 | cut off short dome | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 11 |  | C | [5 empty] | 3298.4
S53-2.01 | Install period support fixture | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 14 |  | C | [5 empty] | 3298.4
S53-2.02 | Install FPA on support stand. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 15 |  | C | [5 empty] | 3298.4
S53-3.01 | Install the domes (left and right side), | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 18 |  | C | [5 empty] | 3298.4
S53-6.01 | Rotate 2 TF coils over the MC on the right side | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 25 |  | C | [5 empty] | 3298.4
S53-6.04 | Install TF support brackets | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 28 |  | C | [5 empty] | 3298.4
S53-6.06 | Install TF support brackets | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 30 |  | C | [5 empty] | 3298.4
S53-9.01 | Tack weld the left and right port 4's. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 37 |  | C | [5 empty] | 3298.4
7503-415.5 | MC Interface:meas holes/mark bushings f/drilling | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 27 | X | C | 6 |  |  |  |  | 3374.4
7503-415.6 | drill eccentric custom holes in bushings | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 28 | X | C | 6 |  |  |  |  | 3374.4
S53-13.04 | Install or identify three primary fiducials | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 46 |  | C | [5 empty] | 3410.4
S53-14.01 | Install crane rigging to completed Period assy | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 54 |  | C | [5 empty] | 3410.4
S53-14.03 | Transfer Period 3 to Station 6 in NCSX tTC. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 56 |  | C | [5 empty] | 3410.4
7503-120 | Test movement of FPA's incl position checks. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 21 | X | C | 6 |  |  |  |  | 3410.4
7503-419.2 | FPA Metrology checks to assure alignment | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 34 | X | C | 6 |  |  |  |  | 3410.4
7503-419.2 | FPA Metrology checks to assure alignment | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 34 | X | C | 6 |  |  |  |  | 3410.4
1421-3067 | Procure 2 studs f/joint test.Use existing part | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 21 | X | C |  | C |  |  |  | 3607.2
7503-438 | Align guide mechanism for solenoid installation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 52 | X | C | 6 |  |  |  |  | 3666.18
7503-440 | Install solenoid assembly | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 54 | X | C | 6 |  |  |  |  | 3666.18
7503-444 | Install solenoid support structure | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 53 | X | C | 6 |  |  |  |  | 3666.18
7503-120 | Test movement of FPA's incl position checks. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 21 | X | C | 6 |  |  |  |  | 3954.2
7503-400 | Install inboard and outboard shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 3954.2
7503-402 | Move all FPA's together, chk fitup,tack shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 3954.2
7503-404 | Weld inboard shims on mating flanges | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 3954.2
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 23 | X | C | 6 |  |  |  |  | 4092.48
7503-406 | Install TF coils at ends of each FPA | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 4092.48
S33-6.03 | move the left MCHP over the VV. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 46 |  | C | [5 empty] | 4123
7503-090 | Install local Platforms around FPA-1 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 | EC45 | 7503 | F | A |  | X |  | 24 | X | C | 6 |  |  |  |  | 4499.2
7503-130 | Install local Platforms around FPA-2 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 25 | X | C | 6 |  |  |  |  | 4499.2
7503-190 | Install local Platforms around FPA-3 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 | EC45 | 7503 | F | A |  | X |  | 26 | X | C | 6 |  |  |  |  | 4499.2
453-1-4 | TF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 4566.56
453-1-5 | PF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 4566.56
453-1-6 | Trim Coil Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 4566.56
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 23 | X | C | 6 |  |  |  |  | 4745.04
7503-451 | Raise lower PF 5&6 coils into final position | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 59 | X | C | 6 |  |  |  |  | 4798.8
S21-5.12 | Adjust shims locally. Re-torque all studs to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | A1 | 2050 |  |  |  | 4806.6
S21-6.11 | Loosen studs, adjust shims. Re-torque to 50%. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 4806.6
S21-6.15 | Loosen studs, adjust shims. Re-torque to 50%. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 4806.6
S21-7.01 | Place ôA/Bö assy, ôAö coil dwn, on 40deg fix. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 09 |  | C | B1 | 2070 |  |  |  | 4806.6
S21-7.11 | adjust shims locally. Re-torque all studs to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 4806.6
S21-7.15 | adjust shims locally. Re-torque all studs to 50 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 4806.6
7503-452 | Instl Upper PF 4, 5 & 6 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 60 | X | C | 6 |  |  |  |  | 4906.32
S32-7.13 | Perform position adjustments right side MCHP | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 63 |  | C | [5 empty] | 4947.6
S33-1.01 | Install Station 3 site monuments | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 11 |  | C | [5 empty] | 4947.6
S33-7.13 | Perform position adjustments right side MCHP | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 63 |  | C | [5 empty] | 4947.6
S53-11.01 | Install tMC coolant manifold | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 40 |  | C | [5 empty] | 4947.6
S53-2.04 | Install internal VV working platforms | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 17 |  | C | [5 empty] | 4947.6
S53-5.03 | Platforms may need to be altered | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 24 |  | C | [5 empty] | 4947.6
S53-6.08 | Install machine support plates | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 32 |  | C | [5 empty] | 4947.6
7503-400 | Install inboard and outboard shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 4962.77
7503-402 | Move all FPA's together, chk fitup,tack shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 4962.77
7503-404 | Weld inboard shims on mating flanges | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 4962.77
7503-416 | Position Spool pieces and Bolt MC flanges | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 29 | X | C | 6 |  |  |  |  | 4962.77
S53-13.15 | Check trim coils (voltage etc) | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 52 |  | C | [5 empty] | 5115.6
7503-422 | Weld all six port 4's in place | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 36 | X | C | 6 |  |  |  |  | 5115.6
7503-410 | Install spacer supports and spacers | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 5456.64
7503-414 | Remove Spacers & Machine spacers to fit | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 5456.64
7503-415 | Re-install spacers | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 5456.64
7503-432 | Fill MC/VVSA annulus with pourable aerogel insul | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 47 | X | C | 6 |  |  |  |  | 5456.64
7503-120 | Test movement of FPA's incl position checks. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 21 | X | C | 6 |  |  |  |  | 5624
7503-424 | Install TF alignment & traction ring | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 41 | X | C | 6 |  |  |  |  | 5712.42
7503-426 | Pull TF coil radially inward. Verify nose fit up | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 42 | X | C | 6 |  |  |  |  | 5712.42
7503-428 | Lock TF coils at four support locations | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 43 | X | C | 6 |  |  |  |  | 5712.42
7503-456 | Install elec pwr, LN2, & instr feedthrus | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 63 | X | C | 6 |  |  |  |  | 5815.2
7503-466 | Connect 150C bakeout | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 68 | X | C | 6 |  |  |  |  | 5815.2
7503-473 | Install cryostat circulation duct | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 72 | X | C | 6 |  |  |  |  | 5815.2
453-1-4 | TF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 6029.38
453-1-5 | PF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 6029.38
453-1-6 | Trim Coil Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 6029.38
INTRF-054 | FDR prep AB/BC/AA inboard shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142F | 15 | M | C |  | C |  |  |  | 6032.8
453-1-4 | TF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 6185.6
453-1-5 | PF Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 6185.6
453-1-6 | Trim Coil Coil Test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | T |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 6185.6
1421-3135 | FDR Prep | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142J | 17 | M | C |  | C |  |  |  | 6228.8
S32-10.01 | transfer the unit to the transfer support frame | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 74 |  | C | [5 empty] | 6596.8
S32-7.08 | Install temp scaffolding to install flange hw | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 58 |  | C | [5 empty] | 6596.8
S32-9.04 | Install VV lateral supports and align | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 72 |  | C | [5 empty] | 6596.8
S33-10.01 | transfer the unit to the transfer support frame | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 74 |  | C | [5 empty] | 6596.8
S33-2.01 | Install MCHP support cart assemblies | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 16 |  | C | [5 empty] | 6596.8
S33-7.08 | Install temp scaffolding to install flange hw | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 58 |  | C | [5 empty] | 6596.8
S33-9.04 | Install VV lateral supports and align | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 72 |  | C | [5 empty] | 6596.8
S53-2.03 | Install external working platforms | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 16 |  | C | [5 empty] | 6596.8
S53-9.02 | Install boots on both port 4's. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 38 |  | C | [5 empty] | 6596.8
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 23 | X | C | 6 |  |  |  |  | 6748.8
7503-406 | Install TF coils at ends of each FPA | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 6748.8
7503-412 | Move FPA's & spacers together/chk fitup | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 6748.8
S53-13.03 | bring the VV into proper alignment | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 45 |  | C | [5 empty] | 6820.8
7503-451 | Raise lower PF 5&6 coils into final position | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 59 | X | C | 6 |  |  |  |  | 6825.28
7503-422.1 | Install E-Beam mapping & diag equipt | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 37 | X | C | 6 |  |  |  |  | 6845.2
7503-452 | Instl Upper PF 4, 5 & 6 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 60 | X | C | 6 |  |  |  |  | 6978.24
1421-3115B | Assemble & test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142C |  | X | C |  | C |  |  |  | 7515
7503-419.2 | FPA Metrology checks to assure alignment | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 34 | X | C | 6 |  |  |  |  | 7908.4
S21-7.14 | Measure the tooling balls on all coils. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 8011
7503-415.5 | MC Interface:meas holes/mark bushings f/drilling | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 27 | X | C | 6 |  |  |  |  | 8184.96
7503-415.6 | drill eccentric custom holes in bushings | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 28 | X | C | 6 |  |  |  |  | 8184.96
S33-1.02 | Install floor mounted tracks and VV base support | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 12 |  | C | [5 empty] | 8246
S53-8.01 | Perform a fit-up check of the four TF coils | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 36 |  | C | [5 empty] | 8246
S53-12.01 | Install Rogowski coils | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 42 |  | C | [5 empty] | 8432.67
S53-13.11 | Check Assembly (bolts, etc) | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 48 |  | C | [5 empty] | 8526
S53-13.12 | Check Diagnostics (Loops, thermocouples) | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 49 |  | C | [5 empty] | 8526
S53-13.13 | Check manifolds (pressure, flow, etc.) | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 50 |  | C | [5 empty] | 8526
7503-415.6 | drill eccentric custom holes in bushings | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 28 | X | C | 6 |  |  |  |  | 8592
7503-424 | Install TF alignment & traction ring | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 41 | X | C | 6 |  |  |  |  | 9420.2
7503-426 | Pull TF coil radially inward. Verify nose fit up | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 42 | X | C | 6 |  |  |  |  | 9420.2
7503-428 | Lock TF coils at four support locations | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 43 | X | C | 6 |  |  |  |  | 9420.2
7503-417 | Retorque all super nuts after 30 days | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 30 | X | C | 6 |  |  |  |  | 9925.54
7503-400 | Install inboard and outboard shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 10123.2
7503-402 | Move all FPA's together, chk fitup,tack shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 10123.2
7503-404 | Weld inboard shims on mating flanges | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 10123.2
7503-416 | Position Spool pieces and Bolt MC flanges | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 29 | X | C | 6 |  |  |  |  | 10123.2
S22-9.01 | Install trim coil | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 | 40 | 1815 |  |  |  |  | S4P3 | 43 |  | C | [5 empty] | 10231.2
S53-13.14 | Check 6 modcoils (voltage etc) | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 51 |  | C | [5 empty] | 10231.2
S53-13.16 | Check TF coils (voltage etc) | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 53 |  | C | [5 empty] | 10231.2
7503-090 | Install local Platforms around FPA-1 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 | EC45 | 7503 | F | A |  | X |  | 24 | X | C | 6 |  |  |  |  | 10913.28
7503-130 | Install local Platforms around FPA-2 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 25 | X | C | 6 |  |  |  |  | 10913.28
7503-190 | Install local Platforms around FPA-3 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 | EC45 | 7503 | F | A |  | X |  | 26 | X | C | 6 |  |  |  |  | 10913.28
7503-422.1 | Install E-Beam mapping & diag equipt | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 37 | X | C | 6 |  |  |  |  | 11248
7503-430 | Install MC structure insulation boots port 4's | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 45 | X | C | 6 |  |  |  |  | 11248
7503-434 | Instl in-cryostat cabling for elect pwr to coils | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 49 | X | C | 6 |  |  |  |  | 11248
7503-436 | Connect cabling, and I&C to MC & TF Coils | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 50 | X | C | 6 |  |  |  |  | 11248
730.8200 | PTP and Cool down | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 73 | X | C | 6 |  |  |  |  | 11630.4
7503-454 | Install cryostat base, vapor barrier port boots | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 62 | X | C | 6 |  |  |  |  | 11630.4
7503-458 | Integrated Electrical testing | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 64 | X | C | 6 |  |  |  |  | 11630.4
7503-464 | Connect coil & VV instrumentation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 67 | X | C | 6 |  |  |  |  | 11630.4
7503-471 | Install cryostat upper section, VB & port boots | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 70 | X | C | 6 |  |  |  |  | 11630.4
1803-201 | Station 2 Assembly Specification | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 2.00 |  | 10 | C |  | C |  | 3 | P | 12457.6
1421-3119B | Document test results | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142C |  | X | C |  | C |  |  |  | 12489.81
S21-10.02 | Make local service runs/connections | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 13 |  | C |  | 2100 |  |  |  | 12817.6
S53-10.01 | Install PF coil support structure | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 39 |  | C | [5 empty] | 13193.6
7503-120 | Test movement of FPA's incl position checks. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 21 | X | C | 6 |  |  |  |  | 13641.6
7503-150A | FPA-3 Installation and assembly test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 19 | X | C | 6 |  |  |  |  | 13690.4
7503-456 | Install elec pwr, LN2, & instr feedthrus | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 63 | X | C | 6 |  |  |  |  | 14105.6
7503-466 | Connect 150C bakeout | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 68 | X | C | 6 |  |  |  |  | 14105.6
7503-473 | Install cryostat circulation duct | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 72 | X | C | 6 |  |  |  |  | 14105.6
730.8200 | PTP and Cool down | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 73 | X | C | 6 |  |  |  |  | 14156
7503-458 | Integrated Electrical testing | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 64 | X | C | 6 |  |  |  |  | 14156
453-1-8 | Testing PTPs, ISTPs | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | S |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 14363.2
7503-420 | Mate-up and Weld spacers onto vvsa | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 35 | X | C | 6 |  |  |  |  | 15346.8
S21-6.16 | Install bushings. Tighten back to 50% | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2P1 | 11 |  | C | B1 | 2060 |  |  |  | 16022
S21-7.16 | Install bushings | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 11 |  | C | C1 | 2070 |  |  |  | 16022
7503-160 | Position all FPA's / Spool Pieces @ MC Interface | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 23 | X | C | 6 |  |  |  |  | 16369.92
7503-406 | Install TF coils at ends of each FPA | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 16369.92
7503-412 | Move FPA's & spacers together/chk fitup | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 16369.92
S32-7.15 | Pre-fit & Install bushings | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 65 |  | C | [5 empty] | 16492
S33-7.15 | Pre-fit & Install bushing. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 65 |  | C | [5 empty] | 16492
7503-451 | Raise lower PF 5&6 coils into final position | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 59 | X | C | 6 |  |  |  |  | 16555.52
7503-260 | PTP Pumpdown & leak check VV | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 40 | X | C | 6 |  |  |  |  | 16872
7503-452 | Instl Upper PF 4, 5 & 6 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 60 | X | C | 6 |  |  |  |  | 16926.72
7503-472 | Install midplane cryostat sections & port boots | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 71 | X | C | 6 |  |  |  |  | 17445.6
S53-5.02 | Install MC coolant lines on each MC | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 23 |  | C | [5 empty] | 19790.4
7503-417 | Retorque all super nuts after 30 days | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 30 | X | C | 6 |  |  |  |  | 20246.4
453-1-8 | Testing PTPs, ISTPs | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | S |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 20502.53
S53-7.01 | The TF installation on the left side | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 35 |  | C | [5 empty] | 21439.6
7503-431 | Seal gaps MC shims,cooling tubes, for insul pour | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 46 | X | C | 6 |  |  |  |  | 22496
7503-439 | Complete mag diag & machine I&C | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 51 | X | C | 6 |  |  |  |  | 22496
7503-424 | Install TF alignment & traction ring | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 41 | X | C | 6 |  |  |  |  | 22764.42
7503-426 | Pull TF coil radially inward. Verify nose fit up | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 42 | X | C | 6 |  |  |  |  | 22764.42
7503-428 | Lock TF coils at four support locations | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 43 | X | C | 6 |  |  |  |  | 22764.42
7503-400 | Install inboard and outboard shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 24554.88
7503-402 | Move all FPA's together, chk fitup,tack shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 24554.88
7503-404 | Weld inboard shims on mating flanges | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 24554.88
7503-416 | Position Spool pieces and Bolt MC flanges | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 29 | X | C | 6 |  |  |  |  | 24554.88
S32-8.01 | partially weld the inboard shim. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P2 | 67 |  | C | [5 empty] | 24738
S33-8.01 | partially weld the inboard shim. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S3P3 | 67 |  | C | [5 empty] | 24738
7503-422 | Weld all six port 4's in place | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 36 | X | C | 6 |  |  |  |  | 25308
S53-4.01 | Install boots on ports except for the two port | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 21 |  | C | [5 empty] | 26387.2
7503-150A | FPA-3 Installation and assembly test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 19 | X | C | 6 |  |  |  |  | 27283.2
7503-422.1 | Install E-Beam mapping & diag equipt | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 37 | X | C | 6 |  |  |  |  | 27283.2
7503-430 | Install MC structure insulation boots port 4's | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 45 | X | C | 6 |  |  |  |  | 27283.2
7503-439 | Complete mag diag & machine I&C | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 51 | X | C | 6 |  |  |  |  | 27283.2
7503-454 | Install cryostat base, vapor barrier port boots | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 62 | X | C | 6 |  |  |  |  | 28211.2
7503-458 | Integrated Electrical testing | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 64 | X | C | 6 |  |  |  |  | 28211.2
7503-464 | Connect coil & VV instrumentation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 67 | X | C | 6 |  |  |  |  | 28211.2
7503-471 | Install cryostat upper section, VB & port boots | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 70 | X | C | 6 |  |  |  |  | 28211.2
453-1-8 | Testing PTPs, ISTPs | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | S |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 31289.67
S53-11.02 | Connect MC coolant lines to the manifold | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 41 |  | C | [5 empty] | 32984
7503-420 | Mate-up and Weld spacers onto vvsa | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 35 | X | C | 6 |  |  |  |  | 33744
1421-3138 | Resolve issues, release assembly spec&drawings | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142J | 18 | X | C |  | C |  |  |  | 37372.8
7503-260 | PTP Pumpdown & leak check VV | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 40 | X | C | 6 |  |  |  |  | 40924.8
7503-434 | Instl in-cryostat cabling for elect pwr to coils | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 49 | X | C | 6 |  |  |  |  | 40924.8
7503-436 | Connect cabling, and I&C to MC & TF Coils | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 50 | X | C | 6 |  |  |  |  | 40924.8
730.8200 | PTP and Cool down | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 73 | X | C | 6 |  |  |  |  | 42316.8
7503-472 | Install midplane cryostat sections & port boots | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 71 | X | C | 6 |  |  |  |  | 42316.8
453-1-8 | Testing PTPs, ISTPs | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | S |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 44496.86
7503-150A | FPA-3 Installation and assembly test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 19 | X | C | 6 |  |  |  |  | 44992
7503-470 | Install cryostat cooling syst & instrumentation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 69 | X | C | 6 |  |  |  |  | 46521.6
1421-3134 | Issue interface dwgs for comment | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142J | 11 | X | C |  | C |  |  |  | 46716
453-1-8 | Testing PTPs, ISTPs | 0 | A Critical path | A Critical path | A CRITICAL PATH | 4 | 45 | 453 |  | 9450 |  | 4501 | S |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 48693.76
7503-417 | Retorque all super nuts after 30 days | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 30 | X | C | 6 |  |  |  |  | 49109.76
S53-3.02 | Install small dome ports remaining circ ports. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 19 |  | C | [5 empty] | 49476
S53-3.03 | Leak check each port after it is welded. | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P3 | 20 |  | C | [5 empty] | 49476
1421-3115B | Assemble & test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142C |  | X | C |  | C |  |  |  | 49830.4
7503-400 | Install inboard and outboard shims | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 22 | X | C | 6 |  |  |  |  | 51552
7503-150A | FPA-3 Installation and assembly test | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 19 | X | C | 6 |  |  |  |  | 54566.4
7503-431 | Seal gaps MC shims,cooling tubes, for insul pour | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 46 | X | C | 6 |  |  |  |  | 54566.4
7503-422 | Weld all six port 4's in place | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 36 | X | C | 6 |  |  |  |  | 61387.2
7503-470 | Install cryostat cooling syst & instrumentation | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 69 | X | C | 6 |  |  |  |  | 112844.8
7503-420 | Mate-up and Weld spacers onto vvsa | 0 | A Critical path | A Critical path | A CRITICAL PATH | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 35 | X | C | 6 |  |  |  |  | 122774.4
S23-A3B3C3 | Assemble/Align Mod-Coils A3/B3/C3 | 0 | A Critical path | A Critical path | A CRITICAL PATH | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S2P2 |  |  | C | ABC3 |  |  |  |  | 171696.21
S21-2.01 | Set A1 on pre-measured fixt, "B" side down | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C | A1 | 2021 |  |  |  | 1503
S21-2.07 | Remove A1 coil from stand | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C | A1 | 2021 |  |  |  | 1503
S21-2.08 | Measure B1 "A" flange | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C | B1 | 2021 |  |  |  | 3006
S21-2.11 | Measure C1 "A" flange | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C | C1 | 2021 |  |  |  | 3006
S21-2.14 | Measure Type A1-A2 "A" flange | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C | A1 | 2021 |  |  |  | 3158.62
S21-1.02 | Epoxy paint all close fitting interfacing surfac | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C | ABC1 | 2021 |  |  |  | 4509
S21-1.01 | Verify mating MC's A1,B1,C1 | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C | ABC1 | 2021 |  |  |  | 6012
1421-3112B | Procure/fab parts for test&initial assembly | 1 | B <1 week | B <1 week | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142C |  | X | C |  | C |  |  |  | 6032.8
S21-3.02 | Grind shims first article f/assy process qu | 1 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  | C |  | 2021 |  |  |  | 6408.8
1421-3112B | Procure/fab parts for test&initial assembly | 1 | B <1 week | B <1 week | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142C |  | X | C |  | C |  |  |  | 12760
211-125 | Fabricate/Install/Test | 2 | B <1 week | B <1 week | B <1 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 4107.12
7503-240 | Install Vacuum pumping system | 2 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 38 | X | C | 6 |  |  |  |  | 5624
211-125 | Fabricate/Install/Test | 2 | B <1 week | B <1 week | B <1 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 6138.72
211-125 | Fabricate/Install/Test | 2 | B <1 week | B <1 week | B <1 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 6165.64
211-125 | Fabricate/Install/Test | 2 | B <1 week | B <1 week | B <1 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 8486.8
7503-240 | Install Vacuum pumping system | 2 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 38 | X | C | 6 |  |  |  |  | 13641.6
7503-416.1 | Machine Flange A & B of Spool Piece 1 | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 14 | X | C | 6 |  |  |  |  | 1369.04
7503-416.2 | Machine Flange A & B of Spool Piece 2 | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 15 | X | C | 6 |  |  |  |  | 1369.04
7503-416.3 | Machine Flange A & B of Spool Piece 3 | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 16 | X | C | 6 |  |  |  |  | 1369.04
7503-060 | Install Lower PF 4,5&6 into prelim position | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 06 | X | C | 6 |  |  |  |  | 2175.68
7503-060 | Install Lower PF 4,5&6 into prelim position | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 06 | X | C | 6 |  |  |  |  | 2638.72
7503-419 | Remove temporary assy structure | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 32 | X | C | 6 |  |  |  |  | 3374.4
7503-070 | Install 3 Spool Pieces on fixt & test movement | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 06 | X | C | 6 |  |  |  |  | 6596.8
7503-070 | Install 3 Spool Pieces on fixt & test movement | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 06 | X | C | 6 |  |  |  |  | 7648.4
7501-10.10 | Test TC floor deflections with concrete block | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 08 | X | C | 6 |  |  |  |  | 7944
7503-419 | Remove temporary assy structure | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 32 | X | C | 6 |  |  |  |  | 8184.96
7501-10.10 | Test TC floor deflections with concrete block | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 08 | X | C | 6 |  |  |  |  | 9895.2
7501-10.9 | Install test cell metrology site monuments & chk | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 07 | X | C | 6 |  |  |  |  | 10592
7503-070 | Install 3 Spool Pieces on fixt & test movement | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 06 | X | C | 6 |  |  |  |  | 10878.4
7503-020 | Install Permanent support base and columns | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 04 | X | C | 6 |  |  |  |  | 11472.6
7503-015 | Install Temp Assembly Structure | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 05 |  | C | 6 |  |  |  |  | 11916
7503-418 | Raise permanent supports to take machine loads | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 31 | X | C | 6 |  |  |  |  | 12321.36
1421-3125 | Determine geometry&location of high COF shims&pl | 3 | B <1 week | B <1 week | B <1 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142E | 12 | X | [6 empty] | 12457.6
7501-10.8 | Exercise assy struc with concrete blocks & metro | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 | EC45 | 7503 | F | A |  | X |  | 09 | X | C | 6 |  |  |  |  | 13240
7501-11 | Exercise assy struc w/FPA-1 before start of assy | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 11 | X | C | 6 |  |  |  |  | 13240
7503-080A | FPA-1 Installation and assembly test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 09 | X | C | 6 |  |  |  |  | 13240
7503-415.0 | Spool piece installation test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 13 | X | C | 6 |  |  |  |  | 13555.28
7503-418 | Raise permanent supports to take machine loads | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 31 | X | C | 6 |  |  |  |  | 15346.8
7501-10.10 | Test TC floor deflections with concrete block | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 08 | X | C | 6 |  |  |  |  | 16317.6
7503-020 | Install Permanent support base and columns | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 04 | X | C | 6 |  |  |  |  | 16317.6
7503-419.1 | Install/Level FPA's and spool piece supports | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 33 | X | C | 6 |  |  |  |  | 20462.4
7501-10.9 | Install test cell metrology site monuments & chk | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 07 | X | C | 6 |  |  |  |  | 21756.8
7503-419.1 | Install/Level FPA's and spool piece supports | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 33 | X | C | 6 |  |  |  |  | 23725.2
7503-415.7 | Measure vsl gaps to determ spool piece dimension | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 12 | X | C | 6 |  |  |  |  | 23748.48
7503-015 | Install Temp Assembly Structure | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 05 |  | C | 6 |  |  |  |  | 24476.4
7503-418 | Raise permanent supports to take machine loads | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 31 | X | C | 6 |  |  |  |  | 25308
7501-11 | Exercise assy struc w/FPA-1 before start of assy | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 11 | X | C | 6 |  |  |  |  | 26387.2
7503-070 | Install 3 Spool Pieces on fixt & test movement | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 06 | X | C | 6 |  |  |  |  | 26387.2
7503-080A | FPA-1 Installation and assembly test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 09 | X | C | 6 |  |  |  |  | 26387.2
7503-415.0 | Spool piece installation test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 13 | X | C | 6 |  |  |  |  | 27014.4
7503-419.1 | Install/Level FPA's and spool piece supports | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 33 | X | C | 6 |  |  |  |  | 33744
INTRF-050 | Complete Shim fabrication drawings (ORNL) | 3 | B <1 week | B <1 week | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142F | 15 | X | C |  | C |  |  |  | 37372.8
7501-10.10 | Test TC floor deflections with concrete block | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 08 | X | C | 6 |  |  |  |  | 39580.8
7503-020 | Install Permanent support base and columns | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 04 | X | C | 6 |  |  |  |  | 39580.8
7503-416.1 | Machine Flange A & B of Spool Piece 1 | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 14 | X | C | 6 |  |  |  |  | 42960
7503-416.2 | Machine Flange A & B of Spool Piece 2 | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 15 | X | C | 6 |  |  |  |  | 42960
7503-416.3 | Machine Flange A & B of Spool Piece 3 | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 16 | X | C | 6 |  |  |  |  | 42960
7501-10.8 | Exercise assy struc with concrete blocks & metro | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 | EC45 | 7503 | F | A |  | X |  | 09 | X | C | 6 |  |  |  |  | 43513.6
7501-11 | Exercise assy struc w/FPA-1 before start of assy | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 11 | X | C | 6 |  |  |  |  | 43513.6
7503-080A | FPA-1 Installation and assembly test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 09 | X | C | 6 |  |  |  |  | 43513.6
7503-415.0 | Spool piece installation test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 13 | X | C | 6 |  |  |  |  | 44548.48
INTRF-049 | prepare winding form mods for weld clamp bolts | 3 | B <1 week | B <1 week | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142F | 15 | X | C |  | C |  |  |  | 46716
7501-10.8 | Exercise assy struc with concrete blocks & metro | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 | EC45 | 7503 | F | A |  | X |  | 09 | X | C | 6 |  |  |  |  | 52774.4
7501-10.9 | Install test cell metrology site monuments & chk | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 07 | X | C | 6 |  |  |  |  | 52774.4
7501-11 | Exercise assy struc w/FPA-1 before start of assy | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 11 | X | C | 6 |  |  |  |  | 52774.4
7503-080A | FPA-1 Installation and assembly test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 09 | X | C | 6 |  |  |  |  | 52774.4
7503-415.0 | Spool piece installation test | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 13 | X | C | 6 |  |  |  |  | 54028.8
7503-415.7 | Measure vsl gaps to determ spool piece dimension | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 12 | X | C | 6 |  |  |  |  | 55068.48
7503-015 | Install Temp Assembly Structure | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 1 | 9450 |  | 7503 | F | A |  | X |  | 05 |  | C | 6 |  |  |  |  | 59371.2
7503-418 | Raise permanent supports to take machine loads | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 31 | X | C | 6 |  |  |  |  | 61387.2
7503-419.1 | Install/Level FPA's and spool piece supports | 3 | B <1 week | B <1 week | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 33 | X | C | 6 |  |  |  |  | 81849.6
S22-11.03 | Tension tester measure bolt length | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 16 |  | C |  | 2110 |  |  |  | 801.1
S31-6.01 | Install bumper protection components on the VV | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 44 |  | C | [5 empty] | 801.1
S31-7.03 | move the left MCHP to its final position. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 53 |  | C | [5 empty] | 801.1
S31-7.04 | engage the preinstalled Type-A flange bushings. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 54 |  | C | [5 empty] | 801.1
S31-7.06 | AirLoc Wedgemount leveler up to take the load. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 56 |  | C | [5 empty] | 801.1
S32-1.02 | Install floor mounted tracks and VV base support | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 12 |  | C | [5 empty] | 1397
S22-10.03 | Inject stycast to fill in all shim spaces | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 16 |  | C |  | 2100 |  |  |  | 1602.2
S22-11.01 | Install or identify three primary fiducials | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 16 |  | C |  | 2110 |  |  |  | 1602.2
S22-6.01 | A2 ôAö flange dwn, 20deg fixt.Obtain fiduci | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | A2 | 2060 |  |  |  | 1602.2
S22-6.05 | Lower the Type-B coil onto the Type-A coil. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2060 |  |  |  | 1602.2
S22-6.09 | "wiggle" test Tighten bolt and recheck. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2060 |  |  |  | 1602.2
S22-6.13 | Complete tightening of flange bolts to 100%. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2060 |  |  |  | 1602.2
S22-6.15 | Scan the ôBö flange of Type-B coil | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2060 |  |  |  | 1602.2
S22-7.05 | Lower the Type-C coil onto the Type-B coil. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | C2 | 2070 |  |  |  | 1602.2
S22-7.07 | Perform the X-Y positioning of the coil. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | C2 | 2070 |  |  |  | 1602.2
S22-7.09 | "wiggle" test Tighten bolt and recheck. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | C2 | 2070 |  |  |  | 1602.2
S22-7.12 | Complete tightening of flange bolts to 100%. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | C2 | 2070 |  |  |  | 1602.2
S22-8.01 | Tack weld all inboard shims to one flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C |  | 2080 |  |  |  | 1602.2
S23-2.01 | Set the A3 coil on fixture, A side flange down | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 14 |  |  | A3 | 2023 |  |  |  | 1602.2
S23-2.07 | Remove A3 move to holding area. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 16 |  |  | A3 | 2023 |  |  |  | 1602.2
S25-2.01 | Set the A5 coil on fixture, A side flange down | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | A5 | 2025 |  |  |  | 1602.2
S25-2.07 | Remove A5 move to holding area. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | A5 | 2025 |  |  |  | 1602.2
S31-3.02 | Lift the right side MCHP and position | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 24 |  | C | [5 empty] | 1602.2
S31-3.05 | Install temp scaffolding to install flange hw | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 27 |  | C | [5 empty] | 1602.2
S31-3.06 | Install bolts and shims | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 28 |  | C | [5 empty] | 1602.2
S31-3.07 | Tighten flange fasteners to 50% | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 29 |  | C | [5 empty] | 1602.2
S31-3.11 | Remove flange hardware and temp platforms | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 33 |  | C | [5 empty] | 1602.2
S31-4.03 | Determine laser alignment. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 36 |  | C | [5 empty] | 1602.2
S31-4.05 | Disengage MCHP's to move the left MCHP. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 38 |  | C | [5 empty] | 1602.2
S31-5.03 | Install VVSA to base support | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 42 |  | C | [5 empty] | 1602.2
S31-7.1 | Tighten flange fasteners to 50% | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 60 |  | C | [5 empty] | 1602.2
S31-7.11 | "wiggle" test Tighten bolt and recheck. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 61 |  | C | [5 empty] | 1602.2
S31-7.16 | Tighten nuts 100%. & Measure | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 66 |  | C | [5 empty] | 1602.2
S31-9.02 | Attach temporary VV vertical supports | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 70 |  | C | [5 empty] | 1649.2
S31-9.03 | Transfer load to vertical supports. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 71 |  | C | [5 empty] | 1649.2
S31-4.01 | EMeasure monuments on the MCHP's &walls. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 34 |  | C | [5 empty] | 2616
S32-1.01 | Install Station 3 site monuments | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 11 |  | C | [5 empty] | 2794
S22-10.01 | Install all wing support bladders | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 16 |  | C |  | 2100 |  |  |  | 3204.4
S22-11.05 | Install lift support beams | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 16 |  | C |  | 2110 |  |  |  | 3204.4
S22-11.06 | Remove from stand Move A2-B2-C2 to holding area | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 16 |  | C |  | 2110 |  | 3 |  | 3204.4
S22-2.08 | Measure B2 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | B2 | 2022 |  |  |  | 3204.4
S22-2.11 | Measure C2 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | C2 | 2022 |  |  |  | 3204.4
S22-2.14 | Measure Type A1-A2 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | A2 | 2022 |  |  |  | 3204.4
S22-6.04 | Place alumina grind inboard weld shims on coil. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | A2 | 2060 |  |  |  | 3204.4
S22-6.08 | Install studs, supernuts, torque to 50% of final | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2060 |  |  |  | 3204.4
S22-7.01 | ôA/Bö assy ôAö coil dwn, 40deg fixt.Obtain fiduc | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2070 |  |  |  | 3204.4
S22-7.04 | Place alumin grind inboard weld shims on coil. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2070 |  |  |  | 3204.4
S22-7.08 | Install studs, supernuts, torque to 50% of fina | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | C2 | 2070 |  |  |  | 3204.4
S23-2.08 | Measure B3 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 17 |  |  | B3 | 2023 |  |  |  | 3204.4
S23-2.11 | Measure C3 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 18 |  |  | C3 | 2023 |  |  |  | 3204.4
S23-2.14 | Measure Type A3-A4 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 19 |  |  | A3 | 2023 |  |  |  | 3204.4
S24-2.08 | Measure B4 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | B4 | 2024 |  |  |  | 3204.4
S24-2.11 | Measure C4 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | C4 | 2024 |  |  |  | 3204.4
S24-2.14 | Measure Type A3-A4 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | A4 | 2024 |  |  |  | 3204.4
S25-2.08 | Measure B5 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | B5 | 2025 |  |  |  | 3204.4
S25-2.11 | Measure C5 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | C5 | 2025 |  |  |  | 3204.4
S25-2.14 | Measure Type A5-A6 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | A5 | 2025 |  |  |  | 3204.4
S31-3.09 | Perform position adjust on right side MCHP | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 31 |  | C | [5 empty] | 3204.4
S31-4.02 | Place all of the laser screens | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 35 |  | C | [5 empty] | 3204.4
S31-4.06 | Remove both MCHP's. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 39 |  | C | [5 empty] | 3204.4
S31-5.02 | Install VV NBI port support stand. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 41 |  | C | [5 empty] | 3204.4
S31-5.04 | Secure the VVSA to base & NBI port sprt stand. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 43 |  | C | [5 empty] | 3204.4
S31-6.03 | move the left MCHP over the VV. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 46 |  | C | [5 empty] | 3204.4
S31-6.05 | Make adjustments to properly align MCHP. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 48 |  | C | [5 empty] | 3204.4
S31-7.02 | move the right MCHP over the VV | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 52 |  | C | [5 empty] | 3204.4
S31-7.09 | Install bolts, alumina and inboard weld shims. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 59 |  | C | [5 empty] | 3204.4
S26-2.08 | Measure B6 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | B6 | 2026 |  |  |  | 3298.4
S26-2.11 | Measure C6 "A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | C6 | 2026 |  |  |  | 3298.4
S26-2.14 | Measure Type A5-A6"A" flange | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 11 |  |  | A6 | 2026 |  |  |  | 3298.4
S31-10.02 | Transfer Period 1 to Station 5 in NCSX TC | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 75 |  | C | [5 empty] | 3298.4
S31-9.01 | Attach VV permanent vertical supports | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 69 |  | C | [5 empty] | 3298.4
S31-9.05 | Prepare VVSA for transport. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 73 |  | C | [5 empty] | 3298.4
S32-1.03 | Establish the MCHP CG location. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 15 |  | C | [5 empty] | 3298.4
S32-2.02 | Verify cart motion. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 17 |  | C | [5 empty] | 3298.4
S22-1.02 | Epoxy paint all close fitting interfacing surfac | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC2 | 2022 |  |  |  | 4806.6
S22-6.11 | adjust shims locally. Re-torque all studs to 50% | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2060 |  |  |  | 4806.6
S23-1.02 | Epoxy paint all close fitting interfacing surfac | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 14 |  |  | ABC3 | 2023 |  |  |  | 4806.6
S23-3.02 | Compress alumina shims sort by thickness | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 20 |  |  |  | 2023 |  |  |  | 4806.6
S24-1.02 | Epoxy paint all close fitting interfacing surfac | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC4 | 2024 |  |  |  | 4806.6
S25-1.02 | Epoxy paint all close fitting interfacing surfac | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC5 | 2025 |  |  |  | 4806.6
S31-7.13 | Perform position adjustments right side MCHP | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 63 |  | C | [5 empty] | 4806.6
S25-3.02 | Compress alumina shims sort by thickness | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 14 |  |  |  | 2025 |  |  |  | 4877.1
S26-1.02 | Epoxy paint all close fitting interfacing surfac | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC6 | 2026 |  |  |  | 4947.6
S32-1.01 | Install Station 3 site monuments | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 11 |  | C | [5 empty] | 4947.6
S22-1.01 | Verify mating MC's of MCHP will come together | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC2 | 2022 |  |  |  | 6408.8
S22-3.02 | Compress alumina shims sort by thickness | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 14 |  |  |  | 2022 |  |  |  | 6408.8
S23-1.01 | Verify mating MC's of MCHP will come together | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 14 |  |  | ABC3 | 2023 |  |  |  | 6408.8
S24-1.01 | Verify mating MC's of MCHP will come together | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC4 | 2024 |  |  |  | 6408.8
S24-3.02 | Compress alumina shims sort by thickness | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 14 |  |  |  | 2024 |  |  |  | 6408.8
S25-1.01 | Verify mating MC's of MCHP will come together | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC5 | 2025 |  |  |  | 6408.8
S31-7.08 | Install temp scaffolding to install flange hw | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 58 |  | C | [5 empty] | 6408.8
S26-1.01 | Verify mating MC's of MCHP will come together | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 10 |  |  | ABC6 | 2026 |  |  |  | 6596.8
S26-3.02 | Compress alumina shims sort by thickness | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 |  | 9450 | BLCK | 1810 |  |  |  |  | S2PM | 14 |  |  |  | 2026 |  |  |  | 6596.8
S31-10.01 | transfer the unit to the transfer support frame | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 74 |  | C | [5 empty] | 6596.8
S31-9.04 | Install VV lateral supports and align | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 72 |  | C | [5 empty] | 6596.8
S32-2.01 | Install MCHP support cart assemblies | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 16 |  | C | [5 empty] | 6596.8
S32-1.02 | Install floor mounted tracks and VV base support | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P2 | 12 |  | C | [5 empty] | 8246
S22-10.02 | local service connections on each MC. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 16 |  | C |  | 2100 |  |  |  | 12817.6
S22-6.12 | Install bushings | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 20 | 1810 |  |  |  |  | S2PZ | 14 |  | C | B2 | 2060 |  |  |  | 16022
S22-7.11 | Install bushings Replace nut and tighten to 50% | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2PZ | 14 |  | C | C2 | 2070 |  |  |  | 16022
S31-7.15 | Pre-fit & Install bushings | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 65 |  | C | [5 empty] | 16022
S31-8.01 | partially weld the inboard shim. | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 67 |  | C | [5 empty] | 24174
S26A6B6C62 | Assemble/Align Mod-Coils A6/B6/C6 | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S2P3 |  |  | C | ABC6 |  |  |  |  | 53351.62
S26-A6B6C6 | Assemble/Align Mod-Coils A6/B6/C6 | 4 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S2P3 |  |  | C | ABC6 |  |  |  |  | 56732.48
S51-14.02 | Remove platforms | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 55 |  | C | [5 empty] | 1649.2
S51-6.02 | Attach the temp support at end of Type-C MC | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 26 |  | C | [5 empty] | 1649.2
S51-6.05 | Secure First TF assy | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 29 |  | C | [5 empty] | 1649.2
S51-6.07 | Secure 2nd TF coil | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 31 |  | C | [5 empty] | 1649.2
S51-6.1 | Installed one side of the TF support brackets | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 34 |  | C | [5 empty] | 1649.2
S51-1.01 | cut off short dome | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 11 |  | C | [5 empty] | 3298.4
S51-13.04 | Install or identify three primary fiducials | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 46 |  | C | [5 empty] | 3298.4
S51-14.01 | Install crane rigging to completed Period assy | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 54 |  | C | [5 empty] | 3298.4
S51-14.03 | Transfer Period 1 to Station 6 in NCSX tTC. | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 56 |  | C | [5 empty] | 3298.4
S51-2.01 | Install period support fixture | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 14 |  | C | [5 empty] | 3298.4
S51-2.02 | Install FPA on support stand. | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 15 |  | C | [5 empty] | 3298.4
S51-3.01 | Install the domes (left and right side), | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 18 |  | C | [5 empty] | 3298.4
S51-6.01 | Rotate 2 TF coils over the MC on the right side | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 25 |  | C | [5 empty] | 3298.4
S51-6.04 | Install TF support brackets | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 28 |  | C | [5 empty] | 3298.4
S51-6.06 | Install TF support brackets | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 30 |  | C | [5 empty] | 3298.4
S51-9.01 | Tack weld the left and right port 4's. | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 37 |  | C | [5 empty] | 3298.4
S51-11.01 | Install tMC coolant manifold | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 40 |  | C | [5 empty] | 4947.6
S51-13.15 | Check trim coils (voltage etc) | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 52 |  | C | [5 empty] | 4947.6
S51-2.04 | Install internal VV working platforms | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 17 |  | C | [5 empty] | 4947.6
S51-5.03 | Platforms may need to be altered | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 24 |  | C | [5 empty] | 4947.6
S51-6.08 | Install machine support plates | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 32 |  | C | [5 empty] | 4947.6
S51-13.03 | bring the VV into proper alignment | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 45 |  | C | [5 empty] | 6596.8
S51-2.03 | Install external working platforms | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 16 |  | C | [5 empty] | 6596.8
S51-9.02 | Install boots on both port 4's. | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 38 |  | C | [5 empty] | 6596.8
S51-12.01 | Install Rogowski coils | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 42 |  | C | [5 empty] | 8246
S51-13.11 | Check Assembly (bolts, etc) | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 48 |  | C | [5 empty] | 8246
S51-13.12 | Check Diagnostics (Loops, thermocouples) | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 49 |  | C | [5 empty] | 8246
S51-13.13 | Check manifolds (pressure, flow, etc.) | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 50 |  | C | [5 empty] | 8246
S51-8.01 | Perform a fit-up check of the four TF coils | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 36 |  | C | [5 empty] | 8246
S51-13.14 | Check 6 modcoils (voltage etc) | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 51 |  | C | [5 empty] | 9895.2
S51-13.16 | Check TF coils (voltage etc) | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 53 |  | C | [5 empty] | 9895.2
S51-10.01 | Install PF coil support structure | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 39 |  | C | [5 empty] | 13193.6
S51-5.02 | Install MC coolant lines on each MC | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 23 |  | C | [5 empty] | 19790.4
S51-7.01 | The TF installation on the left side | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 35 |  | C | [5 empty] | 21439.6
S51-4.01 | Install boots on ports except for the two port | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 21 |  | C | [5 empty] | 26387.2
S51-11.02 | Connect MC coolant lines to the manifold | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P1 | 41 |  | C | [5 empty] | 32984
S51-3.02 | Install small dome ports remaining circ ports. | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 19 |  | C | [5 empty] | 49476
S51-3.03 | Leak check each port after it is welded. | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P1 | 20 |  | C | [5 empty] | 49476
S25A5B5C52 | Assemble/Align Mod-Coils A5/B5/C5 (under 2 shift | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1810 |  |  |  |  | S2P3 |  |  | C | ABC5 |  |  |  |  | 50053.22
S25-A5B5C5 | Assemble/Align Mod-Coils A5/B5/C5 (under 1 shift | 5 | B <1 week | B <1 week | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S2P3 |  |  | C | ABC5 |  |  |  |  | 125174.28
S21-10.01 | Install all wing support bladders | 6 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 13 |  | C |  | 2100 |  |  |  | 3204.4
METFY07R1 | Dimensional control plans for station 2 | 6 | C <2 weeks | C <2 weeks | B <1 month | 8 | 82 | 820 |  | 9450 |  | 8205 | F | A |  |  |  | 10 |  | C |  |  |  | 3 |  | 83630.4
1421-3075 | Setup test fixture &perform JHA & pre-job brief | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 23 | X | C |  | C |  |  |  | 1202.4
1421-3075 | Setup test fixture &perform JHA & pre-job brief | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 23 | X | C |  | C |  |  |  | 1206.56
S21-10.03 | Inject stycast in all shim spaces | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | 40 | 1810 |  |  |  |  | S2P1 | 13 |  | C |  | 2100 |  |  |  | 1602.2
1421-3077 | Meas joint deflect vs preload & loss of preload | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 24 | X | C |  | C |  |  |  | 1803.6
1421-3079 | Measure joint deflec & preload v. temp @80K | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 25 | X | C |  | C |  |  |  | 1803.6
1421-3084 | Measure joint deflection&preload v. cooldown cyc | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 26 | X | C |  | C |  |  |  | 1803.6
1421-3087 | Perform pullout tests for tapped holes | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 27 | X | C |  | C |  |  |  | 1803.6
1421-3077 | Meas joint deflect vs preload & loss of preload | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 24 | X | C |  | C |  |  |  | 3619.68
1421-3079 | Measure joint deflec & preload v. temp @80K | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 25 | X | C |  | C |  |  |  | 3619.68
1421-3084 | Measure joint deflection&preload v. cooldown cyc | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 26 | X | C |  | C |  |  |  | 3619.68
1421-3087 | Perform pullout tests for tapped holes | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 27 | X | C |  | C |  |  |  | 3619.68
1421-3090 | Document&conduct review of test results | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 29 | X | C |  | C |  |  |  | 6032.8
1421-3081 | Meas joint deflect & preload v. time (days) at | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 28 | X | C |  | C |  |  |  | 12024
1421-3081 | Meas joint deflect & preload v. time (days) at | 7 | C <2 weeks | C <2 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 |  |  | L |  | 142B | 28 | X | C |  | C |  |  |  | 24131.2
7503-462 | LN2 connections from coils to manifolds | 8 | C <2 weeks | C <2 weeks | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 66 | X | C | 6 |  |  |  |  | 11630.4
7503-462 | LN2 connections from coils to manifolds | 8 | C <2 weeks | C <2 weeks | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 66 | X | C | 6 |  |  |  |  | 28211.2
S52-6.02 | Attach the temp support at end of Type-C MC | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 26 |  | C | [5 empty] | 1649.2
S52-6.05 | Secure First TF assy | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 29 |  | C | [5 empty] | 1649.2
S52-6.07 | Secure 2nd TF coil | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 31 |  | C | [5 empty] | 1649.2
S52-6.1 | Installed one side of the TF support brackets | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 34 |  | C | [5 empty] | 1649.2
S52-14.02 | Remove platforms | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 55 |  | C | [5 empty] | 1705.2
S52-1.01 | cut off short dome | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 11 |  | C | [5 empty] | 3298.4
S52-13.04 | Install or identify three primary fiducials | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 46 |  | C | [5 empty] | 3298.4
S52-2.01 | Install period support fixture | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 14 |  | C | [5 empty] | 3298.4
S52-2.02 | Install FPA on support stand. | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 15 |  | C | [5 empty] | 3298.4
S52-3.01 | Install the domes (left and right side), | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 18 |  | C | [5 empty] | 3298.4
S52-6.01 | Rotate 2 TF coils over the MC on the right side | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 25 |  | C | [5 empty] | 3298.4
S52-6.04 | Install TF support brackets | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 28 |  | C | [5 empty] | 3298.4
S52-6.06 | Install TF support brackets | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 30 |  | C | [5 empty] | 3298.4
S52-9.01 | Tack weld the left and right port 4's. | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 37 |  | C | [5 empty] | 3298.4
S52-14.01 | Install crane rigging to completed Period assy | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 54 |  | C | [5 empty] | 3410.4
S52-14.03 | Transfer Period 2 to Station 6 in NCSX tTC. | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 56 |  | C | [5 empty] | 3410.4
S52-11.01 | Install tMC coolant manifold | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 40 |  | C | [5 empty] | 4947.6
S52-13.15 | Check trim coils (voltage etc) | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 52 |  | C | [5 empty] | 4947.6
S52-2.04 | Install internal VV working platforms | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 17 |  | C | [5 empty] | 4947.6
S52-5.03 | Platforms may need to be altered | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 24 |  | C | [5 empty] | 4947.6
S52-6.08 | Install machine support plates | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 32 |  | C | [5 empty] | 4947.6
S52-13.03 | bring the VV into proper alignment | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 45 |  | C | [5 empty] | 6596.8
S52-2.03 | Install external working platforms | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 16 |  | C | [5 empty] | 6596.8
S52-9.02 | Install boots on both port 4's. | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 38 |  | C | [5 empty] | 6596.8
S52-12.01 | Install Rogowski coils | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 42 |  | C | [5 empty] | 8246
S52-13.11 | Check Assembly (bolts, etc) | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 48 |  | C | [5 empty] | 8246
S52-13.12 | Check Diagnostics (Loops, thermocouples) | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 49 |  | C | [5 empty] | 8246
S52-13.13 | Check manifolds (pressure, flow, etc.) | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 50 |  | C | [5 empty] | 8246
S52-8.01 | Perform a fit-up check of the four TF coils | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 36 |  | C | [5 empty] | 8246
S21-9.01 | Install trim coil and supports | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 43 |  | C | [5 empty] | 9895.2
S52-13.14 | Check 6 modcoils (voltage etc) | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 51 |  | C | [5 empty] | 9895.2
S52-13.16 | Check TF coils (voltage etc) | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 53 |  | C | [5 empty] | 9895.2
R1810-2002 | Test out Equip & Procedures | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S2PX | 14 |  |  | 2A |  |  |  |  | 11215.4
S52-10.01 | Install PF coil support structure | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 39 |  | C | [5 empty] | 13193.6
7503-110A | FPA-2 Installation and assembly test | 9 | C <2 weeks | C <2 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 17 | X | C | 6 |  |  |  |  | 13690.4
S52-5.02 | Install MC coolant lines on each MC | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 23 |  | C | [5 empty] | 19790.4
S52-7.01 | The TF installation on the left side | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 35 |  | C | [5 empty] | 21439.6
S52-4.01 | Install boots on ports except for the two port | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 21 |  | C | [5 empty] | 26387.2
7503-110A | FPA-2 Installation and assembly test | 9 | C <2 weeks | C <2 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 17 | X | C | 6 |  |  |  |  | 27283.2
S52-11.02 | Connect MC coolant lines to the manifold | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 2 | 9450 |  | 1815 |  |  |  |  | S4P2 | 41 |  | C | [5 empty] | 32984
7503-110A | FPA-2 Installation and assembly test | 9 | C <2 weeks | C <2 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 17 | X | C | 6 |  |  |  |  | 44992
S52-3.02 | Install small dome ports remaining circ ports. | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 19 |  | C | [5 empty] | 49476
S52-3.03 | Leak check each port after it is welded. | 9 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  |  | S4P2 | 20 |  | C | [5 empty] | 49476
7503-110A | FPA-2 Installation and assembly test | 9 | C <2 weeks | C <2 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 17 | X | C | 6 |  |  |  |  | 54566.4
R1810-209 | Perform metrology setup & checks | 10 | C <2 weeks | C <2 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S2PX | 12 |  |  | 2A |  |  |  |  | 7672.82
1429-3029 | Bolt Tests 3&4. Write Report | 11 | D <3 weeks | D <3 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1429 |  |  | L |  | 142D | 11 | X | [6 empty] | 13259.44
1429-3029 | Bolt Tests 3&4. Write Report | 11 | D <3 weeks | D <3 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1429 |  |  | L |  | 142D | 11 | X | [6 empty] | 16137.74
1429-3062C | PPPL Cut, Grind, debur Outboard Shims | 12 | D <3 weeks | D <3 weeks | B <1 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMU |  | X | [6 empty] | 1861.6
7501-10.3 | Assemble 3 VV spool piece support stands | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 5296
7501-10.4 | Assemble machine base structure | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 5296
7501-10.5 | Assemble 3 FPA installation carts | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 5296
1429-3062C | PPPL Cut, Grind, debur Outboard Shims | 12 | D <3 weeks | D <3 weeks | B <1 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMU |  | X | [6 empty] | 6309.24
7501-10.2 | Assemble 3 FPA support stands | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 7944
1429-3066C | Apply Alumina to OutboardShims | 12 | D <3 weeks | D <3 weeks | B <1 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMU |  | X | [6 empty] | 9308
7501-10.3 | Assemble 3 VV spool piece support stands | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 10878.4
7501-10.4 | Assemble machine base structure | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 10878.4
7501-10.5 | Assemble 3 FPA installation carts | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 10878.4
7501-10.2 | Assemble 3 FPA support stands | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 16317.6
7501-10.3 | Assemble 3 VV spool piece support stands | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 26387.2
7501-10.4 | Assemble machine base structure | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 26387.2
7501-10.5 | Assemble 3 FPA installation carts | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 26387.2
7501-10.2 | Assemble 3 FPA support stands | 12 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 39580.8
PHIL-26 | Grind inbd. Shims to thickness (outside shop) | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 1276
1303-101 | Complete Trim Coil SRD | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 1529.68
1303-110 | Trim Coil FDR | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | M |  | 13 |  |  |  |  | 1529.68
PHIL-04 | water jet cut shims for A/B flange weld test | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL1 |  |  |  | 1803.6
PHIL-23 | Water jet cut inboard 0.625 316 SS | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 1803.6
PHIL-27 | Solution anneal shims | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 1982.72
PHIL-12 | Weld fiducials on A6 & B6 | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C | A6 | PHL2 |  |  |  | 2404.8
PHIL-16 | Re-mount A6 on wedge | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C | A6 | PHL2 |  |  |  | 2404.8
PHIL-18 | Measure B6 on wedge | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C | B6 | PHL2 |  |  |  | 2404.8
PHIL-22 | Water jet cut outboard 0,5" stk 316 SS shims | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 2404.8
PHIL-32 | Align castings | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 2404.8
PHIL-38 | Install all shims and adjust bushings | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 2404.8
PHIL-40 | Perform 25% of welding & measure | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 2404.8
PHIL-41 | Perform 50% of welding & measure | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 2404.8
PHIL-42 | Perform 75% of welding & measure | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 2404.8
PHIL-43 | finish welding & measure | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 2404.8
PHIL-37 | Set up dial ind., CMM, transit system | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 3006
1303-107 | Prepare for FDR | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 3059.36
1303-042 | Install supports onto coils | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 17 | 1 |  | 13 |  |  |  |  | 4589.04
184-035 | Bid & Award Ext Trim Coils | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | T | B |  |  | 133 | 12 | 1 | [5 empty] | P | 4589.04
PHIL-15 | Remove A6 & lower & grout wedge | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C | A6 | PHL2 |  |  |  | 4809.6
PHIL-24 | Assemble castings,align torque&meas inbd. shims | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 4809.6
PHIL-39 | Final align and baseline measurements | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  | C |  | PHL2 |  |  |  | 5410.8
1303-042 | Install supports onto coils | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 17 | 1 |  | 13 |  |  |  |  | 6596.8
1303-103 | Analysis | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 7648.4
1303-103 | Analysis | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 7648.4
1303-116 | Detail Fabrication Drawings | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 12237.44
7501-10 | Fabricate/Assemble assembly structure | 13 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 01 | X | C | 6 |  |  |  |  | 15888
1303-105 | FDR Dwgs for coils and supports | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 16061.64
161-037 | PPPL assemble structure | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 17 | 172 |  | 9450 |  | 1752 | T | A |  | B | 172 | 20 | 1 |  | 17 |  |  |  | P | 29786.74
7501-10 | Fabricate/Assemble assembly structure | 13 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 01 | X | C | 6 |  |  |  |  | 32635.2
184-037 | External Trim Coil & Supports Procurement | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 133 |  | 9450 |  | 1354 | T | B | C |  | 133 | 14 | 1 |  | 13 |  |  |  | P | 47078.9
INTRF-040 | ANalysis of tensile loads (ORNL) | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142J | 10 | X | [6 empty] | 49830.4
161-036.9 | Deliver base support materials | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 17 | 172 |  | 9450 |  | 1752 | T | A | S | 3 | 172 | 20 | 1 |  | 17 |  |  | 3 | P | 51587.52
7501-10 | Fabricate/Assemble assembly structure | 13 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 01 | X | C | 6 |  |  |  |  | 79161.6
1803-6.8 | Procure materials and fixture | 13 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 6.00 | 44 | [7 empty] | 111484.7
7501-10 | Fabricate/Assemble assembly structure | 13 | D <3 weeks | D <3 weeks | B <1 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 01 | X | C | 6 |  |  |  |  | 111760
1803-205 | Station 2 Assembly Drawings | 14 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 2.00 |  | 10 | C |  | C |  | 3 | P | 13200
1429-3026 | COF cyclic testing | 14 | D <3 weeks | D <3 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1429 |  |  | L |  | 142D | 11 | X | [6 empty] | 29970
141-902 | PF6 Lower Inspection & Test | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 31 | 1 | [6 empty] | 1649.2
1355-111 | Installation on PF4,5,6 Coils upon delivery | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 1912.1
141-902 | PF6 Lower Inspection & Test | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 31 | 1 | [6 empty] | 1912.1
1302-225 | PF Coil PDR | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 53 | M |  | 13 |  |  |  |  | 2972.16
1302-270 | PF FDR | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 64 | M |  | 13 |  |  | 3 |  | 2972.16
R1810-2021 | Tools&tooling available for FPA operations | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 13 | M | [6 empty] | 3204.4
1302-200 | Complete PF Coil SRD | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 50 | 1 |  | 13 |  |  |  |  | 4181.52
141-035 | Bid & Award PF Coil Fabrication | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  |  | 13P | 10 | 1 | [5 empty] | P | 6090
R1810-2021 | Tools&tooling available for FPA operations | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 13 | M | [6 empty] | 6540
1302-220 | Prepare for PDR | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 52 | 1 |  | 13 |  |  |  |  | 6687.36
1302-265 | Prepare for FDR | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 63 | 1 |  | 13 |  |  |  |  | 6687.36
1355-111 | Installation on PF4,5,6 Coils upon delivery | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 7833.7
R1810-2011 | Alignment mechanisms, metro equipt &positioning | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 9018
1302-220 | Prepare for PDR | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 52 | 1 |  | 13 |  |  |  |  | 9659.52
1302-265 | Prepare for FDR | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 63 | 1 |  | 13 |  |  |  |  | 9659.52
1302-217 | Drawing Support | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 61 | 1 |  | 13 |  |  |  |  | 11145.6
1302-250 | Analysis Support | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 60 | 1 |  | 13 |  |  |  |  | 13003.2
1302-211 | Complete PF4 PDR Model | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 50 | 1 |  | 13 |  |  |  |  | 13938.4
1302-212 | Complete PF5 PDR Model | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 50 | 1 |  | 13 |  |  |  |  | 14768.56
1302-213 | Complete PF6 PDR Model | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 50 | 1 |  | 13 |  |  |  |  | 14860.8
1302-235 | Detail Drawings PF4 | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 57 | 1 |  | 13 |  |  |  |  | 14860.8
1302-245 | Detail Drawings PF5 | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 58 | 1 |  | 13 |  |  |  |  | 14860.8
1302-260 | Detail Drawings PF6 | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 59 | 1 |  | 13 |  |  |  |  | 14860.8
141-035 | Bid & Award PF Coil Fabrication | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  |  | 13P | 10 | 1 | [5 empty] | P | 29721.6
R1810-2011 | Alignment mechanisms, metro equipt &positioning | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 51040
1352-165 | Fabricate/Dlvr PF 5 Lower | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 24 | 1 |  | 13 |  |  |  | P | 73821.95
1352-145 | Fabricate/Dlvr PF 6 Lower | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 25 | 1 |  | 13 |  |  |  | P | 86654.95
1352-121 | Design/Fab Tooling for PF 5 | 15 | D <3 weeks | D <3 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 18 | 1 |  | 13 |  |  |  | P | 280747.5
711A.040 | Platform nut plates | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  | 27 | 1 | [6 empty] | 139.7
PHIL-05 | solution anneal shims (note: shims not ground). | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL1 |  |  |  | 991.36
711A.040 | Platform nut plates | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  | 27 | 1 | [6 empty] | 2836.98
PHIL-06 | assemble shims&flanges;grind relief in flanges | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL1 |  |  |  | 3607.2
PHIL-07 | weld & monitor distortion; improvise clamping | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL1 |  |  |  | 3607.2
712.020 | Platform Parts | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 4191
PHIL-36 | Install strain gauges | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 4956.8
712.020 | Platform Parts | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 5296
7301-100 | Survey & layout locations for platform posts | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 5439.2
7301-100 | Survey & layout locations for platform posts | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 6620
7301-102 | Machine platform trial assembly & fitup | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 7944
7503-433.1 | Install LN2 manifolds | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 48 | X | C | 6 |  |  |  |  | 11248
7301-100 | Survey & layout locations for platform posts | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 13193.6
PLCT-A2 | Insul,measure,TC, other punch list-A2 | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 | 2 | 9450 |  | 1459 |  |  |  |  | PLCT | 02 |  |  | A2 |  |  |  |  | 15480.9
PLCT-B1 | Insul,measure,TC, other punch list-B1 | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 | 2 | 9450 |  | 1459 |  |  |  |  | PLCT | 03 |  |  | B1 |  |  |  |  | 15480.9
PLCT-A1 | Insul,measure,TC, other punch list-A1 | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 | 2 | 9450 |  | 1459 |  |  |  |  | PLCT | 04 |  |  | A1 |  |  |  |  | 20287.52
712.030 | Miscs Hardware/Material | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 22031.6
712.020 | Platform Parts | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 24738
7503-433.1 | Install LN2 manifolds | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 48 | X | C | 6 |  |  |  |  | 27283.2
7301-102 | Machine platform trial assembly & fitup | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 32635.2
1408-4 | Procure & Deliver Thermocouples | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 66352
7301-102 | Machine platform trial assembly & fitup | 16 | E <4 weeks | E <4 weeks | B <1 month | 7 | 73 | 730 |  | 9450 |  | 7301 | F | A |  |  |  |  | 1 | [6 empty] | 79161.6
S24-A4B4C4 | Assemble/Align Mod-Coils A4/B4/C4 | 16 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S2P2 |  |  | C | ABC4 |  |  |  |  | 108078.85
1429-3028 | Edge loading&Superbolt torque tests 1&2 | 17 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1429 |  |  | L |  | 142D | 11 | X | [6 empty] | 13259.44
1429-3028 | Edge loading&Superbolt torque tests 1&2 | 17 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1429 |  |  | L |  | 142D | 11 | X | [6 empty] | 16137.74
R1810-2013 | Procure alignment mechanisms, fiducials, lifting | 17 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 30060
R1810-2013 | Procure alignment mechanisms, fiducials, lifting | 17 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 31900
INTRF-051 | Release info for procurement of shim material | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142F | 15 | X | C |  | C |  |  |  | 3737.28
1429-3062 | PPPL Cut, Grind, debur Outboard Shims | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMS | 18 | X | [6 empty] | 4367.78
1421-3131 | PDR prep for requirements, design,&development | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142E | 15 | M | [6 empty] | 6228.8
R1810-207 | Compress alumina shims and sort | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S2PX | 12 |  |  | 2A |  |  |  |  | 9018
1429-3027 | Friction Life Test | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1429 |  |  | L |  | 142D | 11 | X | [6 empty] | 13259.44
1429-3062 | PPPL Cut, Grind, debur Outboard Shims | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMS | 18 | X | [6 empty] | 14859.28
1429-3027 | Friction Life Test | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1429 |  |  | L |  | 142D | 11 | X | [6 empty] | 16137.74
1421-3127 | Structural analyses to performance rqmts for bol | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142E | 13 | X | [6 empty] | 37372.8
1429-3066 | Apply Alumina to OutboardShims | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMS | 18 | X | [6 empty] | 42152.99
1429-3060 | Deliver Shim Stock | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  | S |  | SHMS | 17 | X | [6 empty] | 77274.56
1352-122 | Design/Fab Tooling for PF 6 | 18 | E <4 weeks | E <4 weeks | B <1 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 19 | 1 |  | 13 |  |  |  | P | 331639.61
IH1-001 | Coil to coil scoping analysis | 21 | F <5 weeks | F <5 weeks | C <2 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 | 2 |  | L |  | 142E | 10 | X | [6 empty] | 36000
IH1-001 | Coil to coil scoping analysis | 21 | F <5 weeks | F <5 weeks | C <2 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 | 2 |  | L |  | 142E | 10 | X | [6 empty] | 80974.4
S31-3.01 | Move right base support cart to its final positi | 22 | F <5 weeks | F <5 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 23 |  | C | [5 empty] | 801.1
PHIL-11 | Mount A6 on angle plate | 22 | F <5 weeks | F <5 weeks | C <2 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 1202.4
S31-2.04 | Position left MCHP on the cart assembly | 22 | F <5 weeks | F <5 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 19 |  | C | [5 empty] | 1602.2
S31-2.07 | Set positioning stop on the cart | 22 | F <5 weeks | F <5 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 22 |  | C | [5 empty] | 1602.2
S31-2.05 | Secure left MCHP on support cart base. | 22 | F <5 weeks | F <5 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 20 |  | C | [5 empty] | 3204.4
1302-251 | PDR Level Design Support Support | 23 | F <5 weeks | F <5 weeks | C <2 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 51 | 1 |  | 13 |  |  |  |  | 10900.12
7501-10.1 | Fab struct to go between assy sleds&FPA's | 23 | F <5 weeks | F <5 weeks | C <2 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 15888
R1810-2006 | Surface grind set of metal shims for qualificat | 23 | F <5 weeks | F <5 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S2PX | 12 |  |  | 2A |  |  |  |  | 18036
7501-10.1 | Fab struct to go between assy sleds&FPA's | 23 | F <5 weeks | F <5 weeks | C <2 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 32635.2
PHIL-25 | Purchase (2) grinding machines | 23 | F <5 weeks | F <5 weeks | C <2 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 51040
7501-10.1 | Fab struct to go between assy sleds&FPA's | 23 | F <5 weeks | F <5 weeks | C <2 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 79161.6
7501-10.1 | Fab struct to go between assy sleds&FPA's | 23 | F <5 weeks | F <5 weeks | C <2 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 111760
220-137 | Test | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 948.56
220-137 | Test | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 2053.56
220-133 | Procure/Install VPS mechanical | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 5691.36
220-133 | Procure/Install VPS mechanical | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 6160.68
220-117 | Procure/Install AC pwr & Instrumentation | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 7274.4
220-117 | Procure/Install AC pwr & Instrumentation | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 9188.64
220-117 | Procure/Install AC pwr & Instrumentation | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 10740
220-133 | Procure/Install VPS mechanical | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 14320
220-133 | Procure/Install VPS mechanical | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 19098.24
220-117 | Procure/Install AC pwr & Instrumentation | 25 | F <5 weeks | F <5 weeks | C <2 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 26521.6
PLCT-B2 | Insul,measure,TC other punch list-B2 | 26 | G <6 weeks | G <6 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1459 |  |  |  |  | PLCT | 01 |  |  | B2 |  |  |  |  | 15480.9
PLTS-A1 | Grinding -A1 | 27 | G <6 weeks | G <6 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 04 |  |  | A1 |  |  |  |  | 6688.35
R1810-2052 | Bushing test B-C | 27 | G <6 weeks | G <6 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 12 | [7 empty] | 8416.8
1303-114 | Disposition FDR Chits | 28 | G <6 weeks | G <6 weeks | C <2 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 1529.68
1303-112 | Prepare Procurement Coil Spec | 28 | G <6 weeks | G <6 weeks | C <2 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 01 | 1 |  | 13 |  |  |  |  | 4589.04
162-039 | Fabricate Final TF Assy components Components | 28 | G <6 weeks | G <6 weeks | C <2 month | 1 | 15 | 151 |  | 9450 |  | 1550 | T | A | A | B |  | 15 | 1 |  | 15 |  |  |  | P | 83133.18
162-040 | Fabricate Machine/base support interface | 28 | G <6 weeks | G <6 weeks | C <2 month | 1 | 15 | 151 |  | 9450 |  | 1550 | T | A | A | B |  | 15 | 1 |  | 15 |  |  |  | P | 92713.42
162-038 | Fabricate PF Mounting components | 28 | G <6 weeks | G <6 weeks | C <2 month | 1 | 15 | 151 |  | 9450 |  | 1550 | T | A | A | B |  | 15 | 1 |  | 15 |  |  |  | P | 268267.82
162-037 | Fabricate TF/MCWF mounting Components | 28 | G <6 weeks | G <6 weeks | C <2 month | 1 | 15 | 151 |  | 9450 |  | 1550 | T | A | A | B |  | 15 | 1 |  | 15 |  |  |  | P | 328830.26
R1810-2005 | Trial bushing and shim test on prototype | 29 | G <6 weeks | G <6 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 2552
R1810-2005 | Trial bushing and shim test on prototype | 29 | G <6 weeks | G <6 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 18036
442-1-8 | Kirk Keys-Commission | 30 | G <6 weeks | G <6 weeks | C <2 month | 4 | 44 | 442 |  | 9450 |  | 4401 | S |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 1657.6
442-1-6 | Kirk Keys-Install | 30 | G <6 weeks | G <6 weeks | C <2 month | 4 | 44 | 442 |  | 9450 |  | 4401 | F |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 2954.4
442-1-8 | Kirk Keys-Commission | 30 | G <6 weeks | G <6 weeks | C <2 month | 4 | 44 | 442 |  | 9450 |  | 4401 | S |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 2954.4
442-1-8 | Kirk Keys-Commission | 30 | G <6 weeks | G <6 weeks | C <2 month | 4 | 44 | 442 |  | 9450 |  | 4401 | S |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 3031
442-1-6 | Kirk Keys-Install | 30 | G <6 weeks | G <6 weeks | C <2 month | 4 | 44 | 442 |  | 9450 |  | 4401 | F |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 3637.2
442-1-6 | Kirk Keys-Install | 30 | G <6 weeks | G <6 weeks | C <2 month | 4 | 44 | 442 |  | 9450 |  | 4401 | F |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 6630.4
1803-613 | Detail dwgs-man access port | 30 | G <6 weeks | G <6 weeks | C <2 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 6.00 |  | 10 | [5 empty] | P | 6693.72
442-1-6 | Kirk Keys-Install | 30 | G <6 weeks | G <6 weeks | C <2 month | 4 | 44 | 442 |  | 9450 |  | 4401 | F |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 21480
714.025 | Update Final Assembly Plan | 30 | G <6 weeks | G <6 weeks | C <2 month | 7 | 74 | 742 |  | 9450 |  | 7401 | F | A |  |  |  | 11 | 1 | [6 empty] | 26480
1803-605 | Station 6 Assembly Drawings | 30 | G <6 weeks | G <6 weeks | C <2 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 6.00 |  | 10 | [5 empty] | P | 53549.76
1803-601 | Station 6 Assembly Specification | 30 | G <6 weeks | G <6 weeks | C <2 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 6.00 |  | 10 | [5 empty] | P | 71259.83
PHIL-34 | Weld procedure/weld qual. | 31 | H <7 weeks | H <7 weeks | C <2 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 4208.4
1302-214 | Prepare,Review & Approve conductor spec | 32 | H <7 weeks | H <7 weeks | C <2 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 54 | 1 |  | 13 |  |  |  |  | 2972.16
1302-216 | Prepare,Review & Approve coil spec | 32 | H <7 weeks | H <7 weeks | C <2 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 55 | 1 |  | 13 |  |  |  |  | 8916.48
INTRF-045 | FDR prep outboard shims | 33 | H <7 weeks | H <7 weeks | C <2 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142A | 12 | M | [6 empty] | 6228.8
IH4-020 | Prepare outboard shim dwgs and release | 33 | H <7 weeks | H <7 weeks | C <2 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142A | 11 | X | [6 empty] | 9343.2
7503-460 | Instl transition box,cabling,&connect to pwr sup | 34 | H <7 weeks | H <7 weeks | C <2 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 65 | X | C | 6 |  |  |  |  | 11630.4
7503-460 | Instl transition box,cabling,&connect to pwr sup | 34 | H <7 weeks | H <7 weeks | C <2 month | 7 | 75 | 750 | 2 | 9450 |  | 7503 | F | A |  | X |  | 65 | X | C | 6 |  |  |  |  | 28211.2
R1810-2017 | Determine fiducial types&locations | 35 | H <7 weeks | H <7 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 13 | [7 empty] | 2552
R1810-2017 | Determine fiducial types&locations | 35 | H <7 weeks | H <7 weeks | C <2 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 13 | [7 empty] | 16533
INTRF-047 | Resolve chit's and issue outboard shim drawings | 36 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142A | 13 | M | [6 empty] | 9343.2
4101-100.1 | Prepare Preliminary One line diagram | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 293.12
4101-100.1 | Prepare Preliminary One line diagram | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 357.16
4101-100.1 | Prepare Preliminary One line diagram | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 740.52
412-1-6 | C-site Pulsed AC Power Distr-Install | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | F |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 1020.96
P3-171V | VPI (Station 5) B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 18 | 1 |  | B6 |  |  |  | 5 | 1281.76
412-1-6 | C-site Pulsed AC Power Distr-Install | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | F |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 1477.2
412-1-6 | C-site Pulsed AC Power Distr-Install | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | F |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 2424.8
P3-071 | Wind coil B5 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 2 | 07 | 1 |  | B5 |  |  |  | 3 | 2507.13
P2-171C | Final Clamps & Warm Test (Station1) B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 18 | 1 |  | B6 |  |  |  | 1 | 2563.52
P3-161 | Wind coil B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 09 | 1 |  | B6 |  |  |  | 4 | 2563.52
412-1-8 | C-site Pulsed AC Power Distr-Commission | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | S |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 3315.2
412-1-8 | C-site Pulsed AC Power Distr-Commission | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | S |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 3637.2
PLTS-B6 | Grinding -B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 17 |  |  | B6 |  |  |  |  | 3925.39
412-1-8 | C-site Pulsed AC Power Distr-Commission | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | S |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 4431.6
451-4-2 | Final Dsn AC auxiliaries & grounding-Dsn | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 17 |  |  | 45 |  |  |  |  | 4936.8
412-1-6 | C-site Pulsed AC Power Distr-Install | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | F |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 6630.4
412-1-4 | C-site Pulsed AC Power Distr-Procure | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 41 | 412 |  | 9450 |  | 4101 | T |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 7102.29
451-4-2 | Final Dsn AC auxiliaries & grounding-Dsn | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 17 |  |  | 45 |  |  |  |  | 7143.2
P3-061 | Receive B5, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 02 | 1 |  | B5 |  |  |  | 1 | 9318.6
P2-031 | Receive C6, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 04 | 1 |  | C6 |  |  |  | 1 | 9933.64
P3-151 | Receive B6, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 05 | 1 |  | B6 |  |  |  | 1 | 9933.64
P2-171C | Final Clamps & Warm Test (Station1) B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 18 | 1 |  | B6 |  |  |  | 1 | 11215.4
P2-171C | Final Clamps & Warm Test (Station1) B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 18 | 1 |  | B6 |  |  |  | 1 | 12248.68
PLCT-C6 | Insul,measure,TC,SG other punch list-C6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 18 |  |  | C6 |  |  |  |  | 16422.55
P3-061 | Receive B5, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 02 | 1 |  | B5 |  |  |  | 1 | 18336.6
PLTS-C6 | Grinding & Drill Holes -C6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 18 |  |  | C6 |  |  |  |  | 19226.4
P2-031 | Receive C6, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 04 | 1 |  | C6 |  |  |  | 1 | 19546.84
P3-151 | Receive B6, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 05 | 1 |  | B6 |  |  |  | 1 | 19546.84
P3-061 | Receive B5, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 02 | 1 |  | B5 |  |  |  | 1 | 20251.7
P2-031 | Receive C6, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 04 | 1 |  | C6 |  |  |  | 1 | 21589.4
P3-151 | Receive B6, Prep& Instl Cladding | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 05 | 1 |  | B6 |  |  |  | 1 | 21589.4
P3-171V | VPI (Station 5) B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 18 | 1 |  | B6 |  |  |  | 5 | 22110.36
P3-171V | VPI (Station 5) B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 18 | 1 |  | B6 |  |  |  | 5 | 24409.24
P3-080 | Instl Chill Plates,Tubing,Bag B5 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 07 | 1 |  | B5 |  |  |  | 3 | 31403.12
P3-170 | Instl Chill Plates,Tubing,Bag B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 09 | 1 |  | B6 |  |  |  | 4 | 31403.12
P3-080 | Instl Chill Plates,Tubing,Bag B5 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 07 | 1 |  | B5 |  |  |  | 3 | 34543.04
P3-170 | Instl Chill Plates,Tubing,Bag B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 09 | 1 |  | B6 |  |  |  | 4 | 34543.04
P3-071 | Wind coil B5 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 2 | 07 | 1 |  | B5 |  |  |  | 3 | 60641.27
P3-161 | Wind coil B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 09 | 1 |  | B6 |  |  |  | 4 | 62005.14
P3-071 | Wind coil B5 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 2 | 07 | 1 |  | B5 |  |  |  | 3 | 66703.52
P3-161 | Wind coil B6 | 37 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 09 | 1 |  | B6 |  |  |  | 4 | 68204.88
PHIL-33 | Fit&install bushings 25% stock, 25% eccentric | 38 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 6012
R56-70 | Test | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 3118.4
R56-10 | Requirements, Codes&Standards | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 6203.6
R56-20 | Preliminary Design | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 6231.71
R56-40 | Procurement | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 6414.4
R56-70 | Test | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 12828.8
R56-40 | Procurement | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 14008
R56-50 | PLC Programming | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 19243.2
R56-35 | Final Design | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 22450.4
R56-40 | Procurement | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 28640
1421-3107 | PPPL Machine bushings Bushings | 39 | I < 8 weeks | I < 8 weeks | C <2 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | BUSH | 10 | X | [6 empty] | 43915.58
R1810-5106 | Testout Sta 5 equipt & procedures | 42 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 15 |  |  | 5 |  |  |  |  | 12817.6
R1810-5108 | Fixtures installed-final metrology | 42 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 17 |  |  | 5 |  |  |  |  | 15381.12
R1810-5112 | Weld wire & welding supplies | 42 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 14 |  |  | 5 |  |  |  |  | 19620
R1810-5107 | Check 3 sled interfaces adjust holes | 42 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 16 |  |  | 5 |  |  |  |  | 30762.24
R1810-5101 | MTM NCR hardware re-purchase | 42 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 10 |  |  | 5 |  |  |  |  | 54936
R1810-2003 | Trial tensioning test on prototype with UT | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 3006
R54-110 | Test | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 22 | [7 empty] | 3118.4
R1810-2003 | Trial tensioning test on prototype with UT | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PR | 11 | [7 empty] | 3828
R54-10 | Preliminary System Design | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 10 | [7 empty] | 6203.6
R54-20 | Final SystemDesign | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 12 | [7 empty] | 6235.22
R54-110 | Test | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 22 | [7 empty] | 6414.4
R54-90 | Central Clock (EPICS) Programming | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 20 | [7 empty] | 12828.8
PLCT-B6 | Insul,measure,TC,SG other punch list-B6 | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 17 |  |  | B6 |  |  |  |  | 16502.66
R54-80 | UNT - Device Driver Prog (EPICS/MDSplus) | 43 | J < 9 weeks | J < 9 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 19 | [7 empty] | 25657.6
PLTS-B2 | Grinding -B2 | 44 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 01 |  |  | B2 |  |  |  |  | 15706.35
442-1-4 | Kirk Keys-Procure | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 4 | 44 | 442 |  | 9450 |  | 4401 | T |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 1477.2
R1810-2025 | Install SECOND Holding 20 deg fixture | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 2552
R1810-2027 | Install THIRD Holding 20 deg fixture | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 2552
R1810-2029 | Install LAST Holding 20 deg fixture | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 2552
442-1-4 | Kirk Keys-Procure | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 4 | 44 | 442 |  | 9450 |  | 4401 | T |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 3637.2
R1810-2025 | Install SECOND Holding 20 deg fixture | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 4509
R1810-2029 | Install LAST Holding 20 deg fixture | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 4509
442-1-2 | Kirk Keys-Dsn | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 4 | 44 | 442 |  | 9450 |  | 4401 | 2 |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 6062
442-1-2 | Kirk Keys-Dsn | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 4 | 44 | 442 |  | 9450 |  | 4401 | 2 |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 7386
R1810-2027 | Install THIRD Holding 20 deg fixture | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 9018
442-1-2 | Kirk Keys-Dsn | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 4 | 44 | 442 |  | 9450 |  | 4401 | 2 |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 10209.6
442-1-4 | Kirk Keys-Procure | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 4 | 44 | 442 |  | 9450 |  | 4401 | T |  |  |  | 442 |  |  |  | 44 |  |  |  |  | 14320
1421-3025 | Deliver bladders | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | BLAD | 16 | X | [6 empty] | 16396.6
1302-218 | PF Stress Analysis with leads | 45 | J < 9 weeks | J < 9 weeks | D <3 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 62 | 1 |  | 13 |  |  |  |  | 22291.2
380-135 | E-beam mapping- Assemble | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | F | B |  |  |  |  | 1 | [6 empty] | 1326.08
412-1-2 | C-site Pulsed AC Power Distr-Dsn | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 4 | 41 | 412 |  | 9450 |  | 4101 | 2 |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 1974.72
412-1-2 | C-site Pulsed AC Power Distr-Dsn | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 4 | 41 | 412 |  | 9450 |  | 4101 | 2 |  |  |  | 412 |  |  |  | 41 |  |  |  |  | 2857.28
380-135 | E-beam mapping- Assemble | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | F | B |  |  |  |  | 1 | [6 empty] | 3422.6
380-120 | E-beam mapping-Procure Ports | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | F | B |  |  |  |  | 1 | [6 empty] | 5728
380-115 | E-beam mapping-Procure Rack | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 6414.4
380-130 | E-beam mapping-Procure Data Acquisition | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 14320
380-135 | E-beam mapping- Assemble | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | F | B |  |  |  |  | 1 | [6 empty] | 28647.36
380-135 | E-beam mapping- Assemble | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | F | B |  |  |  |  | 1 | [6 empty] | 28771.2
380-135 | E-beam mapping- Assemble | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | F | B |  |  |  |  | 1 | [6 empty] | 32072
380-115 | E-beam mapping-Procure Rack | 46 | K < 10 weeks | K < 10 weeks | D <3 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 40955.2
R1810-5103 | metrology network in NCSX TC | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 12 |  |  | 5 |  |  |  |  | 9156
R1810-5103 | metrology network in NCSX TC | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 12 |  |  | 5 |  |  |  |  | 12817.6
PLTS-C1 | Grinding & Drill Holes -C1 | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 05 |  |  | C1 |  |  |  |  | 18512.16
PLTS-C2 | Grinding & Drill Holes -C2 | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 06 |  |  | C2 |  |  |  |  | 19226.4
PLTS-C3 | Grinding & Drill Holes -C3 | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 07 |  |  | C3 |  |  |  |  | 19226.4
PLTS-C4 | Grinding & Drill Holes -C4 | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 08 |  |  | C4 |  |  |  |  | 19226.4
PLCT-A3 | Insul,measure,TC, other punch list-A3 | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 09 |  |  | A3 |  |  |  |  | 19306.51
PLCT-C4 | Insul,measure,TC, other punch list-C4 | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 08 |  |  | C4 |  |  |  |  | 22110.36
R1810-5102 | Monuments,reflectors,CCR's | 47 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1815 |  |  |  | X | S4P0 | 11 |  |  | 5 |  |  |  |  | 67689
P2-051V | VPI (Station 5) C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 17 | 1 |  | C6 |  |  |  | 5 | 1281.76
1701-121 | Cryostat- PDR | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [6 empty] | M | [6 empty] | 1324
1701-141 | Cryostat- FDR | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [6 empty] | M | [6 empty] | 1324
623-181 | GN2 Cryostat Cooling Sys-WBS 62/171 FDR | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 |  | M | [6 empty] | 1324
132-002 | PDR WBS 162 Coil leads | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 16 | 162 |  | 9450 |  | 1601 | 1 | A | L |  | 162 | 01 | M |  | 16 |  |  |  |  | 1387.28
R52-70 | OPC - EPICS/PLC Interface | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 2532.22
P2-041 | Wind coil C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 09 | 1 |  | C6 |  |  |  | 4 | 2563.52
P2-051C | Final Clamps & Warm Test (Station1) C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 17 | 1 |  | C6 |  |  |  | 7 | 2563.52
R52-30 | Procurement | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 3101.8
1701-103 | Cryostat- Joint R&D | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [13 empty] | 3298.4
PLTS-A2 | Grinding -A2 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 02 |  |  | A2 |  |  |  |  | 3682.35
PLTS-B1 | Grinding -B1 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 03 |  |  | B1 |  |  |  |  | 3682.35
R52-30 | Procurement | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 5253
R52-10 | Preliminary Design | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 6203.6
R52-20 | Final Design | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 6203.6
R52-100 | Installation | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 20 | [7 empty] | 6414.4
R52-110 | Test | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 20 | [7 empty] | 6414.4
623-261 | WBS 62/171 Cryo systems PTP | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 6820.8
623-261 | WBS 62/171 Cryo systems PTP | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 6845.2
R52-100 | Installation | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 20 | [7 empty] | 7796
P2-051C | Final Clamps & Warm Test (Station1) C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 17 | 1 |  | C6 |  |  |  | 7 | 11215.4
P2-051C | Final Clamps & Warm Test (Station1) C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 17 | 1 |  | C6 |  |  |  | 7 | 12248.68
R52-40 | EPICS Programming - Base | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 12407.2
R52-80 | Appl. Programming-T/C | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 12828.8
R52-100 | Installation | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 20 | [7 empty] | 15314.4
R52-90 | Programming - misc. | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 16036
623-221 | GN2 Cryostat Cooling Sys-Assemble & Install | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 19891.2
R52-100 | Installation | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 20 | [7 empty] | 20462.4
PLCT-C3 | Insul,measure,TC, other punch list-C3 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 07 |  |  | C3 |  |  |  |  | 20748.49
P2-051V | VPI (Station 5) C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 17 | 1 |  | C6 |  |  |  | 5 | 22110.36
1701-101 | Cryostat- Preliminary Design | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [13 empty] | 23832
1701-131 | Cryostat- Final Design | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [13 empty] | 23832
P2-051V | VPI (Station 5) C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 17 | 1 |  | C6 |  |  |  | 5 | 24409.24
R52-30 | Procurement | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 25146
R52-70 | OPC - EPICS/PLC Interface | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 25470.22
P2-050 | Instl Chl Plates,Tubing, Bag C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 09 | 1 |  | C6 |  |  |  | 4 | 31403.12
P2-050 | Instl Chl Plates,Tubing, Bag C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 09 | 1 |  | C6 |  |  |  | 4 | 34543.04
1701-102 | Cryostat- Stress analysis | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [13 empty] | 38242
1701-101 | Cryostat- Preliminary Design | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [13 empty] | 49614.84
1701-131 | Cryostat- Final Design | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [13 empty] | 49614.84
P2-041 | Wind coil C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 09 | 1 |  | C6 |  |  |  | 4 | 62005.14
P2-041 | Wind coil C6 | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 09 | 1 |  | C6 |  |  |  | 4 | 68204.88
623-221 | GN2 Cryostat Cooling Sys-Assemble & Install | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 136416
623-201 | GN2 Cryostat Cooling Sys-Procure Hardware | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 144346.32
132-001 | Title I design WBS 162 Coil leads | 49 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 16 | 162 |  | 9450 |  | 1601 | 1 | A | L |  | 162 | 01 | 1 |  | 16 |  |  |  |  | 152991.5
PHIL-30 | Zenex - fabricate eccentric bushings | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 1658.8
PLCT-A5 | Insul,measure,TC, other punch list-A5 | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 14 |  |  | A5 |  |  |  |  | 16502.66
PLCT-A6 | Insul,measure,TC,SG other punch list-A6 | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 16 |  |  | A6 |  |  |  |  | 16502.66
PLCT-B3 | Insul,measure,TC, other punch list-B3 | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 10 |  |  | B3 |  |  |  |  | 16502.66
PLCT-B4 | Insul,measure,TC, other punch list-B4 | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 12 |  |  | B4 |  |  |  |  | 16502.66
PLCT-B5 | Insul,measure,TC, other punch list-B5 | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 15 |  |  | B5 |  |  |  |  | 16502.66
PLCT-A4 | Insul,measure,TC, other punch list-A4 | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 11 |  |  | A4 |  |  |  |  | 19306.51
PLCT-C5 | Insul,measure,TC, other punch list-C5 | 50 | K < 10 weeks | K < 10 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 13 |  |  | C5 |  |  |  |  | 20428.05
361-016 | fabricate and assemble Visible tv camera sys | 51 | L < 11 weeks | L < 11 weeks | D <3 month | 3 | 36 | 360 |  | 9450 |  | 3601 | F | B |  |  |  |  | 1 | [6 empty] | 1326.08
361-015 | Procure flange,window and material | 51 | L < 11 weeks | L < 11 weeks | D <3 month | 3 | 36 | 360 |  | 9450 |  | 3601 | F | B |  |  |  |  | 1 | [6 empty] | 5012
361-001 | Design Visible Camera sys | 51 | L < 11 weeks | L < 11 weeks | D <3 month | 3 | 36 | 360 |  | 9450 |  | 3601 | 2 | B |  |  |  |  | 1 | [6 empty] | 6845.2
361-016 | fabricate and assemble Visible tv camera sys | 51 | L < 11 weeks | L < 11 weeks | D <3 month | 3 | 36 | 360 |  | 9450 |  | 3601 | F | B |  |  |  |  | 1 | [6 empty] | 7502.88
361-001 | Design Visible Camera sys | 51 | L < 11 weeks | L < 11 weeks | D <3 month | 3 | 36 | 360 |  | 9450 |  | 3601 | 2 | B |  |  |  |  | 1 | [6 empty] | 10209.6
PLCT-C2 | Insul,measure,TC, other punch list-C2 | 51 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1459 |  |  |  |  | PLCT | 06 |  |  | C2 |  |  |  |  | 20428.05
R54-100 | Installation | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 21 | [7 empty] | 5104.8
R54-100 | Installation | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 21 | [7 empty] | 6236.8
R54-100 | Installation | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 21 | [7 empty] | 6414.4
R54-60 | Procurement | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 17 | [7 empty] | 6414.4
R54-60 | Procurement | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 17 | [7 empty] | 7004
R54-100 | Installation | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 21 | [7 empty] | 10231.2
PLCT-C1 | Insul,measure,TC, other punch list-C1 | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLCT | 05 |  |  | C1 |  |  |  |  | 20748.49
R54-60 | Procurement | 53 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 17 | [7 empty] | 22912
141-900 | PF4 Lower Inspection & Test | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 29 | 1 | [6 empty] | 1649.2
141-900 | PF4 Lower Inspection & Test | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 29 | 1 | [6 empty] | 1912.1
444-4-4 | Signal Conditioning & Cabling-Procure | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | T |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 2954.4
444-4-2 | Signal Conditioning & Cabling-Dsn | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | 2 |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 3013.26
444-4-8 | Signal Conditioning & Cabling-Commission | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | S |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 3315.2
1429-3062X | PPPL cut, grind and debur Inboard Shims | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMT |  | X | [6 empty] | 4371.08
444-4-6 | Signal Conditioning & Cabling-Install | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | F |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 4431.6
444-4-8 | Signal Conditioning & Cabling-Commission | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | S |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 6062
444-4-8 | Signal Conditioning & Cabling-Commission | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | S |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 8863.2
1429-3062X | PPPL cut, grind and debur Inboard Shims | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 14 | 142 |  | 9450 |  | 1431 |  |  |  |  | SHMT |  | X | [6 empty] | 14887.82
444-4-4 | Signal Conditioning & Cabling-Procure | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | T |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 17184
1352-150 | Fabricate/Dlvr PF 4 lower | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 23 | 1 |  | 13 |  |  |  | P | 21125.1
444-4-6 | Signal Conditioning & Cabling-Install | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | F |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 23206.4
1352-120 | Tooling for PF 4 | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 20 | 1 |  | 13 |  |  |  | P | 74072.29
444-4-2 | Signal Conditioning & Cabling-Dsn | 54 | L < 11 weeks | L < 11 weeks | D <3 month | 4 | 44 | 444 |  | 9450 |  | 4401 | 2 |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 87197.61
211-101 | Preliminary Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 987.36
211-101 | Preliminary Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 2752.08
211-109 | Final Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 3062.88
R53-40 | Installation | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 14 | [7 empty] | 3063.79
R53-30 | Procurement | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 13 | [7 empty] | 3101.8
R53-120 | Test | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 21 | [7 empty] | 3118.4
R53-30 | Procurement | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 13 | [7 empty] | 3502
211-101 | Preliminary Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 3517.44
211-109 | Final Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 3794.24
1302-240 | Disposition PDR Chits | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 56 | 1 |  | 13 |  |  |  |  | 4458.24
211-101 | Preliminary Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 5296
211-109 | Final Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 6062
R53-10 | Preliminary Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 10 | [7 empty] | 6203.6
R53-120 | Test | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 21 | [7 empty] | 6414.4
211-121 | Procure Material and Supplies | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 7160
211-109 | Final Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 2 | 21 | 211 |  | 9450 |  | 2101 | [13 empty] | 8214.24
R53-20 | Final Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 12 | [7 empty] | 12407.2
R53-50 | MDSplus Installation | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 15 | [7 empty] | 12828.8
R53-60 | MDSplus Programming - Tree Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 16 | [7 empty] | 12828.8
R53-70 | MDSplus Programming - Shot Sync | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 17 | [7 empty] | 12828.8
R53-90 | MDSplus Programming - Acquisition | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 20 | [7 empty] | 12828.8
1701-100 | Cryostat- Conceptual Design | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 1 | 17 | 171 |  | 9450 |  | 1701 | [13 empty] | 15888
R53-30 | Procurement | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 13 | [7 empty] | 23749
R53-110 | Programming - Misc. | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 18 | [7 empty] | 25657.6
R53-80 | MDSplus Programming - Dispatcher | 55 | L < 11 weeks | L < 11 weeks | D <3 month | 5 | 53 | 530 |  | 9450 |  | 5301 | [5 empty] | 19 | [7 empty] | 25657.6
S31-1.02 | Install floor mounted tracks and VV base support | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 12 |  | C | [5 empty] | 1308
P1-161 | Wind coil A6 | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 08 | 1 |  | A6 |  |  |  | 3 | 2563.52
S31-1.01 | Install Station 3 site monuments | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 11 |  | C | [5 empty] | 2616
S31-1.03 | Establish the MCHP CG location. | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 15 |  | C | [5 empty] | 3204.4
S31-2.02 | Verify cart motion. | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 17 |  | C | [5 empty] | 3204.4
S31-1.01 | Install Station 3 site monuments | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 11 |  | C | [5 empty] | 4806.6
S31-2.01 | Install MCHP support cart assemblies | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 16 |  | C | [5 empty] | 6408.8
S31-1.02 | Install floor mounted tracks and VV base support | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  |  | S3P1 | 12 |  | C | [5 empty] | 8011
P1-151 | Receive A6, Prep& Instl Cladding | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 03 | 1 |  | A6 |  |  |  | 1 | 9751.41
P1-151 | Receive A6, Prep& Instl Cladding | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 03 | 1 |  | A6 |  |  |  | 1 | 19188.25
P1-151 | Receive A6, Prep& Instl Cladding | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 1.5 | 9450 |  | 1451 | F | A |  |  | 1A | 03 | 1 |  | A6 |  |  |  | 1 | 21193.04
P1-170 | Instl Chill Plates,Tubing,Bag A6 | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 08 | 1 |  | A6 |  |  |  | 3 | 31403.12
P1-170 | Instl Chill Plates,Tubing,Bag A6 | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 08 | 1 |  | A6 |  |  |  | 3 | 34543.04
P1-161 | Wind coil A6 | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 08 | 1 |  | A6 |  |  |  | 3 | 62005.14
P1-161 | Wind coil A6 | 56 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 08 | 1 |  | A6 |  |  |  | 3 | 68204.88
1355-112 | Installation on TF Coils upon delivery | 57 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 5545.09
1355-112 | Installation on TF Coils upon delivery | 57 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 23501.1
141-039 | Bid & Award Materials | 58 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  |  | 13P | 15 | 1 | [5 empty] | P | 8916.48
1352-100 | Materials Delivery PF 4,5,6 | 58 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 17 | 1 |  | 13 |  |  |  | P | 178529.66
R56-60 | Installation | 59 | M < 12 weeks | M < 12 weeks | D <3 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 6236.8
INTRF-035 | PPPL Determine shim material | 59 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 18 | 185 |  | 9450 | HW | 1810 | 2 |  | L |  | S2PR | 10 | X |  |  | PHL1 |  |  |  | 6969.2
R56-60 | Installation | 59 | M < 12 weeks | M < 12 weeks | D <3 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 9621.6
1421-3106 | Deliver Bushings Material | 59 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | BUSH | 10 | X | [6 empty] | 10271.8
R56-60 | Installation | 59 | M < 12 weeks | M < 12 weeks | D <3 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 30628.8
R56-60 | Installation | 59 | M < 12 weeks | M < 12 weeks | D <3 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 40924.8
141-901 | PF5 Lower Inspection & Test | 60 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 30 | 1 | [6 empty] | 1649.2
141-901 | PF5 Lower Inspection & Test | 60 | M < 12 weeks | M < 12 weeks | D <3 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 30 | 1 | [6 empty] | 1912.1
PLTS-A3 | Grinding -A3 | 61 | N < 13 weeks | N < 13 weeks | D <3 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 09 |  |  | A3 |  |  |  |  | 3925.39
1416-204.1 | Modify Type-B clamps for stud attachment | 62 | N < 13 weeks | N < 13 weeks | D <3 month | 1 | 14 | 142 |  | 9450 | MC | 1416 | F |  | L |  | MCDB |  | X | [6 empty] | 7786
R55-110 | GISRTC - Installation | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 21 | [7 empty] | 1559.2
R55-90 | GISRTC - Procurement | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 20 | [7 empty] | 1751
R55-110 | GISRTC - Installation | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 21 | [7 empty] | 3062.88
R55-80 | GISRTC -Final Design | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 20 | [7 empty] | 3147.47
R55-110 | GISRTC - Installation | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 21 | [7 empty] | 3207.2
R55-120 | GISRTC -Test | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 21 | [7 empty] | 3207.2
R55-90 | GISRTC - Procurement | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 20 | [7 empty] | 3207.2
R55-70 | GISRTC - Preliminary Design | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 20 | [7 empty] | 6203.6
R55-90 | GISRTC - Procurement | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 20 | [7 empty] | 8592
R55-100 | GISRTC LabVIEW Programming | 63 | N < 13 weeks | N < 13 weeks | D <3 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 21 | [7 empty] | 19243.2
P2-161 | Wind coil B4 | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 06 | 1 |  | B4 |  |  |  | 2 | 2404.8
IH1-0000 | PEER REVIEW OF JOINT CONCEPT | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 | 2 |  | L |  | 142G | 10 | X | [6 empty] | 12457.6
1421-3143 | Add bolt holes to C winding form dwg CC interfac | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142G | 16 | X | [6 empty] | 21800.8
P2-170 | Instl Chill Plates,Tubing,Bag B4 | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 2 | 06 | 1 |  | B4 |  |  |  | 2 | 29458.8
P2-170 | Instl Chill Plates,Tubing,Bag B4 | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 2 | 06 | 1 |  | B4 |  |  |  | 2 | 32402.72
P2-161 | Wind coil B4 | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 06 | 1 |  | B4 |  |  |  | 2 | 58166.1
P2-161 | Wind coil B4 | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 2 | 06 | 1 |  | B4 |  |  |  | 2 | 63978.84
IH1-000 | ESTABLISH CONCEPT | 64 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 | 2 |  | L |  | 142G | 10 | X | [6 empty] | 105889.6
1702-515 | Conduct PDR | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 11 | M |  |  |  |  | 3 |  | 743.04
1702-525 | Base Support Structure FDR | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 13 | M | [6 empty] | 743.04
1702-530 | Resolve chits, issue dwgs for fab,Issue requisit | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 14 | [7 empty] | 5944.32
1416-604 | Finalize draft documents - materials, eddy curre | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | X | [6 empty] | 6470.4
1702-530 | Resolve chits, issue dwgs for fab,Issue requisit | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 14 | [7 empty] | 6687.36
1416-603 | Update, review and approve FMECA | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | X | [6 empty] | 9705.6
1416-605 | Prepare Type-ABC closeout FDR | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | M |  |  |  |  | 3 |  | 11646.72
1416-606 | Resolve FDR comments | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | X | [6 empty] | 11646.72
1416-601 | Prepare EM and structural analysis of leads | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | X |  |  |  |  | 3 |  | 12940.8
1416-602 | Design memo KF structural analysis | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | X | [6 empty] | 15528.96
1702-510 | Base support structure prel. design & analysis | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 10 | [7 empty] | 33065.28
1702-520 | Final design. Assy dwgs, fab dwgs, BOMs,specs/SO | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 12 | [7 empty] | 33065.28
1416-601 | Prepare EM and structural analysis of leads | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | X |  |  |  |  | 3 |  | 35665.92
1702-510 | Base support structure prel. design & analysis | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 10 | [7 empty] | 41610.24
1702-520 | Final design. Assy dwgs, fab dwgs, BOMs,specs/SO | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 17 | 171 |  | 9450 |  | 1702 | 1 |  |  |  |  | 12 | [7 empty] | 41610.24
1416-601 | Prepare EM and structural analysis of leads | 65 | N < 13 weeks | N < 13 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDF |  | X |  |  |  |  | 3 |  | 61500
445-1-2 | Ground Fault Protection-Dsn | 66 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | 2 |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 2344.96
445-1-2 | Ground Fault Protection-Dsn | 66 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | 2 |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 4936.8
445-1-2 | Ground Fault Protection-Dsn | 66 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | 2 |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 28572.8
1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 66 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  | S |  | STUD | 12 | X | [6 empty] | 98992.08
1302-210 | Update PF Coil SDD | 67 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 50 | 1 |  | 13 |  |  |  |  | 4458.24
1302-205 | Update PF Analysis | 67 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 50 | 1 |  | 13 |  |  |  |  | 28706.96
P2-131 | Wind coil A5 | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 3 | 07 | 1 |  | A5 |  |  |  | 2 | 2404.8
P1-061 | Receive A5, Prep& Instl Cladding | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 2* | 9450 |  | 1451 | F | A |  |  | 1A | 01 | 1 |  | A5 |  |  |  | 1 | 9318.6
P1-061 | Receive A5, Prep& Instl Cladding | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 2* | 9450 |  | 1451 | F | A |  |  | 1A | 01 | 1 |  | A5 |  |  |  | 1 | 18411.75
P1-061 | Receive A5, Prep& Instl Cladding | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 2* | 9450 |  | 1451 | F | A |  |  | 1A | 01 | 1 |  | A5 |  |  |  | 1 | 20251.7
P2-140 | Instl Chl Plates,Tubing, Bag A5 | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 3 | 07 | 1 |  | A5 |  |  |  | 2 | 29768.12
P2-140 | Instl Chl Plates,Tubing, Bag A5 | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 3 | 07 | 1 |  | A5 |  |  |  | 2 | 32743.23
P2-131 | Wind coil A5 | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 3 | 07 | 1 |  | A5 |  |  |  | 2 | 58166.1
P2-131 | Wind coil A5 | 68 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 3 | 07 | 1 |  | A5 |  |  |  | 2 | 63978.84
1803-6.2 | Complete platform models | 69 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 6.00 | 10 | [7 empty] | 9592.8
1803-6.5 | Complete drawing package | 69 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 6.00 | 10 | [7 empty] | 19185.6
162-057 | Deliver Belleville Washers | 69 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 15 | 151 |  | 9450 |  | 1550 | T | A | A | B |  | 15 | 1 |  | 15 |  |  |  | P | 25106.83
1803-6.1 | Complete Stage 6 support models | 69 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 6.00 | 10 | [7 empty] | 28778.4
162-053 | Deliver Inconnel hardware | 69 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 15 | 151 |  | 9450 |  | 1550 | T | A | A | B |  | 15 | 1 |  | 15 |  |  |  | P | 107848.23
162-051 | Deliver G11/Teflon parts | 69 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 15 | 151 |  | 9450 |  | 1550 | T | A |  | B |  | 15 | 1 |  | 15 |  |  |  | P | 155701.41
R1810-2023 | Install FIRST Holding 20 deg fixture | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 2552
7501-10.7 | Fab 3 concrete blocks for testing assy struct | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 3310
411-2-8 | Grounding-Commission | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | S |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 4431.6
411-2-8 | Grounding-Commission | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | S |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 5104.8
411-2-6 | Grounding-Install | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | F |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 5170.2
R1810-2023 | Install FIRST Holding 20 deg fixture | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  |  | S2PX | 11 | [7 empty] | 6012
411-2-8 | Grounding-Commission | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | S |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 6630.4
411-2-6 | Grounding-Install | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | F |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 7146.72
411-2-6 | Grounding-Install | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | F |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 9282.56
411-2-4 | Grounding-Procure | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | T |  | C |  | 411 |  |  |  | 41 |  |  |  |  | 14218.6
7501-10.7 | Fab 3 concrete blocks for testing assy struct | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 15832.32
411-2-6 | Grounding-Install | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 4 | 41 | 411 |  | 9450 |  | 4101 | F |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 25060
7501-10.7 | Fab 3 concrete blocks for testing assy struct | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 25146
7501-10.6 | Fab 3 laser support poles | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 33528
7501-10.6 | Fab 3 laser support poles | 70 | o < 4 months | o < 14 weeks' | E < 4 month | 7 | 75 | 750 | 1 | 9450 | EC45 | 7503 | F | A |  | X |  | 02 | X | C | 6 |  |  |  |  | 39580.8
R55-60 | FCPC -Test | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 1559.2
R55-30 | FCPC - Procurement | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 1751
R55-50 | FCPC - Installation | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 3118.4
R55-30 | FCPC - Procurement | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 3207.2
PHIL-21 | Prepare angle plate dogs & chocks | 71 | o < 4 months | P < 15 weeks | E < 4 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 4809.6
R55-10 | FCPC - Preliminary Design | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 6203.6
R55-50 | FCPC - Installation | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 6414.4
R55-60 | FCPC -Test | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 6414.4
R55-30 | FCPC - Procurement | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 8592
R55-20 | FCPC -Final Design | 71 | o < 4 months | P < 15 weeks | E < 4 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 12744.48
PLTS-B3 | Grinding -B3 | 73 | o < 4 months | P < 15 weeks | E < 4 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 10 |  |  | B3 |  |  |  |  | 3925.39
441-130 | Pre-commissioning tests | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 1432
441-110 | PLC CWD's & Cabling | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 2857.28
441-100 | PLC Specification | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 4285.92
441-105 | Prep Block diagrams | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 4285.92
441-125 | Program Control pages | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 5908.8
441-125 | Program Control pages | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 6414.4
441-130 | Pre-commissioning tests | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 7386
441-135 | Install I/O Cabling control & protection | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 7386
441-100 | PLC Specification | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 8207.36
441-105 | Prep Block diagrams | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 11724.8
441-120 | Program PLC Logic | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 11817.6
441-135 | Install I/O Cabling control & protection | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 12124
441-125 | Program Control pages | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 18186
441-130 | Pre-commissioning tests | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 18186
441-135 | Install I/O Cabling control & protection | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 20419.2
441-110 | PLC CWD's & Cabling | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 25648
441-135 | Install I/O Cabling control & protection | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 33152
441-110 | PLC CWD's & Cabling | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 35174.4
441-120 | Program PLC Logic | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 36372
441-135 | Install I/O Cabling control & protection | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 54416
441-115 | deliver PLC | 75 | o < 4 months | P < 15 weeks | E < 4 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 98920.77
123-050 | Fabricate& Deliver Insul Boots | 76 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 12 | 123 |  | 9450 |  | 1204 | T | A |  |  | 122 | 24 |  |  | 12 |  |  |  | P | 72997.33
P2-080 | Instl Chill Plates,Tubing,Bag B3 | 77 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 06 | 1 |  | B3 |  |  |  | 4 | 29458.8
P2-080 | Instl Chill Plates,Tubing,Bag B3 | 77 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 3 | 06 | 1 |  | B3 |  |  |  | 4 | 32402.72
1421-3062 | Re-order balance of stud kits | 78 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | STUD | 12 | X | [6 empty] | 408475.32
1416-3198 | Report Results & Issue Dwgs | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | MC | 1416 |  |  | L |  | MCDC | 16 | X | [6 empty] | 1393.84
1416-305 | Review and approve insulation concept | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | MC | 1416 | F |  | L |  | MCDC | 13 | X | [6 empty] | 1742.3
1416-305 | Review and approve insulation concept | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | MC | 1416 | F |  | L |  | MCDC | 13 | X | [6 empty] | 4671.6
1416-3198 | Report Results & Issue Dwgs | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | MC | 1416 |  |  | L |  | MCDC | 16 | X | [6 empty] | 6228.8
1416-304 | Revise assembly models/drawings | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 | MC | 1416 | F |  | L |  | MCDC | 12 | X | [6 empty] | 9343.2
1416-506 | Check and promote top-level models/drawings | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDE | 90 | X |  |  |  |  | 3 |  | 12687.12
1416-503 | Complete models/drawings of power cable connect | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDE | 10 | X | [6 empty] | 19030.68
1416-504 | Complete models/drawings of protective covers | 79 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDE | 10 | X | [6 empty] | 19030.68
163.001 | Design Coil protection(input to WBS 4 & 5) | 80 | o < 4 months | Q < 16 weeks | E < 4 month | 1 | 16 | 163 |  | 9450 |  | 1601 | 1 | A | L |  | 163 |  | 1 | [6 empty] | 38150.2
445-1-6 | Ground Fault Protection-Install | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | F |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 1020.96
445-1-8 | Ground Fault Protection-Commission | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 2652.16
445-1-4 | Ground Fault Protection-Procure | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | T |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 2908.08
445-1-8 | Ground Fault Protection-Commission | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 3637.2
445-1-8 | Ground Fault Protection-Commission | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 4431.6
445-1-6 | Ground Fault Protection-Install | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | F |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 7274.4
445-1-6 | Ground Fault Protection-Install | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | F |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 7386
445-1-6 | Ground Fault Protection-Install | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | F |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 9945.6
445-1-4 | Ground Fault Protection-Procure | 81 | o < 4 months | R < 17 weeks | E < 4 month | 4 | 44 | 445 |  | 9450 |  | 4401 | T |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 25475.54
124-130 | VV NB port cover Fabrication | 81 | o < 4 months | R < 17 weeks | E < 4 month | 1 | 12 | 124 |  | 9450 |  | 1204 | T | A | S |  | 124P | 22 |  |  | 12 |  |  |  | P | 83786.32
1803-305 | Station 3 Assembly Drawings | 84 | o < 4 months | R < 17 weeks | E < 4 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 3.00 |  | 10 | [5 empty] | P | 13287.36
PLTS-A4 | Grinding -A4 | 85 | o < 4 months | R < 17 weeks | F <5 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 11 |  |  | A4 |  |  |  |  | 3925.39
141-037 | Bid & Award Conductor | 85 | o < 4 months | R < 17 weeks | F <5 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  |  | 13P | 12 | 1 | [5 empty] | P | 8916.48
141-038.1 | PF Conductor Delivery | 85 | o < 4 months | R < 17 weeks | F <5 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A | C | 2 | 13P | 14 | 1 |  | 13 |  |  |  | P | 149635.2
1355-105 | FDR | 86 | o < 4 months | S < 18 weeks | F <5 month | 1 | 13 | 134 |  | 9450 |  | 1355 | F | A |  |  | 134 |  | M | [6 empty] | 1486.08
1355-107 | Prep req,bid,award T/C and wire | 86 | o < 4 months | S < 18 weeks | F <5 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 2229.12
1355-103 | Prepare Installation Procedures | 86 | o < 4 months | S < 18 weeks | F <5 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 3715.2
1355-101 | Design, and Review | 86 | o < 4 months | S < 18 weeks | F <5 month | 1 | 13 | 134 |  | 9450 |  | 1355 | F | A |  |  | 134 |  | 1 | [6 empty] | 11145.6
1355-109 | Deliver of T/C and wire | 86 | o < 4 months | S < 18 weeks | F <5 month | 1 | 13 | 134 |  | 9450 |  | 1355 | F | A |  |  | 134 |  | 1 | [6 empty] | 13080
411-2-2 | Grounding-Dsn | 87 | o < 4 months | S < 18 weeks | F <5 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 12857.76
411-2-2 | Grounding-Dsn | 87 | o < 4 months | S < 18 weeks | F <5 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 19747.2
1803-301 | Station 3 Assembly Specification | 88 | P < 5 months | S < 18 weeks | F <5 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 3.00 |  | 10 | [5 empty] | P | 38218.4
PLTS-B4 | Grinding -B4 | 91 | P < 5 months | T < 19 weeks | F <5 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 12 |  |  | B4 |  |  |  |  | 3925.39
PLTS-C5 | Grinding & Drill Holes -C5 | 91 | P < 5 months | T < 19 weeks | F <5 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 13 |  |  | C5 |  |  |  |  | 19226.4
6401-002 | Bakeout Sys-PDR | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | M | [6 empty] | 1529.68
R51-50 | Installation | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 1559.2
R51-60 | Test | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 1559.2
6401-009 | Bakeout Sys-FDR | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | M | [6 empty] | 1581.68
R51-30 | Procurement | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 3207.2
R51-60 | Test | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 3207.2
6401-017 | Bakeout Sys- ACC Review | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 3410.4
R51-10 | Preliminary Design | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 4652.7
R51-20 | Final Design | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 4721.21
R55-45 | FCPC PLC Integration-EPICS Prog. | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 6414.4
R51-30 | Procurement | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 7004
6401-017 | Bakeout Sys- ACC Review | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 7908.4
6401-020 | Bakeout Sys-PTP Testing | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 7908.4
R51-50 | Installation | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 9621.6
6401-020 | Bakeout Sys-PTP Testing | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 10231.2
6401-001 | Bakeout Sys-Preliminary Design | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 14810.4
6401-005 | Bakeout Sys-Final Design | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 15138
6401-000 | Bakeout Sys- Requirements Definition | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 15296.8
R55-40 | FCPC LabVIEW Programming | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 55 | 550 |  | 9450 |  | 5501 | [5 empty] | 10 | [7 empty] | 19243.2
6401-001 | Bakeout Sys-Preliminary Design | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 29063.92
6401-005 | Bakeout Sys-Final Design | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 29706.12
6401-004 | Bakeout Sys- EA Analysis | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 30593.6
R51-50 | Installation | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 30628.8
R51-50 | Installation | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 41777.4
R51-30 | Procurement | 93 | P < 5 months | T < 19 weeks | F <5 month | 5 | 51 | 510 |  | 9450 |  | 5101 | [13 empty] | 42673.6
6401-013 | Assemble & Install | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 169667.4
6401-010 | Bakeout Sys-Procure Piping & Equipt | 93 | P < 5 months | T < 19 weeks | F <5 month | 6 | 64 | 640 |  | 9450 |  | 6401 | 2 | B |  |  |  |  | 1 | [6 empty] | 236552.08
1803-505 | Station 5 Assembly Drawings | 97 | P < 5 months | U < 20 weeks | F <5 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 5.00 |  | 10 | [5 empty] | P | 20068.8
1803-611 | Detail dwgs-welding ports | 97 | P < 5 months | U < 20 weeks | F <5 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 5.00 |  | 10 | [5 empty] | P | 20068.8
1803-501 | Station 5 Assembly Specification | 97 | P < 5 months | U < 20 weeks | F <5 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 5.00 |  | 10 | [5 empty] | P | 32352
1803-509 | Field period Assy Dwgs | 97 | P < 5 months | U < 20 weeks | F <5 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 5.00 |  | 10 | [5 empty] | P | 40137.6
191-002 | PDR WBS 161 LN2 manifolds&piping | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 16 | 161 |  | 9450 |  | 1601 | 1 | A | L |  | 161 | 11 | M |  | 16 |  |  | 3 |  | 1294.08
191-012 | FDR WBS 161 LN2 manifolds&piping | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 16 | 161 |  | 9450 |  | 1601 | 2 | A | L |  | 161 | 13 | M |  | 16 |  |  |  |  | 1294.08
623-141 | GN2 Cryostat Cooling Sys-WBS 62/171 PDR | 99 | P < 5 months | U < 20 weeks | F <5 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 |  | M | [6 empty] | 1324
623-161 | GN2 Cryostat Cooling Sys-Final Design | 99 | P < 5 months | U < 20 weeks | F <5 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 3702.6
431-275 | Power cabling & Installation | 99 | P < 5 months | U < 20 weeks | F <5 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 7386
1408-1 | Procure Batt insulation | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 10208
623-161 | GN2 Cryostat Cooling Sys-Final Design | 99 | P < 5 months | U < 20 weeks | F <5 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 13240
191-038 | Fab and deliver-manifold assy,hoses,valves etc | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 16 | 161 |  | 9450 |  | 1601 | 2 | A | L |  | 161 | 15 | 1 | [6 empty] | 20131.21
623-121 | GN2 Cryostat Cooling Sys-Analysis | 99 | P < 5 months | U < 20 weeks | F <5 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 30593.6
431-275 | Power cabling & Installation | 99 | P < 5 months | U < 20 weeks | F <5 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 30628.8
431-275 | Power cabling & Installation | 99 | P < 5 months | U < 20 weeks | F <5 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 36372
191-038 | Fab and deliver-manifold assy,hoses,valves etc | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 16 | 161 |  | 9450 |  | 1601 | 2 | A | L |  | 161 | 15 | 1 | [6 empty] | 40120.69
431-275 | Power cabling & Installation | 99 | P < 5 months | U < 20 weeks | F <5 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 43097.6
191-038 | Fab and deliver-manifold assy,hoses,valves etc | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 16 | 161 |  | 9450 |  | 1601 | 2 | A | L |  | 161 | 15 | 1 | [6 empty] | 79849.61
191-001 | Title I design WBS 161 LN2 manifolds&piping | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 16 | 161 |  | 9450 |  | 1601 | 1 | A | L |  | 161 | 10 | 1 |  | 16 |  |  |  |  | 84115.2
191-011 | Title II design WBS 161 LN2 manifolds&piping | 99 | P < 5 months | U < 20 weeks | F <5 month | 1 | 16 | 161 |  | 9450 |  | 1601 | 2 | A | L |  | 161 | 12 | 1 |  | 16 |  |  |  |  | 84115.2
431-275 | Power cabling & Installation | 99 | P < 5 months | U < 20 weeks | F <5 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 200480
444-2-4 | DC Potential Transducers (DCPTs)-Procure | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | T |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 2041.92
444-2-6 | DC Potential Transducers (DCPTs)-Install | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | F |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 2041.92
444-2-6 | DC Potential Transducers (DCPTs)-Install | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | F |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 2954.4
444-2-6 | DC Potential Transducers (DCPTs)-Install | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | F |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 3637.2
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | S |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 3637.2
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | 2 |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 4431.6
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | S |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 4431.6
444-2-8 | DC Potential Transducers (DCPTs)-Commission | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | S |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 4972.8
444-2-2 | DC Potential Transducers (DCPTs)-Dsn | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | 2 |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 5104.8
444-2-4 | DC Potential Transducers (DCPTs)-Procure | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | T |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 8592
444-2-6 | DC Potential Transducers (DCPTs)-Install | 100 | P < 5 months | U < 20 weeks | F <5 month | 4 | 44 | 444 |  | 9450 |  | 4401 | F |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 13260.8
1355-113 | Installation on PF1a Coils upon delivery | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 197.71
1355-113 | Installation on PF1a Coils upon delivery | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 134 |  | 9450 |  | 1355 | T | A |  |  | 134 |  | 1 | [6 empty] | 1364.16
163-037 | CS Support Structure Procurement/Fab | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 | EC45 | 1353 | T | A |  |  | 132A | 23 | 1 |  | 13 |  |  |  | P | 2536.46
141-903 | Refurbish PF 1a | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 34 | 1 | [6 empty] | 6820.8
141-904 | Assemble PF1a and CS structure | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 35 | 1 | [6 empty] | 7908.4
1353-001 | Design PF1a upper to lower interconnect bus | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 |  | 1353 | T | A |  |  | 132A | 10 | 1 | [5 empty] | P | 12342
141-904 | Assemble PF1a and CS structure | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 35 | 1 | [6 empty] | 13641.6
1353-002 | Engr & analysis of bus | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 |  | 1353 | T | A |  |  | 132A | 10 | 1 | [5 empty] | P | 15296.8
1353-005 | Fab & Deliver PF1a bus | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 | EC45 | 1353 | T | A |  |  | 132A | 13 | 1 |  | 13 |  |  |  | P | 48162.54
1421-3065 | Deliver Superbolts (PE007332) | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | STUD | 12 | X | [6 empty] | 157905
163-037 | CS Support Structure Procurement/Fab | 101 | P < 5 months | V < 21 weeks | F <5 month | 1 | 13 | 132 |  | 9450 | EC45 | 1353 | T | A |  |  | 132A | 23 | 1 |  | 13 |  |  |  | P | 245320.78
445-2-135 | Overload Protect-Documentation | 102 | P < 5 months | V < 21 weeks | F <5 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 2942.53
445-2-135 | Overload Protect-Documentation | 102 | P < 5 months | V < 21 weeks | F <5 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 8134.83
445-2-105 | Overload Protect-Write spec and approve | 102 | P < 5 months | V < 21 weeks | F <5 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 14286.4
R54-50 | Test - Clock Dist. | 103 | P < 5 months | V < 21 weeks | F <5 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 16 | [7 empty] | 3207.2
R54-50 | Test - Clock Dist. | 103 | P < 5 months | V < 21 weeks | F <5 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 16 | [7 empty] | 9945.6
R54-50 | Test - Clock Dist. | 103 | P < 5 months | V < 21 weeks | F <5 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 16 | [7 empty] | 18465
PLTS-A5 | Grinding -A5 | 104 | P < 5 months | V < 21 weeks | F <5 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 14 |  |  | A5 |  |  |  |  | 3925.39
1302-275 | Resolve Chits | 110 | Q < 6 months | W < 22 weeks | G <6 month | 1 | 13 | 132 |  | 9450 | EC45 | 1302 | 2 | A |  |  |  | 65 | 1 |  | 13 |  |  |  |  | 14860.8
1803-3.3 | Analyze single point lift | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 23 | [7 empty] | 2787.68
1803-3.6 | Revise drawings per FDR input and release for Fa | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 32 | [7 empty] | 5398.08
1803-3.3 | Analyze single point lift | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 23 | [7 empty] | 6969.2
R1810-3103 | Install station 3 platforms (8 required) | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 17 |  |  | 3 |  |  |  |  | 8972.32
R1810-3103 | Install station 3 platforms (8 required) | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 17 |  |  | 3 |  |  |  |  | 13080
R1810-3107 | Test out station 3 equipment and procedures | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 17 |  |  | 3 |  |  |  |  | 13080
METDCP-3 | Dimensional control plans for station 3 | 111 | Q < 6 months | X < 23 weeks | G <6 month | 8 | 82 | 820 |  | 9450 |  | 8205 | F | A |  |  |  | 11 | [5 empty] | 3 |  | 28553.23
R1810-3109 | Begin assy of first field period assy | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 17 |  |  | 3 |  |  |  |  | 52320
METDCP-5 | Dimensional control plans for station 5 | 111 | Q < 6 months | X < 23 weeks | G <6 month | 8 | 82 | 820 |  | 9450 |  | 8205 | F | A |  |  |  | 12 | [5 empty] | 3 |  | 59443.2
1803-3.11 | Procure materials and fixture | 111 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 44 | [7 empty] | 60445.47
METDCP-6 | Dimensional control plans for station 6 | 111 | Q < 6 months | X < 23 weeks | G <6 month | 8 | 82 | 820 |  | 9450 |  | 8205 | F | A |  |  |  | 13 | [5 empty] | 3 |  | 89164.8
445-2-110 | Overload Protect-Design | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 4009.92
445-2-110 | Overload Protect-Design | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 4761.78
445-2-140 | Overload Protection&cabling design,procure instl | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 6819.75
445-2-140 | Overload Protection&cabling design,procure instl | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 7956.48
445-2-140 | Overload Protection&cabling design,procure instl | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 10209.6
1803-3.5 | Flange bolt/VV support access platform | 112 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 29 | [7 empty] | 13495.2
445-2-110 | Overload Protect-Design | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 17405.9
445-2-140 | Overload Protection&cabling design,procure instl | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 17726.4
445-2-140 | Overload Protection&cabling design,procure instl | 112 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 18616
1803-6.9 | Design followup and prelim analysis | 112 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 6.00 | 10 | [7 empty] | 22291.2
PLTS-B5 | Grinding -B5 | 113 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 15 |  |  | B5 |  |  |  |  | 3925.39
411-1-100 | Ex-Test cell AC pwr-Reactiv.&new instl | 114 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 619
411-1-100 | Ex-Test cell AC pwr-Reactiv.&new instl | 114 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 1433.03
411-1-100 | Ex-Test cell AC pwr-Reactiv.&new instl | 114 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 1688.34
411-1-100 | Ex-Test cell AC pwr-Reactiv.&new instl | 114 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 1911.15
380-010 | E-beam mapping- Prelim Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 3726
380-010 | E-beam mapping- Prelim Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 4936.8
380-100 | E-beam mapping-Final Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 4936.8
411-1-100 | Ex-Test cell AC pwr-Reactiv.&new instl | 114 | Q < 6 months | X < 23 weeks | G <6 month | 4 | 41 | 411 |  | 9450 |  | 4101 | 2 |  |  |  | 411 |  |  |  | 41 |  |  |  |  | 7000.83
380-010 | E-beam mapping- Prelim Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 8275
380-100 | E-beam mapping-Final Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 8275
380-100 | E-beam mapping-Final Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 15509
380-010 | E-beam mapping- Prelim Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 27824
380-100 | E-beam mapping-Final Design | 114 | Q < 6 months | X < 23 weeks | G <6 month | 3 | 38 | 380 |  | 9450 |  | 3801 | 2 | B |  |  |  |  | 1 | [6 empty] | 27824
122-051 | Deliver Port Thermal Insulation | 115 | Q < 6 months | X < 23 weeks | G <6 month | 1 | 12 | 122 |  | 9450 |  | 1204 | T | A |  |  | 122 | 34 |  |  | 12 |  |  |  | P | 32700
R1810-1113 | Prepare &transfer completed VV to holding area | 116 | Q < 6 months | Y < 24 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 19 | M |  | 1 |  |  |  |  | 3204.4
1204-147 | Field/Fab support (title III) T/C&Heater Tape | 116 | Q < 6 months | Y < 24 weeks | G <6 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124U | 15 | [7 empty] | 4012.08
1204-146 | Procurement support T/C and Heater Tape Leads | 116 | Q < 6 months | Y < 24 weeks | G <6 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124U | 14 | [7 empty] | 6032.8
R1810-1110 | Install Final Internal&Ext monuments & meas | 116 | Q < 6 months | Y < 24 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 16 |  |  | 1 |  |  |  |  | 6408.8
R1810-1111 | Final Scan | 116 | Q < 6 months | Y < 24 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 17 |  |  | 1 |  |  |  |  | 6408.8
R1810-1114 | Install heater tape on all removable ports | 116 | Q < 6 months | Y < 24 weeks | G <6 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 18 |  |  | 1 |  |  |  |  | 16022
1204-140 | Design T/C and Heater Tape Leads | 116 | Q < 6 months | Y < 24 weeks | G <6 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124U | 10 | [7 empty] | 20511.52
1803-6.3 | Structural Analysis | 119 | Q < 6 months | Y < 24 weeks | G <6 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 6.00 | 10 | [7 empty] | 22291.2
P2-081C | Final Clamps & Warm Test (Station1) B3 | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 12 | 1 |  | B3 |  |  |  | 1 | 2404.8
P3-141C | Final Clamps & Warm Test (Station1) A4 | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 11 | 1 |  | A4 |  |  |  | 1 | 2404.8
1303-041 | Fabricate Supports | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 16 | 1 |  | 13 |  |  |  |  | 3059.36
1303-041 | Fabricate Supports | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 16 | 1 |  | 13 |  |  |  |  | 3298.4
1303-040 | Procure materials for supports | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 15 | 1 |  | 13 |  |  |  |  | 4589.04
1303-040 | Procure materials for supports | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 13 | 133 |  | 9450 |  | 1354 | 2 | B |  |  | 133 | 15 | 1 |  | 13 |  |  |  |  | 6985
P2-081C | Final Clamps & Warm Test (Station1) B3 | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 12 | 1 |  | B3 |  |  |  | 1 | 10521
P3-141C | Final Clamps & Warm Test (Station1) A4 | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 11 | 1 |  | A4 |  |  |  | 1 | 10521
P2-081C | Final Clamps & Warm Test (Station1) B3 | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 12 | 1 |  | B3 |  |  |  | 1 | 11489.74
P3-141C | Final Clamps & Warm Test (Station1) A4 | 121 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 11 | 1 |  | A4 |  |  |  | 1 | 11489.74
PLTS-A6 | Grinding -A6 | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 | 1 | 9450 |  | 1459 |  |  |  |  | PLTS | 16 |  |  | A6 |  |  |  |  | 3925.39
623-101 | GN2 Cryostat Cooling Sys-Preliminary Design | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 4936.8
623-100 | GN2 Cryostat Cooling Sys Development | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 13193.6
623-101 | GN2 Cryostat Cooling Sys-Preliminary Design | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 13240
623-100 | GN2 Cryostat Cooling Sys Development | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 19747.2
1751-161 | Cryostat- Fabricate Components | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 17 | 171 |  | 9450 |  | 1751 | [13 empty] | 20462.4
623-100 | GN2 Cryostat Cooling Sys Development | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 26480
623-100 | GN2 Cryostat Cooling Sys Development | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 623 |  | 9450 |  | 6201 |  |  |  |  | 623 | [8 empty] | 28572.8
1751-161 | Cryostat- Fabricate Components | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 17 | 171 |  | 9450 |  | 1751 | [13 empty] | 68208
1751-151 | Cryostat- Procure Materials and Supplies | 122 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 17 | 171 |  | 9450 |  | 1751 | [13 empty] | 174575.12
621-141 | LN2 - LHe Supply-Fabricate & Assembly | 124 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [8 empty] | 6630.4
621-141 | LN2 - LHe Supply-Fabricate & Assembly | 124 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [8 empty] | 13641.6
621-131 | LN2 - LHe Supply-Procure Hardware & Materials | 124 | Q < 6 months | Z < 25 weeks | G <6 month | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [8 empty] | 40282.16
1408-2 | Epoxy (existing order) | 125 | Q < 6 months | Z < 25 weeks | G <6 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 58166.95
1204-140.2 | Design Drafting T/C and Heater Tape Leads | 126 | Q < 6 months | AA < 26 weeks | G <6 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124U | 11 | [7 empty] | 3373.8
1204-140.1 | Peer Review T/C and Heater Tape Leads | 126 | Q < 6 months | AA < 26 weeks | G <6 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124U | 12 | [7 empty] | 4524.6
1408-5 | Epoxy/glass for mold shell | 126 | Q < 6 months | AA < 26 weeks | G <6 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 16775.71
1803-5.2 | Complete platform models | 127 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 5.00 | 53 | [7 empty] | 9592.8
1803-5.4 | Structural Analysis | 127 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 5.00 | 59 | [7 empty] | 11145.6
R54-70 | UNT - Timing & Seq Emulation (FPGA Pgm) | 127 | Q < 6 months | AA < 26 weeks | H <7 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 18 | [7 empty] | 12473.6
1803-5.7 | Complete dwg package and release for Fa | 127 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 5.00 | 71 | [7 empty] | 14389.2
1803-5.1 | Complete FP support models | 127 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 5.00 | 50 | [7 empty] | 27276.48
1408-7 | Misc tech shop support | 127 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 50127.62
1803-5.9 | Procure materials and fixture (2 stations) | 127 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 5.00 | 75 | [7 empty] | 94071.36
1408-6 | VPI clean manifold contract | 128 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 12942.86
P2-171V | VPI (Station 5) B5 | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 15 | 1 |  | B5 |  |  |  | 5 | 1281.76
P3-171C | Final Clamps & Warm Test (Station1) B5 | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 15 | 1 |  | B5 |  |  |  | 1 | 2563.52
R1810-3108 | Procure ,Fabricate 3 legged actuator lift fixtur | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 14 |  |  | 3 |  |  |  |  | 7848
R1810-3112 | Load Test 3 legged actuator lift fixtur | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 15 |  |  | 3 |  |  |  |  | 10254.08
P3-171C | Final Clamps & Warm Test (Station1) B5 | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 15 | 1 |  | B5 |  |  |  | 1 | 11215.4
P3-171C | Final Clamps & Warm Test (Station1) B5 | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 15 | 1 |  | B5 |  |  |  | 1 | 12248.68
P2-171V | VPI (Station 5) B5 | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 15 | 1 |  | B5 |  |  |  | 5 | 22110.36
P2-171V | VPI (Station 5) B5 | 129 | Q < 6 months | AA < 26 weeks | H <7 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 15 | 1 |  | B5 |  |  |  | 5 | 24409.24
445-2-120 | Overload Protect-Test 4 units | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 4849.6
445-2-130 | Overload Protect-Write & perform ISTP | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 4849.6
445-2-120 | Overload Protect-Test 4 units | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 5908.8
445-2-130 | Overload Protect-Write & perform ISTP | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 5908.8
445-2-115 | Overload Protect-Fabr 4 chassis | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 8863.2
445-2-125 | Overload Protect-Install & Rack wiring | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 8863.2
445-2-125 | Overload Protect-Install & Rack wiring | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 11669.35
445-2-115 | Overload Protect-Fabr 4 chassis | 132 | R > 6 months | AB > 6 months | H <7 month | 4 | 44 | 445 |  | 9450 |  | 4401 | S |  |  |  | 445 |  |  |  | 44 |  |  |  |  | 18186
P1-171V | VPI (Station 5) A6 | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 16 | 1 |  | A6 |  |  |  | 5 | 1281.76
P1-171C | Final Clamps & Warm Test (Station1) A6 | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 16 | 1 |  | A6 |  |  |  | 1 | 2563.52
453-1-2 | New Procedures | 134 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 453 |  | 9450 |  | 4501 | 2 |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 4328.01
R1810-3106 | Load test 3 ledded actuator system | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 13 |  |  | 3 |  |  |  |  | 7690.56
P1-171C | Final Clamps & Warm Test (Station1) A6 | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 16 | 1 |  | A6 |  |  |  | 1 | 11215.4
P1-171C | Final Clamps & Warm Test (Station1) A6 | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 16 | 1 |  | A6 |  |  |  | 1 | 12248.68
453-1-2 | New Procedures | 134 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 453 |  | 9450 |  | 4501 | 2 |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 19941.33
P1-171V | VPI (Station 5) A6 | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 16 | 1 |  | A6 |  |  |  | 5 | 22110.36
P1-171V | VPI (Station 5) A6 | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 16 | 1 |  | A6 |  |  |  | 5 | 24409.24
R1810-3104 | Procure 3 legged actuator system | 134 | R > 6 months | AB > 6 months | H <7 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 12 |  |  | 3 |  |  |  |  | 56244
1204-153 | Deliver T/C and Heater Tape Leads | 136 | R > 6 months | AB > 6 months | H <7 month | 1 | 12 | 122 |  | 9450 |  | 1204 | F | A |  |  | 124U | [8 empty] | 36951
1416-507 | Update, review and approve coil asm spec | 137 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDE | 10 | X | [6 empty] | 12940.8
1408-4.1 | Procure & Deliver Strain Gages | 137 | R > 6 months | AB > 6 months | H <7 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 49704
1204-130 | Deliver Heater Tape for port stubs | 140 | R > 6 months | AB > 6 months | H <7 month | 1 | 12 | 122 |  | 9450 |  | 1204 | F | A |  |  | 124T | [8 empty] | 20143.2
R54-30 | Preliminary Design - Clock Dist. | 143 | R > 6 months | AB > 6 months | H <7 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 14 | [7 empty] | 3207.2
R54-40 | Final Design - Clock Dist. | 143 | R > 6 months | AB > 6 months | H <7 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 15 | [7 empty] | 3207.2
R1810-3150 | Fab New legs | 143 | R > 6 months | AB > 6 months | H <7 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 16 |  |  | 3 |  |  |  |  | 5127.04
R54-30 | Preliminary Design - Clock Dist. | 143 | R > 6 months | AB > 6 months | H <7 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 14 | [7 empty] | 7386
R54-40 | Final Design - Clock Dist. | 143 | R > 6 months | AB > 6 months | H <7 month | 5 | 54 | 540 |  | 9450 |  | 5401 | [5 empty] | 15 | [7 empty] | 22158
622-141 | LN2 Coil Cooling Supply-Assemble Skid | 144 | R > 6 months | AB > 6 months | H <7 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 2812
622-151 | LN2 Coil Cooling Supply-Relocate skid to NCSX TC | 144 | R > 6 months | AB > 6 months | H <7 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 2812
622-141 | LN2 Coil Cooling Supply-Assemble Skid | 144 | R > 6 months | AB > 6 months | H <7 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 15346.8
622-151 | LN2 Coil Cooling Supply-Relocate skid to NCSX TC | 144 | R > 6 months | AB > 6 months | H <7 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 15346.8
622-131 | LN2 Coil Cooling Supply-Procure Hardware | 144 | R > 6 months | AB > 6 months | H <7 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 22398.49
431-265 | Fabricate bus components | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 2857.28
431-265 | Fabricate bus components | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 4936.8
431-265 | Fabricate bus components | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 5862.4
451-0-2 | Develop SRD | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 03 |  |  | 45 |  |  |  |  | 7143.2
431-265 | Fabricate bus components | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 9618
451-2-2.1 | Final Design C-Site | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 14 |  |  | 45 |  |  |  |  | 14286.4
451-6-2 | Final design C-Site -Cabling | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 13 |  |  | 45 |  |  |  |  | 14286.4
451-2-2.1 | Final Design C-Site | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 14 |  |  | 45 |  |  |  |  | 14810.4
451-6-2 | Final design C-Site -Cabling | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 13 |  |  | 45 |  |  |  |  | 14810.4
451-2-2 | PDR Prep Power system -Dsn | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 12 |  |  | 45 |  |  |  |  | 15797.76
451-2-2 | PDR Prep Power system -Dsn | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 12 |  |  | 45 |  |  |  |  | 17143.68
431-265 | Fabricate bus components | 146 | R > 6 months | AB > 6 months | H <7 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  | C |  | 431 | 10 |  |  | 43 |  |  |  |  | 62865
1501-525P | PDR | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [5 empty] | M |  |  |  |  | 3 |  | 696.92
1501-525P | PDR | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [5 empty] | M |  |  |  |  | 3 |  | 696.92
1501-541 | FDR Coil Structures | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [5 empty] | M |  |  |  |  | 3 |  | 696.92
1501-541 | FDR Coil Structures | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [5 empty] | M |  |  |  |  | 3 |  | 696.92
1501-558 | Prepare requisition for Coil Structure & CSS h/w | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 743.04
1501-537 | FDR Prep | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 871.15
1501-525 | PDR Prep | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 1742.3
1501-525 | PDR Prep | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 1742.3
1501-537 | FDR Prep | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 1742.3
1501-533 | Detail CAD Drawings,BOM | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 3484.6
1501-545 | Resolve Chits | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 3657.55
1501-545 | Resolve Chits | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 3657.55
1501-522 | Prelim CAD models & Dwgs | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 27876.8
1501-533F | Integrated Stress Analysis | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 41815.2
1501-533 | Detail CAD Drawings,BOM | 149 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 55753.6
132-012 | FDR WBS 162 Coil leads | 150 | R > 6 months | AB > 6 months | I < 8 month | 1 | 16 | 162 |  | 9450 |  | 1601 | 2 | A | L |  | 162 | 01 | M |  | 16 |  |  |  |  | 1387.28
132-038 | Deliver Lead hardware and cables | 150 | R > 6 months | AB > 6 months | I < 8 month | 1 | 16 | 162 |  | 9450 |  | 1601 | T | A | C |  | 162 | 01 | 1 |  | 16 |  |  |  | P | 114187.68
132-011 | Title II design WBS 162 Coil leads | 150 | R > 6 months | AB > 6 months | I < 8 month | 1 | 16 | 162 |  | 9450 |  | 1601 | 2 | A | L |  | 162 | 01 | 1 |  | 16 |  |  |  |  | 158843.56
1501-550 | Peer Review Updated C.S.Design | 154 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 743.04
1501-550 | Peer Review Updated C.S.Design | 154 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 743.04
1501-562 | Prepare Specs for Coil Structure & CSS h/w | 154 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 1857.6
1501-549 | Update C.S.Support Design | 154 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 3599.9
1501-554 | Resolve Chits from peer review | 154 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 3715.2
1501-554 | Resolve Chits from peer review | 154 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 3715.2
713.020 | Lab Fab/Assy/Installation | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | F | A |  |  |  |  | 1 | [6 empty] | 5807.62
713.060 | Torque wrenches and multipliers | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | T | A |  |  |  |  | 1 | [5 empty] | P | 6731.95
1501-549 | Update C.S.Support Design | 154 | R > 6 months | AB > 6 months | I < 8 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 7199.8
713.020 | Lab Fab/Assy/Installation | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | F | A |  |  |  |  | 1 | [6 empty] | 11739.27
713.020 | Lab Fab/Assy/Installation | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | F | A |  |  |  |  | 1 | [6 empty] | 13463.91
713.040 | General procurements | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | T | A |  |  |  |  | 1 | [5 empty] | P | 63647.97
713.030 | Tooling,assy fixtures,misc equipt | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | T | A |  |  |  |  | 1 | [5 empty] | P | 84863.97
713.050 | Welding tools, materials & equipt | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | T | A |  |  |  |  | 1 | [5 empty] | P | 113151.95
713.060 | Torque wrenches and multipliers | 154 | R > 6 months | AB > 6 months | I < 8 month | 7 | 76 | 760 |  | 9450 |  | 7601 | T | A |  |  |  |  | 1 | [5 empty] | P | 113151.95
1803-3.8 | Generate laser trace drawing for each screen | 157 | R > 6 months | AB > 6 months | I < 8 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 38 | [7 empty] | 8996.8
R56-30 | PLC Training | 159 | R > 6 months | AB > 6 months | I < 8 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 2546
R56-30 | PLC Training | 159 | R > 6 months | AB > 6 months | I < 8 month | 5 | 56 | 560 |  | 9450 |  | 5601 | [13 empty] | 12828.8
R1810-2004 | Receive Drawings & Hardware (shims & Bolts) | 163 | R > 6 months | AB > 6 months | I < 8 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S2PX | 12 |  |  | 2A |  |  |  |  | 10521
1803-5.8 | Complete models and dwgs for test cell metrology | 163 | R > 6 months | AB > 6 months | I < 8 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 5.00 | 74 | [7 empty] | 19185.6
P2-081V | VPI (Station 5) B3 | 164 | R > 6 months | AB > 6 months | I < 8 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 12 | 1 |  | B3 |  |  |  | 5 | 1202.4
P2-081V | VPI (Station 5) B3 | 164 | R > 6 months | AB > 6 months | I < 8 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 12 | 1 |  | B3 |  |  |  | 5 | 20741.4
P2-081V | VPI (Station 5) B3 | 164 | R > 6 months | AB > 6 months | I < 8 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 12 | 1 |  | B3 |  |  |  | 5 | 22896.82
1803-3.9 | Assembly sequence plan and Installation procedur | 168 | R > 6 months | AB > 6 months | I < 8 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 41 | [7 empty] | 6969.2
1803-3.10 | VV/MC clearance report (for VVSA1, 2 and 3) | 168 | R > 6 months | AB > 6 months | I < 8 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 44 | [7 empty] | 12544.56
452-1-4 | Diagnostics AC Power Distr-Procure | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | T |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 987.36
452-1-4 | Diagnostics AC Power Distr-Procure | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | T |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 1397
452-1-6 | Diagnostics AC Power Distr-Install | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | F |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 4353.16
452-1-8 | Diagnostics AC Power Distr-Commission | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | S |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 4431.6
452-1-6 | Diagnostics AC Power Distr-Install | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | F |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 10028.68
452-1-6 | Diagnostics AC Power Distr-Install | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | F |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 11909.05
452-1-8 | Diagnostics AC Power Distr-Commission | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | S |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 12124
452-1-8 | Diagnostics AC Power Distr-Commission | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | S |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 13260.8
452-1-2 | Diagnostics AC Power Distr-Dsn | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | 2 |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 14286.4
452-1-2 | Diagnostics AC Power Distr-Dsn | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | 2 |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 19747.2
452-1-6 | Diagnostics AC Power Distr-Install | 170 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 452 |  | 9450 |  | 4501 | F |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 52102.4
1501-521 | Complete Preliminary Stress analysis | 171 | R > 6 months | AB > 6 months | J <9 month | 1 | 15 | 151 |  | 9450 |  | 1501 | 1 | [12 empty] | 12196.1
P1-081C | Final Clamps & Warm Test (Station1) A5 | 173 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 14 | 1 |  | A5 |  |  |  | 1 | 2563.52
1803-3.7 | Transportation study (move between test cells) | 173 | R > 6 months | AB > 6 months | J <9 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 3.00 | 35 | [7 empty] | 4498.4
P1-081C | Final Clamps & Warm Test (Station1) A5 | 173 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 14 | 1 |  | A5 |  |  |  | 1 | 11215.4
P1-081C | Final Clamps & Warm Test (Station1) A5 | 173 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 14 | 1 |  | A5 |  |  |  | 1 | 12248.68
122-037 | Deliver Pourable Insulation | 176 | R > 6 months | AB > 6 months | J <9 month | 1 | 12 | 122 |  | 9450 |  | 1204 | T | A |  |  | 122 | 44 |  |  | 12 |  |  |  | P | 114560
P1-081V | VPI (Station 5) A5 | 179 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 14 | 1 |  | A5 |  |  |  | 5 | 1281.76
P1-081V | VPI (Station 5) A5 | 179 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 14 | 1 |  | A5 |  |  |  | 5 | 22110.36
P1-081V | VPI (Station 5) A5 | 179 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 14 | 1 |  | A5 |  |  |  | 5 | 24409.24
1204-148 | Machine 12 2.75 cf blanks | 181 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124U | 15 | [7 empty] | 4461.12
1204-151 | Machine 6 commercial aluminum boxes | 181 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124U | 15 | [7 empty] | 4461.12
1421-3072 | Deliver Add'l stud kits for c-c joint&weld clmp | 181 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | STUD | 12 | X | [6 empty] | 59827.92
8501-133 | OP-AD-39, Conduct of Operations | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 19 | [7 empty] | 2719.6
8501-137 | OP-AD-56, Cntrl Equipt & Syst Status (chain of c | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 21 | [7 empty] | 2719.6
8501-141 | OP-AD-24, Cntrl Workplace Cleanliness D-Site Exp | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 22 | [7 empty] | 2719.6
8501-145 | OP-AD-31, D- Site Fire Watch Requirements | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 23 | [7 empty] | 2719.6
8501-149 | OP-AD-03, Experimental Proposals for NCSX | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 24 | [7 empty] | 2719.6
8501-153 | OP-AD-117 Operation of the NCSX Access System | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 25 | [7 empty] | 2719.6
8501-133 | OP-AD-39, Conduct of Operations | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 19 | [7 empty] | 3310
8501-137 | OP-AD-56, Cntrl Equipt & Syst Status (chain of c | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 21 | [7 empty] | 3310
8501-141 | OP-AD-24, Cntrl Workplace Cleanliness D-Site Exp | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 22 | [7 empty] | 3310
8501-145 | OP-AD-31, D- Site Fire Watch Requirements | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 23 | [7 empty] | 3310
8501-149 | OP-AD-03, Experimental Proposals for NCSX | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 24 | [7 empty] | 3310
8501-153 | OP-AD-117 Operation of the NCSX Access System | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 25 | [7 empty] | 3310
8501-181 | NCSX-OP-XX, HPP Daily Operations | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 33 | [7 empty] | 5439.2
8501-185 | NCSX-OP-XX, ACP & PDP Trip Control Settings | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 34 | [7 empty] | 5439.2
8501-205 | OP-ECS-245 FCPC Daily Startup/Shutdown Procedure | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 39 | [7 empty] | 5624
8501-209 | NCSX-XX Leak Checking of NCSX | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 41 | [7 empty] | 5624
8501-181 | NCSX-OP-XX, HPP Daily Operations | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 33 | [7 empty] | 6620
8501-185 | NCSX-OP-XX, ACP & PDP Trip Control Settings | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 34 | [7 empty] | 6620
8501-205 | OP-ECS-245 FCPC Daily Startup/Shutdown Procedure | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 39 | [7 empty] | 6845.2
8501-209 | NCSX-XX Leak Checking of NCSX | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 41 | [7 empty] | 6845.2
8501-157 | NCSX-OP-XX, Prep of Exper Areas for Machine Ops | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 26 | [7 empty] | 8158.8
8501-161 | NCSX-OP-XX, Operation of the NCSX TVPS | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 27 | [7 empty] | 8158.8
8501-165 | NCSX-OP-XX, Testing NCSX HIS Safe for Access | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 28 | [7 empty] | 8158.8
8501-169 | NCSX-OP-XX, Testing the NCSX Emergency Stop Syst | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 29 | [7 empty] | 8158.8
8501-173 | NCSX-OP-XX, NCSX Training Matrix | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 31 | [7 empty] | 8158.8
8501-177 | NCSX-OP-XX, NCSX Ops Guide -Startup and Shutdown | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 32 | [7 empty] | 8158.8
8501-189 | NCSX-OP-G-XX Preparation for NCSX pumpdown | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 35 | [7 empty] | 8158.8
8501-193 | NCSX-OP-XX Helium H/C System Operations Procedur | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 36 | [7 empty] | 8241.96
8501-197 | NCSX-OP-G-XX Daily Hi-Pot Test Vacuum Vessel | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 37 | [7 empty] | 8380.56
8501-157 | NCSX-OP-XX, Prep of Exper Areas for Machine Ops | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 26 | [7 empty] | 9930
8501-161 | NCSX-OP-XX, Operation of the NCSX TVPS | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 27 | [7 empty] | 9930
8501-165 | NCSX-OP-XX, Testing NCSX HIS Safe for Access | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 28 | [7 empty] | 9930
8501-169 | NCSX-OP-XX, Testing the NCSX Emergency Stop Syst | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 29 | [7 empty] | 9930
8501-173 | NCSX-OP-XX, NCSX Training Matrix | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 31 | [7 empty] | 9930
8501-177 | NCSX-OP-XX, NCSX Ops Guide -Startup and Shutdown | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 32 | [7 empty] | 9930
8501-189 | NCSX-OP-G-XX Preparation for NCSX pumpdown | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 35 | [7 empty] | 9930
8501-193 | NCSX-OP-XX Helium H/C System Operations Procedur | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 36 | [7 empty] | 10031.34
8501-197 | NCSX-OP-G-XX Daily Hi-Pot Test Vacuum Vessel | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 37 | [7 empty] | 10200.24
8501-129 | NCSX-XX, Administrative Control of Procedures | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 18 | [7 empty] | 10878.4
8501-201 | ISTP-NCSX-01 Coil EnergizationTests | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 38 | [7 empty] | 11248
8501-129 | NCSX-XX, Administrative Control of Procedures | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 18 | [7 empty] | 13240
8501-201 | ISTP-NCSX-01 Coil EnergizationTests | 184 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S |  |  |  | PROC | 38 | [7 empty] | 13690.4
8501-101 | SAD NCSX Safety Assessment Document (SAD) | 185 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S | A | X | X | PROC | 17 | 1 | [6 empty] | 21756.8
8501-101 | SAD NCSX Safety Assessment Document (SAD) | 185 | R > 6 months | AB > 6 months | J <9 month | 8 | 85 | 850 |  | 9450 |  | 8501 | S | A | X | X | PROC | 17 | 1 | [6 empty] | 26480
451-1-2 | Calculations-Dsn | 186 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 15 |  |  | 45 |  |  |  |  | 987.36
451-1-2 | Calculations-Dsn | 186 | R > 6 months | AB > 6 months | J <9 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 15 |  |  | 45 |  |  |  |  | 7143.2
1204-173 | Purchase material for boxes&spacers (in job 1204 | 187 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 16 | [7 empty] | 300.6
1204-161 | Fab Protective Boxes | 187 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 13 | [7 empty] | 561.44
1204-161 | Fab Protective Boxes | 187 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 13 | [7 empty] | 601.2
1204-173 | Purchase material for boxes&spacers (in job 1204 | 187 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 16 | [7 empty] | 603.28
1204-160 | Design Protective Boxes | 187 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 10 | [7 empty] | 3318.04
1204-161 | Fab Protective Boxes | 187 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 13 | [7 empty] | 4461.12
1204-173 | Purchase material for boxes&spacers (in job 1204 | 187 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 16 | [7 empty] | 5208
1803-5.5 | Design followup & prelim analysis | 187 | R > 6 months | AB > 6 months | J <9 month | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 5.00 | 50 | [7 empty] | 10453.8
1204-173M | Material Delivery (desifn/fab in job 3101) | 187 | R > 6 months | AB > 6 months | J <9 month | 1 | 12 | 125 |  | 9450 |  | 1204 | F | A |  |  | 124V | [8 empty] | 12275.12
R1810-1109 | Loop termination & verification | 187 | R > 6 months | AB > 6 months | J <9 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 14 |  |  | 1 |  |  |  |  | 27054
3101-317 | PRELIM DESIGN ROWGOWSKI COIL incl prototype | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 127.6
3101-325 | FINAL DESIGN ROWGOSKI COIL | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 449.84
3101-317 | PRELIM DESIGN ROWGOWSKI COIL incl prototype | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 1503
3101-325 | FINAL DESIGN ROWGOSKI COIL | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 1982.72
3101-329 | FAB ROWGOWSKI COILS incl clamps | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD3 | 13 | [7 empty] | 2358.68
3101-317 | PRELIM DESIGN ROWGOWSKI COIL incl prototype | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 2974.08
3101-329 | FAB ROWGOWSKI COILS incl clamps | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD3 | 13 | [7 empty] | 4134.34
3101-329 | FAB ROWGOWSKI COILS incl clamps | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD3 | 13 | [7 empty] | 5834.8
3101-316 | CONCEP DESIGN ROWGOWSKI COIL | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 9049.2
3101-329 | FAB ROWGOWSKI COILS incl clamps | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD3 | 13 | [7 empty] | 9558.27
3101-317 | PRELIM DESIGN ROWGOWSKI COIL incl prototype | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 12065.6
3101-325 | FINAL DESIGN ROWGOSKI COIL | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 19003.32
3101-340 | subcontract winding 3 mandrels | 188 | R > 6 months | AB > 6 months | J <9 month | 3 | 31 | 310 |  | 9450 |  | 3101 | 1 | A |  |  | MD3 | 10 | [7 empty] | 19140
P3-081C | Final Clamps & Warm Test (Station1) B4 | 189 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 13 | 1 |  | B4 |  |  |  | 1 | 2404.8
P3-081C | Final Clamps & Warm Test (Station1) B4 | 189 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 13 | 1 |  | B4 |  |  |  | 1 | 10521
P3-081C | Final Clamps & Warm Test (Station1) B4 | 189 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 | 1 | 9450 |  | 1451 | F | A |  |  | 1 | 13 | 1 |  | B4 |  |  |  | 1 | 11489.74
1408-3 | Misc and safety supplies ($7k/mo.) | 189 | R > 6 months | AB > 6 months | J <9 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 81438.89
220-101 | Preliminary Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 2344.96
220-101 | Preliminary Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 2752.08
220-109 | Final Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 3669.44
220-109 | Final Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 4689.92
220-101 | Preliminary Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 5714.56
220-101 | Preliminary Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 9379.92
220-101 | Preliminary Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 10592
220-109 | Final Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 14564
220-109 | Final Design | 190 | R > 6 months | AB > 6 months | J <9 month | 2 | 22 | 220 |  | 9450 |  | 2201 | [5 empty] | 10 | [7 empty] | 16291.44
1204-170 | Autocad dwgs of field runs/tag#/ports assignmt | 193 | R > 6 months | AB > 6 months | K <10 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 12 | [7 empty] | 16891.84
443-1-2 | Develop Control Algorithms-Dsn | 195 | R > 6 months | AB > 6 months | K <10 month | 4 | 44 | 443 |  | 9450 |  | 4401 | 2 |  |  |  | 443 |  |  |  | 44 |  |  |  |  | 14772
P3-081V | VPI (Station 5) B4 | 202 | R > 6 months | AB > 6 months | K <10 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 13 | 1 |  | B4 |  |  |  | 5 | 1202.4
1416-508 | Complete drawing rev to leads, terminal asm (ECN | 202 | R > 6 months | AB > 6 months | K <10 month | 1 | 14 | 142 |  | 9450 |  | 1416 | F |  | L |  | MCDE | 10 | X | [6 empty] | 12457.6
P3-081V | VPI (Station 5) B4 | 202 | R > 6 months | AB > 6 months | K <10 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 13 | 1 |  | B4 |  |  |  | 5 | 20741.4
P3-081V | VPI (Station 5) B4 | 202 | R > 6 months | AB > 6 months | K <10 month | 1 | 14 | 142 | 2 | 9450 |  | 1451 | F | A |  |  | 5 | 13 | 1 |  | B4 |  |  |  | 5 | 22896.82
452-2-8 | Diagnostics sensor cabling-Commission | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | S |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 1477.2
452-2-8 | Diagnostics sensor cabling-Commission | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | S |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 2424.8
452-2-8 | Diagnostics sensor cabling-Commission | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | S |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 2652.16
452-2-4 | Diagnostics sensor cabling-Procure | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | T |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 2796.15
452-2-6 | Diagnostics sensor cabling-Install | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | F |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 2954.4
452-2-2 | Diagnostics sensor cabling-Dsn | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | 2 |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 4285.92
452-2-6 | Diagnostics sensor cabling-Install | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | F |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 4849.6
452-2-6 | Diagnostics sensor cabling-Install | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | F |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 13260.8
452-2-2 | Diagnostics sensor cabling-Dsn | 205 | R > 6 months | AB > 6 months | K <10 month | 4 | 45 | 452 |  | 9450 |  | 4501 | 2 |  |  |  | 452 |  |  |  | 45 |  |  |  |  | 19747.2
132-048 | Deliver Material for Transition Boxes | 216 | R > 6 months | AB > 6 months | L <11 month | 1 | 16 | 162 |  | 9450 |  | 1601 | T | A | L |  | 162 | 01 | 1 |  | 16 |  |  |  | P | 9909.44
132-049 | Assemble Transition boxes (6) | 216 | R > 6 months | AB > 6 months | L <11 month | 1 | 16 | 162 |  | 9450 |  | 1601 | T | A | L |  | 162 | 01 | 1 |  | 16 |  |  |  | P | 20462.4
453-1-3 | Preop Testing-Procure test equipt | 217 | R > 6 months | AB > 6 months | L <11 month | 4 | 45 | 453 |  | 9450 |  | 4501 | 2 |  |  |  | 453 |  |  |  | 45 |  |  |  |  | 28187.69
R1810-1313 | Install precision magnetic diagnostic sensors | 219 | R > 6 months | AB > 6 months | L <11 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 17 |  |  | 1 |  |  |  |  | 4509
R1810-1315 | Verify installation magnetic diagnostic sensors | 219 | R > 6 months | AB > 6 months | L <11 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 18 |  |  | 1 |  |  |  |  | 6012
R1810-1311 | Wind magnetic diagnostic sensors | 219 | R > 6 months | AB > 6 months | L <11 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 13 |  |  | 1 |  |  |  |  | 21042
621-101 | LN2 - LHe Supply-Preliminary Design | 221 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [8 empty] | 1974.72
622-101 | LN2 Coil Cooling Supply-Prelim Design | 221 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 3702.6
621-101 | LN2 - LHe Supply-Preliminary Design | 221 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [8 empty] | 7282
622-101 | LN2 Coil Cooling Supply-Prelim Design | 221 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 7282
621-121 | LN2 - LHe Supply-Final Design | 222 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [8 empty] | 2962.08
622-121 | LN2 Coil Cooling Supply-Final Design | 222 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 3702.6
621-121 | LN2 - LHe Supply-Final Design | 222 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [8 empty] | 7282
622-121 | LN2 Coil Cooling Supply-Final Design | 222 | R > 6 months | AB > 6 months | L <11 month | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [8 empty] | 7282
R1810-1300 | Install Templates | 227 | R > 6 months | AB > 6 months | L <11 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 13 |  |  | 1 |  |  |  |  | 4509
R52-50 | EPICS Programming - VDCT db editor | 229 | R > 6 months | AB > 6 months | L <11 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 6273.87
R52-60 | IOC Programming - MDSplus data & events | 229 | R > 6 months | AB > 6 months | L <11 month | 5 | 52 | 520 |  | 9450 |  | 5201 | [5 empty] | 10 | [7 empty] | 18821.6
6101-115 | Test Vac Pmp water sys | 234 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | F | B |  |  | 613 |  | 1 | [6 empty] | 1324
6101-115 | Test Vac Pmp water sys | 234 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | F | B |  |  | 613 |  | 1 | [6 empty] | 3298.4
6101-110 | Fabricate and Install Vac Pmp water sys | 234 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | F | B |  |  | 613 |  | 1 | [6 empty] | 7282
6101-110 | Fabricate and Install Vac Pmp water sys | 234 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | F | B |  |  | 613 |  | 1 | [6 empty] | 13853.28
6301-020 | Vac Vent and Air sys-Test | 237 | R > 6 months | AB > 6 months | M <12 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 1324
R1810-1211 | Weld cooling/htg risers | 237 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 14 |  |  | 1 |  |  |  |  | 2552
6301-020 | Vac Vent and Air sys-Test | 237 | R > 6 months | AB > 6 months | M <12 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 3298.4
6301-017 | Vac Vent and Air sys- Fabricate and Install | 237 | R > 6 months | AB > 6 months | M <12 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 3310
R1810-1209 | Install cooling/htg lines to vac vsl | 237 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 13 |  |  | 1 |  |  |  |  | 22545
R1810-1211 | Weld cooling/htg risers | 237 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 14 |  |  | 1 |  |  |  |  | 24048
6301-017 | Vac Vent and Air sys- Fabricate and Install | 237 | R > 6 months | AB > 6 months | M <12 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 26552.12
3101-804 | Purchase 900ft cable | 239 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | VLPB | [8 empty] | 321.58
3101-804 | Purchase 900ft cable | 239 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | VLPB | [8 empty] | 2092.8
3101-800 | Design Routing and Boxes | 239 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | VLPB | [8 empty] | 2398.2
R1810-1219 | Prepare& transfer completed VV to holding area | 239 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 22 | M |  | 1 |  |  |  |  | 3204.4
R1810-1216 | Install Final Internal&Ext monuments & meas | 239 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 19 |  |  | 1 |  |  |  |  | 6408.8
R1810-1217 | Final Scan | 239 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 20 |  |  | 1 |  |  |  |  | 6408.8
3101-800 | Design Routing and Boxes | 239 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | VLPB | [8 empty] | 7396.34
R1810-1214 | Install heater tape on all removable ports | 239 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 21 |  |  | 1 |  |  |  |  | 16022
R1810-1215 | Loop termination & verification | 239 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 18 |  |  | 1 |  |  |  |  | 28839.6
444-3-2 | DC Shunts-Dsn | 240 | R > 6 months | AB > 6 months | M <12 month | 4 | 44 | 444 |  | 9450 |  | 4401 | 2 |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 4083.84
444-3-2 | DC Shunts-Dsn | 240 | R > 6 months | AB > 6 months | M <12 month | 4 | 44 | 444 |  | 9450 |  | 4401 | 2 |  |  |  | 444 |  |  |  | 44 |  |  |  |  | 4431.6
441-095 | Design Interlock sys | 241 | R > 6 months | AB > 6 months | M <12 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 4936.8
441-095 | Design Interlock sys | 241 | R > 6 months | AB > 6 months | M <12 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 11724.8
441-097 | Install Interlock sys | 241 | R > 6 months | AB > 6 months | M <12 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 11914.42
441-095 | Design Interlock sys | 241 | R > 6 months | AB > 6 months | M <12 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 14286.4
441-097 | Install Interlock sys | 241 | R > 6 months | AB > 6 months | M <12 month | 4 | 44 | 441 |  | 9450 |  | 4401 | F |  |  |  | 441 |  |  |  | 44 |  |  |  |  | 14517.06
3101-426 | Purchase SS Sheet | 242 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 11 | [7 empty] | 80.11
3101-426 | Purchase SS Sheet | 242 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 11 | [7 empty] | 1137.96
3101-454 | Weld end plates of PF protective boxes | 242 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 13 | [7 empty] | 1441.98
3101-425 | Design Protective boxes for PF | 242 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 10 | [7 empty] | 7194.6
3101-452 | Form Protective boxes | 242 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 12 | [7 empty] | 13475.22
3101-425 | Design Protective boxes for PF | 242 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 10 | [7 empty] | 17686.9
3101-802 | Fab 3 protective Boxes | 249 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | VLPB | [8 empty] | 156.96
3101-802 | Fab 3 protective Boxes | 249 | R > 6 months | AB > 6 months | M <12 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | VLPB | [8 empty] | 961.32
R1810-1212 | Trim seal plates | 258 | R > 6 months | AB > 6 months | M <12 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 17 |  |  | 1 |  |  |  |  | 3204.4
6101-100 | Design Vac Pmp water sys | 258 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | 2 | B |  |  | 613 |  | 1 | [6 empty] | 3310
6101-105 | Procure Hardware and materials Vac Pmp water sys | 258 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | F | B |  |  | 613 |  | 1 | [6 empty] | 3310
6101-105 | Procure Hardware and materials Vac Pmp water sys | 258 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | F | B |  |  | 613 |  | 1 | [6 empty] | 4149.09
6101-100 | Design Vac Pmp water sys | 258 | R > 6 months | AB > 6 months | M <12 month | 6 | 61 | 613 |  | 9450 | EC45 | 6101 | 2 | B |  |  | 613 |  | 1 | [6 empty] | 9873.6
451-3-2 | Dwgs,asbuilts -Elect Dsn | 259 | R > 6 months | AB > 6 months | M <12 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 10 |  |  | 45 |  |  |  |  | 39499.89
451-3-2 | Dwgs,asbuilts -Elect Dsn | 259 | R > 6 months | AB > 6 months | M <12 month | 4 | 45 | 451 |  | 9450 |  | 4501 | 2 |  |  |  | 451 | 10 |  |  | 45 |  |  |  |  | 57153.53
431-240 | Simulate each of 6 pwr loops in PSCAD | 260 | R > 6 months | AC > 12 months | M <12 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 18572.32
431-261 | Redo power loop design | 260 | R > 6 months | AC > 12 months | M <12 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 22858.24
431-250 | c-site dc sys DGS dsn documentation | 260 | R > 6 months | AC > 12 months | M <12 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 29620.8
431-261 | Redo power loop design | 260 | R > 6 months | AC > 12 months | M <12 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 29620.8
431-250 | c-site dc sys DGS dsn documentation | 260 | R > 6 months | AC > 12 months | M <12 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 32144.4
3101-428 | Purchase aad'l CoAxial cable | 261 | R > 6 months | AC > 12 months | N <13 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 15 | [7 empty] | 155.51
3101-450 | Prototype PF Loops | 261 | R > 6 months | AC > 12 months | N <13 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 16 | [7 empty] | 1585.32
3101-428 | Purchase aad'l CoAxial cable | 261 | R > 6 months | AC > 12 months | N <13 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 15 | [7 empty] | 5817.6
3101-458 | FabTF,PF & solenoid co-wound loops | 261 | R > 6 months | AC > 12 months | N <13 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 17 | [7 empty] | 17174.3
R1810-1331 | Prepare & transfer completed VV to holding area | 273 | R > 6 months | AC > 12 months | N <13 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 32 | M |  | 1 |  |  |  |  | 3204.4
R1810-1314 | Install heater tape on all removable ports | 273 | R > 6 months | AC > 12 months | N <13 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 31 |  |  | 1 |  |  |  |  | 16022
R1810-1112 | Trim seal plates | 275 | R > 6 months | AC > 12 months | N <13 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 15 |  |  | 1 |  |  |  |  | 3204.4
6301-005 | Vac Vent and Air sys- PDR | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | M | [6 empty] | 1324
6301-010 | Vac Vent and Air sys- FDR | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | M | [6 empty] | 1324
6301-009 | Vac Vent and Air sys- Final dsn | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 1986
6301-013 | Vac Vent and Air sys- Procure hardware and compo | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 3310
6301-001 | Vac Vent and Air sys- Prelim Dsn | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 8606
6301-001 | Vac Vent and Air sys- Prelim Dsn | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 9873.6
6301-009 | Vac Vent and Air sys- Final dsn | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 9873.6
6301-013 | Vac Vent and Air sys- Procure hardware and compo | 285 | R > 6 months | AC > 12 months | O <14 month | 6 | 63 | 630 |  | 9450 |  | 6301 | 2 | B |  |  |  |  | 1 | [6 empty] | 34086.8
3101-427 | Purchase Heat Shrink tubing | 286 | R > 6 months | AC > 12 months | O <14 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 14 | [7 empty] | 450.9
3101-427 | Purchase Heat Shrink tubing | 286 | R > 6 months | AC > 12 months | O <14 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 14 | [7 empty] | 2552
R1810-1S04 | Install Final Internal&Ext monuments & meas | 288 | R > 6 months | AC > 12 months | O <14 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1SP |  |  |  | 1 |  |  |  |  | 3298.4
1803-609 | Detail dwgs-spool piece | 288 | R > 6 months | AC > 12 months | O <14 month | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  | 1.00 |  | 10 |  |  |  |  | 3 | P | 17008.28
R1810-1S03 | Attachdiagnostics, studs and coolant lines | 288 | R > 6 months | AC > 12 months | O <14 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1SP |  |  |  | 1 |  |  |  |  | 28036.4
R1810-1328 | Install Final Internal&Ext monuments & meas | 299 | R > 6 months | AC > 12 months | O <14 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 29 |  |  | 1 |  |  |  |  | 6408.8
R1810-1329 | Final Scan | 299 | R > 6 months | AC > 12 months | O <14 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 30 |  |  | 1 |  |  | 3 |  | 6408.8
R1810-1327 | Loop termination & verification | 299 | R > 6 months | AC > 12 months | O <14 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 28 |  |  | 1 |  |  |  |  | 28839.6
R1810-1115 | Purchase pump | 320 | R > 6 months | AC > 12 months | P <15 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 13 |  |  | 1 |  |  |  |  | 5104
R1810-1108 | Perform final acceptance testing (H/C flow test) | 320 | R > 6 months | AC > 12 months | P <15 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 12 |  |  | 1 |  |  |  |  | 7515
1361C-112 | Fab, Test & Deliver Coil #12 | 331 | R > 6 months | AC > 12 months | Q <16 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
1361C-118 | Fab, Test & Deliver Coil #18 | 336 | R > 6 months | AC > 12 months | Q <16 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47220
R1810-1105 | Instl cooling lines & Weld cooling/htg risers | 340 | R > 6 months | AC > 12 months | Q <16 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 10 |  |  | 1 |  |  |  |  | 2552
R1810-1107 | Verify Instl of H/C lines,headers,manifolds | 340 | R > 6 months | AC > 12 months | Q <16 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 11 |  |  | 1 |  |  |  |  | 7515
R1810-1105 | Instl cooling lines & Weld cooling/htg risers | 340 | R > 6 months | AC > 12 months | Q <16 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P1 | 10 |  |  | 1 |  |  |  |  | 46593
141-906 | PF6 Upper Inspection & Test | 341 | R > 6 months | AC > 12 months | Q <16 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 33 | 1 | [6 empty] | 1649.2
141-906 | PF6 Upper Inspection & Test | 341 | R > 6 months | AC > 12 months | Q <16 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 33 | 1 | [6 empty] | 1912.1
1352-166 | Fabricate/Dlvr PF 5 Upper | 341 | R > 6 months | AC > 12 months | Q <16 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 26 | 1 |  | 13 |  |  |  | P | 74148.05
1352-146 | Fabricate/Dlvr PF 6 Upper | 341 | R > 6 months | AC > 12 months | Q <16 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 27 | 1 |  | 13 |  |  |  | P | 86654.95
1361C-111 | Fab, Test & Deliver Coil #11 | 348 | R > 6 months | AC > 12 months | Q <16 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
1361C-117 | Fab, Test & Deliver Coil #17 | 352 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47220
R1810-1319 | Verify installation of local I&C | 356 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 20 |  |  | 1 |  |  |  |  | 3006
R1810-1317 | Install local I&C (incl thermocouples) | 356 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 19 |  |  | 1 |  |  |  |  | 7515
R1810-1325 | Verify Instl of H/C lines,headers,manifolds | 356 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 23 |  |  | 1 |  |  |  |  | 7515
R1810-1308 | Perform final acceptance testing (H/C flow test) | 356 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 24 |  |  | 1 |  |  |  |  | 7614.2
R1810-1321 | Install cooling/htg lines to vac vsl | 356 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 21 |  |  | 1 |  |  |  |  | 22545
R1810-1323 | Weld cooling/htg risers | 356 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 22 |  |  | 1 |  |  |  |  | 24048
1361C-101 | Fab, Test & Deliver Coil #1 | 356 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 27210
1361C-110 | Fab, Test & Deliver Coil #10 | 357 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
R1810-1312 | Trim seal plates | 360 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 25 |  |  | 1 |  |  |  |  | 3204.4
1204-113 | Deliver -Local I&C | 360 | R > 6 months | AC > 12 months | R <18 month | 1 | 12 | 122 |  | 9450 |  | 1204 | F | A |  |  | 125 | [8 empty] | 34400.96
1361C-104 | Fab, Test & Deliver Coil #4 | 360 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
1361C-116 | Fab, Test & Deliver Coil #16 | 369 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47220
1361C-109 | Fab, Test & Deliver Coil #9 | 374 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
141-905 | PF5 Upper Inspection & Test | 376 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 32 | 1 | [6 empty] | 1649.2
141-905 | PF5 Upper Inspection & Test | 376 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 32 | 1 | [6 empty] | 1912.1
1361C-103 | Fab, Test & Deliver Coil #3 | 379 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
1361C-108 | Fab, Test & Deliver Coil #8 | 380 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
1361C-115 | Fab, Test & Deliver Coil #15 | 385 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47220
431-210 | Organize & verify documentation | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 439.68
431-200 | Condition/spare parts inventory | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 879.36
431-225 | Reactivate DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 1172.48
431-230 | Duumy Load test of DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 1172.48
431-210 | Organize & verify documentation | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 1234.2
431-230 | Duumy Load test of DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 1397
431-200 | Condition/spare parts inventory | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 1428.64
431-210 | Organize & verify documentation | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 2857.28
431-215 | Document status | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 2857.28
431-225 | Reactivate DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 3206
431-230 | Duumy Load test of DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 3206
431-230 | Duumy Load test of DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 5714.56
431-225 | Reactivate DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 7143.2
431-225 | Reactivate DF & PEI units | 387 | R > 6 months | AC > 12 months | R <18 month | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  |  |  |  | 11176
R1810-1208 | Perform final acceptance testing (H/C flow test) | 390 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 16 |  |  | 1 |  |  |  |  | 5104
R1810-1208 | Perform final acceptance testing (H/C flow test) | 390 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 16 |  |  | 1 |  |  |  |  | 7515
R1810-1213 | Verify Instl of H/C lines,headers,manifolds | 390 | R > 6 months | AC > 12 months | R <18 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P2 | 15 |  |  | 1 |  |  |  |  | 7515
1361C-102 | Fab, Test & Deliver Coil #2 | 391 | R > 6 months | AC > 12 months | R <18 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 43590
1361C-107 | Fab, Test & Deliver Coil #7 | 393 | R > 6 months | AD > 18 months | S < 19 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
1361C-106 | Fab, Test & Deliver Coil #6 | 402 | R > 6 months | AD > 18 months | S < 19 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [5 empty] | 3 | P | 47210
1361C-114 | Fab, Test & Deliver Coil #14 | 402 | R > 6 months | AD > 18 months | S < 19 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
141-900A | PF4 Upper Inspection & Test | 405 | R > 6 months | AD > 18 months | S < 19 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 29 | 1 | [6 empty] | 1649.2
141-900A | PF4 Upper Inspection & Test | 405 | R > 6 months | AD > 18 months | S < 19 month | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 29 | 1 | [6 empty] | 1912.1
1352-151 | Fabricate/Dlvr PF 4 upper | 405 | R > 6 months | AD > 18 months | S < 19 month | 1 | 13 | 132 |  | 9450 |  | 1352 | T | A |  | B | 13P | 23 | 1 |  | 13 |  |  |  | P | 21125.1
1361C-113 | Fab, Test & Deliver Coil #13 | 418 | R > 6 months | AD > 18 months | T < 20 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
1361C-105 | Fab, Test & Deliver Coil #5 | 422 | R > 6 months | AD > 18 months | T < 20 month | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 13Y | 01 | [6 empty] | P | 47210
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 20443
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 26448
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 47010
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 49746
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 57279
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 60163
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 74372
920.000 | Startup Personnel | 426 | R > 6 months | AD > 18 months | T < 20 month | 8 | 85 | 850 | 1 | 9450 | EC45 | 8501 | S | A | X |  |  | 10 | 1 | L | [5 empty] | 83368
R1810-1307 | Verify installation of heater tapes | 442 | R > 6 months | AD > 18 months | U <21 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 12 |  |  | 1 |  |  |  |  | 1503
R1810-1309 | Attach studs forcoolant lines | 442 | R > 6 months | AD > 18 months | U <21 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 12 |  |  | 1 |  |  |  |  | 4509
1403-47C | Perform cool-down/warmup analysis | 445 | R > 6 months | AD > 18 months | U <21 month | 1 | 14 | 142 |  | 9450 |  | 1416 | 2 |  | L |  | TCCO | 01 | [7 empty] | 7430.4
1421-3142 | FDR Prep for C-C shims | 449 | R > 6 months | AD > 18 months | U <21 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142G | 19 | X | [6 empty] | 6470.4
1421-3145 | Bolt reach & access study (mockup) | 449 | R > 6 months | AD > 18 months | U <21 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142G | 17 | X | [6 empty] | 32352
1421-3140 | Prep C-C shim drawings and release | 449 | R > 6 months | AD > 18 months | U <21 month | 1 | 14 | 142 |  | 9450 | DSN | 1421 |  |  | L |  | 142G | 18 | X | [6 empty] | 58233.6
R1810-1305 | Install heater tape on vertical ports | 450 | R > 6 months | AD > 18 months | U <21 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 11 |  |  | 1 |  |  |  |  | 10521
R1810-1304 | Layout diag &coolant paths on vessel | 450 | R > 6 months | AD > 18 months | U <21 month | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S1P3 | 11 |  |  | 1 |  |  |  |  | 18036
[5 empty] | V <22 month | [20 empty] | 0
1421-3080 | Purchase G-11 shims and machine for C-C inboard | 497 | R > 6 months | AD > 18 months | W <23 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | STUD | 12 | X | [6 empty] | 1883.52
1421-3080 | Purchase G-11 shims and machine for C-C inboard | 497 | R > 6 months | AD > 18 months | W <23 month | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | STUD | 12 | X | [6 empty] | 3845.28
1204-171 | Prep Dwgs of spacer loops | 593 | R > 6 months | AE > 24 months | X <24 month | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 14 | [7 empty] | 6747.6
R1810-3102 | Misc M&S | 1060 | R > 6 months | AE > 24 months | Z >24 month | 1 | 18 | 185 | 1 | 9450 |  | 1810 |  |  |  | X | S3P0 | 10 |  |  | 3 |  |  |  |  | 6540
1408-8 | Cutting hardware for flange bolts | 1089 | R > 6 months | AE > 24 months | Z >24 month | 1 | 14 | 142 |  | 9450 |  | 1408 | F | A |  |  |  | 02 | 1 | [5 empty] | 1 | 3889.44
8210-07 | Update plant model | 1249 | R > 6 months | AE > 24 months | Z >24 month | 8 | 82 |  |  | 9450 |  | 8215 |  |  |  |  | RBLX | [8 empty] | 6032.8
8210-07 | Update plant model | 1249 | R > 6 months | AE > 24 months | Z >24 month | 8 | 82 |  |  | 9450 |  | 8215 |  |  |  |  | RBLX | [8 empty] | 8996.8
R1810-2050 | Consulting support for welding trials | 1261 | R > 6 months | AE > 24 months | Z >24 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 25520
R1810-2050 | Consulting support for welding trials | 1261 | R > 6 months | AE > 24 months | Z >24 month | 1 | 18 | 185 |  | 9450 |  | 1810 |  |  |  |  | S2PR |  |  |  |  | PHL2 |  |  |  | 63800
INTRF-030 | ORNL verify weld access | 1314 | R > 6 months | AE > 24 months | Z >24 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142H | 14 | X | [6 empty] | 6228.8
INTRF-010 | Develop Weld Geometry Procedure | 1314 | R > 6 months | AE > 24 months | Z >24 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142H | 15 | X | [6 empty] | 6969.2
INTRF-025 | ORNL build plywood mockup of flange | 1314 | R > 6 months | AE > 24 months | Z >24 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142H | 13 | X | [6 empty] | 21800.8
INTRF-025 | ORNL build plywood mockup of flange | 1314 | R > 6 months | AE > 24 months | Z >24 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142H | 13 | X | [6 empty] | 30000
INTRF-030 | ORNL verify weld access | 1314 | R > 6 months | AE > 24 months | Z >24 month | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  | 142H | 14 | X | [6 empty] | 39000
INTRF-001 | PPPL buy SS plate for weld trials | 1322 | R > 6 months | AE > 24 months | Z >24 month | 1 | 18 | 185 |  | 9450 | HW | 1810 | 2 |  | L |  | S2PR | 11 | X |  |  | PHL1 |  |  |  | 1206.56
INTRF-001 | PPPL buy SS plate for weld trials | 1322 | R > 6 months | AE > 24 months | Z >24 month | 1 | 18 | 185 |  | 9450 | HW | 1810 | 2 |  | L |  | S2PR | 11 | X |  |  | PHL1 |  |  |  | 39556
MCWF-004 | PPPL Overisght | 1360 | R > 6 months | AE > 24 months | Z >24 month | 1 | 14 | 141 |  | 9450 |  | 1411 | T | A |  |  |  | 51 |  |  | C6 |  |  |  | P | 6969.2
ECP53RBX03 | FY07 Rebaseline exercise |  |  | XX LOE |  | 1 | 13 |  |  | 9450 |  | 1361 |  |  |  |  | RBLX | [8 empty] | 1393.84
MCWF-003 | Contract closeout final cost increment |  |  | XX LOE |  | 1 | 14 | 141 |  | 9450 | X | 1411 | T | A |  |  |  | 48 | [6 empty] | P | 2640
ECP53RBX02 | FY07 Rebaseline exercise |  |  | XX LOE |  | 1 | 13 |  |  | 9450 |  | 1302 |  |  |  |  | RBLX | [8 empty] | 4529.98
99.07X | Retroactive MHX exclusion |  |  | XX LOE |  | 1 | 13 | 131 |  | 9450 |  | 1361 | A | A |  |  |  |  | 1 | [6 empty] | 138700
131-033 | Title III engr | 332 |  | XX LOE |  | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 130 | 16 | 1 |  |  |  | LOE |  |  | 190982.94
131-033 | Title III engr | 332 |  | XX LOE |  | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 130 | 16 | 1 |  |  |  | LOE |  |  | 6044.31
131-033 | Title III engr | 332 |  | XX LOE |  | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 130 | 16 | 1 |  |  |  | LOE |  |  | 10386.02
131-033 | Title III engr | 332 |  | XX LOE |  | 1 | 13 | 131 |  | 9450 | EC45 | 1361 | T | A |  |  | 130 | 16 | 1 |  |  |  | LOE |  |  | 5344.75
132-015 | Title III design WBS 162 Coil leads | 222 |  | XX LOE |  | 1 | 16 | 162 |  | 9450 |  | 1601 | F | A | L |  | 162 | 01 | 1 |  |  |  | LOE |  |  | 19579.88
141-031 | Title III engr WBS 132 | 846 |  | XX LOE |  | 1 | 13 | 132 |  | 9450 |  | 1352 | F | A |  |  | 13P | 28 | 1 |  |  |  | LOE |  |  | 148348.45
1421-4000 | Misc Tech Shop support through FPA sta 3 | 999 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 | HW | 1431 |  |  |  |  | TECH | 12 | X |  |  |  | LOE |  |  | 76905.6
145XSPRV-1 | Winding Engineering oversight and supervision | 1057 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 |  | 1451 | F | A |  |  | LABR | 02 | 1 |  |  |  | LOE |  | 1 | 310636.42
145XSPRV-1 | Winding Engineering oversight and supervision | 1057 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 |  | 1451 | F | A |  |  | LABR | 02 | 1 |  |  |  | LOE |  | 1 | 220926.49
145XSPRV-2 | Winding Engineering oversight and supervision | 1105 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 |  | 1451 | F | A |  |  | LABR | 02 | 1 |  |  |  | LOE |  | 1 | 151931.88
145XSPRV-3 | Winding Engineering oversight and supervision | 1018 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 |  | 1451 | F | A |  |  | LABR | 02 | 1 |  |  |  | LOE |  | 1 | 176572.52
161-038 | Title III | 886 |  | XX LOE |  | 1 | 17 | 172 |  | 9450 |  | 1752 | T | A |  | B | 172 | 20 | 1 |  | 17 |  | LOE |  | P | 8277.26
162-031 | Title III engr WBS 151 | 813 |  | XX LOE |  | 1 | 15 | 151 |  | 9450 |  | 1550 | F | A |  |  |  | 16 | 1 |  |  |  | LOE |  |  | 14151.47
163-015 | Title III design CS sprt struc | 101 |  | XX LOE |  | 1 | 13 | 132 |  | 9450 |  | 1353 | F | A |  |  | 132A | 24 | 1 |  |  |  | LOE |  |  | 13670.7
1751-171 | Cryostat- Title III | 660 |  | XX LOE |  | 1 | 17 | 171 |  | 9450 |  | 1751 | [10 empty] | LOE |  |  | 61606.8
1802MAY | May cost incr | 1335 |  | XX LOE |  | 1 | 18 | 186 |  | 9450 |  | 1802 | 1 |  | L |  | A | 01 |  |  |  |  | LOE |  |  | 15000
1802ORNL02 | ORNL Title III field period assy station 2 | 4 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 96768.52
1802ORNL02 | ORNL Title III field period assy station 2 | 4 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 49729.31
1802ORNL02 | ORNL Title III field period assy station 2 | 4 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 6330.33
1802ORNL03 | ORNL Title III field period assy station 3 | 0 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 73342.92
1802ORNL03 | ORNL Title III field period assy station 3 | 0 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 6350.7
1802ORNL03 | ORNL Title III field period assy station 3 | 0 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 37449.4
1802ORNL05 | ORNL Title III field period assy station 5 | 0 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 77161.29
1802ORNL05 | ORNL Title III field period assy station 5 | 0 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 6420
1802ORNL05 | ORNL Title III field period assy station 5 | 0 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 38589.95
1803-010 | Models,design reviews, meetings,reporting, | 925 |  | XX LOE |  | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  |  |  | 10 |  |  |  | LOE |  | P | 99312.88
1803-010 | Models,design reviews, meetings,reporting, | 925 |  | XX LOE |  | 1 | 18 | 186 |  | 9450 |  | 1806 | 2 | A | L |  |  |  | 10 |  |  |  | LOE |  | P | 77165.62
1803-2.1 | Assembly sequence plan drafted | 65 |  | XX LOE |  | 1 | 18 | 186 |  | 9450 |  | 1803 | 1 |  | L |  | 2.00 | 11 |  |  |  |  | LOE |  |  | 0
184-015 | Title III WBS 133 Rxt Trim Coils | 13 |  | XX LOE |  | 1 | 13 | 133 |  | 9450 |  | 1354 | F | B |  |  | 133 | 18 | 1 |  |  |  | LOE |  |  | 22180.36
184-015 | Title III WBS 133 Rxt Trim Coils | 13 |  | XX LOE |  | 1 | 13 | 133 |  | 9450 |  | 1354 | F | B |  |  | 133 | 18 | 1 |  |  |  | LOE |  |  | 3105
1901-07 | WBS 191 FY07 LOE | 1249 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 57111.87
1901-07 | WBS 191 FY07 LOE | 1249 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 3102
1901-07 | WBS 191 FY07 LOE | 1249 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 0
1901-07 | WBS 191 FY07 LOE | 1249 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 17166.57
1901-08 | WBS 191 FY08 LOE | 1000 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 139362.71
1901-08 | WBS 191 FY08 LOE | 1000 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 6312
1901-08 | WBS 191 FY08 LOE | 1000 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 20889.5
1901-08 | WBS 191 FY08 LOE | 1000 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 41889.37
1901-09 | WBS 191 FY09 LOE | 752 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 148199.65
1901-09 | WBS 191 FY09 LOE | 752 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 6420
1901-09 | WBS 191 FY09 LOE | 752 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 21928.88
1901-09 | WBS 191 FY09 LOE | 752 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 191 | [5 empty] | LOE |  |  | 44545.56
1901-10 | WBS 191 FY10 SA LOE | 502 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 153862.32
1901-10 | WBS 191 FY10 SA LOE | 502 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 6420
1901-10 | WBS 191 FY10 SA LOE | 502 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 22499.52
1901-10 | WBS 191 FY10 SA LOE | 502 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 46247.64
1901-11 | WBS 191 FY10 LOE | 423 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 50677.24
1901-11 | WBS 191 FY10 LOE | 423 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 6420
1901-11 | WBS 191 FY10 LOE | 423 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 23049.78
1901-11 | WBS 191 FY10 LOE | 423 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 191 | [5 empty] | LOE |  |  | 15232.46
1902-07 | WBS 192 FY07 | 1249 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 62889.08
1902-07 | WBS 192 FY07 | 1249 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 18189.6
1902-07 | WBS 192 FY07 | 1249 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 3102
1902-08 | WBS 192 FY08 | 1000 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 153460.09
1902-08 | WBS 192 FY08 | 1000 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 43308.47
1902-08 | WBS 192 FY08 | 1000 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 3156
1902-09 | WBS 192 FY09 | 752 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 163190.95
1902-09 | WBS 192 FY09 | 752 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 44548.13
1902-09 | WBS 192 FY09 | 752 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  |  |  | 192 | [5 empty] | LOE |  |  | 3210
1902-10 | WBS 192 FY10 | 502 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 192 | [5 empty] | LOE |  |  | 169426.43
1902-10 | WBS 192 FY10 | 502 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 192 | [5 empty] | LOE |  |  | 46379.17
1902-10 | WBS 192 FY10 | 502 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 192 | [5 empty] | LOE |  |  | 3210
1902-11 | WBS 192 FY10 | 423 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 192 | [5 empty] | LOE |  |  | 55803.55
1902-11 | WBS 192 FY10 | 423 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 192 | [5 empty] | LOE |  |  | 15319.55
1902-11 | WBS 192 FY10 | 423 |  | XX LOE |  | 1 | 19 | 191 | 1 | 9450 |  | 1901 |  |  | H |  | 192 | [5 empty] | LOE |  |  | 3210
191-031 | Title III engr WBS 161 | 941 |  | XX LOE |  | 1 | 16 | 161 |  | 9450 |  | 1601 | F | A | L |  | 161 | 17 | 1 |  |  |  | LOE |  |  | 9714.2
191-031 | Title III engr WBS 161 | 941 |  | XX LOE |  | 1 | 16 | 161 |  | 9450 |  | 1601 | F | A | L |  | 161 | 17 | 1 |  |  |  | LOE |  |  | 12722.2
191-031 | Title III engr WBS 161 | 941 |  | XX LOE |  | 1 | 16 | 161 |  | 9450 |  | 1601 | F | A | L |  | 161 | 17 | 1 |  |  |  | LOE |  |  | 5360.49
ECP53RBX08 | FY07 Rebaseline exercise | 1333 |  | XX LOE |  | 1 | 16 |  |  | 9450 |  | 1601 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 6228.8
ECP53RBX09 | FY07 Rebaseline exercise | 1333 |  | XX LOE |  | 1 | 15 |  |  | 9450 |  | 1501 | [10 empty] | LOE |  |  | 6969.2
INTRF-100 | Misc travel, meetings,reporting,job 1416&1421 | 1148 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  |  | 99 | M |  |  |  | LOE |  |  | 3607.91
INTRF-100 | Misc travel, meetings,reporting,job 1416&1421 | 1148 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  |  | 99 | M |  |  |  | LOE |  |  | 9385.04
INTRF-100 | Misc travel, meetings,reporting,job 1416&1421 | 1148 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  |  | 99 | M |  |  |  | LOE |  |  | 196747.15
INTRF-100 | Misc travel, meetings,reporting,job 1416&1421 | 1148 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  |  | 99 | M |  |  |  | LOE |  |  | 23352.69
R1801-004S | LOE Crane support, fixt setup (2nd shft 1.2 fte | 718 |  | XX LOE |  | 1 | 18 | 185 | 2 | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 139343.95
R1802-001 | Metrology Engr Super FY07 | 1249 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 62722.8
R1802-003 | Metrology Engr Super FY08 | 999 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 160310.88
R1802-004 | Metrology Engr Super FY09 | 718 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 194695.1
R1802-004S | Metrology Engr Super FY09 (2n shft suprt .5 fte | 718 |  | XX LOE |  | 1 | 18 | 181 | 2 | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 134631.52
R1802-005 | FPA Management FY07 | 1249 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 108439.58
R1802-005 | FPA Management FY07 | 1249 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 7273.2
R1802-007 | FPA Management FY08 | 999 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 277523.54
R1802-008 | FPA Management FY09 | 718 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 322131.05
R1802-013 | HP Coverage in the TFTR TC LOE FY07 | 1249 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 59214.54
R1802-015 | HP Coverage in the TFTR TC LOE FY08 | 999 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 149857.4
R1802-016 | HP Coverage in the TFTR TC LOE FY09 | 830 |  | XX LOE |  | 1 | 18 | 181 |  | 9450 | RBSE | 1802 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 104271.28
R1810-001 | LOE Crane support, fixture setupfor FY07 | 1249 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 64854.45
R1810-003 | LOE Crane support, fixture setupfor FY08 | 999 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 165923.83
R1810-004 | LOE Crane support, fixture setupfor FY09 | 718 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 192599.92
R1810-005 | LOE Field Supervision for FY07 | 1249 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 96036.83
R1810-007 | LOE Field Supervision for FY08 | 999 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 245765.14
R1810-008 | LOE Field Supervision for FY09 | 718 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 285266.98
R1810-008S | LOE Field Supervision for 2nd shft 1.0 fte | 718 |  | XX LOE |  | 1 | 18 | 185 | 2 | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 206388.38
R1810-009 | LOE Metrology sprt FY07 1.5 fte EM & 1.0 fte TB | 1249 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 150382.62
R1810-009 | LOE Metrology sprt FY07 1.5 fte EM & 1.0 fte TB | 1249 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 47449.71
R1810-011 | LOE Metrology sprt FY08 1.5 fte EM & 1.0 fte TB | 999 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 578844
R1810-011 | LOE Metrology sprt FY08 1.5 fte EM & 1.0 fte TB | 999 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 192264
R1810-012 | LOE Metrology sprt FY09 1.5 fte EM & 1.0 fte TB | 718 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 325636.63
R1810-012 | LOE Metrology sprt FY09 1.5 fte EM & 1.0 fte TB | 718 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 107612.52
R1810-013 | Misc M&S FY07 | 1249 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 19140
R1810-015 | Misc M&S FY08 | 999 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 47088
R1810-016 | Misc M&S FY09 | 718 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S0P0 |  |  | L |  |  | LOE |  |  | 57664.57
R1810-1203 | Misc Hardware | 1163 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S1P2 | 10 |  |  |  |  | LOE |  |  | 2584.38
R1810-1303 | Misc Hardware | 1206 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S1P3 | 10 |  |  |  |  | LOE |  |  | 0
R1810-1303 | Misc Hardware | 1206 |  | XX LOE |  | 1 | 18 | 185 |  | 9450 | RBSE | 1810 |  |  |  |  | S1P3 | 10 |  |  |  |  | LOE |  |  | 2571.8
R1810-2001 | Misc Hardware and hardware rework (1/2 fte loe) | 1095 |  | XX LOE |  | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S2PR | 15 |  | L | 2A |  | LOE |  |  | 12949.54
R1810-2001 | Misc Hardware and hardware rework (1/2 fte loe) | 1095 |  | XX LOE |  | 1 | 18 | 185 | 1 | 9450 | RBSE | 1810 |  |  |  | X | S2PR | 15 |  | L | 2A |  | LOE |  |  | 74964.33
REBASE1421 | Re-baseline exercise | 1322 |  | XX LOE |  | 1 | 14 | 142 |  | 9450 | HW | 1421 | 2 |  | L |  |  | 99 | M |  |  |  | LOE |  |  | 39864.32
1204-172 | Title III | 1249 |  | XX LOE |  | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | 124V | 15 |  |  |  |  | LOE |  |  | 18098.4
1802ORNLFA | ORNL Title III final machine assy | 0 |  | XX LOE |  | 7 | 74 | 750 |  | 9450 | RBSE | 7401 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 294742.07
1802ORNLFA | ORNL Title III final machine assy | 0 |  | XX LOE |  | 7 | 74 | 750 |  | 9450 | RBSE | 7401 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 12840
1802ORNLFA | ORNL Title III final machine assy | 0 |  | XX LOE |  | 7 | 74 | 750 |  | 9450 | RBSE | 7401 |  |  |  |  | A | 10 |  |  |  |  | LOE |  |  | 73799.64
211-117 | Title III | 644 |  | XX LOE |  | 2 | 21 | 211 |  | 9450 |  | 2101 | [10 empty] | LOE |  |  | 2738.08
3101-330 | Title III | 188 |  | XX LOE |  | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD3 | 14 |  |  |  |  | LOE |  |  | 9434.71
3101-456 | Title III | 242 |  | XX LOE |  | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | MD4 | 18 |  |  |  |  | LOE |  |  | 5788.44
3101-806 | Title III | 239 |  | XX LOE |  | 3 | 31 | 310 |  | 9450 |  | 3101 | F | A |  |  | VLPB | [5 empty] | LOE |  |  | 964.74
390-03 | LOE Support FY07 | 1249 |  | XX LOE |  | 3 | 39 | 390 |  | 9450 |  | 3901 | 2 | B | X |  |  |  | 1 |  |  |  | LOE |  |  | 11359.44
390-04 | LOE Support FY08 | 1000 |  | XX LOE |  | 3 | 39 | 390 |  | 9450 |  | 3901 | 2 | B | X |  |  |  | 1 |  |  |  | LOE |  |  | 29228.35
390-05 | LOE Support FY09 | 752 |  | XX LOE |  | 3 | 39 | 390 |  | 9450 |  | 3901 | 2 | B | X |  |  |  | 1 |  |  |  | LOE |  |  | 30084.7
390-06 | LOE Support FY10 | 504 |  | XX LOE |  | 3 | 39 | 390 |  | 9450 |  | 3901 | 2 | B | X |  |  |  | 1 |  |  |  | LOE |  |  | 62037.9
431-276 | Maint of C-site rectifiers | 216 |  | XX LOE |  | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  | LOE |  |  | 6763.64
431-276 | Maint of C-site rectifiers | 216 |  | XX LOE |  | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  | LOE |  |  | 9482.78
431-276 | Maint of C-site rectifiers | 216 |  | XX LOE |  | 4 | 43 | 431 |  | 9450 |  | 4301 | F |  |  |  | 431 | 10 |  |  | 43 |  | LOE |  |  | 5779.96
621-151 | LN2 - LHe Supply-Title III | 124 |  | XX LOE |  | 6 | 62 | 621 |  | 9450 |  | 6201 |  |  |  |  | 621 | [5 empty] | LOE |  |  | 7529.72
622-161 | LN2 Coil Cooling Supply-Title III | 144 |  | XX LOE |  | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 622 | [5 empty] | LOE |  |  | 7454.33
623-262 | GN2 Cryostat Cooling Supply-Title III | 527 |  | XX LOE |  | 6 | 62 | 622 |  | 9450 |  | 6201 |  |  |  |  | 623 | [5 empty] | LOE |  |  | 8177.58
714.020 | LOE Prior to assy starting | 926 |  | XX LOE |  | 7 | 74 | 742 |  | 9450 |  | 7401 | F | A |  |  |  | 10 | 1 |  |  |  | LOE |  |  | 19463.09
714.020 | LOE Prior to assy starting | 926 |  | XX LOE |  | 7 | 74 | 742 |  | 9450 |  | 7401 | F | A |  |  |  | 10 | 1 |  |  |  | LOE |  |  | 12926.85
714.030 | LOE Start of assy through thru completion | 0 |  | XX LOE |  | 7 | 74 | 742 | LOE | 9450 |  | 7401 | F | A |  |  | A | 13 | 1 |  |  |  | LOE |  |  | 562372.03
714.030 | LOE Start of assy through thru completion | 0 |  | XX LOE |  | 7 | 74 | 742 | LOE | 9450 |  | 7401 | F | A |  |  | A | 13 | 1 |  |  |  | LOE |  |  | 462049.56
714.031 | Additional supervision for 2nd shift | 0 |  | XX LOE |  | 7 | 74 | 742 | 2 | 9450 |  | 7401 | F | A |  |  | A | 13 | 1 |  |  |  | LOE |  |  | 260116.73
7401ACPWR | Prior ac pwr work reclassified as gpp |  |  | XX LOE |  | 7 | 74 | 742 |  | 9450 |  | 7401 | F | A |  |  |  | 01 | 1 |  |  |  | LOE |  |  | -308300
7501-05 | Construction Support Crew during machine assy | 0 |  | XX LOE |  | 7 | 75 | 750 |  | 9450 | EC45 | 7501 | F | A |  |  | S0P0 |  | 1 |  |  |  | LOE |  |  | 367407.19
7501-05 | Construction Support Crew during machine assy | 0 |  | XX LOE |  | 7 | 75 | 750 |  | 9450 | EC45 | 7501 | F | A |  |  | S0P0 |  | 1 |  |  |  | LOE |  |  | 593554.71
7501-06 | Construction Support Crew for 2nd shift | 0 |  | XX LOE |  | 7 | 75 | 742 | 2 | 9450 |  | 7501 | F | A |  |  | S0P0 | 13 | 1 |  |  |  | LOE |  |  | 160437.74
7501-06 | Construction Support Crew for 2nd shift | 0 |  | XX LOE |  | 7 | 75 | 742 | 2 | 9450 |  | 7501 | F | A |  |  | S0P0 | 13 | 1 |  |  |  | LOE |  |  | 285120.9
810.005 | Project Management OfficePPPL FY07 (LOE) | 1249 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | F | A |  |  |  | 05 | 1 |  |  |  | LOE |  |  | 132556.36
810.005 | Project Management OfficePPPL FY07 (LOE) | 1249 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | F | A |  |  |  | 05 | 1 |  |  |  | LOE |  |  | 89944.91
810.005 | Project Management OfficePPPL FY07 (LOE) | 1249 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | F | A |  |  |  | 05 | 1 |  |  |  | LOE |  |  | 15944.64
810.005 | Project Management OfficePPPL FY07 (LOE) | 1249 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | F | A |  |  |  | 05 | 1 |  |  |  | LOE |  |  | 5104
810.005 | Project Management OfficePPPL FY07 (LOE) | 1249 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | F | A |  |  |  | 05 | 1 |  |  |  | LOE |  |  | 3564
810.005 | Project Management OfficePPPL FY07 (LOE) | 1249 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | F | A |  |  |  | 05 | 1 |  |  |  | LOE |  |  | 26553.7
810.104X | Project Management Office ORNL FY07(LOE) | 1249 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8102 | F | A |  | X |  |  | 1 |  |  |  | LOE |  |  | 60420
810.105X | Project Management Office ORNL FY08 (LOE) | 1000 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8102 | F | A |  | X |  |  | 1 |  |  |  | LOE |  |  | 159000
810.105Z | Project Management Office ORNL FY09 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8102 | F | A | H | X |  |  | 1 |  |  |  | LOE |  |  | 160000
810.106X | Project Management Office ORNL FY10 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8102 | F | A |  | X |  |  | 1 |  |  |  | LOE |  |  | 101000
810.106Z | Project Management Office ORNL FY11 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8102 | F | A |  | X |  |  | 1 |  |  |  | LOE |  |  | 18960
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 204835.13
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 236084.75
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 82016
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 12180
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 13080
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 208223.05
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 138991.88
810.900 | Project Management Office PPPL FY08 (LOE) | 999 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 138761.77
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 210003.36
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 242455.18
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 84078.34
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 12420
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 13970
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 284345.55
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 167549.11
810.901 | Project Management Office PPPL FY09 (SA LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A | H | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 142826.5
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 108448.44
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 249691.96
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 7638
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 89828.58
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 11456
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 292837.66
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 166876.22
810.909 | Project Management Office PPPL FY10 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 147685.19
810.910 | Project Management Office PPPL FY11 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 35720.07
810.910 | Project Management Office PPPL FY11 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 82102.41
810.910 | Project Management Office PPPL FY11 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 5220
810.910 | Project Management Office PPPL FY11 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 22338.36
810.910 | Project Management Office PPPL FY11 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 4404
810.910 | Project Management Office PPPL FY11 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 96455.45
810.910 | Project Management Office PPPL FY11 (LOE) | 423 |  | XX LOE |  | 8 | 81 | 810 |  | 9450 |  | 8101 | S | A |  | X |  | 10 | 1 |  | STRO |  | LOE |  |  | 53158.15
820-004Y | RLM (WBS 2,3 &6 ) (SA LOE) | 502 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A | H | X |  | 21 | 1 |  |  |  | LOE |  |  | 148616.69
820.00004Z | Reqmnts mgt & design verification | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 20 | 1 |  |  |  | LOE |  |  | 106998.75
820.00004Z | Reqmnts mgt & design verification | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 20 | 1 |  |  |  | LOE |  |  | 41449.96
820.0004Z | RLM (WBS 13,15,17) (SA LOE) | 502 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 18 | 1 |  |  |  | LOE |  |  | 114466.7
820.004X | RLM (fabrication) (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A | H | X |  | 21 | 1 |  |  |  | LOE |  |  | 739152.77
820.004Z | Reqmnts mgt & design verification | 1249 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 19 | 1 |  |  |  | LOE |  |  | 13938.4
820.005 | RLM (WBS 4 & 5) (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | S | A |  |  |  | 22 | 1 |  |  |  | LOE |  |  | 178479.64
820.04X | Engr Management FY07 (LOE) | 1252 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 15 | 1 |  |  |  | LOE |  |  | 71782.76
820.04X | Engr Management FY07 (LOE) | 1252 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 15 | 1 |  |  |  | LOE |  |  | 71782.76
820.04Y | Engr management (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 16 | 1 |  |  |  | LOE |  |  | 21377.32
820.04Y | Engr management (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 16 | 1 |  |  |  | LOE |  |  | 510200.86
820.04Z | RLM (WBS 13,15,17) (SA LOE) | 1249 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 17 | 1 |  |  |  | LOE |  |  | 154562.92
8203FY07 | Design Integration ,& metro support | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8203 | F | A |  |  |  | 70 | 1 |  |  |  | LOE |  |  | 518654.59
8203FY07 | Design Integration ,& metro support | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8203 | F | A |  |  |  | 70 | 1 |  |  |  | LOE |  |  | 332323.99
8203FY07 | Design Integration ,& metro support | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8203 | F | A |  |  |  | 70 | 1 |  |  |  | LOE |  |  | 129663.65
8203FY08 | CAD Support (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8203 | F | A |  |  |  | 70 | 1 |  |  |  | LOE |  |  | 284649.84
8203FY08 | CAD Support (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8203 | F | A |  |  |  | 70 | 1 |  |  |  | LOE |  |  | 142324.92
8204FY07 | Systems Analysis FY07 Analysis for structure dsn | 1249 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8204 | F | A |  |  |  | 20 | 1 |  |  |  | LOE |  |  | 55753.6
8204FY08 | Systems Analysis, studies and tech assurance | 423 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8204 | F | A |  |  |  | 20 | 1 |  |  |  | LOE |  |  | 583441.27
8204FY08 | Systems Analysis, studies and tech assurance | 423 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8204 | F | A |  |  |  | 20 | 1 |  |  |  | LOE |  |  | 255493.89
8204FY08 | Systems Analysis, studies and tech assurance | 423 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8204 | F | A |  |  |  | 20 | 1 |  |  |  | LOE |  |  | 259307.23
8205FY07 | Systems Engineering Support document control | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 30 | 1 |  |  |  | LOE |  |  | 162079.56
8205FY08 | Systems Engineering Support (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 31 | 1 |  |  |  | LOE |  |  | 213487.38
8205FY08 | Systems Engineering Support (SA LOE) | 422 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 |  | 8202 | F | A |  | X |  | 31 | 1 |  |  |  | LOE |  |  | 70598.92
8210-08 | Plant Design FY08 | 423 |  | XX LOE |  | 8 | 82 |  |  | 9450 |  | 8215 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 49290.42
8210-08 | Plant Design FY08 | 423 |  | XX LOE |  | 8 | 82 |  |  | 9450 |  | 8215 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 36758.23
8210-08 | Plant Design FY08 | 423 |  | XX LOE |  | 8 | 82 |  |  | 9450 |  | 8215 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 19670.37
ECP53RBX16 | FY07 Rebaseline exercise | 1333 |  | XX LOE |  | 8 | 81 |  |  | 9450 |  | 8101 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 4435.4
ECP53RBX19 | FY07 Rebaseline exercise | 1316 |  | XX LOE |  | 8 | 82 |  |  | 9450 |  | 8202 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 29619.1
ECP53RBX23 | FY07 Rebaseline exercise | 1315 |  | XX LOE |  | 8 | 82 |  |  | 9450 |  | 8210 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 9049.2
ECP53RBX25 | FY07 Rebaseline exercise | 1333 |  | XX LOE |  | 8 | 82 |  |  | 9450 |  | 8210 |  |  |  |  | RBLX | [5 empty] | LOE |  |  | 9765
METFY08R | Support FPA Station 2 | 4 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A |  |  |  | 14 |  |  |  |  | LOE |  |  | 44955.54
METFY08R | Support FPA Station 2 | 4 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A |  |  |  | 14 |  |  |  |  | LOE |  |  | 44955.54
METFY08RX | Support FPA Station 3 | 0 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A | H |  |  | 15 |  |  |  |  | LOE |  |  | 45277.53
METFY08RX | Support FPA Station 3 | 0 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A | H |  |  | 15 |  |  |  |  | LOE |  |  | 45277.53
METFY09 | Support FPA Station 5 | 0 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A |  |  |  | 16 |  |  |  |  | LOE |  |  | 30721.6
METFY09 | Support FPA Station 5 | 0 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A |  |  |  | 16 |  |  |  |  | LOE |  |  | 30721.6
METFY10 | Support Final Machine Assy | 0 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A |  |  |  | 17 |  |  |  |  | LOE |  |  | 47081.43
METFY10 | Support Final Machine Assy | 0 |  | XX LOE |  | 8 | 82 | 820 |  | 9450 | EC45 | 8205 | F | A |  |  |  | 17 |  |  |  |  | LOE |  |  | 47081.43
R58-10 | WBS58 -FY07 Management & Integration LOE | 1248 |  | XX LOE |  | 5 | 58 | 580 |  | 9450 |  | 5801 | [10 empty] | LOE |  |  | 7039.66
R58-20 | WBS58 -FY08 Management & Integration LOE | 999 |  | XX LOE |  | 5 | 58 | 580 |  | 9450 |  | 5801 | [10 empty] | LOE |  |  | 24107.2
R58-30 | WBS58 -FY09 Management & Integration LOE | 750 |  | XX LOE |  | 5 | 58 | 580 |  | 9450 |  | 5801 | [10 empty] | LOE |  |  | 18610.8
R58-40 | WBS58 -FY10 Management & Integration LOE | 502 |  | XX LOE |  | 5 | 58 | 580 |  | 9450 |  | 5801 | [10 empty] | LOE |  |  | 19243.2