## Sheet1
|  |  | PROJECT ESTIMATE | [8 empty] | DOE Review Estimate
|  |  |  | Allocation of Contingency Allowances | [8 empty] | Contingency
| WBS | ACWP (Through 4/30/07) | ETC | Uncertainty | Schedule | Sched Mitig | Risk | Management Increment ("unknown unknowns") | Total | % of ETC | TOTAL EAC | ETC | Total | % of ETC | TOTAL EAC
12 | Vacuum Vessel | 9753 | 156 | 29.6375 |  |  | 10.4425 | 0 | 40.08 | 25.69% | 9949.08 |  |  | #DIV/0! | 9753
13 | Conventional Coils | 3226 | 3462 | 527.3565 |  |  | 175.1056 | 400 | 1102.4621 | 31.84% | 7790.4621 |  |  | #DIV/0! | 3226
14 | Modular Coils | 34196 | 6247 | 1002.0523 |  |  | 405.7351 | 200 | 1607.7874 | 25.74% | 42050.7874 |  |  | #DIV/0! | 34196
15 | Structures | 335 | 1262 | 173.2647 |  |  | 7.9662 | 150 | 331.2309 | 26.25% | 1928.2309 |  |  | #DIV/0! | 335
16 | Coil Services | 3 | 861 | 66.7872 |  |  | 225.0106 | 0 | 291.7979 | 33.89% | 1155.7979 |  |  | #DIV/0! | 3
17 | Cryostat & Base Support Structure | 431 | 784 | 111.7813 |  |  | 4.9534 | 150 | 266.7347 | 34.02% | 1481.7347 |  |  | #DIV/0! | 431
18 | Field Period Assembly | 3479 | 10104 | 1645.4569 |  | 355.2814 | 127.1874 | 500 | 2627.9257 | 26.01% | 16210.9257 |  |  | #DIV/0! | 3479
19 | Stellarator Core Mgmt & Integr | 2128 | 1620 | 127.1447 | 179.366 |  | 10.2213 | 0 | 316.7321 | 19.55% | 4064.7321 |  |  | #DIV/0! | 2128
2 | Auxiliary Systems | 348 | 241 | 34.0614 |  |  | 1.5175 | 10 | 45.5789 | 18.91% | 634.5789 |  |  | #DIV/0! | 348
3 | Diagnostics | 954 | 717 | 83.663 |  |  | 4.5258 | 75 | 163.1888 | 22.76% | 1834.1888 |  |  | #DIV/0! | 954
4 | Electrical Power Systems | 720 | 2425 | 182.33 |  |  | 52.7055 | 175 | 410.0355 | 16.91% | 3555.0355 |  |  | #DIV/0! | 720
5 | I&C Systems | 33 | 1136 | 155.8583 |  |  | 7.169 | 0 | 163.0274 | 14.35% | 1332.0274 |  |  | #DIV/0! | 33
6 | Facility Systems | 24 | 1379 | 372.2653 |  |  | 8.7037 | 0 | 380.969 | 27.63% | 1783.969 |  |  | #DIV/0! | 24
7 | Test Cell Prep & Machine Assy | 963 | 7951 | 2374.6555 |  |  | 161.6839 | 500 | 3036.3394 | 38.19% | 11950.3394 |  |  | #DIV/0! | 963
81 | Project Management | 3376 | 4342 | 375 | 1122 |  | 79 |  | 1576 | 36.3% | 9294 |  |  | #DIV/0! | 3376
82 | Project Engineering | 5248 | 5948 | 600 | 628 |  |  |  | 1228 | 20.65% | 12424 |  |  | #DIV/0! | 5248
84 | Project Physics | 470 | [6 empty] | 0 |  | 470 |  |  | #DIV/0! | 470
85 | Start-up | 0 | 764.83 | 75 |  |  |  | 200 | 275 | 35.96% | 1039.83 |  |  | #DIV/0! | 0
89 | Allocations | 1416 | 1453.77 | 100 | 417 |  |  |  | 517 | 35.56% | 3386.77 |  |  | #DIV/0! | 1416
| dcma | 75 | [8 empty] | 75 |  |  |  | 75
| Total | 67178 | 50853.6 | 8036.3147 | 2346.366 | 355.2814 | 1281.9276 | 2360 | 14379.8897 | 28.28% | 132411.4897 | 0 | 0 | #DIV/0! | 67178
Note on F6: Chris Gruber: Based on % of total Uncertainty Contingency)- see Uncertainty Results worksheets
Note on G6: Chris Gruber: Total of both Uncertainty and Risk schedule contingency cost allowance split on basis of contribution to standing army calc - see Mis Inputs sheet
Note on I6: Chris Gruber: Based on % of total risk impact by WBS -- see Risk Model worksheet