## Summary-Separate Models
Summary of Risk/Contingency Analysis Results
Base Schedule |  | 45.25 | months
Schedule Uncertainty Contingency at 90% |  | 7.9139
Risk Schedule Contingency at 90% |  | 3.6421
Total Schedule Contingency (90%) |  | 11.556 | months
Base ETC |  | 50848.68
Contingency at 90% (Std Uncertainty) |  | 7221.42 | 14.2%
Cost of Schedule Uncertainty Contingency |  | 1596.6207 | 3.14%
Cost of Schedule Risk Mitigation |  | 350.3442 | 0.689%
Total Uncertainty Contingency - 90% Confidence |  | 9168.385 | 18.03%
Risk Cost Contingency (from Risk Model) at 90% |  | 1279.1585 | 2.516%
Risk Schedule Contingency (cost of stretch) - 90% |  | 734.795 | 1.445%
Total Risk Contingency - 90% Confidence |  | 2013.9535 | 3.961%
Total Cost Contingency (90%) |  | 11182.3384 | 21.99%
ETC with Contingency (@90%) |  | 62031.0184
| Contingency Spread by Year |  | $M
| 2008 | 20% | 2.2365
| 2009 | 25% | 2.7956
| 2010 | 30% | 3.3547
| 2011 | 25% | 2.7956

## Uncertainty Results
Percentiles | Total ETC With Uncertainty Contingency | Total Schedule Duration | Schedule Mitigation Cost Adder
0% | 51641.343 | 39.7674 | 6.9786
5% | 54215.2573 | 43.2864 | 8.7
10% | 54620.0466 | 44.0702 | 24.531
15% | 54914.3828 | 44.6846 | 43.8877
20% | 55146.1662 | 45.1655 | 61.951
25% | 55347.2492 | 45.6599 | 79.3532
30% | 55536.3945 | 46.1103 | 96.9776
35% | 55720.2941 | 46.499 | 114.4499
40% | 55888.2759 | 46.9388 | 131.1814
45% | 56064.7862 | 47.3625 | 147.7954
50% | 56252.8774 | 47.7913 | 164.8932
55% | 56430.5394 | 48.3041 | 181.8274
60% | 56615.7258 | 48.807 | 199.8538
65% | 56804.8319 | 49.3463 | 218.0881
70% | 56993.1651 | 49.9468 | 237.5356
75% | 57207.3278 | 50.6028 | 257.0155
80% | 57445.2107 | 51.3275 | 283.8522
85% | 57736.2255 | 52.1607 | 313.2932
90% | 58070.1 | 53.1639 | 350.3442
95% | 58637.1368 | 54.3883 | 405.5816
100% | 60997.4406 | 58.922 | 650.4427

## Risk Results
Percentiles | Risk Cost Contingency | Risk Schedule Contingency
0% | -494.5249 | -2.1869
5% | -212.2617 | -0.40844
10% | -95.4082 | -0.29247
15% | 0 | -0.17957
20% | 67.4484 | -0.06076
25% | 110.321 | 0
30% | 144.1971 | 0
35% | 177.1719 | 0
40% | 209.1532 | 0
45% | 239.7583 | 0
50% | 270.3695 | 0
55% | 303.9739 | 0.075464
60% | 377.3899 | 0.18915
65% | 484.1366 | 0.30172
70% | 585.6303 | 0.41706
75% | 708.7711 | 0.95154
80% | 910.1531 | 1.8927
85% | 1093.8855 | 2.7443
90% | 1279.1585 | 3.6421
95% | 1532.9624 | 6.6822
100% | 3185.9468 | 14.7302
Risk Contingency Summary
@90% | Cost Risks | 1279.1585
| Cost Impact of Schedule | 734.795
| Total Risk Contingency | 2013.9535

## Contingency by Year
Major Contributors to Uncertainty Contingency
|  | Spread of Dollars by Year | [5 empty] | Weighted Contingency Spread by Year
Job | % | 2007 | 2008 | 2009 | 2010 | 2011 |  | 2007 | 2008 | 2009 | 2010 | 2011
* 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | 38.49% | 0% | 0% | 18.66% | 81.34% | 0% |  | 0% | 0% | 7.182% | 31.31% | 0%
A - Oversight and Supervision | 5.085% | 0% | 0% | 34.76% | 51.44% | 13.8% |  | 0% | 0% | 1.768% | 2.616% | 0.7018%
S0P0 - General Assy Support | 6% | 0% | 0% | 23.86% | 57.28% | 18.86% |  | 0% | 0% | 1.431% | 3.437% | 1.132%
* S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 2.049% | 0% | 0% | 100% | 0% | 0% |  | 0% | 0% | 2.049% | 0% | 0%
13P - PF Coil Fabrication | 2.018% | 0% | 59.39% | 38.87% | 1.741% | 0% |  | 0% | 1.199% | 0.7845% | 0.03513% | 0%
| 53.64% | [6 empty] | 0% | 0% | 10.38% | 37.36% | 1.834%
All Other | 46.36% | Assume spread equally with none in 2007 and extra in 2011 | [6 empty] | 11.59% | 11.59% | 11.59% | 11.59%
|  |  |  | Total Uncertainty Contingency Spead |  |  |  |  | 11.59% | 21.97% | 48.95% | 18%
|  |  |  | Uncertainty Contingency |  |  | 7571.7643 |  | 877.531 | 1663.5363 | 3706.3434 | 1362.9176
Risk Contingency Spread
| Primary contributor is Labor Rate risk, so spread as constant % of base costs | [7 empty] | 25% | 25% | 25% | 25%
|  |  |  | Risk Contingency |  |  | 1279.1585 |  | 319.7896 | 319.7896 | 319.7896 | 319.7896
|  |  |  | Schedule Contingency all in 2011 | [7 empty] | 2331.4157
|  |  |  | Total Contingency by Year |  |  | 11220.9025 |  | 1197.3207 | 1983.3259 | 4026.133 | 4014.1229
[9 empty] | 10.67% | 17.68% | 35.88% | 35.77%
[7 empty] | Conservative Projection |  | 20% | 25% | 30% | 25%
Note on B4: Chris Gruber: Contribution to Variance from Uncertainty Model Sensitivty Analysis
Note on I3: Chris Gruber: % times % by year

## Estimate Uncertainty Range
[8 empty] | updated | Estimate Uncertainty Range | [5 empty] | updated | updated | updated | updated | Percent ETC by Year
WBS2 |  |  | Job | WBS4 | Maturity | Complexity | Lookup | ETC TOTAL | Low | High | "High" cont increment (High -ETC) | relative contingency mapping | relative cont % | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011
12 | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124P - VV Personnel Access Port & Lateral sprts | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124P - VV Personnel Access Port & Lateral sprts | H | L | HL | 83.79 | 79.6005 | 92.169 | 8.379 | 9.2038 | 10.98% |  |  |  | 83.79 |  | 0% | 0% | 0% | 100% | 0%
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 125 - VV Local I&C | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 125 - VV Local I&C | H | L | HL | 34.4 | 32.68 | 37.84 | 3.44 | 3.7786 | 10.98% | 34.4 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation | H | L | HL | 220.25 | 209.2375 | 242.275 | 22.025 | 24.1932 | 10.98% |  | 104.57 | 1.12 | 114.56 |  | 0% | 47.48% | 0.5085% | 52.01% | 0%
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124T - Heater Tape for Port Stub | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124T - Heater Tape for Port Stub | H | L | HL | 20.14 | 19.133 | 22.154 | 2.014 | 2.2123 | 10.98% |  | 20.14 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124U - T/C and Heater Tape Leads | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124U - T/C and Heater Tape Leads | H | L | HL | 36.95 | 35.1025 | 40.645 | 3.695 | 4.0587 | 10.98% |  | 36.95 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124V - Flux loop junction boxes and spacer templates | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124V - Flux loop junction boxes and spacer templates | H | L | HL | 12.28 | 11.666 | 13.508 | 1.228 | 1.3489 | 10.98% | 12.28 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1250 - Job: 1250 - Vacuum Vessel Fabrication**CLOSED** |  | 1250 - Job: 1250 - Vacuum Vessel Fabrication**CLOSED** |  | FROZEN |  | FROZEN | -251.69 | -251.69 | -251.69 | 0 | 0 | 0% | -251.69 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
13 | 1302 - Job: 1302 - PF Design -KALISH | RBLX - FY07 Rebaseline Exercise | 1302 - Job: 1302 - PF Design -KALISH | RBLX - FY07 Rebaseline Exercise | FROZEN |  | FROZEN | 4.53 | 4.53 | 4.53 | 0 | 0 | 0% | 4.53 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1302 - Job: 1302 - PF Design -KALISH | - | 1302 - Job: 1302 - PF Design -KALISH | - | L | L | LL | 252.68 | 214.778 | 315.85 | 63.17 | 69.3885 | 27.46% | 39.25 | 213.43 |  |  |  | 15.53% | 84.47% | 0% | 0% | 0%
| 1352 - Job: 1352 - PF Coil Procurement-KALISH | 13P - PF Coil Fabrication | 1352 - Job: 1352 - PF Coil Procurement-KALISH | 13P - PF Coil Fabrication | L | L | LL | 1629.88 | 1385.398 | 2037.35 | 407.47 | 447.5817 | 27.46% |  | 967.97 | 633.54 | 28.37 |  | 0% | 59.39% | 38.87% | 1.741% | 0%
| 1353 - Job: 1353 - CS Structure Procurement-DAHLGREN | 132A - CS Support Structure | 1353 - Job: 1353 - CS Structure Procurement-DAHLGREN | 132A - CS Support Structure | H | L | HL | 337.33 | 320.4635 | 371.063 | 33.733 | 37.0537 | 10.98% |  |  | 78.26 | 259.07 |  | 0% | 0% | 23.2% | 76.8% | 0%
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 133 - Trim Coils | 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 133 - Trim Coils | L | L | LL | 161.9 | 137.615 | 202.375 | 40.475 | 44.4594 | 27.46% |  |  | 161.9 |  |  | 0% | 0% | 100% | 0% | 0%
| 1355 - Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 134 - TF/PF Loacl I&C | 1355 - Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 134 - TF/PF Loacl I&C | M | L | ML | 72.01 | 64.809 | 82.8115 | 10.8015 | 11.8648 | 16.48% |  | 31.66 | 38.79 | 1.56 |  | 0% | 43.97% | 53.87% | 2.166% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight | 1361 - Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight | H | M | HM | 212.76 | 191.484 | 244.674 | 31.914 | 35.0556 | 16.48% | 99.18 | 113.58 |  |  |  | 46.62% | 53.38% | 0% | 0% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | 13Y - TF Fabrication Contract | 1361 - Job: 1361 - TF Fabrication-KALISH | 13Y - TF Fabrication Contract | H | M | HM | 826.2 | 743.58 | 950.13 | 123.93 | 136.1298 | 16.48% | 165.22 | 660.98 |  |  |  | 20% | 80% | 0% | 0% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | RBLX - FY07 Rebaseline Exercise | 1361 - Job: 1361 - TF Fabrication-KALISH | RBLX - FY07 Rebaseline Exercise | FROZEN |  | FROZEN | 1.39 | 1.39 | 1.39 | 0 | 0 | 0% | 1.39 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1361 - Job: 1361 - TF Fabrication-KALISH | - | 1361 - Job: 1361 - TF Fabrication-KALISH | - | FROZEN |  | FROZEN | -38.28 | -38.28 | -38.28 | 0 | 0 | 0% | -38.28 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
14 | 1404 - Job: 1404 - MCWF R&D 1st Prod Casting**CLOSED** | - | 1404 - Job: 1404 - MCWF R&D 1st Prod Casting**CLOSED** | - | FROZEN |  | FROZEN | -35.94 | -35.94 | -35.94 | 0 | 0 | 0% | -35.94 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - | 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - | L | M | LM | 349.6 | 279.68 | 489.44 | 139.84 | 153.606 | 43.94% | 177.74 | 171.86 |  |  |  | 50.84% | 49.16% | 0% | 0% | 0%
| 1411 - Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - | 1411 - Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - | H | L | HL | -80.39 | -76.3705 | -88.429 | -8.039 | -8.8304 | 10.98% | -80.39 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications | L | M | LM | 7.79 | 6.232 | 10.906 | 3.116 | 3.4227 | 43.94% | 7.79 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDC - Blanket thermal insulation | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDC - Blanket thermal insulation | L | M | LM | 23.38 | 18.704 | 32.732 | 9.352 | 10.2726 | 43.94% | 23.38 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDE - Top level assy models/drawings | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDE - Top level assy models/drawings | L | M | LM | 76.15 | 60.92 | 106.61 | 30.46 | 33.4585 | 43.94% | 39.1 | 37.05 |  |  |  | 51.35% | 48.65% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDF - Analysis and closeout documentation | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDF - Analysis and closeout documentation | L | M | LM | 165.11 | 132.088 | 231.154 | 66.044 | 72.5454 | 43.94% |  | 165.11 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | TCCO - Type C Design Closeout | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | TCCO - Type C Design Closeout | L | M | LM | 7.43 | 5.944 | 10.402 | 2.972 | 3.2646 | 43.94% |  | 7.43 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142A - Outboard Interface | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142A - Outboard Interface | L | M | LM | 24.92 | 19.936 | 34.888 | 9.968 | 10.9493 | 43.94% | 24.92 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | - | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | - | L | M | LM | 272.96 | 218.368 | 382.144 | 109.184 | 119.9322 | 43.94% | 159.23 | 113.73 |  |  |  | 58.33% | 41.67% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142B - Outboard Interface-Bolted Joint Tests-Tension | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142B - Outboard Interface-Bolted Joint Tests-Tension | L | M | LM | 72.38 | 57.904 | 101.332 | 28.952 | 31.8021 | 43.94% | 72.38 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142C - Outboard Interface-Bolted Joint Tests-Shear | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142C - Outboard Interface-Bolted Joint Tests-Shear | L | M | LM | 88.63 | 70.904 | 124.082 | 35.452 | 38.9419 | 43.94% | 87.8 | 0.83 |  |  |  | 99.06% | 0.9365% | 0% | 0% | 0%
| 1429 - Job: 1429 - MC Interface R&D-GETTELFINGER | 142D - Outboard Interface-Friction | 1429 - Job: 1429 - MC Interface R&D-GETTELFINGER | 142D - Outboard Interface-Friction | L | M | LM | 118.16 | 94.528 | 165.424 | 47.264 | 51.9167 | 43.94% | 118.16 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142E - Inboard Interface-Design | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142E - Inboard Interface-Design | L | M | LM | 173.03 | 138.424 | 242.242 | 69.212 | 76.0253 | 43.94% | 173.03 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142F - Inboard Interface-AB/BC/AA | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142F - Inboard Interface-AB/BC/AA | L | M | LM | 93.86 | 75.088 | 131.404 | 37.544 | 41.2399 | 43.94% | 93.86 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142G - Inboard Interface-CC | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142G - Inboard Interface-CC | L | M | LM | 237.21 | 189.768 | 332.094 | 94.884 | 104.2245 | 43.94% | 140.15 | 97.06 |  |  |  | 59.08% | 40.92% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142H - Weld Access test | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142H - Weld Access test | L | M | LM | 104 | 83.2 | 145.6 | 41.6 | 45.6951 | 43.94% | 104 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142J - Overall MC Interface | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142J - Overall MC Interface | L | M | LM | 140.15 | 112.12 | 196.21 | 56.06 | 61.5786 | 43.94% | 140.15 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | TECH - Misc Tech Shop Support | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | TECH - Misc Tech Shop Support | M | M | MM | 76.91 | 65.3735 | 96.1375 | 19.2275 | 21.1203 | 27.46% |  | 76.91 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders | M | M | MM | 16.4 | 13.94 | 20.5 | 4.1 | 4.5036 | 27.46% | 16.4 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BUSH - Bushings | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BUSH - Bushings | M | M | MM | 54.19 | 46.0615 | 67.7375 | 13.5475 | 14.8811 | 27.46% | 17.71 | 36.48 |  |  |  | 32.68% | 67.32% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMS - Shims-Outboard | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMS - Shims-Outboard | M | M | MM | 138.65 | 117.8525 | 173.3125 | 34.6625 | 38.0747 | 27.46% | 83.68 | 54.97 |  |  |  | 60.35% | 39.65% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMT - Shims-Inboard | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMT - Shims-Inboard | M | M | MM | 19.26 | 16.371 | 24.075 | 4.815 | 5.289 | 27.46% | 1.93 | 17.33 |  |  |  | 10.02% | 89.98% | 0% | 0% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMU - Shims- C-C Joint | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | SHMU - Shims- C-C Joint | M | M | MM | 17.48 | 14.858 | 21.85 | 4.37 | 4.8002 | 27.46% |  |  |  | 17.48 |  | 0% | 0% | 0% | 100% | 0%
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | STUD - Studs Washers Nuts | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | STUD - Studs Washers Nuts | M | M | MM | 716.57 | 609.0845 | 895.7125 | 179.1425 | 196.7775 | 27.46% | 242.54 | 474.03 |  |  |  | 33.85% | 66.15% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1A - Station 1a/4 Casting Prep | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1A - Station 1a/4 Casting Prep | H | H | HH | 248.16 | 210.936 | 310.2 | 62.04 | 68.1473 | 27.46% | 110.74 | 137.42 |  |  |  | 44.62% | 55.38% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2 - Station 2-Winding Instl Chill Plates Tubing Bag | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2 - Station 2-Winding Instl Chill Plates Tubing Bag | H | H | HH | 578.01 | 491.3085 | 722.5125 | 144.5025 | 158.7275 | 27.46% | 276.6 | 301.41 |  |  |  | 47.85% | 52.15% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3 - Station 4-Winding Instl Chill Plates Tubing Bag | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 3 - Station 4-Winding Instl Chill Plates Tubing Bag | H | H | HH | 645.71 | 548.8535 | 807.1375 | 161.4275 | 177.3186 | 27.46% | 248.27 | 397.44 |  |  |  | 38.45% | 61.55% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5 - Station 5-VPI | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 5 - Station 5-VPI | H | H | HH | 326.53 | 277.5505 | 408.1625 | 81.6325 | 89.6685 | 27.46% | 122.88 | 203.65 |  |  |  | 37.63% | 62.37% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI | H | H | HH | 203.39 | 172.8815 | 254.2375 | 50.8475 | 55.853 | 27.46% | 73.25 | 130.14 |  |  |  | 36.01% | 63.99% | 0% | 0% | 0%
| 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | LABR - LOE Oversight & Supervision | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | LABR - LOE Oversight & Supervision | H | H | HH | 860.07 | 731.0595 | 1075.0875 | 215.0175 | 236.184 | 27.46% | 309.04 | 551.03 |  |  |  | 35.93% | 64.07% | 0% | 0% | 0%
| 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLTS - Punchlist Tech shop/RESA | 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLTS - Punchlist Tech shop/RESA | M | L | ML | 175.81 | 158.229 | 202.1815 | 26.3715 | 28.9675 | 16.48% | 40.87 | 134.94 |  |  |  | 23.25% | 76.75% | 0% | 0% | 0%
| 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians | 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians | M | L | ML | 325.25 | 292.725 | 374.0375 | 48.7875 | 53.5902 | 16.48% | 48.7 | 276.55 |  |  |  | 14.97% | 85.03% | 0% | 0% | 0%
15 | 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | - | 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | - | M | L | ML | 186.61 | 167.949 | 214.6015 | 27.9915 | 30.747 | 16.48% | 164.21 | 22.4 |  |  |  | 88% | 12% | 0% | 0% | 0%
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | - | 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | - | M | L | ML | 1075.76 | 968.184 | 1237.124 | 161.364 | 177.2488 | 16.48% |  | 402.95 | 672.81 |  |  | 0% | 37.46% | 62.54% | 0% | 0%
16 | 1601 - Job: 1601 - Coil Services Design-GORANSON | RBLX - FY07 Rebaseline Exercise | 1601 - Job: 1601 - Coil Services Design-GORANSON | RBLX - FY07 Rebaseline Exercise | H | L | HL | 6.23 | 5.9185 | 6.853 | 0.623 | 0.68433 | 10.98% | 6.23 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution | 1601 - Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution | H | L | HL | 338.72 | 321.784 | 372.592 | 33.872 | 37.2064 | 10.98% |  | 239.44 | 99.28 |  |  | 0% | 70.69% | 29.31% | 0% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 162 - 162 - Electrical Leads | 1601 - Job: 1601 - Coil Services Design-GORANSON | 162 - 162 - Electrical Leads | H | L | HL | 478.75 | 454.8125 | 526.625 | 47.875 | 52.5879 | 10.98% |  | 83.9 | 235.06 | 159.79 |  | 0% | 17.52% | 49.1% | 33.38% | 0%
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 163 - 163 - Coil Protection System | 1601 - Job: 1601 - Coil Services Design-GORANSON | 163 - 163 - Coil Protection System | H | L | HL | 38.15 | 36.2425 | 41.965 | 3.815 | 4.1906 | 10.98% |  |  | 38.15 |  |  | 0% | 0% | 100% | 0% | 0%
17 | 1701 - Job: 1701 - Cryostat Design-GETTLEFINGER | - | 1701 - Job: 1701 - Cryostat Design-GETTLEFINGER | - | L | M | LM | 206.97 | 165.576 | 289.758 | 82.788 | 90.9377 | 43.94% |  |  | 206.97 |  |  | 0% | 0% | 100% | 0% | 0%
| 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | - | 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | - | M | L | ML | 163.47 | 147.123 | 187.9905 | 24.5205 | 26.9343 | 16.48% |  | 163.47 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1751 - Job: 1751 - Cryostat Procurement-GETTLEFINGER | - | 1751 - Job: 1751 - Cryostat Procurement-GETTLEFINGER | - | H | L | HL | 324.85 | 308.6075 | 357.335 | 32.485 | 35.6829 | 10.98% |  |  |  | 324.85 |  | 0% | 0% | 0% | 100% | 0%
| 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 172 - 172 - Base Support Structure | 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 172 - 172 - Base Support Structure | M | L | ML | 89.65 | 80.685 | 103.0975 | 13.4475 | 14.7713 | 16.48% |  | 61.39 | 28.26 |  |  | 0% | 68.48% | 31.52% | 0% | 0%
18 | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | H | M | HM | 1988.22 | 1789.398 | 2286.453 | 298.233 | 327.5913 | 16.48% | 252.65 | 789.76 | 857.93 | 87.88 |  | 12.71% | 39.72% | 43.15% | 4.42% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 2.00 - Station 2-Modular Coil Sub- Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 2.00 - Station 2-Modular Coil Sub- Assembly | L | L | LL | 0 | 0 | 0 | 0 | 0 | #DIV/0! | [5 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.00 - Station 3-Modular Coil to VVSA Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.00 - Station 3-Modular Coil to VVSA Assembly | M | L | ML | 122.11 | 109.899 | 140.4265 | 18.3165 | 20.1196 | 16.48% | 97.38 | 24.73 |  |  |  | 79.75% | 20.25% | 0% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 5.00 - Station 5-Final Field Period Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 5.00 - Station 5-Final Field Period Assembly | M | L | ML | 186.12 | 167.508 | 214.038 | 27.918 | 30.6663 | 16.48% | 33.37 | 152.75 |  |  |  | 17.93% | 82.07% | 0% | 0% | 0%
| 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 6.00 - 6.00-Final Machine Assembly | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 6.00 - 6.00-Final Machine Assembly | L | M | LM | 213.63 | 170.904 | 299.082 | 85.452 | 93.864 | 43.94% |  | 138.16 | 75.47 |  |  | 0% | 64.67% | 35.33% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1.00 - 1.00-VV Prep Station | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1.00 - 1.00-VV Prep Station | M | M | MM | 17 | 14.45 | 21.25 | 4.25 | 4.6684 | 27.46% |  | 9.18 | 7.82 |  |  | 0% | 54% | 46% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 2.00 - Station 2-Modular Coil Sub- Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 2.00 - Station 2-Modular Coil Sub- Assembly | M | M | MM | 25.66 | 21.811 | 32.075 | 6.415 | 7.0465 | 27.46% | 25.66 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 3.00 - Station 3-Modular Coil to VVSA Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 3.00 - Station 3-Modular Coil to VVSA Assembly | M | M | MM | 51.5 | 43.775 | 64.375 | 12.875 | 14.1424 | 27.46% | 22.73 | 28.77 |  |  |  | 44.14% | 55.86% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 5.00 - Station 5-Final Field Period Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 5.00 - Station 5-Final Field Period Assembly | M | M | MM | 112.63 | 95.7355 | 140.7875 | 28.1575 | 30.9294 | 27.46% |  | 112.63 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 6.00 - 6.00-Final Machine Assembly | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 6.00 - 6.00-Final Machine Assembly | M | M | MM | 131.5 | 111.775 | 164.375 | 32.875 | 36.1112 | 27.46% |  | 129.31 | 2.19 |  |  | 0% | 98.33% | 1.665% | 0% | 0%
| 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | - | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | - | M | M | MM | 176.47 | 149.9995 | 220.5875 | 44.1175 | 48.4605 | 27.46% | 43.5 | 102.6 | 30.37 |  |  | 24.65% | 58.14% | 17.21% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General Assy Support | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General Assy Support | H | M | HM | 2922.26 | 2630.034 | 3360.599 | 438.339 | 481.4895 | 16.48% | 377.86 | 1229.89 | 1149.69 | 164.82 |  | 12.93% | 42.09% | 39.34% | 5.64% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | H | M | HM | 131.58 | 118.422 | 151.317 | 19.737 | 21.6799 | 16.48% | 96.33 | 35.25 |  |  |  | 73.21% | 26.79% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | H | M | HM | 135.96 | 122.364 | 156.354 | 20.394 | 22.4016 | 16.48% | 70.56 | 65.4 |  |  |  | 51.9% | 48.1% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | H | M | HM | 209.55 | 188.595 | 240.9825 | 31.4325 | 34.5267 | 16.48% | 143.14 | 66.41 |  |  |  | 68.31% | 31.69% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | H | M | HM | 31.33 | 28.197 | 36.0295 | 4.6995 | 5.1621 | 16.48% |  |  | 31.33 |  |  | 0% | 0% | 100% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | L | H | LH | 532.95 | 373.065 | 852.72 | 319.77 | 351.2485 | 65.91% | 480.88 | 52.07 |  |  |  | 90.23% | 9.77% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PX - Setup | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PX - Setup | L | H | LH | 100.46 | 70.322 | 160.736 | 60.276 | 66.2096 | 65.91% | 77.06 | 23.4 |  |  |  | 76.71% | 23.29% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | L | H | LH | 169.36 | 118.552 | 270.976 | 101.616 | 111.6192 | 65.91% | 20.27 | 118.62 | 30.47 |  |  | 11.97% | 70.04% | 17.99% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P1 - Station 2-MC Sub Assy A1-B1-C1 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P1 - Station 2-MC Sub Assy A1-B1-C1 | L | H | LH | 159.82 | 111.874 | 255.712 | 95.892 | 105.3317 | 65.91% |  | 159.82 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PZ - Station 2 MC Sub Assy A2-B2-C2 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PZ - Station 2 MC Sub Assy A2-B2-C2 | L | H | LH | 95.33 | 66.731 | 152.528 | 57.198 | 62.8286 | 65.91% |  | 95.33 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P2 - Station 2-Modular Coil Subassembly-FP#2 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P2 - Station 2-Modular Coil Subassembly-FP#2 | L | H | LH | 279.78 | 195.846 | 447.648 | 167.868 | 184.3931 | 65.91% |  | 190.5 | 89.28 |  |  | 0% | 68.09% | 31.91% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P3 - Station 2-Modular Coil Subassembly-FP#3 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P3 - Station 2-Modular Coil Subassembly-FP#3 | L | H | LH | 285.31 | 199.717 | 456.496 | 171.186 | 188.0377 | 65.91% |  |  | 285.31 |  |  | 0% | 0% | 100% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | L | H | LH | 181.16 | 126.812 | 289.856 | 108.696 | 119.3961 | 65.91% |  | 181.16 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | L | H | LH | 166.85 | 116.795 | 266.96 | 100.11 | 109.9649 | 65.91% |  | 135.63 | 31.22 |  |  | 0% | 81.29% | 18.71% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | L | H | LH | 171.08 | 119.756 | 273.728 | 102.648 | 112.7528 | 65.91% |  |  | 171.08 |  |  | 0% | 0% | 100% | 0% | 0%
| 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | L | H | LH | 172.73 | 120.911 | 276.368 | 103.638 | 113.8402 | 65.91% |  |  | 172.73 |  |  | 0% | 0% | 100% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | L | M | LM | 223.18 | 178.544 | 312.452 | 89.272 | 98.06 | 43.94% |  | 223.18 |  |  |  | 0% | 100% | 0% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | L | M | LM | 362.82 | 290.256 | 507.948 | 145.128 | 159.4145 | 43.94% |  |  | 362.82 |  |  | 0% | 0% | 100% | 0% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | L | M | LM | 373 | 298.4 | 522.2 | 149.2 | 163.8874 | 43.94% |  |  | 364.47 | 8.53 |  | 0% | 0% | 97.71% | 2.287% | 0%
| 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | L | M | LM | 375.54 | 300.432 | 525.756 | 150.216 | 165.0034 | 43.94% |  |  | 289.77 | 85.77 |  | 0% | 0% | 77.16% | 22.84% | 0%
19 | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 191 - 191 - Stellarator Core Management & Oversight | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 191 - 191 - Stellarator Core Management & Oversight | H | L | HL | 831.33 | 789.7635 | 914.463 | 83.133 | 91.3167 | 10.98% | 77.38 | 208.45 | 221.09 | 229.03 | 95.38 | 9.308% | 25.07% | 26.59% | 27.55% | 11.47%
| 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 192 - 192 - Stellarator Core Integration & Analysis | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 192 - 192 - Stellarator Core Integration & Analysis | H | L | HL | 788.4 | 748.98 | 867.24 | 78.84 | 86.6011 | 10.98% | 84.18 | 199.92 | 210.95 | 219.02 | 74.33 | 10.68% | 25.36% | 26.76% | 27.78% | 9.428%
21 | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | - | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | - | L | L | LL | 68.48 | 58.208 | 85.6 | 17.12 | 18.8053 | 27.46% |  |  | 12.55 | 55.93 |  | 0% | 0% | 18.33% | 81.67% | 0%
22 | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - | M | L | ML | 172 | 154.8 | 197.8 | 25.8 | 28.3398 | 16.48% |  |  | 70 | 102 |  | 0% | 0% | 40.7% | 59.3% | 0%
31 | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD3 - Rogowski Coils | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD3 - Rogowski Coils | H | L | HL | 97.61 | 92.7295 | 107.371 | 9.761 | 10.7219 | 10.98% | 77.43 | 20.18 |  |  |  | 79.33% | 20.67% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD4 - TF and PF Co-wound Loops | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD4 - TF and PF Co-wound Loops | H | L | HL | 74.54 | 70.813 | 81.994 | 7.454 | 8.1878 | 10.98% | 5.84 | 68.7 |  |  |  | 7.835% | 92.17% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads | H | L | HL | 47.38 | 45.011 | 52.118 | 4.738 | 5.2044 | 10.98% | 43.49 | 3.89 |  |  |  | 91.79% | 8.21% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124V - Flux loop junction boxes and spacer templates | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124V - Flux loop junction boxes and spacer templates | H | L | HL | 56.79 | 53.9505 | 62.469 | 5.679 | 6.238 | 10.98% | 56.79 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | VLPB - Voltage Loops & Protective Boxes | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | VLPB - Voltage Loops & Protective Boxes | H | L | HL | 14.29 | 13.5755 | 15.719 | 1.429 | 1.5697 | 10.98% |  | 14.29 |  |  |  | 0% | 100% | 0% | 0% | 0%
36 | 3601 - Job: 3601 - Edge Divertor Diagnostics-STRATTON | - | 3601 - Job: 3601 - Edge Divertor Diagnostics-STRATTON | - | H | L | HL | 30.9 | 29.355 | 33.99 | 3.09 | 3.3942 | 10.98% |  |  |  | 30.9 |  | 0% | 0% | 0% | 100% | 0%
38 | 3801 - Job: 3801 - Electron Beam Mapping-STRATTON | - | 3801 - Job: 3801 - Electron Beam Mapping-STRATTON | - | M | M | MM | 262.97 | 223.5245 | 328.7125 | 65.7425 | 72.2143 | 27.46% |  |  | 101.31 | 161.66 |  | 0% | 0% | 38.53% | 61.47% | 0%
39 | 3901 - Job: 3901 - Diagnostics sys Integration-STRATTON | - | 3901 - Job: 3901 - Diagnostics sys Integration-STRATTON | - | H | L | HL | 132.71 | 126.0745 | 145.981 | 13.271 | 14.5774 | 10.98% | 11.36 | 29.23 | 30.08 | 62.04 |  | 8.56% | 22.03% | 22.67% | 46.75% | 0%
41 | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | - | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | - | FROZEN |  | FROZEN | -104.1 | -104.1 | -104.1 | 0 | 0 | 0% | -104.1 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems | H | L | HL | 123.69 | 117.5055 | 136.059 | 12.369 | 13.5866 | 10.98% |  |  | 49.62 | 74.07 |  | 0% | 0% | 40.12% | 59.88% | 0%
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 412 - 412 - Experimental AC Power Systems | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 412 - 412 - Experimental AC Power Systems | H | L | HL | 34.87 | 33.1265 | 38.357 | 3.487 | 3.8303 | 10.98% |  |  | 7.17 | 27.7 |  | 0% | 0% | 20.56% | 79.44% | 0%
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems | 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems | H | L | HL | 602.83 | 572.6885 | 663.113 | 60.283 | 66.2173 | 10.98% |  | 10.99 | 273.79 | 318.05 |  | 0% | 1.823% | 45.42% | 52.76% | 0%
44 | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks | M | L | ML | 481.68 | 433.512 | 553.932 | 72.252 | 79.3646 | 16.48% |  |  | 190.27 | 291.41 |  | 0% | 0% | 39.5% | 60.5% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 442 - 442 - Kirk Key Interlocks | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 442 - 442 - Kirk Key Interlocks | M | L | ML | 85.44 | 76.896 | 98.256 | 12.816 | 14.0776 | 16.48% |  |  |  | 85.44 |  | 0% | 0% | 0% | 100% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 443 - 443 - Real Time Control Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 443 - 443 - Real Time Control Systems | M | L | ML | 14.77 | 13.293 | 16.9855 | 2.2155 | 2.4336 | 16.48% |  |  |  | 14.77 |  | 0% | 0% | 0% | 100% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 444 - 444 - Instrument Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 444 - 444 - Instrument Systems | M | L | ML | 219.85 | 197.865 | 252.8275 | 32.9775 | 36.2238 | 16.48% |  |  | 44.41 | 175.44 |  | 0% | 0% | 20.2% | 79.8% | 0%
| 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 445 - 445 - Coil Protection Systems | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 445 - 445 - Coil Protection Systems | M | L | ML | 282.55 | 254.295 | 324.9325 | 42.3825 | 46.5547 | 16.48% |  |  | 79.43 | 203.12 |  | 0% | 0% | 28.11% | 71.89% | 0%
45 | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces | H | L | HL | 215.14 | 204.383 | 236.654 | 21.514 | 23.6319 | 10.98% |  |  | 214.75 | 0.39 |  | 0% | 0% | 99.82% | 0.1813% | 0%
| 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452 - 452 - Electrical Systems Support | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452 - 452 - Electrical Systems Support | H | L | HL | 199.07 | 189.1165 | 218.977 | 19.907 | 21.8667 | 10.98% |  |  | 105.37 | 93.7 |  | 0% | 0% | 52.93% | 47.07% | 0%
| 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453 - 453 - System Testing (PTP's) | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453 - 453 - System Testing (PTP's) | H | L | HL | 268.9 | 255.455 | 295.79 | 26.89 | 29.5371 | 10.98% |  |  | 35.47 | 180.05 | 53.38 | 0% | 0% | 13.19% | 66.96% | 19.85%
51 | 5101 - Job: 5101 - Network and Fiber Infrastruct-SICHTA | - | 5101 - Job: 5101 - Network and Fiber Infrastruct-SICHTA | - | M | L | ML | 150.61 | 135.549 | 173.2015 | 22.5915 | 24.8154 | 16.48% |  |  | 7.33 | 143.28 |  | 0% | 0% | 4.867% | 95.13% | 0%
52 | 5201 - Job: 5201 - I&C Systems-SICHTA | - | 5201 - Job: 5201 - I&C Systems-SICHTA | - | M | L | ML | 196.68 | 177.012 | 226.182 | 29.502 | 32.4062 | 16.48% |  |  | 81.27 | 115.41 |  | 0% | 0% | 41.32% | 58.68% | 0%
53 | 5301 - Job: 5301 - Data Acquisition-SICHTA | - | 5301 - Job: 5301 - Data Acquisition-SICHTA | - | M | L | ML | 164.19 | 147.771 | 188.8185 | 24.6285 | 27.053 | 16.48% |  |  | 50.6 | 113.59 |  | 0% | 0% | 30.82% | 69.18% | 0%
54 | 5401 - Job: 5401 - Facility Timing & Synchron.-SICHTA | - | 5401 - Job: 5401 - Facility Timing & Synchron.-SICHTA | - | M | M | MM | 204.82 | 174.097 | 256.025 | 51.205 | 56.2457 | 27.46% |  |  | 11.5 | 193.32 |  | 0% | 0% | 5.615% | 94.39% | 0%
55 | 5501 - Job: 5501 - Real Time Control System-SICHTA | - | 5501 - Job: 5501 - Real Time Control System-SICHTA | - | M | L | ML | 128.84 | 115.956 | 148.166 | 19.326 | 21.2285 | 16.48% |  |  | 16.74 | 112.1 |  | 0% | 0% | 12.99% | 87.01% | 0%
56 | 5601 - Job: 5601 - Central Safety &Interlock Sys-SICHTA | - | 5601 - Job: 5601 - Central Safety &Interlock Sys-SICHTA | - | L | M | LM | 221.92 | 177.536 | 310.688 | 88.768 | 97.5064 | 43.94% |  |  | 11.6 | 210.32 |  | 0% | 0% | 5.227% | 94.77% | 0%
58 | 5801 - Job: 5801 - Central I&C Integr& Oversight-SICHTA | - | 5801 - Job: 5801 - Central I&C Integr& Oversight-SICHTA | - | H | L | HL | 68.99 | 65.5405 | 75.889 | 6.899 | 7.5781 | 10.98% | 6.97 | 24.17 | 18.61 | 19.24 |  | 10.1% | 35.03% | 26.97% | 27.89% | 0%
61 | 6101 - Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System | 6101 - Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System | L | L | LL | 46.4 | 39.44 | 58 | 11.6 | 12.7419 | 27.46% |  |  | 46.4 |  |  | 0% | 0% | 100% | 0% | 0%
62 | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 621 - 621 - LN2-LHe Supply System | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 621 - 621 - LN2-LHe Supply System | L | M | LM | 87.58 | 70.064 | 122.612 | 35.032 | 38.4806 | 43.94% |  |  | 19.5 | 68.08 |  | 0% | 0% | 22.27% | 77.73% | 0%
| 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 622 - 622 - LN2 Coil Cooling Supply | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 622 - 622 - LN2 Coil Cooling Supply | L | M | LM | 88.14 | 70.512 | 123.396 | 35.256 | 38.7266 | 43.94% |  |  | 36.3 | 51.84 |  | 0% | 0% | 41.18% | 58.82% | 0%
| 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 623 - 623 - GN2 Cryostat Cooling System | 6201 - Job: 6201 - Cryogenic Syst-GETTELFINGER | 623 - 623 - GN2 Cryostat Cooling System | L | M | LM | 478.85 | 383.08 | 670.39 | 191.54 | 210.3954 | 43.94% |  |  | 214.87 | 263.98 |  | 0% | 0% | 44.87% | 55.13% | 0%
63 | 6301 - Job: 6301 - Utility Systems-DUDEK | - | 6301 - Job: 6301 - Utility Systems-DUDEK | - | L | L | LL | 104.87 | 89.1395 | 131.0875 | 26.2175 | 28.7984 | 27.46% |  |  | 104.87 |  |  | 0% | 0% | 100% | 0% | 0%
64 | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | - | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | - | L | M | LM | 573.4 | 458.72 | 802.76 | 229.36 | 251.9384 | 43.94% |  |  | 106.99 | 466.41 |  | 0% | 0% | 18.66% | 81.34% | 0%
73 | 7301 - Job: 7301 - Platform Design & Fab-PERRY | - | 7301 - Job: 7301 - Platform Design & Fab-PERRY | - | L | L | LL | 204.12 | 173.502 | 255.15 | 51.03 | 56.0534 | 27.46% | 2.43 | 4.96 | 196.73 |  |  | 1.19% | 2.43% | 96.38% | 0% | 0%
74 | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | A - Oversight and Supervision | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | A - Oversight and Supervision | L | M | LM | 1665.91 | 1332.728 | 2332.274 | 666.364 | 731.9615 | 43.94% |  |  | 579.05 | 856.96 | 229.9 | 0% | 0% | 34.76% | 51.44% | 13.8%
| 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - | FROZEN |  | FROZEN | -249.43 | -249.43 | -249.43 | 0 | 0 | 0% | -308.3 | 22.75 | 36.12 |  |  | 123.6% | -9.121% | -14.48% | 0% | 0%
75 | 7501 - Job: 7501 - Construction Support Crew-PERRY | S0P0 - General Assy Support | 7501 - Job: 7501 - Construction Support Crew-PERRY | S0P0 - General Assy Support | L | M | LM | 1406.52 | 1125.216 | 1969.128 | 562.608 | 617.9917 | 43.94% |  |  | 335.57 | 805.63 | 265.32 | 0% | 0% | 23.86% | 57.28% | 18.86%
| 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | - | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | - | L | M | LM | 4511.85 | 3609.48 | 6316.59 | 1804.74 | 1982.4004 | 43.94% |  |  | 1668.05 | 2205.4 | 638.4 | 0% | 0% | 36.97% | 48.88% | 14.15%
76 | 7601 - Job: 7601 - Tooling Design & Fabrication-PERRY | - | 7601 - Job: 7601 - Tooling Design & Fabrication-PERRY | - | L | L | LL | 412.55 | 350.6675 | 515.6875 | 103.1375 | 113.2905 | 27.46% |  |  | 207.46 | 205.09 |  | 0% | 0% | 50.29% | 49.71% | 0%
81 | 8101 - Job: 8101 - Project Management & Control-NEILSON | RBLX - FY07 Rebaseline Exercise | 8101 - Job: 8101 - Project Management & Control-NEILSON | RBLX - FY07 Rebaseline Exercise | FROZEN |  | FROZEN | 4.44 | 4.44 | 4.44 | 0 | 0 | 0% | 4.44 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 8101 - Job: 8101 - Project Management & Control-NEILSON | - | 8101 - Job: 8101 - Project Management & Control-NEILSON | - | H | L | HL | 3839.35 | 3647.3825 | 4223.285 | 383.935 | 421.7299 | 10.98% | 273.67 | 1034.17 | 1157.65 | 1074.46 | 299.4 | 7.128% | 26.94% | 30.15% | 27.99% | 7.798%
| 8102 - Job: 8102 - NCSX MIE Management ORNL-LYON | - | 8102 - Job: 8102 - NCSX MIE Management ORNL-LYON | - | H | L | HL | 499.38 | 474.411 | 549.318 | 49.938 | 54.8539 | 10.98% | 60.42 | 159 | 159.36 | 101.64 | 18.96 | 12.1% | 31.84% | 31.91% | 20.35% | 3.797%
82 | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | RBLX - FY07 Rebaseline Exercise | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | RBLX - FY07 Rebaseline Exercise | FROZEN |  | FROZEN | 29.62 | 29.62 | 29.62 | 0 | 0 | 0% | 29.62 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 8202 - Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | - | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | - | H | L | HL | 2618.96 | 2488.012 | 2880.856 | 261.896 | 287.6773 | 10.98% | 446.73 | 665.03 | 662.58 | 659.92 | 184.7 | 17.06% | 25.39% | 25.3% | 25.2% | 7.052%
| 8203 - Job: 8203 - Design Integration-BROWN | - | 8203 - Job: 8203 - Design Integration-BROWN | - | M | M | MM | 1407.63 | 1196.4855 | 1759.5375 | 351.9075 | 386.5496 | 27.46% | 159.92 | 377.18 | 375.67 | 374.16 | 120.7 | 11.36% | 26.8% | 26.69% | 26.58% | 8.575%
| 8204 - Job: 8204 - Systems Analysis-BROOKS | - | 8204 - Job: 8204 - Systems Analysis-BROOKS | - | M | M | MM | 1153.99 | 980.8915 | 1442.4875 | 288.4975 | 316.8975 | 27.46% | 180.66 | 294.59 | 293.41 | 292.24 | 93.09 | 15.66% | 25.53% | 25.43% | 25.32% | 8.067%
| 8205 - Job: 8205 - Dimensional Control Coordin-ELLIS | - | 8205 - Job: 8205 - Dimensional Control Coordin-ELLIS | - | L | H | LH | 596.86 | 417.802 | 954.976 | 358.116 | 393.3693 | 65.91% | 101.71 | 265.77 | 161.84 | 56.01 | 11.53 | 17.04% | 44.53% | 27.12% | 9.384% | 1.932%
| 8210 - Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise | 8210 - Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise | FROZEN |  | FROZEN | 18.81 | 18.81 | 18.81 | 0 | 0 | 0% | 18.81 |  |  |  |  | 100% | 0% | 0% | 0% | 0%
| 8215 - Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise | 8215 - Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise | FROZEN |  | FROZEN | 120.75 | 120.75 | 120.75 | 0 | 0 | 0% | 15.03 | 32 | 31.87 | 31.74 | 10.11 | 12.45% | 26.5% | 26.39% | 26.29% | 8.373%
85 | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | - | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | - | H | L | HL | 418.83 | 397.8885 | 460.713 | 41.883 | 46.006 | 10.98% |  |  |  |  | 418.83 | 0% | 0% | 0% | 0% | 100%
| 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | PROC - Startup Documentation | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | PROC - Startup Documentation | H | L | HL | 346 | 328.7 | 380.6 | 34.6 | 38.0061 | 10.98% |  |  | 275.78 | 70.22 |  | 0% | 0% | 79.71% | 20.29% | 0%
89 | 8998 - Job: 8998 - Allocations-STRYKOWSKY | - | 8998 - Job: 8998 - Allocations-STRYKOWSKY | - | H | L | HL | 1453.77 | 1381.0815 | 1599.147 | 145.377 | 159.6881 | 10.98% | 144.04 | 384.38 | 406.23 | 430.8 | 88.32 | 9.908% | 26.44% | 27.94% | 29.63% | 6.075%
[6 empty] | ETC= |  | 50848.68 | 44071.517 | 63349.124 | 12500.444 | 13731 |  | 6204.6 | 14392.4 | 15066.3 | 12583.03 | 2602.35 | 12.2% | 28.3% | 29.63% | 24.75% | 5.118% | 100%
[6 empty] | Cost thru 4/30/07= |  | 67306 | -13.33% | 24.58% |  |  |  | 50848.68
[6 empty] | EAC= |  | 118154.68 |  | 63349.124
[10 empty] | total contingency derived from the monteo carlo analysis plus our increment= |  | 13731
Note on F2: Christopher O. Gruber: Enter L, M or H
Note on G2: Christopher O. Gruber: Enter L, M or H

## Schedule Ranges
NCSX Schedule Uncertainty Model
Duration Range
Schedule Activity |  | Base Duration (mos) on Critical Path | Estimate Uncertainty | Low | High | Adjusted High | Schedule Calc | Schedule Duration | Mitigation Cost Adder
CP and Near CP Activities
Job 1421 - Modular Coil Interface Design |  | 4.43 | LM | 3.544 | 6.202 | 6.202 | 0 | 0
Jobs 1806/1802-Field Period Assy station 2 specs, dwgs,procedures,training,prep. |  | 1.42 | HM | 1.278 | 1.633 | 1.633 | 0 | 0
Job -1810 Field Period Assembly Stations 1,2,3
| Station 2 MC Sub-assy A1/B1/C1 and A2/B2/C2 (in parallel) | 6.76 | LH | 4.732 | 10.816 | 6.8 | 0 | 0 | 0
| Station 3 Assemble Mod Coils and VVSA FP#1 | 4.5 | LH | 3.15 | 7.2 | 4.5 | 0 | 0 | 0
Job - 1815 Field Period Assembly Station 5 | [8 empty] | 0
| Station 5 Final Assembly FP#3 | 8.66 | LM | 6.928 | 12.124 | 8.7 | 0 | 0 | 0
Job 7503 Final Machine Assembly (Station 6) |  | 18.48 | LM | 14.784 | 25.872 | 25.872 | 0 | 0
Job 8501 - Integrated System Testing |  | 1 | HL | 0.95 | 1.1 | 1.1 | 0 | 0
|  | 45.25 |  | 35.366 | 64.947 | 54.807 |  | 0 | 0
| Estimated Cost per month for Schedule Stretch | 201.75 | thousand
Note on G9: Chris Gruber: assumes increase accommodated by 2nd shift with added cost
Note on G10: Chris Gruber: assumes increase accommodated by 2nd shift with added cost
Note on H6: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H7: Chris Gruber: Independent of Estimate Uncertainty
Note on H9: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H10: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on G13: Chris Gruber: Already worked on 2 shifts so no ability to lessen impact
Note on H13: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on G12: Chris Gruber: assumes increase accommodated by 2nd shift with added cost
Note on H12: Chris Gruber: 90% Correlation with Estimate Probability Profile

## Risk Model
NCSX Risk Register
[8 empty] | Cost Impact ($k) |  | Schedule Impact (mos)
No. | Job | Risk Description | Mitigation Plan | Likelihood of Occurrence a | Consequences | Risk Class | Basis of Estimate | Low CI | High CI | Low SI | High SI | Cost Pr | Sched Pr | Pr of Occurrence | Cost Impact | Schedule Impact
1 | 1354 7503 | Additional trim coils may be required to suppress field errors from n>1 modes | Analysis being performed to firm up requirements | U | Marginal | Low | Costs could more than double the present estimate | 200 | 400 | 0 | 0 | 0 |  | 0 | 0 | 0
2 | 1361 | TF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil already procured. Ample float in schedule to avoid critical path impact. | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 15 | 35 | 0 | 0 | 0 |  | 0 | 0 | 0
3 | 1352 | PF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil will be procured in advance and available to wind a new coil if required. Float in schedule appears adequate to avoid critical path impact. | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 15 | 35 | 0 | 0 | 0 |  | 0 | 0 | 0
4 | 1421 | Modular coil interface design needs to change significantly from the baseline for unforeseen technical reasons | Task forces formed to expedite resolution of feasibility issues. Development activities are underway. | VU | Critical | Moderate | Design of the MC interface is on the critical path. Potential impacts include [1] additional design and development (4 engineers for 1-2 months) plus $100K M&S and [2] a change in the cost of field period and final assembly to a change in the design (+/- | -100 | 600 | 1 | 2 | 0 | 0 | 0 | 0 | 0
5 | 1421 | As a result of the development trials for weld distortion, the welding time increases significantly above present allowance | Welding time estimates consistent with time requirements for first R&D article which appeared to have very low distortion. Risk goes away at conclusion of ongoing weld R&D. | U | Significant | Moderate | Nominal welding time may double. Estimate based on $300K/mo for FPA activities. | 0 | 600 | 0 | 2 | 0 | 0 | 0 | 0 | 0
6 | 1451 | Damage or loss of modular coil during VPI or testing requiring the conductor to be stripped off and re-wound | Continue to use same rigorous process used for first 12 coils during which there were no fabrication mihaps requiring re-winding a coil | U | Significant | Moderate | ~$35K in materials; ~$380K in labor. 7.5 months to do work with the potential for a 2 month impact on the critical path. | 400 | 450 | 0 | 2 | 0 | 0 | 0 | 0 | 0
7 | 1451 | Failure of major piece of winding equipment (e.g., motor, gear box, etc.) resulting in extended downtime in a winding station | Use three remaining winding stations to continue MC fabrication while fourth station is being repaired | U | Negligible | Low | ~$10K for equipment plus repair costs | 10 | 30 | 0 | 0 | 0 |  | 0 | 0 | 0
8 | 1810 7503 | "Back office" support for FPA and final assembly becomes a chronic bottleneck, stretching out the time required to complete assembly operations | Additional support budgeted for Brown, Brooks, and Ellis providing "2 deep" back office support. Should be available to mitigate peak demands once training in key skills is completed. | VU | Significant | Low | Estimated impact is <2 months on the critical path. Cost impact covers up to 2 months of FPA/final assembly. | 0 | 600 | 0 | 2 | 0 | 0 | 0 | 0 | 0
9 | 1810 | Modular coil damaged during assembly requiring significant rework to coil | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood | VU | Negligible | Low | Nominally repaired with a 2-man crew within 2 weeks | 10 | 20 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
10 | 1810 | VV surface component (coolant tube, flux loop, or TC) damaged during FPA requiring significant rework | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood | VU | Negligible | Low | Nominally repaired with a 2-man crew within 2 weeks | 10 | 20 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
11 | 1810 | Unacceptable distortion in a field period when welding modular coil shims requiring | Likelihood of occurrence is very unlikely as a result of extensive welding R&D and careful monitoring during welding. | VU | Marginal | Low | Cut apart and re-weld two coils back together. Nominally a 2.5-man crew in 12 weeks. | 25 | 35 | 0.75 | 1.25 | 0 | 0 | 0 | 0 | 0
12 | 1810 | Field period damaged during loading, transport, or unloading from TFTR TC to NCSX TC | Extreme care will be taken when transporting a field period. Additonal reviews including external reviewers will be performed. | NC | Crisis | Low | High impact-low probability event not covered by contingency | [6 empty] | 0 | 0 | 0
13 | 1815 | Multiple vacuum leaks during initial pumpdown | Welds will be leak checked during FPA when leaks can be addressed without significantly impacting the critical path. Likelihood of many leaks appearing during initial pumpdown is considered extremely unlikely with this mitigation plan. | NC | Marginal | Low | Impact of having only a few leaks is covered in estimate uncertainty with present mitigation plan | [6 empty] | 0 | 0 | 0
14 | 7503 | Insulation on TF/PF coil fails during initial cooldown and testing requiring in situ repair | Ist of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . Ring | VU | Marginal | Low | Insulation fault in lead area is considered the most likely failure scenario. Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellarator core. 3 techs/1 engr for duration of active repair )1-2 months). | 50 | 150 | 1 | 2 | 0 | 0 | 0 | 0 | 0
15 | 7503 | Insulation on TF/PF coil fails during initial cooldown and testing requiring dismantling stellarator core | Ist of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . Ring | NC | Crisis | Low | High impact-low probability event not covered by contingency | [6 empty] | 0 | 0 | 0
16 | 7503 | Insulation on modular coil fails during initial cooldown and testing requiring in situ repair | C1 tested at full current at cryogenic temeprature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. In addition, routine field tests will be performed on each assembly station to ensure that the electrical | VU | Marginal | Low | Insulation fault in lead area is considered the most likely failure scenario. Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellarator core. 3 techs/1 engr for duration of active repair )1-2 months). | 50 | 150 | 1 | 2 | 0 | 0 | 0 | 0 | 0
17 | 7503 | Insulation on modular coil fails during initial cooldown and testing requiring stellarator core disassembly | C1 tested at full current at cryogenic temeprature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. In addition, routine field tests will be performed on each assembly station to ensure that the electrical | NC | Crisis | Low | High impact-low probability event not covered by contingency | [6 empty] | 0 | 0 | 0
18 | 7503 | Unanticipated problems with cryostat penetrations (icing, excessive condensation). May require warming up the stellarator core to effect repair with consequent impacts to critical path activities. | Rapid repair materials will be on hand. | U | Marginal | Low | Nominally repaired with a 4-man crew in 1 week with 3 weeks for warmup/cooldown (if required) | 15 | 30 | 0.25 | 1 | 0 | 0 | 0 | 0 | 0
19 |  | Loss or prolonged unavailability of certain key personnel from the project could substantially impact the schedule. | See mitigation plans for individuals listed below. | [10 empty] | #N/A
| 1901 | Mike Cole (ORNL) | Brad Nelson is been budgeted (15%) on the project. Should Cole become unavailable, Nelson would step in and handle Cole's responsibilties until a suitable longer term solution was implemented. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5 |  | 0 | 0 | 0 | 0
| 8203 | Tom Brown (PPPL) | Bob Ellis has been budgeted along with a designer to provide support to Tom Brown in Design Integration during peak demands and pick up the slack for Brown if he became unavailable. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5 |  | 0 | 0 | 0 | 0
| 8204 | Art Brooks (PPPL) | An EA/EM engineer has been budgeted to provide support to Brooks in Systems Analysis and Technical Assurance during peak demands and pick up the slack for Brooks should he became unavailable. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5 |  | 0 | 0 | 0 | 0
| 8205 | Bob Ellis (PPPL) | An EA/EM engineer has been budgeted to provide support to Ellis in Dimensional Control Coordination during peak demands and pick up the slack for Ellis should he become unavailable. | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5 |  | 0 | 0 | 0 | 0
| 1802 7401 | Mike Viola (PPPL) Erik Perry (PPPL) | Viola and Perry will be cross-trained such that each could do the other's job | VU | Marginal | Low | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5 |  | 0 | 0 | 0 | 0
20 | 1803 7503 | Assembly sled for final assembly is not adequately stiff or does not provide repeatable motion | Functionality of sled will be determined first with concrete blocks and later with first FP. Ample time to make design modifications between arrival of the first and third FPs. | U | Negligible | Low | Nominal cost impact is 1 man-month of engineering design and up to half the fabrication cost of the sled | 25 | 75 | 0 | 0 | 0 |  | 0 | 0 | 0
21 | 7503 | TC floor is not adequately rigid for present metrology plan | Copper sheet and spongy surface removed from TC floor. Fiducials will be placed. Concrete blocks will be placed to see if floor is adequately stiff. | VU | Marginal | Low | Nominal cost impact is 2 man-months of engineering design and $50-150K for local reinforcement of building structures | 50 | 200 | 0 | 0 | 0 |  | 0 | 0 | 0
22 | 1421 7503 | Modular coils are shorted across toroidal break between field periods causing problematic field errors | Need very low impedence, multiple shorts to get into trouble | NC | [9 empty] | 0 | 0 | 0
23 | 8101 | GPP projects not completed in time to support project needs | The crane and the HVAC systems are the main GPP projects that would need to be completed. The GPP projects have strong Lab and DOE oversight. Ample float is provided in the schedule so project delays due to GPP delays are not considered credible (P<1%). | NC | [9 empty] | 0 | 0 | 0
24 | 8501 | Coils are hooked up with incorrect polarity | Test during ISTP and fix | U | Negligible | Low | Covered in estimate uncertainty with present mitigation plan | [6 empty] | 0 | 0 | 0
25 | 8101 | Escalation of Stainless Sheet and Inconel higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Marginal | Moderate | See separate sheet - assume 3% to 20% higher per year escalation rate | 37.0011 | 266.1648 | 0 | 0 | 0 |  | 0 | 0 | 0
26 | 8101 | Escalation of Copper higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Negligible | Low | See separate sheet - assume 5% to 20% higher per year escalation rate | 11 | 81 | 0 | 0 | 0 |  | 0 | 0 | 0
27 | 8101 | Labor rates may be significantly lower/higher than projected |  | L | Marginal | Moderate | Escalation rate may be anywhere in the range of 2-5% instead of the nominal rate of 3.4% for labor. Schedule impact is due to annual funding constraints. | -500 | 500 | -0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
28 | 1810 1815 7503 | Metrology equipment and general purpose tooling/ lifting equipment (e.g.cranes) not available to support the schedule | Maintenance contract mitigates impact of metrology equipment. Additional $200K budgeted for a 3rd laser tracker and/or spare metrology equipment. Should result in improved efficiency as well as failure mitigation. | U | Marginal | Low | Up to 2 week impact on FPA and critical path. FPA cost impact assumed to be $300k/mo. | 0 | 150 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
29 | 1352 | No suitable PF coil vendor submits bid. PF coils need to be built in-house. | PF is last major, special procurement. Sources sought received two qualified respondants. Capability to build at PPPL (and overseas) exists if needed. | U | Marginal | Low | Cost impact estimated to be up to $300k (1/3 of fabrication costs) for potentially higher labor rates at PPPL. No impact on critical path expected. | 0 | 300 | 0 | 0 | 0 |  | 0 | 0 | 0
30 | 8101 | Funding profile may not match assumptions which in turn could impact cost and schedule |  | U | Significant | Moderate | Cost impact derived from stretchout | 0 | 0 | -2 | 2 |  | 0 | 0 | 0 | 0
31 | 8101 | Overhead rates may change signficiantly which in turn could impact cost and schedule |  | U | Significant | Moderate | Overhead rates are determined by institutional funding and are outside the project's control. -2%/+0% on the rates are representative of variation in three-year institutional averages over the past 10 years. | -900 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0
a VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
[15 empty] | 0 | 0

## Likelihood
| Probability of Occurrence |  | Criteria
| Qualitative | Quantitative
| Non-credible | <0.01 | Extremely unlikely occur anytime in the project life cycle, or the probability of the occurrence judged to be less than 1%.
VU | Very Unlikely | >0.01 but <0.1 | Very unlikely to occur anytime in the project life cycle, or the probability of the occurrence is judged to be less than 10%.
U | Unlikely | >0.1 but <0.4 | Unlikely to occur in the project life cycle , or the probability of the occurrence is judged to be greater than 10% but less than 40%.
L | Likely | >0.4 but <0.8 | Will likely occur sometime during the project life cycle of the project or its facilities, or the probability of the occurrence is judged to be greater than 40% but less than 80%.
VL | Very Likely | >0.8 | Very likely to occur sometime during the project life cycle or the probability of occurrence is judged to be 80% or greater.
* P = Probability of Occurrence
Concept Explanation
For each identified risk, a Probability of Occurrence is defined using the above criteria.
Also for each risk, the consequential impacts are estimated -- as either an absolute value or a range with most likely, low and high values defined
Both cost impacts and schedule impacts should be estimated.
For schedule impact, the value (or range) should reflect impact to the project completion -- that is the impact to the project critical path
Separate models will then be constructed to determine overall cost and schedule probability profiles (using Monte Carlo simulation)
Each risk will represent a variable in the model. The Pr of Occurrence will use the values shown on the right above and
the ranges for cost and schedule impacts.
L | 0 | 0
NC | 0 | 0
U | 0 | 0
VL | 0 | 0
VU | 0 | 0

## Standard Estimate Uncertainty
Estimate Uncertainty Matrix
Design Complexity
| Design Maturity | Low |  | Medium |  | High
| Low | -15% | 25% | -20% | 40% | -30% | 60%
| Medium | -10% | 15% | -15% | 25% | -20% | 40%
| High | -5% | 10% | -10% | 15% | -15% | 25%
|  | Low | High
| HH | -15% | 25%
| HL | -5% | 10%
| HM | -10% | 15%
| LH | -30% | 60%
| LL | -15% | 25%
| LM | -20% | 40%
| MH | -20% | 40%
| ML | -10% | 15%
| MM | -15% | 25%
Definitions
Design Maturity
| High | Final design available. All design features/requirements well known.
No further design development or evolution expected that will impact estimate
| Medium | Preliminary design available. Some additional design evolution likely
Further developments can be somewhat expected/anticipated and reflected in estimate
| Low | No better than conceptual design basis currently available. Design details, procedures,
etc. still need much development and evolution of requirements beyond estimate basis is likely and expected
Design Complexity
| Low | Work is fairly well understood -- either standard construction or repetition of activities performed in past
Little likelihood of estimate not being well understood and requirements not being well defined
| Medium | More complex work requirements that have potential to impact cost and schedule estimates
Limited experience performing similar tasks, so ability to estimate accurately is somewhat suspect
| High | Extremely challenging tasks and/or requirements. Unique or first-of-a-kind assembly or work tasks
No good basis for estimating work exists so there is a high degree of estimate uncertainty
Basis for Estimate Uncertainties
Per AACEI Recommended Practice 18R-97, Cost Estimate Classification System
As Applied in Engineering, Procurement and Construction for the Process Industry
| Estimate Class | Level of Definition |  | Accuracy Range |  |  |  | NCSX Definition | Range Used
| 5 | 0 - 2% |  | -20 to -50% - +30 to +100% |  |  |  | L maturity; H complexity | -30/+60%
| 4 | 1 - 15% |  | -15 to -30% - +20 to +50% |  |  |  | MH and LM | -20/+40%
| 3 | 10 - 40% |  | -10 to -20% - +10 to +30% |  |  |  | MM and LL | -15/+25%
| 2 | 30 - 70% |  | -5 to -15% - +5 to +20% |  |  |  | ML and HM | -10/+15%
| 1 | 50 - 100% |  | -3 to -10% - +3 to +15% |  |  |  | H maturity; L complexity | -5/+10%

## Misc Inputs
Standing army calculation
WBS | JOB | Description | Cost/yr | Cost/mo.
19 | 1901 | Stellarator core management | 185 | 15.4167
81 | 8101 | PPPL Management | 1000 | 83.3333
81 | 8102 | ORNL Management | 158 | 13.1667
82 | 8202 | Engineering mgt | 550 | 45.8333
82 | 8203 | Design Integration | 98 | 8.1667
82 | 8204 | Systems Analysis | 0 | 0
82 | 8205 | Dimensional control | 0 | 0
82 | 8215 | Plant Design | 0 | 0
89 | 8998 | Allocations | 430 | 35.8333
201.75
Second Shift oversight,support, cost dif
Crane support, fixture setup, misc support |  |  | 1.2 fte | 16.6
Field Supervision |  |  | 1.0 fte | 24.69
Metrology crews (task dependent) |  |  | n/a | 0
Metrology engineer |  |  | .5 fte | 16
Shift differntial (@ 5fte crew size) |  |  |  | 6.93
64.22

## Escalation Risk
Special Materials
Delivery cost estimate (includes raw material cost, and vendor fabrication) |  |  |  | as spent $K
|  |  |  | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | TOTAL
C - copper
| 1352 - Job: 1352 - PF Coil Procurement-KALISH | 141-038.1 | PF Conductor Delivery |  | 95.3 |  |  |  | 95.3
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 184-037 | External Trim Coil Procurement |  |  | 33.7 |  |  | 33.7
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 132-038 | Deliver Lead hardware and cables |  |  | 64.7 | 17.8 |  | 82.5
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-4 | Grounding-Procure |  |  | 10 |  |  | 10
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-265 | Fabricate bus components |  |  | 45 |  |  | 45
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-275 | Power cabling & Installation |  |  | 140 |  |  | 140
|  |  |  | 0 | 95.3 | 293.4 | 17.8 | 0 | 406.5
S - Stainless Steel/Inconnel
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124-130 | VV NB port cover Fabrication |  |  | 58.5 |  |  | 58.5
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | INTRF-001 | PPPL buy SS plate for weld trials | 30 |  |  |  |  | 30
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 77.6 |  |  |  |  | 77.6
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3060 | Deliver Shim Stock | 57.1 | 3.5 |  |  |  | 60.6
| 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 161-036.9 | Deliver base support materials |  | 30 |  |  |  | 30
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-037 | Fabricate TF/MCWF mounting Components |  | 371.2 | 88.4 |  |  | 459.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-038 | Fabricate PF Mounting components |  |  | 480.1 | 108.7 |  | 588.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-039 | Fabricate Final TF Assy components Components |  |  | 83.6 |  |  | 83.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-040 | Fabricate Machine/base support interface |  |  | 84.8 |  |  | 84.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-053 | Deliver Inconnel hardware |  | 97.5 |  |  |  | 97.5
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-057 | Deliver Belleville Washers |  | 13.9 |  |  |  | 13.9
|  |  |  | 164.7 | 516.1 | 795.4 | 108.7 | 0 | 1584.9
Estimate Raw material cost (delivery cost estimate x 50%)
| C - copper - base estimate (assumes 2.5%/year escalation) |  |  | 0 | 47.65 | 146.7 | 8.9 | 0 | 203.25
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 1.4295 | 8.934 | 0.82527 | 0 | 11.1888
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 9.53 | 64.548 | 6.4792 | 0 | 80.5572
| S - Stainless Steel/Inconnel (assumes 2.5%/year escalation) |  |  | 82.35 | 258.05 | 397.7 | 54.35 | 0 | 792.45
| Additional SS/Inconel Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 7.7415 | 24.2199 | 5.0397 | 0 | 37.0011
| Additional SS/Inconel Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 51.61 | 174.988 | 39.5668 | 0 | 266.1648